{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":524,"n_cols":25,"rows_kept":524,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["ST. LUCIE COUNTY   - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["ST. LUCIE COUNTY   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"1999-08-05",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"ST. LUCIE COUNTY","Date: ==>","OCTOBER 24,2001",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[1,"Expand Media, Admin & Food Svc. , Skills lab, & Art classroom","Lawnwood Elem.",{"$nulls":4},1500000,1500000]
[2,"Replace Admin/Media Bldg","Dan McCarty Middle",{"$nulls":4},4000000,4000000]
[3,"Roofing Repairs","District Wide",125977,{"$nulls":4},125977]
[4,"Roofing Repairs","Ft. Pierce Magnet, White City, Forest Grove, Mariposa, Dale Cassens & ESE, Bayshore",null,350000,null,null,null,350000]
[5,"Roofing Repairs","Southport, North Compound, Preston Court, PSL High",null,null,360000,null,null,360000]
[6,"Roofing Repairs","St. Lucie Elementary, Weatherbee Elementary",null,null,null,370000,null,370000]
[7,"Roofing Repairs","Pt St Lucie Elem, White City Elem,FP Central",{"$nulls":4},380000,380000]
[8,"Flooring / Carpet","Lakewood Park Elem.",110000,{"$nulls":4},110000]
[9,"Flooring / Carpet","Port St. Lucie High, Manatee, Mariposa",null,300000,null,null,null,300000]
[10,"Flooring / Carpet","Anglewood, Garden City, Floresta",null,null,300000,null,null,300000]
[11,"Flooring / Carpet","Floresta, Southport, Forest Grove",null,null,null,300000,null,300000]
[12,"Flooring / Carpet","Forest Grove, Port St. Lucie Elem",{"$nulls":4},300000,300000]
[13,"HVAC Repairs","Southern Oaks Middle",200000,{"$nulls":4},200000]
[14,"HVAC Repairs","Garden City Elem. ",null,2000000,null,null,null,2000000]
[15,"HVAC Chiller Replacement","Dan McCarty Middle",100000,{"$nulls":4},100000]
[16,"HVAC Repairs/Controls/Air Handlers","Village Green, Windmill Point, Flo Elem, Morningside, Lakewood Park",null,null,1300000,null,null,1300000]
[17,"HVAC Repairs/Controls","Parkway, Dale Cassens, Means Court Annex",null,null,null,1000000,null,1000000]
[18,"HVAC Repairs/Controls","Mariposa",null,null,null,500000,null,500000]
[19,"HVAC Repairs/Controls","Manatee Elem, PSL High",{"$nulls":4},1000000,1000000]
[20,"HVAC Repairs","District Wide",879935,600000,600000,600000,600000,3279935]
[21,"Painting","Dale Cassens & ESE Office, Garden City Elem",60000,{"$nulls":4},60000]
[22,"Painting","St Lucie, Weatherbee, Dan McCarty, HRD, FP Central, PSL High",null,267100,null,null,null,267100]
[23,"Painting","St Lucie West Centennial HS, St Lucie West Middle, Savanna Ridge Elem, Lincoln Park Academy",null,null,191000,null,null,191000]
[24,"Painting","Forest Grove, Southport Middle, Floresta, Southern Oaks",null,null,null,170500,null,170500]
[25,"Painting","PSL Elem, Windmill Pt, Village Green, Morningside, Parkway, Means Ct, Preston Ct., Anglewood",{"$nulls":4},117000,117000]
[26,"Pave parking & Repaving","North Bus Compound/County Office ",null,600000,null,null,null,600000]
[27,"HVAC - Small Repairs","District Wide",80000,100000,100000,100000,100000,480000]
[28,"Fire Alarms / Security Systems","District wide",210000,200000,200000,200000,200000,1010000]
[29,"Life Safety","District wide",150000,300000,300000,300000,300000,1350000]
[30,"Relocate Portables","Various Locations Districtwide",106065,185000,185000,75000,75000,626065]
[31,"Re-Varnishing - Gym floors","Gym Floors at Middle & High Schools",82000,80000,80000,80000,85000,407000]
[32,"Basketball Court resurfacing","Various Locations Districtwide",null,80000,80000,80000,80000,320000]
[33,"Replace Doors & hardware","Various Locations Districtwide",10000,25000,25000,25000,25000,110000]
[34,"ADA upgrades","Various Locations Districtwide",27696,750000,750000,750000,800000,3077696]
[35,"Wetlands Monitoring","District Wide",20000,20000,20000,20000,20000,100000]
[36,"Stormwater Management","District Wide",170000,170000,170000,170000,170000,850000]
[37,"Elevator Servicing","Various Locations Districtwide",7200,{"$nulls":4},7200]
[38,"Portables Roof Repair","Various Locations Districtwide",20000,{"$nulls":4},20000]
[39,"Water Heater Replacement","Various Locations Districtwide",9000,{"$nulls":4},9000]
[40,"Water Coolers Replacement","Various Locations Districtwide",22000,{"$nulls":4},22000]
[41,"IAQ Remediation Project and Bard Units","District Wide",225000,{"$nulls":4},225000]
[42,"Replace\\Renovate buildings 1,3,5,6,7,11,12,13,18,19,20,24 & 25","Lincoln Park Academy",{"$nulls":4},19000000,19000000]
[43,"Replace\\Renovate bldgs 1 thru 20","Ft. Pierce Central High",{"$nulls":4},22000000,22000000]
[44,"Replace\\Renovate buildings 1-7","Ft. Pierce Westwood High",{"$nulls":4},22000000,22000000]
[45,"Correct Drainage Problems","Parkway",null,200000,null,null,null,200000]
[46,"Correct Drainage Problems","Morningside Elem.",null,200000,null,null,null,200000]
[47,"Correct Drainage Problems","Anglewood Center",null,200000,null,null,null,200000]
[48,"Correct Drainage Problems","Woodlands",null,null,200000,null,null,200000]
[49,"Correct Drainage Problems","Lakewood Park Elem.",null,null,200000,null,null,200000]
[50,"Correct Drainage Problems","Floresta Elem. ",null,null,200000,null,null,200000]
[51,"Covered bus drop off & pick up","Port St. Lucie High",null,null,null,200000,null,200000]
[52,"Covered bus drop off & pick up","Manatee Elem.",null,null,null,200000,null,200000]
[53,"Covered bus drop off & pick up","Forrest Grove Middle ",{"$nulls":4},200000,200000]
[54,"Cafeteria-Food Service","Lawnwood Elem.",null,null,400000,null,null,400000]
[55,"Expand ESE suite. Remodel 8 - intermediate classrooms.","Garden City Elem. ",null,null,null,460000,null,460000]
[56,"Add 1-Music, 1-Art, 2-skill Dev Labs","Port St. Lucie Elem.",{"$nulls":4},778189,778189]
[57,"Add 1-Art, 2-Skill Development Labs,  5-Resource Rooms","Lakewood Park Elem.",{"$nulls":4},729073,729073]
[58,"Acquistion of Sears Bldg","District Offices",1700000,{"$nulls":4},1700000]
[59,"Renovation/Remodeling of Sears Bldg","District Offices",5500000,{"$nulls":4},5500000]
[60,"Expand Food Service Area","Dale Cassens ",{"$nulls":4},395000,395000]
[61,"Add Art Classroom, two skills development labs","Floresta Elementary",{"$nulls":4},443039,443039]
[62,"Convert Building 03 Rooms 352A through 352D to PE Multipurpose","Forest Grove Middle School",{"$nulls":4},175000,175000]
[63,"Outdoor Basketball Court","Garden City Elem. ",null,null,null,18000,null,18000]
[64,"Track Repairs & Repairs to Ticket Booths","Lawnwood Stadium",{"$nulls":4},55000,55000]
[65,"Repairs to Restrooms","Northport Middle School",null,91118,null,null,null,91118]
[66,"Add Restroom Facilities near the Stadium","Pt. Lucie High School",{"$nulls":4},350000,350000]
[67,"Remodel/Renovate West Half","Ft. Pierce Magnet",{"$nulls":4},7000000,7000000]
[68,"HVAC Renovations/EM Controls","Lakewood Park",null,650000,null,null,null,650000]
[69,"HVAC Renovations/EM Controls","Floresta, Morningside, Windmill Point, Village Green, Manatee, Mariposa, Parkway, Garden City, St. Lucie Elem, Dale Cassens",{"$nulls":4},6500000,6500000]
[70,"Storm Water Management","Port St. Lucie Elem, Northport",{"$nulls":4},400000,400000]
[71,"Add Culinary Arts Dining Room","Pt. Lucie High School",{"$nulls":4},204000,204000]
[72,"Classroom Remodeling to provide additional Student Stations","SLW Centennial High",null,42400,null,null,null,42400]
[73,"Field House w/restrooms, Concession, & Storage","SLW Centennial High",{"$nulls":4},300000,300000]
[74,"New Classroom wing","Northport Middle School",{"$nulls":4},5000000,5000000]
[75,"New High School","To be determined",{"$nulls":4},40200000,40200000]
[76,"New Middle School","To be determined",{"$nulls":4},20750000,20750000]
[77,"New Elementary School","To be determined",{"$nulls":4},12800000,12800000]
[]
["1.","ST. LUCIE COUNTY Total",null,9814873,7410618,5661000,5618500,169031301,197536292]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New High School",{"$nulls":5},40200000,40200000]
[null,"Additional Middle School Space",{"$nulls":5},20750000,20750000]
[null,"New Elementary School",{"$nulls":5},12800000,12800000]
[{"$nulls":8},0]
["2 .","ST. LUCIE COUNTY Total",null,0,0,0,0,73750000,73750000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[1,"White City Elem.",579,579,634,1.0949913644214162,0,643,1.1105354058721935]
[2,"Fairlawn Elem.",915,915,609,0.6655737704918033,0,648,0.7081967213114754]
[3,"Ft. Pierce Magnet School",505,505,328,0.6495049504950495,0,329,0.6514851485148515]
[4,"Lawnwood Elem.",1027,1027,731,0.7117818889970788,0,692,0.6738072054527751]
[5,"St. Lucie Elem.",986,986,660,0.6693711967545639,0,665,0.6744421906693712]
[6,"Dan McCarty Middle",2007,1806,977,0.5409745293466224,0,1034,0.5725359911406424]
[7,"F. K. Sweet Elem.",959,959,600,0.6256517205422315,0,653,0.6809176225234619]
[8,"Garden City Elem.",1379,1431,528,0.3689727463312369,0,611,0.42697414395527605]
[10,"C.A. Moore Elem.",945,945,549,0.580952380952381,0,662,0.7005291005291006]
[11,"Lincoln Park Academy",2642,2377,1821,0.7660917122423223,0,1860,0.7824989482541018]
[12,"Ft. Pierce Central",2661,2527,1576,0.6236644242184408,0,1934,0.7653343886030867]
[13,"Ft. Pierce Westwood",2445,2322,1399,0.6024978466838932,0,1520,0.6546080964685616]
[14,"Anglewood Center",203,203,42,0.20689655172413793,0,20,0.09852216748768473]
[15,"Woodlands Academy",330,330,98,0.296969696969697,0,98,0.296969696969697]
[16,"Port St. Lucie Elem.",928,928,868,0.9353448275862069,0,876,0.9439655172413793]
[17,"Morningside Elem.",842,842,663,0.7874109263657957,0,691,0.8206650831353919]
[18,"Lakewood Park Elem.",902,902,715,0.7926829268292683,0,706,0.7827050997782705]
[19,"Floresta Elem.",772,772,726,0.9404145077720207,0,759,0.9831606217616581]
[20,"Bayshore Elem.",764,764,790,1.0340314136125655,0,796,1.0418848167539267]
[21,"Northport Middle",1584,1425,968,0.6792982456140351,0,1085,0.7614035087719299]
[22,"Windmill Point Elem.",790,790,721,0.9126582278481012,0,769,0.9734177215189873]
[23,"Village Green Elem.",760,760,822,1.081578947368421,0,822,1.081578947368421]
[24,"Port St. Lucie High",2653,2520,1750,0.6944444444444444,0,1998,0.7928571428571428]
[25,"Parkway Elem.",858,858,593,0.6911421911421911,0,643,0.7494172494172494]
[26,"Dale Cassens ESE Center",218,218,121,0.555045871559633,0,106,0.48623853211009177]
[27,"Southport Middle",1395,1255,1176,0.9370517928286852,0,1092,0.8701195219123506]
[28,"Mariposa Elem.",823,823,706,0.8578371810449574,0,748,0.9088699878493317]
[29,"Manatee Elem.",870,870,807,0.9275862068965517,0,822,0.9448275862068966]
[30,"Forest Grove Middle",1876,1688,1169,0.6925355450236966,0,1196,0.7085308056872038]
[30,"Agritech Farm",78,78,0,0,0,0,0]
[32,"Rivers Edge Elem.",943,943,814,0.8632025450689289,0,822,0.8716861081654295]
[33,"Southern Oaks Middle",1440,1296,1035,0.7986111111111112,0,1088,0.8395061728395061]
[34,"Weatherbee Elem.",1003,1003,778,0.7756729810568295,0,822,0.8195413758723828]
[35,"St. Lucie West Cent. High",2141,2033,1568,0.7712739793408756,0,1934,0.9513034923757994]
[36,"St. Lucie West Middle",1458,1312,914,0.6966463414634146,0,966,0.7362804878048781]
[37,"Savanna Ridge Elem.",1003,1003,594,0.5922233300099701,0,565,0.5633100697906281]
["2a.","ST. LUCIE COUNTY Total",41684,39995,28850,0.72,0,29557,0.74]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"Yet to be determined"]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[1,"White City Elem.",0,"-",0,0,2,-2,0]
[2,"Fairlawn Elem.",0,"-",0,0,0,0,0]
[3,"Ft. Pierce Magnet School",0,"-",0,0,0,0,0]
[4,"Lawnwood Elem.",7,"4SLCSB/2FED",177,0,7,0,92]
[5,"St. Lucie Elem.",0,"-",0,0,0,0,0]
[6,"Dan McCarty Middle",12,"2 Lease/12SLCSB",291,0,0,12,42]
[7,"F. K. Sweet Elem.",0,"-",0,0,0,0,0]
[8,"Garden City Elem.",0,"-",0,0,0,0,0]
[9,"C.A. Moore Elem.",0,"-",0,0,0,0,0]
[10,"Lincoln Park Academy",3,"SLCSB",88,0,3,0,21]
[11,"Ft. Pierce Central",31,"23SLCSB/2FED",930,0,31,0,383]
[12,"Ft. Pierce Westwood",17,"15SLCSB/FED2",523,0,17,0,220]
[13,"Anglewood Center",2,"1SLCSB/1FED",56,0,2,0,27]
[14,"Woodlands Academy",13,"11SLCSB/2FED",286,0,13,0,152]
[15,"Port St. Lucie Elem.",7,"4SLCSB/4FED",174,0,7,0,101]
[16,"Morningside Elem.",5,"SLCSB",96,0,5,0,44]
[17,"Lakewood Park Elem.",4,"FED",156,0,4,0,95]
[18,"Floresta Elem.",1,"SLCSB",26,0,1,0,4]
[19,"Bayshore Elem.",1,"SLCSB",26,0,1,0,31]
[20,"Northport Middle",12,"SLCSB",308,0,12,0,108]
[21,"Windmill Point Elem.",3,"SLCSB",52,0,2,1,11]
[22,"Village Green Elem.",1,"FED",26,0,1,0,20]
[23,"Port St. Lucie High",26,"26SLCSB/1FED",810,0,27,-1,262]
[24,"Parkway Elem.",6,"SLCSB",120,0,5,1,68]
[25,"Dale Cassens ESE Center",5,"SLCSB",32,0,4,1,57]
[26,"Southport Middle",3,"SLCSB",84,0,3,0,16]
[27,"Mariposa Elem.",0,"-",0,0,0,0,0]
[28,"Manatee Elem.",2,"SLCSB",52,0,2,0,14]
[29,"Forest Grove Middle",15,"SLCSB",420,0,15,0,97]
[30,"Agritech Farm",3,"SLCSB",78,0,3,0,12]
[31,"St. Lucie Superintendent Ofc.",8,"SLCSB",0,0,0,8,36]
[32,"Preston Court Annex",2,"FED",0,0,0,2,42]
[33,"Rivers Edge Elem.",1,"SLCSB",26,0,1,0,4]
[34,"Southern Oaks Middle",0,"SLCSB",0,0,1,0,10]
[35,"Weatherbee Elem.",0,"-",0,0,0,0,0]
[36,"St. Lucie West Cent. High",0,"-",0,0,0,0,0]
[37,"St. Lucie West Middle",0,"-",0,0,0,0,0]
[38,"Savanna Ridge Elem.",0,"-",0,0,0,0,0]
["2c1.","ST. LUCIE COUNTY Total",190,null,4837,0,169,22,"Avg Age 10.36"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02","2002-03","2003-04","2004-05","2005-06","5 YEAR TOTAL"]
[null,"None.",0,0,0,0,0,0,0]
["2c2.","ST. LUCIE COUNTY Total",0,0,0,0,0,0,0]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,null,0]
["2c3.","ST. LUCIE COUNTY Total",0,null,0,0,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"No Charter Schools are projected"]
["2c4.","ST. LUCIE COUNTY Total",0,null,null,0,0,0,0]
[]
[null,"Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[1,"White City Elem.",25,579,634,25.36,643,0,25.72]
[2,"Fairlawn Elem.",34,915,609,17.91,648,0,19.06]
[3,"Ft. Pierce Magnet School",21,505,328,15.62,329,0,15.67]
[4,"Lawnwood Elem.",36,1027,731,20.31,692,0,19.22]
[5,"St. Lucie Elem.",39,986,660,16.92,665,0,17.05]
[6,"Dan McCarty Middle",63,1806,977,15.51,1034,0,16.41]
[7,"F. K. Sweet Elem.",37,959,600,16.22,653,0,17.65]
[8,"Garden City Elem.",56,1431,528,9.43,611,0,10.91]
[9,"C.A. Moore Elem.",34,945,549,16.15,662,0,19.47]
[10,"Lincoln Park Academy",98,2377,1821,18.58,1860,0,18.98]
[11,"Ft. Pierce Central",97,2527,1576,16.25,1934,0,19.94]
[12,"Ft. Pierce Westwood",86,2322,1399,16.27,1520,0,17.67]
[13,"Anglewood Center",8,203,42,5.25,20,0,2.5]
[14,"Woodlands Academy",11,259,98,8.91,98,0,8.91]
[15,"Port St. Lucie Elem.",36,928,868,24.11,876,0,24.33]
[16,"Morningside Elem.",32,842,663,20.72,691,0,21.59]
[17,"Lakewood Park Elem.",34,902,715,21.03,706,0,20.76]
[18,"Floresta Elem.",29,772,726,25.03,759,0,26.17]
[19,"Bayshore Elem.",29,764,790,27.24,796,0,27.45]
[20,"Northport Middle",50,1425,968,19.36,1085,0,21.7]
[21,"Windmill Point Elem.",30,790,721,24.03,769,0,25.63]
[22,"Village Green Elem.",29,760,822,28.34,822,0,28.34]
[23,"Port St. Lucie High",99,2520,1750,17.68,1998,0,20.18]
[24,"Parkway Elem.",33,858,593,17.97,643,0,19.48]
[25,"Dale Cassens Center",44,218,121,"-",106,null,"-"]
[26,"Southport Middle",39,1255,1176,30.15,1092,0,28]
[27,"Mariposa Elem.",31,823,706,22.77,748,0,24.13]
[28,"Manatee Elem.",33,870,807,24.45,822,0,24.91]
[29,"Forrest Grove Middle",60,1688,1169,19.48,1196,0,19.93]
[30,"Agritech Farm",0,0,0,0,0,0,0]
[31,"Rivers Edge Elem.",36,943,814,22.61,822,0,22.83]
[32,"Southern Oaks Middle",47,1296,1035,22.02,1088,0,23.15]
[33,"Weatherbee Elem.",37,1003,778,21.03,822,0,22.22]
[34,"St. Lucie West Cent. High",86,2033,1568,18.23,1934,0,22.49]
[35,"St. Lucie West Middle",48,1312,914,19.04,966,0,20.13]
[36,"Savanna Ridge Elem.",37,1003,594,16.05,565,0,15.27]
["2e.","ST. LUCIE COUNTY Total",1544,39846,28850,"District Avg 19",30675,0,"District Avg 20"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02","2002-03","2003-04","2004-05","2005-06","5 YEAR AVERAGE"]
[1,"White City Elem.",null,50,50,50,50,50,50]
[2,"Fairlawn Elem.",null,0,0,0,0,0,0]
[3,"Ft. Pierce Magnet School",null,0,0,0,0,0,0]
[4,"Lawnwood Elem.",null,150,150,150,150,150,150]
[5,"St. Lucie Elem.",null,0,0,0,0,0,0,null,0]
[6,"Dan McCarty Middle",null,0,0,0,0,0,0]
[7,"F. K. Sweet Elem.",null,0,0,0,0,0,0]
[8,"Garden City Elem.",null,0,0,0,0,0,0]
[9,"C.A. Moore Elem.",null,0,0,0,0,0,0]
[10,"Lincoln Park Academy",null,88,88,88,88,88,88]
[11,"Ft. Pierce Central",null,930,930,930,930,930,930]
[12,"Ft. Pierce Westwood",null,390,390,390,390,390,390]
[13,"Anglewood Center",null,56,56,56,56,56,56]
[14,"Woodlands Academy",null,220,220,220,220,220,220]
[15,"Port St. Lucie Elem.",null,150,150,150,150,150,150]
[16,"Morningside Elem.",null,77,77,77,77,77,77]
[17,"Lakewood Park Elem.",null,130,130,130,130,130,130]
[18,"Floresta Elem.",null,0,0,0,0,0,0]
[19,"Bayshore Elem.",null,26,26,26,26,26,26]
[20,"Northport Middle",null,283,283,283,283,283,283]
[21,"Windmill Point Elem.",null,26,26,26,26,26,26]
[22,"Village Green Elem.",null,26,26,26,26,26,26]
[23,"Port St. Lucie High",null,630,630,630,630,630,630]
[24,"Parkway Elem.",null,144,144,144,144,144,144]
[25,"Dale Cassens ESE Center",null,32,32,32,32,32,32]
[26,"Southport Middle",null,84,84,84,84,84,84]
[27,"Mariposa Elem.",null,0,0,0,0,0,0]
[28,"Manatee Elem.",null,52,52,52,52,52,52]
[29,"Forest Grove Middle",null,392,392,392,392,392,392]
[30,"Agritech Alternative School",null,78,78,78,78,78,78]
[31,"Rivers Edge Elem.",null,0,0,0,0,0,0]
[32,"Southern Oaks Middle",null,0,0,0,0,0,0]
[33,"Weatherbee Elem.",null,26,26,26,26,26,26]
[34,"St. Lucie West Cent. High",null,0,0,0,0,0,0]
[35,"St. Lucie West Middle",null,0,0,0,0,0,0]
[36,"Savanna Ridge Elem.",null,0,0,0,0,0,0]
["2f.","ST. LUCIE COUNTY Total students in relocatables by year",null,4040,4040,4040,4040,4040,4040]
[null,"Total number of CO-FTE students projected by year",null,28923,29182,29331,29486,29557,29295.8]
[null,"Percent in relocatables by year",null,0.14,0.14,0.14,0.14,0.14,0.14]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
["3 .","The projected cost for each project identified in the tentative district facilities work program."]
[null,"The projected cost for each project identified in the tentative district facilities work program."]
[]
[]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 "]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":8},"State Average","State Average","State Average","State Average","State Average","State Average"]
[{"$nulls":9},"Year",2000,2000,2000,2000,2000,1999]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02","2000 State Avg","2000 State Avg","Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta",1,79,110,156,9213,12712,22844]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,2,86,113,165,9863,13751,18853]
["3a.","ST. LUCIE COUNTY Total 2000-01",null,0,0,0,{"$error":"#DIV/0!"},null,null,3,68,128,222,14900,18106,26448]
[]
["3b.","2002-03 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","2000 State Avg","2000 State Avg","2000 State Avg","1999 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","ST. LUCIE COUNTY Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2003-04 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","ST. LUCIE COUNTY Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2004-05 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","ST. LUCIE COUNTY Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2005-06 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New High School ",3,null,2000,316234,158.12,68,128,0,{"$error":"#DIV/0!"},0,0,0]
[null,"New Middle School",2,null,1200,163865,136.55,86,113,0,{"$error":"#DIV/0!"},0,0,0]
[null,"New Elementary School",1,null,800,107268,134.09,79,110,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#VALUE!"},0,0,0]
["3e","ST. LUCIE COUNTY Total 2005-06",null,0,4000,316234,79.06,null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","ST. LUCIE COUNTY 5-Year Total",null,0,4000,316234,null,null,null,"2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[{"$nulls":9},"GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the",{"$nulls":7},222,0,14900,18106,26448]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc.",{"$nulls":8},0]
[]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,0,0,0,0,0,0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,16493726,16988538,17498194,18023140,18563834,87567432]
[null,"  less amount used to purchase school busses",null,1000000,1200000,1300000,1400000,1500000,6400000]
[null,"  less amount used to purchase other vehicles",null,null,250000,250000,250000,250000,1000000]
[null,"  less amount transferred to operating budget for maintenance/repair",null,3800000,3200000,2900000,2600000,2300000,14800000,0]
[null,"  less amount used for maintenance/repair",{"$nulls":6},0,0]
[null,"  less amount used to purchase capital outlay equipment",null,3052178,3018000,3500000,3500000,3500000,16570178,1]
[null,"  less amount used to correct environmental problems",{"$nulls":6},0,0.07]
[null,"  less amount transferred to operating budget for salaries",{"$nulls":6},0,0.01]
[null,"  less amount used to pay debt service for s.237 loans",{"$nulls":4},0,0,0,0.17]
[null,"  less amount to pay debt service for COP's ",null,8315000,8315000,8315000,8315000,8315000,41575000,0]
[null,"  less other (County Debt Service)",null,151000,151000,151000,151000,151000,755000,0.19]
[null,"  less other (capital lease)",null,175548,176000,176000,176000,176000,879548,0]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,678538,906194,1631140,2371834,5587706,0]
[null,"P E C O New Construction",null,3014873,2972580,2144572,1953921,1994042,12079988,0]
[null,"  less amount used to pay debt service for s.237 loans",null,-500000,-500000,-500000,-500000,-500000,-2500000,0.47]
[null,"C O & D S   Bond Proceeds",{"$nulls":6},0,0.01]
[null,"C O & D S maximum potential bond proceeds",null,100000,100000,100000,100000,100000,500000,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,0.06]
[null,"Proceeds from a s.237 loan",{"$nulls":6},0,0.0638103216273374,0.24]
[null,"Proceeds from local governmental infrastructure sales surtax",{"$nulls":6},0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0]
[null,"Proceeds from Certificates of Participation (COP's)",null,8800000,{"$nulls":4},8800000]
[null,"Less amount used to pay s.237 loan",null,-2291000,{"$nulls":4},-2291000]
[null,"Less amount used for equipment",null,-809000,{"$nulls":4},-809000]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",{"$nulls":6},0]
[null,"Impact fees received",null,1000000,1000000,1000000,1000000,1000000,5000000]
[null,"  less amount used to pay for technology throughout district infrastructure",null,-1000000,-1000000,-1000000,-1000000,-1000000,-5000000]
[null,"Sales Tax Revenue Bond",null,2600000,{"$nulls":4},2600000]
[null,"  less amount used to pay debt service for s.237 loans",null,-1100000,{"$nulls":4},-1100000]
["4.","ST. LUCIE COUNTY Total",null,9814873,3251118,2650766,3185061,3965876,22867694]
[{"$nulls":10},{"$error":"#REF!"}]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected",{"$nulls":8},{"$error":"#REF!"}]
[null,"in paragraph 4 above.",{"$nulls":8},{"$error":"#REF!"}]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06",null,null,{"$error":"#REF!"}]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL",1.0538103216273373,{"$error":"#REF!"}]
[1,"Fire Alarms / Security Systems - District wide",null,210000,200000,200000,200000,200000,1010000]
[2,"Painting Dale Cassens, ESE Office, & Garden City",null,60000,{"$nulls":4},60000]
[3,"HVAC Repairs District Wide",null,879935,600000,600000,600000,600000,3279935]
[4,"Life Safety - District wide",null,150000,300000,300000,300000,300000,1350000]
[5,"Relocate Portables - Various Locations Districtwide",null,106065,{"$nulls":4},106065]
[6,"Re-Varnishing - Gym floors - Gym Floors at Middle & High Schools",null,82000,80000,80000,80000,85000,407000]
[7,"Replace Doors & hardware - Various Locations Districtwide",null,10000,25000,25000,25000,25000,110000]
[8,"HVAC Repairs - Southern Oaks Middle",null,200000,{"$nulls":4},200000]
[9,"HVAC Chiller Replacement - Dan McCarty",null,100000,{"$nulls":4},100000]
[10,"Acquisition of Sears Bldg",null,1700000,{"$nulls":4},1700000]
[11,"Renovation/Remodel Sears Bldg for Admin space",null,5500000,{"$nulls":4},5500000]
[12,"HVAC - Small Repairs-District Wide",null,80000,100000,100000,100000,100000,480000]
[13,"Floor Covering Replacement-Lakewood Park",null,110000,{"$nulls":4},110000]
[14,"Roofing Repairs-District Wide",null,125977,350000,360000,370000,380000,1585977]
[15,"ADA",null,27696,{"$nulls":4},27696]
[16,"Wetlands Monitoring",null,20000,20000,20000,20000,20000,100000]
[17,"Stormwater Management",null,170000,170000,170000,170000,170000,850000]
[18,"Elevator Servicing",null,7200,{"$nulls":4},7200]
[19,"Portables Roof Repair",null,20000,{"$nulls":4},20000]
[20,"Water Heater Replacement",null,9000,{"$nulls":4},9000]
[21,"Water Coolers Replacement",null,22000,{"$nulls":4},22000]
[22,"IAQ Remediation Project and Bard Units",null,225000,{"$nulls":4},225000]
[23,"Relocate Portables - Various Locations Districtwide",null,null,185000,null,null,null,185000]
[24,"Basketball Court resurfacing - Various Locations Districtwide",null,null,80000,null,null,null,80000]
[25,"HVAC Renovations/EM Controls","Lakewood Park",null,650000,null,null,null,650000]
[26,"Correct Drainage Problems - Morningside Elem.",null,null,200000,null,null,null,200000]
[27,"Repairs to Restrooms - Northport Middle School",null,null,91118,null,null,null,91118]
[28,"HVAC Repairs - Village Green, Windmill Point, Floresta, Morningside, Lakewood Park",null,null,null,795766,null,null,795766]
[29,"HVAC Repairs/Controls - Parkway, Dale Cassens, Means Court Annex",{"$nulls":4},1000000,null,1000000]
[30,"HVAC Repairs/Controls -Mariposa",{"$nulls":4},320061,null,320061]
[31,"HVAC Renovations/EM Controls","Floresta, Morningside, Windmill Point, Village Green, Manatee, Mariposa, Parkway, Garden City, St. Lucie Elem, Dale Cassens",{"$nulls":4},2085876,2085876]
[32,"Correct Drainage Problems - Parkway","Anglewood",null,200000,null,null,null,200000]
[{"$nulls":8},0]
["5.","ST. LUCIE COUNTY Total",0,9814873,3251118,2650766,3185061,3965876,22867694]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01","2001-02","2002-03","2003-04","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["6.","ST. LUCIE COUNTY Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[1,"ADA upgrades - Various Locations Districtwide",null,null,750000,750000,750000,800000,3050000]
[2,"Relocate Portables - Various Locations Districtwide",null,null,null,185000,75000,75000,335000]
[3,"Basketball Court resurfacing - Various Locations Districtwide",null,null,null,80000,80000,80000,240000]
[4,"HVAC Repairs/Controls -Mariposa",{"$nulls":4},179939,null,179939]
[5,"HVAC Repairs - Village Green, Windmill Point, Floresta, Morningside, Lakewood Park",null,null,null,504234,null,null,504234]
[6,"HVAC Repairs - Manatee, PSL High",{"$nulls":5},1000000,1000000]
[7,"HVAC Repairs -  Garden City",null,null,2000000,null,null,null,2000000]
[8,"Expand Media, Admin & Food Svc. , Skills lab, & Art classroom - Lawnwood Elem.",{"$nulls":5},1500000,1500000]
[9,"Replace Admin/Media Bldg - Dan McCarty Middle",{"$nulls":5},4000000,4000000]
[10,"Flooring / Carpet - Pt St lucie High, Manatee, Mariposa",null,null,300000,null,null,null,300000]
[11,"Flooring / Carpet - Anglewood, Garden City, Floresta",null,null,null,300000,null,null,300000]
[12,"Flooring / Carpet - Floresta, Southport, Forest Grove",{"$nulls":4},300000,null,300000]
[13,"Flooring / Carpet - Forest Grove, Pt. St. Lucie Elementary",{"$nulls":5},300000,300000]
[14,"Painting - Dan McCarty,St Lucie, Weatherbee, HRD, FP Central, PSL High",null,null,267100,null,null,null,267100]
[15,"Painting - St Lucie West Centennial HS, St Lucie West Middle, Savanna Ridge Elem, Lincoln Park Academy",null,null,null,191000,null,null,191000]
[16,"Painting - Forest Grove, Southport Middle, Floresta, Southern Oaks",{"$nulls":4},170500,null,170500]
[17,"Painting - PSL Elem, Windmill Point, Village Green, Morningside, Parkway, Means Court, Preston Court, Anglewood",{"$nulls":5},117000,117000]
[18,"Pave parking & Repaving - North Bus Compound/County Office ",null,null,600000,null,null,null,600000]
[19,"Replace\\Renovate buildings 1,3,5,6,7,11,12,13,18,19,20,24 & 25 - Lincoln Park Academy",{"$nulls":5},19000000,19000000]
[20,"Replace\\Renovate bldgs 1 thru 20 - Ft. Pierce Central High",{"$nulls":5},22000000,22000000]
[21,"Replace\\Renovate buildings 1-7 - Ft. Pierce Westwood High",{"$nulls":5},22000000,22000000]
[22,"Correct Drainage Problems - Anglewood Center",null,null,200000,null,null,null,200000]
[23,"Correct Drainage Problems - Woodlands",null,null,null,200000,null,null,200000]
[24,"Correct Drainage Problems - Lakewood Park Elem.",null,null,null,200000,null,null,200000]
[25,"Correct Drainage Problems - Floresta Elem. ",null,null,null,200000,null,null,200000]
[26,"Covered bus drop off & pick up - Port St. Lucie High",{"$nulls":4},200000,null,200000]
[27,"Covered bus drop off & pick up - Manatee Elem.",{"$nulls":4},200000,null,200000]
[28,"Covered bus drop off & pick up - Forrest Grove Middle ",{"$nulls":5},200000,200000]
[29,"Cafeteria-Food Service - Lawnwood Elem.",null,null,null,400000,null,null,400000]
[30,"Expand ESE suite. Remodel 8 - intermediate classrooms. - Garden City Elem. ",{"$nulls":4},460000,null,460000]
[31,"Add 1-Music, 1-Art, 2-skill Dev Labs - Port St. Lucie Elem.",{"$nulls":5},778189,778189]
[32,"Add 1-Art, 2-Skill Development Labs,  5-Resource Rooms - Lakewood Park Elem.",{"$nulls":5},729073,729073]
[33,"Expand Food Service Area - Dale Cassens ",{"$nulls":5},395000,395000]
[34,"Add Art Classroom, two skills development labs - Floresta Elementary",{"$nulls":5},443039,443039]
[35,"Convert Building 03 Rooms 352A through 352D to PE Multipurpose - Forest Grove Middle School",{"$nulls":5},175000,175000]
[36,"Outdoor Basketball Court - Garden City Elem. ",{"$nulls":4},18000,null,18000]
[37,"Track Repairs & Repairs to Ticket Booths - Lawnwood Stadium",{"$nulls":5},55000,55000]
[38,"Add Restroom Facilities near the Stadium - Pt. Lucie High School",{"$nulls":5},350000,350000]
[39,"Remodel/Renovate West Half","Ft. Pierce Magnet",{"$nulls":4},7000000,7000000]
[40,"HVAC Renovations/EM Controls","Floresta, Morningside, Windmill Point, Village Green, Manatee, Mariposa, Parkway, Garden City, St. Lucie Elem, Dale Cassens",{"$nulls":4},4414124,4414124]
[41,"Storm Water Management","Port St. Lucie Elem, Northport",{"$nulls":4},400000,400000]
[42,"Classroom Remodeling to provide additional Student Stations","SLW Centennial High",null,42400,null,null,null,42400]
[43,"Field House w/restrooms, Concession, & Storage","SLW Centennial High",{"$nulls":4},300000,300000]
[44,"Add Culinary Arts Dining Room ","Port St, Lucie High",{"$nulls":4},204000,204000]
[45,"New Classroom wing","Northport Middle School",{"$nulls":4},5000000,5000000]
[46,"New High School","To be determined",{"$nulls":4},40200000,40200000]
[47,"New Middle School","To be determined",{"$nulls":4},20750000,20750000]
[48,"New Elementary School","To be determined",{"$nulls":4},12800000,12800000]
["7.","ST. LUCIE COUNTY Total",0,0,4159500,3010234,2433439,165065425,174668598]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02","2002-03","2003-04","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
[]
[]
[]
[]
[]
[]
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[]
[null,"SCHOOL BOARD OF ","ST. LUCIE COUNTY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Dr. William Vogel",null,null,"2001-10-24"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:",{"$nulls":4},"Michael Averyt",null,null,"2001-10-24"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["DISTRICT POINT-OF-CONTACT PERSON: ",null,null,"Richard Stabile","Director of Facilities","561-340-7100",null,"stabiler@stlucie.k12.fl.us"]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null," "]
[{"$nulls":10}," "]
[]
[{"$nulls":9}," "]
[{"$nulls":10}," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}