| Activity | Dates and Deadlines |
| --- | --- |
| Principal places NAEP 2015 assessment date(s) on school calendar and appoints School NAEP Coordinator. | August 2014 |
| Principal gives the NAEP folder distributed to them by the District Assessment Coordinator to their School Coordinator. School Coordinator reviews packet contents. | August 2014 |
| School NAEP coordinator registers as a new user on MyNAEP using the schools registration ID. He or she completes the online Provide School Information Form (PSI). | Before September 12, 2014 |
| School NAEP coordinator periodically accesses the MyNAEP website for the latest information regarding the administration of NAEP 2015. | August 2014 to Assessment Day |
| NAEP Preassessment Packets arrive at schools. | December 2, 2014 |
| Student sample available to schools via MyNAEP. Identify withdrawn and ineligible students, provide any missing information, update demographic data, and update SD and ELL classifications. | December 8, 2014 |
| Preassessment Scheduling Call (PSC) from NAEP representative to review the information you share via the MyNAEP website. Make arrangements for a Preassessment Review Call (PRC) in January when final assessment arrangements will be made. | December 8 – 19, 2014 |
| Complete tasks listed under the Prepare for Assessment menu category which includes providing information about students with disabilities (SD) and English language learners (ELL). | December 2014 – January 2015 |
| Submit Current Roster of Students via email. | January 5, 2015 |
| PRC reminder email | 5 days before call |
| PRCs with email follow-up to finalize preassessment activities. | January 5 – 23, 2015 |
| Principal and/or School NAEP Coordinator meets with faculty and students to explain NAEP and its importance. | Prior to the Assessment |
| School NAEP coordinator identifies possible incentives to offer the students. | Prior to the Assessment |
| School distributes Parent/Guardian Notification Letters. | At Least 2 Weeks Prior to Assessment Day |
| Visit the Support Assessment Activities page of MyNAEP to print student appointment cards. Notify teachers so they will know when to release students. Coordinate principal’s and teachers’ completion of questionnaires. | 1 Week Prior to Assessment Day |
| School NAEP Coordinator prepares for the assessment day by verifying that selected testing sites are available as well as work space for the NAEP field staff. Field staff will need a list of parent/guardian refusals and any student withdrawals since school submitted Current Roster of Students in January. | Ongoing |
| NAEP testing window | January 26 – March 6, 2015 |
| School NAEP Coordinator schedules a make-up session if less than 90% of the students participate in the assessment. | by March 13, 2015 |
| Confirm that all confidential hardcopy NAEP materials have been shredded by visiting the Wrap Up page on MyNAEP. | June 1, 2015 or last day of school, whichever comes first |