{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":281,"n_cols":25,"rows_kept":281,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Baker County  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Baker County   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Baker County","Date: ==>","2000-08-09",null,"For fiscal years","  2000-2001 through 2004-2005"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety",{"$nulls":6},0]
[null,"  Telephone/Intercom system","District -Wide",150000,{"$nulls":4},150000]
[{"$nulls":8},0]
[null,"Paving",{"$nulls":6},0]
[null,"  County-wide paving","District-Wide",227925.33,null,null,null,100000,327925.32999999996]
[null," Tennis courts & Track","BCHS",200000,{"$nulls":4},200000]
[null,null,"BCMS",{"$nulls":4},100000,100000]
[null,"Flooring",{"$nulls":6},0]
[null,"  Carpet","District-Wide",270000,null,null,null,100000,370000]
[{"$nulls":8},0]
[null,"Roofing","BCMS",93879.22,null,null,null,100000,193879.22]
[null,"Covered Walkways","District-Wide",125000,{"$nulls":4},125000]
[{"$nulls":8},0]
[null,"Equipment","District-Wide",87951.12,null,null,null,100000,187951.12]
[{"$nulls":8},0]
[null,"Wall Partitions","WES",52949.03,{"$nulls":4},52949.03]
[null,"Brick Sealing","BCHS",50000,{"$nulls":4},50000]
[{"$nulls":8},0]
[null,"EPA Fuel Tank Removal","Transportation",{"$nulls":4},125000,125000]
[{"$nulls":8},0]
[{"$nulls":8},0]
["1.","Baker County Total",null,1257704.7,0,0,0,625000,1882704.7]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Westside Elementary New Wing",null,756138,{"$nulls":4},756138]
[null,"Keller Intermediate New Wing",null,435408,{"$nulls":4},435408]
[null,"New Elementary School \"B\"",null,null,10557233,624358,628673,null,11810264]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2 .","Baker County Total",null,1191546,10557233,624358,628673,0,13001810]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1999-00 FISH Satisfactory","Actual 1999-00","Actual 1999-00","Actual 1999-00","New Stu Capacity to","Projected 2004-05","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Macclenny Elementary",833,833,700,0.84,null,800,0.96]
[null,"Westside Elementary",789,789,721,0.91,null,737,0.93]
[null,"Keller Intermediate School",724,724,717,0.99,null,720,0.99]
[null,"Baker County Middle School",1121,1008,1147,1.14,null,1114,1.11]
[null,"Baker County High School",1494,1344,1177,0.88,null,1138,0.85]
["2a.","Baker County Total",4961,4698,4462,0.95,0,4509,0.96]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School \"B\" in the North Macclenny area."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"Baker Co High School",4,"BCSB",90,null,5,-1,18]
[null,"Baker Co MiddleSchool",11,"BCSB",247.5,null,11,0,264]
[null,"Keller Intermediate School",3,"BCSB",75,null,2,1,38]
[null,"Macclenny Elementary",1,"Fed",25,null,0,null,19]
[null,"Macclenny Elementary",10,"BCSB",250,null,0,null,278]
[null,"Westside Elementary",11,"BCSB",275,null,0,11,159]
[null,"Baker Co Alternative School",3,"BCSB",75,null,4,-1,6]
[{"$nulls":7},0]
["2c1.","Baker County Total",43,null,1037.5,0,22,10,"Avg Age 18.19"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"Westside Elementary",11,11,{"$nulls":4},11]
[null,"Macclenny Elementary",11,null,null,11,null,null,11]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","Baker County Total",22,11,0,11,0,0,22]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05","FISH Stu. Sta.","# Years Leased "]
[null,"Baker Co High School",3,"Leased",67.5,15,4,90,31]
[null,"Baker Co Middle School",3,"Leased",67.5,25,3,67.5,37]
[null,"Baker Co Alternative School",3,"Leased",75,5,4,100,21]
[null,"Keller Intermediate School",1,"Leased",25,1,0,0]
[null,"Macclenny Elementary School",1,"Leased",25,6,0,0]
[null,"Westside Elementary School",7,"Leased",150,77,0,0]
["2c3.","Baker County Total",18,null,410,129,11,257.5,89]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2004-05"]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c4.","Baker County Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"Macclenny Elementary",46,999,700,15.22,800,0,17.39]
[null,"Westside Elementary",15,946,721,48.07,737,0,49.13]
[null,"Keller Intermediate",32,868,717,22.41,720,0,22.5]
[null,"Baker Co Middle School",40,1209,1147,28.68,1114,0,27.85]
[null,"Baker Co High School",67,1612,1177,17.57,1177,0,17.57]
["2e.","Baker County Total",200,5634,4462,"District Avg 22",4548,0,"District Avg 23"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR AVERAGE"]
[null,"Macclenny Elementary",null,250,250,0,0,0,100,null,0]
[null,"Westside Elementary",null,0,0,0,0,0,0]
[null,"Keller Intermediate School",null,50,50,50,50,50,50]
[null,"Baker Co Middle School",null,247.5,247.5,247.5,247.5,247.5,247.5]
[null,"Baker Co High School",null,112.5,112.5,112.5,112.5,112.5,112.5]
[null,"Baker Co Alternative School",null,100,100,100,100,100,100]
["2f.","Baker County Total students in relocatables by year",null,760,760,510,510,510,610]
[null,"Total number of CO-FTE students projected by year",null,4412,4415,4468,4477,4509,4456.2]
[null,"Percent in relocatables by year",null,0.17,0.17,0.11,0.11,0.11,0.14]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01 ","2000-01 ","2000-01 ","2000-01 ","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"KIS New Wing",0,950285,120,3640,30.33,0,0,0,7919.04,0,0,0]
[null,"WES New Wing",0,1650285,175,7805,44.6,0,0,0,9430.2,0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","Baker County Total 2000-01",null,2600570,295,11445,38.8,null,null,null,8815.49]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","Baker County Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Elementary 'B'",1,11810264,800,98995,123.74,70,107,174,14762.83,7485,11173,16419]
["3c","Baker County Total 2002-03",null,11810264,800,98995,123.74,null,null,null,14762.83]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","Baker County Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","Baker County Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","Baker County 5-Year Total",null,14410834,1095,110440]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,622666,632700,668800,703000,735300,3362466]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,622666,632700,668800,703000,735300,3362466,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,250000,158175,167200,175750,299693,1050818,0.312514089361796]
[null,"  less amount used to purchase other vehicles",null,50000,{"$nulls":4},50000,0.0148700388345934]
[null,"  less amount transferred to operating budget for maintenance/repair",null,40000,{"$nulls":4},40000,0.0118960310676747]
[null,"  less amount used for maintenance/repair",null,321558,0,0,0,300000,621558,0.184851831959044]
[null,"  less amount used to purchase capital outlay equipment",null,87951.12,0,0,0,100000,187951.12,0.0558968090681066]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,125000,125000,0.0371750970864836]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",{"$nulls":6},0,0]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,-126843.12,474525,501600,527250,-89393,1287138.88,0.382796102622302,0.43]
[null,"P E C O New Construction",null,107352,56683,103266,81931,69901,419133,null,0.14]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,19492,19492,19492,19492,19492,97460,null,0.03]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,1191545.6,0,0,0,0,1191545.6,null,0.4]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","Baker County Total",null,1191546.48,550700,624358,628673,0,2995277.48,1.0000000000000002,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"KIS New Wing",120,435408,{"$nulls":4},435408]
[null,"WES New Wing",175,756138,{"$nulls":4},756138]
[null,"New Elem School \"B\"",800,null,546963,624358,628673,null,1799994]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["5.","Baker County Total",1095,1191546,546963,624358,628673,0,2991540]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (Special Facilities Funding)",null,0,10010270,0,0,0,10010270]
["6.","Baker County Total",null,0,10010270,0,0,0,10010270]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New Elem 'B'",null,0,10010270,0,0,null,10010270]
[null,null,null,0,0,null,0,null,0]
[null,null,null,0,0,0,null,0,0]
["7.","Baker County Total",0,0,10010270,0,0,0,10010270]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2000."]
[]
[null,"SCHOOL BOARD OF ","Baker County  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}