{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":50,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":1027,"n_cols":25,"rows_kept":1027,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["BREVARD  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["BREVARD   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"BREVARD","Date: ==>","2001-09-24",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Fire Safety, ADA, & Asbestos","Various",250000,250000,250000,250000,250000,1250000]
[null,"Major Maintenance","Various",1400000,1500000,1500000,1500000,1500000,7400000]
[null,"Paving","Various",350000,500000,500000,500000,500000,2350000]
[null,"Renovate / Site Improvements","Various",5400000,5000000,5000000,5000000,5000000,25400000]
[null,"Health & Safety","Various",3750000,4000000,4000000,4000000,4000000,19750000,36400000]
[null,"Portable Lease ","Various",750000,1058535,1307070,2068470,2068470,7252545,null,36400000]
[null,"Portable Renovation & Repair","Various",800000,0,0,0,0,800000]
[null,"School Furniture Replacement","Various",600000,600000,600000,600000,600000,3000000]
[null,"Replacement Portable Infrastructure","Various",0,2405050,2405050,2802000,0,7612100]
[null,"Portable Relocation","Various",250000,250000,250000,250000,250000,1250000,19914645]
[null,"Safety to Life & Maintenance","Various",4580294,3918753,3618456,3506775,3516703,19140981]
[null,"HVAC Upgrades/Replacements","Various",2800000,2200000,2200000,2200000,2200000,11600000]
[null,null,"Hans Christian Anderson Elementary",0,0,0,1332820,0,1332820]
[null,null,"Apollo Elementary",0,0,0,0,1253510,1253510]
[null,null,"Audubon Elementary",0,1046480,0,0,0,1046480]
[null,null,"Cambridge Elementary",0,0,1418310,0,0,1418310]
[null,null,"Cape View Elementary",0,0,0,0,1791170,1791170]
[null,null,"Challenger 7 Elementary ",0,0,1851940,0,0,1851940]
[null,null,"Columbia Elementary",0,0,0,1906530,0,1906530]
[null,null,"Coquina Elementary",0,0,0,0,1372990,1372990]
[null,null,"Dr. W. J. Creel Elementary",0,0,2037340,0,0,2037340]
[null,null,"Croton Elementary",0,0,0,0,2686240,2686240]
[null,null,"Discovery Elementary",0,0,0,0,322390,322390]
[null,null,"Endeavour Elementary",0,0,0,376980,0,376980]
[null,null,"Gardendale Elementary",0,2338100,0,0,0,2338100]
[null,null,"Golfview Elementary",0,0,150000,0,0,150000]
[null,null,"Harbor City Elementary",0,0,0,1970390,0,1970390]
[null,null,"Lockmar Elementary",0,0,1046480,0,0,1046480]
[null,null,"Christa McAuliffe Elementary",0,0,0,1906530,0,1906530]
[null,null,"Mila Elementary",0,0,0,0,886830,886830]
[null,null,"Mims Elementary",0,0,0,0,1715980,1715980]
[null,null,"Oak Park Elementary",0,1496590,0,0,0,1496590]
[null,null,"Ocean Breeze Elementary",0,0,1294710,0,0,1294710]
[null,null,"Pinewood Elementary",0,0,0,250000,0,250000]
[null,null,"Port Malabar Elementary",0,0,1294710,0,0,1294710]
[null,null,"Riverview Elementary",0,0,0,300000,0,300000]
[null,null,"Theodore Roosevelt Elementary",0,0,0,0,2030130,2030130]
[null,null,"Sabal Elementary",0,1377110,0,0,0,1377110]
[null,null,"Saturn Elementary ",0,0,0,0,1767480,1767480]
[null,null,"Sea Park Elementary",0,1377110,0,0,0,1377110]
[null,null,"South Lake Elementary",0,0,0,637570,0,637570]
[null,null,"Surfside Elementary",0,1400000,0,0,0,1400000]
[null,null,"Tropical Elementary",0,0,1541910,0,0,1541910]
[null,null,"John F. Turner Sr. Elementary",0,0,0,822970,0,822970]
[null,null,"University Park Elementary",0,0,0,1014550,0,1014550]
[null,null,"DeLaura Middle",0,0,2532770,0,0,2532770]
[null,null,"Edgewood Middle",0,0,2656370,0,0,2656370]
[null,null,"Herbert C. Hoover Middle",0,0,1665510,0,0,1665510]
[null,null,"Andrew Jackson Middle",0,0,0,0,2030130,2030130]
[null,null,"Thomas Jefferson Middle",0,0,1665510,0,null,1665510]
[null,null,"Lyndon B. Johnson Middle",0,0,0,0,2030130,2030130]
[null,null,"John F. Kennedy Middle",0,0,0,0,477920,477920]
[null,null,"Ronald McNair Middle",0,1256600,0,0,null,1256600]
[null,null,"James Madison Middle",0,0,0,0,2160940,2160940]
[null,null,"Southwest Middle",0,0,2532770,0,0,2532770]
[null,null,"Astronaut High",0,0,null,5132490,0,5132490]
[null,null,"Cocoa Beach Jr./Sr. High",0,2698600,0,0,0,2698600]
[null,null,"Melbourne Senior High",0,0,0,0,835330,835330]
[null,null,"Merritt Island Senior High",0,4862630,0,0,0,4862630]
[null,null,"Palm Bay Senior High",0,3060130,0,0,0,3060130]
[null,null,"Rockledge Senior High",0,0,0,1843700,0,1843700]
[null,null,"Satellite Senior High",0,3060130,0,0,0,3060130]
[null,null,"Titusville High ",0,800000,0,0,0,800000]
[null,null,"Rockedge Center",0,0,0,0,1000000,1000000]
[null,"Noise Attenuation Improvements @ 5 MS Gyms",null,210775,{"$nulls":4},210775]
[null,"Other Projects","Various",1523367,1142780,1000000,4246351,7678629,15591127]
[null,"Maintenance, Repair, and Renovation Totals",null,22664436,47598598,44318906,44418126,49924972,208925038,102119412]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,4580294,3918753,3618456,3506775,3516703,19140981]
["1.","BREVARD Total",null,18084142,43679845,40700450,40911351,46408269,189784057]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Remodel / Renovate Projects","Hans Christian Anderson Elementary",0,0,0,0,3285720,3285720]
[null,null,"Apollo Elementary",0,0,0,0,3133896,3133896]
[null,null,"Atlantis Elementary",0,0,0,0,180845,180845]
[null,null,"Audubon Elementary",0,0,0,0,2417058,2417058]
[null,null,"Cambridge Elementary",0,0,0,0,1776670,1776670]
[null,null,"Cape View Elementary",0,0,0,0,3214320,3214320]
[null,null,"Columbia Elementary",0,0,0,0,336265,336265]
[null,null,"Coquina Elementary",0,0,0,0,2684383,2684383]
[null,null,"Dr. W. J. Creel Elementary",0,0,0,0,3152284,3152284]
[null,null,"Croton Elementary",0,0,0,0,2916154,2916154]
[null,null,"Devereux South Pine Grove",0,0,0,0,542315,542315]
[null,null,"Discovery Elementary",0,0,0,0,275834,275834]
[null,null,"Endeavour Elementary",0,0,0,0,770243,770243]
[null,null,"Enterprise Elementary",0,0,0,0,173864,173864]
[null,null,"Fairglen Elementary",0,0,0,0,562264,562264]
[null,null,"Gardendale Elementary",0,0,0,0,3037781,3037781]
[null,null,"Gemini Elementary",0,0,0,0,150000,150000]
[null,null,"Golfview Elementary",0,0,0,0,1864109,1864109]
[null,null,"Harbor City Elementary",0,0,0,0,2876985,2876985]
[null,null,"Spessard L. Holland Elementary",0,0,0,0,975535,975535]
[null,null,"Imperial Estates Elementary",0,0,0,0,331395,331395]
[null,null,"Indialantic Elementary",0,0,0,0,1640194,1640194]
[null,null,"Jupiter Elementary",0,0,0,0,242762,242762]
[null,null,"Lockmar Elementary",0,0,0,0,2965289,2965289]
[null,null,"Christa McAuliffe Elementary",0,0,0,0,472496,472496]
[null,null,"Meadowlane",0,0,0,0,185185,185185]
[null,null,"Mila Elementary",0,0,0,0,2864064,2864064]
[null,null,"Mims Elementary",0,0,0,0,1992074,1992074]
[null,null,"Oak Park Elementary",0,0,0,0,3407510,3407510]
[null,null,"Ocean Breeze Elementary",0,0,0,0,3073581,3073581]
[null,null,"Palm Bay Elementary",0,0,0,0,2739961,2739961]
[null,null,"Pinewood Elementary",0,0,0,0,1878437,1878437]
[null,null,"Port Malabar Elementary",0,0,0,0,1013908,1013908]
[null,null,"Riverview Elementary",0,0,0,0,3068225,3068225]
[null,null,"Riviera Elementary",0,0,0,0,269585,269585]
[null,null,"Theodore Roosevelt Elementary",0,0,0,0,4238285,4238285]
[null,null,"Sabal Elementary",0,0,0,0,3000295,3000295]
[null,null,"Saturn Elementary ",0,0,0,0,3527729,3527729]
[null,null,"Sea Park Elementary",0,0,0,0,2566839,2566839]
[null,null,"South Lake Elementary",0,0,0,0,2992039,2992039]
[null,null,"Suntree Elementary",0,0,0,0,216790,216790]
[null,null,"Surfside Elementary",0,0,0,0,2537743,2537743]
[null,null,"Tropical Elementary",0,0,0,0,3214419,3214419]
[null,null,"John F. Turner Sr. Elementary",0,0,0,0,2023273,2023273]
[null,null,"University Park Elementary",0,0,0,0,809903,809903]
[null,null,"Central Middle",0,0,0,0,237331,237331]
[null,null,"Clearlake Middle",0,0,0,0,459785,459785]
[null,null,"DeLaura Middle",0,0,0,0,5065043,5065043]
[null,null,"Edgewood Middle",0,0,0,0,4871800,4871800]
[null,null,"Herbert C. Hoover Middle",0,0,0,0,4900650,4900650]
[null,null,"Andrew Jackson Middle",0,0,0,0,5019400,5019400]
[null,null,"Thomas Jefferson Middle",0,0,0,0,5369775,5369775]
[null,null,"Lyndon B. Johnson Middle",0,0,0,0,5560060,5560060]
[null,null,"John F. Kennedy Middle",0,0,0,0,5897250,5897250]
[null,null,"Ronald McNair Middle",0,0,0,0,1953537,1953537]
[null,null,"James Madison Middle",0,0,0,0,5382900,5382900]
[null,null,"Southwest Middle",0,0,0,0,266008,266008]
[null,null,"Space Coast Middle School",0,0,0,0,68999,68999]
[null,null,"Stone Middle",0,0,0,0,2254621,2254621]
[null,null,"Astronaut High",0,0,0,0,5783311,5783311]
[null,null,"Cocoa Beach Jr./Sr. High",0,0,0,0,2665430,2665430]
[null,null,"Cocoa Senior High",0,0,0,0,1251275,1251275]
[null,null,"Eau Gallie Senior High",0,0,0,0,8513894,8513894]
[null,null,"Melbourne Senior High",0,0,0,0,4146459,4146459]
[null,null,"Merritt Island Senior High",0,0,0,0,10375966,10375966]
[null,null,"Palm Bay Senior High",0,0,0,0,8076106,8076106]
[null,null,"Rockledge Senior High",0,0,0,0,3851522,3851522]
[null,null,"Satellite Senior High",0,0,0,0,11092395,11092395]
[null,null,"Titusville High ",0,0,0,0,7555183,7555183]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,1058850,1058850]
[null,null,"Rockledge Center",0,0,0,0,40000,40000,197316056]
[null,"Classroom Additions","Note: If all classroom additions were completed per the Plant Survey (June 13, 2000) and year 5 of this plan became a reality, portables would actually be reduced to \"0\".",{"$nulls":5},0,197316056]
[null,141.351,"Gardendale Elementary",0,0,0,0,1602920.34,1602920.34]
[null,null,"Gemini Elementary",0,0,0,0,1068613.56,1068613.56]
[null,null,"Indialantic Elementary",0,0,0,0,1068613.56,1068613.56]
[null,null,"Mims Elementary",0,0,0,0,1602920.34,1602920.34]
[null,null,"Ocean Breeze Elementary",0,0,0,0,329347.83,329347.83]
[null,null,"Palm Bay Elementary",0,0,0,0,486954.195,486954.195]
[null,null,"Riverview Elementary",0,0,0,0,788031.825,788031.825]
[null,null,"Saturn Elementary ",0,0,0,0,658695.66,658695.66]
[null,null,"South Lake Elementary",0,0,0,0,959773.29,959773.29]
[null,null,"Surfside Elementary",0,0,0,0,1317391.32,1317391.32]
[null,null,"Clearlake Middle",0,0,0,0,1706985.5856,1706985.5856]
[null,null,"DeLaura Middle",0,0,0,0,929874.7392000002,929874.7392000002]
[null,null,"Edgewood Middle",0,0,0,0,1571044.1472000002,1571044.1472000002]
[null,null,"Hoover Middle School",0,0,0,0,929874.7392000002,929874.7392000002]
[null,null,"Andrew Jackson Middle",0,0,0,0,929874.7392000002,929874.7392000002]
[null,null,"Thomas Jefferson Middle",0,0,0,0,929874.7392000002,929874.7392000002]
[null,null,"Lyndon B. Johnson Middle",0,0,0,0,1342873.8048000003,1342873.8048000003]
[null,null,"John F. Kennedy Middle",0,0,0,0,929874.7392000002,929874.7392000002]
[null,null,"James Madison Middle",0,0,0,0,2980900.4544000006,2980900.4544000006]
[null,null,"Ronald McNair Middle",0,0,0,0,505234.32960000006,505234.32960000006]
[null,null,"Astronaut High",0,0,0,0,3611484.8932000003,3611484.8932000003]
[null,null,"Cocoa Beach Jr./Sr. High ",0,0,0,0,547680.4608000001,547680.4608000001]
[null,null,"Cocoa Senior High",0,0,0,0,548951.9308000001,548951.9308000001]
[null,null,"Eau Gallie Senior High",0,0,0,0,1245601.3148,1245601.3148]
[null,194.59480000000002,"Merritt Island Senior High",0,0,0,0,1317017.6064000002,1317017.6064000002]
[null,179.09760000000003,"Rockledge Senior High",0,0,0,0,1669623.384,1669623.384]
[null,null,"Satellite Senior High",0,0,0,0,5302124.5156000005,5302124.5156000005]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,821520.6912000001,821520.6912000001]
[null,"New Additions (expand core & equity per facility list)",null,0,0,0,0,null,0,37703678.734400004]
[null,null,"Apollo Elementary",0,0,0,0,1799822,1799822]
[null,null,"Audubon Elementary",0,0,0,0,2946461.595,2946461.595]
[null,null,"Cambridge Elementary",0,0,0,0,2659802,2659802]
[null,null,"Cape View Elementary",0,0,0,0,2319005,2319005]
[null,null,"Coquina Elementary",0,0,0,0,2241261,2241261]
[null,null,"Croton Elementary",0,0,0,0,2055809,2055809]
[null,null,"Endeavour Elementary",0,0,0,0,2354625,2354625]
[null,null,"Gardendale Elementary",0,0,0,0,2492866.236,2492866.236]
[null,null,"Golfview Elementary",0,0,0,0,1813675,1813675]
[null,null,"Harbor City Elementary",0,0,0,0,2252145,2252145]
[null,null,"Spessard L. Holland Elementary",0,0,0,0,1432592,1432592]
[null,null,"Imperial Estates Elementary",0,0,0,0,956805,956805]
[null,null,"Indialantic Elementary",0,0,0,0,3291499.386,3291499.386]
[null,null,"Lockmar Elementary",0,0,0,0,1941739,1941739]
[null,null,"Mila Elementary",0,0,0,0,2263595,2263595]
[null,null,"Oak Park Elementary",0,0,0,0,1361351,1361351]
[null,null,"Ocean Breeze Elementary",0,0,0,0,2645808.018,2645808.018]
[null,null,"Palm Bay Elementary",0,0,0,0,2502760.806,2502760.806]
[null,null,"Pinewood Elementary",0,0,0,0,725413,725413]
[null,null,"Port Malabar Elementary",0,0,0,0,1941739,1941739]
[null,null,"Riverview Elementary",0,0,0,0,468578.17500000005,468578.17500000005]
[null,null,"Theodore Roosevelt Elementary",0,0,0,0,146157,146157]
[null,null,"Sabal Elementary",0,0,0,0,2419646,2419646]
[null,null,"Saturn Elementary ",0,0,0,0,725413.332,725413.332]
[null,null,"Sea Park Elementary",0,0,0,0,2863489,2863489]
[null,null,"South Lake Elementary",0,0,0,0,2192919.71,2192919.71]
[null,null,"Surfside Elementary",0,0,0,0,3202165.554,3202165.554]
[null,null,"Tropical Elementary",0,0,0,0,2636620,2636620]
[null,null,"John F. Turner Sr. Elementary",0,0,0,0,2207620,2207620]
[null,null,"University Park Elementary",0,0,0,0,3448964,3448964]
[null,null,"Clearlake Middle",0,0,0,0,417369.4143999999,417369.4143999999]
[null,null,"DeLaura Middle",0,0,0,0,1443347.5584000002,1443347.5584000002]
[null,null,"Edgewood Middle",0,0,0,0,1192445.8527999998,1192445.8527999998]
[null,null,"Herbert C. Hoover Middle",0,0,0,0,1447003.2607999998,1447003.2607999998]
[null,null,"Andrew Jackson Middle",0,0,0,0,967029.2607999998,967029.2607999998]
[null,null,"Thomas Jefferson Middle",0,0,0,0,1447003.2607999998,1447003.2607999998]
[null,null,"Lyndon B. Johnson Middle",0,0,0,0,2270718.1952,2270718.1952]
[null,null,"John F. Kennedy Middle",0,0,0,0,1447003.2607999998,1447003.2607999998]
[null,null,"James Madison Middle",0,0,0,0,585457,585457]
[null,null,"Ronald McNair Middle",0,0,0,0,1010598.6704,1010598.6704]
[null,null,"Stone Middle",0,0,0,0,277042,277042]
[null,null,"Astronaut High",0,0,0,0,1564153.1067999997,1564153.1067999997]
[null,null,"Bayside High School",0,0,0,0,2072435,2072435]
[null,null,"Cocoa Beach Jr./Sr. High",0,0,0,0,4693042.7916,4693042.7916]
[null,null,"Cocoa High School",0,0,0,0,4840156.0692,4840156.0692]
[null,null,"Palm Bay High",0,0,0,0,1769842.4832000004,1769842.4832000004]
[null,null,"Rockledge High",0,0,0,0,58378.61599999992,58378.61599999992]
[null,null,"Satellite Senior High",0,0,0,0,6268871.4843999995,6268871.4843999995]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,3080105.3087999998,3080105.3087999998]
["2 .","BREVARD Total Including Section 1",null,18084142,43679845,40700450,40911351,380590353.14079994,523966141.14079994,99162349.40639998]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Roy Allen Elementary",270,270,517,1.91,598,556,0.64]
[null,"Hans Christian Anderson Elementary",726,726,796,1.1,-24,777,1.11]
[null,"Apollo Elementary",1030,1030,974,0.95,-195,985,1.18]
[null,"Atlantis Elementary",912,912,738,0.81,-29,768,0.87]
[null,"Audubon Elementary",739,739,673,0.91,134,721,0.83]
[null,"Cambridge Elementary",783,783,619,0.79,-361,518,1.23]
[null,"Cape View Elementary",748,748,469,0.63,-283,407,0.88]
[null,"Lewis Carroll Elementary",891,891,839,0.94,-204,913,1.33]
[null,"Challenger 7 Elementary ",752,752,564,0.75,-29,404,0.56]
[null,"Columbia Elementary",928,928,734,0.79,-205,731,1.01]
[null,"Coquina Elementary",627,627,537,0.86,-72,558,1.01]
[null,"Dr. W. J. Creel Elementary",1311,1311,951,0.73,-293,851,0.84]
[null,"Croton Elementary",628,628,484,0.77,-213,427,1.03]
[null,"Discovery Elementary",1097,1097,994,0.91,-176,674,0.73]
[null,"Endeavour Elementary",905,905,613,0.68,-159,505,0.68]
[null,"Enterprise Elementary",928,928,851,0.92,0,699,0.75]
[null,"Fairglen Elementary",940,940,860,0.91,-131,768,0.95]
[null,"Gardendale Elementary",864,864,639,0.74,-259,539,0.89]
[null,"Gemini Elementary",713,713,725,1.02,-37,540,0.8]
[null,"Golfview Elementary",856,856,609,0.71,-116,613,0.83]
[null,"Harbor City Elementary",630,630,559,0.89,-241,520,1.34]
[null,"Spessard L. Holland Elementary",747,747,486,0.65,-156,365,0.62]
[null,"Imperial Estates Elementary",735,735,520,0.71,-73,404,0.61]
[null,"Indialantic Elementary",828,828,760,0.92,-92,776,1.05]
[null,"Jupiter Elementary",1031,1031,855,0.83,-151,1004,1.14]
[null,"Lockmar Elementary",1144,1144,943,0.82,-56,942,0.87]
[null,"Longleaf Elementary",1087,1087,1012,0.93,-189,1187,1.32]
[null,"Christa McAuliffe Elementary",938,938,838,0.89,-244,691,1]
[null,"Meadowlane Elementary",1072,1072,926,0.86,-198,981,1.12]
[null,"Mila Elementary",901,901,473,0.52,-223,495,0.73]
[null,"Mims Elementary",673,673,622,0.92,-58,637,1.04]
[null,"Oak Park Elementary",1033,1033,888,0.86,-123,809,0.89]
[null,"Ocean Breeze Elementary",686,686,587,0.86,-160,570,1.08]
[null,"Palm Bay Elementary",1062,1062,656,0.62,-376,478,0.7]
[null,"Pinewood Elementary",653,653,480,0.74,-198,408,0.9]
[null,"Port Malabar Elementary",1020,1020,893,0.88,-150,789,0.91]
[null,"Riverview Elementary",686,686,375,0.55,-235,340,0.75]
[null,"Riviera Elementary",944,944,727,0.77,-58,716,0.81]
[null,"Theodore Roosevelt Elementary",810,810,691,0.85,-110,557,0.8]
[null,"Sabal Elementary",650,650,517,0.8,-225,410,0.96]
[null,"Saturn Elementary ",955,955,768,0.8,-115,798,0.95]
[null,"Sea Park Elementary",600,600,475,0.79,-215,373,0.97]
[null,"Sherwood Elementary",889,889,770,0.87,-40,779,0.92]
[null,"South Lake Elementary",750,750,504,0.67,-250,423,0.85]
[null,"Devereux Normandy Center",62,62,62,1,0,60,0.97]
[null,"Devereux South Pine Grove ",348,348,54,0.16,0,51,0.15]
[null,"Suntree Elementary",999,999,993,0.99,-191,1080,1.34]
[null,"Surfside Elementary",630,630,568,0.9,-50,594,1.02]
[null,"Tropical Elementary",976,976,918,0.94,-279,852,1.22]
[null,"John F. Turner Sr. Elementary",925,925,717,0.78,-186,686,0.93]
[null,"University Park Elementary",841,841,551,0.66,-187,643,0.98]
[null,"Westside Elementary",940,940,868,0.92,0,1057,1.12]
[null,"Ralph M. Williams Jr. Elementary",1077,1077,981,0.91,-210,1081,1.25]
[null,"Freedom 7 Elementary",509,509,148,0.29,0,342,0.67]
[null,"West Melbourne Elementary",664,664,187,0.28,0,370,0.56]
[null,"Robert L. Stevenson Elementary",225,225,145,0.64,0,273,1.21]
[null,"Central Middle ",1880,1692,824,0.49,-54,1059,0.65]
[null,"Clearlake Middle",960,864,612,0.71,-63,591,0.74]
[null,"DeLaura Middle",991,891.9,845,0.95,-298,820,1.38]
[null,"Edgewood Middle",896,806.4,488,0.61,-306,468,0.94]
[null,"Herbert C. Hoover Middle",732,658.8000000000001,527,0.8,-41,492,0.8]
[null,"Andrew Jackson Middle",811,729.9,709,0.97,-85,640,0.99]
[null,"Thomas Jefferson Middle",827,744.3000000000001,537,0.72,-107,508,0.8]
[null,"Lyndon B. Johnson Middle",1267,1140.3,994,0.87,-10,981,0.87]
[null,"John F. Kennedy Middle",761,684.9,587,0.86,-12,633,0.94]
[null,"Ronald McNair Middle",744,669.6,411,0.61,-192,405,0.85]
[null,"James Madison Middle",729,656.1,809,1.23,259,721,0.79]
[null,"Southwest Middle",1732,1558.8,1323,0.85,-42,1442,0.95]
[null,"Space Coast Middle ",1880,1692,1167,0.69,-33,1133,0.68]
[null,"Stone Middle",1277,1149.3,807,0.7,-399,676,0.9]
[null,"Astronaut High",1659,1576.05,1516,0.96,169,1464,0.84]
[null,"Bayside High",2490,2365.5,1681,0.71,-90,1763,0.77]
[null,"Cocoa Beach Jr./Sr. High",1494,1419.3,1247,0.88,-114,1494,1.14]
[null,"Cocoa Senior High",1865,1771.75,1218,0.69,-195,1441,0.91]
[null,"Eau Gallie Senior High",2578,2449.1,2016,0.82,-265,2558,1.17]
[null,"Melbourne Senior High",2073,1969.35,2196,1.12,-44,2330,1.21]
[null,"Merritt Island Senior High",1967,1868.6499999999999,1802,0.96,-61,2095,1.16]
[null,"Palm Bay Senior High",2512,2386.4,1757,0.74,-547,1954,1.06]
[null,"Rockledge Senior High",1372,1303.3999999999999,1525,1.17,169,1803,1.22]
[null,"Satellite Senior High",1971,1872.4499999999998,1868,1,37,2108,1.1]
[null,"Titusville High ",2308,2192.6,2129,0.97,4,2608,1.19]
[null,"West Shore Jr./Sr. High",1041,988.9499999999999,1181,1.19,40,940,0.91]
["2a.","BREVARD Total",84185,81469.80000000002,67479,0.83,-9373,68622,0.95]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"None"]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,"Roy Allen Elementary",10,"LEASED",200,null,0,10,111]
[null,"Roy Allen Elementary",4,"SBBC",70,null,0,4,154]
[null,"Hans Christian Anderson Elementary",0,"LEASED",0,null,1,-1,"-"]
[null,"Hans Christian Anderson Elementary",1,"SBBC",21,null,0,1,40]
[null,"Audubon Elementary",2,"SBBC",38,null,0,2,39]
[null,"Audubon Elementary",6,"LEASED",116,null,1,5,59]
[null,"Cambridge Elementary",7,"LEASED",125,null,6,1,64]
[null,"Cambridge Elementary",5,"SBBC",94,null,1,4,166]
[null,"Lewis Carroll Elementary",8,"SBBC",166,null,3,5,288]
[null,"Lewis Carroll Elementary",0,"LEASED","-",null,9,-9,"-"]
[null,"Columbia Elementary",7,"LEASED",136,null,5,2,85]
[null,"Columbia Elementary",3,"SBBC",60,null,3,0,32]
[null,"Dr. W. J. Creel Elementary",0,"LEASED","-",null,1,-1,"-"]
[null,"Dr. W. J. Creel Elementary",1,"SBBC",17,null,0,1,38]
[null,"Discovery Elementary",9,"LEASED",176,null,5,4,98]
[null,"Discovery Elementary",2,"SBBC",40,null,0,2,32]
[null,"Endeavour Elementary",9,"LEASED",184,null,8,1,95]
[null,"Endeavour Elementary",1,"SBBC",20,null,0,1,16]
[null,"Fairglen Elementary",3,"SBBC",61,null,2,1,24]
[null,"Fairglen Elementary",0,"LEASED",0,null,0,0,"-"]
[null,"Gardendale Elementary",12,"LEASED",221,null,13,-1,160]
[null,"Gardendale Elementary",1,"SBBC",10,null,0,1,38]
[null,"Gemini Elementary",6,"LEASED",117,null,6,0,74]
[null,"Gemini Elementary",2,"SBBC",40,null,0,2,56]
[null,"Golfview Elementary",1,"LEASED",16,null,1,0,11]
[null,"Harbor City Elementary",1,"LEASED",16,null,2,-1,14]
[null,"Harbor City Elementary",3,"SBBC",63,null,0,3,116]
[null,"Indialantic Elementary",10,"LEASED",200,null,8,2,115]
[null,"Indialantic Elementary",1,"SBBC",20,null,1,0,15]
[null,"Jupiter Elementary",0,"SBBC",0,null,0,0,16]
[null,"Jupiter Elementary",6,"LEASED",135,null,12,-6,62]
[null,"Longleaf Elementary",7,"SBBC",147,null,0,7,358]
[null,"Longleaf Elementary",0,"LEASED","-",null,14,-14,"-"]
[null,"Christa McAuliffe Elementary",7,"LEASED",129,null,6,1,55]
[null,"Christa McAuliffe Elementary",5,"SBBC",86,null,2,3,72]
[null,"Meadowlane Elementary",7,"LEASED",140,null,5,2,91]
[null,"Mila Elementary",3,"LEASED",58,null,5,-2,35]
[null,"Mila Elementary",1,"SBBC",20,null,0,1,16]
[null,"Mims Elementary",3,"LEASED",70,null,11,-8,33]
[null,"Mims Elementary",10,"SBBC",177,null,4,6,264]
[null,"Ocean Breeze Elementary",5,"LEASED",80,null,5,0,62]
[null,"Ocean Breeze Elementary",1,"SBBC",16,null,0,1,16]
[null,"Palm Bay Elementary",0,"LEASED","-",null,8,-8,"-"]
[null,"Palm Bay Elementary",12,"SBBC",227,null,0,12,318]
[null,"Port Malabar Elementary",1,"LEASED",25,null,4,-3,11]
[null,"Port Malabar Elementary",6,"SBBC",125,null,1,5,212]
[null,"Riverview Elementary",4,"LEASED",88,null,4,0,116]
[null,"Theodore Roosevelt Elementary",1,"LEASED",12,null,0,1,12]
[null,"Sabal Elementary",1,"LEASED",20,null,0,1,0]
[null,"Sabal Elementary",5,"SBBC",83,null,1,4,167]
[null,"Saturn Elementary ",1,"LEASED",21,null,2,-1,13]
[null,"Saturn Elementary ",1,"SBBC",21,null,0,1,38]
[null,"South Lake Elementary",1,"LEASED",25,null,2,-1,11]
[null,"South Lake Elementary",4,"SBBC",55,null,1,3,128]
[null,"Suntree Elementary",0,"SBBC",0,null,0,0,55]
[null,"Suntree Elementary",4,"LEASED",76,null,8,-4,97]
[null,"Surfside Elementary",1,"LEASED",20,null,4,-3,11]
[null,"Surfside Elementary",2,"SBBC",40,null,0,2,32]
[null,"Tropical Elementary",0,"LEASED","-",null,6,-6,"-"]
[null,"Tropical Elementary",8,"SBBC",167,null,0,8,296]
[null,"John F. Turner Sr. Elementary",6,"LEASED",104,null,5,1,66]
[null,"John F. Turner Sr. Elementary",4,"SBBC",82,null,3,1,76]
[null,"University Park Elementary",4,"LEASED",76,null,12,-8,66]
[null,"University Park Elementary",7,"SBBC",122,null,1,6,198]
[null,"Ralph M. Williams Jr. Elementary",0,"LEASED","-",null,14,-14,"-"]
[null,"Ralph M. Williams Jr. Elementary",7,"SBBC",147,null,0,7,397]
[null,"John F. Kennedy Middle",0,"LEASED","-",null,1,-1,"-"]
[null,"John F. Kennedy Middle",2,"SBBC",44,null,1,1,46]
[null,"Astronaut High",3,"SBBC",72,null,1,2,90]
[null,"Astronaut High",0,"LEASED","-",null,2,-2,"-"]
[null,"Bayside Senior High",1,"SBBC",24,null,0,1,"-"]
[null,"Cocoa Beach Jr./Sr. High",4,"LEASED",92,null,10,-6,22]
[null,"Cocoa Beach Jr./Sr. High",10,"SBBC",239,null,2,8,261]
[null,"Cocoa Senior High",1,"SBBC",24,null,0,1,"-"]
[null,"Devereux South Pine Grove",12,"LEASED",276,null,0,12,102]
[null,"Eau Gallie Senior High",6,"LEASED",166,null,20,-14,8]
[null,"Eau Gallie Senior High",7,"SBBC",184,null,1,6,242]
[null,"Melbourne Senior High",0,"LEASED","-",null,5,-5,"-"]
[null,"Melbourne Senior High",1,"SBBC",24,null,0,1,40]
[null,"Merritt Island Senior High",1,"LEASED",23,null,12,-11,13]
[null,"Merritt Island Senior High",11,"SBBC",250,null,6,5,260]
[null,"Palm Bay Senior High",0,"LEASED","-",null,18,-18,"-"]
[null,"Palm Bay Senior High",15,"SBBC",376,null,1,14,480]
[null,"Rockledge Senior High",0,"LEASED","-",null,6,-6,"-"]
[null,"Rockledge Senior High",3,"SBBC",72,null,0,3,120]
[null,"Satellite Senior High",2,"SBBC",46,null,1,1,47]
[null,"Satellite Senior High",12,"LEASED",346,null,21,-9,45]
[null,"West Shore Jr/Sr High",0,"LEASED","-",null,4,-4,"-"]
[null,"West Shore Jr/Sr High",0,"SBBC","-",null,0,0,80]
["2c1.","BREVARD Total",341,null,7079,0,328,13,"Avg Age 21.1"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"Roy Allen Elementary",14,14,0,0,0,0,14]
[null,"Audubon Elementary",8,8,0,0,0,0,8]
[null,"Christa McAuliffe Elementary",4,1,1,1,1,0,4]
[null,"Cambridge Elementary",2,0,0,1,1,0,2]
[null,"Columbia Elementary",2,2,0,0,0,0,2]
[null,"Gemini Elementary",2,2,0,0,0,0,2]
[null,"Discovery Elementary",2,2,0,0,0,0,2]
[null,"Endeavour Elementary",2,0,0,1,1,0,2]
[null,"Fairglen Elementary",2,2,0,0,null,0,2]
[null,"Harbor City Elementary",2,0,0,0,1,1,2]
[null,"Indialantic Elementary",2,0,0,1,1,0,2]
[null,"John F. Turner Sr. Elementary",2,1,1,null,null,0,2]
[null,"Meadowlane Elementary",2,0,0,1,1,0,2]
[null,"Ocean Breeze Elementary",1,0,0,1,0,0,1]
[null,"Palm Bay Elementary",4,0,1,1,1,1,4]
[null,"Port Malabar Elementary",2,2,0,0,0,0,2]
[null,"Riverview Elementary",4,4,0,0,0,0,4]
[null,"Sabal Elementary",5,1,1,1,1,1,5]
[null,"South Lake Elementary",2,2,0,0,0,0,2]
[null,"Theodore Roosevelt Elementary",1,1,0,0,0,0,1]
[null,"Tropical Elementary",2,0,0,1,1,0,2]
[null,"University Park Elementary",1,1,0,0,0,0,1]
[null,"Devereux South Pine Grove",2,2,0,0,0,0,2]
[null,"Bayside Senior High",1,1,0,0,0,0,1]
[null,"Cocoa Beach Jr./Sr. High",4,4,0,0,0,0,4]
[null,"Eau Gallie Senior High",2,2,0,0,0,0,2]
[null,"UNITS ADDED TO OTHER SITES",-102,-26,-19,-19,-19,-19,77]
["2c2.","BREVARD Total",-25,26,-15,-10,-10,-16,154]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2000-01","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,"Roy Allen Elementary",10,"LEASED",200,3,0,0,0]
[null,"Hans Christian Anderson Elementary",0,"LEASED",0,0,1,21,5]
[null,"Audubon Elementary",6,"LEASED",116,3,1,22,5]
[null,"Cambridge Elementary",7,"LEASED",125,3,6,103,5]
[null,"Lewis Carroll Elementary",0,"LEASED",0,3,6,126,5]
[null,"Columbia Elementary",7,"LEASED",136,3,5,110,5]
[null,"Dr. W.J. Creel Elementary",0,"LEASED",0,0,1,17,5]
[null,"Discovery Elementary",9,"LEASED",176,3,5,110,5]
[null,"Endeavour Elementary",9,"LEASED",184,3,8,166,5]
[null,"Gardendale Elementary",12,"LEASED",221,3,13,231,5]
[null,"Gemini Elementary",6,"LEASED",117,3,8,157,5]
[null,"Golfview Elementary",1,"LEASED",16,3,0,0,0]
[null,"Harbor City Elementary",1,"LEASED",16,3,2,37,5]
[null,"Indialantic Elementary",10,"LEASED",200,3,8,160,5]
[null,"Jupiter Elementary",6,"LEASED",135,3,12,270,5]
[null,"Longleaf Elementary",0,"LEASED",0,3,14,308,5]
[null,"Christa McAuliffe Elementary",7,"LEASED",129,3,6,107,5]
[null,"Meadowlane Elementary",7,"LEASED",140,3,5,100,5]
[null,"Mila Elementary",3,"LEASED",58,3,5,80,5]
[null,"Mims Elementary",3,"LEASED",90,3,11,242,5]
[null,"Ocean Breeze Elementary",5,"LEASED",80,3,5,80,5]
[null,"Palm Bay Elementary",0,"LEASED",0,0,8,176,5]
[null,"Port Malabar Elementary",1,"LEASED",25,3,4,88,5]
[null,"Riverview Elementary",4,"LEASED",88,3,4,88,5]
[null,"Theodore Roosevelt Elementary",1,"LEASED",12,3,0,0,0]
[null,"Sabal Elementary",1,"LEASED",20,3,0,0,0]
[null,"Saturn Elementary ",1,"LEASED",21,3,2,42,5]
[null,"South Lake Elementary",1,"LEASED",25,3,2,47,5]
[null,"Suntree Elementary",4,"LEASED",76,0,8,152,5]
[null,"Surfside Elementary",1,"LEASED",20,3,4,80,5]
[null,"Tropical Elementary",0,"LEASED",0,0,6,132,5]
[null,"John F. Turner Sr. Elementary",6,"LEASED",104,3,5,90,5]
[null,"University Park Elementary",4,"LEASED",76,3,12,210,5]
[null,"Ralph M. Williams Jr. Elementary",0,"LEASED",0,0,14,308,5]
[null,"John F. Kennedy Middle",0,"LEASED",0,0,1,22,5]
[null,"Astronaut High",0,"LEASED",0,0,2,44,5]
[null,"Cocoa Beach Jr./Sr. High",4,"LEASED",92,3,10,220,5]
[null,"Eau Gallie Senior High",6,"LEASED",166,3,20,440,5]
[null,"Melbourne Senior High",0,"LEASED",0,0,5,110,5]
[null,"Merritt Island Senior High",1,"LEASED",23,3,12,265,5]
[null,"Palm Bay Senior High",0,"LEASED",0,0,14,352,5]
[null,"Rockledge Senior High",0,"LEASED",0,0,6,132,5]
[null,"Satellite Senior High",12,"LEASED",346,3,21,462,5]
["2c3.","BREVARD Total",156,null,3233,96,282,5907,195]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"Campus Primary- K-2\nTitusville (321)269-1234)",4,"Dr. Elaine Clifford",2000,80,75,2,140]
[null,"Educational Horizons-1-4\nRockledge, Rockledge",3,"Educational Horizons, Inc\nContact: Cindy Thomas",1998,78,64,2,78]
[null,"Educational Horizons-1-4\nRockledge, W.Melbourne",4,"Educational Horizons, Inc\nContact: Cindy Thomas",1999,78,34,2,75]
[null,"Explorer Elementary & Middle\nMelbourne",8,"Explorer Elementary \nSchool, Inc",1998,200,185,3,200]
[null,"Milestones Community- Elem\nPalm Bay",13,"Milestones Community\n Schools, Inc",1998,200,153,3,175]
[null,"Odyssey- K-6\nPalm Bay",7,"Constance MacPherson\nContact: Ace Young",1999,150,140,3,160]
[null,"Palm Bay Academy- Palm Bay",7,"Madhu Longani",1998,155,150,3,185]
[null,"Royal Palm-K-6\nPalm Bay",5,"Royal Pal Charter\nSchool, Inc. - contact\nCindy Thomas",1999,80,75,4,208]
[null,"Sculptor Elementary K-7\n- Titusville",8,"Brevard Innovative\nCharter Schools, Inc.",1998,286,286,3,330]
[null,"Stepping Stones K-4\nPalm Bay",null,"Milestones Community\n Schools, Inc",2001,100,null,5,100]
["2c4.","BREVARD Total",59,null,null,1407,1162,30,1651]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"Roy Allen Elementary",19,738,517,27.21,556,14,16.85]
[null,"Hans Christian Anderson Elementary",24,702,796,33.17,702,0,29.25]
[null,"Apollo Elementary",43,988,974,22.65,985,-13,32.83]
[null,"Atlantis Elementary",34,892,738,21.71,788,-2,24.63]
[null,"Audubon Elementary",34,703,673,19.79,792,5,20.31]
[null,"Cambridge Elementary",36,773,619,17.19,528,-20,33]
[null,"Cape View Elementary",34,748,469,13.79,407,-17,23.94]
[null,"Lewis Carroll Elementary",37,929,839,22.68,923,-8,31.83]
[null,"Challenger 7 Elementary ",28,732,564,20.14,404,-3,16.16]
[null,"Columbia Elementary",37,888,734,19.84,739,-12,29.56]
[null,"Coquina Elementary",28,595,537,19.18,467,-9,24.58]
[null,"Dr. W. J. Creel Elementary",21,1226,951,45.29,922,3,38.42]
[null,"Croton Elementary",30,628,484,16.13,435,-16,31.07]
[null,"Discovery Elementary",43,1033,994,23.12,1023,-14,35.28]
[null,"Endeavour Elementary",41,867,613,14.95,714,-11,23.8]
[null,"Enterprise Elementary",35,908,851,24.31,801,0,22.89]
[null,"Fairglen Elementary",42,920,860,20.48,785,-6,21.81]
[null,"Gardendale Elementary",42,874,639,15.21,650,-17,26]
[null,"Gemini Elementary",34,695,725,21.32,694,2,19.28]
[null,"Golfview Elementary",35,812,609,17.4,639,-9,24.58]
[null,"Harbor City Elementary",28,618,559,19.96,458,-13,30.53]
[null,"Spessard L. Holland Elementary",30,711,486,16.2,544,-6,22.67]
[null,"Imperial Estates Elementary",26,697,520,20,516,-3,22.43]
[null,"Indialantic Elementary",36,828,760,21.11,736,-8,26.29]
[null,"Jupiter Elementary",41,1023,855,20.85,769,-6,21.97]
[null,"Lockmar Elementary",45,1098,943,20.96,862,-2,20.05]
[null,"Longleaf Elementary",43,1129,1012,23.53,928,-4,23.79]
[null,"Christa McAuliffe Elementary",38,918,838,22.05,743,-12,28.58]
[null,"Meadowlane Elementary",42,1048,926,22.05,792,-9,24]
[null,"Mila Elementary",37,858,473,12.78,554,-14,24.09]
[null,"Mims Elementary",33,697,622,18.85,625,-5,22.32]
[null,"Oak Park Elementary",45,991,888,19.73,824,-15,27.47]
[null,"Ocean Breeze Elementary",34,668,587,17.26,513,-16,28.5]
[null,"Palm Bay Elementary",46,1012,656,14.26,723,-18,25.82]
[null,"Pinewood Elementary",25,707,480,19.2,443,-5,22.15]
[null,"Port Malabar Elementary",41,992,893,21.78,783,-8,23.73]
[null,"Riverview Elementary",30,703,375,12.5,448,-13,26.35]
[null,"Riviera Elementary",36,924,727,20.19,740,-2,21.76]
[null,"Theodore Roosevelt Elementary",32,798,691,21.59,469,-13,24.68]
[null,"Sabal Elementary",32,613,517,16.16,395,-18,28.21]
[null,"Saturn Elementary ",42,955,768,18.29,740,-14,26.43]
[null,"Sea Park Elementary",26,600,475,18.27,385,-12,27.5]
[null,"Sherwood Elementary",33,889,770,23.33,804,-1,25.13]
[null,"South Lake Elementary",33,733,504,15.27,492,-15,27.33]
[null,"Suntree Elementary",45,1088,993,34.24,840,0,18.67]
[null,"Surfside Elementary",29,630,568,12.91,566,-7,25.73]
[null,"Tropical Elementary",44,954,918,22.95,701,-17,25.96]
[null,"John F. Turner Sr. Elementary",40,910,717,21.09,656,-11,22.62]
[null,"University Park Elementary",34,850,551,16.21,466,-12,21.18]
[null,"Westside Elementary",34,940,868,25.53,904,3,24.43]
[null,"Ralph M. Williams Jr. Elementary",44,1150,933,21.2,930,4,19.38]
[null,"Freedom 7 Elementary",10,261,148,14.8,365,0,36.5]
[null,"West Melbourne Elementary",14,364,187,13.36,380,-9,76]
[null,"Robert L. Stevenson Elementary",12,225,145,12.08,222,6,12.33]
[null,"Central Middle ",59,1805,1113,18.86,1319,-2,23.14]
[null,"Clearlake Middle",39,960,668,17.13,672,-6,20.36]
[null,"DeLaura Middle",41,964,821,20.02,643,-15,24.73]
[null,"Edgewood Middle",34,882,454,13.35,497,-16,27.61]
[null,"Herbert C. Hoover Middle",32,762,526,16.44,617,-9,26.83]
[null,"Andrew Jackson Middle",33,799,662,20.06,644,-10,28]
[null,"Thomas Jefferson Middle",33,805,568,17.21,637,-11,28.95]
[null,"Lyndon B. Johnson Middle",41,1053,927,22.61,1079,-6,30.83]
[null,"John F. Kennedy Middle",30,724,583,19.43,619,-7,26.91]
[null,"Ronald McNair Middle",26,712,371,14.27,472,-7,24.84]
[null,"James Madison Middle",30,738,784,26.13,811,0,27.03]
[null,"Southwest Middle",61,1765,1358,22.26,1442,-1,24.03]
[null,"Space Coast Middle ",59,1805,1136,19.25,1395,0,23.64]
[null,"Stone Middle",49,1325,796,16.24,740,-13,20.56]
[null,"Astronaut High",60,1558,1468,24.47,1732,5,26.65]
[null,"Bayside High",80,2377,1347,16.84,2196,3,26.46]
[null,"Cocoa Beach Jr./Sr. High",57,1494,1203,21.11,1217,-1,21.73]
[null,"Cocoa Senior High",76,1794,1228,16.16,1581,-7,22.91]
[null,"Eau Gallie Senior High",91,2541,1980,21.76,2141,-10,26.43]
[null,"Melbourne Senior High",77,2128,2283,29.65,1928,-3,26.05]
[null,"Merritt Island Senior High",73,1927,1817,24.89,1797,-7,27.23]
[null,"Palm Bay Senior High",93,2504,1982,21.31,1876,-29,29.31]
[null,"Rockledge Senior High",51,1373,1463,28.69,1466,4,26.65]
[null,"Satellite Senior High",74,1970,1802,24.35,1884,-2,26.17]
[null,"Titusville High ",90,2256,2157,23.97,2196,0,24.4]
[null,"West Shore Jr./Sr. High",43,1099,684,15.91,913,3,19.85]
[]
["2e.","BREVARD Total",3269,82353,66720,"District Avg 20",67784,-555,"District Avg 25"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR AVERAGE"]
[null,"Hans Christian Anderson Elementary",null,21,21,21,21,21,21]
[null,"Cambridge Elementary",null,219,219,197,175,175,197]
[null,"Lewis Carroll Elementary",null,208,208,208,230,252,221.2]
[null,"Columbia Elementary",null,196,196,174,174,152,178.4]
[null,"Dr. W. J. Creel Elementary",null,17,17,17,17,17,17]
[null,"Discovery Elementary",null,216,216,216,238,238,224.8]
[null,"Endeavour Elementary",null,204,204,182,160,160,182]
[null,"Fairglen Elementary",null,20,20,20,42,42,28.8]
[null,"Gardendale Elementary",null,231,231,231,231,231,231]
[null,"Gemini Elementary",null,113,113,113,113,113,113]
[null,"Golfview Elementary",null,16,16,16,16,16,16]
[null,"Harbor City Elementary",null,79,79,79,57,35,65.8]
[null,"Indialantic Elementary",null,220,220,198,176,176,198]
[null,"Jupiter Elementary",null,135,157,201,223,267,196.6]
[null,"Longleaf Elementary",null,147,191,235,279,301,230.6]
[null,"Christa McAuliffe Elementary",null,195,173,151,129,129,155.4]
[null,"Meadowlane Elementary",null,140,140,120,100,100,120]
[null,"Mila Elementary",null,78,78,100,100,100,91.2]
[null,"Mims Elementary",null,247,269,291,291,291,277.8]
[null,"Ocean Breeze Elementary",null,96,96,74,74,74,82.8]
[null,"Palm Bay Elementary",null,227,205,183,161,139,183]
[null,"Port Malabar Elementary",null,105,105,105,105,105,105]
[null,"Riverview Elementary",null,0,0,0,0,0,0]
[null,"Theodore Roosevelt Elementary",null,0,0,0,0,0,0]
[null,"Sabal Elementary",null,96,74,52,30,22,54.8]
[null,"Saturn Elementary ",null,42,42,42,42,42,42]
[null,"South Lake Elementary",null,63,63,63,63,63,63]
[null,"Suntree Elementary",null,139,139,139,161,161,147.8]
[null,"Surfside Elementary",null,60,60,82,82,82,73.2]
[null,"Tropical Elementary",null,167,167,145,123,123,145]
[null,"John F. Turner Sr. Elementary",null,170,154,154,154,154,157.2]
[null,"University Park Elementary",null,198,220,220,242,242,224.4]
[null,"Ralph M. Williams Jr. Elementary",null,189,233,255,299,299,255]
[null,"John F. Kennedy Middle",null,44,44,44,44,44,44]
[null,"Astronaut High",null,72,75,75,75,75,74.4]
[null,"Cocoa Beach Jr./Sr. High",null,239,239,261,261,283,256.6]
[null,"Eau Gallie Senior High",null,350,394,438,482,526,438]
[null,"Melbourne Senior High",null,24,46,68,90,112,68]
[null,"Merritt Island Senior High",null,273,295,339,383,427,343.4]
[null,"Palm Bay Senior High",null,376,398,420,442,464,420]
[null,"Rockledge Senior High",null,72,94,94,116,138,102.8]
[null,"Satellite Senior High",null,392,436,480,524,568,480]
[null,"Westshore Jr/Sr High",null,44,44,66,88,88]
["2f.","BREVARD Total students in relocatables by year",null,6140,6391,6569,6813,7047,6592]
[null,"Total number of CO-FTE students projected by year",null,68122,68615,68711,68700,68622,68554]
[null,"Percent in relocatables by year",null,0.09,0.09,0.1,0.1,0.1,0.1]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","BREVARD Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","BREVARD Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","BREVARD Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","BREVARD Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":5},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","BREVARD Total 2005-06",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","BREVARD 5-Year Total",null,0,0,0]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,34658398,35178273.97,35705948.07955,36241537.300743245,36785160.36025439,178569317.71054763]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,34658398,35178273.97,35705948.07955,36241537.300743245,36785160.36025439,178569317.71054763,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,2112600,2100000,2100000,2100000,2100000,10512600,0.06]
[null,"  less amount used to purchase other vehicles",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase capital outlay equipment",null,500000,500000,500000,500000,500000,2500000,0.01]
[null,"  less amount used to correct environmental problems",null,null,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,null,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,5750000,5500000,5250000,0,0,16500000,0.09]
[null,"  less amount to pay debt service for COP's ",null,13331138,13329578,13328953,13331138,13329578,66650385,0.37]
[null,"  less other (please be specific)",null,null,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,12964660,13748695.969999999,14526995.079549998,20310399.300743245,20855582.360254392,82406332.71054763,0.46,0.8]
[null,"P E C O New Construction",null,3939402,4147669,2456972,2096422,2181517,14821982,null,0.14]
[null,"C O & D S   Bond Proceeds  ",null,320080,250000,250000,250000,250000,1320080,null,0.01]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,0,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,null,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Other State",null,100000,0,0,0,0,100000]
[null,"Interest - CO & DS Loans",null,60000,60000,60000,60000,60000,300000]
[null,"Interest",null,500000,500000,500000,500000,500000,2500000]
[null,"Property Sales",null,200000,200000,200000,200000,200000,1000000]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","BREVARD Total",null,18084142,18906364.97,17993967.079549998,23416821.300743245,24047099.360254392,102448394.71054763,0.99,0.9500000000000001]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Fire Safety, ADA, & Asbestos",0,250000,250000,250000,250000,250000,1250000]
[null,"Major Maintenance",0,1400000,1500000,1500000,1500000,1500000,7400000]
[null,"Paving",0,350000,500000,500000,500000,500000,2350000]
[null,"Renovate / Site Improvements",0,5400000,5000000,5000000,5000000,5000000,25400000]
[null,"Health & Safety",0,3750000,4000000,4000000,4000000,4000000,19750000]
[null,"Portable Lease",0,750000,1058535,1307070,2068470,2068470,7252545]
[null,"Portable Renovation & Repair",0,800000,0,0,0,0,800000]
[null,"Portable Relocation",0,250000,250000,250000,250000,250000,1250000]
[null,"Replacement Portable Infrastructure",0,0,2405050,1386897,2802000,0,6593947]
[null,"Noise Attenuation Improvements @ 5 MS Gyms",null,210775,0,0,0,0,210775]
[null,"Other projects- districtwide",0,1523367,1142780,1000000,4246351,7678629,15591127]
[null,"School/Portable Furniture Replacement",null,600000,600000,600000,600000,600000,3000000]
[null,"HVAC Upgrades/Replacements",0,2800000,2200000,2200000,2200000,2200000,11600000]
["5.","BREVARD Total",0,18084142,18906365,17993967,23416821,24047099,102448394]
[{"$nulls":7},84364252]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","BREVARD Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Renovate / Site Improvements",0,0,0,0,0,0,0]
[null,"Portable Replacement (5 year)",0,0,0,1018153,0,0,1018153]
[null,"HVAC Upgrades/Replacements",null,0,0,0,null,null,0]
[null,"Hans Christian Anderson Elementary",0,0,0,0,1332820,0,1332820]
[null,"Apollo Elementary",0,0,0,0,0,1253510,1253510]
[null,"Audubon Elementary",0,0,1046480,0,0,0,1046480]
[null,"Cambridge Elementary",0,0,0,1418310,0,0,1418310]
[null,"Cape View Elementary",0,0,0,0,0,1791170,1791170]
[null,"Challenger 7 Elementary ",0,0,0,1851940,0,0,1851940]
[null,"Columbia Elementary",0,0,0,0,1906530,0,1906530]
[null,"Coquina Elementary",0,0,0,0,0,1372990,1372990]
[null,"Dr. W. J. Creel Elementary",0,0,0,2037340,0,0,2037340]
[null,"Croton Elementary",0,0,0,0,0,2686240,2686240]
[null,"Discovery Elementary",0,0,0,0,0,322390,322390]
[null,"Endeavour Elementary",0,0,0,0,376980,0,376980]
[null,"Gardendale Elementary",0,0,2338100,0,0,0,2338100]
[null,"Golfview Elementary",0,0,0,150000,0,0,150000]
[null,"Harbor City Elementary",0,0,0,0,1970390,0,1970390]
[null,"Lockmar Elementary",0,0,0,1046480,0,0,1046480]
[null,"Christa McAuliffe Elementary",0,0,0,0,1906530,0,1906530]
[null,"Mila Elementary",0,0,0,0,0,886830,886830]
[null,"Mims Elementary",0,0,0,0,0,1715980,1715980]
[null,"Oak Park Elementary",0,0,1496590,0,0,0,1496590]
[null,"Ocean Breeze Elementary",0,0,0,1294710,0,0,1294710]
[null,"Pinewood Elementary",0,0,0,0,250000,0,250000]
[null,"Port Malabar Elementary",0,0,0,1294710,0,0,1294710]
[null,"Riverview Elementary",0,0,0,0,300000,0,300000]
[null,"Theodore Roosevelt Elementary",0,0,0,0,0,2030130,2030130]
[null,"Sabal Elementary",0,0,1377110,0,0,0,1377110]
[null,"Saturn Elementary ",0,0,0,0,0,1767480,1767480]
[null,"Sea Park Elementary",0,0,1377110,0,0,0,1377110]
[null,"South Lake Elementary",0,0,0,0,637570,0,637570]
[null,"Surfside Elementary",0,0,1400000,0,0,0,1400000]
[null,"Tropical Elementary",0,0,0,1541910,0,0,1541910]
[null,"John F. Turner Sr. Elementary",0,0,0,0,822970,0,822970]
[null,"University Park Elementary",0,0,0,0,1014550,0,1014550]
[null,"DeLaura Middle",0,0,0,2532770,0,0,2532770]
[null,"Edgewood Middle",0,0,0,2656370,0,0,2656370]
[null,"Herbert C. Hoover Middle",0,0,0,1665510,0,0,1665510]
[null,"Andrew Jackson Middle",0,0,0,0,0,2030130,2030130]
[null,"Thomas Jefferson Middle",0,0,0,1665510,0,null,1665510]
[null,"Lyndon B. Johnson Middle",0,0,0,0,0,2030130,2030130]
[null,"John F. Kennedy Middle",0,0,0,0,0,477920,477920]
[null,"Ronald McNair Middle",0,0,1256600,0,0,0,1256600]
[null,"James Madison Middle",0,0,0,0,0,2160940,2160940]
[null,"Southwest Middle",0,0,0,2532770,0,0,2532770]
[null,"Astronaut High",0,0,0,0,5132490,0,5132490]
[null,"Cocoa Beach Jr./Sr. High",0,0,2698600,0,0,0,2698600]
[null,"Melbourne Senior High",0,0,0,0,0,835330,835330]
[null,"Merritt Island Senior High",0,0,4862630,0,0,0,4862630]
[null,"Palm Bay Senior High",0,0,3060130,0,0,0,3060130]
[null,"Rockledge Senior High",0,0,0,0,1843700,0,1843700]
[null,"Satellite Senior High",0,0,3060130,0,0,0,3060130]
[null,"Titusville High ",0,0,800000,0,0,0,800000]
[null,"Rockedge Center",0,0,0,0,0,1000000,1000000]
[null,"Remodel/Renovate Projects",{"$nulls":6},0]
[null,"Hans Christian Anderson Elementary",-24,0,0,0,0,3285720,3285720]
[null,"Apollo Elementary",-195,0,0,0,0,3133896,3133896]
[null,"Atlantis Elementary",-29,0,0,0,0,180845,180845]
[null,"Audubon Elementary",-277,0,0,0,0,2417058,2417058]
[null,"Cambridge Elementary",-361,0,0,0,0,1776670,1776670]
[null,"Cape View Elementary",-283,0,0,0,0,3214320,3214320]
[null,"Columbia Elementary",-225,0,0,0,0,336265,336265]
[null,"Coquina Elementary",-24,0,0,0,0,2684383,2684383]
[null,"Dr. W. J. Creel Elementary",-324,0,0,0,0,3152284,3152284]
[null,"Croton Elementary",-233,0,0,0,0,2916154,2916154]
[null,"Devereux South Pine Grove",null,0,0,0,0,542315,542315]
[null,"Discovery Elementary",-276,0,0,0,0,275834,275834]
[null,"Endeavour Elementary",-246,0,0,0,0,770243,770243]
[null,"Enterprise Elementary",-151,0,0,0,0,173864,173864]
[null,"Fairglen Elementary",-67,0,0,0,0,562264,562264]
[null,"Gardendale Elementary",-459,0,0,0,0,3037781,3037781]
[null,"Gemini Elementary",-116,0,0,0,0,150000,150000]
[null,"Golfview Elementary",-200,0,0,0,0,1864109,1864109]
[null,"Harbor City Elementary",-245,0,0,0,0,2876985,2876985]
[null,"Spessard L. Holland Elementary",-156,0,0,0,0,975535,975535]
[null,"Imperial Estates Elementary",-73,0,0,0,0,331395,331395]
[null,"Indialantic Elementary",-327,0,0,0,0,1640194,1640194]
[null,"Jupiter Elementary",-141,0,0,0,0,242762,242762]
[null,"Lockmar Elementary",-56,0,0,0,0,2965289,2965289]
[null,"Christa McAuliffe Elementary",-244,0,0,0,0,472496,472496]
[null,"Meadowlane",-198,0,0,0,0,185185,185185]
[null,"Mila Elementary",-223,0,0,0,0,2864064,2864064]
[null,"Mims Elementary",-298,0,0,0,0,1992074,1992074]
[null,"Oak Park Elementary",-207,0,0,0,0,3407510,3407510]
[null,"Ocean Breeze Elementary",-210,0,0,0,0,3073581,3073581]
[null,"Palm Bay Elementary",-411,0,0,0,0,2739961,2739961]
[null,"Pinewood Elementary",-198,0,0,0,0,1878437,1878437]
[null,"Port Malabar Elementary",-170,0,0,0,0,1013908,1013908]
[null,"Riverview Elementary",-386,0,0,0,0,3068225,3068225]
[null,"Riviera Elementary",-58,0,0,0,0,269585,269585]
[null,"Theodore Roosevelt Elementary",-110,0,0,0,0,4238285,4238285]
[null,"Sabal Elementary",-266,0,0,0,0,3000295,3000295]
[null,"Saturn Elementary ",-305,0,0,0,0,3527729,3527729]
[null,"Sea Park Elementary",-215,0,0,0,0,2566839,2566839]
[null,"South Lake Elementary",-410,0,0,0,0,2992039,2992039]
[null,"Suntree Elementary",-6,0,0,0,0,216790,216790]
[null,"Surfside Elementary",-260,0,0,0,0,2537743,2537743]
[null,"Tropical Elementary",-279,0,0,0,0,3214419,3214419]
[null,"John F. Turner Sr. Elementary",-210,0,0,0,0,2023273,2023273]
[null,"University Park Elementary",-213,0,0,0,0,809903,809903]
[null,"Central Middle",-60,0,0,0,0,237331,237331]
[null,"Clearlake Middle",-304,0,0,0,0,459785,459785]
[null,"DeLaura Middle",-388,0,0,0,0,5065043,5065043]
[null,"Edgewood Middle",-431,0,0,0,0,4871800,4871800]
[null,"Herbert C. Hoover Middle",-102,0,0,0,0,4900650,4900650]
[null,"Andrew Jackson Middle",-151,0,0,0,0,5019400,5019400]
[null,"Thomas Jefferson Middle",-175,0,0,0,0,5369775,5369775]
[null,"Lyndon B. Johnson Middle",-111,0,0,0,0,5560060,5560060]
[null,"John F. Kennedy Middle",-69,0,0,0,0,5897250,5897250]
[null,"Ronald McNair Middle",-109,0,0,0,0,1953537,1953537]
[null,"James Madison Middle",-242,0,0,0,0,5382900,5382900]
[null,"Southwest Middle",-46,0,0,0,0,266008,266008]
[null,"Space Coast Middle School",-33,0,0,0,0,68999,68999]
[null,"Stone Middle",-399,0,0,0,0,2254621,2254621]
[null,"Astronaut High",-65,0,0,0,0,5783311,5783311]
[null,"Cocoa Beach Jr./Sr. High",-172,0,0,0,0,2665430,2665430]
[null,"Cocoa Senior High",-223,0,0,0,0,1251275,1251275]
[null,"Eau Gallie Senior High",-413,0,0,0,0,8513894,8513894]
[null,"Melbourne Senior High",-44,0,0,0,0,4146459,4146459]
[null,"Merritt Island Senior High",-357,0,0,0,0,10375966,10375966]
[null,"Palm Bay Senior High",-759,0,0,0,0,8076106,8076106]
[null,"Rockledge Senior High",-23,0,0,0,0,3851522,3851522]
[null,"Satellite Senior High",-448,0,0,0,0,11092395,11092395]
[null,"Titusville High ",4,0,0,0,0,7555183,7555183]
[null,"West Shore Jr./Sr. High",0,0,0,0,0,1058850,1058850]
[null,"Rockledge Center",0,0,0,0,0,40000,40000]
[null,"Classroom Additions"]
[null,"Gardendale Elementary",245,0,0,0,0,1602920.34,1602920.34]
[null,"Gemini Elementary",120,0,0,0,0,1068613.56,1068613.56]
[null,"Indialantic Elementary",235,0,0,0,0,1068613.56,1068613.56]
[null,"Mims Elementary",240,0,0,0,0,1602920.34,1602920.34]
[null,"Ocean Breeze Elementary",50,0,0,0,0,329347.83,329347.83]
[null,"Palm Bay Elementary",75,0,0,0,0,486954.195,486954.195]
[null,"Riverview Elementary",125,0,0,0,0,1068613.56,1068613.56]
[null,"Saturn Elementary ",100,0,0,0,0,658695.66,658695.66]
[null,"Surfside Elementary",210,0,0,0,0,1317391.32,1317391.32]
[null,"South Lake Elementary",150,0,0,0,0,959773.29,959773.29]
[null,"Clearlake Middle",91,0,0,0,0,0,0]
[null,"DeLaura Middle",56,0,0,0,0,929874.7392000002,929874.7392000002]
[null,"Edgewood Middle",91,0,0,0,0,1571044.1472000002,1571044.1472000002]
[null,"Hoover Middle School",56,0,0,0,0,929874.7392000002,929874.7392000002]
[null,"Andrew Jackson Middle",56,0,0,0,0,929874.7392000002,929874.7392000002]
[null,"Thomas Jefferson Middle",56,0,0,0,0,929874.7392000002,929874.7392000002]
[null,"Lyndon B. Johnson Middle",99,0,0,0,0,1342873.8048000003,1342873.8048000003]
[null,"John F. Kennedy Middle",56,0,0,0,0,929874.7392000002,929874.7392000002]
[null,"James Madison Middle",259,0,0,0,0,2980900.4544000006,2980900.4544000006]
[null,"Ronald McNair Middle",28,0,0,0,0,505234.32960000006,505234.32960000006]
[null,"Astronaut High",229,0,0,0,0,3611484.8932000003,3611484.8932000003]
[null,"Cocoa Beach Jr./Sr. High ",240,0,0,0,0,547680.4608000001,547680.4608000001]
[null,"Cocoa Senior High",28,0,0,0,0,548951.9308000001,548951.9308000001]
[null,"Eau Gallie Senior High",102,0,0,0,0,1245601.3148,1245601.3148]
[null,"Merritt Island Senior High",394,0,0,0,0,1317017.6064000002,1317017.6064000002]
[null,"Rockledge Senior High",192,0,0,0,0,1669623.384,1669623.384]
[null,"Satellite Senior High",490,0,0,0,0,5302124.5156000005,5302124.5156000005]
[null,"West Shore Jr./Sr. High",56,0,0,0,0,821520.6912000001,821520.6912000001]
[null,"New Additions\n (expand core & equity per facility list)"]
[null,"Apollo Elementary",0,0,0,0,0,1799822,1799822]
[null,"Audubon Elementary",0,0,0,0,0,2946461.595,2946461.595]
[null,"Cambridge Elementary",0,0,0,0,0,2659802,2659802]
[null,"Cape View Elementary",0,0,0,0,0,2319005,2319005]
[null,"Coquina Elementary",0,0,0,0,0,2241261,2241261]
[null,"Croton Elementary",0,0,0,0,0,2055809,2055809]
[null,"Endeavour Elementary",0,0,0,0,0,2354625,2354625]
[null,"Gardendale Elementary",0,0,0,0,0,2492866.236,2492866.236]
[null,"Golfview Elementary",0,0,0,0,0,1813675,1813675]
[null,"Harbor City Elementary",0,0,0,0,0,2252145,2252145]
[null,"Spessard L. Holland Elementary",0,0,0,0,0,1432592,1432592]
[null,"Imperial Estates Elementary",0,0,0,0,0,956805,956805]
[null,"Indialantic Elementary",0,0,0,0,0,3291499.386,3291499.386]
[null,"Lockmar Elementary",0,0,0,0,0,1941739,1941739]
[null,"Mila Elementary",0,0,0,0,0,2263595,2263595]
[null,"Oak Park Elementary",0,0,0,0,0,1361351,1361351]
[null,"Ocean Breeze Elementary",0,0,0,0,0,2645808.018,2645808.018]
[null,"Palm Bay Elementary",0,0,0,0,0,2502760.806,2502760.806]
[null,"Pinewood Elementary",0,0,0,0,0,725413,725413]
[null,"Port Malabar Elementary",0,0,0,0,0,1941739,1941739]
[null,"Riverview Elementary",0,0,0,0,0,187996.43999999994,187996.43999999994]
[null,"Theodore Roosevelt Elementary",0,0,0,0,0,146157,146157]
[null,"Sabal Elementary",0,0,0,0,0,2419646,2419646]
[null,"Saturn Elementary ",0,0,0,0,0,725413.332,725413.332]
[null,"Sea Park Elementary",0,0,0,0,0,2863489,2863489]
[null,"South Lake Elementary",0,0,0,0,0,2192919.71,2192919.71]
[null,"Surfside Elementary",0,0,0,0,0,3202165.554,3202165.554]
[null,"Tropical Elementary",0,0,0,0,0,2636620,2636620]
[null,"John F. Turner Sr. Elementary",0,0,0,0,0,2207620,2207620]
[null,"University Park Elementary",0,0,0,0,0,3448964,3448964]
[null,"Clearlake Middle",0,0,0,0,0,2124355,2124355]
[null,"DeLaura Middle",0,0,0,0,0,1443347.5584000002,1443347.5584000002]
[null,"Edgewood Middle",0,0,0,0,0,1192445.8527999998,1192445.8527999998]
[null,"Herbert C. Hoover Middle",0,0,0,0,0,1447003.2607999998,1447003.2607999998]
[null,"Andrew Jackson Middle",0,0,0,0,0,967029.2607999998,967029.2607999998]
[null,"Thomas Jefferson Middle",0,0,0,0,0,1447003.2607999998,1447003.2607999998]
[null,"Lyndon B. Johnson Middle",0,0,0,0,0,2270718.1952,2270718.1952]
[null,"John F. Kennedy Middle",0,0,0,0,0,1447003.2607999998,1447003.2607999998]
[null,"James Madison Middle",0,0,0,0,0,585457,585457]
[null,"Ronald McNair Middle",0,0,0,0,0,1010598.6704,1010598.6704]
[null,"Stone Middle",0,0,0,0,0,277042,277042]
[null,"Astronaut High",0,0,0,0,0,1564153.1067999997,1564153.1067999997]
[null,"Bayside High School",0,0,0,0,0,2072435,2072435]
[null,"Cocoa Beach Jr./Sr. High",0,0,0,0,0,4693042.7916,4693042.7916]
[null,"Cocoa High School",0,0,0,0,0,4840156.0692,4840156.0692]
[null,"Palm Bay High",0,0,0,0,0,1769842.4832000004,1769842.4832000004]
[null,"Rocklegde High",0,0,0,0,0,58378.61599999992,58378.61599999992]
[null,"Satellite Senior High",0,0,0,0,0,6268871.4843999995,6268871.4843999995]
[null,"West Shore Jr./Sr. High",0,0,0,0,0,3080105.3087999998,3080105.3087999998]
[{"$nulls":8},0]
["7.","BREVARD Total",-10356,0,24773480,22706483,17494530,356543254.14079994,421517747.1408]
[null,null,"."]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this 10 day of October, 2001."]
[]
[null,"SCHOOL BOARD OF ","BREVARD  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"RICHARD A. DIPATRI, Ed.D."]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"B. EUGENE BURKETT",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"ED CURRY","ASSISTANT SUPERINTENDENT, FACILITIES (321)633-1000 x450",null,null,"currye@brevard.k12.fl.us",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]
[]
["DISTRICT REVIEWER:  _________________________________________________________________________________________________________________________________________________",null,null,"ANIBAL E. CAUSSADE","FACILITY PLANNER","(321)633-1000 X 657",null,"caussadea@brevard.k12.fl.us"]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address"]
[]
["DOCUMENT PREPARED BY:  BRPH COMPANIES"]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}