{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["5YrWkPlan - 99"],"not_rendered":{"charts":0,"images":1,"macros":0,"external_links":1,"defined_names":3,"comments":90,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"5YrWkPlan - 99","index":0,"n_rows":1347,"n_cols":25,"rows_kept":1347,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[null,"            SCHOOL DISTRICT FACILITIES WORK PROGRAM -- WORKSHEET"]
["BREVARD   SCHOOL  DISTRICT"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":23},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 1999, and all data accurate as of December 3, 1999.",{"$nulls":23},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"BREVARD ","Date: ==>","1999-12-10",null,"For fiscal years","1999-2004"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment.  (See Note)"]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":10}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-04"]
[null,"Project","Location","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","Estimated Cost","5 YEAR TOTAL"]
[null,"Fire Safety & ADA","Various",280321,294337.05,309053.9025,324506.59762500005,340731.9275062501,1548950.4776312502]
[null,"Major Maintenance","Various",1565232,1565250,1565250,1565250,1565250,7826232]
[null,"Paving","Various",545842,546000,546000,546000,546000,2729842]
[null,"Renovate / Site Improvements","Various",4489309,4500000,4500000,4500000,4500000,22489309]
[null,"Roofing Repairs","Various",2162900,500000,500000,500000,500000,4162900]
[null,"Maintenance Projects","Various",2504681,2500000,2500000,2500000,2500000,12504681]
[null,"Re-roofing Projects"]
[null,null,"Eau Gallie Senior High + HVAC Replacement",5126305,0,0,0,0,5126305]
[null,null,"Melbourne High",945194,0,0,0,0,945194]
[null,null,"Riverview Elementary",554760,0,0,0,0,554760]
[null,null,"Rockledge  High (Partial)",785494,0,0,0,0,785494]
[null,null,"Rockledge Elementary",157335,0,0,0,0,157335]
[null,null,"Capeview Elementary",919125,0,0,0,0,919125]
[null,null,"DeLaura Jr. High",926959,0,0,0,0,926959]
[null,null,"Devereux South Pine Grove",133685,0,0,0,0,133685]
[null,null,"Dr. W. J. Creel Elementary",350135,0,0,0,0,350135]
[null,null,"Apollo Elementary (Partial)",152382,0,0,0,0,152382]
[null,null,"Coquina Elementary (Partial)",166289,0,0,0,0,166289]
[null,null,"Gardendale Elementary (Partial)",92671,0,0,0,0,92671]
[null,null,"Surfside Elementary (Partial)",228648,0,0,0,0,228648]
[null,null,"Fairglen Elementary (Partial)",136421,0,0,0,0,136421]
[null,null,"Oak Park Elementary (Partial)",149039,0,0,0,0,149039]
[null,null,"Pinewood Elementary (Partial)",107331,0,0,0,0,107331]
[null,null,"Tropical Elementary (Partial)",16099,0,0,0,0,16099]
[null,null,"Kennedy Middle (Partial)",1541554,0,0,0,0,1541554]
[null,null,"Edgewood Middle (Partial)",1062580,0,0,0,0,1062580]
[null,null,"Ronald McNair Middle (Partial)",937,0,0,0,0,937]
[null,null,"Golfview Elementary (Partial)",1059582,0,0,0,0,1059582]
[null,null,"Stone Middle (Partial) ",133997,0,0,0,0,133997]
[null,null,"Astronaut High (Partial)",201770,0,0,0,0,201770]
[null,null,"Cocoa Beach Jr./Sr. High (Partial)",7053,0,0,0,0,7053]
[null,null,"Merritt Island Senior High (Partial)",87174,0,0,0,0,87174]
[null,null,"Satellite High (Partial)",218276,0,0,0,0,218276]
[null,null,"Titusville High (Partial) ",4324,0,0,0,0,4324]
[null,null,"West Shore Jr./Sr. High (Partial)",176028,0,0,0,0,176028]
[null,null,"West Melbourne Elementary",1090422,0,0,0,0,1090422]
[null,null,"Whispering Hills",454899,0,0,0,0,454899]
[null,null,"Freedom 7 Elementary",570327,0,0,0,0,570327]
[null,"Safety to Life ","Various",288031,311016,317156,331572,349122,1596897]
[null,"Health & Safety","Various",5168498,5200000,5200000,5200000,5200000,25968498]
[null,"Portable Lease","Various",821491,830000,750000,400000,100000,2901491]
[null,"Portable Renovation & Repair","Various",262332,250000,150000,100000,50000,812332]
[null,"Portable Relocation","Various",251084,250000,250000,150000,150000,1051084]
[null,"HVAC Upgrades/Replacements","Various",2200000,0,0,0,0,2200000]
[null,null,"Roy Allen Elementary",0,null,1400000,0,0,1400000]
[null,null,"Hans Christian Anderson Elementary",0,0,0,1202000,0,1202000]
[null,null,"Apollo Elementary",0,1030000,0,0,0,1030000]
[null,null,"Atlantis Elementary",0,0,0,0,1176000,1176000]
[null,null,"Audubon Elementary",0,null,963000,0,0,963000]
[null,null,"Cambridge Elementary",0,0,0,1322000,0,1322000]
[null,null,"Cape View Elementary",0,1494000,0,0,0,1494000]
[null,null,"Lewis Carroll Elementary",0,0,0,0,0,0]
[null,null,"Central Pine Grove School",0,0,0,0,0,0]
[null,null,"Challenger 7 Elementary ",0,0,0,1743000,0,1743000]
[null,null,"Columbia Elementary",0,0,0,1743000,0,1743000]
[null,null,"Coquina Elementary",0,1133000,0,0,0,1133000]
[null,null,"Dr. W. J. Creel Elementary",0,0,1867000,0,0,1867000]
[null,null,"Croton Elementary",0,2266000,0,0,0,2266000]
[null,null,"Discovery Elementary",0,0,0,0,248000,248000]
[null,null,"Endeavour Elementary",0,0,0,0,310000,310000]
[null,null,"Enterprise Elementary",0,0,0,0,1176000,1176000]
[null,null,"Fairglen Elementary",0,0,0,0,0,0]
[null,null,"Gardendale Elementary",0,0,2217000,0,0,2217000]
[null,null,"Gemini Elementary",0,0,0,0,0,0]
[null,null,"Golfview Elementary",0,0,0,1082000,0,1082000]
[null,null,"Harbor City Elementary",0,0,0,0,1857000,1857000]
[null,null,"Spessard L. Holland Elementary",0,0,0,0,0,0]
[null,null,"Imperial Estates Elementary",0,0,0,0,338000,338000]
[null,null,"Indialantic Elementary",0,0,0,0,506000,506000]
[null,null,"Jupiter Elementary",0,0,0,0,0,0]
[null,null,"Lockmar Elementary",0,0,0,962000,0,962000]
[null,null,"Longleaf Elementary",0,0,0,0,0,0]
[null,null,"Christa McAuliffe Elementary",0,0,0,1743000,0,1743000]
[null,null,"Meadowlane Elementary",0,0,0,0,0,0]
[null,null,"Mila Elementary",0,0,0,0,805000,805000]
[null,null,"Mims Elementary",0,0,0,0,1609000,1609000]
[null,null,"Oak Park Elementary",0,0,1400000,0,0,1400000]
[null,null,"Ocean Breeze Elementary",0,0,1167000,0,0,1167000]
[null,null,"Palm Bay Elementary",0,0,0,0,0,0]
[null,null,"Pinewood Elementary",0,0,0,721000,0,721000]
[null,null,"Port Malabar Elementary",0,0,0,1623000,0,1623000]
[null,null,"Riverview Elementary",0,0,0,1623000,0,1623000]
[null,null,"Riviera Elementary",0,0,0,0,1176000,1176000]
[null,null,"Theodore Roosevelt Elementary",0,1700000,0,0,0,1700000]
[null,null,"Sabal Elementary",0,1246000,0,0,0,1246000]
[null,null,"Saturn Elementary ",0,1473000,0,0,0,1473000]
[null,null,"Sea Park Elementary",0,0,1284000,0,0,1284000]
[null,null,"Sherwood Elementary",0,0,0,0,0,0]
[null,null,"South Lake Elementary",0,0,0,0,563000,563000]
[null,null,"Devereux South Pine Grove School",0,0,0,0,0,0]
[null,null,"Suntree Elementary",0,0,0,0,0,0]
[null,null,"Surfside Elementary",0,0,1400000,0,0,1400000]
[null,null,"Tropical Elementary",0,0,0,1442000,0,1442000]
[null,null,"John F. Turner Sr. Elementary",0,0,0,721000,0,721000]
[null,null,"University Park Elementary",0,0,0,0,929000,929000]
[null,null,"Westside Elementary",0,0,0,0,0,0]
[null,null,"Freedom 7 Elementary",0,0,0,0,0,0]
[null,null,"West Melbourne Elementary",0,0,0,0,0,0]
[null,null,"Robert L. Stevenson Elementary",0,0,0,0,0,0]
[null,null,"Whispering Hills",0,0,0,0,0,0]
[null,null,"Central Middle ",0,0,0,0,0,0]
[null,null,"Clearlake Middle",0,0,0,0,450000,450000]
[null,null,"DeLaura Middle",0,0,2334000,0,0,2334000]
[null,null,"Edgewood Middle",0,0,2451000,0,0,2451000]
[null,null,"Herbert C. Hoover Middle",0,0,1517000,0,0,1517000]
[null,null,"Andrew Jackson Middle",0,1700000,0,0,0,1700000]
[null,null,"Thomas Jefferson Middle",0,0,1517000,0,0,1517000]
[null,null,"Lyndon B. Johnson Middle",0,1700000,0,0,0,1700000]
[null,null,"John F. Kennedy Middle",0,0,0,0,394000,394000]
[null,null,"Ronald McNair Middle",0,1133000,0,0,0,1133000]
[null,null,"James Madison Middle",0,1813000,0,0,0,1813000]
[null,null,"Southwest Middle",0,0,0,2404000,0,2404000]
[null,null,"Space Coast Middle ",0,0,0,0,0,0]
[null,null,"Stone Middle",1617359,0,0,0,0,1617359]
[null,null,"Astronaut High",0,0,0,4928000,0,4928000]
[null,null,"Bayside High",0,0,0,0,0,0]
[null,null,"Cocoa Beach Jr./Sr. High",0,2493000,0,0,0,2493000]
[null,null,"Cocoa Senior High",0,0,0,0,338000,338000]
[null,null,"Eau Gallie Senior High",0,0,0,0,0,0]
[null,null,"Melbourne Senior High",0,0,0,0,732000,732000]
[null,null,"Merritt Island Senior High",0,0,4668000,0,0,4668000]
[null,null,"Palm Bay Senior High",0,2833000,0,0,0,2833000]
[null,null,"Rockledge Senior High",0,0,0,1683000,0,1683000]
[null,null,"Satellite Senior High",0,0,2917000,0,0,2917000]
[null,null,"Titusville High ",0,1246000,0,0,0,1246000]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,450000,450000]
[null,null,"520 Compound",0,0,0,0,0,0]
[null,null,"Educational Services Facility",0,0,0,0,0,0]
[null,null,"Maintenance Department",0,0,0,0,0,0]
[null,null,"Mid-West Melbourne Elementary",0,0,0,0,0,0]
[null,null,"Melbourne Bus Compound",0,0,0,0,0,0]
[null,null,"Bus Garage & Maintenance Shop (North Area)",0,0,0,0,0,0]
[null,null,"Devereux Normandy",0,0,0,0,0,0]
[null,null,"Rockedge Center",0,0,0,0,1000000,1000000]
[null,null,"Satellite Bus Compound",0,0,0,0,0,0]
[null,"Vocational Lab. Upgrades","Various",0,950000,950000,950000,950000,3800000]
[null,"Technology Enhancements","Various",14571,0,0,0,0,14571]
[null,"Bus Compound Renovations","Melbourne Bus Parking/Service Area",862420,0,0,0,0,862420]
[null,null,"Bus Maintenance Building - Stone",108933,0,0,0,0,108933]
[null,"Covered Eating Area"]
[null,null,"Merritt Island Senior High",120000,0,0,0,0,120000]
[null,null,"Titusville High ",120000,0,0,0,0,120000]
[null,null,"Eau Gallie Senior High",120000,0,0,0,0,120000]
[null,"Athletic / P. E. Fields","West Shore Jr./Sr. High",250000,0,0,0,0,250000]
[null,"Kitchen Upgrades","Various",0,250000,250000,0,0,500000]
[null,"Custodial Equipment","Various",446763,250000,250000,250000,250000,1446763]
["1.","BREVARD  Total",null,41756562,41456603.05,45139459.9025,42259328.597625,31058103.92750625,201670057.47763124]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[]
[null,"Project Description",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"Elementary School \"Q\"","Melbourne Area",10213994,0,0,0,0,10213994]
[null,"Music Building","Titusville High",1009000,0,0,0,0,1009000]
[null,"Remodel / Renovate Projects"]
[null,null,"Roy Allen Elementary",0,1802541,0,0,0,1802541]
[null,null,"Hans Christian Anderson Elementary",0,0,0,3076255,0,3076255]
[null,null,"Apollo Elementary",0,0,3514416,0,0,3514416]
[null,null,"Atlantis Elementary",0,0,0,0,0,0]
[null,null,"Audubon Elementary",0,2663160,0,0,0,2663160]
[null,null,"Cambridge Elementary",0,1547220,0,null,0,1547220]
[null,null,"Cape View Elementary",0,2806975,0,0,0,2806975]
[null,null,"Lewis Carroll Elementary",0,0,0,0,0,0]
[null,null,"Challenger 7 Elementary ",0,0,0,282681,0,282681]
[null,null,"Columbia Elementary",0,0,0,296265,0,296265]
[null,null,"Coquina Elementary",0,2461913,0,0,0,2461913]
[null,null,"Dr. W. J. Creel Elementary",0,0,2948803,0,0,2948803]
[null,null,"Croton Elementary",0,2103614,0,0,0,2103614]
[null,null,"Discovery Elementary",0,0,0,0,215834,215834]
[null,null,"Endeavour Elementary",0,0,0,0,520773,520773]
[null,null,"Enterprise Elementary",0,0,0,0,0,0]
[null,null,"Fairglen Elementary",0,0,0,0,0,0]
[null,null,"Gardendale Elementary",0,0,2314736,0,0,2314736]
[null,null,"Gemini Elementary",0,0,0,0,2689217,2689217]
[null,null,"Golfview Elementary",0,0,0,1634644,0,1634644]
[null,null,"Harbor City Elementary",0,0,0,0,2634520,2634520]
[null,null,"Spessard L. Holland Elementary",0,0,0,0,504226,504226]
[null,null,"Imperial Estates Elementary",0,0,0,0,201930,201930]
[null,null,"Indialantic Elementary",0,0,0,0,1433729,1433729]
[null,null,"Jupiter Elementary",0,0,0,0,0,0]
[null,null,"Lockmar Elementary",0,0,0,2720824,0,2720824]
[null,null,"Longleaf Elementary",0,0,0,0,0,0]
[null,null,"Christa McAuliffe Elementary",0,0,0,251521,0,251521]
[null,null,"Meadowlane Elementary",0,0,0,0,0,0]
[null,null,"Mila Elementary",0,0,0,0,2613599,2613599]
[null,null,"Mims Elementary",0,1957059,0,0,0,1957059]
[null,null,"Oak Park Elementary",0,0,3219060,0,0,3219060]
[null,null,"Ocean Breeze Elementary",0,0,2867101,0,0,2867101]
[null,null,"Palm Bay Elementary",0,0,0,2394961,0,2394961]
[null,null,"Pinewood Elementary",0,1638972,0,0,0,1638972]
[null,null,"Port Malabar Elementary",0,0,0,1231641,0,1231641]
[null,null,"Riverview Elementary",0,2696800,0,0,0,2696800]
[null,null,"Riviera Elementary",0,0,0,0,0,0]
[null,null,"Theodore Roosevelt Elementary",0,4114685,0,0,0,4114685]
[null,null,"Sabal Elementary",0,2755825,0,0,0,2755825]
[null,null,"Saturn Elementary ",0,3348264,0,0,0,3348264]
[null,null,"Sea Park Elementary",0,0,2398834,0,0,2398834]
[null,null,"Sherwood Elementary",0,0,0,0,0,0]
[null,null,"South Lake Elementary",0,0,2862574,0,0,2862574]
[null,null,"Devereux South Pine Grove School",0,0,0,0,0,0]
[null,null,"Suntree Elementary",0,0,0,0,0,0]
[null,null,"Surfside Elementary",0,0,2060113,0,0,2060113]
[null,null,"Tropical Elementary",0,3171112,0,0,0,3171112]
[null,null,"John F. Turner Sr. Elementary",0,0,0,1833808,0,1833808]
[null,null,"University Park Elementary",0,0,0,0,612453,612453]
[null,null,"Westside Elementary",0,0,0,0,0,0]
[null,null,"Freedom 7 Elementary",2509000,0,0,0,0,2509000]
[null,null,"West Melbourne Elementary",2527500,0,0,0,0,2527500]
[null,null,"Robert L. Stevenson Elementary",726250,0,0,0,0,726250]
[null,null,"Whispering Hills Primary School",1082000,0,0,0,0,1082000]
[null,null,"Central Middle ",0,0,0,113031,0,113031]
[null,null,"Clearlake Middle",0,0,0,0,348373,348373]
[null,null,"DeLaura Middle",0,4980043,0,0,0,4980043]
[null,null,"Edgewood Middle",0,0,4656802,0,0,4656802]
[null,null,"Herbert C. Hoover Middle",0,0,4728660,0,0,4728660]
[null,null,"Andrew Jackson Middle",0,4843189,0,0,0,4843189]
[null,null,"Thomas Jefferson Middle",0,0,5124785,0,0,5124785]
[null,null,"Lyndon B. Johnson Middle",0,5560060,0,0,0,5560060]
[null,null,"John F. Kennedy Middle",0,0,0,0,5761236,5761236]
[null,null,"Ronald McNair Middle",0,1953537,0,0,0,1953537]
[null,null,"James Madison Middle",0,5228907,0,0,0,5228907]
[null,null,"Southwest Middle",0,0,0,90008,0,90008]
[null,null,"Space Coast Middle ",0,0,0,0,9999,9999]
[null,null,"Stone Middle",0,2160621,0,0,0,2160621]
[null,null,"Astronaut High",0,0,0,5402151,0,5402151]
[null,null,"Bayside High",0,0,0,0,0,0]
[null,null,"Cocoa Beach Jr./Sr. High",0,2621430,0,0,0,2621430]
[null,null,"Cocoa Senior High",0,0,0,0,1009010,1009010]
[null,null,"Eau Gallie Senior High",0,0,0,0,8366894,8366894]
[null,null,"Melbourne Senior High",0,0,0,0,3774459,3774459]
[null,null,"Merritt Island Senior High",0,0,10098966,0,0,10098966]
[null,null,"Palm Bay Senior High",0,7844106,0,0,0,7844106]
[null,null,"Rockledge Senior High",0,0,0,3378932,0,3378932]
[null,null,"Satellite Senior High",0,0,10776395,0,0,10776395]
[null,null,"Titusville High ",0,7136948,0,0,0,7136948]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,471270,471270]
[null,null,"520 Compound",0,0,0,1185840,0,1185840]
[null,null,"Educational Services Facility",0,0,0,0,0,0]
[null,null,"Maintenance Department",0,0,0,0,0,0]
[null,null,"Mid-South Area Support Services",0,0,0,0,0,0]
[null,null,"Melbourne Bus Compound",0,0,0,0,0,0]
[null,null,"Bus Garage & Maintenance Shop (North Area)",0,0,0,0,137700,137700]
[null,null," Devereux Normandy",0,0,0,0,0,0]
[null,null,"Rockledge Center",0,0,0,0,22130,22130]
[null,null,"Satellite Bus Compound",0,0,0,0,139266,139266]
[null,"Classroom Additions"]
[null,null,"Roy Allen Elementary",0,3552433,0,0,0,3552433]
[null,null,"Gardendale Elementary",0,0,0,4568888,0,4568888]
[null,null,"Gemini Elementary",0,0,3618162,0,0,3618162]
[null,null,"Indialantic Elementary",0,0,0,0,4430082,4430082]
[null,null,"Mims Elementary",0,0,5432684,0,0,5432684]
[null,null,"Ocean Breeze Elementary",0,0,0,3153965,0,3153965]
[null,null,"Palm Bay Elementary",0,0,0,0,3147321,3147321]
[null,null,"Riverview Elementary",0,1414217,0,0,0,1414217]
[null,null,"Sabal Elementary",0,0,3708768,0,0,3708768]
[null,null,"Saturn Elementary ",0,0,0,1964213,0,1964213]
[null,null,"Surfside Elementary",0,0,4834770,0,0,4834770]
[null,null,"South Lake Elementary",0,0,0,0,3462393,3462393]
[null,null,"DeLaura Middle",0,0,null,0,1835539,1835539]
[null,null,"James Madison Middle",0,3566357,0,0,0,3566357]
[null,null,"Astronaut High",0,0,0,5175638,0,5175638]
[null,null,"Cocoa Beach Jr./Sr. High ",0,5442250,0,0,0,5442250]
[null,null,"Eau Gallie Senior High",0,0,0,0,1740067,1740067]
[null,null,"Merritt Island Senior High",0,0,10250281,0,0,10250281]
[null,null,"Palm Bay Senior High",0,0,0,0,3498425,3498425]
[null,null,"Rockledge Senior High",0,0,0,1728002,0,1728002]
[null,null,"Satellite Senior High",0,0,null,0,12064878,12064878]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,5225065,5225065]
[null,"New Additions"]
[null,null,"Apollo Elementary",0,0,0,1799822,0,1799822]
[null,null,"Audubon Elementary",0,0,3107602,0,0,3107602]
[null,null,"Cambridge Elementary",0,0,0,2842851,0,2842851]
[null,null,"Cape View Elementary",0,0,2319005,0,0,2319005]
[null,null,"Coquina Elementary",0,0,0,2241261,0,2241261]
[null,null,"Croton Elementary",0,0,2380916,0,0,2380916]
[null,null,"Endeavour Elementary",0,0,0,0,2354625,2354625]
[null,null,"Golfview Elementary",0,0,0,0,1813675,1813675]
[null,null,"Harbor City Elementary",0,0,0,0,2832250,2832250]
[null,null,"Spessard L. Holland Elementary",0,0,1432592,0,0,1432592]
[null,null,"Imperial Estates Elementary",0,0,0,0,956805,956805]
[null,null,"Lockmar Elementary",0,0,0,1941739,0,1941739]
[null,null,"Mila Elementary",0,0,0,0,2263595,2263595]
[null,null,"Oak Park Elementary",0,0,1361351,0,0,1361351]
[null,null,"Pinewood Elementary",0,0,0,0,725413,725413]
[null,null,"Port Malabar Elementary",0,0,0,0,1941739,1941739]
[null,null,"Theodore Roosevelt Elementary",0,0,0,146157,0,146157]
[null,null,"Sea Park Elementary",0,0,0,3357510,0,3357510]
[null,null,"Tropical Elementary",0,0,0,3596393,0,3596393]
[null,null,"John F. Turner Sr. Elementary",0,0,0,2207620,0,2207620]
[null,null,"University Park Elementary",0,0,0,0,3448964,3448964]
[null,null,"Clearlake Middle",0,0,2124355,0,0,2124355]
[null,null,"Edgewood Middle",0,0,2763490,0,0,2763490]
[null,null,"Herbert C. Hoover Middle",0,0,2376878,0,0,2376878]
[null,null,"Andrew Jackson Middle",0,null,null,1896904,0,1896904]
[null,null,"Thomas Jefferson Middle",0,0,0,2376878,0,2376878]
[null,null,"Lyndon B. Johnson Middle",0,0,0,0,3613592,3613592]
[null,null,"John F. Kennedy Middle",0,0,null,null,2376878,2376878]
[null,null,"Ronald McNair Middle",0,1515833,0,0,2376878,3892711]
[null,null,"Southwest Middle",0,0,0,null,174952,174952]
[null,null,"Stone Middle",0,0,0,0,277042,277042]
[null,null,"Bayside High",0,0,0,0,2072435,2072435]
[null,null,"Cocoa Senior High",0,0,0,0,5389108,5389108]
[null,null,"Titusville High ",0,0,0,0,2072435,2072435]
[null,"Ancillary New Construction"]
[null,null,"Maintenance Department",0,0,0,0,4173758,4173758]
[null,null,"Bus Garage & Maintenance Shop (North Area)",0,0,0,654792,0,654792]
[null,null,"Satellite Bus Compound",0,0,0,323088,0,323088]
["2 .","BREVARD  Total",null,18067744,90888071,103282099,63868283,105734532,381840729]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1998-99 FISH Satisfactory","Actual 1998-99","Actual 1998-99","Actual 1998-99","New Stu Capacity to","Projected 2003-04","Projected 2003-04"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE","Utilization"]
[null,"Roy Allen Elementary",764,764,524.35,0.69,-224,459,0.85]
[null,"Hans Christian Anderson Elementary",773,773,1017.29,1.32,-40,673,0.92]
[null,"Apollo Elementary",1042,1042,876.57,0.84,-220,944,1.15]
[null,"Atlantis Elementary",928,928,703.09,0.76,-202,685,0.94]
[null,"Audubon Elementary",731,731,605.83,0.83,-202,492,0.93]
[null,"Cambridge Elementary",673,673,482.5,0.72,-235,564,1.29]
[null,"Cape View Elementary",760,760,487.91,0.64,-299,418,0.91]
[null,"Lewis Carroll Elementary",822,822,778.07,0.95,-83,894,1.21]
[null,"Central Pine Grove School",62,62,16.45,0.27,-62,0,"-"]
[null,"Challenger 7 Elementary ",751,751,618.46,0.82,-270,585,1.22]
[null,"Columbia Elementary",952,952,799.3,0.84,-244,631,0.89]
[null,"Coquina Elementary",584,584,388.98,0.67,-283,431,1.43]
[null,"Dr. W. J. Creel Elementary",1242,1242,999.89,0.81,-353,1064,1.2]
[null,"Croton Elementary",648,648,505.1,0.78,-204,470,1.06]
[null,"Discovery Elementary",1223,1223,1146.27,0.94,-323,1064,1.18]
[null,"Endeavour Elementary",925,925,600.69,0.65,-269,654,1]
[null,"Enterprise Elementary",928,928,931.71,1,-48,673,0.76]
[null,"Fairglen Elementary",938,938,926.43,0.99,-133,821,1.02]
[null,"Gardendale Elementary",923,923,668.17,0.72,-229,604,0.87]
[null,"Gemini Elementary",677,677,686.09,1.01,-14,685,1.03]
[null,"Golfview Elementary",900,900,575.52,0.64,-207,628,0.91]
[null,"Harbor City Elementary",643,643,575.58,0.9,-150,592,1.2]
[null,"Spessard L. Holland Elementary",778,778,602.56,0.77,-265,559,1.09]
[null,"Imperial Estates Elementary",751,751,623.44,0.83,-222,485,0.92]
[null,"Indialantic Elementary",855,855,793.68,0.93,-94,798,1.05]
[null,"Jupiter Elementary",1108,1108,779.66,0.7,-308,728,0.91]
[null,"Lockmar Elementary",1017,1017,1009.45,0.99,-196,801,0.98]
[null,"Longleaf Elementary",940,940,862.75,0.92,-62,1351,1.54]
[null,"Christa McAuliffe Elementary",952,952,934.94,0.98,-257,750,1.08]
[null,"Meadowlane Elementary",1089,1089,952.31,0.87,-322,892,1.16]
[null,"Mila Elementary",850,850,553.8,0.65,-315,606,1.13]
[null,"Mims Elementary",637,637,587.59,0.92,94,740,1.01]
[null,"Oak Park Elementary",1047,1047,947.73,0.91,-225,705,0.86]
[null,"Ocean Breeze Elementary",666,666,649.31,0.97,-145,571,1.1]
[null,"Palm Bay Elementary",1122,1122,790.44,0.7,-351,706,0.92]
[null,"Pinewood Elementary",764,764,497.22,0.65,-322,445,1.01]
[null,"Port Malabar Elementary",1075,1075,959.2,0.89,-305,888,1.15]
[null,"Riverview Elementary",891,891,664.78,0.75,-402,510,1.04]
[null,"Riviera Elementary",938,938,775.05,0.83,-149,835,1.06]
[null,"Theodore Roosevelt Elementary",818,818,691.86,0.85,-179,732,1.15]
[null,"Sabal Elementary",694,694,598.74,0.86,-103,541,0.92]
[null,"Saturn Elementary ",1029,1029,922.77,0.9,-168,712,0.83]
[null,"Sea Park Elementary",650,650,527.41,0.81,-197,418,0.92]
[null,"Sherwood Elementary",899,899,743.06,0.83,-89,819,1.01]
[null,"South Lake Elementary",837,837,612.86,0.73,-291,477,0.87]
[null,"Devereux South Pine Grove School",58,58,35.92,0.62,-29,19,0.66]
[null,"Suntree Elementary",1014,1014,929.31,0.92,-174,979,1.17]
[null,"Surfside Elementary",677,677,562.01,0.83,-81,605,1.02]
[null,"Tropical Elementary",1010,1010,991.78,0.98,-106,864,0.96]
[null,"John F. Turner Sr. Elementary",1018,1018,783.52,0.77,-188,590,0.71]
[null,"University Park Elementary",904,904,572.12,0.63,-410,519,1.05]
[null,"Westside Elementary",940,940,727.53,0.77,-77,1036,1.2]
[null,"Ralph M. Williams Jr. Elementary",null,940,"-","-",-34,949,1.05]
[null,"Freedom 7 Elementary",null,399,"-","-",0,350,0.88]
[null,"West Melbourne Elementary",null,476,"-","-",0,350,0.74]
[null,"Robert L. Stevenson Elementary",null,415,"-","-",0,350,0.84]
[null,"Whispering Hills Primary School",null,0,"-","-",0,275,"-"]
[null,"Elementary School \"Q\"",null,940,"-","-",940,940,"-"]
[null,"Central Middle ",1833,1649,1615,0.98,-379,1070,0.84]
[null,"Clearlake Middle",956,860,866.33,1.01,-163,652,0.94]
[null,"DeLaura Middle",1004,903,1256.34,1.39,-104,881,1.1]
[null,"Edgewood Middle",921,828,644.55,0.78,-315,530,1.03]
[null,"Herbert C. Hoover Middle",766,689,771.26,1.12,-72,590,0.96]
[null,"Andrew Jackson Middle",811,729,672.02,0.92,-69,578,0.88]
[null,"Thomas Jefferson Middle",847,762,842.97,1.11,-188,618,1.08]
[null,"Lyndon B. Johnson Middle",1600,1440,1316.78,0.91,-395,1122,1.07]
[null,"John F. Kennedy Middle",909,818,835.14,1.02,-173,662,1.03]
[null,"Ronald McNair Middle",890,801,554.22,0.69,-359,427,0.97]
[null,"James Madison Middle",753,677,807.4,1.19,166,762,0.9]
[null,"Southwest Middle",1725,1552,1339.13,0.86,-217,1304,0.98]
[null,"Space Coast Middle ",1833,1649,1087.08,0.66,-391,1040,0.83]
[null,"Stone Middle",1283,1154,765.4,0.66,-449,769,1.09]
[null,"Astronaut High",1647,1564,1480.07,0.95,-19,1525,0.99]
[null,"Bayside High",1700,1615,930.84,0.58,425,1816,0.89]
[null,"Cocoa Beach Jr./Sr. High",1112,1000,1116.54,1.12,163,1437,1.24]
[null,"Cocoa Senior High",1867,1773,1242.72,0.7,-322,1421,0.98]
[null,"Eau Gallie Senior High",1767,1678,1521.53,0.91,506,2389,1.09]
[null,"Melbourne Senior High",1575,1496,1624.9,1.09,909,2421,1.01]
[null,"Merritt Island Senior High",1726,1639,1293.95,0.79,225,2039,1.09]
[null,"Palm Bay Senior High",2528,2401,2330.58,0.97,-808,2037,1.28]
[null,"Rockledge Senior High",1417,1346,1506.3,1.12,111,1587,1.09]
[null,"Satellite Senior High",1501,1425,1378.47,0.97,459,1986,1.05]
[null,"Titusville High ",2241,2128,2039.97,0.96,310,2117,0.87]
[null,"West Shore Jr./Sr. High",915,823,548.82,0.67,90,925,1.01]
["2a.","BREVARD  Total",80044,80486,66985.36000000002,0.83,-10385,70631,1.01]
[]
["2b.","Proposed Location of Planned Facilities"]
[]
[null,"New Elementary Schools (940 Student Stations) in the Melbourne Area. "]
[]
[{"$nulls":6},"# of Units","Projected"]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1998-99","Owner","Student Stations","as classroom space","in 2003-04","units by 2003-04","Column \"C\""]
[null,"Roy Allen Elementary",16,"SBBC / LEASED",290,0,0,16,297]
[null,"Hans Christian Anderson Elementary",5,"SBBC",110,0,0,5,181]
[null,"Apollo Elementary",0,"-",0,0,0,0,0]
[null,"Atlantis Elementary",0,"-",0,0,0,0,0]
[null,"Audubon Elementary",7,"SBBC / LEASED",114,0,0,7,93]
[null,"Cambridge Elementary",8,"SBBC / LEASED",93,0,0,8,88]
[null,"Cape View Elementary",0,"-",0,0,0,0,0]
[null,"Lewis Carroll Elementary",3,"SBBC",63,0,6,-3,63]
[null,"Central Pine Grove School",1,"SBBC",0,0,0,1,0]
[null,"Challenger 7 Elementary ",0,"-",0,0,0,0,0]
[null,"Columbia Elementary",10,"SBBC / LEASED",196,0,7,3,101]
[null,"Coquina Elementary",0,"-",0,0,0,0,0]
[null,"Dr. W. J. Creel Elementary",2,"SBBC",22,0,1,1,70]
[null,"Croton Elementary",0,"-",0,0,0,0,0]
[null,"Discovery Elementary",15,"SBBC / LEASED",301,0,8,7,174]
[null,"Endeavour Elementary",13,"SBBC / LEASED",220,0,10,3,113]
[null,"Enterprise Elementary",0,"-",0,0,0,0,0]
[null,"Fairglen Elementary",2,"SBBC",42,0,1,1,18]
[null,"Gardendale Elementary",13,"SBBC / LEASED",290,0,0,13,147]
[null,"Gemini Elementary",7,"SBBC / LEASED",125,0,1,6,87]
[null,"Golfview Elementary",3,"SBBC / LEASED",41,0,0,3,31]
[null,"Harbor City Elementary",6,"SBBC / LEASED",96,0,1,5,139]
[null,"Spessard L. Holland Elementary",0,"-",0,0,0,0,0]
[null,"Imperial Estates Elementary",0,"-",0,0,0,0,0]
[null,"Indialantic Elementary",11,"LEASED",198,0,3,8,97]
[null,"Jupiter Elementary",8,"SBBC / LEASED",186,0,7,1,69]
[null,"Lockmar Elementary",2,"LEASED",20,0,0,2,10]
[null,"Longleaf Elementary",0,"SBBC",0,0,4,-4,0]
[null,"Christa McAuliffe Elementary",14,"SBBC / LEASED",215,0,7,7,152]
[null,"Meadowlane Elementary",9,"LEASED",167,0,4,5,102]
[null,"Mila Elementary",5,"SBBC / LEASED",67,0,3,2,71]
[null,"Mims Elementary",11,"SBBC / LEASED",202,0,0,11,159]
[null,"Oak Park Elementary",3,"SBBC",51,0,0,3,61]
[null,"Ocean Breeze Elementary",7,"LEASED",86,0,0,7,56]
[null,"Palm Bay Elementary",12,"SBBC",252,0,0,12,507]
[null,"Pinewood Elementary",0,"-",0,0,0,0,192]
[null,"Port Malabar Elementary",8,"SBBC / LEASED",179,0,0,8,253]
[null,"Riverview Elementary",17,"LEASED",318,0,0,17,98]
[null,"Riviera Elementary",1,"LEASED",10,0,0,1,106]
[null,"Theodore Roosevelt Elementary",4,"LEASED",54,0,0,4,45]
[null,"Sabal Elementary",7,"SBBC",132,0,2,5,331]
[null,"Saturn Elementary ",7,"SBBC",110,0,0,7,46]
[null,"Sea Park Elementary",3,"SBBC / LEASED",30,0,0,3,95]
[null,"Sherwood Elementary",0,"-",0,0,0,0,26]
[null,"South Lake Elementary",8,"SBBC / LEASED",147,0,0,8,277]
[null,"Devereux South Pine Grove School",0,"-",0,0,0,0,37]
[null,"Suntree Elementary",4,"-",92,0,0,4,418]
[null,"Surfside Elementary",5,"SBBC / LEASED",83,0,2,3,41]
[null,"Tropical Elementary",8,"SBBC",175,0,1,7,272]
[null,"John F. Turner Sr. Elementary",12,"SBBC / LEASED",280,0,2,10,125]
[null,"University Park Elementary",13,"SBBC / LEASED",220,0,8,5,227]
[null,"Westside Elementary",0,"-",0,0,0,0,0]
[null,"Ralph M. Williams Jr. Elementary",0,"SBBC",0,0,4,-4,0]
[null,"Freedom 7 Elementary",0,"-",0,0,0,0,0]
[null,"West Melbourne Elementary",0,"-",0,0,0,0,0]
[null,"Robert L. Stevenson Elementary",0,"-",0,0,0,0,0]
[null,"Whispering Hills Primary School",0,"-",0,0,0,0,0]
[null,"Central Middle ",0,"-",0,0,0,0,0]
[null,"Clearlake Middle",4,"-",0,0,0,4,0]
[null,"DeLaura Middle",0,"-",0,0,0,0,0]
[null,"Edgewood Middle",2,"LEASED",25,0,0,2,5]
[null,"Herbert C. Hoover Middle",2,"-",225,0,0,2,95]
[null,"Andrew Jackson Middle",0,"-",0,0,0,0,0]
[null,"Thomas Jefferson Middle",4,"SBBC",25,0,0,4,13]
[null,"Lyndon B. Johnson Middle",12,"-",625,0,0,12,530]
[null,"John F. Kennedy Middle",12,"SBBC",250,0,0,12,156]
[null,"Ronald McNair Middle",7,"-",200,0,0,7,271]
[null,"James Madison Middle",1,"SBBC",75,0,0,1,20]
[null,"Southwest Middle",0,"-",75,0,0,0,78]
[null,"Space Coast Middle ",0,"-",0,0,0,0,0]
[null,"Stone Middle",0,"-",0,0,0,0,0]
[null,"Astronaut High",3,"SBBC",150,0,1,2,157]
[null,"Bayside High",0,"-",0,0,0,0,0]
[null,"Cocoa Beach Jr./Sr. High",0,"SBBC / LEASED",25,0,0,0,12]
[null,"Cocoa Senior High",1,"-",100,0,0,1,41]
[null,"Eau Gallie Senior High",8,"SBBC / LEASED",300,0,4,4,242]
[null,"Melbourne Senior High",1,"SBBC",800,0,1,0,409]
[null,"Merritt Island Senior High",4,"SBBC / LEASED",100,0,1,3,29]
[null,"Palm Bay Senior High",22,"SBBC",675,0,5,17,865]
[null,"Rockledge Senior High",3,"SBBC",75,0,0,3,111]
[null,"Satellite Senior High",0,"SBBC / LEASED",75,0,0,0,105]
[null,"Titusville High ",1,"-",25,0,0,1,37]
[null,"West Shore Jr./Sr. High",0,"-",0,0,0,0,0]
["2c1.","BREVARD  Total",377,"SBBC / LEASED",9102,0,94,283,"Avg Age 21.2"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"Location","Total # Units to be replaced","(increase) / decrease","(increase) / decrease","(increase) / decrease","(increase) / decrease","(increase) / decrease","(increase) / decrease"]
[null,"Roy Allen Elementary",16,-1,0,17,0,0,16]
[null,"Hans Christian Anderson Elementary",5,4,0,0,0,1,5]
[null,"Apollo Elementary",0,0,0,0,0,0,0]
[null,"Atlantis Elementary",0,0,0,0,0,0,0]
[null,"Audubon Elementary",7,-7,0,14,0,0,7]
[null,"Cambridge Elementary",8,-6,0,1,13,0,8]
[null,"Cape View Elementary",0,0,0,0,0,0,0]
[null,"Lewis Carroll Elementary",3,-5,0,1,0,1,-3]
[null,"Central Pine Grove School",1,1,0,0,0,0,1]
[null,"Challenger 7 Elementary ",0,0,0,0,0,0,0]
[null,"Columbia Elementary",10,-1,0,0,2,2,3]
[null,"Coquina Elementary",0,0,0,0,0,0,0]
[null,"Dr. W. J. Creel Elementary",2,0,0,0,0,1,1]
[null,"Croton Elementary",0,0,0,0,0,0,0]
[null,"Discovery Elementary",15,0,0,1,0,6,7]
[null,"Endeavour Elementary",13,-1,0,0,1,3,3]
[null,"Enterprise Elementary",0,0,0,0,0,0,0]
[null,"Fairglen Elementary",2,-1,0,1,0,1,1]
[null,"Gardendale Elementary",13,0,0,1,8,4,13]
[null,"Gemini Elementary",7,0,0,0,0,6,6]
[null,"Golfview Elementary",3,-4,0,1,3,3,3]
[null,"Harbor City Elementary",6,0,0,0,0,5,5]
[null,"Spessard L. Holland Elementary",0,0,0,0,0,0,0]
[null,"Imperial Estates Elementary",0,0,0,0,0,0,0]
[null,"Indialantic Elementary",11,-3,0,0,0,11,8]
[null,"Jupiter Elementary",8,1,0,0,0,0,1]
[null,"Lockmar Elementary",2,1,0,1,0,0,2]
[null,"Longleaf Elementary",0,-4,0,0,0,0,-4]
[null,"Christa McAuliffe Elementary",14,1,0,1,2,3,7]
[null,"Meadowlane Elementary",9,0,0,2,1,2,5]
[null,"Mila Elementary",5,0,0,1,0,1,2]
[null,"Mims Elementary",11,-5,0,2,14,0,11]
[null,"Oak Park Elementary",3,0,0,2,1,0,3]
[null,"Ocean Breeze Elementary",7,0,0,0,5,2,7]
[null,"Palm Bay Elementary",12,0,0,1,5,6,12]
[null,"Pinewood Elementary",0,0,0,0,0,0,0]
[null,"Port Malabar Elementary",8,0,0,1,0,7,8]
[null,"Riverview Elementary",17,6,0,2,9,0,17]
[null,"Riviera Elementary",1,0,0,1,0,0,1]
[null,"Theodore Roosevelt Elementary",4,2,0,2,0,0,4]
[null,"Sabal Elementary",7,-1,0,0,0,6,5]
[null,"Saturn Elementary ",7,4,0,1,0,2,7]
[null,"Sea Park Elementary",3,0,0,1,0,2,3]
[null,"Sherwood Elementary",0,0,0,0,0,0,0]
[null,"South Lake Elementary",8,1,0,2,0,5,8]
[null,"Devereux South Pine Grove School",0,0,0,0,0,0,0]
[null,"Suntree Elementary",4,4,0,0,0,0,4]
[null,"Surfside Elementary",5,0,0,0,0,3,3]
[null,"Tropical Elementary",8,0,0,1,4,2,7]
[null,"John F. Turner Sr. Elementary",12,-1,0,0,1,10,10]
[null,"University Park Elementary",13,-1,0,1,1,3,4]
[null,"Westside Elementary",0,0,0,0,0,0,0]
[null,"Ralph M. Williams Jr. Elementary",0,-4,0,0,0,0,-4]
[null,"Freedom 7 Elementary",0,0,0,0,0,0,0]
[null,"West Melbourne Elementary",0,0,0,0,0,0,0]
[null,"Robert L. Stevenson Elementary",0,0,0,0,0,0,0]
[null,"Whispering Hills Primary School",0,0,0,0,0,0,0]
[null,"Central Middle ",0,0,0,0,0,0,0]
[null,"Clearlake Middle",4,4,0,0,0,0,4]
[null,"DeLaura Middle",0,0,0,0,0,0,0]
[null,"Edgewood Middle",2,0,0,0,0,2,2]
[null,"Herbert C. Hoover Middle",2,2,0,0,0,0,2]
[null,"Andrew Jackson Middle",0,0,0,0,0,0,0]
[null,"Thomas Jefferson Middle",4,2,0,0,0,2,4]
[null,"Lyndon B. Johnson Middle",12,12,0,0,0,0,12]
[null,"John F. Kennedy Middle",12,10,0,0,0,2,12]
[null,"Ronald McNair Middle",7,7,0,0,0,0,7]
[null,"James Madison Middle",1,0,0,0,1,0,1]
[null,"Southwest Middle",0,0,0,0,0,0,0]
[null,"Space Coast Middle ",0,0,0,0,0,0,0]
[null,"Stone Middle",0,0,0,0,0,0,0]
[null,"Astronaut High",3,0,0,0,0,2,2]
[null,"Bayside High",0,0,0,0,0,0,0]
[null,"Cocoa Beach Jr./Sr. High",0,-7,0,0,7,0,0]
[null,"Cocoa Senior High",1,0,0,0,0,1,1]
[null,"Eau Gallie Senior High",8,-6,0,0,6,2,2]
[null,"Melbourne Senior High",1,0,0,0,0,0,0]
[null,"Merritt Island Senior High",4,-9,0,0,5,8,4]
[null,"Palm Bay Senior High",22,0,0,0,7,10,17]
[null,"Rockledge Senior High",3,0,0,0,0,3,3]
[null,"Satellite Senior High",0,-13,0,0,13,0,0]
[null,"Titusville High ",1,1,0,0,0,0,1]
[null,"West Shore Jr./Sr. High",0,0,0,0,0,0,0]
["2c2.","BREVARD  Total",377,-17,0,59,109,130,281]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1998-99","Owner","FISH Stu. Sta.","# Years Leased (avg.)","# leased 2003-04","FISH Stu. Sta.","# Years Leased "]
[null,"Roy Allen Elementary",10,"LEASED",210,7,0,0,0]
[null,"Hans Christian Anderson Elementary",0,"LEASED",0,0,0,0,0]
[null,"Apollo Elementary",0,"LEASED",0,0,0,0,0]
[null,"Atlantis Elementary",0,"LEASED",0,0,0,0,0]
[null,"Audubon Elementary",6,"LEASED",93,9,0,0,0]
[null,"Cambridge Elementary",7,"LEASED",82,7,0,0,0]
[null,"Cape View Elementary",0,"LEASED",0,0,0,0,0]
[null,"Lewis Carroll Elementary",0,"LEASED",0,0,0,0,0]
[null,"Central Pine Grove School",0,"LEASED",0,0,0,0,0]
[null,"Challenger 7 Elementary ",0,"LEASED",0,0,0,0,0]
[null,"Columbia Elementary",8,"LEASED",154,9,0,0,0]
[null,"Coquina Elementary",0,"LEASED",0,0,0,0,0]
[null,"Dr. W. J. Creel Elementary",0,"LEASED",0,0,0,0,0]
[null,"Croton Elementary",0,"LEASED",0,0,0,0,0]
[null,"Discovery Elementary",10,"LEASED",196,10,0,0,0]
[null,"Endeavour Elementary",12,"LEASED",199,9,0,0,0]
[null,"Enterprise Elementary",0,"LEASED",0,0,0,0,0]
[null,"Fairglen Elementary",2,"LEASED",42,9,0,0,0]
[null,"Gardendale Elementary",12,"LEASED",279,9,0,0,0]
[null,"Gemini Elementary",6,"LEASED",104,8,0,0,0]
[null,"Golfview Elementary",2,"LEASED",31,9,0,0,0]
[null,"Harbor City Elementary",2,"LEASED",20,9,0,0,0]
[null,"Spessard L. Holland Elementary",0,"LEASED",0,0,0,0,0]
[null,"Imperial Estates Elementary",0,"LEASED",0,0,0,0,0]
[null,"Indialantic Elementary",11,"LEASED",198,8,0,0,0]
[null,"Jupiter Elementary",6,"LEASED",144,7,0,0,0]
[null,"Lockmar Elementary",2,"LEASED",20,5,0,0,0]
[null,"Longleaf Elementary",0,"LEASED",0,0,0,0,0]
[null,"Christa McAuliffe Elementary",9,"LEASED",123,7,0,0,0]
[null,"Meadowlane Elementary",9,"LEASED",167,10,0,0,0]
[null,"Mila Elementary",4,"LEASED",46,8,0,0,0]
[null,"Mims Elementary",4,"LEASED",85,8,0,0,0]
[null,"Oak Park Elementary",0,"LEASED",0,0,0,0,0]
[null,"Ocean Breeze Elementary",6,"LEASED",76,9,0,0,0]
[null,"Palm Bay Elementary",0,"LEASED",0,0,0,0,0]
[null,"Pinewood Elementary",0,"LEASED",0,0,0,0,0]
[null,"Port Malabar Elementary",1,"LEASED",27,8,0,0,0]
[null,"Riverview Elementary",17,"LEASED",318,14,0,0,0]
[null,"Riviera Elementary",1,"LEASED",10,10,0,0,0]
[null,"Theodore Roosevelt Elementary",4,"LEASED",54,9,0,0,0]
[null,"Sabal Elementary",0,"LEASED",0,0,0,0,0]
[null,"Saturn Elementary ",5,"LEASED",67,9,0,0,0]
[null,"Sea Park Elementary",1,"LEASED",10,11,0,0,0]
[null,"Sherwood Elementary",0,"LEASED",0,0,0,0,0]
[null,"South Lake Elementary",1,"LEASED",27,9,0,0,0]
[null,"Devereux South Pine Grove School",0,"LEASED",0,0,0,0,0]
[null,"Suntree Elementary",3,"LEASED",81,9,0,0,0]
[null,"Surfside Elementary",3,"LEASED",41,9,0,0,0]
[null,"Tropical Elementary",0,"LEASED",0,0,0,0,0]
[null,"John F. Turner Sr. Elementary",9,"LEASED",123,8,0,0,0]
[null,"University Park Elementary",6,"LEASED",118,9,0,0,0]
[null,"Westside Elementary",0,"LEASED",0,0,0,0,0]
[null,"Ralph M. Williams Jr. Elementary",0,"LEASED",0,0,0,0,0]
[null,"Freedom 7 Elementary",0,"LEASED",0,0,0,0,0]
[null,"West Melbourne Elementary",0,"LEASED",0,0,0,0,0]
[null,"Robert L. Stevenson Elementary",0,"LEASED",0,0,0,0,0]
[null,"Whispering Hills Primary School",0,"LEASED",0,0,0,0,0]
[null,"Central Middle ",0,"LEASED",0,0,0,0,0]
[null,"Clearlake Middle",3,"LEASED",30,10,0,0,0]
[null,"DeLaura Middle",0,"LEASED",0,0,0,0,0]
[null,"Edgewood Middle",2,"LEASED",20,7,0,0,0]
[null,"Herbert C. Hoover Middle",1,"LEASED",10,9,0,0,0]
[null,"Andrew Jackson Middle",0,"LEASED",0,0,0,0,0]
[null,"Thomas Jefferson Middle",1,"LEASED",10,10,0,0,0]
[null,"Lyndon B. Johnson Middle",0,"LEASED",0,0,0,0,0]
[null,"John F. Kennedy Middle",8,"LEASED",183,8,0,0,0]
[null,"Ronald McNair Middle",0,"LEASED",0,0,0,0,0]
[null,"James Madison Middle",0,"LEASED",0,0,0,0,0]
[null,"Southwest Middle",0,"LEASED",0,0,0,0,0]
[null,"Space Coast Middle ",0,"LEASED",0,0,0,0,0]
[null,"Stone Middle",0,"LEASED",0,0,0,0,0]
[null,"Astronaut High",0,"LEASED",0,0,0,0,0]
[null,"Bayside High",0,"LEASED",0,0,0,0,0]
[null,"Cocoa Beach Jr./Sr. High",0,"LEASED",0,0,0,0,0]
[null,"Cocoa Senior High",0,"LEASED",0,0,0,0,0]
[null,"Eau Gallie Senior High",2,"LEASED",36,5,0,0,0]
[null,"Melbourne Senior High",0,"LEASED",0,0,0,0,0]
[null,"Merritt Island Senior High",3,"LEASED",45,8,0,0,0]
[null,"Palm Bay Senior High",0,"LEASED",0,0,0,0,0]
[null,"Rockledge Senior High",0,"LEASED",0,0,0,0,0]
[null,"Satellite Senior High",0,"LEASED",0,0,0,0,0]
[null,"Titusville High ",0,"LEASED",0,0,0,0,0]
[null,"West Shore Jr./Sr. High",0,"LEASED",0,0,0,0,0]
[null,"Mid. South Community Education",0,"LEASED",0,0,0,0,0]
["2c3.","BREVARD  Total",199,"LEASED",3479,319,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2003-04"]
[null,"Educational Horizons Charter",null,"Cynthia D. Thomas",1998,75,25,3,75]
[null,"Explorer Elementary & Middle",null,"Ace Young",1998,200,200,3,200]
[null,"Milestones Community School",null,"Nick Zambri",1997,200,66,3,200]
[null,"Odyssey Charter School ",null,"Constance MacPherson",1999,200,96,3,200]
[null,"Palm Bay Academy",null,"Madhu Longani",1998,175,125,3,175]
[null,"Sculptor Elementary",null,"Ollie Striby",1999,238,80,3,238]
["2c4.","BREVARD  Total",0,null,null,1088,592,3,592]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[null,"Year Round Schools (Single Track)",{"$nulls":5},"Special Care Edu. Serv. Organization"]
[null,null,"Challenger 7 Elementary"]
[null,null,"Endeavour Elementary"]
[null,null,"Gardendale Elementary"]
[null,null,"Riverview Elementary"]
[null,"Block Scheduling"]
[null,null,"Astronaut High"]
[null,null,"Space Coast Middle"]
[null,null,"Titusville High"]
[]
["2e.","Average Class Size (5 years out -- 2003-04) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes."]
[]
[]
[{"$nulls":5},"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2003-04 CO-FTE","be added (removed)","2003-04 Class size"]
[null,"Roy Allen Elementary",18,571,546,30.33,459,-8,45.9]
[null,"Hans Christian Anderson Elementary",29,612,737,25.41,673,-8,32.05]
[null,"Apollo Elementary",42,874,900,21.43,944,-6,26.22]
[null,"Atlantis Elementary",34,928,745,21.91,685,0,20.15]
[null,"Audubon Elementary",31,617,583,18.81,492,-4,18.22]
[null,"Cambridge Elementary",26,508,579,22.27,564,-3,24.52]
[null,"Cape View Elementary",34,568,506,14.88,418,-6,14.93]
[null,"Lewis Carroll Elementary",31,759,825,26.61,894,-3,31.93]
[null,"Challenger 7 Elementary ",28,751,656,23.43,585,0,20.89]
[null,"Columbia Elementary",37,756,764,20.65,631,-9,22.54]
[null,"Coquina Elementary",22,380,446,20.27,431,-7,28.73]
[null,"Dr. W. J. Creel Elementary",21,906,1011,48.14,1064,-10,96.73]
[null,"Croton Elementary",30,590,491,16.37,470,-1,16.21]
[null,"Discovery Elementary",48,922,1156,24.08,1064,-14,31.29]
[null,"Endeavour Elementary",39,536,811,20.79,654,-12,24.22]
[null,"Enterprise Elementary",34,928,884,26,673,0,19.79]
[null,"Fairglen Elementary",42,806,906,21.57,821,-5,22.19]
[null,"Gardendale Elementary",41,633,668,16.29,604,-12,20.83]
[null,"Gemini Elementary",30,732,702,23.4,685,1,22.1]
[null,"Golfview Elementary",34,684,740,21.76,628,-7,23.26]
[null,"Harbor City Elementary",27,499,591,21.89,592,-5,26.91]
[null,"Spessard L. Holland Elementary",29,622,610,21.03,559,-5,23.29]
[null,"Imperial Estates Elementary",26,612,620,23.85,485,-5,23.1]
[null,"Indialantic Elementary",33,777,821,24.88,798,-2,25.74]
[null,"Jupiter Elementary",42,916,803,19.12,728,-8,21.41]
[null,"Lockmar Elementary",34,941,998,29.35,801,-2,25.03]
[null,"Longleaf Elementary",34,860,893,26.26,1351,-2,42.22]
[null,"Christa McAuliffe Elementary",34,737,900,26.47,750,-7,27.78]
[null,"Meadowlane Elementary",41,864,914,22.29,892,-9,27.88]
[null,"Mila Elementary",30,657,560,18.67,606,-7,26.35]
[null,"Mims Elementary",27,725,626,23.19,740,5,23.13]
[null,"Oak Park Elementary",42,876,942,22.43,705,-6,19.58]
[null,"Ocean Breeze Elementary",26,511,601,23.12,571,-4,25.95]
[null,"Palm Bay Elementary",44,846,840,19.09,706,-11,21.39]
[null,"Pinewood Elementary",22,436,528,24,445,-10,37.08]
[null,"Port Malabar Elementary",42,716,972,23.14,888,-14,31.71]
[null,"Riverview Elementary",40,543,550,13.75,510,-12,18.21]
[null,"Riviera Elementary",34,864,791,23.26,835,-2,26.09]
[null,"Theodore Roosevelt Elementary",31,687,691,22.29,732,-4,27.11]
[null,"Sabal Elementary",33,553,610,18.48,541,-5,19.32]
[null,"Saturn Elementary ",43,894,1035,24.07,712,-4,18.26]
[null,"Sea Park Elementary",26,415,532,20.46,418,-7,22]
[null,"Sherwood Elementary",33,799,802,24.3,819,-3,27.3]
[null,"South Lake Elementary",34,548,640,18.82,477,-10,19.88]
[null,"Devereux South Pine Grove School",5,74,38,7.6,19,0,3.8]
[null,"Suntree Elementary",37,916,742,20.05,979,-3,28.79]
[null,"Surfside Elementary",29,570,574,19.79,605,-4,24.2]
[null,"Tropical Elementary",46,841,1001,21.76,864,-8,22.74]
[null,"John F. Turner Sr. Elementary",35,738,821,23.46,590,-6,20.34]
[null,"University Park Elementary",35,467,597,17.06,519,-16,27.32]
[null,"Westside Elementary",34,940,775,22.79,1036,-2,32.38]
[null,"Ralph M. Williams Jr. Elementary",34,940,755,22.21,949,0,27.91]
[null,"New Elementary \"Q\"",34,940,"-","-",940,0,27.65]
[null,"Freedom 7 Elementary",24,365,"-","-",350,0,14.58]
[null,"West Melbourne Elementary",33,490,"-","-",350,0,10.61]
[null,"Robert L. Stevenson Elementary",6,362,"-","-",350,0,58.33]
[null,"Whispering Hills Primary School",26,320,"-","-",275,0,10.58]
[null,"Central Middle ",54,1596,1794.23,33.23,1070,-2,20.58]
[null,"Clearlake Middle",38,812,888.82,23.39,652,-1,17.62]
[null,"DeLaura Middle",40,904,1187.65,29.69,881,-3,23.81]
[null,"Edgewood Middle",30,915,709.71,23.66,530,0,17.67]
[null,"Herbert C. Hoover Middle",31,635,791.24,25.52,590,-1,19.67]
[null,"Andrew Jackson Middle",32,676,646.63,20.21,578,0,18.06]
[null,"Thomas Jefferson Middle",32,777,820.62,25.64,618,2,18.18]
[null,"Lyndon B. Johnson Middle",57,1034,1373.87,24.1,1122,-12,24.93]
[null,"John F. Kennedy Middle",31,1038,835.1,26.94,662,-8,28.78]
[null,"Ronald McNair Middle",30,648,606.68,20.22,427,-6,17.79]
[null,"James Madison Middle",29,861,802.05,27.66,762,10,19.54]
[null,"Southwest Middle",62,1539,1904.08,30.71,1304,0,21.03]
[null,"Space Coast Middle ",55,1654,949.38,17.26,1040,0,18.91]
[null,"Stone Middle",46,1155,1042.81,22.67,769,-4,18.31]
[null,"Astronaut High",66,1460,1455.15,22.05,1525,4,21.79]
[null,"Bayside High",51,2233,"-","-",1816,23,24.54]
[null,"Cocoa Beach Jr./Sr. High",41,1125,1008.83,24.61,1437,7,29.94]
[null,"Cocoa Senior High",76,1749,1218.04,16.03,1421,-4,19.74]
[null,"Eau Gallie Senior High",66,2119,1428.42,21.64,2389,15,29.49]
[null,"Melbourne Senior High",61,1939,1559.12,25.56,2421,16,31.44]
[null,"Merritt Island Senior High",63,1587,1189.91,18.89,2039,-5,35.16]
[null,"Palm Bay Senior High",90,2062,2070.1,23,2037,-22,29.96]
[null,"Rockledge Senior High",54,1492,1389.22,25.73,1587,4,27.36]
[null,"Satellite Senior High",57,1469,1330.14,23.34,1986,0,34.84]
[null,"Titusville High ",95,2211,2012.97,21.19,2117,3,21.6]
[null,"West Shore Jr./Sr. High",37,1137,"-","-",925,0,25]
[null,"Rockledge Center",24,536,167.36,6.97,0,0,0]
[null,"Devereux Normandy",5,45,129.2,25.84,46,0,9.2]
["2e.","BREVARD  Total",3189,74330,67140.33,"District Avg 21",70677,-276,"District Avg 24"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year.  (See Note)"]
[]
[]
[]
[null,"Site                              ",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR AVERAGE"]
[null,"Roy Allen Elementary",null,297,297,0,0,0,118.8]
[null,"Hans Christian Anderson Elementary",null,21,21,21,0,0,12.6]
[null,"Apollo Elementary",null,0,0,0,0,0,0]
[null,"Atlantis Elementary",null,0,0,0,0,0,0]
[null,"Audubon Elementary",null,133,133,0,0,0,53.2]
[null,"Cambridge Elementary",null,185,185,165,11,0,109.2]
[null,"Cape View Elementary",null,0,0,0,0,0,0]
[null,"Lewis Carroll Elementary",null,166,166,146,21,0,99.8]
[null,"Challenger 7 Elementary ",null,0,0,0,0,0,0]
[null,"Columbia Elementary",null,196,196,196,42,0,126]
[null,"Coquina Elementary",null,0,0,0,0,0,0]
[null,"Dr. W. J. Creel Elementary",null,20,20,20,0,0,12]
[null,"Croton Elementary",null,0,0,0,0,0,0]
[null,"Discovery Elementary",null,282,282,262,42,0,173.6]
[null,"Endeavour Elementary",null,197,197,197,75,0,133.2]
[null,"Enterprise Elementary",null,0,0,0,0,0,0]
[null,"Fairglen Elementary",null,61,61,41,0,0,32.6]
[null,"Gardendale Elementary",null,231,231,215,65,0,148.4]
[null,"Gemini Elementary",null,106,106,106,21,0,67.8]
[null,"Golfview Elementary",null,117,117,111,0,0,69]
[null,"Harbor City Elementary",null,75,75,75,0,0,45]
[null,"Spessard L. Holland Elementary",null,0,0,0,0,0,0]
[null,"Imperial Estates Elementary",null,0,0,0,0,0,0]
[null,"Indialantic Elementary",null,232,232,232,0,0,139.2]
[null,"Jupiter Elementary",null,155,155,155,42,0,101.4]
[null,"Longleaf Elementary",null,84,84,84,0,0,50.4]
[null,"Lockmar Elementary",null,6,6,0,0,0,2.4]
[null,"Christa McAuliffe Elementary",null,161,161,141,0,0,92.6]
[null,"Meadowlane Elementary",null,152,152,112,0,0,83.2]
[null,"Mila Elementary",null,56,56,50,21,0,36.6]
[null,"Mims Elementary",null,283,283,243,33,0,168.4]
[null,"Oak Park Elementary",null,49,49,7,7,0,22.4]
[null,"Ocean Breeze Elementary",null,56,56,56,30,0,39.6]
[null,"Palm Bay Elementary",null,224,224,203,84,0,147]
[null,"Pinewood Elementary",null,0,0,0,0,0,0]
[null,"Port Malabar Elementary",null,170,170,145,66,0,110.2]
[null,"Riverview Elementary",null,137,137,88,91,0,90.6]
[null,"Riviera Elementary",null,6,6,0,0,0,2.4]
[null,"Theodore Roosevelt Elementary",null,12,12,0,0,0,4.8]
[null,"Sabal Elementary",null,137,137,137,55,0,93.2]
[null,"Saturn Elementary ",null,63,63,42,0,0,33.6]
[null,"Sea Park Elementary",null,12,12,6,0,0,6]
[null,"Sherwood Elementary",null,0,0,0,0,0,0]
[null,"South Lake Elementary",null,100,100,57,51,0,61.6]
[null,"Devereux South Pine Grove School",null,0,0,0,0,0,0]
[null,"Suntree Elementary",null,0,0,0,0,0,0]
[null,"Surfside Elementary",null,66,66,66,21,0,43.8]
[null,"Tropical Elementary",null,167,167,146,66,0,109.2]
[null,"John F. Turner Sr. Elementary",null,192,192,192,0,0,115.2]
[null,"University Park Elementary",null,222,222,202,73,0,143.8]
[null,"Westside Elementary",null,0,0,0,0,0,0]
[null,"Ralph M. Williams Jr. Elementary",null,84,84,84,null,null,84]
[null,"Freedom 7 Elementary",null,0,0,0,0,0,0]
[null,"West Melbourne Elementary",null,0,0,0,0,0,0]
[null,"Robert L. Stevenson Elementary",null,0,0,0,0,0,0]
[null,"Whispering Hills Primary School",null,0,0,0,0,0,0]
[null,"Central Middle ",null,0,0,0,0,0,0]
[null,"Clearlake Middle",null,0,0,0,0,0,0]
[null,"DeLaura Middle",null,0,0,0,0,0,0]
[null,"Edgewood Middle",null,6,6,6,0,0,3.6]
[null,"Herbert C. Hoover Middle",null,0,0,0,0,0,0]
[null,"Andrew Jackson Middle",null,0,0,0,0,0,0]
[null,"Thomas Jefferson Middle",null,12,12,12,10,0,9.2]
[null,"Lyndon B. Johnson Middle",null,0,0,0,96,0,19.2]
[null,"John F. Kennedy Middle",null,32,32,32,35,0,26.2]
[null,"Ronald McNair Middle",null,0,0,0,0,0,0]
[null,"James Madison Middle",null,22,22,22,0,0,13.2]
[null,"Southwest Middle",null,0,0,0,0,0,0]
[null,"Space Coast Middle ",null,0,0,0,0,0,0]
[null,"Stone Middle",null,0,0,0,0,0,0]
[null,"Astronaut High",null,72,72,72,0,0,43.2]
[null,"Bayside High",null,0,0,0,0,0,0]
[null,"Cocoa Beach Jr./Sr. High",null,166,166,166,0,0,99.6]
[null,"Cocoa Senior High",null,24,24,24,0,0,14.4]
[null,"Eau Gallie Senior High",null,350,350,350,0,0,210]
[null,"Melbourne Senior High",null,24,24,24,0,0,14.4]
[null,"Merritt Island Senior High",null,247,247,247,0,0,148.2]
[null,"Palm Bay Senior High",null,544,544,544,120,0,350.4]
[null,"Rockledge Senior High",null,72,72,72,0,0,43.2]
[null,"Satellite Senior High",null,378,378,378,0,0,226.8]
[null,"Titusville High ",null,0,0,0,0,0,0]
[null,"West Shore Jr./Sr. High",null,0,0,0,0,0,0]
["2f.","BREVARD  Total students in relocatables by year",null,6862,6862,5952,1178,0,4170.8]
[null,"Total number of CO-FTE students projected by year",null,68331,67639,68533,69328,69697,68705.6]
[null,"Percent in relocatables by year",null,0.1,0.1,0.09,0.02,0,0.06]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[]
[null,"None."]
[{"$nulls":11},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":8},"Year",1997,1997,1997,1997,1997,1997]
[{"$nulls":10},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":10},1,96,112,147,8492,13172,19094]
[null,"1997 State-wide totals - Gross Sq Ft per student station: Elem low 96, avg 112, high 147; Middle low 68, avg 108, high 131; High School low 127, avg 150, high 178 ",{"$nulls":8},2,68,108,131,11596,14169,17037]
[null,"1997 State-wide totals - Cost per student station: Elem low 8,341, avg 11,305, high 16,402; Middle low 7,478,avg 12,759, high 15,800; High School low 13,985, avg 20,182, high  28,785 ",{"$nulls":8},3,127,150,178,11385,25596,64760]
[]
["3a.","1999-2000 Year","Type of School (new schools only)  Others=0","1999-00","1999-00","1999-00","1999-00","1997 State Avg","1997 State Avg","1997 State Avg","1999 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Elementary School \"Q\"",1,10213994,940,112164,119.32,96,112]
[null,"Portable Classroom Replacement"]
[null,"Roy Allen Elementary",1,3552433,450,22077,49.06,96,112]
[null,"Remodel",{"$nulls":5},0,0]
[null,"Audubon Elementary",1,278834,17,2498,146.94,96,112]
["3a","BREVARD  Total 1999-00",null,3831267,467,24575,52.62,null,null,null,8204]
[]
["3b.","2000-2001 Year","Type of School (new schools only)  Others=0","2000-01","2000-01","2000-01","2000-01","1997 State Avg","1997 State Avg","1997 State Avg","2000 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Portable Classroom Replacement"]
[null,"Cambridge Elementary",1,164020,10,1424,142.4,96,112]
[null,"Mims Elementary",1,4510550,275,14503,52.74,96,112]
[null,"Palm Bay Elementary",1,1640200,100,5016,50.16,96,112]
[null,"Merritt Island Senior High",3,6735690,234,8868,37.9,127,150]
[null,"Palm Bay Senior High",3,1813455,63,8905,141.35,127,150]
[null,"Satellite Senior High",3,12064878,574,38124,66.42,127,150]
[null,"Remodel",1,1982192,180,19108,106.16,96,112]
[null,"Mims Elementary",1,180442,11,831,75.55,96,112]
[null,"Merritt Island Senior High",3,460560,16,2848,178,127,150]
[null,"Palm Bay Senior High",3,805980,28,4984,178,127,150,178,28785,13985,20182,28785]
["3b","BREVARD  Total 2000-01",null,17307507,872,74800,85.78,null,null,null,19848.06]
[]
["3c.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02","1997 State Avg","1997 State Avg","1997 State Avg","2001 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Classroom Additions"]
[null,"Croton Elementary",1,820100,50,2563,51.26,96,112]
[null,"Lyndon B. Johnson Middle",2,1564200,99,8247,83.3,68,108]
[null,"James Madison Middle",2,3566357,259,18967,73.23,68,108]
[null,"Portable Classroom Replacement"]
[null,"Gardendale Elementary",1,4568888,315,14547,46.18,96,112]
[null,"Ocean Breeze Elementary",1,1230150,75,3844,51.25,96,112]
[null,"Riverview Elementary",1,1414217,150,7359,49.06,96,112]
[null,"Tropical Elementary",1,2460300,150,9922,66.15,96,112]
[null,"Cocoa Beach Jr./Sr. High",3,5442250,204,14132,69.27,127,150]
[null,"Eau Gallie Senior High",3,1740067,102,9836,96.43,127,150]
[null,"Remodel"]
[null,"Coquina Elementary",1,1312160,80,11760,147,96,112]
[null,"Tropical Elementary",1,1148140,70,10290,147,96,112,147,16402,8341,13305,16402]
["3c.","BREVARD  Total 2001-02",null,9642617,456,46018,100.92,null,null,null,21146.09]
[]
["3d.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","1997 State Avg","1997 State Avg","1997 State Avg","2002 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Classroom Additions"]
[null,"Herbert C. Hoover Middle",2,884800,56,5711,101.98,68,108]
[null,"Andrew Jackson Middle",2,884800,56,5711,101.98,68,108]
[null,"Ronald McNair Middle",2,442400,28,3103,110.82,68,108]
[null,"Portable Classroom Replacement"]
[null,"Gemini Elementary",1,3618162,265,12190,46,96,112]
[null,"Harbor City Elementary",1,1968240,120,4514,37.62,96,112]
[null,"Sabal Elementary",1,3280400,200,10032,50.16,96,112]
[null,"Saturn Elementary",1,1964213,220,9640,43.82,96,112]
[null,"Surfside Elementary",1,4264520,260,13909,53.5,96,112]
[null,"Edgewood Middle",2,1437800,91,9649,106.03,68,108]
[null,"Astronaut High",3,5175638,229,20368,88.94,127,150]
[null,"Remodel"]
[null,"Endeavour Elementary",1,520778,59,2321,39.34,96,112]
["3d","BREVARD  Total 2002-03",null,520778,59,2321,39.34,null,null,null,8826.75]
[]
["3e.","2003-04 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1997 State Avg","1997 State Avg","1997 State Avg","1998 Projected","1997 State Avg","1997 State Avg","1997 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Classroom Additions"]
[null,"Clearlake Middle",2,1437800,91,9649,106.03,68,108]
[null,"DeLaura Middle",2,884800,56,5711,101.98,68,108]
[null,"Portable Classroom Replacement"]
[null,"Indialantic Elementary",1,3854470,235,12737,54.2,96,112]
[null,"Sea Park Elementary",1,1230150,75,3844,51.25,96,112]
[null,"South Lake Elementary",1,3362410,205,9878,48.19,96,112]
[null,"Thomas Jefferson Middle",2,884800,56,5711,101.98,68,108]
[null,"John F. Kennedy Middle",2,884800,56,5711,101.98,68,108]
[null,"Cocoa Senior High",3,805980,28,3103,110.82,127,150]
[null,"Remodel"]
[null,"Mila Elementary",1,164020,10,1470,147,96,112]
["3e.","BREVARD  Total 1998-99",null,970000,38,4573,120.34,null,null,null,25526.32]
[]
["3f.","BREVARD  5-Year Total",null,32272169,1892,152287,399]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the projects included"]
[null,"in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc. (See Note)"]
[]
[]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,0,0,0,0,0,0]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,31846256,32323949.839999996,32808809.087599993,33300941.22391399,33800455.3422727,164080411.4937867]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,30253943,30707752.144999996,31168368.427174993,31635893.953582615,32110432.36288635,155876389.88864395,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,2000000,2100000,2205000,2315250,2431012.5,11051262.5,0.0708976035940714]
[null,"  less amount used to purchase other vehicles",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used for maintenance/repair",null,630000,661500,694575,729303.75,765768.9375,3481147.6875,0.0223327451321325]
[null,"  less amount used to purchase capital outlay equipment",null,787500,826875,868218.75,911629.6875,957211.171875,4351434.609375,0.0279159314151656]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,26000000,20800000,15600000,10400000,5200000,78000000,0.500396500430387]
[null,"  less amount to pay debt service for COP's ",null,0,0,0,0,0,0,0]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"Source %"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,836443,6319377.144999996,11800574.677174993,17279710.516082615,22756439.75351135,58992545.09176895,0.378457219428243,0.33]
[null,"P E C O New Construction",null,4336544,1740770,2641615,3276938,2931161,14927028,null,0.08]
[null,"P E C O Maintenance",null,2782979,4017073,3824855,3810926,3827641,18263474]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,20000000,15000000,10000000,5000000,0,50000000,null,0.28]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,0,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,10213994,0,0,0,0,10213994,null,0.06]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Carryover 1998-99",null,26000000,0,0,0,0,26000000]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0]
["4.","BREVARD  Total",null,64169960,27077220.144999996,28267044.677174993,29367574.516082615,29515241.75351135,178397041.09176895]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[]
[null,"Project Description","Location","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"Fire Safety & ADA","Various",280321,294337.05,309053.9025,324506.59762500005,340731.9275062501,1548950.4776312502]
[null,"Major Maintenance","Various",1565232,1565250,1565250,1565250,1565250,7826232]
[null,"Paving","Various",545842,546000,546000,546000,546000,2729842]
[null,"Renovate / Site Improvements","Various",4489309,4500000,4500000,4500000,4500000,22489309]
[null,"Roofing Repairs","Various",2162900,500000,500000,500000,500000,4162900]
[null,"Maintenance Projects","Various",2504681,2500000,2500000,2500000,2500000,12504681]
[null,"Re-roofing Projects"]
[null,null,"Eau Gallie Senior High + HVAC Replacement",5126305,0,0,0,0,5126305]
[null,null,"Melbourne High",945194,0,0,0,0,945194]
[null,null,"Riverview Elementary",554760,0,0,0,0,554760]
[null,null,"Rockledge  High (Partial)",785494,0,0,0,0,785494]
[null,null,"Rockledge Elementary",157335,0,0,0,0,157335]
[null,null,"Capeview Elementary",919125,0,0,0,0,919125]
[null,null,"DeLaura Jr. High",926959,0,0,0,0,926959]
[null,null,"Devereux South Pine Grove",133685,0,0,0,0,133685]
[null,null,"Dr. W. J. Creel Elementary",350135,0,0,0,0,350135]
[null,null,"Apollo Elementary (Partial)",152382,0,0,0,0,152382]
[null,null,"Coquina Elementary (Partial)",166289,0,0,0,0,166289]
[null,null,"Gardendale Elementary (Partial)",92671,0,0,0,0,92671]
[null,null,"Surfside Elementary (Partial)",228648,0,0,0,0,228648]
[null,null,"Fairglen Elementary (Partial)",136421,0,0,0,0,136421]
[null,null,"Oak Park Elementary (Partial)",149039,0,0,0,0,149039]
[null,null,"Pinewood Elementary (Partial)",107331,0,0,0,0,107331]
[null,null,"Tropical Elementary (Partial)",16099,0,0,0,0,16099]
[null,null,"Kennedy Middle (Partial)",1541554,0,0,0,0,1541554]
[null,null,"Edgewood Middle (Partial)",1062580,0,0,0,0,1062580]
[null,null,"Ronald McNair Middle (Partial)",937,0,0,0,0,937]
[null,null,"Golfview Elementary (Partial)",1059582,0,0,0,0,1059582]
[null,null,"Stone Middle (Partial) ",133997,0,0,0,0,133997]
[null,null,"Astronaut High (Partial)",201770,0,0,0,0,201770]
[null,null,"Cocoa Beach Jr./Sr. High (Partial)",7053,0,0,0,0,7053]
[null,null,"Merritt Island Senior High (Partial)",87174,0,0,0,0,87174]
[null,null,"Satellite High (Partial)",218276,0,0,0,0,218276]
[null,null,"Titusville High (Partial) ",4324,0,0,0,0,4324]
[null,null,"West Shore Jr./Sr. High (Partial)",176028,0,0,0,0,176028]
[null,null,"West Melbourne Elementary",1090422,0,0,0,0,1090422]
[null,null,"Whispering Hills Primary",454899,0,0,0,0,454899]
[null,null,"Freedom 7 Elementary",570327,0,0,0,0,570327]
[null,"Safety to Life ","Various",288031,311016,317156,331572,349122,1596897]
[null,"Health & Safety","Various",5168498,5200000,5200000,5200000,5200000,25968498]
[null,"Portable Lease","Various",821491,830000,750000,400000,100000,2901491]
[null,"Portable Renovation & Repair","Various",262332,250000,150000,100000,50000,812332]
[null,"Portable Relocation","Various",251084,250000,250000,150000,150000,1051084]
[null,"HVAC Upgrades/Replacements","Various",2200000,0,0,0,0,2200000]
[null,null,"Stone Middle",1617359,0,0,0,0,1617359]
[null,"Technology Enhancements","Various",14571,0,0,0,0,14571]
[null,"Bus Compound Renovations","Melbourne Bus Parking/Service Area",862420,0,0,0,0,862420]
[null,null,"Bus Maintenance Building - Stone",108933,0,0,0,0,108933]
[null,"Covered Eating Area"]
[null,null,"Merritt Island Senior High",120000,0,0,0,0,120000]
[null,null,"Titusville High ",120000,0,0,0,0,120000]
[null,null,"Eau Gallie Senior High",120000,0,0,0,0,120000]
[null,"Athletic / P. E. Fields","West Shore Jr./Sr. High",250000,0,0,0,0,250000]
[null,"Custodial Equipment","Various",446763,250000,250000,250000,250000,1446763]
[null,"Elementary School \"Q\"","Melbourne Area",10213994,{"$nulls":4},10213994]
[null,"Music Building","Titusville High",1009000,{"$nulls":4},1009000]
[null,"Remodel / Renovate Projects"]
[null,null,"Freedom 7 Elementary",2509000,{"$nulls":4},2509000]
[null,null,"West Melbourne Elementary",2527500,{"$nulls":4},2527500]
[null,null,"Robert L. Stevenson Elementary",726250,{"$nulls":4},726250]
[null,null,"Whispering Hills Primary School",1082000,{"$nulls":4},1082000]
[null,"HVAC Upgrades/Replacements"]
[null,null,"Roy Allen Elementary",0,null,1400000,0,0,1400000]
[null,null,"Hans Christian Anderson Elementary",0,0,0,1202000,0,1202000]
[null,null,"Apollo Elementary (Partial)",0,768617,0,0,0,768617]
[null,null,"Atlantis Elementary",0,0,0,0,1176000,1176000]
[null,null,"Audubon Elementary",0,null,963000,0,0,963000]
[null,null,"Cambridge Elementary",0,0,0,1322000,0,1322000]
[null,null,"Cape View Elementary",0,1494000,0,0,0,1494000]
[null,null,"Challenger 7 Elementary ",0,0,0,1743000,0,1743000]
[null,null,"Columbia Elementary",0,0,0,1743000,0,1743000]
[null,null,"Coquina Elementary",0,1133000,0,0,0,1133000]
[null,null,"Dr. W. J. Creel Elementary",0,0,1867000,0,0,1867000]
[null,null,"Croton Elementary",0,2266000,0,0,0,2266000]
[null,null,"Discovery Elementary",0,0,0,0,248000,248000]
[null,null,"Endeavour Elementary",0,0,0,0,310000,310000]
[null,null,"Enterprise Elementary",0,0,0,0,1176000,1176000]
[null,null,"Gardendale Elementary",0,0,2217000,0,0,2217000]
[null,null,"Golfview Elementary",0,0,0,1082000,0,1082000]
[null,null,"Harbor City Elementary",0,0,0,0,1857000,1857000]
[null,null,"Imperial Estates Elementary",0,0,0,0,338000,338000]
[null,null,"Indialantic Elementary",0,0,0,0,506000,506000]
[null,null,"Lockmar Elementary (Partial)",0,0,0,919246,0,919246]
[null,null,"Christa McAuliffe Elementary",0,0,0,1743000,0,1743000]
[null,null,"Mila Elementary",0,0,0,0,805000,805000]
[null,null,"Mims Elementary",0,0,0,0,1609000,1609000]
[null,null,"Oak Park Elementary",0,0,1400000,0,0,1400000]
[null,null,"Ocean Breeze Elementary",0,0,1167000,0,0,1167000]
[null,null,"Port Malabar Elementary",0,0,0,1623000,0,1623000]
[null,null,"Riverview Elementary",0,0,0,1623000,0,1623000]
[null,null,"Riviera Elementary",0,0,0,0,1176000,1176000]
[null,null,"Theodore Roosevelt Elementary",0,1700000,0,0,0,1700000]
[null,null,"Sabal Elementary",0,1246000,0,0,0,1246000]
[null,null,"Saturn Elementary ",0,1473000,0,0,0,1473000]
[null,null,"Sea Park Elementary (Partial)",0,0,1015585,0,0,1015585]
[null,null,"South Lake Elementary",0,0,0,0,563000,563000]
[null,null,"Surfside Elementary",0,0,1400000,0,0,1400000]
[null,null,"University Park Elementary",0,0,0,0,929000,929000]
[null,null,"Clearlake Middle",0,0,0,0,450000,450000]
[null,null,"John F. Kennedy Middle",0,0,0,0,394000,394000]
[null,null,"Cocoa Senior High",0,0,0,0,338000,338000]
[null,null,"Melbourne Senior High",0,0,0,0,732000,732000]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,450000,450000]
[null,null,"Rockledge Center (Partial)",0,0,0,0,407138,407138]
["5.","BREVARD  Total",null,59824306,27077220.05,28267044.9025,29367574.597625002,29515241.92750625,174051387.47763124]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"SIT Program award received","3 Charter Schools (50%)",836677,0,0,0,0,836677]
[null,"SIT Program award pending","Williams & Westside Elem. + Bayside High ",4500000,0,0,0,0,4500000]
[null,"Other (specify) - pending approval","Appropriation 19A",612230,0,0,0,0,612230]
["6.","BREVARD  Total",null,5948907,0,0,0,0,5948907]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[]
[null,"Project Description",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"HVAC Upgrades/Replacements"]
[null,null,"Apollo Elementary (Partial)",0,261383,0,0,0,261383]
[null,null,"Lockmar Elementary (Partial)",0,0,0,42754,0,42754]
[null,null,"Pinewood Elementary",0,0,0,721000,0,721000]
[null,null,"Sea Park Elementary (Partial)",0,0,268415,0,0,268415]
[null,null,"Tropical Elementary",0,0,0,1442000,0,1442000]
[null,null,"John F. Turner Sr. Elementary",0,0,0,721000,0,721000]
[null,null,"DeLaura Middle",0,0,2334000,0,0,2334000]
[null,null,"Edgewood Middle",0,0,2451000,0,0,2451000]
[null,null,"Herbert C. Hoover Middle",0,0,1517000,0,0,1517000]
[null,null,"Andrew Jackson Middle",0,1700000,0,0,0,1700000]
[null,null,"Thomas Jefferson Middle",0,0,1517000,0,0,1517000]
[null,null,"Lyndon B. Johnson Middle",0,1700000,0,0,0,1700000]
[null,null,"James Madison Middle",0,1813000,0,0,0,1813000]
[null,null,"Ronald McNair Middle",0,1133000,0,0,0,1133000]
[null,null,"Astronaut High",0,0,0,4928000,0,4928000]
[null,null,"Southwest Middle (Partial)",0,0,0,2404000,0,2404000]
[null,null,"Cocoa Beach Jr./Sr. High",0,2493000,0,0,0,2493000]
[null,null,"Merritt Island Senior High",0,0,4668000,0,0,4668000]
[null,null,"Palm Bay Senior High",0,2833000,0,0,0,2833000]
[null,null,"Rockledge Senior High",0,0,0,1683000,0,1683000]
[null,null,"Satellite Senior High",0,0,2917000,0,0,2917000]
[null,null,"Titusville High ",0,1246000,0,0,0,1246000]
[null,null,"Rockledge Center (Partial)",0,0,0,0,592862,592862]
[null,"Vocational Lab. Upgrades","Various",0,950000,950000,950000,950000,3800000]
[null,"Kitchen Upgrades","Various",0,250000,250000,null,null,500000]
[null,"Remodel / Renovate Projects"]
[null,null,"Roy Allen Elementary",0,1802541,0,0,0,1802541]
[null,null,"Hans Christian Anderson Elementary",0,0,0,3076255,0,3076255]
[null,null,"Apollo Elementary",0,0,3514416,0,0,3514416]
[null,null,"Audubon Elementary",0,2663160,0,0,0,2663160]
[null,null,"Cambridge Elementary",0,1547220,0,null,0,1547220]
[null,null,"Cape View Elementary",0,2806975,0,0,0,2806975]
[null,null,"Challenger 7 Elementary ",0,0,0,282681,0,282681]
[null,null,"Columbia Elementary",0,0,0,296265,0,296265]
[null,null,"Coquina Elementary",0,2461913,0,0,0,2461913]
[null,null,"Dr. W. J. Creel Elementary",0,0,2948803,0,0,2948803]
[null,null,"Croton Elementary",0,2103614,0,0,0,2103614]
[null,null,"Discovery Elementary",0,0,0,0,215834,215834]
[null,null,"Endeavour Elementary",0,0,0,0,520773,520773]
[null,null,"Gardendale Elementary",0,0,2314736,0,0,2314736]
[null,null,"Gemini Elementary",0,0,0,0,2689217,2689217]
[null,null,"Golfview Elementary",0,0,0,1634644,0,1634644]
[null,null,"Harbor City Elementary",0,0,0,0,2634520,2634520]
[null,null,"Spessard L. Holland Elementary",0,0,0,0,504226,504226]
[null,null,"Imperial Estates Elementary",0,0,0,0,201930,201930]
[null,null,"Indialantic Elementary",0,0,0,0,1433729,1433729]
[null,null,"Lockmar Elementary",0,0,0,2720824,0,2720824]
[null,null,"Christa McAuliffe Elementary",0,0,0,251521,0,251521]
[null,null,"Mila Elementary",0,0,0,0,2613599,2613599]
[null,null,"Mims Elementary",0,1957059,0,0,0,1957059]
[null,null,"Oak Park Elementary",0,0,3219060,0,0,3219060]
[null,null,"Ocean Breeze Elementary",0,0,2867101,0,0,2867101]
[null,null,"Palm Bay Elementary",0,0,0,2394961,0,2394961]
[null,null,"Pinewood Elementary",0,1638972,0,0,0,1638972]
[null,null,"Port Malabar Elementary",0,0,0,1231641,0,1231641]
[null,null,"Riverview Elementary",0,2696800,0,0,0,2696800]
[null,null,"Theodore Roosevelt Elementary",0,4114685,0,0,0,4114685]
[null,null,"Sabal Elementary",0,2755825,0,0,0,2755825]
[null,null,"Saturn Elementary ",0,3348264,0,0,0,3348264]
[null,null,"Sea Park Elementary",0,0,2398834,0,0,2398834]
[null,null,"South Lake Elementary",0,0,2862574,0,0,2862574]
[null,null,"Surfside Elementary",0,0,2060113,0,0,2060113]
[null,null,"Tropical Elementary",0,3171112,0,0,0,3171112]
[null,null,"John F. Turner Sr. Elementary",0,0,0,1833808,0,1833808]
[null,null,"University Park Elementary",0,0,0,0,612453,612453]
[null,null,"Central Middle ",0,0,0,113031,0,113031]
[null,null,"Clearlake Middle (Partial)",0,0,0,0,348373,348373]
[null,null,"DeLaura Middle",0,4980043,0,0,0,4980043]
[null,null,"Edgewood Middle",0,0,4656802,0,0,4656802]
[null,null,"Herbert C. Hoover Middle",0,0,4728660,0,0,4728660]
[null,null,"Andrew Jackson Middle",0,4843189,0,0,0,4843189]
[null,null,"Thomas Jefferson Middle",0,0,5124785,0,0,5124785]
[null,null,"Lyndon B. Johnson Middle",0,5560060,0,0,0,5560060]
[null,null,"John F. Kennedy Middle",0,0,0,0,5761236,5761236]
[null,null,"Ronald McNair Middle",0,1953537,0,0,0,1953537]
[null,null,"James Madison Middle",0,5228907,0,0,0,5228907]
[null,null,"Southwest Middle",0,0,0,90008,0,90008]
[null,null,"Space Coast Middle ",0,0,0,0,9999,9999]
[null,null,"Stone Middle",0,2160621,0,0,0,2160621]
[null,null,"Astronaut High",0,0,0,5402151,0,5402151]
[null,null,"Cocoa Beach Jr./Sr. High",0,2621430,0,0,0,2621430]
[null,null,"Cocoa Senior High",0,0,0,0,1009010,1009010]
[null,null,"Eau Gallie Senior High",0,0,0,0,8366894,8366894]
[null,null,"Melbourne Senior High",0,0,0,0,3774459,3774459]
[null,null,"Merritt Island Senior High",0,0,10098966,0,0,10098966]
[null,null,"Palm Bay Senior High",0,7844106,0,0,0,7844106]
[null,null,"Rockledge Senior High",0,0,0,3378932,0,3378932]
[null,null,"Satellite Senior High",0,0,10776395,0,0,10776395]
[null,null,"Titusville High ",0,7136948,0,0,0,7136948]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,471270,471270]
[null,null,"520 Compound",0,0,0,1185840,0,1185840]
[null,null,"Bus Garage & Maintenance Shop (North Area)",0,0,0,0,137700,137700]
[null,null,"Rockledge Center",0,0,0,0,22130,22130]
[null,null,"Satellite Bus Compound",0,0,0,0,139266,139266]
[null,"Classroom Additions"]
[null,null,"Roy Allen Elementary",0,3552433,0,0,0,3552433]
[null,null,"Gardendale Elementary",0,0,0,4568888,0,4568888]
[null,null,"Gemini Elementary",0,0,3618162,0,0,3618162]
[null,null,"Indialantic Elementary",0,0,0,0,4430082,4430082]
[null,null,"Mims Elementary",0,0,5432684,0,0,5432684]
[null,null,"Ocean Breeze Elementary",0,0,0,3153965,0,3153965]
[null,null,"Palm Bay Elementary",0,0,0,0,3147321,3147321]
[null,null,"Riverview Elementary",0,1414217,0,0,0,1414217]
[null,null,"Sabal Elementary",0,0,3708768,0,0,3708768]
[null,null,"Saturn Elementary ",0,0,0,1964213,0,1964213]
[null,null,"Surfside Elementary",0,0,4834770,0,0,4834770]
[null,null,"South Lake Elementary",0,0,0,0,3462393,3462393]
[null,null,"DeLaura Middle",0,0,null,0,1835539,1835539]
[null,null,"James Madison Middle",0,3566357,0,0,0,3566357]
[null,null,"Astronaut High",0,0,0,5175638,0,5175638]
[null,null,"Cocoa Beach Jr./Sr. High ",0,5442250,0,0,0,5442250]
[null,null,"Eau Gallie Senior High",0,0,0,0,1740067,1740067]
[null,null,"Merritt Island Senior High",0,0,10250281,0,0,10250281]
[null,null,"Palm Bay Senior High",0,0,0,0,3498425,3498425]
[null,null,"Rockledge Senior High",0,0,0,1728002,0,1728002]
[null,null,"Satellite Senior High",0,0,null,0,12064878,12064878]
[null,null,"West Shore Jr./Sr. High",0,0,0,0,5225065,5225065]
[null,"New Additions"]
[null,null,"Apollo Elementary",0,0,0,1799822,0,1799822]
[null,null,"Audubon Elementary",0,0,3107602,0,0,3107602]
[null,null,"Cambridge Elementary",0,0,0,2842851,0,2842851]
[null,null,"Cape View Elementary",0,0,2319005,0,0,2319005]
[null,null,"Coquina Elementary",0,0,0,2241261,0,2241261]
[null,null,"Croton Elementary",0,0,2380916,0,0,2380916]
[null,null,"Endeavour Elementary",0,0,0,0,2354625,2354625]
[null,null,"Golfview Elementary",0,0,0,0,1813675,1813675]
[null,null,"Harbor City Elementary",0,0,0,0,2832250,2832250]
[null,null,"Spessard L. Holland Elementary",0,0,1432592,0,0,1432592]
[null,null,"Imperial Estates Elementary",0,0,0,0,956805,956805]
[null,null,"Lockmar Elementary",0,0,0,1941739,0,1941739]
[null,null,"Mila Elementary",0,0,0,0,2263595,2263595]
[null,null,"Oak Park Elementary",0,0,1361351,0,0,1361351]
[null,null,"Pinewood Elementary",0,0,0,0,725413,725413]
[null,null,"Port Malabar Elementary",0,0,0,0,1941739,1941739]
[null,null,"Theodore Roosevelt Elementary",0,0,0,146157,0,146157]
[null,null,"Sea Park Elementary",0,0,0,3357510,0,3357510]
[null,null,"Tropical Elementary",0,0,0,3596393,0,3596393]
[null,null,"John F. Turner Sr. Elementary",0,0,0,2207620,0,2207620]
[null,null,"University Park Elementary",0,0,0,0,3448964,3448964]
[null,null,"Clearlake Middle",0,0,2124355,0,0,2124355]
[null,null,"Edgewood Middle",0,0,2763490,0,0,2763490]
[null,null,"Herbert C. Hoover Middle",0,0,2376878,0,0,2376878]
[null,null,"Andrew Jackson Middle",0,null,null,1896904,0,1896904]
[null,null,"Thomas Jefferson Middle",0,0,0,2376878,0,2376878]
[null,null,"Lyndon B. Johnson Middle",0,0,0,0,3613592,3613592]
[null,null,"John F. Kennedy Middle",0,0,null,null,2376878,2376878]
[null,null,"Ronald McNair Middle",0,1515833,0,0,2376878,3892711]
[null,null,"Southwest Middle",0,0,0,null,174952,174952]
[null,null,"Stone Middle",0,0,0,0,277042,277042]
[null,null,"Bayside High",0,0,0,0,2072435,2072435]
[null,null,"Cocoa Senior High",0,0,0,0,5389108,5389108]
[null,null,"Titusville High ",0,0,0,0,2072435,2072435]
[null,"Ancillary New Construction"]
[null,null,"Maintenance Department",0,0,0,0,4173758,4173758]
[null,null,"Bus Garage & Maintenance Shop (North Area)",0,0,0,654792,0,654792]
[null,null,"Satellite Bus Compound",0,0,0,323088,0,323088]
["7.","BREVARD  Total",null,0,105267454,120154514,76760037,107277394,409459399]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2 and 1. above, the message \"Check Totals\" appears.  "]
[null," -- They should balance ! !"]
[]
[null,"Project Description",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":9}
["Respectfully submitted this 15 day of  December 1999."]
[]
[null,"SCHOOL BOARD OF ","BREVARD   COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Dr. David E. Sawyer",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"B. Eugene Burkett",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,null,"Assistant Superintendent for Facility Services",null,"321-633-1000, ext. 450","currye@brevard.k12.fl.us",null," "]
[null,null,null,"Edward T. Curry","Job Title",null,"Phone number(s)","E-Mail Address"]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,null,"Construction Estimator/Scheduler",null,"321-633-1000, ext. 657","caussadea@brevard.k12.fl.us"]
[null,null,null,"Anibal E. Caussade","Job Title",null,"Phone number(s)","E-Mail Address",null,null," "]