{"text_format":"2","workbook":"xls","n_sheets":1,"sheets":["Broward 03 WkPln"],"not_rendered":{"charts":0,"images":2,"macros":1,"external_links":6,"defined_names":50,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Broward 03 WkPln","index":0,"n_rows":5246,"n_cols":16,"rows_kept":5246,"cut":false,"hidden":false,"merged":[[3701,1,3701,10],[3710,1,3710,10],[3712,1,3712,10],[3733,1,3733,10],[5198,1,5198,8],[5199,1,5199,8],[3735,2,3735,10],[3756,2,3756,10],[3760,1,3760,10],[3765,2,3765,10]],"flags":["formulas_cached_only"]}
[]
["Broward  SCHOOL DISTRICT - - TENTATIVE FACILITIES WORK PROGRAM"]
["Broward   SCHOOL  DISTRICT - -  WORKSHEET ",{"$nulls":7},"Last Revised"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the Office of Educational Facilities, and a copy submitted ",{"$nulls":7},"2003-10-13"]
["electronically in digital format, as you received it (not a fax), prior to November 1, 2003, and all data accurate as of July 15, 2003."]
["District: ====>",null,"Broward","Date: ==>","2003-12-05",null,"For fiscal years","  2003-2004 through 2007-2008"]
[]
["Section 1013.35 School district facilities 5 - Year work program; definitions; preparation, adoption, and amendment."]
[]
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["2b1","A schedule of major repair and renovation projects necessary to maintain the educational facilities and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Facilities Remodeling & Renovation",{"$nulls":6},0]
[1741,"Flooring And Wheelchair Lift","Anderson, Boyd H High",1000000,"","","","",1000000]
[1741,"Concession Stand ","Anderson, Boyd H High ",91886,{"$nulls":4},91886]
[1741,"Horticulture Complex ","Anderson, Boyd H High ",34250,{"$nulls":4},34250]
[1741,"Repair Ballfield Lights ","Anderson, Boyd H High ",98250,{"$nulls":4},98250]
[1741,"Restrooms for ESE Cluster Program","Anderson, Boyd H High ",83132,{"$nulls":4},83132]
[1741,"Kitchen/Cafeteria","Anderson, Boyd H. High","","",418358,4272318,"",4690676]
[1741,"Remodeling & Renovation","Anderson, Boyd H. High","","","",3629000,"",3629000]
[1791,"Covered Walkway","Apollo Middle",2211,"","","","",2211]
[1791,"Remodeling/ Addition","Apollo Middle",879140,"","","","",879140]
[1791,"HVAC Locker Room","Apollo Middle ",85000,{"$nulls":4},85000]
[9161,"Title I Roofing ","At Risk Programs Admin Site ",220000,{"$nulls":4},220000]
[2221,"Remodel/Renovate Media Center","Atlantic Technical Center","","",202840,1825560,"",2028400]
[343,"Bundled Renovation Projects","Attucks Middle",101420,982760,"","","",1084180]
[343,"Pool Renovations","Attucks Middle ",64425,{"$nulls":4},64425]
[2001,"Enclose Media Ctr, Parent Drop Off","Banyan Elementary","",405680,"","","",405680]
[641,"Playground","Bayview Elementary",115950,"","","","",115950]
[641,"Shoreline Stabilization ","Bayview Elementary ",249900,{"$nulls":4},249900]
[9855,"Air Conditioning","BECON/ITV",13439,"","","","",13439]
[9855,"Remodeling / Expansion","BECON/ITV",17372,"","","","",17372]
[201,"Kitchen/Cafeteria","Bennett Elementary",4056800,"","","","",4056800]
[341,"Overhead Pavilion ","Bethune, Mary M. Elementary",375408,{"$nulls":4},375408]
[341,"Playground","Bethune, Mary M. Elementary",112376,"","","","",112376]
[361,"Regional Athletic Facility","Blanche Ely High","",1669584,"","","",1669584]
[971,"Cafeteria Replacement","Boulevard Heights Elementary",4869266,"","","","",4869266]
[871,"Covered Walkway","Bright Horizons Center ",50000,{"$nulls":4},50000]
[871,"Pool Renovations ","Bright Horizons Center ",13000,{"$nulls":4},13000]
[871,"Two Bathrooms ","Bright Horizons Center ",75000,{"$nulls":4},75000]
[871,"Playground","Bright Horizons Center ","",115950,"","","",115950]
[811,"Remodeling/Renovation","Broadview Elementary","",507100,"","","",507100]
[501,"Cafeteria Replacement","Broward Estates Elementary",2894322,"","","","",2894322]
[2771,"Special Program","Broward Fire Academy",58305,"","","","",58305]
[2771,"Burn Building","Broward Fire Academy ",4265428,{"$nulls":4},4265428]
[3421,"Playground","Carver Ranches Family Res Ctr","",136158,"","","",136158]
[1382,"Demolition","Castle Hill Annex",949223,"","","","",949223]
[1461,"Remodeling/Renovation","Castle Hill Elementary",730000,"","","","",730000]
[2641,"Student Drop-Off","Central Park Elementary",134422,"","","","",134422]
[1421,"8 Classroom Addition ","Coconut Creek Elementary ",1316556,{"$nulls":4},1316556]
[1421,"Covered Walkway","Coconut Creek Elementary ",134940,{"$nulls":4},134940]
[1421,"Painting","Coconut Creek Elementary ",72621,{"$nulls":4},72621]
[1681,"Food Court","Coconut Creek High",200000,1800000,"","","",2000000]
[1681,"Remodeling/Renovation","Coconut Creek High",30000,"","","","",30000]
[1681,"Track Renovation","Coconut Creek High",166959,"","","","",166959]
[1681,"Food Court-Closed Campus ","Coconut Creek High ",141658,{"$nulls":4},141658]
[331,"Kitchen/Cafeteria","Collins Elementary","","","",400000,3600000,4000000]
[1211,"New Cafe / Kitch / Multipurpose Area / Stage","Cooper City Elementary",3437780,"","","","",3437780]
[1931,"Kitchen/Cafeteria","Cooper City High",456390,4107510,"","","",4563900]
[1931,"Remodeling, Renovation & IEQ","Cooper City High",704889,"","","","",704889]
[1931,"Regional Athletic Facility ","Cooper City High ",1528135,{"$nulls":4},1528135]
[1931,"Remodeling/Renovation","Cooper City High ",9602530,{"$nulls":4},9602530]
[3041,"Wetlands Mitigation ","Coral Park Elementary ",191000,{"$nulls":4},191000]
[2551,"Drainage","Coral Springs Elementary","",659230,"","","",659230]
[2551,"Covered Walkway ","Coral Springs Elementary ",31481,{"$nulls":4},31481]
[1151,"Remodeling / Renovation","Coral Springs High",812380,"","","","",812380]
[2561,"Kitchen/Cafeteria","Coral Springs Middle",760650,"","","","",760650]
[3111,"Playground","Country Hills Elementary",141096,"","","","",141096]
[901,"Playground","Cresthaven Elementary","",72470,"","","",72470]
[221,"Drainage","Croissant Park Elementary ",125000,{"$nulls":4},125000]
[221,"Roads ","Croissant Park Elementary ",16391,{"$nulls":4},16391]
[1871,"Remodel Rooms to Science","Crystal Lake Community Middle",152130,"","","","",152130]
[1781,"Drainage","Cypress Elementary",1496,"","","","",1496]
[1781,"Playground","Cypress Elementary","",72470,"","","",72470]
[1781,"Replace Kitchen/Cafeteria","Cypress Elementary",400000,3600000,"","","",4000000]
[101,"Cooling Tower","Dania Elementary","",152130,"","","",152130]
[101,"Kitchen/Cafeteria","Dania Elementary","","",405680,3651120,"",4056800]
[2801,"Lighting ","Davie Elementary",300262,"","","","",300262]
[2801,"Playground","Davie Elementary","",112376,"","","",112376]
[2801,"Classroom Add/Bus Drives ","Davie Elementary ",263270,{"$nulls":4},263270]
[11,"Kitchen/Cafeteria","Deerfield Beach Elementary",4310350,"","","","",4310350]
[11,"Remodeling / Renovation","Deerfield Beach Elementary",150000,"","","","",150000]
[1711,"Food Court","Deerfield Beach High","","",200000,1800000,"",2000000]
[1711,"Regional Athletic Facility","Deerfield Beach High","",1669584,"","","",1669584]
[911,"Pool Replacement ","Deerfield Beach Middle ",953408,{"$nulls":4},953408]
[911,"Portable Restrooms","Deerfield Beach Middle ",30000,{"$nulls":4},30000]
[911,"Remodel Lounge 3 classroom","Deerfield Beach Middle ",16726,{"$nulls":4},16726]
[391,"Bus Drive","Deerfield Park Elementary",405680,"","","","",405680]
[271,"Playground","Dillard Elementary","",112376,"","","",112376]
[271,"Playground","Dillard Elementary","",72470,"","","",72470]
[371,"Food Court","Dillard High",265000,2385000,"","","",2650000]
[0,"Asbestos Abatement","District Wide",3779660,{"$nulls":4},3779660]
[0,"Contingency","District Wide",30150451,10198000,3950000,4300000,4248277,52846728]
[0,"Design Fees","District Wide",2573478,1000000,"","","",3573478]
[0,"Restroom Renovations Reserve","District Wide",3000000,"","","","",3000000]
[0,"Ancillary Facilities","District Wide ",2446000,{"$nulls":4},2446000]
[0,"Asbestos","District Wide ",478881,2548000,2548000,"","",5574881]
[0,"Asbestos","District Wide ",174496,{"$nulls":4},174496]
[0,"Asbestos ","District Wide ",101820,{"$nulls":4},101820]
[0,"Class Size Reduction Renovations","District Wide ",490000,{"$nulls":4},490000]
[0,"Closed Campus High Schools ","District Wide ",608382,{"$nulls":4},608382]
[0,"Contingency Misc Structure Repairs","District Wide ",644876,{"$nulls":4},644876]
[0,"Estimating/Master Plan/Inspections","District Wide ",172000,{"$nulls":4},172000]
[0,"Inspections (Fire) ","District Wide ",18871,{"$nulls":4},18871]
[0,"Remodeling Contingency","District Wide ",40511,{"$nulls":4},40511]
[0,"Roads ","District Wide ",1162584,{"$nulls":4},1162584]
[0,"Teacher Training Center","District Wide ",302006,{"$nulls":4},302006]
[0,"Wellfield Protect/Water Mgmt ","District Wide ",333426,{"$nulls":4},333426]
[0,"Wetlands Mitigation ","District Wide ",125795,{"$nulls":4},125795]
[301,"Playground","Drew Resource Center",237578,"","","","",237578]
[3221,"Playground","Drew, Charles Elementary",141096,"","","","",141096]
[721,"Playground","Driftwood Elementary",141096,"","","","",141096]
[721,"Remodeling/Renovation","Driftwood Elementary",1185000,"","","","",1185000]
[861,"Remodeling/Renovation","Driftwood Middle",93000,"","","","",93000]
[861,"Drainage","Driftwood Middle ",125000,{"$nulls":4},125000]
[3441,"Drainage","Eagle Ridge Elementary",150000,"","","","",150000]
[3441,"Playground","Eagle Ridge Elementary",353566,"","","","",353566]
[9603,"Open End Contracts","Facilities Department ",2586185,{"$nulls":4},2586185]
[9603,"Spec Funding ","Facilities Department ",10504,{"$nulls":4},10504]
[1641,"Playground","Fairway Elementary","",112376,"","","",112376]
[1641,"Playground","Fairway Elementary","",72470,"","","",72470]
[1641,"Corridors ","Fairway Elementary ",63415,{"$nulls":4},63415]
[1641,"Drainage ","Fairway Elementary ",59043,{"$nulls":4},59043]
[2541,"Additional for Roofing Project","Flamingo Elementary",101000,"","","","",101000]
[2541,"Drainage","Flamingo Elementary",181136,{"$nulls":4},181136]
[2541,"Drainage","Flamingo Elementary ",40439,"","","","",40439]
[3392,"Move To Main Campus ","Flanagan High Annex ",39300,{"$nulls":4},39300]
[851,"Demolish Blding/Construct Play","Floranada Elementary ",162483,{"$nulls":4},162483]
[2631,"Playground","Forest Hills Elementary","",141096,"","","",141096]
[951,"Remodeling/Renovation","Fort Lauderdale High",450000,"","","","",450000]
[951,"Refinish Basketball Gym Floor ","Fort Lauderdale High ",30000,{"$nulls":4},30000]
[921,"Pagoda Walkway Replace/Repair ","Foster, Stephen Elementary",94683,{"$nulls":4},94683]
[921,"Kitchen/Cafeteria","Foster, Stephen Elementary","","","",400000,3600000,4000000]
[592,"Playground","Hallandale Adult/Community","",129908,"","","",129908]
[592,"Remodeling/Renovation","Hallandale Adult/Community",175000,"","","","",175000]
[403,"Auditorium Renovations","Hallandale High",111305,"","","","",111305]
[403,"Remodeling and Renovation","Hallandale High",4452268,"","","","",4452268]
[403,"Site Improvements","Hallandale High","",222611,"","","",222611]
[403,"Renovations ","Hallandale High ",401994,{"$nulls":4},401994]
[491,"Remodeling / New Construction","Harbordale Elementary",3206208,"","","","",3206208]
[491,"Replace Old Buildings","Harbordale Elementary",400000,3600000,"","","",4000000]
[3131,"Drainage /IEQ","Hawkes Bluff Elementary",101420,912780,"","","",1014200]
[121,"Remodel Specialized Classrooms","Hollywood Central Elementary ",95000,{"$nulls":4},95000]
[111,"Kitchen/Cafeteria","Hollywood Hills Elementary",4044020,"","","","",4044020]
[1661,"Food Court","Hollywood Hills High","",200000,1800000,"","",2000000]
[1661,"Remodeling And Renovation","Hollywood Hills High",4340800,409589,"","","",4750389]
[1661,"Track Renovations","Hollywood Hills High","",166959,"","","",166959]
[1661,"Closed Campus ","Hollywood Hills High ",90860,{"$nulls":4},90860]
[9067,"Fire Support System","Hortt Admin Site ",94764,{"$nulls":4},94764]
[1971,"Kitchen/Cafeteria","Hunt, James S. Elementary",2028400,"","","","",2028400]
[3471,"Remodeling/Renovation","Indian Ridge Middle",175000,"","","","",175000]
[9129,"HVAC and Fire Alarm","ITV Center",1172714,{"$nulls":4},1172714]
[9129,"Print Shop ","ITV Center",50968,{"$nulls":4},50968]
[9129,"Renovations","ITV Center",912727,{"$nulls":4},912727]
[2914,"Western/Cypress Bay Annex","Cypress Bay Annex",69910,{"$nulls":4},69910]
[9328,"Ancillary Facilities ","Kathleen Wright Admin Site ",4153337,{"$nulls":4},4153337]
[9328,"Board Office Renovation ","Kathleen Wright Admin Site ",38880,{"$nulls":4},38880]
[9328,"Garage Repairs ","Kathleen Wright Admin Site ",23305,{"$nulls":4},23305]
[9328,"Office/Elevator Renovations ","Kathleen Wright Admin Site ",32562,{"$nulls":4},32562]
[9328,"Reroof KCW Bldg","Kathleen Wright Admin Site ",23061,{"$nulls":4},23061]
[1611,"New Kitchen/Cafeteria/Multi-Purpose","King Martin Luther Elementary ",1209381,{"$nulls":4},1209381]
[831,"Playground","Lake Forest Elementary",115950,"","","","",115950]
[405,"Existing Project","Lanier-James Education Center",1703141,"","","","",1703141]
[621,"Drainage","Larkdale Elementary",608520,"","","","",608520]
[621,"Playground","Larkdale Elementary",115950,"","","","",115950]
[621,"Remodeling/Renovation","Larkdale Elementary",30000,"","","","",30000]
[621,"Generator Vault ","Larkdale Elementary ",214965,{"$nulls":4},214965]
[1701,"Remodeling","Lauderdale Lakes Middle",879140,"","","","",879140]
[1701,"Remodeling/Renovation","Lauderdale Lakes Middle","",30000,"","","",30000]
[431,"Partial Replacement","Lauderdale Manors Elementary",404180,3651120,"","","",4055300]
[431,"Cafe/Kitch/Multi Purpose","Lauderdale Manors Elementary ",2210216,{"$nulls":4},2210216]
[1391,"HVAC","Lauderhill Middle",811360,"","","","",811360]
[1391,"Remodeling","Lauderhill Middle",879140,"","","","",879140]
[1391,"Remodeling/Renovation","Lauderhill Middle","",1225000,"","","",1225000]
[1391,"Athletic Facilities/Gym Locker","Lauderhill Middle ",1000000,{"$nulls":4},1000000]
[1391,"Occupation Labs/Reception Area","Lauderhill Middle ",3322674,{"$nulls":4},3322674]
[1381,"Site Improvement-City Reimbursement","Lauderhill P T Elementary ",500000,{"$nulls":4},500000]
[1381,"Remodeling/Renovation","Lauderhill P T Elementary ",800000,"","","","",800000]
[1091,"Remodeling / Addition","Lloyd Estates Elementary",2185789,196865,"","","",2382654]
[1091,"Remodeling/Renovation","Lloyd Estates Elementary",30000,"","","","",30000]
[1091,"Renovation","Lloyd Estates Elementary",1534237,"","","","",1534237]
[1091,"Class Size Reduction ","Lloyd Estates Elementary ",55260,{"$nulls":4},55260]
[2741,"Remodeling/Renovation","Maplewood Elementary","","",200000,"","",200000]
[2741,"Drainage","Maplewood Elementary ",70000,{"$nulls":4},70000]
[1161,"Kitchen/Cafeteria","Margate Elementary",4056800,"","","","",4056800]
[1161,"Playground","Margate Elementary","",72470,"","","",72470]
[581,"Kitchen/Cafeteria","Margate Middle",405680,3651120,"","","",4056800]
[581,"Install A/C In Computer Lab ","Margate Middle ",25000,{"$nulls":4},25000]
[1671,"Cafe/Kitch/Multi Purp ","Markham, Robert Elementary ",842599,{"$nulls":4},842599]
[241,"Auditorium Ren/Remodel/Stage","McArthur High",66149,{"$nulls":4},66149]
[241,"Food Court","McArthur High","","",200000,1800000,"",2000000]
[1291,"Intercom","McFatter Technical Center",100000,"","","","",100000]
[481,"Joint Use Fac-Admin Bldg","McNicol Middle-Mod Cal",500000,{"$nulls":4},500000]
[481,"Joint Use Fac-Admin Bldg","McNicol Middle-Mod Cal",593406,{"$nulls":4},593406]
[481,"Joint Use Fac-Admin Bldg","McNicol Middle-Mod Cal",26500,{"$nulls":4},26500]
[761,"Kitchen/Cafeteria","Meadowbrook Elementary",365112,3286008,"","","",3651120]
[761,"Playground","Meadowbrook Elementary","",157046,"","","",157046]
[531,"Playground","Miramar Elementary","",112376,"","","",112376]
[531,"Playground","Miramar Elementary","",72470,"","","",72470]
[1751,"Dimmer Board/Stage/Control Rm ","Miramar High ",19200,{"$nulls":4},19200]
[1841,"Addition","Mirror Lake Elementary",55653,"","","","",55653]
[1841,"Kitchen/Cafeteria","Mirror Lake Elementary","","","",400000,3600000,4000000]
[1841,"Playground","Mirror Lake Elementary",115950,"","","","",115950]
[2231,"Playground","North Lauderdale Elementary",115950,{"$nulls":4},115950]
[2231,"Kindergarten Playground","North Lauderdale Elementary ",60000,"","","","",60000]
[41,"Remodeling/Renovation","North Side Elementary",30000,"","","","",30000]
[1241,"Kitchen/Cafeteria","Northeast High","","",507100,5071000,"",5578100]
[1241,"Master Plan Facility","Northeast High",55653,"","","","",55653]
[1241,"Remodeling and Renovation","Northeast High",712741,"","","","",712741]
[1241,"Fire Alarm ","Northeast High",259500,{"$nulls":4},259500]
[1241,"Pool Renovations ","Northeast High",80700,{"$nulls":4},80700]
[1241,"Renovation/Remodel ","Northeast High ",3879180,{"$nulls":4},3879180]
[1282,"Playground","Nova Blanche Forman Elementary","",141096,"","","",141096]
[1271,"Kitchen/Cafeteria","Nova Eisenhower Elementary",507100,"","","","",507100]
[1282,"Bus/Parent Drive ","Nova Foreman Elementary",56655,{"$nulls":4},56655]
[1282,"Traffic Signal ","Nova Foreman Elementary",35000,{"$nulls":4},35000]
[1281,"Remodeling And Renovation","Nova High ",3233305,"","","","",3233305]
[1281,"Bus/Parent Drive ","Nova High ",411691,{"$nulls":4},411691]
[1281,"Pool Renovations ","Nova High ",15000,{"$nulls":4},15000]
[1281,"Resurface Asphalt Track","Nova High ",164621,{"$nulls":4},164621]
[1311,"Remodeling, Renovations & Site Improvement","Nova Middle",1260091,"","","","",1260091]
[1311,"Bus/Parent Drive ","Nova Middle ",66203,{"$nulls":4},66203]
[31,"Bus Loop","Oakland Park Elementary ",167405,"","","","",167405]
[31,"Driveway Safety Renovations ","Oakland Park Elementary ",104373,{"$nulls":4},104373]
[31,"Play Courts","Oakland Park Elementary ",100000,{"$nulls":4},100000]
[461,"Classroom Renovation ","Oakridge Elementary ",656823,{"$nulls":4},656823]
[471,"Joint Project w/City Demolition Ballfield","Olsen Middle ",94430,{"$nulls":4},94430]
[1831,"Kitchen/Cafeteria","Oriole Elementary","","","",400000,3600000,4000000]
[1831,"Playground","Oriole Elementary",72470,"","","","",72470]
[3311,"Playground","Palm Cove Elementary","",72470,"","","",72470]
[1131,"Drainage/parking","Palmview Elementary","",253550,"","","",253550]
[1131,"New Cafe / Kitch / Multipurpose Area / Stage","Palmview Elementary",2781954,394709,"","","",3176663]
[1951,"Playground","Park Ridge Elementary","",141096,"","","",141096]
[3171,"Walkways/Drainage ","Park Springs Elementary ",113444,{"$nulls":4},113444]
[701,"Fire Alarm","Parkway Middle",37055,"","","","",37055]
[701,"Remodeling And Renovation","Parkway Middle",6622119,157588,"","","",6779707]
[2071,"Kitchen/Cafeteria","Pasadena Lakes Elementary","","","",400000,3600000,4000000]
[2661,"Playground","Pembroke Lakes Elementary","",112376,"","","",112376]
[2661,"Playground","Pembroke Lakes Elementary",72470,"","","","",72470]
[1221,"New Cafe / Kitch / Multipurpose Area / Stage","Pembroke Lakes Elementary",4132670,281177,"","","",4413847]
[1631,"New Kitchen/Cafeteria","Perry, Annabel Elementary",4056800,"","","","",4056800]
[2861,"Remodeling & Renovation","Pines Lakes Elementary","",2083772,"","","",2083772]
[2861,"Remodeling & Renovation / IEQ","Pines Lakes Elementary",592627,"","","","",592627]
[1901,"Existing Project","Piper High",1825445,"","","","",1825445]
[1451,"Kitchen/Cafeteria","Plantation High",7926654,"","","","",7926654]
[1451,"Playground","Plantation High","",129908,"","","",129908]
[1451,"Track Renovations ","Plantation High",166959,"","","","",166959]
[21,"Site Improvement","Pompano Beach Middle",55653,"","","","",55653]
[3121,"Driveway","Quiet Waters Elem ",250000,{"$nulls":4},250000]
[2721,"Remodeling/Renovation","Ramblewood Elementary","",400000,"","","",400000]
[2711,"Renovate Rest Rooms","Ramblewood Middle","","","",400000,"",400000]
[2121,"Remodeling/Addition","Rickards Middle",3053432,"","","","",3053432]
[2891,"Playground","Riverglades Elementary","",141096,"","","",141096]
[2891,"Drainage","Riverglades Elementary ",75000,{"$nulls":4},75000]
[151,"Playground","Riverland Elementary",115950,"","","","",115950]
[3031,"Remodeling/Renovation","Riverside Elementary","","",1000000,"","",1000000]
[3031,"Covered Walkway/IEQ","Riverside Elementary ",1023194,{"$nulls":4},1023194]
[681,"Remodeling And Renovation","Rock Island Elementary",2062533,205826,"","","",2268359]
[1851,"Remodeling/Renovation","Royal Palm Elementary",260000,"","","","",260000]
[1851,"Site Needs","Royal Palm Elementary",55653,"","","","",55653]
[1851,"Repair Roof ","Royal Palm Elementary ",100000,{"$nulls":4},100000]
[9335,"New Construction","S/W Bus Parking Facilities",8494492,"","","","",8494492]
[9005,"Bldg Renovation/Moves ","Sailboat Bend Complex ",157799,{"$nulls":4},157799]
[891,"Traffic Flow Issue(HSS)","Sanders Park Elementary ",100000,{"$nulls":4},100000]
[3061,"Covered Walkway/IEQ","Sandpiper Elementary ",918815,{"$nulls":4},918815]
[3061,"Traffic Loop Added","Sandpiper Elementary ",30000,{"$nulls":4},30000]
[3241,"Museum's Environmental Center ","Science Museum-Leased ",4416200,{"$nulls":4},4416200]
[2871,"Playground","Sea Castle Elementary","",72470,"","","",72470]
[601,"New Media Center","Seagull School",333917,1892196,"","","",2226113]
[601,"Playground","Seagull School",136158,"","","","",136158]
[601,"Water/Sewer","Seagull School","",1014200,"","","",1014200]
[601,"Bus Loop ","Seagull School ",11226,{"$nulls":4},11226]
[1891,"IEQ","Seminole Middle ",1001147,{"$nulls":4},1001147]
[1811,"Kitchen/Cafeteria","Sheridan Hills Elementary","","","",400000,3600000,4000000]
[1811,"Playground","Sheridan Hills Elementary",72470,"","","","",72470]
[1321,"Drainage","Sheridan Park Elementary ",75000,{"$nulls":4},75000]
[1051,"Air Conditioning","Sheridan Technical Center",742667,"","","","",742667]
[2971,"Remodeling/Renovation","Silver Lakes Middle",1000000,"","","","",1000000]
[2971,"BECON","Silver Lakes Middle ",100000,{"$nulls":4},100000]
[3081,"Playground","Silver Ridge Elementary",115950,"","","","",115950]
[405,"Training Course","South Area Alternative Center ",12295,{"$nulls":4},12295]
[9279,"Remodeling","South Area Bus Parking Lot",106372,"","","","",106372]
[171,"Regional Athletic Facility","South Broward High",1669584,"","","","",1669584]
[171,"Pool Renovations ","South Broward High ",213700,{"$nulls":4},213700]
[2351,"Regional Athletic Facility","South Plantation High",1605586,"","","","",1605586]
[2351,"Renovation","South Plantation High",20028,"","","","",20028]
[691,"Bus Loop/Parking","Stirling Elementary",141562,"","","","",141562]
[3011,"Drainage","Stoneman Douglas High",600000,"","","","",600000]
[3011,"Track Renovations ","Stoneman Douglas High","",166959,"","","",166959]
[3011,"Closed Campus ","Stoneman Douglas High ",25000,{"$nulls":4},25000]
[211,"Remodeling and Renovation","Stranahan High",2270449,"","","","",2270449]
[211,"Swimming Pool & Track Renovations","Stranahan High",2527697,"","","","",2527697]
[1171,"Drop Off Area","Sunshine Elementary",162272,"","","","",162272]
[2621,"Playground","Tamarac Elementary",72470,{"$nulls":4},72470]
[2621,"Kindergarten Playground","Tamarac Elementary ",60000,"","","","",60000]
[2751,"Remodeling And Renovation","Taravella J P High",7178927,"","","","",7178927]
[2751,"Remodeling/Renovation","Taravella J P High",1740000,"","","","",1740000]
[2751,"Stadium Design","Taravella J P High",150000,"","","","",150000]
[2751,"Track Renovations ","Taravella J P High","",166959,"","","",166959]
[2751,"Girl's Softball ","Taravella J P High ",30000,{"$nulls":4},30000]
[9356,"Remodeling/Renovation","Technology/Support Serv Site",990000,"","","","",990000]
[9356,"Major Renovations ","Technology/Support Serv Site ",20100,{"$nulls":4},20100]
[9356,"Office Moves ","Technology/Support Serv Site ",156182,{"$nulls":4},156182]
[571,"Playground","Tedder Elementary",141096,"","","","",141096]
[571,"Cafe/Kitch/Multipurp ","Tedder Elementary ",3768244,{"$nulls":4},3768244]
[3151,"Access Road To Parking Lot ","Tequesta Trace Middle ",56848,{"$nulls":4},56848]
[3151,"Sidewalk/ Gate ","Tequesta Trace Middle ",17200,{"$nulls":4},17200]
[1021,"Remodeling/Renovation","The Quest Center",457580,"","","","",457580]
[9387,"Remodeling and Renovation","The Weld Shop ",768712,{"$nulls":4},768712]
[3481,"Remodeling/Renovation","Tradewinds Elementary",750000,"","","","",750000]
[731,"Kitchen/Cafeteria","Tropical Elementary",365112,3286008,"","","",3651120]
[731,"DHH Classroom","Tropical Elementary ",65000,{"$nulls":4},65000]
[9077,"Installation of BECON Tower","Twin Lakes Complex ",70000,{"$nulls":4},70000]
[9077,"Landscaping","Twin Lakes Complex ",14000,{"$nulls":4},14000]
[9077,"Renovate Learning Research Lab","Twin Lakes Complex ",44021,{"$nulls":4},44021]
[1621,"Cafe, Kitch, Multipurp/Stage, Drain, and IEQ","Village Elementary",4708432,"","","","",4708432]
[321,"New Cafe / Kitch / Multipurpose Area / Stage","Walker Elementary",2893986,281177,"","","",3175163]
[321,"Playground","Walker Elementary",112376,"","","","",112376]
[511,"Remodeling/Renovation","Watkins Elementary",87000,"","","","",87000]
[9334,"Construction ","West Central Bus Parking/Maint",4271002,{"$nulls":4},4271002]
[2681,"Playground","Westchester Elementary","",72470,"","","",72470]
[2681,"Remodeling/Renovation","Westchester Elementary",110000,"","","","",110000]
[2831,"Drainage Repairs ","Western High ",199927,{"$nulls":4},199927]
[2831,"Gym Bleachers ","Western High ",125000,{"$nulls":4},125000]
[2052,"Replace Chiller ","Westpine Middle ",81743,{"$nulls":4},81743]
[631,"Playground","Westwood Heights Elementary",72470,"","","","",72470]
[631,"Playground ","Westwood Heights Elementary","",101420,"","","",101420]
[452,"General Renovations ","Whiddon-Rogers Ed",97388,{"$nulls":4},97388]
[452,"Student Patio Resurfacing ","Whiddon-Rogers Ed",44602,{"$nulls":4},44602]
[452,"Remodeling and Renovation","Whiddon-Rogers Ed Center",1577374,734284,"","","",2311658]
[452,"Remodeling/Renovation","Whiddon-Rogers Ed Center","",50000,"","","",50000]
[991,"Pool Renovations ","Wingate Oaks Center ",13000,{"$nulls":4},13000]
[3091,"Playground","Winston Park Elementary","",141096,"","","",141096]
[3091,"Wetlands ","Winston Park Elementary ",32542,{"$nulls":4},32542]
[3321,"Playground","Young, Virginia S. Elementary",141096,"","","","",141096]
[3321,"Remodeling / Renovation","Young, Virginia S. Elementary",65000,"","","","",65000]
[3001,"Drainage","Young, Walter C. Middle","",253550,"","","",253550]
[null,"Indoor Environmental Quality",{"$nulls":6},0]
[1741,"Indoor Environmental Quality","Anderson, Boyd H High ",279773,{"$nulls":4},279773]
[1791,"Indoor Environmental Quality","Apollo Middle ",34723,{"$nulls":4},34723]
[2221,"Indoor Environmental Quality","Atlantic Vocational Center ",126500,{"$nulls":4},126500]
[2511,"Indoor Environmental Quality","Atlantic West Elementary ",55812,{"$nulls":4},55812]
[2611,"Indoor Environmental Quality","Bair Middle ",124608,{"$nulls":4},124608]
[2001,"Indoor Environmental Quality","Banyan Elementary ",80000,{"$nulls":4},80000]
[201,"Indoor Environmental Quality","Bennett Elementary ",79713,{"$nulls":4},79713]
[971,"Indoor Environmental Quality","Boulevard Heights Elementary ",58184,{"$nulls":4},58184]
[871,"Indoor Environmental Quality","Bright Horizons Center ",79246,{"$nulls":4},79246]
[811,"Indoor Environmental Quality","Broadview Elementary ",205993,{"$nulls":4},205993]
[501,"Indoor Environmental Quality","Broward Estates Elementary ",58159,{"$nulls":4},58159]
[2771,"Indoor Environmental Quality","Broward Fire Academy ",47656,{"$nulls":4},47656]
[1461,"Indoor Environmental Quality","Castle Hill Elementary ",183108,{"$nulls":4},183108]
[2641,"Indoor Environmental Quality","Central Park Elementary ",60612,{"$nulls":4},60612]
[1421,"Indoor Environmental Quality","Coconut Creek Elementary ",285835,{"$nulls":4},285835]
[1681,"Indoor Environmental Quality","Coconut Creek High ",2401911,{"$nulls":4},2401911]
[231,"Indoor Environmental Quality","Colbert Elementary",26042,{"$nulls":4},26042]
[331,"Indoor Environmental Quality","Collins Elementary ",133001,{"$nulls":4},133001]
[3041,"Indoor Environmental Quality","Coral Park Elementary ",22738,{"$nulls":4},22738]
[3041,"Indoor Environmental Quality","Coral Park Elementary ",674842,{"$nulls":4},674842]
[1151,"Indoor Environmental Quality","Coral Springs High ",260421,{"$nulls":4},260421]
[3111,"Indoor Environmental Quality","Country Hills Elementary ",53588,{"$nulls":4},53588]
[2981,"Indoor Environmental Quality","Country Isles Elementary ",580922,{"$nulls":4},580922]
[901,"Indoor Environmental Quality","Cresthaven Elementary ",77043,{"$nulls":4},77043]
[221,"Indoor Environmental Quality","Croissant Park Elementary ",12114,{"$nulls":4},12114]
[3222,"Indoor Environmental Quality","Cross Creek Center ",236947,{"$nulls":4},236947]
[1871,"Indoor Environmental Quality","Crystal Lake Comm Middle ",121120,{"$nulls":4},121120]
[1781,"Indoor Environmental Quality","Cypress Elementary ",17689,{"$nulls":4},17689]
[1071,"Indoor Environmental Quality","Dandy, William Middle",165764,{"$nulls":4},165764]
[101,"Indoor Environmental Quality","Dania Elementary ",9942,{"$nulls":4},9942]
[2801,"Indoor Environmental Quality","Davie Elementary ",75360,{"$nulls":4},75360]
[11,"Indoor Environmental Quality","Deerfield Beach Elementary ",199113,{"$nulls":4},199113]
[1711,"Indoor Environmental Quality","Deerfield Beach High ",203123,{"$nulls":4},203123]
[911,"Indoor Environmental Quality","Deerfield Beach Middle ",175409,{"$nulls":4},175409]
[271,"Indoor Environmental Quality","Dillard Elementary ",287238,{"$nulls":4},287238]
[371,"Indoor Environmental Quality","Dillard High ",515383,{"$nulls":4},515383]
[0,"Indoor Environmental Quality","District Wide ",18262363,8000000,10000000,8000000,null,44262363]
[3221,"Indoor Environmental Quality","Drew Elementary ",33795,{"$nulls":4},33795]
[721,"Indoor Environmental Quality","Driftwood Elementary ",185128,{"$nulls":4},185128]
[3191,"Indoor Environmental Quality","Embassy Creek Elementary ",121988,{"$nulls":4},121988]
[9830,"Indoor Environmental Quality","ESEA Title I",17500,{"$nulls":4},17500]
[951,"Indoor Environmental Quality","Fort Lauderdale High ",18901,{"$nulls":4},18901]
[2851,"Indoor Environmental Quality","Griffin Elementary ",7100,{"$nulls":4},7100]
[131,"Indoor Environmental Quality","Hallandale Elem-Year Round ",7494,{"$nulls":4},7494]
[403,"Indoor Environmental Quality","Hallandale High ",51356,{"$nulls":4},51356]
[3131,"Indoor Environmental Quality","Hawkes Bluff Elementary ",192234,{"$nulls":4},192234]
[121,"Indoor Environmental Quality","Hollywood Central Elementary ",1141132,{"$nulls":4},1141132]
[111,"Indoor Environmental Quality","Hollywood Hills Elementary ",14210,{"$nulls":4},14210]
[1661,"Indoor Environmental Quality","Hollywood Hills High ",178000,{"$nulls":4},178000]
[1761,"Indoor Environmental Quality","Hollywood Park Elementary ",43016,{"$nulls":4},43016]
[2531,"Indoor Environmental Quality","Horizon Elementary ",80000,{"$nulls":4},80000]
[1971,"Indoor Environmental Quality","Hunt James S Elementary ",95078,{"$nulls":4},95078]
[3181,"Indoor Environmental Quality","Indian Trace Elementary ",531090,{"$nulls":4},531090]
[9129,"Indoor Environmental Quality","ITV Center",8000,{"$nulls":4},8000]
[1611,"Indoor Environmental Quality","King Martin Luther Elementary ",103588,{"$nulls":4},103588]
[831,"Indoor Environmental Quality","Lake Forest Elementary",6500,{"$nulls":4},6500]
[621,"Indoor Environmental Quality","Larkdale Elementary ",82977,{"$nulls":4},82977]
[1701,"Indoor Environmental Quality","Lauderdale Lakes Middle ",217606,{"$nulls":4},217606]
[431,"Indoor Environmental Quality","Lauderdale Manors Elementary ",347431,{"$nulls":4},347431]
[2741,"Indoor Environmental Quality","Maplewood Elementary ",19622,{"$nulls":4},19622]
[1161,"Indoor Environmental Quality","Margate Elementary ",92840,{"$nulls":4},92840]
[581,"Indoor Environmental Quality","Margate Middle ",33731,{"$nulls":4},33731]
[1671,"Indoor Environmental Quality","Markham, Robert Elementary ",13882,{"$nulls":4},13882]
[3291,"Indoor Environmental Quality","Marshall, Thurgood Elementary ",64958,{"$nulls":4},64958]
[1291,"Indoor Environmental Quality","McFatter Voc-Tech Center",7500,{"$nulls":4},7500]
[761,"Indoor Environmental Quality","Meadowbrook Elementary ",76400,{"$nulls":4},76400]
[531,"Indoor Environmental Quality","Miramar Elementary ",552892,{"$nulls":4},552892]
[1841,"Indoor Environmental Quality","Mirror Lake Elementary ",238186,{"$nulls":4},238186]
[2691,"Indoor Environmental Quality","Morrow Elementary ",118740,{"$nulls":4},118740]
[881,"Indoor Environmental Quality","New River Middle ",20000,{"$nulls":4},20000]
[2671,"Indoor Environmental Quality","Nob Hill Elementary ",79741,{"$nulls":4},79741]
[1191,"Indoor Environmental Quality","North Fork Elem ",75789,{"$nulls":4},75789]
[2231,"Indoor Environmental Quality","North Lauderdale Elementary ",104436,{"$nulls":4},104436]
[1271,"Indoor Environmental Quality","Nova Eisenhower Elementary ",35204,{"$nulls":4},35204]
[1282,"Indoor Environmental Quality","Nova Forman Elementary ",12228,{"$nulls":4},12228]
[1281,"Indoor Environmental Quality","Nova High ",16136,{"$nulls":4},16136]
[1311,"Indoor Environmental Quality","Nova Middle ",25297,{"$nulls":4},25297]
[461,"Indoor Environmental Quality","Oakridge Elementary ",258625,{"$nulls":4},258625]
[471,"Indoor Environmental Quality","Olsen Middle ",715069,{"$nulls":4},715069]
[1831,"Indoor Environmental Quality","Oriole Elementary ",83517,{"$nulls":4},83517]
[3311,"Indoor Environmental Quality","Palm Cove Elementary ",96160,{"$nulls":4},96160]
[3171,"Indoor Environmental Quality","Park Springs Elementary ",1023823,{"$nulls":4},1023823]
[1221,"Indoor Environmental Quality","Pembroke Pines Elementary ",10000,{"$nulls":4},10000]
[1011,"Indoor Environmental Quality","Perry Henry D Middle ",205103,{"$nulls":4},205103]
[931,"Indoor Environmental Quality","Peters Elementary ",123500,{"$nulls":4},123500]
[1881,"Indoor Environmental Quality","Pines Middle ",132110,{"$nulls":4},132110]
[2811,"Indoor Environmental Quality","Pinewood Elementary ",173363,{"$nulls":4},173363]
[1451,"Indoor Environmental Quality","Plantation High ",38535,{"$nulls":4},38535]
[1451,"Indoor Environmental Quality","Plantation High ",174960,{"$nulls":4},174960]
[551,"Indoor Environmental Quality","Plantation Middle ",117578,{"$nulls":4},117578]
[1251,"Indoor Environmental Quality","Plantation Park Elementary ",73400,{"$nulls":4},73400]
[9018,"Indoor Environmental Quality","Pompano Admin Site ",228908,{"$nulls":4},228908]
[751,"Indoor Environmental Quality","Pompano Beach Elementary ",500672,{"$nulls":4},500672]
[3121,"Indoor Environmental Quality","Quiet Waters Elem ",94747,{"$nulls":4},94747]
[2721,"Indoor Environmental Quality","Ramblewood Elementary ",141,{"$nulls":4},141]
[2711,"Indoor Environmental Quality","Ramblewood Middle ",155920,{"$nulls":4},155920]
[2121,"Indoor Environmental Quality","Rickards Middle ",22329,{"$nulls":4},22329]
[2891,"Indoor Environmental Quality","Riverglades Elementary ",149914,{"$nulls":4},149914]
[681,"Indoor Environmental Quality","Rock Island Elementary ",9612,{"$nulls":4},9612]
[9005,"Indoor Environmental Quality","Sailboat Bend Complex ",33787,{"$nulls":4},33787]
[891,"Indoor Environmental Quality","Sanders Park Elementary ",43238,{"$nulls":4},43238]
[3401,"Indoor Environmental Quality","Sawgrass Elementary ",13173,{"$nulls":4},13173]
[2871,"Indoor Environmental Quality","Sea Castle Elementary ",335743,{"$nulls":4},335743]
[601,"Indoor Environmental Quality","Seagull School ",86000,{"$nulls":4},86000]
[1051,"Indoor Environmental Quality","Sheridan Vocational",95832,{"$nulls":4},95832]
[3081,"Indoor Environmental Quality","Silver Ridge Elementary ",1642793,{"$nulls":4},1642793]
[171,"Indoor Environmental Quality","South Broward High ",327360,{"$nulls":4},327360]
[2351,"Indoor Environmental Quality","South Plantation High ",239333,{"$nulls":4},239333]
[691,"Indoor Environmental Quality","Stirling Elementary ",269030,{"$nulls":4},269030]
[211,"Indoor Environmental Quality","Stranahan High ",197295,{"$nulls":4},197295]
[611,"Indoor Environmental Quality","Sunland Park Elementary ",1005802,{"$nulls":4},1005802]
[251,"Indoor Environmental Quality","Sunrise Middle ",332222,{"$nulls":4},332222]
[1171,"Indoor Environmental Quality","Sunshine Elementary ",124174,{"$nulls":4},124174]
[2621,"Indoor Environmental Quality","Tamarac Elementary ",106369,{"$nulls":4},106369]
[2751,"Indoor Environmental Quality","Taravella J P High ",596844,{"$nulls":4},596844]
[571,"Indoor Environmental Quality","Tedder Elementary ",90725,{"$nulls":4},90725]
[3151,"Indoor Environmental Quality","Tequesta Trace Middle ",129907,{"$nulls":4},129907]
[3481,"Indoor Environmental Quality","Tradewinds Elementary ",62975,{"$nulls":4},62975]
[731,"Indoor Environmental Quality","Tropical Elementary ",15928,{"$nulls":4},15928]
[321,"Indoor Environmental Quality","Walker Elementary ",159664,{"$nulls":4},159664]
[2881,"Indoor Environmental Quality","Welleby Elementary ",31017,{"$nulls":4},31017]
[161,"Indoor Environmental Quality","West Hollywood Elementary ",402080,{"$nulls":4},402080]
[2681,"Indoor Environmental Quality","Westchester Elementary ",46184,{"$nulls":4},46184]
[2831,"Indoor Environmental Quality","Western High ",84798,{"$nulls":4},84798]
[2052,"Indoor Environmental Quality","Westpine Middle ",642408,{"$nulls":4},642408]
[631,"Indoor Environmental Quality","Westwood Heights Elementary ",26635,{"$nulls":4},26635]
[412,"Indoor Environmental Quality","Whiddon-Rogers Annex ",195000,{"$nulls":4},195000]
[452,"Indoor Environmental Quality","Whiddon-Rogers Ed",129983,{"$nulls":4},129983]
[991,"Indoor Environmental Quality","Wingate Oaks Center ",78817,{"$nulls":4},78817]
[3091,"Indoor Environmental Quality","Winston Park Elementary ",49889,{"$nulls":4},49889]
[3321,"Indoor Environmental Quality","Young, Virginia S Elem ",326452,{"$nulls":4},326452]
[3001,"Indoor Environmental Quality","Young, Walter C Middle ",135131,{"$nulls":4},135131]
[null,"Education Technology Services - Technology Upgrades",{"$nulls":6},0]
[1211,"Technology","Cooper City Elementary ",5460,{"$nulls":4},5460]
[2551,"Technology","Coral Springs Elementary ",7266,{"$nulls":4},7266]
[0,"Capitalized Cost-Tech ","District Wide",1387935,400000,400000,400000,400000,2987935]
[0,"CD/IM System","District Wide",2314430,500000,500000,500000,500000,4314430]
[0,"Cust Serv Mgmt System ","District Wide",2330915,{"$nulls":4},2330915]
[0,"Data Warehouse Ph I","District Wide",634539,{"$nulls":4},634539]
[0,"Distance Learning ","District Wide",2769488,1400000,500000,500000,500000,5669488]
[0,"District Technology Programs","District Wide",null,6100000,7300000,9300000,9300000,32000000]
[0,"E-Learning Tech 1.1","District Wide",1054807,300000,300000,300000,300000,2254807]
[0,"Emerging Technologies","District Wide",1117405,500000,500000,500000,500000,3117405]
[0,"End User Equip/Computer Labs ","District Wide",4789368,1000000,1000000,1000000,1000000,8789368]
[0,"End User Equipment/Refresh ","District Wide",13840695,2000000,2000000,2000000,2000000,21840695]
[0,"Infra-Equip.Refresh/Upgrade ","District Wide",5828501,500000,500000,500000,500000,7828501]
[0,"Office Upgrades ","District Wide",1165010,400000,400000,400000,400000,2765010]
[0,"Portable Sites Upgrade (Tech) ","District Wide",8591650,3212315,3212315,1000000,1000000,17016280]
[0,"Student Benchwalk Assesment Mgmt System","District Wide",1500000,500000,500000,500000,500000,3500000]
[0,"WAN/ICI Design Phase","District Wide",10082505,2500000,2500000,2500000,2500000,20082505]
[0,"Board Support System ","District Wide ",150000,{"$nulls":4},150000]
[0,"CCC Licensing Fees","District Wide ",449300,{"$nulls":4},449300]
[0,"Compass Learning Josten's Fees","District Wide ",696855,{"$nulls":4},696855]
[0,"Computer Based Trng ","District Wide ",500196,{"$nulls":4},500196]
[0,"D/W Infra Improve ","District Wide ",679464,{"$nulls":4},679464]
[0,"Data Warehouse-Tech ","District Wide ",500000,"",500000,"",500000,1500000]
[0,"ETS Thin Client Deploy 4.3","District Wide ",2412000,{"$nulls":4},2412000]
[0,"High School Network Upgrade ","District Wide ",14098,{"$nulls":4},14098]
[0,"Metrology Equipment","District Wide ",700000,700000,700000,700000,700000,3500000]
[0,"Middle Sch Tech Upgrades ","District Wide ",1679,{"$nulls":4},1679]
[0,"Plan 4-Tech ","District Wide ",921504,{"$nulls":4},921504]
[0,"Tech Ed Lab- M S ","District Wide ",21014,{"$nulls":4},21014]
[0,"Teleconference System ","District Wide ",386,{"$nulls":4},386]
[0,"Upgrade Area Offices ","District Wide ",102959,{"$nulls":4},102959]
[831,"Technology","Lake Forest Elementary",5946,{"$nulls":4},5946]
[461,"Technology","Oakridge Elementary ",117,{"$nulls":4},117]
[1831,"Technology ","Oriole Elementary ",1226,{"$nulls":4},1226]
[1131,"Technology","Palmview Elementary ",2152,{"$nulls":4},2152]
[2121,"Technology ","Rickards Middle ",262,{"$nulls":4},262]
[3401,"Technology","Sawgrass Elementary ",6206,{"$nulls":4},6206]
[null,"Health Safety & Sanitation",{"$nulls":6},0]
[1741,"Fire Sprinkler System","Anderson, Boyd H High ",275000,{"$nulls":4},275000]
[1741,"Repair/replace baseball bleachers","Anderson, Boyd H. High",6000,"","","","",6000]
[1741,"Electrical/Fire Safety Violations","Anderson, Boyd H. High",9561,10518,11570,12727,14000,58376]
[1741,"Flooring:  Installation of Tile","Anderson, Boyd H. High","",80000,"","","",80000]
[1741,"Repair / Replace Stage Rigging","Anderson, Boyd H. High",90000,"","","","",90000]
[1791,"Electrical/Fire Safety Violations","Apollo Middle",10028,11031,12134,13348,14683,61224]
[1791,"Fire Rate Corridors","Apollo Middle",223600,"","","","",223600]
[1791,"Provide Fire Sprinkler Protection - KIVA","Apollo Middle",50000,"","","","",50000]
[1791,"Drainage ","Apollo Middle ",50000,{"$nulls":4},50000]
[2221,"Electrical/Fire Safety Violations","Atlantic Vocational Center ",10258,11284,12412,13654,15019,62627]
[2221,"Flooring:  Installation of Tile","Atlantic Vocational Center ","",65000,"","","",65000]
[2221,"Fire Safety Equipment ","Atlantic Vocational Center ",208500,{"$nulls":4},208500]
[2221,"HSS/Fire Alarms","Atlantic Vocational Center ",145130,{"$nulls":4},145130]
[2511,"Electrical/Fire Safety Violations","Atlantic West Elementary",8090,8899,9789,10768,11845,49391]
[2511,"Flooring: Installation of Tile","Atlantic West Elementary","",50000,"","","",50000]
[2511,"Generator:  Install New Generator","Atlantic West Elementary","",120000,"","","",120000]
[2511,"Provide Fire Sprinkler Protection","Atlantic West Elementary",220000,"","","","",220000]
[2511,"Replace Fire Alarm System","Atlantic West Elementary","","",160000,"","",160000]
[2511,"Install Bus/Parent Drive","Atlantic West Elementary ",200000,{"$nulls":4},200000]
[343,"Bleachers:  Replace baseball bleachers","Attucks Middle","",6000,"","","",6000]
[343,"Bleachers: Replace Softball Bleachers","Attucks Middle",2500,"","","","",2500]
[343,"Electrical/Fire Safety Violations","Attucks Middle",10028,11031,12134,13348,14683,61224]
[343,"Fencing: Replace Fence (perimeter of school)","Attucks Middle",116120,"","","","",116120]
[343,"Provide Fire Sprinkler Protection","Attucks Middle","","","",350000,"",350000]
[343,"Replace Fire Alarm System","Attucks Middle",195000,"","","","",195000]
[343,"Bus Drive","Attucks Middle ",80000,{"$nulls":4},80000]
[2611,"Electrical/Fire Safety Violations","Bair Middle",30886,33975,37373,41110,45221,188565]
[2611,"Flooring:  Installation of Tile","Bair Middle","",90000,"","","",90000]
[2611,"Provide Fire Sprinkler Protection","Bair Middle","","","",350000,"",350000]
[2611,"HSS/Intercoms","Bair Middle ",4770,{"$nulls":4},4770]
[2001,"Electrical/Fire Safety Violations","Banyan Elementary",6954,7650,8415,9257,10183,42459]
[2001,"Flooring:  Installation of Tile","Banyan Elementary",65000,"","","","",65000]
[2001,"Provide Fire Sprinkler Protection","Banyan Elementary",220000,"","","","",220000]
[2001,"Replace Fire Alarm System","Banyan Elementary","","","","",160000,160000]
[641,"Electrical/Fire Safety Violations","Bayview Elementary",3282,3611,3972,4369,4806,20040]
[641,"Flooring:  Installation of Tile Media Center","Bayview Elementary","",25000,"","","",25000]
[9855,"Electrical/Fire Safety Violations","BECON/ITV",3661,4028,4431,4874,5361,22355]
[9855,"Fire Alarm & Intercom Replacement","BECON/ITV",245000,"","","","",245000]
[9855,"Flooring:  Installation of Tile","BECON/ITV","",15000,"","","",15000]
[201,"Electrical/Fire Safety Violations","Bennett Elementary",5950,6545,7200,7919,8711,36325]
[201,"Fencing: Replace Fence (perimeter of school)","Bennett Elementary","",47500,"","","",47500]
[201,"Flooring:  Installation of Tile","Bennett Elementary",30000,"","","","",30000]
[201,"HSS/Intercoms","Bennett Elementary ",61695,{"$nulls":4},61695]
[341,"Driveway Improvements","Bethune, Mary M. Elementary",127874,{"$nulls":4},127874]
[341,"Electrical/Fire Safety Violations","Bethune, Mary M. Elementary",9628,10591,11650,12815,14097,58781]
[341,"Fencing: Replace Fence (west side of school)","Bethune, Mary M. Elementary",5954,"","","","",5954]
[341,"Flooring: Installation of Tile","Bethune, Mary M. Elementary",75000,"","","","",75000]
[361,"Bleachers: Replace Baseball Bleachers","Blanche Ely High","",2500,"","","",2500]
[361,"Electrical/Fire Safety Violations","Blanche Ely High",36703,40374,44411,48853,53738,224079]
[361,"Flooring: Installation of Tile","Blanche Ely High","",50000,"","","",50000]
[361,"Provide Fire Sprinkler Protection","Blanche Ely High","",385000,"","","",385000]
[971,"Electrical/Fire Safety Violations","Boulevard Heights Elementary",4345,4780,5258,5784,6362,26529]
[971,"Flooring: Installation of Tile","Boulevard Heights Elementary","",75000,"","","",75000]
[971,"Replace Fire Alarm System","Boulevard Heights Elementary","","","","",160000,160000]
[971,"Parent Drive Improvement","Boulevard Heights Elementary ",250000,{"$nulls":4},250000]
[871,"Electrical/Fire Safety Violations","Bright Horizons School",6954,7650,8415,9257,10183,42459]
[811,"Electrical/Fire Safety Violations","Broadview Elementary",10563,11620,12782,14060,15466,64491]
[811,"Driveway Safety Renov.","Broadview Elementary ",200000,{"$nulls":4},200000]
[501,"Electrical/Fire Safety Violations","Broward Estates Elementary",6819,7501,8251,9076,9984,41631]
[501,"Fencing: Replace Fence (perimeter of school)","Broward Estates Elementary",43847,"","","","",43847]
[501,"Flooring:  Installation of Tile","Broward Estates Elementary",35000,"","","","",35000]
[2771,"Electrical/Fire Safety Violations","Broward Fire Academy",3000,3300,3630,3993,4392,18315]
[2771,"Replace Fire Alarm System","Broward Fire Academy","","","","",160000,160000]
[1461,"Electrical/Fire Safety Violations","Castle Hill Elementary",4145,4560,5016,5518,6070,25309]
[1461,"Flooring:  Installation of Tile","Castle Hill Elementary",65000,"","","","",65000]
[1461,"Generator:  Install New Generator.","Castle Hill Elementary","",120000,"","","",120000]
[1461,"Provide Fire Sprinkler Protection","Castle Hill Elementary","","",240000,"","",240000]
[9327,"Electrical/Fire Safety Violations","Central Area Admin",1148,1163,1279,1407,1548,6545]
[2641,"Electrical/Fire Safety Violations","Central Park Elementary",15443,16988,18687,20555,22611,94284]
[2641,"Flooring:  Installation of Tile","Central Park Elementary",65000,"","","","",65000]
[3771,"Electrical/Fire Safety Violations","Challenger Elementary",1210,1320,1430,1573,1730,7263]
[2961,"Electrical/Fire Safety Violations","Chapel Trail Elementary",11366,12503,13753,15129,16642,69393]
[2961,"Landing Gate","Chapel Trail Elementary ",10000,{"$nulls":4},10000]
[1421,"Electrical/Fire Safety Violations","Coconut Creek Elementary",8557,9413,10354,11390,12529,52243]
[1421,"Fencing:  Replace Fence.","Coconut Creek Elementary",59400,"","","","",59400]
[1421,"Provide Fire Sprinkler Protection","Coconut Creek Elementary","","",240000,"","",240000]
[1681,"Bleachers: Replace Gym Bleachers","Coconut Creek High",175000,"","","","",175000]
[1681,"Electrical/Fire Safety Violations","Coconut Creek High",13037,14341,15775,17353,19088,79594]
[1681,"Fencing:  Replace Fence.","Coconut Creek High",133750,"","","","",133750]
[1681,"Flooring: Installation of Tile","Coconut Creek High","",50000,"","","",50000]
[1681,"Repair / Replace Stage Rigging","Coconut Creek High",90000,"","","","",90000]
[1681,"Bus/Parent Drives","Coconut Creek High ",150000,{"$nulls":4},150000]
[1681,"Fire Sprinkler System","Coconut Creek High ",275000,{"$nulls":4},275000]
[3741,"Electrical/Fire Safety Violations","Coconut Palm Elementary",3300,3630,3993,4392,4831,20146]
[3741,"Staff overflow parking","Coconut Palm Elementary",150000,"","","","",150000]
[231,"Electrical/Fire Safety Violations","Colbert Elementary",9828,10811,11892,13081,14389,60001]
[231,"Replace Fire Alarm System","Colbert Elementary","","",160000,"","",160000]
[331,"Electrical/Fire Safety Violations","Collins Elementary",10028,11031,12134,13348,14683,61224]
[1211,"Electrical/Fire Safety Violations","Cooper City Elementary",7020,7722,8494,9344,10278,42858]
[1211,"Infra-Electric:  Install New Generator","Cooper City Elementary","",120000,"","","",120000]
[1931,"Electrical/Fire Safety Violations","Cooper City High",13037,14341,15775,17353,19088,79594]
[1931,"Fencing:  Replace Fence.","Cooper City High","",129750,"","","",129750]
[1931,"Repair / Replace Stage Rigging","Cooper City High",90000,"","","","",90000]
[1931,"HSS/Playfield","Cooper City High ",91100,{"$nulls":4},91100]
[3041,"Electrical/Fire Safety Violations","Coral Park Elementary",2540,2794,3073,3381,3719,15507]
[3041,"Fencing:  Replace Fence.","Coral Park Elementary","",63000,"","","",63000]
[3041,"HSS/Fire Alarms","Coral Park Elementary ",31615,{"$nulls":4},31615]
[2551,"Electrical/Fire Safety Violations","Coral Springs Elementary",6418,7060,7766,8543,9397,39184]
[2551,"Flooring:  Installation of Tile","Coral Springs Elementary",45000,"","","","",45000]
[2551,"Provide Fire Sprinkler Protection","Coral Springs Elementary",220000,"","","","",220000]
[2551,"Replace Fire Alarm System","Coral Springs Elementary","",40000,"","","",40000]
[1151,"Bleachers: Replace Baseball Bleachers","Coral Springs High",7000,"","","","",7000]
[1151,"Electrical/Fire Safety Violations","Coral Springs High",7288,8017,8819,9701,10671,44496]
[1151,"Fencing: Replace Fence.","Coral Springs High",46000,"","","","",46000]
[1151,"Provide Fire Sprinkler Protection","Coral Springs High","","","","",450000,450000]
[1151,"Repair / Replace Stage Rigging","Coral Springs High","",90000,"","","",90000]
[1151,"HSS/Fire Alarms","Coral Springs High ",231505,{"$nulls":4},231505]
[2561,"Electrical/Fire Safety Violations","Coral Springs Middle",9962,10959,12055,13260,14586,60822]
[2561,"Provide Fire Sprinkler Protection","Coral Springs Middle","","","",350000,"",350000]
[3111,"Electrical/Fire Safety Violations","Country Hills Elementary",12702,13973,15370,16907,18598,77550]
[3111,"Fire Alarm Replacement","Country Hills Elementary",120000,"","","","",120000]
[3111,"Flooring:  Installation of Tile","Country Hills Elementary",14570,"","","","",14570]
[2981,"Electrical/Fire Safety Violations","Country Isles Elementary",6085,6694,7363,8100,8910,37152]
[901,"Electrical/Fire Safety Violations","Cresthaven Elementary",9360,10296,11326,12458,13704,57144]
[901,"Flooring:  Installation of Tile","Cresthaven Elementary","",75000,"","","",75000]
[901,"Upgrade Fire Alarm Horns","Cresthaven Elementary",90000,"","","","",90000]
[221,"Electrical/Fire Safety Violations","Croissant Park Elementary",4947,5442,5986,6585,7244,30204]
[221,"Fencing: Replace Fence","Croissant Park Elementary","",64900,"","","",64900]
[221,"Flooring:  Installation of Tile","Croissant Park Elementary","",75000,"","","",75000]
[3222,"Remodel Time Out Room ","Cross Creek Center ",50501,{"$nulls":4},50501]
[3222,"Electrical/Fire Safety Violations","Cross Creek School",3209,3530,3883,4271,4698,19591]
[3222,"Flooring:  Installation of Tile","Cross Creek School","",30000,"","","",30000]
[1871,"Bus Drive","Crystal Lake Comm Middle ",250000,{"$nulls":4},250000]
[1871,"HSS/Bus Drive","Crystal Lake Comm Middle ",233626,{"$nulls":4},233626]
[1871,"Electrical/Fire Safety Violations","Crystal Lake Community Middle",10964,12061,13267,14594,16053,66939]
[1871,"Replace Fire Alarm System","Crystal Lake Community Middle","","","","",95000,95000]
[3623,"Electrical/Fire Safety Violations","Cypress Bay High",9000,9900,10890,11979,13177,54946]
[3621,"Replace Fire Alarm System","Cypress Bay High - 10th Grade Annex","","","","",160000,160000]
[1781,"Electrical/Fire Safety Violations","Cypress Elementary",3142,3457,3803,4183,4601,19186]
[1781,"Provide Fire Sprinkler Protection","Cypress Elementary","","",240000,"","",240000]
[2123,"Electrical/Fire Safety Violations","Cypress Run Alternative / Exceptional Center",869,956,1052,1157,1273,5307]
[1071,"Electrical/Fire Safety Violations","Dandy, William Middle",10095,11105,12216,13437,14781,61634]
[1071,"Flooring:  Installation of Tile","Dandy, William Middle","",45000,"","","",45000]
[101,"Electrical/Fire Safety Violations","Dania Elementary",5282,5811,6392,7031,7734,32250]
[101,"Provide Fire Sprinkler Protection","Dania Elementary","",230000,"","","",230000]
[101,"Replace Fire Alarm System","Dania Elementary","","",160000,"","",160000]
[2801,"Electrical/Fire Safety Violations","Davie Elementary",3611,3973,4370,4807,5288,22049]
[2801,"Provide Fire Sprinkler Protection","Davie Elementary",220000,"","","","",220000]
[2801,"Fire Alarm/Safety","Davie Elementary ",2953,{"$nulls":4},2953]
[11,"Electrical/Fire Safety Violations","Deerfield Beach Elementary",11566,12723,13995,15395,16935,70614]
[1711,"Electrical/Fire Safety Violations","Deerfield Beach High",25805,28386,31225,34347,37782,157545]
[1711,"Replace Fire Alarm System","Deerfield Beach High","","","",325000,"",325000]
[1711,"Fire Sprinkler System","Deerfield Beach High ",275000,{"$nulls":4},275000]
[911,"Electrical/Fire Safety Violations","Deerfield Beach Middle",10964,12061,13267,14594,16053,66939]
[911,"HSS/Fire Alarms","Deerfield Beach Middle ",60179,{"$nulls":4},60179]
[911,"Parent Drive Improvement","Deerfield Beach Middle ",150000,{"$nulls":4},150000]
[391,"Electrical/Fire Safety Violations","Deerfield Park Elementary",9226,10149,11164,12280,13508,56327]
[391,"Flooring:  Installation of Tile","Deerfield Park Elementary","",67500,"","","",67500]
[271,"Electrical/Fire Safety Violations","Dillard Elementary",4947,5442,5986,6585,7244,30204]
[271,"Flooring:  Installation of Tile","Dillard Elementary","",65000,"","","",65000]
[271,"Upgrade Fire Alarm Horns","Dillard Elementary",90000,"","","","",90000]
[371,"Electrical/Fire Safety Violations","Dillard High",47465,52212,57433,63177,69495,289782]
[371,"Fencing:  Replace Fence.","Dillard High","",83750,"","","",83750]
[371,"Provide Fire Sprinkler Protection","Dillard High","","","",375000,"",375000]
[0,"Asphalt Repairs:  Basketball/tennis courts","District Wide",168927,100000,100000,100000,100000,568927]
[0,"Automatic Electronic Defibrillators","District Wide",122372,50000,50000,50000,25000,297372]
[0,"Automatic Fire Curtain Closers","District Wide",115000,{"$nulls":4},115000]
[0,"Basketball Padding for High Schools","District Wide",20000,"","","","",20000]
[0,"Battery Lights Installation","District Wide","",200000,200000,200000,100000,700000]
[0,"Battery Lights Installation ","District Wide",300000,{"$nulls":4},300000]
[0,"Bike Safety Program","District Wide",31065,10000,10000,10000,10000,71065]
[0,"Bleachers ","District Wide",485492,{"$nulls":4},485492]
[0,"Bleachers:  Emergency repairs ","District Wide",175000,25000,50000,50000,50000,350000]
[0,"Boiler Inspections","District Wide",135811,118000,121000,124000,127000,625811]
[0,"Bus Barricades ","District Wide",52608,{"$nulls":4},52608]
[0,"Bus Drive","District Wide",159049,{"$nulls":4},159049]
[0,"Bus Safety \"Day Lights\"","District Wide",45000,15000,15000,"","",75000]
[0,"Compactors","District Wide",75000,50000,50000,50000,50000,275000]
[0,"Design","District Wide",150000,150000,150000,150000,150000,750000]
[0,"Drainage Replacement ","District Wide",105000,{"$nulls":4},105000]
[0,"Electric ","District Wide",236722,{"$nulls":4},236722]
[0,"Electrical/Fire Safety","District Wide",275000,{"$nulls":4},275000]
[0,"Elevator Inspections","District Wide",30000,35000,40000,45000,50000,200000]
[0,"Emergency Drives","District Wide",205159,200000,200000,200000,200000,1005159]
[0,"Emergency Fencing","District Wide",102631,100000,100000,100000,100000,502631]
[0,"Emergency Fire Alarms","District Wide",100204,100000,100000,100000,100000,500204]
[0,"Emergency Flooring","District Wide",214722,200000,200000,200000,200000,1014722]
[0,"Emergency Funding","District Wide",1057404,750000,800000,850000,900000,4357404]
[0,"Emergency Funding Contingency ","District Wide",376325,{"$nulls":4},376325]
[0,"Emergency Generators ","District Wide",1027939,{"$nulls":4},1027939]
[0,"Emergency HSS","District Wide",9308,{"$nulls":4},9308]
[0,"Energy Management","District Wide",4021191,{"$nulls":4},4021191]
[0,"Exhaust Fans/Ventilation ","District Wide",506859,{"$nulls":4},506859]
[0,"Exterior Survey of Lighting ","District Wide",85895,50000,50000,50000,50000,285895]
[0,"Fencing ","District Wide",1333279,{"$nulls":4},1333279]
[0,"Fencing: Replace Fence","District Wide",1555260,{"$nulls":4},1555260]
[0,"Fire Alarm Inspections ","District Wide",1878,{"$nulls":4},1878]
[0,"Fire Alarm Inspections & Repairs","District Wide",670440,500000,500000,500000,500000,2670440]
[0,"Fire Alarm Monitoring System","District Wide",75000,75000,75000,75000,50000,350000]
[0,"Fire Alarms ","District Wide",1158446,{"$nulls":4},1158446]
[0,"Fire Rate Of Corridors","District Wide",500000,{"$nulls":4},500000]
[0,"Fire Safety Abatement","District Wide",1828122,100000,100000,100000,100000,2228122]
[0,"Fire Safety Abatement","District Wide",43952,{"$nulls":4},43952]
[0,"Fire Safety Corrections","District Wide",166505,{"$nulls":4},166505]
[0,"Fire Sprinkler System Designs ","District Wide",65000,{"$nulls":4},65000]
[0,"Flooring ","District Wide",1336971,{"$nulls":4},1336971]
[0,"Flooring: Install of Tile","District Wide",1078677,{"$nulls":4},1078677]
[0,"HSS - Contingency","District Wide",1500000,1500000,1500000,1500000,1500000,7500000]
[0,"HSS Bike Racks","District Wide",49930,{"$nulls":4},49930]
[0,"HSS Concerns","District Wide",448075,{"$nulls":4},448075]
[0,"Inspection of Fire Sprinkler Systems","District Wide",290019,150000,150000,150000,150000,890019]
[0,"Inspection of Stage Rigging at 65 Schools","District Wide",50000,50000,50000,50000,50000,250000]
[0,"Inspections (Fire)","District Wide",26000,28000,30000,35000,40000,159000]
[0,"Install Emer. Generators","District Wide",60000,{"$nulls":4},60000]
[0,"Install Security Cameras","District Wide",100000,100000,100000,100000,100000,500000]
[0,"Installation of Fire Sprinklers in Storage/Restroom Areas","District Wide",300000,150000,150000,150000,150000,900000]
[0,"Intercoms ","District Wide",726022,{"$nulls":4},726022]
[0,"Key Boxes","District Wide",7862,5000,5000,5000,5000,27862]
[0,"Kitchen hood cleaning","District Wide",260000,70000,72000,74000,76000,552000]
[0,"Miscellaneous Site Work ","District Wide",90438,{"$nulls":4},90438]
[0,"Outside Security Lighting","District Wide",140314,{"$nulls":4},140314]
[0,"Playground Pavilions","District Wide",497637,150000,150000,150000,150000,1097637]
[0,"Playground Repairs","District Wide",355291,145000,155000,165000,175000,995291]
[0,"Portable Skirting","District Wide",176846,50000,50000,50000,50000,376846]
[0,"Repair Security Cameras","District Wide",299291,100000,100000,100000,100000,699291]
[0,"Repair/Repl.Exhaust Fans","District Wide",266484,{"$nulls":4},266484]
[0,"Repair/Replace. of Ramp","District Wide",8000,{"$nulls":4},8000]
[0,"Replace Bleachers","District Wide",578986,{"$nulls":4},578986]
[0,"Replace Pool Lane","District Wide",242997,{"$nulls":4},242997]
[0,"Replace Unsafe Picnic Tables/Furniture","District Wide",161733,100000,100000,100000,100000,561733]
[0,"Secondary Means of Egress","District Wide",934811,200000,100000,50000,50000,1334811]
[0,"Security/Safety Hardware","District Wide",197102,100000,100000,100000,100000,597102]
[0,"Security/Safety/Emergency Lighting","District Wide",100121,50000,50000,50000,50000,300121]
[0,"Shelter/Severe Weather Preparedness","District Wide",54021,50000,50000,50000,50000,254021]
[0,"Special Safety Inspect.","District Wide",99545,{"$nulls":4},99545]
[0,"Special Safety Inspections","District Wide",181886,100000,100000,100000,100000,581886]
[0,"Sport Light Replace/Repair","District Wide",150578,{"$nulls":4},150578]
[0,"Stage Rigging/Lights/Flooring ","District Wide",976892,{"$nulls":4},976892]
[0,"Storage Building","District Wide",228681,150000,150000,150000,100000,778681]
[0,"Test and Maint. Elect. Main Distribute Switchgear","District Wide",1858918,650000,650000,650000,850000,4658918]
[0,"Thermal Scanning Electrical Mechanical Systems (FPL)","District Wide",303338,250000,250000,250000,250000,1303338]
[0,"Tumbling Mats","District Wide",60000,"","","","",60000]
[0,"Vision Windows in Doors","District Wide",120428,25000,25000,25000,25000,220428]
[0,"Weight Room Equipment Maint/Repair","District Wide",18000,18000,20000,25000,25000,106000]
[301,"Electrical/Fire Safety Violations","Drew Resource Center",5616,6178,6796,7475,8223,34288]
[301,"HSS/Fire Alarms","Drew Resource Center ",216287,{"$nulls":4},216287]
[3221,"Electrical/Fire Safety Violations","Drew, Charles Elementary",2407,2648,2913,3204,3524,14696]
[721,"Electrical/Fire Safety Violations","Driftwood Elementary",5483,6032,6635,7299,8029,33478]
[861,"Electrical/Fire Safety Violations","Driftwood Middle",11231,12355,13591,14950,16445,68572]
[861,"Bus Driveway ","Driftwood Middle ",240936,{"$nulls":4},240936]
[3461,"Electrical/Fire Safety Violations","Eagle Point Elementary",4279,4707,5178,5695,6265,26124]
[3461,"Replace Fire Alarm System","Eagle Point Elementary","","","","",125000,125000]
[3441,"Electrical/Fire Safety Violations","Eagle Ridge Elementary",4547,5002,5502,6052,6657,27760]
[3441,"Replace Fire Alarm System","Eagle Ridge Elementary","","",160000,"","",160000]
[361,"HSS/Fire Alarms","Ely High ",97100,{"$nulls":4},97100]
[3191,"Electrical/Fire Safety Violations","Embassy Creek Elementary",5081,5590,6149,6764,7440,31024]
[3301,"Electrical/Fire Safety Violations","Endeavor Primary Learning Center",3000,3300,3630,3993,4392,18315]
[9830,"Electrical/Fire Safety Violations","ESEA Title I",8200,9020,9922,10914,12005,50061]
[2942,"Electrical/Fire Safety Violations","Everglades Elementary",5125,5638,6202,6822,7504,31291]
[1641,"Electrical/Fire Safety Violations","Fairway Elementary",7755,8531,9384,10323,11355,47348]
[1641,"Provide Fire Sprinkler Protection","Fairway Elementary","","",240000,"","",240000]
[3622,"Electrical/Fire Safety Violations","Falcon Cove Middle",6218,6840,7524,8276,9104,37962]
[3622,"Parent Drive Renovations ","Falcon Cove Middle ",499777,{"$nulls":4},499777]
[2541,"Electrical/Fire Safety Violations","Flamingo Elementary",5616,6178,6796,7475,8223,34288]
[2541,"Infra-Electric:  Install New Generator","Flamingo Elementary","",120000,"","","",120000]
[2541,"Provide Fire Sprinkler Protection","Flamingo Elementary",220000,"","","","",220000]
[2541,"HSS/Fire Alarms","Flamingo Elementary ",3573,{"$nulls":4},3573]
[3392,"Fire Alarm System ","Flanagan High Annex ",30000,{"$nulls":4},30000]
[3513,"School Zone Lights & Signs ","Flanagan High-9th Grade Ctr ",13207,{"$nulls":4},13207]
[3391,"Electrical/Fire Safety Violations","Flanagan, Charles High",7488,8237,9061,9967,10964,45717]
[3391,"Repair / Replace Stage Rigging","Flanagan, Charles High","",90000,"","","",90000]
[851,"Electrical/Fire Safety Violations","Floranada Elementary",4659,5125,5638,6201,6821,28444]
[3051,"Bleachers: Replace Gym Bleachers","Forest Glen Middle","","",100000,"","",100000]
[3051,"Electrical/Fire Safety Violations","Forest Glen Middle",10430,11473,12620,13882,15270,63675]
[3051,"Flooring:  Installation of Tile","Forest Glen Middle","",40000,"","","",40000]
[2631,"Electrical/Fire Safety Violations","Forest Hills Elementary",10964,12061,13267,14594,16053,66939]
[2631,"Provide Fire Sprinkler Protection","Forest Hills Elementary",220000,"","","","",220000]
[2631,"Replace Fire Alarm System","Forest Hills Elementary","","","",195000,"",195000]
[951,"Electrical/Fire Safety Violations","Fort Lauderdale High",14040,15444,16988,18687,20556,85715]
[951,"Flooring:  Installation of Tile","Fort Lauderdale High",25000,"","","","",25000]
[951,"Provide Fire Sprinkler Protection","Fort Lauderdale High","","","",375000,"",375000]
[951,"Replace Dimmer Board","Fort Lauderdale High",100000,"","","","",100000]
[921,"Electrical/Fire Safety Violations","Foster, Stephen Elementary",10964,12061,13267,14594,16053,66939]
[921,"Fencing:  Replace Fence","Foster, Stephen Elementary","",63000,"","","",63000]
[921,"Flooring:  Installation of Tile","Foster, Stephen Elementary","",40000,"","","",40000]
[3531,"Electrical/Fire Safety Violations","Fox Trail Elementary",5125,5638,6202,6822,7504,31291]
[3531,"Parking Lot","Fox Trail Elementary",95000,"","","","",95000]
[3642,"Electrical/Fire Safety Violations","Gator Run Elementary",5125,5638,6202,6822,7504,31291]
[2851,"Electrical/Fire Safety Violations","Griffin Elementary",3343,3678,4046,4450,4895,20412]
[2851,"Provide Fire Sprinkler Protection","Griffin Elementary",220000,"","","","",220000]
[592,"Electrical/Fire Safety Violations","Hallandale Adult/Community",7621,8384,9222,10145,11160,46532]
[592,"Fencing: Replace Fence (perimeter of school)","Hallandale Adult/Community","",115103,"","","",115103]
[131,"Electrical/Fire Safety Violations","Hallandale Elementary",5214,5736,6310,6941,7635,31836]
[131,"Flooring: Installation of Tile","Hallandale Elementary",75000,"","","","",75000]
[131,"Replace Fire Alarm System","Hallandale Elementary","","","",160000,"",160000]
[592,"HSS/Fire Alarms","Hallandale Food Service ",47640,{"$nulls":4},47640]
[592,"HSS/Intercoms","Hallandale Food Service ",189666,{"$nulls":4},189666]
[403,"Bleachers: Replace Track Bleachers","Hallandale High",30000,"","","","",30000]
[403,"Electrical/Fire Safety Violations","Hallandale High",5549,6104,6714,7386,8125,33878]
[403,"Flooring:  Installation of Tile","Hallandale High",75000,"","","","",75000]
[403,"Provide Fire Sprinkler Protection","Hallandale High","","","","",450000,450000]
[403,"Repair / Replace Stage Rigging","Hallandale High","",90000,"","","",90000]
[403,"Replace Fire Alarm System","Hallandale High","",325000,"","","",325000]
[491,"Electrical/Fire Safety Violations","Harbordale Elementary",5081,5590,6149,6764,7440,31024]
[491,"HSS/Fire Alarms","Harbordale Elementary ",59955,{"$nulls":4},59955]
[3131,"Electrical/Fire Safety Violations","Hawkes Bluff Elementary",6954,7650,8415,9257,10183,42459]
[3131,"Flooring:  Installation of Tile","Hawkes Bluff Elementary",17000,"","","","",17000]
[3131,"Replace existing Edwards (5721B) fire alarm system ","Hawkes Bluff Elementary",120000,"","","","",120000]
[3131,"Replace Fire Alarm System","Hawkes Bluff Elementary","",160000,"","","",160000]
[121,"Electrical/Fire Safety Violations","Hollywood Central Elementary",6686,7355,8091,8900,9790,40822]
[121,"Repair / Replace Stage Rigging","Hollywood Central Elementary","",90000,"","","",90000]
[121,"Upgrade Fire Alarm Horns","Hollywood Central Elementary",90000,"","","","",90000]
[121,"Road Signs/Lights ","Hollywood Central Elementary ",31468,{"$nulls":4},31468]
[111,"Electrical/Fire Safety Violations","Hollywood Hills Elementary",5750,6325,6958,7653,8418,35104]
[1661,"Bus Drive","Hollywood Hills High",400000,"","","","",400000]
[1661,"Electrical/Fire Safety Violations","Hollywood Hills High",12969,14266,15693,17262,18988,79178]
[1661,"Replace Fire Alarm System","Hollywood Hills High","","","","",325000,325000]
[1661,"HSS/Install Softball Field","Hollywood Hills High ",37865,{"$nulls":4},37865]
[1761,"Electrical/Fire Safety Violations","Hollywood Park Elementary",3544,3899,4289,4718,5190,21640]
[1761,"Provide Fire Sprinkler Protection","Hollywood Park Elementary","","",240000,"","",240000]
[2531,"Electrical/Fire Safety Violations","Horizon Elementary",20123,22136,24350,26785,29464,122858]
[2531,"Flooring:  Installation of Tile","Horizon Elementary",75000,"","","","",75000]
[2531,"Provide Fire Sprinkler Protection","Horizon Elementary",220000,"","","","",220000]
[9067,"Electric/Fire Safety Violations","Hortt Admin Site",9371,10309,11340,12474,13721,57215]
[1971,"Electrical/Fire Safety Violations","Hunt, James S. Elementary",9661,10628,11691,12860,14146,58986]
[1971,"Flooring:  Installation of Tile","Hunt, James S. Elementary",35000,"","","","",35000]
[3471,"Electrical/Fire Safety Violations","Indian Ridge Middle",6218,6840,7524,8276,9104,37962]
[3471,"Replace Fire Alarm System","Indian Ridge Middle","","","","",195000,195000]
[3181,"Electrical/Fire Safety Violations","Indian Trace Elementary",4045,4450,4895,5385,5924,24699]
[9328,"Electrical/Fire Safety Violations","Kathleen Wright Admin Site",9371,10309,11340,12474,13721,57215]
[1611,"HSS/Fire Alarms","King Martin Luther Elementary ",30000,{"$nulls":4},30000]
[1611,"Electrical/Fire Safety Violations","King, Martin Luther Elementary",4947,5442,5986,6585,7244,30204]
[1611,"Flooring:  Installation of Tile","King, Martin Luther Elementary",50000,"","","","",50000]
[1611,"Provide Fire Sprinkler Protection","King, Martin Luther Elementary","",230000,"","","",230000]
[831,"Electrical/Fire Safety Violations","Lake Forest Elementary",4680,5148,5663,6229,6852,28572]
[3591,"Electrical/Fire Safety Violations","Lakeside Elementary",5125,5638,6202,6822,7504,31291]
[405,"Electrical/Fire Safety Violations","Lanier-James Education Center",5883,6472,7119,7831,8614,35919]
[405,"Replace Fire Alarm System","Lanier-James Education Center","",160000,"","","",160000]
[621,"Electrical/Fire Safety Violations","Larkdale Elementary",5081,5590,6149,6764,7440,31024]
[621,"Flooring:  Installation of Tile","Larkdale Elementary",75000,"","","","",75000]
[621,"Flooring:  Installation of Tile","Larkdale Elementary","",25000,"","","",25000]
[621,"Replace Fire Alarm System","Larkdale Elementary",160000,"","","","",160000]
[1701,"Electrical/Fire Safety Violations","Lauderdale Lakes Middle",13371,14709,16180,17798,19578,81636]
[1701,"Flooring:  Installation of Tile","Lauderdale Lakes Middle",75000,"","","","",75000]
[1701,"Provide Fire Sprinkler Protection - KIVA","Lauderdale Lakes Middle",50000,"","","","",50000]
[431,"Electrical/Fire Safety Violations","Lauderdale Manors Elementary",7354,8090,8899,9789,10768,44900]
[431,"Flooring:  Installation of Tile","Lauderdale Manors Elementary",48000,"","","","",48000]
[1391,"Bleachers: Replace Gym Bleachers","Lauderhill Middle","",100000,"","","",100000]
[1391,"Electrical/Fire Safety Violations","Lauderhill Middle",29817,32799,36079,39687,43656,182038]
[1391,"Flooring:  Installation of Tile","Lauderhill Middle",75000,"","","","",75000]
[1391,"Provide Fire Sprinkler Protection - KIVA","Lauderhill Middle",50000,"","","","",50000]
[1381,"Electrical/Fire Safety Violations","Lauderhill, P. T. Elementary",6418,7060,7766,8543,9397,39184]
[3821,"Electrical/Fire Safety Violations","Liberty Elementary",3000,3300,3630,3993,4392,18315]
[1091,"Electrical/Fire Safety Violations","Lloyd Estates Elementary",5014,5516,6068,6674,7341,30613]
[1091,"Provide Fire Sprinkler Protection","Lloyd Estates Elementary","",230000,"","","",230000]
[1091,"HSS/Fire Alarms","Lloyd Estates Elementary ",58615,{"$nulls":4},58615]
[1091,"HSS/Intercoms","Lloyd Estates Elementary ",35000,{"$nulls":4},35000]
[3231,"Electrical/Fire Safety Violations","Lockhart Stadium",4906,5397,5937,6530,7183,29953]
[3101,"Electrical/Fire Safety Violations","Lyons Creek Middle",6218,6840,7524,8276,9104,37962]
[3831,"Electrical/Fire Safety Violations","Manatee Bay Elementary",3000,3300,3630,3993,4392,18315]
[2741,"Electrical/Fire Safety Violations","Maplewood Elementary",8959,9855,10841,11925,13118,54698]
[2741,"Provide Fire Sprinkler Protection","Maplewood Elementary",220000,"","","","",220000]
[2741,"Intercom System","Maplewood Elementary ",49940,{"$nulls":4},49940]
[1161,"Electrical/Fire Safety Violations","Margate Elementary",6786,7465,8212,9033,9936,41432]
[1161,"Replace Fire Alarm System","Margate Elementary","","",160000,"","",160000]
[581,"Electrical/Fire Safety Violations","Margate Middle",6686,7355,8091,8900,9790,40822]
[1671,"Electrical/Fire Safety Violations","Markham, Robert Elementary",5349,5884,6472,7120,7832,32657]
[3291,"Electrical/Fire Safety Violations","Marshall, Thurgood Elementary",3611,3973,4370,4807,5288,22049]
[241,"Bleachers:  Replace pool bleachers","McArthur High",25000,"","","","",25000]
[241,"Campus Drainage Repair","McArthur High",250000,"","","","",250000]
[241,"Electrical/Fire Safety Violations","McArthur High",12302,13533,14886,16375,18013,75109]
[241,"Intercom/Master Clock","McArthur High",150000,{"$nulls":4},150000]
[241,"Parent/Bus Drop Off Expansion","McArthur High",500000,"","","","",500000]
[241,"Replace Covered Walkways","McArthur High",475000,"","","","",475000]
[1291,"Electrical/Fire Safety Violations","McFatter Technical Center",7354,8090,8899,9789,10768,44900]
[1291,"Provide Intercom System","McFatter Technical Center",250000,"","","","",250000]
[841,"Electrical/Fire Safety Violations","McNab Elementary",1873,2061,2267,2494,2743,11438]
[481,"Electrical/Fire Safety Violations","McNicol Middle",3410,3751,4126,4539,4993,20819]
[761,"Electrical/Fire Safety Violations","Meadowbrook Elementary",6285,6914,7605,8366,9203,38373]
[9214,"Electrical/Fire Safety Violations","Metric Center",3000,3300,3630,3993,4392,18315]
[9214,"Electrical/Fire Safety Violations","Metric Center",15594,17154,18869,20756,22832,95205]
[9214,"Replace Fire Alarm System","Metric Center","",160000,"","","",160000]
[9214,"HSS Concerns","Metric Center ",25000,{"$nulls":4},25000]
[3772,"Electrical/Fire Safety Violations","Millennium Middle",6000,6600,7260,7986,8785,36631]
[531,"Electrical/Fire Safety Violations","Miramar Elementary",4345,4780,5258,5784,6362,26529]
[531,"Upgrade Fire Alarm Horns","Miramar Elementary",90000,"","","","",90000]
[1751,"Electrical/Fire Safety Violations","Miramar High",9628,10591,11650,12815,14097,58781]
[1841,"Electrical/Fire Safety Violations","Mirror Lake Elementary",12769,14046,15451,16996,18696,77958]
[1841,"Provide Fire Sprinkler Protection","Mirror Lake Elementary","","",240000,"","",240000]
[1841,"Fire Alarm Replacement","Mirror Lake Elementary ",120000,{"$nulls":4},120000]
[2691,"Electrical/Fire Safety Violations","Morrow Elementary",3276,3604,3964,4361,4797,20002]
[2691,"Fencing: Replace Fence (perimeter of school)","Morrow Elementary","",56496,"","","",56496]
[2691,"Provide Fire Sprinkler Protection","Morrow Elementary",220000,"","","","",220000]
[2691,"Replace Fire Alarm System","Morrow Elementary","","",160000,"","",160000]
[2691,"HSS/Intercoms","Morrow Elementary ",30000,{"$nulls":4},30000]
[2691,"Parent Drive Widening ","Morrow Elementary ",50000,{"$nulls":4},50000]
[3671,"Electrical/Fire Safety Violations","New Renaissance Middle",6000,6600,7260,7986,8785,36631]
[881,"Bleachers: Replace Gym Bleachers","New River Middle","","",50000,"","",50000]
[881,"Electrical/Fire Safety Violations","New River Middle",3343,3678,4046,4450,4895,20412]
[2671,"Electrical/Fire Safety Violations","Nob Hill Elementary",8959,9855,10841,11925,13118,54698]
[2671,"Flooring:  Installation of Tile","Nob Hill Elementary","",30000,"","","",30000]
[2671,"Provide Fire Sprinkler Protection","Nob Hill Elementary",220000,"","","","",220000]
[2671,"HSS/Fire Alarms","Nob Hill Elementary ",33470,{"$nulls":4},33470]
[561,"Electrical/Fire Safety Violations","Norcrest Elementary",6686,7355,8091,8900,9790,40822]
[521,"Electrical/Fire Safety Violations","North Andrews Gardens Elementary",7421,8164,8980,9878,10866,45309]
[9278,"Electrical/Fire Safety Violations","North Area Maint/Bus Parking",5199,5719,6291,6920,7612,31741]
[9360,"Electrical/Fire Safety Violations","North Area Maint/Warehouse",2856,3142,3456,3802,4182,17438]
[9155,"Electrical/Fire Safety Violations","North Bus Parking Lot",1172,1290,1419,1561,1717,7159]
[9384,"Fire Sprinkler System ","North Central Superintendent ",100000,{"$nulls":4},100000]
[1191,"Electrical/Fire Safety Violations","North Fork Elementary",11499,12649,13914,15305,16836,70203]
[1191,"Flooring:  Installation of Tile","North Fork Elementary",25000,"","","","",25000]
[1191,"Provide Fire Sprinkler Protection","North Fork Elementary","",230000,"","","",230000]
[2231,"Electrical/Fire Safety Violations","North Lauderdale Elementary",4947,5442,5986,6585,7244,30204]
[2231,"Provide Fire Sprinkler Protection","North Lauderdale Elementary","",230000,"","","",230000]
[2231,"Replace Fire Alarm System","North Lauderdale Elementary","","","",160000,"",160000]
[41,"Electrical/Fire Safety Violations","North Side Elementary",6352,6988,7687,8455,9301,38783]
[41,"Flooring:  Installation of Tile","North Side Elementary",30000,"","","","",30000]
[41,"Parent Drive","North Side Elementary",100000,"","","","",100000]
[1241,"Bleachers:  Replace soccer bleachers","Northeast High","",15000,"","","",15000]
[1241,"Bleachers:  Replace track bleachers","Northeast High","",25000,"","","",25000]
[1241,"Bleachers: Replace Softball Bleachers","Northeast High","","",2500,"","",2500]
[1241,"Electrical/Fire Safety Violations","Northeast High",9293,10223,11245,12370,13607,56738]
[1241,"Provide Fire Sprinkler Protection","Northeast High",150000,"","","","",150000]
[1241,"Repair / Replace Stage Rigging","Northeast High",90000,"","","","",90000]
[9384,"Electrical/Fire Safety Violations","North Central Area Office",3300,3630,3993,4392,4831,20146]
[1282,"Electrical/Fire Safety Violations","Nova Blanche Forman Elementary",3611,3973,4370,4807,5288,22049]
[1282,"Provide Fire Sprinkler Protection","Nova Blanche Forman Elementary","",230000,"","","",230000]
[1282,"Traffic Signal","Nova Blanche Forman Elementary",180000,"","","","",180000]
[1271,"Electrical/Fire Safety Violations","Nova Eisenhower Elementary",4012,4414,4855,5341,5875,24497]
[1271,"Provide Fire Sprinkler Protection","Nova Eisenhower Elementary","",230000,"","","",230000]
[1271,"Bus/Parent Drive ","Nova Eisenhower Elementary ",21517,{"$nulls":4},21517]
[1282,"Fire Hydrant","Nova Forman Elementary ",230700,{"$nulls":4},230700]
[1281,"Electrical/Fire Safety Violations","Nova High",10430,11473,12620,13882,15270,63675]
[1281,"Provide Fire Sprinkler Protection","Nova High","","","",450000,"",450000]
[1281,"Repair / Replace Stage Rigging","Nova High","",90000,"","","",90000]
[1281,"Drainage","Nova High ",160000,{"$nulls":4},160000]
[1281,"HSS/Fire Alarms","Nova High ",161011,{"$nulls":4},161011]
[1281,"HSS/Intercoms","Nova High ",145811,{"$nulls":4},145811]
[1311,"Electrical/Fire Safety Violations","Nova Middle",6151,6767,7444,8188,9007,37557]
[1311,"Provide Fire Sprinkler Protection","Nova Middle","","","",350000,"",350000]
[31,"Electrical/Fire Safety Violations","Oakland Park Elementary",7087,7796,8576,9433,10376,43268]
[31,"Repair / Replace Stage Rigging","Oakland Park Elementary",90000,"","","","",90000]
[461,"Electrical/Fire Safety Violations","Oakridge Elementary",3343,3678,4046,4450,4895,20412]
[471,"Bleachers: Replace Gym Bleachers","Olsen Middle","","",100000,"","",100000]
[471,"Electrical/Fire Safety Violations","Olsen Middle",3142,3457,3803,4183,4601,19186]
[471,"Electrical/Fire Safety Violations","Olsen Middle",1605,1766,1943,2137,2351,9802]
[711,"Electrical/Fire Safety Violations","Orange Brook Elementary",5750,6325,6958,7653,8418,35104]
[711,"Parking Lot","Orange Brook Elementary",150000,"","","","",150000]
[1831,"Electrical/Fire Safety Violations","Oriole Elementary",10229,11252,12377,13615,14977,62450]
[1831,"Provide Fire Sprinkler Protection","Oriole Elementary","","",240000,"","",240000]
[3311,"Electrical/Fire Safety Violations","Palm Cove Elementary",4680,5148,5663,6229,6852,28572]
[1131,"Electrical/Fire Safety Violations","Palmview Elementary",5750,6325,6958,7653,8418,35104]
[1131,"Fencing: Replace Fence (perimeter of school)","Palmview Elementary","",94104,"","","",94104]
[1131,"Provide Fire Sprinkler Protection","Palmview Elementary","","",240000,"","",240000]
[1131,"Replace Fire Alarm System","Palmview Elementary","","",160000,"","",160000]
[3571,"Electrical/Fire Safety Violations","Panther Run Elementary",5125,5638,6202,6822,7504,31291]
[3571,"Electrical/Fire Safety Violations","Panther Run Elementary",3000,3300,3630,3993,4392,18315]
[1951,"Electrical/Fire Safety Violations","Park Ridge Elementary",7354,8090,8899,9789,10768,44900]
[3171,"Electrical/Fire Safety Violations","Park Springs Elementary",1873,2061,2267,2494,2743,11438]
[3171,"Replace Fire Alarm System","Park Springs Elementary","","","","",160000,160000]
[3781,"Electrical/Fire Safety Violations","Park Trails Elementary",3300,3630,3993,4392,4831,20146]
[701,"Electrical/Fire Safety Violations","Parkway Middle",12368,13605,14966,16462,18108,75509]
[701,"Flooring:  Installation of Tile","Parkway Middle","",45000,"","","",45000]
[2071,"Electrical/Fire Safety Violations","Pasadena Lakes Elementary",5483,6032,6635,7299,8029,33478]
[2071,"Replace Carpet with Tile-Entire School","Pasadena Lakes Elementary",85000,"","","","",85000]
[2071,"Replace Fire Alarm System","Pasadena Lakes Elementary","",160000,"","","",160000]
[2071,"Driveway Safety Renovations ","Pasadena Lakes Elementary ",150000,{"$nulls":4},150000]
[2661,"Electrical/Fire Safety Violations","Pembroke Lakes Elementary",9561,10518,11570,12727,14000,58376]
[2661,"Flooring:  Installation of Tile","Pembroke Lakes Elementary",85000,"","","","",85000]
[2661,"Provide Fire Sprinkler Protection","Pembroke Lakes Elementary","",230000,"","","",230000]
[2661,"Replace Fire Alarm System","Pembroke Lakes Elementary",160000,"","","","",160000]
[1221,"Electrical/Fire Safety Violations","Pembroke Pines Elementary",8357,9193,10112,11124,12236,51022]
[1221,"Flooring:  Installation of Tile","Pembroke Pines Elementary",85000,"","","","",85000]
[1221,"Provide Fire Sprinkler Protection","Pembroke Pines Elementary","",230000,"","","",230000]
[1631,"Electrical/Fire Safety Violations","Perry, Annabel Elementary",10430,11473,12620,13882,15270,63675]
[1631,"Flooring:  Installation of Tile","Perry, Annabel Elementary",85000,"","","","",85000]
[1631,"Provide Fire Sprinkler Protection","Perry, Annabel Elementary","",230000,"","","",230000]
[1011,"Bleachers: Replace Gym Bleachers","Perry, Henry D. Middle",100000,"","","","",100000]
[1011,"Electrical/Fire Safety Violations","Perry, Henry D. Middle",8692,9562,10518,11570,12727,53069]
[931,"Electrical/Fire Safety Violations","Peters Elementary",6418,7060,7766,8543,9397,39184]
[931,"Flooring:  Installation of Tile","Peters Elementary","",55000,"","","",55000]
[931,"Driveway Safety Renovations ","Peters Elementary ",250000,{"$nulls":4},250000]
[653,"Fire Alarm & Intercom Replacem","Pine Ridge Alternative Center",180000,{"$nulls":4},180000]
[653,"Electrical/Fire Safety Violations","Pine Ridge Alternative Center",5081,5590,6149,6764,7440,31024]
[2861,"Electrical/Fire Safety Violations","Pines Lakes Elementary",8892,9782,10760,11836,13020,54290]
[2861,"Flooring:  Installation of Tile","Pines Lakes Elementary",85000,"","","","",85000]
[2861,"Provide Fire Sprinkler Protection","Pines Lakes Elementary","","",240000,"","",240000]
[2861,"Parent & Bus Drive ","Pines Lakes Elementary ",200000,{"$nulls":4},200000]
[1881,"Electrical/Fire Safety Violations","Pines Middle",14040,15444,16988,18687,20556,85715]
[2811,"Electrical/Fire Safety Violations","Pinewood Elementary",6819,7501,8251,9076,9984,41631]
[2811,"Fencing: Replace Fence (perimeter of school)","Pinewood Elementary","",104280,"","","",104280]
[2811,"Provide Fire Sprinkler Protection","Pinewood Elementary","","",240000,"","",240000]
[2811,"HSS/Firealarm/Intercom","Pinewood Elementary ",119682,{"$nulls":4},119682]
[2571,"Electrical/Fire Safety Violations","Pioneer Middle",8357,9193,10112,11124,12236,51022]
[2571,"Provide Fire Sprinkler Protection","Pioneer Middle","","","",350000,"",350000]
[1901,"Electrical/Fire Safety Violations","Piper High",7621,8384,9222,10145,11160,46532]
[1901,"Flooring:  Installation of Tile","Piper High",45000,"","","","",45000]
[1901,"Repair / Replace Stage Rigging","Piper High","",90000,"","","",90000]
[1901,"Replace Fire Alarm System","Piper High","",325000,"","","",325000]
[1901,"Bus/Parent Drive ","Piper High ",457224,{"$nulls":4},457224]
[941,"Electrical/Fire Safety Violations","Plantation Elementary",4659,5125,5638,6201,6821,28444]
[1451,"Bleachers: Replace tennis bleachers","Plantation High",25000,"","","","",25000]
[1451,"Electrical/Fire Safety Violations","Plantation High",11900,13090,14399,15839,17423,72651]
[1451,"Fencing:  Replace Fence","Plantation High","",126000,"","","",126000]
[1451,"Provide Fire Sprinkler Protection","Plantation High","",385000,"","","",385000]
[1451,"Repair / Replace Stage Rigging","Plantation High","",90000,"","","",90000]
[551,"Electrical/Fire Safety Violations","Plantation Middle",11766,12943,14237,15661,17227,71834]
[551,"Provide Fire Sprinkler Protection - KIVA","Plantation Middle",50000,"","","","",50000]
[551,"HVAC, Fire Alarm/Intercom","Plantation Middle ",388333,{"$nulls":4},388333]
[1251,"Electrical/Fire Safety Violations","Plantation Park Elementary",3611,3973,4370,4807,5288,22049]
[1251,"Flooring:  Installation of Tile","Plantation Park Elementary",30000,"","","","",30000]
[1251,"Provide Fire Sprinkler Protection","Plantation Park Elementary","",230000,"","","",230000]
[751,"Electrical/Fire Safety Violations","Pompano Beach Elementary",5081,5590,6149,6764,7440,31024]
[185,"Bleachers:  Replace gym bleachers","Pompano Beach High School Institute of International Studies","",175000,"","","",175000]
[185,"Electrical/Fire Safety Violations","Pompano Beach High School Institute of International Studies",9000,9900,10890,11979,13177,54946]
[185,"Replace Weight Room","Pompano Beach High School Institute of International Studies","",75000,"","","",75000]
[21,"Electrical/Fire Safety Violations","Pompano Beach Middle",10964,12061,13267,14594,16053,66939]
[21,"Provide Fire Sprinkler Protection","Pompano Beach Middle",125000,"","","","",125000]
[21,"Fire Alarm Replacement ","Pompano Beach Middle ",150000,{"$nulls":4},150000]
[3121,"Electrical/Fire Safety Violations","Quiet Waters Elementary",4212,4634,5097,5607,6168,25718]
[3121,"Fire Alarm Replacement","Quiet Waters Elementary",120000,"","","","",120000]
[2721,"Electrical/Fire Safety Violations","Ramblewood Elementary",4413,4855,5341,5875,6463,26947]
[2721,"Provide Fire Sprinkler Protection","Ramblewood Elementary","","",240000,"","",240000]
[2721,"HSS/Fire Alarms","Ramblewood Elementary ",12981,{"$nulls":4},12981]
[2711,"Electrical/Fire Safety Violations","Ramblewood Middle",4680,5148,5663,6229,6852,28572]
[2711,"Provide Fire Sprinkler Protection","Ramblewood Middle","","","",350000,"",350000]
[2711,"HSS/Firealarm/Intercom","Ramblewood Middle ",3600,{"$nulls":4},3600]
[2121,"Electrical/Fire Safety Violations","Rickards Middle",8023,8826,9709,10679,11747,48984]
[2121,"Provide Fire Sprinkler Protection - KIVA","Rickards Middle",50000,"","","","",50000]
[2121,"Replace Fire Alarm System","Rickards Middle","",195000,"","","",195000]
[2121,"Repair Kiva","Rickards Middle ",100000,{"$nulls":4},100000]
[2891,"Electrical/Fire Safety Violations","Riverglades Elementary",4279,4707,5178,5695,6265,26124]
[151,"Electrical/Fire Safety Violations","Riverland Elementary",3744,4119,4531,4984,5482,22860]
[151,"Flooring:  Installation of Tile","Riverland Elementary","",40000,"","","",40000]
[151,"Upgrade Fire Alarm Horns","Riverland Elementary",90000,"","","","",90000]
[3031,"Electrical/Fire Safety Violations","Riverside Elementary",3343,3678,4046,4450,4895,20412]
[681,"Electrical/Fire Safety Violations","Rock Island Elementary",8759,9635,10599,11658,12824,53475]
[681,"Electrical/Fire Safety Violations","Rock Island Elementary",3000,3300,3630,3993,4392,18315]
[1851,"Electrical/Fire Safety Violations","Royal Palm Elementary",5014,5516,6068,6674,7341,30613]
[1851,"Flooring:  Installation of Tile","Royal Palm Elementary",50000,"","","","",50000]
[9335,"Install Generator","S/W Bus Parking Facilities",286000,"","","","",286000]
[9536,"Electrical/Fire Safety Violations","Safety Department",1210,1320,1430,1573,1730,7263]
[891,"Electrical/Fire Safety Violations","Sanders Park Elementary",5683,6252,6877,7565,8322,34699]
[891,"Provide Fire Sprinkler Protection","Sanders Park Elementary","",230000,"","","",230000]
[3061,"Electrical/Fire Safety Violations","Sandpiper Elementary",5282,5811,6392,7031,7734,32250]
[3061,"Flooring:  Installation of Tile","Sandpiper Elementary","",30000,"","","",30000]
[3401,"Electrical/Fire Safety Violations","Sawgrass Elementary",3544,3899,4289,4718,5190,21640]
[3401,"Flooring:  Installation of Tile","Sawgrass Elementary","",60000,"","","",60000]
[3431,"Electrical/Fire Safety Violations","Sawgrass Springs Middle",7020,7722,8494,9344,10278,42858]
[2871,"Electrical/Fire Safety Violations","Sea Castle Elementary",4279,4707,5178,5695,6265,26124]
[2871,"Flooring: Installation of Tile","Sea Castle Elementary",75000,"","","","",75000]
[2871,"Parent Drive Expansion ","Sea Castle Elementary ",100000,{"$nulls":4},100000]
[601,"Electrical/Fire Safety Violations","Seagull School",7621,8384,9222,10145,11160,46532]
[601,"Fire Alarm & Intercom Replacement","Seagull School ",162960,{"$nulls":4},162960]
[1891,"Bus Drive","Seminole Middle",550000,"","","","",550000]
[1891,"Electrical/Fire Safety Violations","Seminole Middle",8959,9855,10841,11925,13118,54698]
[1891,"Fire Alarm Replacement","Seminole Middle",195000,"","","","",195000]
[1891,"Modify Restrooms","Seminole Middle",80000,"","","","",80000]
[1891,"Provide Fire Sprinkler Protection","Seminole Middle","","","",350000,"",350000]
[1811,"Electrical/Fire Safety Violations","Sheridan Hills Elementary",5683,6252,6877,7565,8322,34699]
[1811,"Provide Fire Sprinkler Protection","Sheridan Hills Elementary","","",240000,"","",240000]
[1321,"Electrical/Fire Safety Violations","Sheridan Park Elementary",3811,4193,4612,5074,5581,23271]
[1321,"Provide Fire Sprinkler Protection","Sheridan Park Elementary","",230000,"","","",230000]
[1051,"Electrical/Fire Safety Violations","Sheridan Technical Center",17048,18753,20628,22691,24960,104080]
[3371,"Electrical/Fire Safety Violations","Silver Lakes Elementary",5125,5638,6202,6822,7504,31291]
[3371,"Bus/Parent Drive","Silver Lakes Elementary Q-91 ",80662,{"$nulls":4},80662]
[2971,"Electrical/Fire Safety Violations","Silver Lakes Middle",6954,7650,8415,9257,10183,42459]
[2971,"Flooring:  Installation of Tile","Silver Lakes Middle","",40000,"","","",40000]
[2971,"HSS/Firealarm/Intercom","Silver Lakes Middle ",160231,{"$nulls":4},160231]
[3491,"Electrical/Fire Safety Violations","Silver Palms Elementary",5282,5811,6392,7031,7734,32250]
[3081,"Electrical/Fire Safety Violations","Silver Ridge Elementary",4947,5442,5986,6585,7244,30204]
[3081,"Replace Fire Alarm System","Silver Ridge Elementary","","","",180000,"",180000]
[3581,"Electrical/Fire Safety Violations","Silver Shores Elementary",3000,3300,3630,3993,4392,18315]
[3331,"Electrical/Fire Safety Violations","Silver Trail Middle",6886,7575,8333,9166,10083,42043]
[3331,"Chainlink Fence ","Silver Trail Middle ",1942,{"$nulls":4},1942]
[3331,"Temporary Drive HSS","Silver Trail Middle ",70278,{"$nulls":4},70278]
[9316,"Replace Fire Alarm System","South Area Admin Site","","",120000,"","",120000]
[9279,"Electrical/Fire Safety Violations","South Area Bus Parking Lot",1099,1209,1330,1463,1609,6710]
[9379,"Electrical/Fire Safety Violations","South Area Maint",338,372,409,450,495,2064]
[171,"Bleachers:  Replace softball bleachers","South Broward High",18000,"","","","",18000]
[171,"Electrical/Fire Safety Violations","South Broward High",9000,9900,10890,11979,13177,54946]
[2351,"Bleachers:  Replace baseball bleachers","South Plantation High",20000,"","","","",20000]
[2351,"Electrical/Fire Safety Violations","South Plantation High",9895,10885,11974,13171,14488,60413]
[2351,"Repair / Replace Stage Rigging","South Plantation High",90000,"","","","",90000]
[691,"Driveway  ","Stirling Elementary",200000,"","","","",200000]
[691,"Electrical/Fire Safety Violations","Stirling Elementary",4747,5222,5744,6319,6951,28983]
[691,"Upgrade Fire Alarm Horns","Stirling Elementary",90000,"","","","",90000]
[3011,"Electrical/Fire Safety Violations","Stoneman Douglas High",10964,12061,13267,14594,16053,66939]
[3011,"Flooring:  Installation of Tile","Stoneman Douglas High","",100000,"","","",100000]
[3011,"Repair / Replace Stage Rigging","Stoneman Douglas High","",90000,"","","",90000]
[3011,"Replace Fire Alarm System","Stoneman Douglas High","","","","",325000,325000]
[211,"Bleachers: Replace Football/Track Bleachers","Stranahan High","","",25000,"","",25000]
[211,"Electrical/Fire Safety Violations","Stranahan High",24736,27210,29931,32924,36216,151017]
[211,"Flooring:  Installation of Tile","Stranahan High","",75000,"","","",75000]
[211,"Provide Fire Sprinkler Protection","Stranahan High",250000,"","","","",250000]
[211,"HSS/Bleachers","Stranahan High ",36176,{"$nulls":4},36176]
[211,"HSS/Intercoms","Stranahan High ",84700,{"$nulls":4},84700]
[611,"Electrical/Fire Safety Violations","Sunland Park Elementary",11433,12577,13835,15218,16740,69803]
[251,"Electrical/Fire Safety Violations","Sunrise Middle",5549,6104,6714,7386,8125,33878]
[251,"Flooring:  Installation of Tile","Sunrise Middle","",40000,"","","",40000]
[251,"Pools:  Renovations / Remarcite / Electrical / Plumbing","Sunrise Middle","",75000,"","","",75000]
[251,"Pools:  Replace Pool Lane Lines","Sunrise Middle","",2700,"","","",2700]
[251,"Pools:  Update Computer Chemical Flow Meter","Sunrise Middle","",3000,"","","",3000]
[3661,"Electrical/Fire Safety Violations","Sunset Lakes Elementary",3000,3300,3630,3993,4392,18315]
[1171,"Electrical/Fire Safety Violations","Sunshine Elementary",4680,5148,5663,6229,6852,28572]
[2621,"Electrical/Fire Safety Violations","Tamarac Elementary",6954,7650,8415,9257,10183,42459]
[2621,"Provide Fire Sprinkler Protection","Tamarac Elementary","",230000,"","","",230000]
[2621,"Replace Fire Alarm System","Tamarac Elementary","","","",160000,"",160000]
[2621,"Driveway Safety Renovations ","Tamarac Elementary ",100000,{"$nulls":4},100000]
[2751,"Electrical/Fire Safety Violations","Taravella J P High",12100,13310,14641,16105,17716,73872]
[2751,"Fencing:  Replace Fence","Taravella J P High","",126000,"","","",126000]
[2751,"Provide Fire Sprinkler Protection","Taravella J P High","","","","",450000,450000]
[2751,"Fire Alarm Replacement ","Taravella J P High ",250000,{"$nulls":4},250000]
[9356,"Electric/Fire Safety Violations","Technology/Support Serv Site",6517,7169,7886,8674,9541,39787]
[571,"Electrical/Fire Safety Violations","Tedder Elementary",5683,6252,6877,7565,8322,34699]
[3151,"Bleachers: Replace Gym Bleachers","Tequesta Trace Middle","","",100000,"","",100000]
[3151,"Electrical/Fire Safety Violations","Tequesta Trace Middle",10095,11105,12216,13437,14781,61634]
[3151,"Fire Alarm Replacement ","Tequesta Trace Middle ",117205,{"$nulls":4},117205]
[1021,"Electrical/Fire Safety Violations","The Quest Center",7354,8090,8899,9789,10768,44900]
[9387,"Electrical/Fire Safety Violations","The Weld Shop",3000,3300,3630,3993,4392,18315]
[3481,"Electrical/Fire Safety Violations","Tradewinds Elementary",4480,4928,5421,5963,6559,27351]
[731,"Electrical/Fire Safety Violations","Tropical Elementary",9293,10223,11245,12370,13607,56738]
[731,"Parent Drive","Tropical Elementary",250000,"","","","",250000]
[731,"Provide Fire Sprinkler Protection","Tropical Elementary","","",240000,"","",240000]
[731,"HSS Parent Drive Expansion","Tropical Elementary ",50000,{"$nulls":4},50000]
[731,"Replace Carpet HSS","Tropical Elementary ",12697,{"$nulls":4},12697]
[9077,"Electrical/Fire Safety Violations","Twin Lakes Complex",9445,10390,11429,12572,13829,57665]
[9077,"HSS/Fire Alarms","Twin Lakes Complex ",45000,{"$nulls":4},45000]
[9077,"HSS/Install Fire Hydrants","Twin Lakes Complex ",230000,{"$nulls":4},230000]
[9077,"HSS/Install Fire Sprinklers","Twin Lakes Complex ",150000,{"$nulls":4},150000]
[9325,"Electrical/Fire Safety Violations","Twin Lk Annex-New Warehouse",1200,1300,1430,1573,1730,7233]
[1621,"Electrical/Fire Safety Violations","Village Elementary",6017,6619,7281,8009,8810,36736]
[1621,"Provide Fire Sprinkler Protection","Village Elementary","",230000,"","","",230000]
[321,"Electrical/Fire Safety Violations","Walker Elementary",25471,28019,30821,33903,37293,155507]
[511,"Electrical/Fire Safety Violations","Watkins Elementary",3476,3824,4206,4627,5090,21223]
[2881,"Electrical/Fire Safety Violations","Welleby Elementary",4680,5148,5663,6229,6852,28572]
[2881,"Flooring:  Installation of Tile","Welleby Elementary","",70000,"","","",70000]
[2881,"Drainage","Welleby Elementary ",70000,{"$nulls":4},70000]
[9334,"Electrical/Fire Safety Violations","West Central Bus Parking/Maint",1200,1300,1430,1573,1730,7233]
[161,"Electrical/Fire Safety Violations","West Hollywood Elementary",4747,5222,5744,6319,6951,28983]
[161,"Upgrade Fire Alarm Horns ","West Hollywood Elementary ",40000,{"$nulls":4},40000]
[2681,"Electrical/Fire Safety Violations","Westchester Elementary",7823,8606,9467,10413,11454,47763]
[2831,"Electrical/Fire Safety Violations","Western High",12502,13753,15128,16641,18305,76329]
[2831,"Provide Fire Sprinkler Protection","Western High","","","","",450000,450000]
[2831,"Repair / Replace Stage Rigging","Western High","",90000,"","","",90000]
[2831,"Replace Dimmer Board","Western High",65000,"","","","",65000]
[2831,"Replace Fire Alarm System","Western High","","","","",325000,325000]
[2831,"Stage Light Panel","Western High ",69785,{"$nulls":4},69785]
[3611,"Electrical/Fire Safety Violations","Westglades Middle (\"LL\")",6000,6600,7260,7986,8785,36631]
[2052,"Additional Drive on West Side","Westpine Middle","",100000,"","","",100000]
[2052,"Electrical/Fire Safety Violations","Westpine Middle",7621,8384,9222,10145,11160,46532]
[2052,"Flooring:  Installation of Tile","Westpine Middle","",40000,"","","",40000]
[2052,"Replace Gym Bleachers","Westpine Middle","",100000,"","","",100000]
[631,"Electrical/Fire Safety Violations","Westwood Heights Elementary",9761,10738,11812,12993,14292,59596]
[631,"Flooring:  Installation of Tile","Westwood Heights Elementary","",50000,"","","",50000]
[412,"Electrical/Fire Safety Violation","Whiddon-Rogers Annex",7421,8164,8980,9878,10866,45309]
[412,"Fire Alarm Replacement ","Whiddon-Rogers Annex ",150000,{"$nulls":4},150000]
[452,"Electrical/Fire Safety Violations","Whiddon-Rogers Ed Center",11633,12797,14077,15484,17032,71023]
[452,"Fencing:  Replace Fence","Whiddon-Rogers Ed Center","",69000,"","","",69000]
[452,"Parent Drive","Whiddon-Rogers Ed Center",150000,"","","","",150000]
[1752,"Electrical/Fire Safety Violations","Whispering Pines Ctr",4747,5222,5744,6319,6951,28983]
[1752,"Replace Fire Alarm System","Whispering Pines Ctr","","",160000,"","",160000]
[1752,"Time Out Room Replace/Renov ","Whispering Pines Ctr ",86223,{"$nulls":4},86223]
[191,"Electrical/Fire Safety Violations","Wilton Manors Elementary",14574,16032,17635,19399,21339,88979]
[991,"Electrical/Fire Safety Violations","Wingate Oaks Center",4680,5148,5663,6229,6852,28572]
[991,"Flooring:  Installation of Tile","Wingate Oaks Center",65000,"","","","",65000]
[3091,"Electrical/Fire Safety Violations","Winston Park Elementary",8557,9413,10354,11390,12529,52243]
[3091,"Flooring:  Installation of Tile","Winston Park Elementary",29000,11000,"","","",40000]
[3091,"Driveway Safety Renovations ","Winston Park Elementary ",100000,{"$nulls":4},100000]
[3321,"Electrical/Fire Safety Violations","Young, Virginia S. Elementary",4513,4965,5462,6008,6609,27557]
[3321,"Upgrade Fire Alarm Horns","Young, Virginia S. Elementary",90000,"","","","",90000]
[3001,"HSS/Fire Alarms","Young, Walter C Middle ",229410,{"$nulls":4},229410]
[3001,"Electrical/Fire Safety Violations","Young, Walter C. Middle",7688,8457,9303,10233,11256,46937]
[null,"District Maintenance",{"$nulls":6},0]
[1741,"Infra-Electric:  Replace electrical service for baseball field.","Anderson, Boyd H. High","",18250,"","","",18250]
[1741,"Mechanical:  Provide proper drainage around courtyard area","Anderson, Boyd H. High","",20000,"","","",20000]
[1741,"Provide Material and labor to Upgrade (Obsolete Hardware)","Anderson, Boyd H. High","","","",265000,"",265000]
[1741,"Replace Sanitary lines in home economics","Anderson, Boyd H. High","","","",20000,"",20000]
[1791,"Infra-Plumbing:  Replace 6\" backflow preventers on fire system.","Apollo Middle","",17665,"","","",17665]
[1791,"Infra-Plumbing:  Replace hot water lines.","Apollo Middle",100000,"","","","",100000]
[1791,"Infra-Site-Miscellaneous:  Resurface tracks/courts with asphalt","Apollo Middle","",91200,"","","",91200]
[1791,"Painting:  Exterior painting of building","Apollo Middle","",80000,"","","",80000]
[1791,"Repair four inch fee to boiler.  ","Apollo Middle","","","",5000,"",5000]
[1791,"Replace lane line, chemical flow meter and remarcite swimming pool.","Apollo Middle","","","",200000,"",200000]
[1791,"Upgrade existing security lighting throughout exterior walkways and corridors ","Apollo Middle","","","",23820,"",23820]
[2221,"Finish upgrading a/c controls from Pnuematic to Electronic.","Atlantic Technical Center","","","",80000,"",80000]
[2221,"Mechanical:  Replace lift station and wet well.","Atlantic Technical Center",18375,"","","","",18375]
[2511,"Infra-Electric:  Install new lighting/transient voltage surge protection","Atlantic West Elementary","",33000,"","","",33000]
[2511,"Infra-Plumbing:  Install somat pulper.","Atlantic West Elementary",19100,"","","","",19100]
[2511,"Infra-Plumbing:  Repipe 3\" galvanized water line.","Atlantic West Elementary","",26085,"","","",26085]
[2511,"Replace 12 air handler units","Atlantic West Elementary","","","",200000,"",200000]
[2511,"Upgrade Model# sp 50 Somat Pulper to an sp75.","Atlantic West Elementary","","","",32000,"",32000]
[343,"Infra-Plumbing:  Install backflow preventers.","Attucks Middle","",25600,"","","",25600]
[343,"Infra-Plumbing:  Replace 2\" backflow preventers ","Attucks Middle","",15400,"","","",15400]
[343,"Infra-Plumbing:  Replace boiler circulation pumps and tanks.","Attucks Middle",12800,"","","","",12800]
[343,"Infra-Site-Miscellaneous:  Renovate pe fields and automate irrigation system","Attucks Middle","",132800,"","","",132800]
[343,"Infra-Site-Miscellaneous:  Resurface track/courts with asphalt","Attucks Middle","",84800,"","","",84800]
[343,"Refinish Gym floor, include logos and gamelines","Attucks Middle","","",18000,"","",18000]
[343,"Resurface Tracks & Courts with Asphalt","Attucks Middle","","",42869,"","",42869]
[2611,"Mechanical:  Replace floor drains in kitchen to grease trap then to main sewer.","Bair Middle",30000,"","","","",30000]
[2611,"Replace Floor Drains","Bair Middle","","","",30000,"",30000]
[2611,"Resurface Tracks & Courts with Asphalt","Bair Middle","","",28200,"","",28200]
[2611,"Upgrade natural gas emergency generator - Secondary Red Cross Shelter","Bair Middle","","",37500,"","",37500]
[2001,"Replace Floor Drains","Banyan Elementary","","","",25000,"",25000]
[9855,"Infra-HVAC: Replace chillers.","BECON/ITV",60000,"","","","",60000]
[201,"Infra-Site-Miscellaneous:  Replace stage floor.","Bennett Elementary","",16000,"","","",16000]
[201,"Infra-Site-Miscellaneous:  Replace wood windows/floors in office & media wing.","Bennett Elementary","",75000,"","","",75000]
[201,"Poor Condition F/Y 4","Bennett Elementary","","","",50000,"",50000]
[201,"Provide and install transient voltage surge suppression devices ","Bennett Elementary","","","",19852,"",19852]
[201,"Replace all intercom wiring & master clock","Bennett Elementary","","",150000,"","",150000]
[201,"Replace grease and sanitary lines from kitchen.","Bennett Elementary","","","",30000,"",30000]
[201,"Storage Building","Bennett Elementary","","","",20000,"",20000]
[341,"Remove boiler from fish 606","Bethune, Mary M. Elementary","","",6897,"","",6897]
[341,"Replace 5 Roof top chw units and 1 package unit","Bethune, Mary M. Elementary","","","",120000,"",120000]
[341,"Replace two air cooled chillers","Bethune, Mary M. Elementary","","","",160000,"",160000]
[341,"Upgrade Model# sp50 Somat Pulper to an sp75.","Bethune, Mary M. Elementary","","","",32000,"",32000]
[361,"Provide Material and labor to Upgrade (Obsolete Hardware)","Blanche Ely High","","","",95000,"",95000]
[361,"Remove approx. 320 1.f. of damaged sidewalk, compact, form pour and broom finish","Blanche Ely High","","","",52000,"",52000]
[361,"Storage Building","Blanche Ely High","","","",20000,"",20000]
[361,"Upgrade Model #sp75 Somat Pulper","Blanche Ely High","","","",32000,"",32000]
[811,"Infra-HVAC:  Replace McQuay air cooled chiller..","Broadview Elementary","",100000,"","","",100000]
[811,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Broadview Elementary","",111000,"","","",111000]
[501,"Upgrade existing security lighting thorughout exterior walkways and corridors","Broward Estates Elementary","","","",50720,"",50720]
[1461,"Paint Exterior","Castle Hill Elementary","","","",50000,"",50000]
[1461,"Replace & upgrade Fire Alarm System","Castle Hill Elementary","","",160000,"","",160000]
[1421,"Automate Irrigation System","Coconut Creek Elementary","","",56511,"","",56511]
[1681,"Infra-Plumbing:  Install 4\" backflow preventers on fire system/fence in units.","Coconut Creek High","",12240,"","","",12240]
[1681,"Infra-Plumbing:  Install grease trap lids.","Coconut Creek High","",8000,"","","",8000]
[1681,"Infra-Plumbing:  Replace grease trap lids/provide new top to grease interceptor","Coconut Creek High",22850,"","","","",22850]
[1681,"Infra-Site-Miscellaneous:  Replace stage floor.","Coconut Creek High","",16000,"","","",16000]
[1681,"Upgrade existing security lighting throughout exterior walkways and corridors ","Coconut Creek High","","","",51650,"",51650]
[1681,"Upgrade natural gas generator to 125kw - secondary Red Cross shelter","Coconut Creek High","","",62500,"","",62500]
[231,"Infra-Electric:  Upgrade classroom lighting.","Colbert Elementary",480000,"","","","",480000]
[231,"Infra-Electric:  Upgrade intercom system","Colbert Elementary",50000,"","","","",50000]
[231,"Infra-Electric:  Upgrade panels and disconnects","Colbert Elementary","",16000,"","","",16000]
[231,"Infra-HVAC:  Replace cooling tower.","Colbert Elementary","",125000,"","","",125000]
[231,"Infra-Plumbing:  Install 2 catch basins.","Colbert Elementary","",35825,"","","",35825]
[231,"Infra-Plumbing:  Install 3 catch basins.","Colbert Elementary","",33000,"","","",33000]
[231,"Infra-Plumbing:  Install storm drainage.","Colbert Elementary","",57600,"","","",57600]
[231,"Infra-Plumbing:  Reinstall septic tank.","Colbert Elementary","",24000,"","","",24000]
[231,"Infra-Plumbing:  Repipe group bathrooms.","Colbert Elementary","",136000,"","","",136000]
[231,"Infra-Plumbing:  Replace domestic water lines in building #3.","Colbert Elementary","",35000,"","","",35000]
[231,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Colbert Elementary","",66000,"","","",66000]
[231,"Infra-Site-Miscellaneous:  Repair/replace exhaust fans","Colbert Elementary","",24000,"","","",24000]
[231,"Provide and install transient voltage surge suppression devices ","Colbert Elementary","","","",19852,"",19852]
[231,"Provide Material and labor to Upgrade (Obsolete Hardware)","Colbert Elementary","","","",70000,"",70000]
[231,"Roofing:  Reroof buildings.","Colbert Elementary",195000,"","","","",195000]
[331,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Collins Elementary","",120000,"","","",120000]
[331,"Provide and install transient voltage surge suppression devices ","Collins Elementary","","","",19852,"",19852]
[331,"replace & upgrade Fire Alarm System","Collins Elementary","","",160000,"","",160000]
[331,"Replace 4 chw air handlers (café)","Collins Elementary","","","",100000,"",100000]
[331,"Replace hardwood floor on stage","Collins Elementary","","",14000,"","",14000]
[1211,"Infra-Electric:  Install new emergency generator","Cooper City Elementary","",120000,"","","",120000]
[1211,"Infra-HVAC:  Replace 5 DX air handler units in the penthouse.","Cooper City Elementary","",100000,"","","",100000]
[1211,"Painting:  Exterior painting of building","Cooper City Elementary","",50000,"","","",50000]
[1211,"Upgrade existing security lighting throughout exterior walkways and corridors ","Cooper City Elementary","","","",24630,"",24630]
[1931,"Infra-Plumbing:  Install 8 catch basins around perimeter of football field.","Cooper City High","",92800,"","","",92800]
[1931,"Infra-Roofing: Reroof Buildings","Cooper City High","","","",25000,"",25000]
[1931,"Replace 19 rooftop a/c units","Cooper City High","","","",300000,"",300000]
[1931,"Replace two water cooled chillers","Cooper City High","","","",195000,"",195000]
[1931,"Replace two york Chillers","Cooper City High","","","",195000,"",195000]
[1931,"Replace Wer Well","Cooper City High","","","",30000,"",30000]
[2551,"Infra-Electric:  Replace switch gear unit","Coral Springs Elementary","",48000,"","","",48000]
[2551,"Infra-HVAC:  Replace cooling tower.","Coral Springs Elementary","",125000,"","","",125000]
[2551,"Infra-Plumbing:  Install somat pulper.","Coral Springs Elementary","",19100,"","","",19100]
[2551,"Provide Material and labor to Upgrade (Obsolete Hardware)","Coral Springs Elementary","","","",90000,"",90000]
[2551,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Coral Springs Elementary","","","",32000,"",32000]
[1151,"Infra-Electric:  Replace switch gear unit","Coral Springs High","",150000,"","","",150000]
[2561,"Infra-Electric:  Replace switch gear unit","Coral Springs Middle",52000,"","","","",52000]
[2561,"Infra-Plumbing:  Remove floor drain in somat room from grease line and reroute back to sanitary sewer.","Coral Springs Middle","",15225,"","","",15225]
[2561,"Renovate Irrigation System","Coral Springs Middle","","",29157,"","",29157]
[3111,"Infra-HVAC:  Replace cooling tower.","Country Hills Elementary","",125000,"","","",125000]
[2981,"Infra-Plumbing:  Install backflow preventers.","Country Isles Elementary","",32000,"","","",32000]
[2981,"Infra-Plumbing:  Install catch basins/storm drainage.","Country Isles Elementary","",100000,"","","",100000]
[2981,"Infra-Plumbing:  Replace 8\" backflow on fire main.","Country Isles Elementary","",19850,"","","",19850]
[2981,"Replace 16 trane cond units and air handlers","Country Isles Elementary","","","",210000,"",210000]
[221,"Replace or Realign Main Sewer","Croissant Park Elementary","","","",10000,"",10000]
[3222,"Replace one air cooled chiller ","Cross Creek School","",100000,"","","",100000]
[1871,"Infra-Plumbing:  Install 6\" backflow preventers on fire system/fence in units.","Crystal Lake Community Middle","",27285,"","","",27285]
[1871,"Infra-Plumbing:  Install drainfield to relieve catch basin.","Crystal Lake Community Middle","",27825,"","","",27825]
[1781,"Infra-Plumbing:  Install 10 catch basins in north and east parking lot.","Cypress Elementary",102645,"","","","",102645]
[1781,"Two air handler units","Cypress Elementary","","","",50000,"",50000]
[1071,"Replace two lift station pumps","Dandy, William Middle","","","",25000,"",25000]
[101,"Painting:  Exterior painting of building","Dania Elementary","",80000,"","","",80000]
[101,"Replace & upgrade Fire Alarm System","Dania Elementary","","",160000,"","",160000]
[101,"Replace 2 a/c package units for kitchen","Dania Elementary","","","",40000,"",40000]
[101,"Resurface Tracks & Courts with Asphalt","Dania Elementary","","",30000,"","",30000]
[3651,"Provide and install transient voltage surge suppression devices ","Dave Thomas Ed Ctr","","","",19852,"",19852]
[2801,"Infra-Plumbing:  Replace domestic water lines and trap primues on all floor drains.","Davie Elementary",75000,"","","","",75000]
[2801,"Infra-Site-Miscellaneous:  Repair/replace exhaust fans.","Davie Elementary","",32000,"","","",32000]
[2801,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Davie Elementary","","","",32000,"",32000]
[11,"Painting:  Exterior painting of building","Deerfield Beach Elementary",80000,"","","","",80000]
[11,"Replace Mcquay air cooled chiller","Deerfield Beach Elementary","","","",100000,"",100000]
[1711,"Infra-Plumbing:  Replace boiler circulating pumps and receiver tanks.","Deerfield Beach High","",8000,"","","",8000]
[1711,"Infra-Plumbing:  Replace galvanized domestic water pipe with copper pipe throughout facility.","Deerfield Beach High",114100,"","","","",114100]
[1711,"Infra-Plumbing:  Replace heat exchange (steam) and repipe.","Deerfield Beach High","",23760,"","","",23760]
[1711,"Infra-Site-Miscellaneous:  Replace stage floor.","Deerfield Beach High","",16000,"","","",16000]
[1711,"Painting:  Exterior painting of building","Deerfield Beach High","",150000,"","","",150000]
[1711,"Replace lane lines for swimming pool, remarcite and upgrade plumbing and electrical ","Deerfield Beach High","","","",200000,"",200000]
[1711,"Retube heat exchanger for hot water boiler.","Deerfield Beach High","","","",25000,"",25000]
[1711,"Upgrade existing security lighting throughout exterior walkways and corridors ","Deerfield Beach High","","","",51650,"",51650]
[911,"Replace air handler units in penthouse total of three.","Deerfield Beach Middle","","","",120000,"",120000]
[911,"Replace chemical flow meter.  Remarcite pool.  Upgrade plumbing and electrical.  ","Deerfield Beach Middle","","","",150000,"",150000]
[391,"Painting:  Exterior painting of building","Deerfield Park Elementary","",80000,"","","",80000]
[391,"Provide and install transient voltage surge suppression devices ","Deerfield Park Elementary","","","",19852,"",19852]
[271,"Infra-Plumbing:  Replace boiler circulating pumps and receiver tanks.","Dillard Elementary","",8000,"","","",8000]
[271,"Many crack & leaks F/Y 4","Dillard Elementary","","","",80000,"",80000]
[271,"Provide and install transient voltage surge suppression devices ","Dillard Elementary","","","",19852,"",19852]
[271,"Upgrade existing security lighting throughout exterior walkways and corridors ","Dillard Elementary","","","",39140,"",39140]
[371,"Buy a temporary lift station on a skid ","Dillard High","","","",10000,"",10000]
[371,"Infra-Site-Miscellaneous:  Replace stage floor.","Dillard High","",16000,"","","",16000]
[371,"Infra-Site-Miscellaneous:  Sand gym floor.","Dillard High","",30000,"","","",30000]
[371,"Provide and install transient voltage surge suppression devices ","Dillard High","","","",19852,"",19852]
[371,"Renovate Football Field","Dillard High","","","",100448,"",100448]
[371,"Replace grease lines & sanitary sewer from kitchen.","Dillard High","","","",50000,"",50000]
[371,"Upgrade Model #sp75 Somat Pulper","Dillard High","","","",32000,"",32000]
[0,"Air Conditioning Replacement Parts & Supplies","District Wide",261602,72600,"","","",334202]
[0,"Coil Cleaning","District Wide",1719104,1150000,1200000,1250000,1200000,6519104]
[0,"Concrete Repairs","District Wide",550672,242000,600000,"",600000,1992672]
[0,"Demolition of Portables","District Wide",849422,705000,"",750000,"",2304422]
[0,"Emergency Air Conditioning Repairs","District Wide",2341526,1000000,2200000,1000000,2200000,8741526]
[0,"Emergency Electrical Projects","District Wide",791038,402500,1900000,375000,2070000,5538538]
[0,"Emergency Generator Parts","District Wide",40264,44291,"",40264,600000,724819]
[0,"Emergency Mechanical Repairs","District Wide",996671,563000,810000,730000,810000,3909671]
[0,"Emergency Ventilation Repairs","District Wide",496836,402500,"",375000,"",1274336]
[0,"Grounds/Site Contingency","District Wide",null,"","","",1000000,1000000]
[0,"Metal Doors","District Wide",456792,423500,500000,385000,500000,2265292]
[0,"Mobile Chiller","District Wide",null,190000,"","","",190000]
[0,"Painting Contingency","District Wide",null,"","","",1000000,1000000]
[0,"Play Court & Track Improvements","District Wide",null,"",320000,"",320000,640000]
[0,"Portable Renovations","District Wide",3491749,3025000,5000000,3000000,5000000,19516749]
[0,"Roofing:  Contingency Fund","District Wide",876108,605000,900000,750000,900000,4031108]
[0,"Security/Hardware Upgrades Facility Key Systems","District Wide",null,"","","",2000000,2000000]
[0,"Site Improvements","District Wide",null,"",800000,"",800000,1600000]
[0,"Athletic Field: Irrigation","District Wide ",555153,{"$nulls":4},555153]
[0,"Athletics Fields/Courts/Asphal","District Wide ",600814,{"$nulls":4},600814]
[0,"Back Flow Prevention ","District Wide ",51756,{"$nulls":4},51756]
[0,"Chillers","District Wide ",13299,{"$nulls":4},13299]
[0,"Contingency Concrete Repairs ","District Wide ",13705,{"$nulls":4},13705]
[0,"Contingency Emergency AC Repairs","District Wide ",170270,{"$nulls":4},170270]
[0,"Contingency Emergency Electrical","District Wide ",43343,{"$nulls":4},43343]
[0,"Contingency Emergency Ventilation","District Wide ",121168,{"$nulls":4},121168]
[0,"Contingency Metal Doors ","District Wide ",11822,{"$nulls":4},11822]
[0,"Electrical ","District Wide ",249508,{"$nulls":4},249508]
[0,"Emergency A/C Repair","District Wide ",132968,{"$nulls":4},132968]
[0,"Gas Serving Lines ","District Wide ",132476,{"$nulls":4},132476]
[0,"Grounds ","District Wide ",265686,{"$nulls":4},265686]
[0,"HVAC","District Wide ",2447593,{"$nulls":4},2447593]
[0,"Infra Roofing","District Wide ",5173763,{"$nulls":4},5173763]
[0,"Infra-Electric","District Wide ",400469,{"$nulls":4},400469]
[0,"Infra-Lighting ","District Wide ",1989852,{"$nulls":4},1989852]
[0,"Infra-Plumbing","District Wide ",169364,{"$nulls":4},169364]
[0,"Infrastructure ","District Wide ",591995,{"$nulls":4},591995]
[0,"Install Plexi-Track ","District Wide ",174473,{"$nulls":4},174473]
[0,"Painting","District Wide ",493745,{"$nulls":4},493745]
[0,"Painting ","District Wide ",1139964,{"$nulls":4},1139964]
[0,"Playground-Workorders ","District Wide ",20887,{"$nulls":4},20887]
[0,"Plumbing ","District Wide ",923036,{"$nulls":4},923036]
[0,"Portable Reserve - Supt. ","District Wide ",262154,{"$nulls":4},262154]
[0,"Replace Dumpster Pad","District Wide ",32000,{"$nulls":4},32000]
[0,"Resurf Track/Court/Asph","District Wide ",206165,{"$nulls":4},206165]
[0,"Roofing ","District Wide ",1356952,{"$nulls":4},1356952]
[0,"Ventilation/Infra HVAC","District Wide ",2066972,{"$nulls":4},2066972]
[3221,"Infra-Electric:  Install weatherproof exit lights.","Drew, Charles Elementary","",15000,"","","",15000]
[721,"Painting:  Exterior painting of building","Driftwood Elementary","",80000,"","","",80000]
[721,"Replace carrier condensing unit for front office","Driftwood Elementary","","","",25000,"",25000]
[721,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Driftwood Elementary","","","",32000,"",32000]
[861,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Driftwood Middle",80000,"","","","",80000]
[861,"Infra-Site-Miscellaneous:  Replace ceiling and light fixtures.","Driftwood Middle",16500,"","","","",16500]
[861,"Infra-Site-Miscellaneous:  Replace patio.","Driftwood Middle",48600,"","","","",48600]
[861,"Infra-Site-Miscellaneous:  Replace stage floor.","Driftwood Middle",16000,"","","","",16000]
[861,"Upgrade Model #sp75 Somat Pulper","Driftwood Middle","","","",32000,"",32000]
[3461,"Flooring:  Replace delaminating floor tiles.","Eagle Point Elementary",10000,"","","","",10000]
[361,"Drainage ","Ely High ",14915,{"$nulls":4},14915]
[3191,"Infra-Electric:  Upgrade stairwell lighting.","Embassy Creek Elementary",10000,"","","","",10000]
[3191,"Infra-HVAC:  Replace 2 cooling towers.","Embassy Creek Elementary","",125000,"","","",125000]
[9830,"Painting:  Exterior painting of building","ESEA Title I","",80000,"","","",80000]
[1641,"Infra-HVAC:  Replace 2 cooling towers.","Fairway Elementary","",125000,"","","",125000]
[2541,"Infra-Plumbing:  Replace somat pulper.","Flamingo Elementary","",19100,"","","",19100]
[2541,"Replace 4 bohn chw air handlers","Flamingo Elementary","","","",100000,"",100000]
[2541,"Replace two Chilled Water pumps","Flamingo Elementary","","","",30000,"",30000]
[3391,"Infra-Plumbing:  Install catch basins and storm drainage.","Flanagan, Charles High","",20000,"","","",20000]
[3391,"Install ceramic tile in restrooms through out campus","Flanagan, Charles High","","","",130000,"",130000]
[3391,"Replace the intercom system, speakers above & under ground","Flanagan, Charles High","","",120000,"","",120000]
[3051,"Infra-HVAC:  Replace 2 cooling towers.","Forest Glen Middle","",125000,"","","",125000]
[2631,"Infra-Electric:  Replace switch gear unit","Forest Hills Elementary",54000,"","","","",54000]
[2631,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Forest Hills Elementary","","","",32000,"",32000]
[951,"Infra-Electric:  Upgrade/replace electrical panels for swimming pool area.","Fort Lauderdale High",20285,"","","","",20285]
[951,"Infra-Site-Miscellaneous:  Screen/recoat gym floor.","Fort Lauderdale High",30000,"","","","",30000]
[951,"Replace pool heater, piping, valves and fittings.","Fort Lauderdale High","","","",18000,"",18000]
[951,"Replace Pump House","Fort Lauderdale High","","",23000,"","",23000]
[951,"Replace sewer from ROTC building","Fort Lauderdale High","","","",10000,"",10000]
[921,"Refinish stage and dance studio","Foster, Stephen Elementary","","",22000,"","",22000]
[921,"Replace sewer from group restroom","Foster, Stephen Elementary","","","",6000,"",6000]
[2851,"Infra-HVAC:  Replace cooling towers.","Griffin Elementary","",125000,"","","",125000]
[2851,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Griffin Elementary","",74000,"","","",74000]
[2851,"Provide and install transient voltage surge suppression devices ","Griffin Elementary","","","",19852,"",19852]
[2851,"Replace york air cooled dhiller and four pumps","Griffin Elementary","","","",140000,"",140000]
[2851,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Griffin Elementary","","","",32000,"",32000]
[131,"Infra-Electric:  Upgrade exterior security lighting.","Hallandale Elementary",10000,"","","","",10000]
[131,"Infra-Electric:  Upgrade intercom system","Hallandale Elementary","",100000,"","","",100000]
[131,"Infra-Electric:  Upgrade panels and disconnects","Hallandale Elementary",15000,"","","","",15000]
[131,"Infra-HVAC:  Replace cooling towers.","Hallandale Elementary","",125000,"","","",125000]
[131,"Infra-Plumbing:  Replace domestic water lines.","Hallandale Elementary","",85000,"","","",85000]
[131,"Infra-Plumbing:  Replace sanitary sewer lines.","Hallandale Elementary","",50000,"","","",50000]
[131,"Painting:  Exterior painting of building","Hallandale Elementary",80000,"","","","",80000]
[131,"Roofing:  Reroof buildings.","Hallandale Elementary",110000,"","","","",110000]
[403,"Replace and upgrade Fire Alarm System","Hallandale High","","",325000,"","",325000]
[403,"Somat Pulper rusted out beyond repair","Hallandale High","","","",3500,"",3500]
[403,"Upgrade Model #sp75 Somat Pulper","Hallandale High","","","",32000,"",32000]
[491,"Infra-Electric:  Upgrade lighting in cafeteria.","Harbordale Elementary","",18670,"","","",18670]
[491,"Infra-Electric:  Upgrade security lighting.","Harbordale Elementary",34225,"","","","",34225]
[491,"Provide and install transient voltage surge suppression devices ","Harbordale Elementary","","","",19852,"",19852]
[111,"Painting:  Exterior painting of building","Hollywood Hills Elementary",50000,"","","","",50000]
[111,"Provide and install transient voltage surge suppression devices ","Hollywood Hills Elementary","","","",19852,"",19852]
[1661,"Infra-Plumbing:  Install 4\" backflow preventers on fire system/fence in units.","Hollywood Hills High","",11925,"","","",11925]
[1661,"Infra-Plumbing:  Install backflow preventers.","Hollywood Hills High","",15000,"","","",15000]
[1661,"Infra-Plumbing:  Retube boiler.","Hollywood Hills High","",16950,"","","",16950]
[1661,"Infra-Site-Miscellaneous:  Screen/recoat gym floor.","Hollywood Hills High",30000,"","","","",30000]
[1661,"Replace 2 dx package units and I unit ventilator","Hollywood Hills High","","","",75000,"",75000]
[2531,"Replace house sewer from main office area","Horizon Elementary","","","",25000,"",25000]
[2531,"Replace Vent Stacks","Horizon Elementary","","","",16000,"",16000]
[2531,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Horizon Elementary","","","",32000,"",32000]
[1971,"Replace two Mcquay air cooled chillers","Hunt, James S. Elementary","","","",200000,"",200000]
[3471,"Replace & upgrade Fire Alarm System","Indian Ridge Middle","","",195000,"","",195000]
[1611,"Install drain in kitchen parking lot","King, Martin Luther Elementary","","","",15000,"",15000]
[1611,"Replace Sewer Line","King, Martin Luther Elementary","","","",4000,"",4000]
[831,"Infra-Electric:  Upgrade exterior security lighting.","Lake Forest Elementary","",10000,"","","",10000]
[831,"Infra-Electric:  Upgrade panels and disconnects","Lake Forest Elementary",20000,"","","","",20000]
[831,"Infra-HVAC:  Replace cooling tower.","Lake Forest Elementary",105000,"","","","",105000]
[831,"Infra-Plumbing:  Install  20 space heaters","Lake Forest Elementary","",31775,"","","",31775]
[831,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Lake Forest Elementary",125000,"","","","",125000]
[405,"Infra-HVAC:  Install 25 ventilator units.","Lanier-James Education Center",150000,"","","","",150000]
[405,"Infra-Plumbing:  Replace domestic water lines.","Lanier-James Education Center",50000,"","","","",50000]
[405,"Provide and install transient voltage surge suppression devices ","Lanier-James Education Center","","","",19852,"",19852]
[621,"Infra-Plumbing:  Replace galvanized domestic water pipe with copper pipe throughout facility.","Larkdale Elementary",76550,"","","","",76550]
[621,"Infra-Plumbing:  Replace somat pulper.","Larkdale Elementary","",19100,"","","",19100]
[621,"Provide Material and labor to Upgrade (Obsolete Hardware)","Larkdale Elementary","","","",70000,"",70000]
[621,"Replace & upgrade Fire Alarm System","Larkdale Elementary","","",160000,"","",160000]
[1701,"Infra-Electric:  Upgrade all lighting in gym.","Lauderdale Lakes Middle",35000,"","","","",35000]
[1701,"Infra-Electric:  Upgrade all walkway lighting.","Lauderdale Lakes Middle",33425,"","","","",33425]
[1701,"Infra-Plumbing:  Install 8\" downspouts to parking lot and 6 catch basins in parking lot.","Lauderdale Lakes Middle","",94650,"","","",94650]
[1701,"Provide Material and labor to Upgrade (Obsolete Hardware)","Lauderdale Lakes Middle","","","",100000,"",100000]
[1701,"Provide Storm Drainage","Lauderdale Lakes Middle","","","",18000,"",18000]
[1701,"Repipe main water line inside main building.","Lauderdale Lakes Middle","","","",60000,"",60000]
[1701,"Replace Sewer Line","Lauderdale Lakes Middle","","","",6000,"",6000]
[1701,"Upgrade Ip gas emergency generator - secondary Red Cross shelter","Lauderdale Lakes Middle","","",37500,"","",37500]
[431,"Infra-Site-Miscellaneous:  Replace windows in cafeteria.","Lauderdale Manors Elementary",50000,"","","","",50000]
[1391,"Provide Material and labor to Upgrade (Obsolete Hardware)","Lauderhill Middle","","","",125000,"",125000]
[1391,"Repipe main water line inside main building.","Lauderhill Middle","","","",60000,"",60000]
[1391,"Replace sewer grease trap, grease and sanitary lines rear of kitchen","Lauderhill Middle","","","",35000,"",35000]
[1391,"Upgrade existing security lighting throughout exterior walkways and corridors ","Lauderhill Middle","","","",23820,"",23820]
[1381,"Mechanical:  Provide storm drainage for perimeter of building.","Lauderhill, P. T. Elementary","",25000,"","","",25000]
[1381,"Provide storm drainage for perimeter of building","Lauderhill, P. T. Elementary","","","",25000,"",25000]
[1091,"Infra-Plumbing:  Install 4 additional manhole covers on grease traps.","Lloyd Estates Elementary","",13675,"","","",13675]
[1091,"Infra-Plumbing:  Install area drains in patio next to cafeteria.","Lloyd Estates Elementary","",29760,"","","",29760]
[1091,"Provide Material and labor to Upgrade (Obsolete Hardware)","Lloyd Estates Elementary","","","",70000,"",70000]
[1091,"Replace MCquay air cooled chiller","Lloyd Estates Elementary","","","",100000,"",100000]
[9604,"Repipe water main from meter, 2-2\" back flows.","Maintenance","","",42828,"","",42828]
[9604,"Replace 5 split a/c systems.","Maintenance","","","",80000,"",80000]
[9604,"Replace main sewer line from front office to city sewer.","Maintenance","","","",20000,"",20000]
[9604,"Storage Building","Maintenance","","","",20000,"",20000]
[2741,"Infra-Electric:  Replace switch gear unit","Maplewood Elementary","",54000,"","","",54000]
[2741,"Infra-HVAC:  Replace cooling towers.","Maplewood Elementary",125000,"","","","",125000]
[2741,"Infra-Plumbing:  Install new somat pulper.","Maplewood Elementary","",19100,"","","",19100]
[2741,"Replace MCquay air cooled chiller","Maplewood Elementary","","","",100000,"",100000]
[2741,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Maplewood Elementary","","","",32000,"",32000]
[1161,"Infra-Plumbing:  Install 12 area drains/pipe/ 2 catch basins.","Margate Elementary","",63175,"","","",63175]
[1161,"Infra-Plumbing:  Install 2 catch basins near basketball court.","Margate Elementary","",27100,"","","",27100]
[1161,"Resurface Tracks & Courts with Asphalt","Margate Elementary","","",18020,"","",18020]
[581,"Replace stage floor","Margate Middle","","",16000,"","",16000]
[581,"Replace two Chilled Water pumps","Margate Middle","","","",20000,"",20000]
[581,"Reroofing project","Margate Middle","","","",170000,"",170000]
[1671,"Replace cafeteria air handler","Markham, Robert Elementary","","","",20000,"",20000]
[1671,"Replace two Chilled Water pumps","Markham, Robert Elementary","","","",20000,"",20000]
[1671,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Markham, Robert Elementary","","","",32000,"",32000]
[3291,"Paint Exterior","Marshall, Thurgood Elementary","","","",120000,"",120000]
[3291,"Painting:  Exterior of building.","Marshall, Thurgood Elementary",120000,"","","","",120000]
[1291,"Infra-Electric:  Upgrade lighting in shop classes","McFatter Technical Center",100000,"","","","",100000]
[1291,"Infra-HVAC:  Install variable frequency drives on 16 air handlers units","McFatter Technical Center","",80000,"","","",80000]
[1291,"Infra-HVAC:  Replace chillers.","McFatter Technical Center","",195000,"","","",195000]
[1291,"Infra-Plumbing:  Replace dust collector.","McFatter Technical Center","",20000,"","","",20000]
[841,"Infra-Site-Miscellaneous:  Replace stage floor.","McNab Elementary","",16000,"","","",16000]
[841,"Provide and install transient voltage surge suppression devices ","McNab Elementary","","","",19852,"",19852]
[841,"Replace hardwood floors on stage and dance studio","McNab Elementary","","",26000,"","",26000]
[841,"Replace Trane air cooled chiller","McNab Elementary","","","",100000,"",100000]
[761,"Mechanical:  Replace/relocate grease trap to rear of kitchen.","Meadowbrook Elementary","",15000,"","","",15000]
[761,"Paint Exterior","Meadowbrook Elementary","","","",50000,"",50000]
[761,"Painting:  Exterior of building.","Meadowbrook Elementary",50000,"","","","",50000]
[761,"Replace and Relocate Grease Trap to Rear of Kitchen","Meadowbrook Elementary","","","",15000,"",15000]
[531,"Infra-Site-Miscellaneous:  Replace locking mechanism on all exterior doors.","Miramar Elementary",10000,"","","","",10000]
[1751,"Infra-Electric:  Upgrade emergency generator.","Miramar High",65000,"","","","",65000]
[1751,"Infra-Electric:  Upgrade panels and disconnects","Miramar High",20000,"","","","",20000]
[1751,"Infra-HVAC:  Replace 2 cooling towers.","Miramar High","",175000,"","","",175000]
[1751,"Infra-Plumbing:  Install catch basins/storm drainage.","Miramar High",60000,"","","","",60000]
[1751,"Infra-Plumbing:  Install drainage system in teachers parking lot/install 6 catch basins.","Miramar High",58900,"","","","",58900]
[1751,"Provide Material and labor to Upgrade (Obsolete Hardware)","Miramar High","","","",265000,"",265000]
[1751,"Upgrade existing security lighting throughout exterior walkways and corridors ","Miramar High","","","",51650,"",51650]
[1841,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Mirror Lake Elementary","",140000,"","","",140000]
[1841,"Replace floor drains and grease trap","Mirror Lake Elementary","","","",25000,"",25000]
[2691,"Infra-Electric:  Replace switch gear unit","Morrow Elementary","",48000,"","","",48000]
[2691,"Infra-HVAC:  Replace cooling towers.","Morrow Elementary",125000,"","","","",125000]
[2691,"Resurface Tracks & Courts with Asphalt","Morrow Elementary","","",16976,"","",16976]
[2691,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Morrow Elementary","","","",32000,"",32000]
[881,"Provide Drainage for Upstairs Entrance","New River Middle","","","",5000,"",5000]
[2671,"Infra-Electric:  Upgrade lighting in cafeteria.","Nob Hill Elementary","",21185,"","","",21185]
[2671,"Provide storm drainage on East side of school","Nob Hill Elementary","","","",50000,"",50000]
[2671,"Replace Vent Stacks Throughout School","Nob Hill Elementary","","","",15000,"",15000]
[2671,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Nob Hill Elementary","","","",32000,"",32000]
[561,"Infra-Electric:  Install new circuit breakers","Norcrest Elementary",35362,"","","","",35362]
[561,"Infra-HVAC:  Replace 2 air handlers in cafeteria.","Norcrest Elementary",90000,"","","","",90000]
[561,"Infra-HVAC:  Replace cooling towers.","Norcrest Elementary","",70000,"","","",70000]
[561,"Infra-Plumbing:  Replace galvanized domestic water pipe with copper pipe throughout facility.","Norcrest Elementary",69750,"","","","",69750]
[561,"Provide and install transient voltage surge suppression devices ","Norcrest Elementary","","","",19852,"",19852]
[561,"Upgrade a/c controls","Norcrest Elementary","","","",30000,"",30000]
[521,"Infra-Electric:  Replace switch gear unit","North Andrews Gardens Elementary",70000,"","","","",70000]
[521,"Infra-HVAC:  Replace 14 fan coiled units and 1 package unit for stage.","North Andrews Gardens Elementary","",60000,"","","",60000]
[521,"Infra-HVAC:  Replace 3 chillers.","North Andrews Gardens Elementary","",175000,"","","",175000]
[521,"Provide and install transient voltage surge suppression devices ","North Andrews Gardens Elementary","","","",19852,"",19852]
[521,"Replace Roof top package unit for cateteria","North Andrews Gardens Elementary","","","",40000,"",40000]
[521,"Replace two rooftop package units for hallways","North Andrews Gardens Elementary","","","",45000,"",45000]
[521,"Resurface Tracks & Courts with Asphalt","North Andrews Gardens Elementary","","",16850,"","",16850]
[1191,"Site Improvements","North Fork Elem ",55448,{"$nulls":4},55448]
[1191,"Infra-Electric:  Upgrade all restroom lighting.","North Fork Elementary",13285,"","","","",13285]
[1191,"Infra-HVAC:  Replace 2 air handlers and 2 condensing units for cafeteria.","North Fork Elementary",40000,"","","","",40000]
[1191,"Infra-Plumbing:  Install 7 catch basins and new piping.","North Fork Elementary","",31022,"","","",31022]
[1191,"Mechanical:  Replace floor drains and grease trap.","North Fork Elementary","",20000,"","","",20000]
[1191,"Replace floor drains and grease trap","North Fork Elementary","","","",20000,"",20000]
[2231,"Automate Irrigation System","North Lauderdale Elementary","","",27686,"","",27686]
[2231,"Infra-HVAC:  Replace air cooled chiller.","North Lauderdale Elementary","",105000,"","","",105000]
[41,"Replace Sewer Line","North Side Elementary","","","",6500,"",6500]
[1241,"Estimate to change out underground galv water piping feeding all buildings on site","Northeast High","","",148547,"","",148547]
[1241,"Estimate to have new natural gas line main extension and service lines","Northeast High","","",11103,"","",11103]
[1241,"Infra-Site-Miscellaneous:  Replace stage floor.","Northeast High","",16000,"","","",16000]
[1282,"Painting:  Exterior painting of building","Nova Blanche Forman Elementary",50000,"","","","",50000]
[1271,"Painting:  Exterior painting of building","Nova Eisenhower Elementary",50000,"","","","",50000]
[1281,"Replace 1 air handler in adminarea and 16 chw units in tech bldg.","Nova High","","","",200000,"",200000]
[1281,"Central Mech Plant ","Nova High ",109616,{"$nulls":4},109616]
[1311,"Replace 3 chw air handlers","Nova Middle","","","",150000,"",150000]
[461,"Provide and install transient voltage surge suppression devices ","Oakridge Elementary","","","",19852,"",19852]
[461,"Storage Building","Oakridge Elementary","","","",20000,"",20000]
[471,"Provide and install transient voltage surge suppression devices ","Olsen Middle","","","",19852,"",19852]
[472,"Infra-Plumbing:  Repipe heating system and insulate.","Olsen Middle Annex","",92000,"","","",92000]
[711,"Infra-Electric:  Upgrade classroom lighting.","Orange Brook Elementary",25000,"","","","",25000]
[711,"Infra-Electric:  Upgrade intercom system","Orange Brook Elementary","",50000,"","","",50000]
[711,"Infra-Electric:  Upgrade panels and disconnects","Orange Brook Elementary",150000,"","","","",150000]
[711,"Infra-Plumbing:  Replace domestic water lines.","Orange Brook Elementary",50000,"","","","",50000]
[711,"Infra-Plumbing:  Replace sanitary sewer lines.","Orange Brook Elementary","",40000,"","","",40000]
[711,"Painting:  Exterior painting of building","Orange Brook Elementary","",50000,"","","",50000]
[711,"Roofing:  Reroof buildings.","Orange Brook Elementary",160000,"","","","",160000]
[1831,"Infra-Electric:  Upgrade lighting in cafeteria.","Oriole Elementary",20855,"","","","",20855]
[1831,"Infra-Electric:  Upgrade security /walkway lighting.","Oriole Elementary",18225,"","","","",18225]
[1831,"Infra-HVAC:  Replace rooftop air cooled condensing unit for administration area.","Oriole Elementary",12500,"","","","",12500]
[1831,"Infra-HVAC:  Replace rooftop air cooled condensing unit for administration area.","Oriole Elementary",12500,"","","","",12500]
[1831,"Replace main sewer from grease trap to city manhole.","Oriole Elementary","","","",40000,"",40000]
[1831,"Upgrade existing security lighting throughout exterior walkways and corridors ","Oriole Elementary","","","",24630,"",24630]
[3311,"Infra-Electric:  Upgrade stairwell lighting.","Palm Cove Elementary","",15000,"","","",15000]
[3311,"Upgrade existing security lighting throughout exterior walkways and corridors ","Palm Cove Elementary","","","",39140,"",39140]
[1131,"Replace two Dunham Bush air cooled chillers","Palmview Elementary","","","",150000,"",150000]
[1951,"Replace three Roof top package units","Park Ridge Elementary","","","",175000,"",175000]
[701,"Repaint exterior - FY3 or ASAP","Parkway Middle","","","",80000,"",80000]
[701,"Replace grease trap and lines","Parkway Middle","","","",32000,"",32000]
[2071,"Infra-HVAC:  Replace 2 condensing units.","Pasadena Lakes Elementary",8000,"","","","",8000]
[2071,"Infra-Plumbing:  Install 9 drains around portables.","Pasadena Lakes Elementary","",23825,"","","",23825]
[2071,"Replace & upgrade Fire Alarm System","Pasadena Lakes Elementary","","",160000,"","",160000]
[2071,"Perimeter Fence ","Pasadena Lakes Elementary ",33819,{"$nulls":4},33819]
[2661,"Replace & upgrade Fire Alarm System","Pembroke Lakes Elementary","","",160000,"","",160000]
[2661,"Replace 2 air cooled chillers","Pembroke Lakes Elementary","","","",120000,"",120000]
[1221,"Replace 7 air handler units ","Pembroke Pines Elementary","","","",160000,"",160000]
[1631,"Storage Building","Perry, Annabel Elementary","","","",20000,"",20000]
[1011,"Resurface Tracks & Courts with Asphalt","Perry, Henry D. Middle","","",36918,"","",36918]
[931,"Install Insulation","Peters Elementary","","","",35000,"",35000]
[931,"Replace Pump House","Peters Elementary","","",19013,"","",19013]
[931,"Drainage ","Peters Elementary ",48000,{"$nulls":4},48000]
[653,"HVAC Heater","Pine Ridge Alternative ",46854,{"$nulls":4},46854]
[653,"New roof 100% of school","Pine Ridge Alternative Center","","","",195000,"",195000]
[653,"Replace old gas heaters with 14 new LP gas heaters","Pine Ridge Alternative Center","","","",20000,"",20000]
[1881,"Replace underground wiring to portables","Pines Middle","","",50000,"","",50000]
[1881,"Gym Hvac/Vinyl Tile ","Pines Middle ",15795,{"$nulls":4},15795]
[2811,"Infra-HVAC:  Replace 7 air handlers in old building.","Pinewood Elementary","",170000,"","","",170000]
[2811,"Infra-HVAC:  Replace cooling towers.","Pinewood Elementary",125000,"","","","",125000]
[2811,"Replace package unit Café Mgr office","Pinewood Elementary","","","",10000,"",10000]
[2811,"Replace three air handler units (north wing)","Pinewood Elementary","","","",120000,"",120000]
[2811,"Upgrade Model #sp75 Somat Pulper","Pinewood Elementary","","","",32000,"",32000]
[2571,"Infra-Site-Miscellaneous:  Concrete repairs.","Pioneer Middle",25000,"","","","",25000]
[2571,"Provide Material and labor to Upgrade (Obsolete Hardware)","Pioneer Middle","","","",95000,"",95000]
[2571,"Upgrade Model #sp75 Somat Pulper","Pioneer Middle","","","",32000,"",32000]
[1901,"Infra-Plumbing:  Install 9\" catch basins in football field.","Piper High","",93650,"","","",93650]
[1901,"Replace two lift station pumps","Piper High","","","",25000,"",25000]
[1451,"Infra-Site-Miscellaneous:  Design/install an automated irrigation system for the PE field","Plantation High",143000,"","","","",143000]
[1451,"Infra-Site-Miscellaneous:  Replace all windows in the mini-gym.","Plantation High",30000,"","","","",30000]
[1451,"Painting:  Exterior of building.","Plantation High",200000,"","","","",200000]
[1451,"Refinish gym floor, including logos and gamelines","Plantation High","","",18000,"","",18000]
[1451,"Repaint Exterior","Plantation High","","","",200000,"",200000]
[1451,"Replace six handhole gaskets on boiler","Plantation High","","","",5000,"",5000]
[1451,"Resurface Tracks & Courts with Asphalt","Plantation High","","",22500,"","",22500]
[1251,"Replace grease trap and lines","Plantation Park Elementary","","","",30000,"",30000]
[9018,"Infra-Electric:  Upgrade intercom system","Pompano Admin Site",80000,"","","","",80000]
[9018,"Infra-Plumbing:  Repipe heating system on roof.","Pompano Admin Site",150850,"","","","",150850]
[9018,"Reconnect Heating Lines, re-pipe and sod","Pompano Admin Site","","",165832,"","",165832]
[751,"Replace cooling towers","Pompano Beach Elementary","","","",90000,"",90000]
[185,"Reroof, Two Roof System, Insulate Existing Deck","Pompano Beach High School Institute of International Studies","","","",185000,"",185000]
[21,"Infra-HVAC:  Replace Trane trace controls.","Pompano Beach Middle",65000,"","","","",65000]
[21,"Infra-Plumbing:  Install 3 additional grease trap lids.","Pompano Beach Middle","",11900,"","","",11900]
[21,"Refinish original hardwood floor on stage","Pompano Beach Middle","","",7300,"","",7300]
[21,"Replace Condensing unit and air handler for gym","Pompano Beach Middle","","","",120000,"",120000]
[3121,"Infra-Plumbing:  Take somat line off of grease trap.","Quiet Waters Elementary",11300,"","","","",11300]
[2721,"Infra-HVAC:  Replace cooling towers.","Ramblewood Elementary",125000,"","","","",125000]
[2721,"Infra-HVAC:  Replace York air cooled chiller.","Ramblewood Elementary",105000,"","","","",105000]
[2721,"Infra-Plumbing:  Install new somat pulper.","Ramblewood Elementary","",19100,"","","",19100]
[2721,"Replace cooling tower ","Ramblewood Elementary","","","",90000,"",90000]
[2721,"Upgrade Model #sp50  Somat Pulper-to an sp 75.","Ramblewood Elementary","","","",32000,"",32000]
[2711,"Infra-Plumbing:  Install new somat pulper.","Ramblewood Middle","",25100,"","","",25100]
[2711,"Replace two rooftop package units for cafeteria","Ramblewood Middle","","","",60000,"",60000]
[2121,"Infra-HVAC:  Replace cooling towers.","Rickards Middle","",150000,"","","",150000]
[2121,"Painting:  Exterior painting of building","Rickards Middle",150000,"","","","",150000]
[2891,"Infra-HVAC:  Replace 2 cooling towers.","Riverglades Elementary",150000,"","","","",150000]
[151,"Infra-HVAC:  Replace all rusted fresh air intake grills.","Riverland Elementary",5000,"","","","",5000]
[151,"Infra-HVAC:  Replace fresh air intake grills.","Riverland Elementary",5000,"","","","",5000]
[151,"Upgrade existing security lighting throughout exterior walkways and corridors ","Riverland Elementary","","","",39140,"",39140]
[151,"Exterior Stucco ","Riverland Elementary ",26165,{"$nulls":4},26165]
[3031,"Infra-Plumbing:  Lower existing area drains in office and library area.","Riverside Elementary","",35860,"","","",35860]
[681,"Infra-Electric:  Install new conduit/wiring for intercom to portable site.","Rock Island Elementary",6225,"","","","",6225]
[681,"Mechanical:  Provide storm drainage around facility/portable area north west of school.","Rock Island Elementary",100000,"","","","",100000]
[681,"Provide Storm Drainage","Rock Island Elementary","","","",100000,"",100000]
[681,"Replace grease trap, grease and sanitary lines","Rock Island Elementary","","","",30000,"",30000]
[681,"Resurface Tracks & Courts with Asphalt","Rock Island Elementary","","",33700,"","",33700]
[1851,"Repaint Exterior","Royal Palm Elementary","","","",50000,"",50000]
[1851,"Replace main sewer between manholes on N. E. and S sides of school","Royal Palm Elementary","","","",35000,"",35000]
[1851,"Replace stage and dance studio floors","Royal Palm Elementary","","",26000,"","",26000]
[891,"Infra-HVAC:  Replace air cooled chiller.","Sanders Park Elementary","",120000,"","","",120000]
[3401,"Infra-HVAC:  Replace 2 cooling towers.","Sawgrass Elementary","",125000,"","","",125000]
[3401,"Need new drainiage on West side of school","Sawgrass Elementary","","","",12000,"",12000]
[3401,"Poor Condition F/Y 4","Sawgrass Elementary","","","",130000,"",130000]
[601,"Mechanical:  replace sanitary sewer from office area to main line.","Seagull School","",8000,"","","",8000]
[601,"Provide and install transient voltage surge suppression devices ","Seagull School","","","",19852,"",19852]
[601,"Replace sanitary sewer from office area to main line","Seagull School","","","",8000,"",8000]
[1891,"Upgrade Model #sp75 Somat Pulper","Seminole Middle","","","",32000,"",32000]
[1811,"Infra-Electric:  Install hallway speakers","Sheridan Hills Elementary","",10000,"","","",10000]
[1811,"Infra-Site-Miscellaneous:  Automate irrigation system.","Sheridan Hills Elementary","",20000,"","","",20000]
[1811,"Upgrade existing security lighting throughout exterior walkways and corridors ","Sheridan Hills Elementary","","","",24630,"",24630]
[1321,"Infra-Electric:  Install new emergency generator","Sheridan Park Elementary",120000,"","","","",120000]
[1321,"Infra-Plumbing:  Install lift station.","Sheridan Park Elementary",10000,"","","","",10000]
[1321,"Infra-Plumbing:  Replace lift station pumps.","Sheridan Park Elementary","",10000,"","","",10000]
[1321,"Infra-Plumbing:  Upgrade domestic lines.","Sheridan Park Elementary",65000,"","","","",65000]
[1321,"Infra-Plumbing:  Upgrade sanitary lines.","Sheridan Park Elementary","",45000,"","","",45000]
[2971,"Replace two cooling towers","Silver Lakes Middle","","","",175000,"",175000]
[3081,"Replace 16 Trane dx units and air handlers","Silver Ridge Elementary","","","",200000,"",200000]
[171,"Infra-Site-Miscellaneous:  Renovate restrooms","South Broward High",100000,"","","","",100000]
[171,"Infra-Site-Miscellaneous:  Replace wood floors, ceramic tiles, ceilings and painting throughout facilities.","South Broward High",200000,"","","","",200000]
[171,"Infra-Site-Miscellaneous:  Screen/recoat gym floor.","South Broward High",20000,"","","","",20000]
[171,"Provide and install transient voltage surge suppression devices ","South Broward High","","","",19852,"",19852]
[2351,"Infra-HVAC:  Replace cooling towers.","South Plantation High",175000,"","","","",175000]
[2351,"Infra-Plumbing:  Retube boiler.","South Plantation High","",17500,"","","",17500]
[2351,"Infra-Site-Miscellaneous:  Replace stage floor.","South Plantation High",16000,"","","","",16000]
[2351,"Upgrade diesel generator to 125 kw - secondary Red Cross Shelter","South Plantation High","","",62500,"","",62500]
[2351,"Roofing ","South Plantation High ",400000,{"$nulls":4},400000]
[691,"Infra-Site-Miscellaneous:  Grade/remove existing soil on PE field/add topsoil/install sod","Stirling Elementary",24000,"","","","",24000]
[691,"Upgrade existing security lighting throughout exterior walkways and corridors ","Stirling Elementary","","","",39140,"",39140]
[3011,"Infra-HVAC:  Replace 2 cooling towers.","Stoneman Douglas High","",175000,"","","",175000]
[3011,"Replace lp gas heater for p.e. area 400,000 btu.","Stoneman Douglas High","","","",10000,"",10000]
[3011,"Archway Demolition/Ext Stucco ","Stoneman Douglas High ",83484,{"$nulls":4},83484]
[3011,"Renovate Outfields","Stoneman Douglas High ",12284,{"$nulls":4},12284]
[211,"Infra-Electric:  Upgrade lighting in auditorium.","Stranahan High",38285,"","","","",38285]
[211,"Infra-HVAC:  Replace variable speed drives on air handlers.","Stranahan High",40000,"","","","",40000]
[211,"Infra-Plumbing:  Replace 2 fire hydrants.","Stranahan High","",78425,"","","",78425]
[211,"Infra-Plumbing:  Replace pool heater.","Stranahan High",18925,"","","","",18925]
[211,"Infra-Plumbing:  Retube boiler and replace hand hole covers.","Stranahan High",17945,"","","","",17945]
[211,"Infra-Plumbing:  Tie lift station into city sewer/run new pipe/install grease traps","Stranahan High","",17775,"","","",17775]
[211,"Replace all underground water pipe from backflow to all buildings","Stranahan High","","","",65000,"",65000]
[211,"Retube heating boiler. Replace fittings as needed.","Stranahan High","","","",25000,"",25000]
[611,"Infra-HVAC:  Replace 2 cooling towers.","Sunland Park Elementary","",125000,"","","",125000]
[251,"Infra-HVAC:  Replace cooling towers.","Sunrise Middle","",150000,"","","",150000]
[251,"Provide and install transient voltage surge suppression devices ","Sunrise Middle","","","",19852,"",19852]
[251,"Provide and install transient voltage surge suppression devices ","Sunrise Middle","","","",19852,"",19852]
[251,"Replace pool heater, piping, valves and fittings.","Sunrise Middle","","","",18000,"",18000]
[251,"Replace two lift station pumps, piping, fittings and check valves.","Sunrise Middle","","","",25000,"",25000]
[1171,"Infra-Electric:  Upgrade intercom system","Sunshine Elementary","",60000,"","","",60000]
[1171,"Infra-Site-Miscellaneous:  Modify mansard metal panels","Sunshine Elementary","",20000,"","","",20000]
[1171,"Infra-Site-Miscellaneous:  Repair/replace sidewalks","Sunshine Elementary",20000,"","","","",20000]
[1171,"Replace hardwood floor on stage","Sunshine Elementary","","",14000,"","",14000]
[2621,"Upgrade Model# sp50 Somat Pulper to an sp75.","Tamarac Elementary","","","",32000,"",32000]
[2751,"Infra-HVAC:  Replace 2 air coiled chillers.","Taravella J P High",80000,"","","","",80000]
[2751,"Infra-Plumbing:  Install 4\" backflow preventers on fire system","Taravella J P High","",17550,"","","",17550]
[2751,"Infra-Plumbing:  Install 6 catch basins between portables.","Taravella J P High","",22100,"","","",22100]
[2751,"Infra-Site-Miscellaneous:  Screen/recoat gym floor.","Taravella J P High",30000,"","","","",30000]
[2751,"Refinish gym floor","Taravella J P High","","",19000,"","",19000]
[2751,"Upgrade Model#sp75 Somat Pulper","Taravella J P High","","","",32000,"",32000]
[2751,"Athletic Storage Bldg","Taravella J P High ",40000,{"$nulls":4},40000]
[571,"Infra-HVAC:  Replace air cooled chiller.","Tedder Elementary","",120000,"","","",120000]
[571,"Infra-Plumbing:  Install 3 additional manhole covers on grease traps.","Tedder Elementary","",12175,"","","",12175]
[571,"Painting:  Exterior painting of building","Tedder Elementary",80000,"","","","",80000]
[571,"Provide and install transient voltage surge suppression devices ","Tedder Elementary","","","",19852,"",19852]
[571,"Replace air cooled chiller.","Tedder Elementary","","","",125000,"",125000]
[3151,"Infra-HVAC:  Replace 2 cooling towers.","Tequesta Trace Middle","",125000,"","","",125000]
[1021,"Replace two heat exchangers","The Quest Center","","","",25000,"",25000]
[731,"Infra-HVAC:  Replace 3 direct expansion air handlers in penthouse.","Tropical Elementary",98000,"","","","",98000]
[9077,"Estimate to install Simplex Storm Water Pump Station; increase discharge lines to 4\".","Twin Lakes Complex","","",17964,"","",17964]
[1621,"Improve Storm Drainage","Village Elementary","","","",5000,"",5000]
[1621,"Infra-Plumbing:  Replace main sewer from rear of school west to city sewer in front of school.","Village Elementary","",30000,"","","",30000]
[1621,"Paint Exterior","Village Elementary","","","",50000,"",50000]
[1621,"Painting:  Exterior painting of building","Village Elementary",80000,"","","","",80000]
[1621,"Replace main sewer line from rear of school to city main.","Village Elementary","","","",25000,"",25000]
[1621,"Storage Building","Village Elementary","","","",20000,"",20000]
[321,"Infra-Electric:  Upgrade security lighting.","Walker Elementary",22000,"","","","",22000]
[321,"Provide and install transient voltage surge suppression devices","Walker Elementary","","","",19852,"",19852]
[321,"Repaint Exterior","Walker Elementary","","","",50000,"",50000]
[321,"Repair and refinish floor","Walker Elementary","","",50000,"","",50000]
[321,"Replace main sewer from manhole by chiller to city sewer.","Walker Elementary","","","",30000,"",30000]
[511,"Infra-HVAC:  Install a/c standby pumps","Watkins Elementary",10000,"","","","",10000]
[2881,"Imrpove storm drainage on East side of school","Welleby Elementary","","","",20000,"",20000]
[2881,"Infra-HVAC:  Replace 2 cooling towers.","Welleby Elementary","",125000,"","","",125000]
[2881,"Infra-Plumbing:  Install catch basin lids.","Welleby Elementary","",14700,"","","",14700]
[2881,"Mechanical:  Improve storm drainage on east side of school.","Welleby Elementary",20000,"","","","",20000]
[161,"Infra-Plumbing:  Install lift station.","West Hollywood Elementary","",10000,"","","",10000]
[2681,"Infra-HVAC:  Replace cooling towers.","Westchester Elementary",125000,"","","","",125000]
[2681,"Infra-Plumbing:  Install new somat pulper.","Westchester Elementary","",19075,"","","",19075]
[2681,"Replace hardwood floors on stage and dance studio","Westchester Elementary","","",26000,"","",26000]
[2831,"Infra-Plumbing:  Install drainage system.","Western High",83000,"","","","",83000]
[2831,"Upgrade Model#sp75 Somat Pulper","Western High","","","",32000,"",32000]
[2831,"Replace Tile And Stucco","Western High ",95000,{"$nulls":4},95000]
[2052,"Infra-Plumbing:  Replace 6\" backflow preventers.","Westpine Middle",15500,"","","","",15500]
[631,"Provide and install transient voltage surge suppression devices","Westwood Heights Elementary","","","",19852,"",19852]
[631,"Replace Pump House","Westwood Heights Elementary","","",28001,"","",28001]
[412,"Infra-Electric:  Upgrade lighting in media center and in administration buildings.","Whiddon-Rogers Annex",20675,"","","","",20675]
[412,"Infra-Site-Miscellaneous:  Install new ceiling (including lighting) in main building.","Whiddon-Rogers Annex",50000,"","","","",50000]
[1752,"Upgrade existing security lighting throughout exterior walkways and corridors","Whispering Pines Ctr","","","",41650,"",41650]
[1752,"Repairs, HVAC, Roof & Walls","Whispering Pines Ctr ",216063,{"$nulls":4},216063]
[991,"Change to F/Y 3 Due to poor condition","Wingate Oaks Center","","","",50000,"",50000]
[991,"Infra-Site-Miscellaneous:  Replace ceiling in main building.","Wingate Oaks Center",50000,"","","","",50000]
[991,"Replace grease and sanitary lines from kitchen.","Wingate Oaks Center","","","",35000,"",35000]
[3091,"Infra-HVAC:  Replace cooling towers.","Winston Park Elementary","",125000,"","","",125000]
[3091,"Infra-Plumbing:  Repipe storm drainage on west side of school.","Winston Park Elementary",120000,"","","","",120000]
[3001,"Infra-Electric:  Provide additional emergency power","Young, Walter C. Middle",50000,"","","","",50000]
[3001,"Infra-Electric:  Upgrade intercom system","Young, Walter C. Middle",75000,"","","","",75000]
[3001,"Infra-HVAC:  Replace 9 air handler units.","Young, Walter C. Middle",18000,"","","","",18000]
[3001,"Replace 52 unit ventilators","Young, Walter C. Middle","","","",225000,"",225000]
[3001,"Replace two cooling towers","Young, Walter C. Middle","","","",160000,"",160000]
[null,"Americans with Disabilities",{"$nulls":6},0]
[1741,"ADA Restrooms","Anderson, Boyd H High ",85605,{"$nulls":4},85605]
[1741,"Curb Ramps","Anderson, Boyd H. High","",648,"","","",648]
[1741,"Handrails at Existing Ramps","Anderson, Boyd H. High","",1350,"","","",1350]
[1741,"Showers","Anderson, Boyd H. High",450,"","","","",450]
[1741,"Visual Alarms location at Corridors","Anderson, Boyd H. High","",1200,"","","",1200]
[1741,"Wheelchair Area at Bleachers","Anderson, Boyd H. High","",15000,"","","",15000]
[1791,"ADA Science Lab Stations","Apollo Middle","","","",15000,"",15000]
[1791,"Curb Ramps","Apollo Middle","",648,"","","",648]
[1791,"Home Economics Kitchen Station ADA Retrofitting","Apollo Middle","","","","",32000,32000]
[1791,"Non-Accessible Pool (Lift)","Apollo Middle","","",8000,"","",8000]
[1791,"Non-accessible restrooms at ESE Cluster Program (Building #2 )","Apollo Middle","","","",60000,"",60000]
[1791,"Showers","Apollo Middle",5700,"","","","",5700]
[1791,"Relocate Telephone Receptionst","Apollo Middle ",1614,{"$nulls":4},1614]
[2221,"Curb Ramps","Atlantic Technical Center","",648,"","","",648]
[2221,"Showers","Atlantic Technical Center","",600,"","","",600]
[2221,"Visual Alarms at Restrooms","Atlantic Technical Center",6000,"","","","",6000]
[2221,"ADA Restrooms","Atlantic Vocational Center ",4887,{"$nulls":4},4887]
[2511,"Curb Ramps","Atlantic West Elementary","",648,"","","",648]
[2511,"Non-verbal Communication System at Elevators","Atlantic West Elementary","",560,"","","",560]
[2511,"Restrooms","Atlantic West Elementary",179315,"","","","",179315]
[2511,"Visual Alarms at Restrooms","Atlantic West Elementary",4500,"","","","",4500]
[2511,"Visual Alarms location at Corridors","Atlantic West Elementary","",400,"","","",400]
[343,"Curb Ramps","Attucks Middle",3048,"","","","",3048]
[343,"Home Economics Kitchen Station ADA Retrofitting","Attucks Middle","","","","",32000,32000]
[343,"Visual Alarms at Restrooms","Attucks Middle",1000,"","","","",1000]
[343,"ADA Restrooms","Attucks Middle ",14850,{"$nulls":4},14850]
[2611,"ADA Science Lab Stations","Bair Middle","","","","",15000,15000]
[2611,"Curb Ramps","Bair Middle",648,"","","","",648]
[2611,"Home Economics Kitchen Station ADA Retrofitting","Bair Middle","","","","",32000,32000]
[2611,"Restrooms","Bair Middle",136225,"","","","",136225]
[2611,"Visual Alarms location at Corridors","Bair Middle","",400,"","","",400]
[2001,"Curb Ramps","Banyan Elementary",648,"","","","",648]
[2001,"Signage","Banyan Elementary",1905,"","","","",1905]
[2001,"Visual Alarms at Restrooms","Banyan Elementary","",2000,"","","",2000]
[2001,"Visual Alarms location at Corridors","Banyan Elementary","",400,"","","",400]
[2001,"ADA Restrooms","Banyan Elementary ",127590,{"$nulls":4},127590]
[641,"Visual Alarms at Restrooms","Bayview Elementary","",3500,"","","",3500]
[9855,"Exterior Ramps","BECON/ITV","","","",60000,"",60000]
[9855,"Interior Doors","BECON/ITV","","","",40000,"",40000]
[9855,"Non-accessible Reception Counters","BECON/ITV","","","",10000,"",10000]
[9855,"Restrooms","BECON/ITV","","","",150000,"",150000]
[9855,"Signage","BECON/ITV","","","",8000,"",8000]
[9855,"Visual Alarms at Restrooms","BECON/ITV","","","",8000,"",8000]
[9855,"Wheelchair Lifts","BECON/ITV","","","",105000,"",105000]
[201,"Curb Ramps","Bennett Elementary",648,"","","","",648]
[201,"Restrooms","Bennett Elementary",155125,"","","","",155125]
[201,"Visual Alarms at Restrooms","Bennett Elementary","",3500,"","","",3500]
[201,"Visual Alarms location at Corridors","Bennett Elementary",1200,"","","","",1200]
[341,"Non Accessible Stage","Bethune, Mary M. Elementary","","","","",65000,65000]
[341,"Ramp at Second Means of Egress of Stage","Bethune, Mary M. Elementary","","","","",30000,30000]
[341,"Showers","Bethune, Mary M. Elementary","",2050,"","","",2050]
[341,"Visual Alarms location at Corridors","Bethune, Mary M. Elementary",1600,"","","","",1600]
[971,"Curb Ramps","Boulevard Heights Elementary",648,"","","","",648]
[971,"Curb Ramps","Boulevard Heights Elementary",648,"","","","",648]
[971,"Restrooms","Boulevard Heights Elementary",132070,"","","","",132070]
[971,"Restrooms","Boulevard Heights Elementary",132070,"","","","",132070]
[971,"Visual Alarms at Restrooms","Boulevard Heights Elementary",2500,"","","","",2500]
[971,"Visual Alarms at Restrooms","Boulevard Heights Elementary",2500,"","","","",2500]
[871,"ADA Restrooms","Bright Horizons Center ",25614,{"$nulls":4},25614]
[871,"Curb Ramps","Bright Horizons School",648,"","","","",648]
[871,"Visual Alarms at Restrooms","Bright Horizons School",500,"","","","",500]
[811,"Curb Ramps","Broadview Elementary",648,"","","","",648]
[811,"Handrails at Existing Ramps","Broadview Elementary",1350,1350,"","","",2700]
[811,"Non-accessible Playgrounds","Broadview Elementary","","","",50000,"",50000]
[811,"ADA Restrooms","Broadview Elementary ",182690,{"$nulls":4},182690]
[501,"Curb Ramps","Broward Estates Elementary","",3048,"","","",3048]
[501,"Non Accessible Stage","Broward Estates Elementary","","","","",65000,65000]
[501,"Showers","Broward Estates Elementary",1500,"","","","",1500]
[501,"Visual Alarms at Restrooms","Broward Estates Elementary",3500,"","","","",3500]
[501,"Visual Alarms location at Corridors","Broward Estates Elementary",400,"","","","",400]
[501,"ADA Restrooms","Broward Estates Elementary ",58100,{"$nulls":4},58100]
[1461,"Doors to Main Entrance of School","Castle Hill Elementary","","",8000,"","",8000]
[1461,"Non-accessible Playgrounds","Castle Hill Elementary","","",20000,"","",20000]
[2641,"Curb Ramp by main entrance of school","Central Park Elementary","","","","",5000,5000]
[2641,"Curb Ramps","Central Park Elementary","",27,"","","",27]
[2641,"Non Accessible Stage","Central Park Elementary","","","","",65000,65000]
[2641,"Signage","Central Park Elementary",6135,"","","","",6135]
[2641,"ADA Restrooms","Central Park Elementary ",71885,{"$nulls":4},71885]
[2961,"Handrails at Existing Ramps","Chapel Trail Elementary","",1350,"","","",1350]
[2961,"Non Accessible Stage","Chapel Trail Elementary","","","","",65000,65000]
[2961,"Walkways & Ramps to P.E. Building","Chapel Trail Elementary","","","","",20500,20500]
[2961,"ADA Restrooms","Chapel Trail Elementary ",31500,{"$nulls":4},31500]
[1421,"Accessible Route (sidewalks) to Playground","Coconut Creek Elementary","","",15000,"","",15000]
[1421,"Curb Ramps","Coconut Creek Elementary",27,"","","","",27]
[1421,"Non-accessible Playgrounds","Coconut Creek Elementary","","",40000,"","",40000]
[1421,"Signage","Coconut Creek Elementary",4065,"","","","",4065]
[1421,"ADA Restrooms","Coconut Creek Elementary ",3000,{"$nulls":4},3000]
[1681,"Curb Ramps","Coconut Creek High",648,"","","","",648]
[1681,"Home Economics Kitchen Station ADA Retrofitting","Coconut Creek High","",12000,"","","",12000]
[1681,"Wheelchair Area at Bleachers","Coconut Creek High","",15000,"","","",15000]
[1681,"ADA Restrooms","Coconut Creek High ",71370,{"$nulls":4},71370]
[1681,"Stadium Restroom ADA","Coconut Creek High ",50000,{"$nulls":4},50000]
[231,"Non Accessible Stage","Colbert Elementary","","","","",65000,65000]
[231,"Visual Alarms location at Corridors","Colbert Elementary",1200,"","","","",1200]
[331,"Accessible Route (sidewalks) to Playground","Collins Elementary","","",8000,"","",8000]
[331,"Handrails at Existing Ramps","Collins Elementary",1350,"","","","",1350]
[331,"Non Accessible Stage","Collins Elementary","","","","",65000,65000]
[331,"Visual Alarms at Restrooms","Collins Elementary","",2500,"","","",2500]
[331,"ADA Restrooms","Collins Elementary ",25450,{"$nulls":4},25450]
[1211,"Non Accessible Stage","Cooper City Elementary","","","","",65000,65000]
[1211,"Visual Alarms at Restrooms","Cooper City Elementary","",3000,"","","",3000]
[1211,"ADA Restrooms","Cooper City Elementary ",155899,{"$nulls":4},155899]
[1931,"Curb Ramps","Cooper City High",648,"","","","",648]
[1931,"Non-verbal Communication System at Elevators","Cooper City High","",560,"","","",560]
[1931,"Visual Alarms at Restrooms","Cooper City High",1000,"","","","",1000]
[1931,"Wheelchair Area at Bleachers","Cooper City High","",30000,"","","",30000]
[3041,"Curb Ramps","Coral Park Elementary",27,"","","","",27]
[3041,"Handrails at Existing Ramps","Coral Park Elementary","",1350,"","","",1350]
[3041,"ADA Restrooms","Coral Park Elementary ",68212,{"$nulls":4},68212]
[2551,"Restrooms","Coral Springs Elementary","",132670,"","","",132670]
[2551,"Showers","Coral Springs Elementary",2550,"","","","",2550]
[2551,"Visual Alarms at Restrooms","Coral Springs Elementary",3000,"","","","",3000]
[2551,"Visual Alarms location at Corridors","Coral Springs Elementary","",400,"","","",400]
[1151,"Accessible Route to Playcourts & Playfields","Coral Springs High","","",15000,"","",15000]
[1151,"Curb Ramps","Coral Springs High","",648,"","","",648]
[1151,"Home Economics Kitchen Station ADA Retrofitting","Coral Springs High","",12000,"","","",12000]
[1151,"Restrooms","Coral Springs High",103815,"","","","",103815]
[2561,"Accessible Route to Playcourts & Playfields","Coral Springs Middle","","",15000,"","",15000]
[2561,"ADA Science Lab Stations","Coral Springs Middle","","","","",15000,15000]
[2561,"Curb Ramps","Coral Springs Middle","",648,"","","",648]
[2561,"Restrooms","Coral Springs Middle","",104605,"","","",104605]
[2561,"Signage","Coral Springs Middle",3060,"","","","",3060]
[2561,"Visual Alarms at Restrooms","Coral Springs Middle",1500,"","","","",1500]
[2561,"Visual Alarms location at Corridors","Coral Springs Middle","",400,"","","",400]
[3111,"Non Accessible Stage","Country Hills Elementary","","","","",65000,65000]
[3111,"Ramp from second means of egress of Music Room","Country Hills Elementary","","",27500,"","",27500]
[3111,"Signage","Country Hills Elementary",5325,"","","","",5325]
[3111,"ADA Restrooms","Country Hills Elementary ",38140,{"$nulls":4},38140]
[2981,"Curb Ramps","Country Isles Elementary","",81,"","","",81]
[2981,"Visual Alarms location at Corridors","Country Isles Elementary","",1200,"","","",1200]
[2981,"ADA Restrooms","Country Isles Elementary ",53450,{"$nulls":4},53450]
[901,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Cresthaven Elementary","","",15000,"","",15000]
[901,"ADA Restrooms","Cresthaven Elementary ",9955,{"$nulls":4},9955]
[221,"Curb Ramps","Croissant Park Elementary","",2400,"","","",2400]
[221,"Non-verbal Communication System at Elevators","Croissant Park Elementary","",560,"","","",560]
[221,"Walkways & Ramps to P.E. Building","Croissant Park Elementary","","","","",15000,15000]
[221,"ADA Restrooms","Croissant Park Elementary ",78879,{"$nulls":4},78879]
[3222,"Curb Ramps","Cross Creek School",648,"","","","",648]
[3222,"Restrooms","Cross Creek School",83915,"","","","",83915]
[3222,"Visual Alarms at Restrooms","Cross Creek School","",1500,"","","",1500]
[1871,"ADA Restrooms","Crystal Lake Comm Middle ",52400,{"$nulls":4},52400]
[1871,"Curb Ramps","Crystal Lake Community Middle",648,"","","","",648]
[1871,"Showers","Crystal Lake Community Middle",400,"","","","",400]
[1781,"Accessible Route (sidewalks) to Playground","Cypress Elementary","","",15000,"","",15000]
[1781,"Doors to Main Entrance of School","Cypress Elementary","","",8000,"","",8000]
[1781,"Signage","Cypress Elementary",3975,"","","","",3975]
[1781,"ADA Restrooms","Cypress Elementary ",29950,{"$nulls":4},29950]
[2123,"Handrails at Existing Ramps","Cypress Run Alternative / Exceptional Center","",1350,"","","",1350]
[2123,"Visual Alarms at Restrooms","Cypress Run Alternative / Exceptional Center",1500,"","","","",1500]
[1071,"ADA Science Lab Stations","Dandy, William Middle","","","","",15000,15000]
[1071,"Home Economics Kitchen Station ADA Retrofitting","Dandy, William Middle","","","","",32000,32000]
[1071,"Restrooms","Dandy, William Middle",56150,"","","","",56150]
[1071,"Visual Alarms at Restrooms","Dandy, William Middle",2000,"","","","",2000]
[101,"Curb Ramps","Dania Elementary","",27,"","","",27]
[101,"Visual Alarms at Restrooms","Dania Elementary","",3000,"","","",3000]
[2801,"Curb Ramps","Davie Elementary",2400,"","","","",2400]
[2801,"Non-accessible Playgrounds","Davie Elementary","","",40000,"","",40000]
[2801,"Restrooms","Davie Elementary","",179315,"","","",179315]
[2801,"Visual Alarms at Restrooms","Davie Elementary",4500,"","","","",4500]
[11,"Curb Ramps","Deerfield Beach Elementary",54,"","","","",54]
[11,"Visual Alarms at Restrooms","Deerfield Beach Elementary","",4500,"","","",4500]
[1711,"Home Economics Kitchen Station ADA Retrofitting","Deerfield Beach High","",12000,"","","",12000]
[1711,"Non-Accessible Pool (Lift)","Deerfield Beach High",8000,"","","","",8000]
[1711,"Non-verbal Communication System at Elevators","Deerfield Beach High","",560,"","","",560]
[1711,"Wheelchair Area at Bleachers","Deerfield Beach High","",15000,"","","",15000]
[1711,"ADA Restrooms","Deerfield Beach High ",131104,{"$nulls":4},131104]
[911,"Curb Ramps","Deerfield Beach Middle","",3048,"","","",3048]
[911,"Non-Accessible Pool (Lift)","Deerfield Beach Middle",8000,"","","","",8000]
[911,"ADA Restrooms","Deerfield Beach Middle ",33600,{"$nulls":4},33600]
[391,"Signage","Deerfield Park Elementary",75,"","","","",75]
[391,"ADA Restrooms","Deerfield Park Elementary ",4800,{"$nulls":4},4800]
[371,"Curb Ramps","Dillard High",648,"","","","",648]
[371,"Home Economics Kitchen Station ADA Retrofitting","Dillard High","",12000,"","","",12000]
[371,"Non-verbal Communication System at Elevators","Dillard High","",560,"","","",560]
[371,"Restrooms","Dillard High",132180,"","","","",132180]
[0,"ADA Accessible Parking Spaces","District Wide ",205200,{"$nulls":4},205200]
[0,"ADA Accessible Parking Spaces","District Wide ",17200,{"$nulls":4},17200]
[0,"ADA Accommodations","District Wide ",50000,{"$nulls":4},50000]
[0,"ADA Correct Ext Doors","District Wide ",114670,{"$nulls":4},114670]
[0,"ADA Correct Showers","District Wide ",111468,{"$nulls":4},111468]
[0,"ADA Corrections","District Wide ",84537,{"$nulls":4},84537]
[0,"ADA Interior Doors","District Wide ",704928,{"$nulls":4},704928]
[0,"ADA Interior Doors","District Wide ",214325,{"$nulls":4},214325]
[0,"ADA Miscellaneous/Ramps","District Wide ",57311,{"$nulls":4},57311]
[0,"ADA Non Access Stage","District Wide ",226346,{"$nulls":4},226346]
[0,"ADA Non Access Stage/Mez","District Wide ",2248610,{"$nulls":4},2248610]
[0,"ADA Non-Acces Recep Count","District Wide ",96200,{"$nulls":4},96200]
[0,"ADA Non-Acces Recep Count","District Wide ",79300,{"$nulls":4},79300]
[0,"ADA Non-Access Playground","District Wide ",140000,{"$nulls":4},140000]
[0,"ADA Playground Retrofit","District Wide ",737267,{"$nulls":4},737267]
[0,"ADA Rescue Area","District Wide ",1494058,{"$nulls":4},1494058]
[0,"ADA Showers","District Wide ",139375,{"$nulls":4},139375]
[0,"ADA Signage","District Wide ",172108,{"$nulls":4},172108]
[0,"ADA TDD.TYY Comm. Equipment","District Wide ",13750,{"$nulls":4},13750]
[0,"ADA TDD.TYY Comm. Equipment","District Wide ",380,{"$nulls":4},380]
[0,"Signage ","District Wide ",307239,{"$nulls":4},307239]
[0,"Visual Alarms","District Wide ",20160,{"$nulls":4},20160]
[0,"Visual Alarms ","District Wide ",224600,{"$nulls":4},224600]
[3221,"ADA Restrooms","Drew Elementary ",20089,{"$nulls":4},20089]
[301,"Curb Ramps","Drew Resource Center","",648,"","","",648]
[301,"Visual Alarms at Restrooms","Drew Resource Center","",2500,"","","",2500]
[301,"Visual Alarms location at Corridors","Drew Resource Center","",2000,"","","",2000]
[301,"ADA Restrooms","Drew Resource Center ",32426,{"$nulls":4},32426]
[3221,"Ramp from second means of egress of Music Room","Drew, Charles Elementary","","",27500,"","",27500]
[3221,"Visual Alarms at Restrooms","Drew, Charles Elementary","",5500,"","","",5500]
[721,"Visual Alarms at Restrooms","Driftwood Elementary",1500,"","","","",1500]
[861,"Accessible Route (sidewalks) to Playfields","Driftwood Middle","","",18000,"","",18000]
[861,"Accessible Route to Playcourts & Playfields","Driftwood Middle","","",25000,"","",25000]
[861,"Curb Ramps","Driftwood Middle","",648,"","","",648]
[861,"Visual Alarms at Restrooms","Driftwood Middle",500,"","","","",500]
[861,"Visual Alarms location at Corridors","Driftwood Middle",800,"","","","",800]
[861,"ADA Restrooms","Driftwood Middle ",39681,{"$nulls":4},39681]
[3461,"Handrails at Existing Ramps","Eagle Point Elementary",1350,"","","","",1350]
[3461,"Non-verbal Communication System at Elevators","Eagle Point Elementary","",560,"","","",560]
[3461,"ADA Restrooms","Eagle Point Elementary ",31530,{"$nulls":4},31530]
[3441,"Non-verbal Communication System at Elevators","Eagle Ridge Elementary","",560,"","","",560]
[3441,"Signage","Eagle Ridge Elementary",3570,"","","","",3570]
[3441,"Walkways & Ramps to P.E. Building","Eagle Ridge Elementary","","","","",12000,12000]
[3441,"ADA Restrooms","Eagle Ridge Elementary ",9143,{"$nulls":4},9143]
[361,"ADA Restrooms","Ely High ",109370,{"$nulls":4},109370]
[3191,"Non-verbal Communication System at Elevators","Embassy Creek Elementary","",560,"","","",560]
[3191,"Restrooms","Embassy Creek Elementary",121495,"","","","",121495]
[3191,"Showers","Embassy Creek Elementary",450,"","","","",450]
[3191,"Visual Alarms at Restrooms","Embassy Creek Elementary","",2500,"","","",2500]
[3191,"Visual Alarms location at Corridors","Embassy Creek Elementary",800,"","","","",800]
[9512,"ADA Accommodations","Equal Educational Opp",93501,50000,50000,50000,50000,293501]
[9830,"Automobile & Van Accessible Parking Spaces","ESEA Title I","","","",2000,"",2000]
[9830,"Exterior Doors","ESEA Title I","","","",5000,"",5000]
[9830,"Install ramps at second mean of Egress and new concrete sidewalk to connect to existing  Sidewalk.","ESEA Title I","","","",50000,"",50000]
[9830,"Non-accessible Reception Counters","ESEA Title I","","","",5000,"",5000]
[9830,"Restrooms","ESEA Title I","","","",50000,"",50000]
[9830,"Signage","ESEA Title I","","","",5000,"",5000]
[9603,"ADA Emergency Projects","Facilities Department",436568,427298,480000,500000,500000,2343866]
[9603,"Capital ADA Projects Contingency Fund","Facilities Department",4860000,"","","","",4860000]
[1641,"Curb Ramps","Fairway Elementary","",27,"","","",27]
[1641,"Restrooms","Fairway Elementary","",360220,"","","",360220]
[1641,"Visual Alarms at Restrooms","Fairway Elementary",3000,"","","","",3000]
[1641,"Visual Alarms location at Corridors","Fairway Elementary","",1200,"","","",1200]
[2541,"Curb Ramps","Flamingo Elementary","",81,"","","",81]
[2541,"Restrooms","Flamingo Elementary",130445,"","","","",130445]
[2541,"Visual Alarms at Restrooms","Flamingo Elementary","",3000,"","","",3000]
[2541,"Visual Alarms location at Corridors","Flamingo Elementary",400,"","","","",400]
[3391,"Accessible Route to Playcourts & Playfields","Flanagan, Charles High","","",25000,"","",25000]
[3391,"Non-verbal Communication System at Elevators","Flanagan, Charles High","",1680,"","","",1680]
[3391,"Signage","Flanagan, Charles High",540,"","","","",540]
[3391,"ADA Restrooms","Flanagan, Charles High ",40413,{"$nulls":4},40413]
[851,"Accessible Route (sidewalks) to Playground","Floranada Elementary","","",15000,"","",15000]
[3051,"Accessible Route to Playcourts & Playfields","Forest Glen Middle","","",10000,"","",10000]
[3051,"ADA Science Lab Stations","Forest Glen Middle","","","","",15000,15000]
[3051,"Curb Ramps","Forest Glen Middle",648,"","","","",648]
[3051,"Home Economics Kitchen Station ADA Retrofitting","Forest Glen Middle","","","","",32000,32000]
[3051,"ADA Restrooms","Forest Glen Middle ",6294,{"$nulls":4},6294]
[2631,"Exterior Doors","Forest Hills Elementary",775,"","","","",775]
[2631,"Restrooms","Forest Hills Elementary",158250,"","","","",158250]
[2631,"Visual Alarms at Restrooms","Forest Hills Elementary",3000,"","","","",3000]
[2631,"Visual Alarms location at Corridors","Forest Hills Elementary",400,"","","","",400]
[951,"Curb Ramps","Fort Lauderdale High",648,"","","","",648]
[921,"ADA Restrooms","Foster, Stephen Elementary",86250,{"$nulls":4},86250]
[921,"Visual Alarms at Restrooms","Foster, Stephen Elementary","",4000,"","","",4000]
[2851,"Curb Ramps","Griffin Elementary","",81,"","","",81]
[2851,"Visual Alarms at Restrooms","Griffin Elementary",2500,"","","","",2500]
[2851,"ADA Restrooms","Griffin Elementary ",45038,{"$nulls":4},45038]
[592,"Curb Ramps","Hallandale Adult/Community",648,"","","","",648]
[592,"Handrails at Existing Ramps","Hallandale Adult/Community","",1350,"","","",1350]
[592,"ADA Restrooms","Hallandale Adult/Community",45344,{"$nulls":4},45344]
[403,"Accessible Route to Playcourts & Playfields","Hallandale High","","",15000,"","",15000]
[403,"Curb Ramps","Hallandale High","",648,"","","",648]
[403,"Handrails at Existing Ramps","Hallandale High",1350,"","","","",1350]
[403,"Non-verbal Communication System at Elevators","Hallandale High","",560,"","","",560]
[403,"Restrooms","Hallandale High","",108150,"","","",108150]
[403,"Showers","Hallandale High","",750,"","","",750]
[491,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Harbordale Elementary","","",25000,"","",25000]
[491,"Curb Ramps","Harbordale Elementary","",27,"","","",27]
[491,"TDD/TYY Comm. Equipment","Harbordale Elementary","",375,"","","",375]
[491,"Visual Alarms at Restrooms","Harbordale Elementary","",3000,"","","",3000]
[491,"ADA Restrooms","Harbordale Elementary ",47350,{"$nulls":4},47350]
[3131,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Hawkes Bluff Elementary","","",25000,"","",25000]
[3131,"Non Accessible Stage","Hawkes Bluff Elementary","","","","",65000,65000]
[3131,"Ramp from second means of egress of Music Room","Hawkes Bluff Elementary","","",27500,"","",27500]
[3131,"Visual Alarms at Restrooms","Hawkes Bluff Elementary",5500,"","","","",5500]
[3131,"ADA Restrooms","Hawkes Bluff Elementary ",22288,{"$nulls":4},22288]
[3131,"Ramp In Music Room (ADA)","Hawkes Bluff Elementary ",14950,{"$nulls":4},14950]
[121,"Curb Ramps","Hollywood Central Elementary",2400,"","","","",2400]
[121,"Visual Alarms at Restrooms","Hollywood Central Elementary","",4500,"","","",4500]
[111,"Accessible Route (sidewalks) to Playground","Hollywood Hills Elementary","","",2000,"","",2000]
[111,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Hollywood Hills Elementary","","",15000,"","",15000]
[111,"Showers","Hollywood Hills Elementary",2550,"","","","",2550]
[111,"Visual Alarms at Restrooms","Hollywood Hills Elementary",1000,"","","","",1000]
[111,"Visual Alarms location at Corridors","Hollywood Hills Elementary","",1600,"","","",1600]
[111,"ADA Restrooms","Hollywood Hills Elementary ",84895,{"$nulls":4},84895]
[1661,"Curb Ramps","Hollywood Hills High","",648,"","","",648]
[1661,"Handrails at Existing Ramps","Hollywood Hills High",1350,"","","","",1350]
[1661,"Home Economics Kitchen Station ADA Retrofitting","Hollywood Hills High","",12000,"","","",12000]
[1661,"Restrooms","Hollywood Hills High",209185,"","","","",209185]
[1661,"Signage","Hollywood Hills High",2545,"","","","",2545]
[1661,"Visual Alarms at Restrooms","Hollywood Hills High",3500,"","","","",3500]
[1661,"Visual Alarms location at Corridors","Hollywood Hills High",400,"","","","",400]
[1661,"Wheelchair Area at Bleachers","Hollywood Hills High","",15000,"","","",15000]
[1761,"Visual Alarms at Restrooms","Hollywood Park Elementary","",4000,"","","",4000]
[1761,"Visual Alarms location at Corridors","Hollywood Park Elementary",800,"","","","",800]
[1761,"ADA Restrooms","Hollywood Park Elementary ",8699,{"$nulls":4},8699]
[2531,"Restrooms","Horizon Elementary","",76350,"","","",76350]
[2531,"Visual Alarms at Restrooms","Horizon Elementary","",3500,"","","",3500]
[2531,"Visual Alarms location at Corridors","Horizon Elementary",800,"","","","",800]
[9067,"Exterior doors","Hortt Admin Site","","","",17000,"",17000]
[9067,"Restrooms","Hortt Admin Site","","","",125000,"",125000]
[9067,"Signage","Hortt Admin Site","","","",10000,"",10000]
[1971,"Curb Ramps","Hunt, James S. Elementary",54,"","","","",54]
[1971,"Restrooms","Hunt, James S. Elementary",105570,"","","","",105570]
[1971,"Visual Alarms at Restrooms","Hunt, James S. Elementary",3000,"","","","",3000]
[3471,"ADA Science Lab Stations","Indian Ridge Middle","","","","",57000,57000]
[3471,"Curb Ramps","Indian Ridge Middle",3048,"","","","",3048]
[3471,"Signage","Indian Ridge Middle",270,"","","","",270]
[3471,"Visual Alarms at Restrooms","Indian Ridge Middle",2500,"","","","",2500]
[3181,"Accessible Route (ramp) to Playground","Indian Trace Elementary","","",8000,"","",8000]
[3181,"Non Accessible Stage","Indian Trace Elementary","","","","",65000,65000]
[3181,"Visual Alarms at Restrooms","Indian Trace Elementary",4500,"","","","",4500]
[3181,"ADA Restrooms","Indian Trace Elementary ",2345,{"$nulls":4},2345]
[1611,"ADA Restrooms","King Martin Luther Elementary ",22517,{"$nulls":4},22517]
[831,"Showers","Lake Forest Elementary",750,"","","","",750]
[831,"Visual Alarms at Restrooms","Lake Forest Elementary","",1000,"","","",1000]
[405,"Curb Ramps","Lanier-James Education Center",648,"","","","",648]
[405,"Visual Alarms at Restrooms","Lanier-James Education Center","",3000,"","","",3000]
[621,"Curb Ramps","Larkdale Elementary","",2454,"","","",2454]
[621,"Restrooms","Larkdale Elementary",211550,"","","","",211550]
[621,"Visual Alarms at Restrooms","Larkdale Elementary","",3500,"","","",3500]
[1701,"Accessible Route to Playcourts & Playfields","Lauderdale Lakes Middle","","",15000,"","",15000]
[1701,"ADA Science Lab Stations","Lauderdale Lakes Middle","","","",15000,"",15000]
[1701,"Curb Ramps","Lauderdale Lakes Middle","",648,"","","",648]
[1701,"Home Economics Kitchen Station ADA Retrofitting","Lauderdale Lakes Middle","","","","",32000,32000]
[1701,"Visual Alarms at Restrooms","Lauderdale Lakes Middle",500,"","","","",500]
[1701,"Visual Alarms location at Corridors","Lauderdale Lakes Middle","",400,"","","",400]
[1701,"ADA Restrooms","Lauderdale Lakes Middle ",61807,{"$nulls":4},61807]
[431,"Curb Ramps","Lauderdale Manors Elementary","",2400,"","","",2400]
[431,"Non-verbal Communication System at Elevators","Lauderdale Manors Elementary","",560,"","","",560]
[431,"Visual Alarms at Restrooms","Lauderdale Manors Elementary",3000,"","","","",3000]
[431,"Visual Alarms location at Corridors","Lauderdale Manors Elementary","",800,"","","",800]
[431,"ADA Restrooms","Lauderdale Manors Elementary ",135615,{"$nulls":4},135615]
[1391,"ADA Science Lab Stations","Lauderhill Middle","","","",15000,"",15000]
[1391,"Curb Ramps","Lauderhill Middle",648,"","","","",648]
[1391,"Home Economics Kitchen Station ADA Retrofitting","Lauderhill Middle","","","","",32000,32000]
[1391,"Non-accessible restrooms at ESE Cluster Program (Building #2 )","Lauderhill Middle","","","",60000,"",60000]
[1391,"Showers","Lauderhill Middle","",3150,"","","",3150]
[1391,"Visual Alarms at Restrooms","Lauderhill Middle","",2500,"","","",2500]
[1391,"ADA Restrooms","Lauderhill Middle ",87300,{"$nulls":4},87300]
[1381,"ADA Restrooms","Lauderhill P T Elementary ",14836,{"$nulls":4},14836]
[1381,"Handrails at Existing Ramps","Lauderhill, P. T. Elementary",1350,"","","","",1350]
[1381,"Non-verbal Communication System at Elevators","Lauderhill, P. T. Elementary","",560,"","","",560]
[1381,"Visual Alarms at Restrooms","Lauderhill, P. T. Elementary","",2000,"","","",2000]
[1381,"Visual Alarms location at Corridors","Lauderhill, P. T. Elementary",800,"","","","",800]
[1091,"Visual Alarms at Restrooms","Lloyd Estates Elementary","",3000,"","","",3000]
[1091,"Visual Alarms location at Corridors","Lloyd Estates Elementary","",1200,"","","",1200]
[1091,"ADA Restrooms","Lloyd Estates Elementary ",158200,{"$nulls":4},158200]
[2741,"Restrooms","Maplewood Elementary",156330,"","","","",156330]
[2741,"Visual Alarms at Restrooms","Maplewood Elementary",3000,"","","","",3000]
[2741,"Visual Alarms location at Corridors","Maplewood Elementary","",400,"","","",400]
[1161,"ADA Restrooms","Margate Elementary ",20490,{"$nulls":4},20490]
[581,"Home Economics Kitchen Station ADA Retrofitting","Margate Middle","","","","",32000,32000]
[581,"Visual Alarms at Restrooms","Margate Middle",1000,"","","","",1000]
[581,"ADA Restrooms","Margate Middle ",1891,{"$nulls":4},1891]
[1671,"Curb Ramps","Markham, Robert Elementary",2400,"","","","",2400]
[1671,"Visual Alarms at Restrooms","Markham, Robert Elementary","",3500,"","","",3500]
[1671,"ADA Restrooms","Markham, Robert Elementary ",72894,{"$nulls":4},72894]
[3291,"Restrooms","Marshall, Thurgood Elementary","",101530,"","","",101530]
[3291,"Showers","Marshall, Thurgood Elementary",750,"","","","",750]
[3291,"Visual Alarms at Restrooms","Marshall, Thurgood Elementary",2500,"","","","",2500]
[3291,"Walkways & Ramps to P.E. Building","Marshall, Thurgood Elementary","","","","",20500,20500]
[241,"Accessible Route to Playcourts & Playfields","McArthur High","","",25000,"","",25000]
[241,"Curb Ramps","McArthur High","",648,"","","",648]
[241,"Handrails at Existing Ramps","McArthur High",1350,"","","","",1350]
[241,"Home Economics Kitchen Station ADA Retrofitting","McArthur High","",12000,"","","",12000]
[241,"Non-Accessible Pool (Lift)","McArthur High",8000,"","","","",8000]
[241,"Non-Accessible Pool (Lift)","McArthur High","","",8000,"","",8000]
[241,"Restrooms","McArthur High",214505,"","","","",214505]
[241,"Showers","McArthur High",6000,"","","","",6000]
[1291,"Curb Ramps","McFatter Technical Center","",648,"","","",648]
[1291,"Visual Alarms at Restrooms","McFatter Technical Center","",2500,"","","",2500]
[1291,"ADA Restrooms","McFatter Voc-Tech Center",11720,{"$nulls":4},11720]
[481,"Curb Ramps","McNicol Middle","",648,"","","",648]
[481,"Home Economics Kitchen Station ADA Retrofitting","McNicol Middle","","","","",32000,32000]
[531,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Miramar Elementary","","",25000,"","",25000]
[531,"Curb Ramps","Miramar Elementary",27,"","","","",27]
[531,"Signage","Miramar Elementary",5310,"","","","",5310]
[531,"ADA Restrooms","Miramar Elementary ",1800,{"$nulls":4},1800]
[1751,"Accessible Route to Playcourts & Playfields","Miramar High","","",15000,"","",15000]
[1751,"Curb Ramps","Miramar High",648,"","","","",648]
[1751,"Handrails at Existing Ramps","Miramar High","",1350,"","","",1350]
[1751,"Home Economics Kitchen Station ADA Retrofitting","Miramar High","",12000,"","","",12000]
[1751,"Restrooms","Miramar High",215205,"","","","",215205]
[1751,"Signage","Miramar High",2610,"","","","",2610]
[1751,"Visual Alarms location at Corridors","Miramar High",400,"","","","",400]
[1841,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Mirror Lake Elementary","","",10000,"","",10000]
[1841,"Doors to Main Entrance of School","Mirror Lake Elementary","","",8000,"","",8000]
[1841,"Non-accessible Playgrounds","Mirror Lake Elementary","","","",50000,"",50000]
[1841,"Visual Alarms at Restrooms","Mirror Lake Elementary",4000,"","","","",4000]
[1841,"Visual Alarms location at Corridors","Mirror Lake Elementary","",400,"","","",400]
[1841,"ADA Restrooms","Mirror Lake Elementary ",29950,{"$nulls":4},29950]
[2691,"Visual Alarms at Restrooms","Morrow Elementary","",2000,"","","",2000]
[2691,"Visual Alarms location at Corridors","Morrow Elementary",400,"","","","",400]
[2691,"ADA Restrooms","Morrow Elementary ",143314,{"$nulls":4},143314]
[9817,"Non-accessible Kitchen Counter","Multicultural/ESOL Prog Serv","","","",2500,"",2500]
[9817,"Non-accessible Reception Counters","Multicultural/ESOL Prog Serv","","","",5000,"",5000]
[9817,"Restrooms","Multicultural/ESOL Prog Serv","","","",70000,"",70000]
[881,"ADA Science Lab Stations","New River Middle","","","","",62000,62000]
[881,"ADA Restrooms","New River Middle ",1178,{"$nulls":4},1178]
[2671,"Visual Alarms at Restrooms","Nob Hill Elementary",3500,"","","","",3500]
[2671,"Visual Alarms location at Corridors","Nob Hill Elementary",800,"","","","",800]
[2671,"ADA Restrooms","Nob Hill Elementary ",4650,{"$nulls":4},4650]
[2671,"ADA Restrooms - ESE Cluster","Nob Hill Elementary ",100000,{"$nulls":4},100000]
[9278,"Access to 2nd Floor","North Area Maint/Bus Parking","","","",140000,"",140000]
[9278,"Automobile & Van Accessible Parking Spaces","North Area Maint/Bus Parking","","","",6000,"",6000]
[9278,"Exterior Doors","North Area Maint/Bus Parking","","","",2600,"",2600]
[9278,"Non-accessible Kitchen Counter","North Area Maint/Bus Parking","","","",2500,"",2500]
[9278,"Restrooms","North Area Maint/Bus Parking","","","",130000,"",130000]
[9278,"Restrooms","North Area Maint/Bus Parking","","","",125000,"",125000]
[9278,"Signage","North Area Maint/Bus Parking","","","",3000,"",3000]
[9278,"Signage","North Area Maint/Bus Parking","","","",5000,"",5000]
[9278,"Visual Alarms at Restrooms","North Area Maint/Bus Parking","","","",5000,"",5000]
[9360,"Automobile & Van Accessible Parking Spaces","North Area Maint/Warehouse","","","",2000,"",2000]
[9360,"Interior Doors","North Area Maint/Warehouse","","","",4000,"",4000]
[9360,"Ramps at Buildings Main Entrance","North Area Maint/Warehouse","","","",40000,"",40000]
[9360,"Restrooms","North Area Maint/Warehouse","","","",20000,"",20000]
[9360,"Signage","North Area Maint/Warehouse","","","",5000,"",5000]
[1191,"Curb Ramps","North Fork Elementary","",27,"","","",27]
[1191,"Restrooms","North Fork Elementary","",287730,"","","",287730]
[1191,"Visual Alarms at Restrooms","North Fork Elementary",4000,"","","","",4000]
[1191,"Visual Alarms location at Corridors","North Fork Elementary","",800,"","","",800]
[2231,"Restrooms","North Lauderdale Elementary","",236335,"","","",236335]
[41,"Curb Ramps","North Side Elementary","",27,"","","",27]
[41,"Visual Alarms at Restrooms","North Side Elementary","",3500,"","","",3500]
[41,"Visual Alarms location at Corridors","North Side Elementary","",400,"","","",400]
[1241,"Curb Ramps","Northeast High","",648,"","","",648]
[1241,"Handrails at Existing Ramps","Northeast High","",1350,"","","",1350]
[1241,"Non-Accessible Pool (Lift)","Northeast High","",8000,"","","",8000]
[1241,"Visual Alarms at Restrooms","Northeast High","",2000,"","","",2000]
[1241,"ADA Restrooms","Northeast High ",195605,{"$nulls":4},195605]
[1282,"Non-accessible Playgrounds","Nova Blanche Forman Elementary","","","",25000,"",25000]
[1282,"Showers","Nova Blanche Forman Elementary","",2100,"","","",2100]
[1282,"Visual Alarms at Restrooms","Nova Blanche Forman Elementary",2500,"","","","",2500]
[1282,"Visual Alarms location at Corridors","Nova Blanche Forman Elementary","",800,"","","",800]
[1271,"Curb Ramps","Nova Eisenhower Elementary",27,"","","","",27]
[1271,"Doors to Main Entrance of School","Nova Eisenhower Elementary","","",8000,"","",8000]
[1271,"Visual Alarms at Restrooms","Nova Eisenhower Elementary","",4000,"","","",4000]
[1271,"Visual Alarms location at Corridors","Nova Eisenhower Elementary","",800,"","","",800]
[1271,"ADA Restrooms","Nova Eisenhower Elementary ",28330,{"$nulls":4},28330]
[1281,"Curb Ramps","Nova High","",648,"","","",648]
[1281,"Non-Accessible Pool (Lift)","Nova High","",8000,"","","",8000]
[1281,"Visual Alarms at Restrooms","Nova High",2500,"","","","",2500]
[1281,"Wheelchair Area at Bleachers","Nova High","",15000,"","","",15000]
[1281,"ADA Restrooms","Nova High ",48917,{"$nulls":4},48917]
[1311,"Curb Ramps","Nova Middle","",648,"","","",648]
[1311,"Home Economics Kitchen Station ADA Retrofitting","Nova Middle","","","","",32000,32000]
[1311,"ADA Restrooms","Nova Middle ",51071,{"$nulls":4},51071]
[31,"ADA Restrooms","Oakland Park Elementary ",21885,{"$nulls":4},21885]
[461,"Visual Alarms at Restrooms","Oakridge Elementary",3000,"","","","",3000]
[461,"Visual Alarms location at Corridors","Oakridge Elementary",400,"","","","",400]
[461,"ADA Restrooms","Oakridge Elementary ",45797,{"$nulls":4},45797]
[471,"ADA Science Lab Stations","Olsen Middle","","","","",15000,15000]
[471,"Curb Ramps","Olsen Middle",3048,"","","","",3048]
[471,"Handrails at Existing Ramps","Olsen Middle",1350,"","","","",1350]
[471,"Home Economics Kitchen Station ADA Retrofitting","Olsen Middle","","","","",32000,32000]
[471,"Restrooms","Olsen Middle",900,"","","","",900]
[711,"Curb Ramps","Orange Brook Elementary",54,"","","","",54]
[711,"Visual Alarms at Restrooms","Orange Brook Elementary",1500,"","","","",1500]
[711,"Visual Alarms location at Corridors","Orange Brook Elementary",400,"","","","",400]
[1831,"Accessible Route (sidewalks) to Playgrounds & Playcourts","Oriole Elementary","","",15000,"","",15000]
[1831,"Non Accessible Stage","Oriole Elementary","","","","",65000,65000]
[1831,"Non-accessible Playgrounds","Oriole Elementary","","",40000,"","",40000]
[1831,"ADA Restrooms","Oriole Elementary ",89500,{"$nulls":4},89500]
[3311,"Non-accessible Playgrounds","Palm Cove Elementary","","",40000,"","",40000]
[3311,"ADA Restrooms","Palm Cove Elementary ",1800,{"$nulls":4},1800]
[1131,"Doors to Main Entrance of School","Palmview Elementary","","",8000,"","",8000]
[1131,"Visual Alarms at Restrooms","Palmview Elementary","",4000,"","","",4000]
[1131,"ADA Restrooms","Palmview Elementary ",29950,{"$nulls":4},29950]
[1951,"ADA Restrooms","Park Ridge Elementary ",50000,{"$nulls":4},50000]
[3171,"Curb Ramps","Park Springs Elementary",2400,"","","","",2400]
[3171,"Ramp from second means of egress of Music Room","Park Springs Elementary","","",27500,"","",27500]
[3171,"Visual Alarms at Restrooms","Park Springs Elementary","",5500,"","","",5500]
[3171,"ADA Restrooms","Park Springs Elementary ",16635,{"$nulls":4},16635]
[701,"Interior Doors (Building #22)","Parkway Middle","","","","",40000,40000]
[701,"Signage  (Building #22)","Parkway Middle","","","","",8000,8000]
[701,"ADA Restrooms","Parkway Middle ",74749,{"$nulls":4},74749]
[2071,"Handrails at Existing Ramps","Pasadena Lakes Elementary","",1350,"","","",1350]
[2071,"Non-accessible Playgrounds","Pasadena Lakes Elementary","","",40000,"","",40000]
[2071,"Visual Alarms at Restrooms","Pasadena Lakes Elementary",2500,"","","","",2500]
[2071,"Visual Alarms location at Corridors","Pasadena Lakes Elementary","",800,"","","",800]
[2071,"ADA Restrooms","Pasadena Lakes Elementary ",149677,{"$nulls":4},149677]
[2661,"Curb Ramps","Pembroke Lakes Elementary",27,"","","","",27]
[2661,"Handrails at Existing Ramps","Pembroke Lakes Elementary",1350,"","","","",1350]
[2661,"Visual Alarms at Restrooms","Pembroke Lakes Elementary",2500,"","","","",2500]
[2661,"Visual Alarms at Restrooms","Pembroke Lakes Elementary",2500,"","","","",2500]
[2661,"Visual Alarms location at Corridors","Pembroke Lakes Elementary",400,"","","","",400]
[2661,"Visual Alarms location at Corridors","Pembroke Lakes Elementary",400,"","","","",400]
[2661,"ADA Restrooms","Pembroke Lakes Elementary ",11155,{"$nulls":4},11155]
[1221,"Curb Ramps","Pembroke Pines Elementary","",2427,"","","",2427]
[1221,"Visual Alarms at Restrooms","Pembroke Pines Elementary","",4000,"","","",4000]
[1221,"Visual Alarms location at Corridors","Pembroke Pines Elementary",400,"","","","",400]
[1221,"ADA Restrooms","Pembroke Pines Elementary ",30450,{"$nulls":4},30450]
[1631,"ADA Restrooms","Perry Annabel Elementary ",29950,{"$nulls":4},29950]
[1631,"Curb Ramps","Perry, Annabel Elementary","",2427,"","","",2427]
[1631,"Doors to Main Entrance of School","Perry, Annabel Elementary","","",8000,"","",8000]
[1631,"Non-accessible Playgrounds","Perry, Annabel Elementary","","",40000,"","",40000]
[1631,"Signage","Perry, Annabel Elementary",3975,"","","","",3975]
[1011,"ADA Science Lab Stations","Perry, Henry D. Middle","","","","",45000,45000]
[1011,"Curb Ramps","Perry, Henry D. Middle","",648,"","","",648]
[1011,"Non-verbal Communication System at Elevators","Perry, Henry D. Middle","",560,"","","",560]
[1011,"Restrooms","Perry, Henry D. Middle","",52700,"","","",52700]
[1011,"Showers","Perry, Henry D. Middle","",4200,"","","",4200]
[1011,"Visual Alarms at Restrooms","Perry, Henry D. Middle","",3000,"","","",3000]
[1011,"Visual Alarms location at Corridors","Perry, Henry D. Middle",400,"","","","",400]
[931,"Non-accessible Playgrounds","Peters Elementary","","","",50000,"",50000]
[931,"ADA Restrooms","Peters Elementary ",63005,{"$nulls":4},63005]
[653,"Curb Ramps","Pine Ridge Alternative Center",2400,"","","","",2400]
[653,"Restrooms","Pine Ridge Alternative Center","",81300,"","","",81300]
[653,"Signage","Pine Ridge Alternative Center",860,"","","","",860]
[2861,"Handrails at Existing Ramps","Pines Lakes Elementary",1350,"","","","",1350]
[2861,"Visual Alarms at Restrooms","Pines Lakes Elementary",3000,"","","","",3000]
[2861,"Visual Alarms at Restrooms","Pines Lakes Elementary",3000,"","","","",3000]
[2861,"Visual Alarms location at Corridors","Pines Lakes Elementary","",800,"","","",800]
[2861,"Visual Alarms location at Corridors","Pines Lakes Elementary","",800,"","","",800]
[2861,"ADA Restrooms","Pines Lakes Elementary ",1550,{"$nulls":4},1550]
[1881,"Restrooms","Pines Middle",101940,"","","","",101940]
[1881,"Signage","Pines Middle",1095,"","","","",1095]
[2811,"Visual Alarms at Restrooms","Pinewood Elementary",2500,"","","","",2500]
[2811,"ADA Restrooms","Pinewood Elementary ",90964,{"$nulls":4},90964]
[2571,"ADA Science Lab Stations","Pioneer Middle","","","","",15000,15000]
[2571,"Showers","Pioneer Middle",4800,"","","","",4800]
[2571,"Signage","Pioneer Middle",390,"","","","",390]
[2571,"ADA Restrooms","Pioneer Middle ",82710,{"$nulls":4},82710]
[1901,"Handrails at Existing Ramps","Piper High","",1350,"","","",1350]
[1901,"Wheelchair Area at Bleachers","Piper High","",15000,"","","",15000]
[1901,"ADA Restrooms","Piper High ",58212,{"$nulls":4},58212]
[1451,"Curb Ramps","Plantation High","",3048,"","","",3048]
[1451,"Handrails at Existing Ramps","Plantation High","",1350,"","","",1350]
[1451,"Showers","Plantation High","",4500,"","","",4500]
[1451,"Wheelchair Area at Bleachers","Plantation High","",15000,"","","",15000]
[1451,"ADA Restrooms","Plantation High ",261656,{"$nulls":4},261656]
[551,"Curb Ramps","Plantation Middle",648,"","","","",648]
[551,"Home Economics Kitchen Station ADA Retrofitting","Plantation Middle","","","","",32000,32000]
[551,"Non-accessible restrooms at ESE Cluster Program (Building #2 )","Plantation Middle","","","",60000,"",60000]
[551,"Visual Alarms at Restrooms","Plantation Middle",2000,"","","","",2000]
[551,"ADA Non Access Restrooms","Plantation Middle ",120000,{"$nulls":4},120000]
[551,"ADA Restrooms","Plantation Middle ",17356,{"$nulls":4},17356]
[1251,"Visual Alarms location at Corridors","Plantation Park Elementary","",400,"","","",400]
[1251,"ADA Restrooms","Plantation Park Elementary ",168530,{"$nulls":4},168530]
[751,"Ramp from second means of egress of Music Room","Pompano Beach Elementary","","",27500,"","",27500]
[751,"ADA Restrooms","Pompano Beach Elementary ",23405,{"$nulls":4},23405]
[21,"Home Economics Kitchen Station ADA Retrofitting","Pompano Beach Middle","","","","",32000,32000]
[21,"ADA Restrooms","Pompano Beach Middle ",104470,{"$nulls":4},104470]
[3121,"Curb Ramps","Quiet Waters Elementary",2400,"","","","",2400]
[3121,"Non Accessible Stage","Quiet Waters Elementary","","","","",65000,65000]
[3121,"Ramp from second means of egress of Music Room","Quiet Waters Elementary","","",27500,"","",27500]
[3121,"Restrooms","Quiet Waters Elementary",23750,"","","","",23750]
[3121,"Visual Alarms at Restrooms","Quiet Waters Elementary","",5500,"","","",5500]
[2721,"Accessible Route (sidewalks) to Playcourts","Ramblewood Elementary","","",10000,"","",10000]
[2721,"Non-accessible Playgrounds","Ramblewood Elementary","","",40000,"","",40000]
[2721,"Restrooms","Ramblewood Elementary","",127310,"","","",127310]
[2721,"Visual Alarms location at Corridors","Ramblewood Elementary","",400,"","","",400]
[2711,"ADA Science Lab Stations","Ramblewood Middle","","","","",15000,15000]
[2711,"Curb Ramps","Ramblewood Middle","",3048,"","","",3048]
[2711,"Home Economics Kitchen Station ADA Retrofitting","Ramblewood Middle","","","","",32000,32000]
[2711,"Restrooms","Ramblewood Middle",102720,"","","","",102720]
[2711,"Showers","Ramblewood Middle",2400,"","","","",2400]
[2121,"ADA Science Lab Stations","Rickards Middle","","","",15000,"",15000]
[2121,"Home Economics Kitchen Station ADA Retrofitting","Rickards Middle","","","","",32000,32000]
[2121,"Non-accessible restrooms at ESE Cluster Program (Building #2 )","Rickards Middle","","","",60000,"",60000]
[2121,"Visual Alarms location at Corridors","Rickards Middle",400,"","","","",400]
[2121,"ADA Restrooms","Rickards Middle ",125140,{"$nulls":4},125140]
[2891,"Non-accessible Playgrounds","Riverglades Elementary","","",20000,"","",20000]
[2891,"Non-verbal Communication System at Elevators","Riverglades Elementary","",560,"","","",560]
[2891,"Restrooms","Riverglades Elementary","",121090,"","","",121090]
[2891,"Visual Alarms at Restrooms","Riverglades Elementary",2500,"","","","",2500]
[2891,"Walkways & Ramps to P.E. Building","Riverglades Elementary","","","","",12000,12000]
[151,"Visual Alarms at Restrooms","Riverland Elementary","",3500,"","","",3500]
[151,"ADA Restrooms","Riverland Elementary ",42950,{"$nulls":4},42950]
[3031,"Non-accessible Playgrounds","Riverside Elementary","","",40000,"","",40000]
[3031,"Restrooms","Riverside Elementary","",104055,"","","",104055]
[3031,"Visual Alarms at Restrooms","Riverside Elementary",4500,"","","","",4500]
[3031,"Visual Alarms location at Corridors","Riverside Elementary",400,"","","","",400]
[681,"Visual Alarms at Restrooms","Rock Island Elementary","",3500,"","","",3500]
[681,"ADA Restrooms","Rock Island Elementary ",281680,{"$nulls":4},281680]
[1851,"Restrooms","Royal Palm Elementary",93600,"","","","",93600]
[891,"Signage","Sanders Park Elementary",1350,"","","","",1350]
[891,"Visual Alarms at Restrooms","Sanders Park Elementary","",4000,"","","",4000]
[891,"ADA Restrooms","Sanders Park Elementary ",150300,{"$nulls":4},150300]
[3061,"Restrooms","Sandpiper Elementary","",56600,"","","",56600]
[3061,"TDD/TYY Comm. Equipment","Sandpiper Elementary",250,"","","","",250]
[3061,"Visual Alarms at Restrooms","Sandpiper Elementary",750,"","","","",750]
[3401,"Signage","Sawgrass Elementary",565,"","","","",565]
[3401,"TDD/TYY Comm. Equipment","Sawgrass Elementary",250,"","","","",250]
[3401,"Walkways & Ramps to P.E. Building","Sawgrass Elementary","","","","",10000,10000]
[3401,"ADA Restrooms","Sawgrass Elementary ",26275,{"$nulls":4},26275]
[3431,"Accessible Route to Playcourts & Playfields","Sawgrass Springs Middle","","",25000,"","",25000]
[3431,"ADA Science Lab Stations","Sawgrass Springs Middle","","","","",45000,45000]
[3431,"Curb Ramps","Sawgrass Springs Middle",648,"","","","",648]
[3431,"Non-accessible Reception Counters","Sawgrass Springs Middle","",560,"","","",560]
[3431,"Non-verbal Communication System at Elevators","Sawgrass Springs Middle","",560,"","","",560]
[3431,"Visual Alarms location at Corridors","Sawgrass Springs Middle",400,"","","","",400]
[3431,"ADA Restrooms","Sawgrass Springs Middle ",36981,{"$nulls":4},36981]
[2871,"Non Accessible Stage","Sea Castle Elementary","","","","",65000,65000]
[2871,"Non-accessible Playgrounds","Sea Castle Elementary","","",40000,"","",40000]
[2871,"Ramp from second means of egress of Music Room","Sea Castle Elementary","","",27500,"","",27500]
[2871,"Visual Alarms at Restrooms","Sea Castle Elementary",8250,"","","","",8250]
[2871,"ADA Restrooms","Sea Castle Elementary ",23750,{"$nulls":4},23750]
[601,"Non-Accessible  Restrooms at Clinic (Portable #R-29)","Seagull School",80000,"","","","",80000]
[601,"Non-Accessible Reception Counters (Portable R-29)","Seagull School",15000,"","","","",15000]
[601,"Signage (Portable #R-29)","Seagull School",3000,"","","","",3000]
[601,"Visual Alarms at Restrooms","Seagull School","",1000,"","","",1000]
[601,"ADA Restrooms","Seagull School ",81260,{"$nulls":4},81260]
[1891,"Accessible Route (sidewalks) to Playcourts","Seminole Middle","","",15000,"","",15000]
[1891,"Home Economics Kitchen Station ADA Retrofitting","Seminole Middle","","","","",32000,32000]
[1891,"Restrooms","Seminole Middle","",60500,"","","",60500]
[1811,"Non Accessible Stage","Sheridan Hills Elementary","","","","",65000,65000]
[1811,"Restrooms","Sheridan Hills Elementary",220505,"","","","",220505]
[1811,"Signage","Sheridan Hills Elementary",75,"","","","",75]
[1811,"Visual Alarms at Restrooms","Sheridan Hills Elementary","",7500,"","","",7500]
[1811,"Visual Alarms location at Corridors","Sheridan Hills Elementary",400,"","","","",400]
[1321,"Curb Ramps","Sheridan Park Elementary","",2509,"","","",2509]
[1321,"Visual Alarms at Restrooms","Sheridan Park Elementary",3000,"","","","",3000]
[1321,"Visual Alarms location at Corridors","Sheridan Park Elementary","",400,"","","",400]
[1321,"ADA Restrooms","Sheridan Park Elementary ",216549,{"$nulls":4},216549]
[1051,"Non-verbal Communication System at Elevators","Sheridan Technical Center","",560,"","","",560]
[1051,"Restrooms","Sheridan Technical Center","",134215,"","","",134215]
[1051,"Showers","Sheridan Technical Center",1500,"","","","",1500]
[1051,"Visual Alarms at Restrooms","Sheridan Technical Center",3500,"","","","",3500]
[2971,"Curb Ramps","Silver Lakes Middle","",648,"","","",648]
[2971,"Home Economics Kitchen Station ADA Retrofitting","Silver Lakes Middle","","","","",32000,32000]
[2971,"ADA Restrooms","Silver Lakes Middle ",80550,{"$nulls":4},80550]
[3491,"Visual Alarms at Restrooms","Silver Palms Elementary","",6000,"","","",6000]
[3491,"ADA Restrooms","Silver Palms Elementary ",28526,{"$nulls":4},28526]
[3081,"Accessible Route (sidewalks) to Playcourts","Silver Ridge Elementary","","",10000,"","",10000]
[3081,"Restrooms","Silver Ridge Elementary","",58550,"","","",58550]
[3331,"Accessible Route to Playcourts & Playfields","Silver Trail Middle","","",10000,"","",10000]
[3331,"ADA Science Lab Stations","Silver Trail Middle","","","","",57000,57000]
[3331,"Curb Ramps","Silver Trail Middle",648,"","","","",648]
[405,"ADA Restrooms","South Area Alternative Center ",56900,{"$nulls":4},56900]
[9379,"Install Accessible Sink at FISH #001","South Area Maint","","","",2500,"",2500]
[9379,"Signage","South Area Maint","","","",8000,"",8000]
[171,"ADA Restrooms","South Broward High ",48038,{"$nulls":4},48038]
[2351,"Home Economics Kitchen Station ADA Retrofitting","South Plantation High","",12000,"","","",12000]
[2351,"Non-verbal Communication System at Elevators","South Plantation High","",560,"","","",560]
[2351,"ADA Restrooms","South Plantation High ",205465,{"$nulls":4},205465]
[9561,"Exterior Ramps","South-Central Area Superintendent","","","",55000,"",55000]
[9561,"Install Accessible Sink at Kitchens (FISH #119D & 116C)","South-Central Area Superintendent","","","",10000,"",10000]
[9561,"Interior Doors","South-Central Area Superintendent","","","",5000,"",5000]
[9561,"Non-accessible Reception Counters","South-Central Area Superintendent","","","",5000,"",5000]
[9561,"Restrooms","South-Central Area Superintendent","","","",2000,"",2000]
[9561,"Signage","South-Central Area Superintendent","","","",10000,"",10000]
[691,"Showers","Stirling Elementary","",450,"","","",450]
[691,"Visual Alarms at Restrooms","Stirling Elementary",6750,"","","","",6750]
[691,"ADA Restrooms","Stirling Elementary ",41202,{"$nulls":4},41202]
[3011,"Accessible Route to Playcourts & Playfields","Stoneman Douglas High","","",25000,"","",25000]
[3011,"Automobile & Van Accessible Parking Spaces ","Stoneman Douglas High","","",3600,"","",3600]
[3011,"Curb Ramps","Stoneman Douglas High",648,"","","","",648]
[3011,"Handrails at Existing Ramps","Stoneman Douglas High","",1350,"","","",1350]
[3011,"Non-verbal Communication System at Elevators","Stoneman Douglas High","",560,"","","",560]
[3011,"Showers","Stoneman Douglas High","",5100,"","","",5100]
[3011,"Signage","Stoneman Douglas High",2410,"","","","",2410]
[3011,"Visual Alarms at Restrooms","Stoneman Douglas High",3500,"","","","",3500]
[3011,"Wheelchair Area at Bleachers","Stoneman Douglas High","",15000,"","","",15000]
[3011,"ADA Restrooms","Stoneman Douglas High ",44240,{"$nulls":4},44240]
[211,"Curb Ramps","Stranahan High","",648,"","","",648]
[211,"Home Economics Kitchen Station ADA Retrofitting","Stranahan High","",12000,"","","",12000]
[211,"Non-Accessible Pool (Lift)","Stranahan High",8000,"","","","",8000]
[211,"Showers","Stranahan High",4350,"","","","",4350]
[211,"Visual Alarms at Restrooms","Stranahan High","",2500,"","","",2500]
[211,"Wheelchair Area at Bleachers","Stranahan High","",15000,"","","",15000]
[211,"ADA Restrooms","Stranahan High ",240965,{"$nulls":4},240965]
[9808,"Curb Ramps","Student Support Serv/ESE","",2400,"","","",2400]
[9808,"Handrails at Existing Ramps","Student Support Serv/ESE",1350,"","","","",1350]
[9808,"Visual Alarms at Restrooms","Student Support Serv/ESE","",2500,"","","",2500]
[611,"ADA Restrooms","Sunland Park Elementary ",19146,{"$nulls":4},19146]
[251,"ADA Science Lab Stations","Sunrise Middle","","","","",15000,15000]
[251,"Home Economics Kitchen Station ADA Retrofitting","Sunrise Middle","","","","",32000,32000]
[251,"ADA Restrooms","Sunrise Middle ",16130,{"$nulls":4},16130]
[251,"ADA Restrooms - ESE Cluster","Sunrise Middle ",100000,{"$nulls":4},100000]
[422,"Signage","Sunset Learning Center",180,"","","","",180]
[422,"ADA Restrooms","Sunset School ",8100,{"$nulls":4},8100]
[1171,"ADA Restrooms","Sunshine Elementary ",143910,{"$nulls":4},143910]
[9701,"ADA Restrooms","Support Services-Associate ",121495,{"$nulls":4},121495]
[2621,"Handrails at Existing Ramps","Tamarac Elementary",1350,"","","","",1350]
[2621,"Non-verbal Communication System at Elevators","Tamarac Elementary","",560,"","","",560]
[2621,"Restrooms","Tamarac Elementary","",127310,"","","",127310]
[2751,"Curb Ramps","Taravella J P High",648,"","","","",648]
[2751,"Non-verbal Communication System at Elevators","Taravella J P High","",560,"","","",560]
[2751,"Visual Alarms at Restrooms","Taravella J P High","",2500,"","","",2500]
[2751,"Wheelchair Area at Bleachers","Taravella J P High","",15000,"","","",15000]
[2751,"ADA Restrooms","Taravella J P High ",55744,{"$nulls":4},55744]
[9356,"Acquisition/Remodeling ","Technology/Support Serv Site ",98441,{"$nulls":4},98441]
[571,"Curb Ramps","Tedder Elementary",2400,"","","","",2400]
[571,"Visual Alarms at Restrooms","Tedder Elementary",1000,"","","","",1000]
[571,"Visual Alarms location at Corridors","Tedder Elementary",1600,"","","","",1600]
[571,"ADA Restrooms","Tedder Elementary ",153205,{"$nulls":4},153205]
[3151,"ADA Science Lab Stations","Tequesta Trace Middle","","","","",15000,15000]
[3151,"Curb Ramps","Tequesta Trace Middle","",2400,"","","",2400]
[3151,"Home Economics Kitchen Station ADA Retrofitting","Tequesta Trace Middle","","","","",32000,32000]
[3151,"ADA Restrooms","Tequesta Trace Middle ",762,{"$nulls":4},762]
[1021,"Curb Ramps","The Quest Center","",648,"","","",648]
[1021,"Visual Alarms at Restrooms","The Quest Center",5000,"","","","",5000]
[1021,"Visual Alarms location at Corridors","The Quest Center","",800,"","","",800]
[1021,"ADA Restrooms","The Quest Center ",122603,{"$nulls":4},122603]
[3481,"Showers","Tradewinds Elementary","",2850,"","","",2850]
[3481,"Visual Alarms at Restrooms","Tradewinds Elementary",2500,"","","","",2500]
[3481,"ADA Restrooms","Tradewinds Elementary ",56481,{"$nulls":4},56481]
[731,"Signage","Tropical Elementary",75,"","","","",75]
[731,"Visual Alarms at Restrooms","Tropical Elementary","",3500,"","","",3500]
[731,"ADA Restrooms","Tropical Elementary ",220505,{"$nulls":4},220505]
[1621,"Non-verbal Communication System at Elevators","Village Elementary","",560,"","","",560]
[1621,"ADA Restrooms","Village Elementary ",76340,{"$nulls":4},76340]
[321,"ADA Restrooms","Walker Elementary ",39997,{"$nulls":4},39997]
[511,"Restrooms","Watkins Elementary",11245,"","","","",11245]
[511,"Visual Alarms at Restrooms","Watkins Elementary","",500,"","","",500]
[2881,"Restrooms","Welleby Elementary","",122090,"","","",122090]
[2881,"Visual Alarms at Restrooms","Welleby Elementary","",2500,"","","",2500]
[2881,"Walkways & Ramps to P.E. Building","Welleby Elementary","","","","",15000,15000]
[161,"Handrails at Existing Ramps","West Hollywood Elementary",1350,"","","","",1350]
[161,"Interior Doors","West Hollywood Elementary",4000,"","","","",4000]
[161,"Non-accessible Reception Counters","West Hollywood Elementary",1300,"","","","",1300]
[161,"Showers","West Hollywood Elementary",2550,"","","","",2550]
[161,"Signage","West Hollywood Elementary",3705,"","","","",3705]
[2681,"Curb Ramps","Westchester Elementary","",54,"","","",54]
[2681,"Visual Alarms at Restrooms","Westchester Elementary","",2500,"","","",2500]
[2681,"Visual Alarms location at Corridors","Westchester Elementary",400,"","","","",400]
[2681,"ADA Restrooms","Westchester Elementary ",126800,{"$nulls":4},126800]
[2831,"Accessible Route to Playcourts & Playfields","Western High","","",15000,"","",15000]
[2831,"Curb Ramps","Western High",648,"","","","",648]
[2831,"Non-verbal Communication System at Elevators","Western High","",560,"","","",560]
[2831,"Wheelchair Area at Bleachers","Western High","",30000,"","","",30000]
[2831,"ADA Restrooms","Western High ",52723,{"$nulls":4},52723]
[2052,"ADA Science Lab Stations","Westpine Middle","","","","",15000,15000]
[2052,"Home Economics Kitchen Station ADA Retrofitting","Westpine Middle","","","","",32000,32000]
[2052,"Restrooms","Westpine Middle","",83900,"","","",83900]
[631,"Visual Alarms at Restrooms","Westwood Heights Elementary","",1000,"","","",1000]
[631,"Visual Alarms location at Corridors","Westwood Heights Elementary","",800,"","","",800]
[412,"ADA Restrooms","Whiddon-Rogers Annex ",65125,{"$nulls":4},65125]
[452,"ADA Restrooms","Whiddon-Rogers Ed Center",67431,{"$nulls":4},67431]
[452,"Interior Doors","Whiddon-Rogers Ed Center",18025,"","","","",18025]
[452,"Visual Alarms at Restrooms","Whiddon-Rogers Ed Center",3500,"","","","",3500]
[452,"Visual Alarms at Restrooms","Whiddon-Rogers Ed Center","",2500,"","","",2500]
[452,"Visual Alarms location at Corridors","Whiddon-Rogers Ed Center","",1200,"","","",1200]
[1752,"Handrails at Existing Ramps","Whispering Pines Ctr","",1350,"","","",1350]
[1752,"Visual Alarms at Restrooms","Whispering Pines Ctr",10000,"","","","",10000]
[1752,"ADA Restrooms","Whispering Pines Ctr ",131019,{"$nulls":4},131019]
[191,"Curb Ramps","Wilton Manors Elementary",2400,"","","","",2400]
[191,"Signage","Wilton Manors Elementary",440,"","","","",440]
[191,"Visual Alarms at Restrooms","Wilton Manors Elementary","",2000,"","","",2000]
[191,"ADA Restrooms","Wilton Manors Elementary ",10300,{"$nulls":4},10300]
[991,"Curb Ramps","Wingate Oaks Center","",648,"","","",648]
[991,"ADA Restrooms","Wingate Oaks Center ",1500,{"$nulls":4},1500]
[3091,"Non Accessible Stage","Winston Park Elementary","","","","",65000,65000]
[3091,"Ramp from second means of egress of Music Room","Winston Park Elementary","","",27500,"","",27500]
[3091,"Restrooms","Winston Park Elementary","",23405,"","","",23405]
[3321,"ADA Restrooms","Young, Virginia S Elem ",1800,{"$nulls":4},1800]
[3321,"Curb Ramps","Young, Virginia S. Elementary","",27,"","","",27]
[3001,"Accessible Route to Playcourts & Playfields","Young, Walter C. Middle","","",25000,"","",25000]
[3001,"Home Economics Kitchen Station ADA Retrofitting","Young, Walter C. Middle","","","","",32000,32000]
[3001,"Restrooms","Young, Walter C. Middle","",40200,"","","",40200]
[3001,"Visual Alarms at Restrooms","Young, Walter C. Middle",1000,"","","","",1000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Maintenance, Repair, and Renovation Totals",null,491761082,132054909,75341372,94619837,81947707,875724907]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,10977710,5950731,8954588,9499166,9969483,45351678]
["2b1","Broward Total",null,480783372,126104178,66386784,85120671,71978224,830373229]
[]
[]
[]
["2b2","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[1741,"Classroom Addition/Site Improvement","Anderson, Boyd H High ",272491,{"$nulls":4},272491]
[1791,"Classroom Addition","Apollo Middle",3779790,"","","","",3779790]
[1791,"Remodel Media Center to expand for excessive capacity","Apollo Middle",{"$nulls":4},839520,839520]
[3702,"New School (Fort Lauderdale)","Arthur Robert Ashe, Jr. Middle (\"GG\")",3747330,"","","","",3747330]
[2221,"Classroom Addition","Atlantic Technical Center",5501370,"","","","",5501370]
[2221,"New Cafeteria / Kitchen due to excessive capacity","Atlantic Technical Center",{"$nulls":4},2820615,2820615]
[2511,"New Kitchen / Dining / Multipurpose / Stage","Atlantic West Elementary",{"$nulls":4},3758525,3758525]
[2511,"New Media Center due to excessive capacity","Atlantic West Elementary",{"$nulls":4},2658498,2658498]
[2511,"Land ","Atlantic West Elementary ",300000,{"$nulls":4},300000]
[343,"New Media Center due to excessive capacity","Attucks Middle",{"$nulls":4},3108219,3108219]
[343,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Attucks Middle",{"$nulls":4},1477059,1477059]
[2611,"New Media Center due to excessive capacity","Bair Middle",{"$nulls":4},2832981,2832981]
[2611,"New Multipurpose","Bair Middle",{"$nulls":4},0,0]
[2001,"Expand Kitchen","Banyan Elementary",{"$nulls":4},607221,607221]
[641,"Phased Replacement II of III","Bayview Elementary",1254089,"","","","",1254089]
[201,"New Media Center due to excessive capacity","Bennett Elementary",{"$nulls":4},2651782,2651782]
[341,"Phased Replacement II","Bethune, Mary M. Elementary",10373604,"","","","",10373604]
[361,"Med/Arts/Kitch/IEQ/HVAC","Blanche Ely High",21296660,"","","","",21296660]
[361,"New Media Center due to excessive capacity","Blanche Ely High",{"$nulls":4},4031710,4031710]
[971,"Remodel Media Center to expand for excessive capacity","Boulevard Heights Elementary",{"$nulls":4},705889,705889]
[811,"Classroom Addition","Broadview Elementary",6478830,"","","","",6478830]
[811,"Land ","Broadview Elementary ",493770,{"$nulls":4},493770]
[501,"Classroom Addition","Broward Estates Elementary",146226,"","","","",146226]
[9612,"Long Range Facilities Master Plan","Capital Planning/Programming ",75245,{"$nulls":4},75245]
[1461,"Classroom Addition / New Cafeteria / Kitchen / Multipurpose area / Stage","Castle Hill Elementary",3483755,"","","","",3483755]
[2641,"Classroom Addition","Central Park Elementary",3590270,"","","","",3590270]
[3771,"New School F-91 Elementary","Challenger Elementary ",839152,{"$nulls":4},839152]
[1421,"New Cafeteria / Kitchen due to excessive capacity","Coconut Creek Elementary",{"$nulls":4},3877507,3877507]
[1681,"New Media Center due to excessive capacity","Coconut Creek High",{"$nulls":4},4514595,4514595]
[3741,"New School E-6 ","Coconut Palm Elementary",582957,{"$nulls":4},582957]
[231,"Classroom Addition","Colbert Elementary",1296764,"","","","",1296764]
[231,"New Cafeteria / Kitchen due to excessive capacity","Colbert Elementary",{"$nulls":4},3861603,3861603]
[231,"Phased Replacement I of II","Colbert Elementary",5634818,"","","","",5634818]
[1211,"4 Class Addition/IEQ/HVAC/Intercom","Cooper City Elementary ",372091,{"$nulls":4},372091]
[1931,"Classroom Addition","Cooper City High",17044682,"","","","",17044682]
[3041,"New Cafeteria / Kitchen due to excessive capacity","Coral Park Elementary",{"$nulls":4},3875902,3875902]
[2551,"New Media Center due to excessive capacity","Coral Springs Elementary",{"$nulls":4},2657462,2657462]
[1151,"Classroom Addition","Coral Springs High",7000000,"","","","",7000000]
[0,"New Media Center due to excessive capacity","Coral Springs High",{"$nulls":4},4363213,4363213]
[1151,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Coral Springs High",{"$nulls":4},2066176,2066176]
[2561,"Classroom Addition  and Kitchen/Cafeteria  renovation","Coral Springs Middle",null,"","",3200000,"",3200000]
[2981,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Country Isles Elementary",{"$nulls":4},768921,768921]
[3731,"Site Acquisition ","Country Lakes High School III",4811,{"$nulls":4},4811]
[3721,"Site Acquisition ","Country Lakes Mid Site ",340148,{"$nulls":4},340148]
[901,"New Cafeteria / Kitchen due to excessive capacity","Cresthaven Elementary",{"$nulls":4},3882043,3882043]
[1871,"Remodel Media Center to expand for excessive capacity","Crystal Lake Community Middle",{"$nulls":4},1275080,1275080]
[3623,"24 Classroom Addition ","Cypress Bay High",null,"",600000,5400000,"",6000000]
[3623,"New High School","Cypress Bay High",2628165,"",null,null,"",2628165]
[1781,"Classroom Addition","Cypress Elementary",1537950,"","","","",1537950]
[1781,"New Media Center due to excessive capacity","Cypress Elementary",{"$nulls":4},2663798,2663798]
[3891,"New School ","Cypress Run Alt Site ",527615,{"$nulls":4},527615]
[3891,"Site Acquisition ","Cypress Run Alt Site ",1225937,{"$nulls":4},1225937]
[2123,"New School","Cypress Run Alternative / Exceptional Center",5359269,"","","","",5359269]
[1071,"Remodel Media Center to expand for excessive capacity","Dandy, William Middle",{"$nulls":4},920325,920325]
[2801,"New Media Center due to excessive capacity","Davie Elementary",{"$nulls":4},2669204,2669204]
[11,"Phased Replacement ","Deerfield Beach Elementary ",207604,{"$nulls":4},207604]
[1711,"24 Classrm/Addition ","Deerfield Beach High",10248388,"","","","",10248388]
[1711,"Remodel Media Center to expand for excessive capacity","Deerfield Beach High",{"$nulls":4},1689540,1689540]
[1711,"Land ","Deerfield Beach High ",40116,{"$nulls":4},40116]
[911,"Classroom Addition","Deerfield Beach Middle",1020000,"","","","",1020000]
[911,"New Media Center due to excessive capacity","Deerfield Beach Middle",{"$nulls":4},3015818,3015818]
[911,"Phased Replacement ","Deerfield Beach Middle ",291071,{"$nulls":4},291071]
[371,"Phased Replacement & New Arts Center","Dillard High",8068795,"","","","",8068795]
[371,"50 Classroom Bldg ","Dillard High ",64651,{"$nulls":4},64651]
[0,"Capitalized Cost","District Wide",43391096,14206000,14632000,15071000,15478000,102778096]
[0,"Class Size Reduction (Classrooms for Kids)","District Wide",43226914,{"$nulls":4},43226914]
[0,"COLA","District Wide",1186103,3760223,6418542,9048223,9686000,30099091]
[0,"Contingency","District Wide",28392324,2098433,8640174,"","",39130931]
[0,"Land","District Wide",9243149,1000000,1000000,1000000,1000000,13243149]
[0,"Lease Agreement - Baudhuin Preschool (Autism Center)","District Wide",280000,280000,280000,280000,280000,1400000]
[0,"Legal & Contingency","District Wide",12618237,3600000,3600000,3600000,3600000,27018237]
[0,"Portables","District Wide",17078878,6000000,6000000,6000000,6000000,41078878]
[0,"Portables","District Wide",7621001,3000000,3000000,3000000,3000000,19621001]
[0,"Future Site Development ","District Wide ",7000000,{"$nulls":4},7000000]
[0,"Land Acquisition ","District Wide ",2858955,{"$nulls":4},2858955]
[0,"Site Improvements ","District Wide ",251068,{"$nulls":4},251068]
[0,"Site Improvements ","District Wide ",71455,{"$nulls":4},71455]
[0,"Special Appropriations","District Wide ",750000,{"$nulls":4},750000]
[301,"New Media Center due to excessive capacity","Drew Resource Center",{"$nulls":4},804088,804088]
[721,"New Media Center due to excessive capacity","Driftwood Elementary",{"$nulls":4},2665544,2665544]
[721,"Phased Replacement II of II","Driftwood Elementary",1746200,"","","","",1746200]
[861,"Classroom Addition","Driftwood Middle",2226908,"","","","",2226908]
[861,"New Cafeteria / Kitchen due to excessive capacity","Driftwood Middle",{"$nulls":4},3833144,3833144]
[861,"Remodel Media Center to expand for excessive capacity","Driftwood Middle",{"$nulls":4},1149665,1149665]
[861,"Phase II - IV Rebuild","Driftwood Middle ",265668,{"$nulls":4},265668]
[3521,"Site Aquisition ","Elem J-91 Site ",13883,{"$nulls":4},13883]
[3661,"Site Acquisition ","Elem Q Sunset Lakes Dev ",4257,{"$nulls":4},4257]
[3701,"New School N-91 Elementary","Elementary N-91/GG",339797,{"$nulls":4},339797]
[30009,"New School - Area F","Elementary School \"Y\" Formerly (Area F #1)",12275000,2725000,"","","",15000000]
[30008,"Land","Elementary School (Area A #1)",null,2000000,"","","",2000000]
[30008,"New School - Area A","Elementary School (Area A #1)",null,"",1500000,10775000,2725000,15000000]
[30012,"Land","Elementary School (Area A #2)",null,"","","",2000000,2000000]
[30013,"Land","Elementary School (Area D #1)",null,"","","",2000000,2000000]
[2914,"New School\n(south central-west)","Elementary School (Area D #2) Formerly \"Y\"",null,1613932,13143856,"","",14757788]
[30010,"New School - Area F","Elementary School (Area F #2)",null,"","",1500000,13500000,15000000]
[30014,"Land","Elementary School (Area F #3)",null,"","","",2000000,2000000]
[30011,"Land","Elementary School (Area G #1)",5000000,5000000,"","","",10000000]
[30011,"New School  - Area G","Elementary School (Area G #1)",null,12275000,2725000,"","",15000000]
[3191,"4 Classroom Addition","Embassy Creek Elementary",{"$nulls":4},891135,891135]
[3191,"4 Classroom Addition","Embassy Creek Elementary ",602633,{"$nulls":4},602633]
[3301,"New School","Endeavor Primary Learning Center",3437970,"","","","",3437970]
[3731,"New School (Miramar)","Everglades High School (\"III\")",16996082,"","","","",16996082]
[3622,"New School \"KK\"","Falcon Cove Middle ",32329,{"$nulls":4},32329]
[2541,"New Kitchen / Dining / Multipurpose / Stage","Flamingo Elementary",{"$nulls":4},4095961,4095961]
[851,"Replacement School ","Floranada Elementary ",40523,{"$nulls":4},40523]
[3051,"New Media Center due to excessive capacity","Forest Glen Middle",{"$nulls":4},2618691,2618691]
[2631,"6 Classroom Addition","Forest Hills Elementary",{"$nulls":4},1336703,1336703]
[2631,"New Media Center due to excessive capacity","Forest Hills Elementary",{"$nulls":4},2662214,2662214]
[951,"Phased Replacement","Fort Lauderdale High",20178121,"","","","",20178121]
[951,"Stadium Design","Fort Lauderdale High",150000,"","","","",150000]
[592,"Classroom Addition","Hallandale Adult/Community",3647802,"","","","",3647802]
[593,"Replacement School-Hallandale Elementary","Hallandale Elementary",12188337,{"$nulls":4},12188337]
[403,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Hallandale High",{"$nulls":4},1639845,1639845]
[403,"Remodel Media Center to expand for excessive capacity","Hallandale High",{"$nulls":4},1571136,1571136]
[403,"Stadium Design","Hallandale High",150000,"","","","",150000]
[3131,"Class Size Reduction ","Hawkes Bluff Elementary ",52489,{"$nulls":4},52489]
[3681,"New High School \"FFF\"","High School \"FFF\"",1126363,{"$nulls":4},1126363]
[30004,"New School (West Central Region of Broward County)","High School \"FFF\"",27419979,2384346,"","","",29804325]
[3541,"Land Acquisition ","High School \"GGG\"",20477,{"$nulls":4},20477]
[3861,"New School (Coral Springs)","High School \"JJJ\"",41554499,"","","","",41554499]
[3861,"Site Acquisition ","High School \"JJJ\"",1215,{"$nulls":4},1215]
[30007,"Land","High School \"LLL\" (Area F)",5000000,"","","","",5000000]
[30007,"New School - Area F","High School \"LLL\" (Area F)",null,5000000,35970000,9030000,"",50000000]
["TBA","New School","High School \"MMM\"",{"$nulls":4},63000000,63000000]
["TBA","New School","High School \"NNN\"",{"$nulls":4},63000000,63000000]
[121,"8 Classroom Addition","Hollywood Central Elementary",{"$nulls":4},1782270,1782270]
[121,"New Cafeteria / Kitchen due to excessive capacity","Hollywood Central Elementary",{"$nulls":4},3877413,3877413]
[121,"New Media Center due to excessive capacity","Hollywood Central Elementary",{"$nulls":4},2668929,2668929]
[121,"Site Expansion","Hollywood Central Elementary ",162700,{"$nulls":4},162700]
[111,"Phased Replacement II of III","Hollywood Hills Elementary",3074729,"","","","",3074729]
[1661,"Classroom Addition","Hollywood Hills High",5205381,"","","","",5205381]
[1761,"New Cafeteria / Kitchen due to excessive capacity","Hollywood Park Elementary",{"$nulls":4},3875020,3875020]
[2531,"Expand Kitchen","Horizon Elementary",{"$nulls":4},637650,637650]
[2531,"New Media Center due to excessive capacity","Horizon Elementary",{"$nulls":4},2662977,2662977]
[2991,"Land Development ","Huntington Elementary Site ",948015,{"$nulls":4},948015]
[831,"First Grade Class Size Reduction Classroom Addition","Lake Forest Elementary",1354808,"","","","",1354808]
[831,"Phased Replacement II of II","Lake Forest Elementary",7233926,"","","","",7233926]
[621,"New Cafeteria / Kitchen due to excessive capacity","Larkdale Elementary",{"$nulls":4},3871116,3871116]
[621,"Remodel Media Center to expand for excessive capacity","Larkdale Elementary",{"$nulls":4},500745,500745]
[1701,"Expand Kitchen","Lauderdale Lakes Middle",{"$nulls":4},942321,942321]
[1701,"Remodel Media Center to expand for excessive capacity","Lauderdale Lakes Middle",{"$nulls":4},818553,818553]
[1391,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Lauderhill Middle",{"$nulls":4},990010,990010]
[1391,"Remodel Media Center to expand for excessive capacity","Lauderhill Middle",{"$nulls":4},1113436,1113436]
[3821,"New School - Elem \"O\" ","Liberty Elementary \"O\"",2028361,{"$nulls":4},2028361]
[3821,"Site Acquisition ","Liberty Elemtary 'O' ",39872,{"$nulls":4},39872]
[1091,"2 Classroom Addition & Remodel Existing Space to 2 Classrooms","Lloyd Estates Elementary",{"$nulls":4},662918,662918]
[3101,"New School \"HH\"","Lyons Creek Middle (HH)",148558,{"$nulls":4},148558]
[3831,"New School - Elem \"P\" ","Manatee Bay Elem 'P' ",2836833,{"$nulls":4},2836833]
[2741,"3 Classroom Addition","Maplewood Elementary",{"$nulls":4},668351,668351]
[1161,"12 Classroom Addition","Margate Elementary ",176713,{"$nulls":4},176713]
[1161,"8 Classroom Addition","Margate Elementary ",633937,{"$nulls":4},633937]
[581,"Classroom Addition","Margate Middle",941735,"","","","",941735]
[581,"Remodel Media Center to expand for excessive capacity","Margate Middle",{"$nulls":4},1116990,1116990]
[241,"Completion of Phased Replacement","McArthur High",null,1332578,11993199,"","",13325777]
[241,"Phased Replacement III of III","McArthur High",17287054,"","","","",17287054]
[1291,"New Cafeteria / Kitchen due to excessive capacity","McFatter Technical Center",{"$nulls":4},2921351,2921351]
[1291,"New Media Center due to excessive capacity","McFatter Technical Center",{"$nulls":4},2223527,2223527]
[1291,"ESOL Modulars--5 Yr Loan","McFatter Voc-Tech Center",284603,{"$nulls":4},284603]
[841,"Phase III of III","McNab Elementary",5730654,"","","","",5730654]
[841,"Remodel Media Center to expand for excessive capacity","McNab Elementary",{"$nulls":4},705759,705759]
[761,"Existing Project","Meadowbrook Elementary",5173261,"","","","",5173261]
[3881,"Land","Middle School \"NN\"",3000443,"","","","",3000443]
[3881,"New Middle School \"NN\"","Middle School \"NN\"",2638991,{"$nulls":4},2638991]
[30005,"New School (south central-west)","Middle School \"NN\"",2638991,24125654,"","","",26764645]
[30006,"New School (southwest)","Middle School \"OO\"",2676465,24088180,"","","",26764645]
["TBA","New School","Middle School \"PP\"",{"$nulls":4},30863700,30863700]
["TBA","New School","Middle School \"QQ\"",{"$nulls":4},30863700,30863700]
["TBA","New School","Middle School \"RR\"",{"$nulls":4},30863700,30863700]
[30015,"New School - Design","Middle School (Area D #1)",null,"",2310000,"","",2310000]
[3772,"New School Middle \"II\"","Millenium Middle II",886462,{"$nulls":4},886462]
[4772,"New School Middle \"II\"","Millenium Middle II",10000,{"$nulls":4},10000]
[1751,"Classroom Addition","Miramar High",9113284,"","","","",9113284]
[1751,"New Cafeteria / Kitchen due to excessive capacity","Miramar High",{"$nulls":4},5646395,5646395]
[1841,"Remodel Existing Space to 4 Classrooms","Mirror Lake Elementary",{"$nulls":4},760725,760725]
[3541,"New School (Coconut Creek)","Monarch High School (\"GGG\")",7855848,"","","","",7855848]
[2691,"New Media Center due to excessive capacity","Morrow Elementary",{"$nulls":4},2664888,2664888]
[3811,"Site Acquisition ","N Area Alternative High School",3000301,{"$nulls":4},3000301]
[3581,"New Elementary","New Elementary",10382548,{"$nulls":4},10382548]
[3661,"New Elementary","New Elementary",9069456,{"$nulls":4},9069456]
[3611,"Construction Middle \"LL\"","New Relief",1193294,{"$nulls":4},1193294]
[3671,"New School Middle \"MM\"","New Renaissance Mid \"MM\"",415181,{"$nulls":4},415181]
[2671,"Classroom Addition","Nob Hill Elementary",1529643,"","","","",1529643]
[561,"New Media Center due to excessive capacity","Norcrest Elementary",{"$nulls":4},2538085,2538085]
[561,"Phased Replacement","Norcrest Elementary",832025,6572016,"","","",7404041]
[521,"Classroom Addition","North Andrews Gardens Elementary",647440,"","","","",647440]
[521,"Phased Replacement ","North Andrews Gardens Elementary",15805525,"","","","",15805525]
[3811,"New school","North Area Alternative High",12729282,"","","","",12729282]
[9384,"North Area Superintendent Remodel/Renovation","North Central Superintendent ",799828,{"$nulls":4},799828]
[1191,"Classroom Addition","North Fork Elementary",2170577,"","","","",2170577]
[1191,"Remodel Cafeteria / Kitchen to expand for excessive capacity","North Fork Elementary",{"$nulls":4},733379,733379]
[2231,"New Media Center due to excessive capacity","North Lauderdale Elementary",{"$nulls":4},2451582,2451582]
[2231,"Class Size Reduction","North Lauderdale Elementary ",774436,{"$nulls":4},774436]
[41,"Land - Purchase Chuch Property","North Side Elementary ",1234700,{"$nulls":4},1234700]
[41,"New Kitchen/Cafeteria","North Side Elementary ",1466857,{"$nulls":4},1466857]
[1241,"Classroom Addition","Northeast High",null,"",2237565,"","",2237565]
[90001,"Land","Northwest Bus Lot/Maintenance Facility",3750000,3750000,"","","",7500000]
[1282,"Classroom Addition","Nova Blanche Forman Elementary",612663,"","","","",612663]
[1282,"New Cafeteria / Kitchen due to excessive capacity","Nova Blanche Forman Elementary",{"$nulls":4},3879556,3879556]
[1271,"Classroom Addition","Nova Eisenhower Elementary",719196,"","","","",719196]
[1271,"New Cafeteria / Kitchen due to excessive capacity","Nova Eisenhower Elementary",{"$nulls":4},3872247,3872247]
[1281,"Classroom Addition","Nova High",5299838,"","","","",5299838]
[1281,"New Media Center due to excessive capacity","Nova High",{"$nulls":4},3510500,3510500]
[1281,"Stadium Design","Nova High",147712,"","","","",147712]
[1311,"Classroom Addition","Nova Middle",38582,"","","","",38582]
[31,"Classroom Addition","Oakland Park Elementary",1461009,"","","","",1461009]
[31,"Site Acquisition ","Oakland Park Elementary ",1433214,{"$nulls":4},1433214]
[461,"Phased Replacement","Oakridge Elementary",null,"",770792,6937128,"",7707920]
[472,"Renovation","Olsen Middle Annex",7819884,"","","","",7819884]
[711,"Phased Replacement","Orange Brook Elementary",8146401,"","","","",8146401]
[1831,"Class Size Reduction","Oriole Elementary ",1337679,{"$nulls":4},1337679]
[3311,"Classroom Addition","Palm Cove Elementary",1779131,"","","","",1779131]
[3761,"New School \"X\"","Park Lakes Elementary-X",635196,{"$nulls":4},635196]
[1951,"Classroom Addition","Park Ridge Elementary",1079586,"","","","",1079586]
[1951,"Expand Kitchen / Dining / Multipurpose / Stage","Park Ridge Elementary",{"$nulls":4},1336431,1336431]
[3171,"Classroom Addition","Park Springs Elementary",null,972573,"","","",972573]
[3781,"New School \"D-6\" ","Park Trails Elementary",836927,{"$nulls":4},836927]
[701,"New Cafeteria / Kitchen due to excessive capacity","Parkway Middle",{"$nulls":4},4837924,4837924]
[701,"New Media Center due to excessive capacity","Parkway Middle",{"$nulls":4},3682287,3682287]
[2071,"Classroom Addition","Pasadena Lakes Elementary",963598,"","","","",963598]
[1631,"Classroom Addition","Perry, Annabel Elementary",3478345,"","","","",3478345]
[1011,"Remodel Media Center to expand for excessive capacity","Perry, Henry D. Middle",{"$nulls":4},943608,943608]
[931,"Classroom Addition & Renovation","Peters Elementary",5650312,"","","","",5650312]
[653,"Classroom Addition","Pine Ridge Alternative Center",8404799,"","","","",8404799]
[2861,"6 Classroom Addition","Pines Lakes Elementary ",587679,{"$nulls":4},587679]
[1881,"Replacement       ","Pines Middle",22053116,"","","","",22053116]
[1881,"Land ","Pines Middle ",298,{"$nulls":4},298]
[2811,"New Media Center due to excessive capacity","Pinewood Elementary",{"$nulls":4},2677723,2677723]
[2811,"Class Size Reduction ","Pinewood Elementary ",81880,{"$nulls":4},81880]
[2571,"New Media Center due to excessive capacity","Pioneer Middle",{"$nulls":4},2777936,2777936]
[1901,"New Cafeteria / Kitchen due to excessive capacity","Piper High",{"$nulls":4},7707614,7707614]
[1901,"New Media Center due to excessive capacity","Piper High",{"$nulls":4},5717975,5717975]
[1901,"Classroom Addition","Piper High ",2837925,{"$nulls":4},2837925]
[1901,"Modular Portables ","Piper High ",18420,{"$nulls":4},18420]
[3691,"New School ","Plantation Elem Replace Site ",18939,{"$nulls":4},18939]
[1451,"Existing Project","Plantation High",3055886,"","","","",3055886]
[1451,"24 Classroom Addition ","Plantation High ",458785,{"$nulls":4},458785]
[1451,"General Renovation/Addition  Phase II","Plantation High ",7166676,{"$nulls":4},7166676]
[551,"Classroom Addition","Plantation Middle",7616719,"","","","",7616719]
[551,"Expand Kitchen","Plantation Middle",{"$nulls":4},975303,975303]
[9380,"Plantation Middle - PAL Parking Lot","Plantation Middle Exchange-PAL",13746,{"$nulls":4},13746]
[1251,"Site Improvement ","Plantation Park Elementary ",19681,{"$nulls":4},19681]
[9018,"Convert to International Studies","Pompano Admin Site ",102843,{"$nulls":4},102843]
[181,"Phased Replacement ","Pompano Beach HS",12558244,{"$nulls":4},12558244]
[21,"Classroom Addition","Pompano Beach Middle",4883963,"","","","",4883963]
[21,"Phased Replacement","Pompano Beach Middle",null,"",674443,6069987,"",6744430]
[9606,"Facilities Div. Consolidation ","Property Mgmt/Site Acquisition",9000000,{"$nulls":4},9000000]
[9606,"New Middle School \"OO\"","Property Mgmt/Site Acquisition",2638991,{"$nulls":4},2638991]
[2721,"Remodel Existing Space to 4 Classrooms","Ramblewood Elementary",{"$nulls":4},760725,760725]
[2721,"4 Classroom Addition ","Ramblewood Elementary ",586028,{"$nulls":4},586028]
[2711,"Classroom Addition","Ramblewood Middle",2505000,"","","","",2505000]
[2711,"Expand Multipurpose","Ramblewood Middle",{"$nulls":4},1833627,1833627]
[151,"4 Classroom Addition","Riverland Elementary",{"$nulls":4},891135,891135]
[151,"New Media Center due to excessive capacity","Riverland Elementary",{"$nulls":4},2658008,2658008]
[3031,"New Cafeteria / Kitchen due to excessive capacity","Riverside Elementary",{"$nulls":4},3887081,3887081]
[3031,"6 Classroom Addition ","Riverside Elementary ",743797,{"$nulls":4},743797]
[1851,"Classroom Addition & Cafeteria / Kitchen / Multipurpose area / Stage","Royal Palm Elementary",3714264,"","","","",3714264]
[1851,"Expand Media","Royal Palm Elementary",{"$nulls":4},909390,909390]
[9335,"Site Acquisition ","S/W Bus Parking Facilities ",1444464,{"$nulls":4},1444464]
[9005,"Hospital Homebound Program","Sailboat Bend Complex ",11206,{"$nulls":4},11206]
[891,"Class Size Reduction ","Sanders Park Elementary ",116146,{"$nulls":4},116146]
[3061,"Classroom Addition","Sandpiper Elementary",1386384,"","","","",1386384]
[3431,"Remodel Media Center to expand for excessive capacity","Sawgrass Springs Middle",{"$nulls":4},915271,915271]
[601,"Classroom Addition and General Renovations","Seagull School",null,2835703,"","","",2835703]
[601,"Hospital Homebound Prog. Move ","Seagull School ",207739,{"$nulls":4},207739]
[1891,"Expand Kitchen","Seminole Middle",{"$nulls":4},625832,625832]
[1891,"New Media Center due to excessive capacity","Seminole Middle",{"$nulls":4},2577404,2577404]
[1811,"Class Size Reduction ","Sheridan Hills Elementary ",16480,{"$nulls":4},16480]
[1321,"Classroom Addition and Cafeteria Replacement","Sheridan Park Elementary",6166616,"","","","",6166616]
[2971,"12 Classroom/Addition","Silver Lakes Middle",2628749,"","","","",2628749]
[2971,"New Media Center due to excessive capacity","Silver Lakes Middle",{"$nulls":4},2606895,2606895]
[3491,"Class Size Reduction ","Silver Palms Elementary ",14585,{"$nulls":4},14585]
[171,"Replacement School ","South Broward High ",8674925,{"$nulls":4},8674925]
[171,"Site Acquisition ","South Broward High ",1094613,{"$nulls":4},1094613]
[2351,"Classroom Addition","South Plantation High",17037919,"","","","",17037919]
[2351,"New Cafeteria / Kitchen due to excessive capacity","South Plantation High",{"$nulls":4},5842704,5842704]
[2351,"Remodel Media Center to expand for excessive capacity","South Plantation High",{"$nulls":4},1542213,1542213]
[691,"Classroom Addition","Stirling Elementary",972190,"","","","",972190]
[3011,"Stadium Design","Stoneman Douglas High",150000,"","","","",150000]
[211,"Classroom Addition","Stranahan High",1945147,"","","","",1945147]
[211,"New Cafeteria / Kitchen due to excessive capacity","Stranahan High",{"$nulls":4},5543077,5543077]
[211,"New Media Center due to excessive capacity","Stranahan High",{"$nulls":4},4112190,4112190]
[211,"Medical Magnet Addition ","Stranahan High ",79095,{"$nulls":4},79095]
[211,"Science Magnet Addition ","Stranahan High ",12778,{"$nulls":4},12778]
[611,"Site Aquisition ","Sunland Park Elementary ",914672,{"$nulls":4},914672]
[1171,"8 Classroom Addition","Sunshine Elementary ",661927,{"$nulls":4},661927]
[2621,"Classroom Building ","Tamarac Elementary ",1040799,{"$nulls":4},1040799]
[2751,"New Cafeteria / Kitchen due to excessive capacity","Taravella J P High",{"$nulls":4},7358911,7358911]
[2751,"New Media Center due to excessive capacity","Taravella J P High",{"$nulls":4},5459286,5459286]
[2751,"24 Classroom Addition ","Taravella J P High ",974879,{"$nulls":4},974879]
[571,"Classroom Addition / Replacement","Tedder Elementary",7715704,"","","","",7715704]
[571,"Class Size Reduction ","Tedder Elementary ",1969299,{"$nulls":4},1969299]
[571,"Site Acquisition ","Tedder Elementary ",780019,{"$nulls":4},780019]
[731,"New Media Center due to excessive capacity","Tropical Elementary",{"$nulls":4},2672207,2672207]
[731,"4 Classroom Addition-Driveway ","Tropical Elementary ",293521,{"$nulls":4},293521]
[9077,"2 Modular Units","Twin Lakes Complex ",200000,{"$nulls":4},200000]
[1621,"Joint Project with City of Sunrise","Village Elementary",950000,"","","","",950000]
[1621,"Classroom Bldg","Village Elementary ",258356,{"$nulls":4},258356]
[321,"Classroom Addition","Walker Elementary",3852162,"","","","",3852162]
[511,"Remodel Media Center to expand for excessive capacity","Watkins Elementary",{"$nulls":4},780009,780009]
[2881,"Classroom Addition","Welleby Elementary",957334,"","","","",957334]
[2681,"New Kitchen / Dining / Multipurpose / Stage","Westchester Elementary",{"$nulls":4},4239319,4239319]
[2681,"New Media Center due to excessive capacity","Westchester Elementary",{"$nulls":4},2663741,2663741]
[2681,"8 Classroom Addition ","Westchester Elementary ",1205265,{"$nulls":4},1205265]
[2831,"Classroom Addition","Western High",12319672,"","","","",12319672]
[2831,"New Media Center due to excessive capacity","Western High",{"$nulls":4},3684873,3684873]
[631,"New Media Center due to excessive capacity","Westwood Heights Elementary",{"$nulls":4},2677013,2677013]
[631,"Phased Replacement ","Westwood Heights Elementary ",29520,{"$nulls":4},29520]
[631,"Site Acquisition ","Westwood Heights Elementary ",230000,{"$nulls":4},230000]
[412,"Remodel Media Center to expand for excessive capacity","Whiddon-Rogers Annex",{"$nulls":4},227285,227285]
[452,"12 Classroom Addition ","Whiddon-Rogers Ed Center",6163882,"","","","",6163882]
[191,"Phased Replace/Covered Walkway","Wilton Manors Elementary ",1580677,{"$nulls":4},1580677]
[3091,"Classroom Addition","Winston Park Elementary",2906405,"","","","",2906405]
[3001,"New Cafeteria / Kitchen due to excessive capacity","Young, Walter C. Middle",{"$nulls":4},3567096,3567096]
[{"$nulls":8},0]
["2b2","Broward Total",null,818920924,128619638,115495571,80911338,527510218,1671457689]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2b2a","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2003-04 FISH Satisfactory","Actual 2003-04","Actual 2002-03","Actual 2003-04","New Stu Capacity to","Projected 2007-08","Projected 2007-08"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[1631,"Annabel C Perry Elementary",850,850,787,0.93,228,821,0.76]
[1791,"Apollo Middle",1767,1590.3,1475,0.93,277.2,1572,0.84]
[4702,"Arthur Robert Ashe, Jr Middle",1574,1416.6,1111,0.78,0,1303,0.92]
[2511,"Atlantic West Elementary",1005,1005,1017,1.01,152,1131,0.98]
[343,"Attucks Middle",1697,1527.3,673,0.44,0,642,0.42]
[2611,"Bair Middle",2104,1893.6,1676,0.89,237.6,1804,0.85]
[2001,"Banyan Elementary",950,950,1002,1.05,152,885,0.8]
[641,"Bayview Elementary",670,670,636,0.95,0,682,1.02]
[201,"Bennett Elementary",645,645,450,0.7,0,556,0.86]
[361,"Blanche Ely Senior High",3197,3037.15,2792,0.92,315,3017,0.9]
[971,"Boulevard Heights Elementary",1003,1003,977,0.97,0,842,0.84]
[1741,"Boyd H Anderson Senior High",3423,3251.85,2691,0.83,0,2761,0.85]
[871,"Bright Horizons",291,291,148,0.51,0,148,0.51]
[811,"Broadview Elementary",1097,1097,974,0.89,38,1101,0.97]
[501,"Broward Estates Elementary",968,968,725,0.75,38,900,0.89]
[1461,"Castle Hill Elementary",967,967,738,0.76,76,788,0.76]
[1382,"Castle Hill Elementary Annex",436,436,752,1.72,0,752,1.72]
[2641,"Central Park Elementary",1084,1084,1157,1.07,304,1055,0.76]
[3771,"Challenger Elementary",1085,1085,1126,1.04,0,1113,1.03]
[2961,"Chapel Trail Elementary",1380,1380,1309,0.95,0,1335,0.97]
[3391,"Charles W Flanagan Senior High",3811,3620.45,3701,1.02,0,3337,0.92]
[1421,"Coconut Creek Elementary",1026,1026,868,0.85,0,764,0.74]
[1681,"Coconut Creek Senior High",2693,2558.35,2533,0.99,0,2636,1.03]
[3741,"Coconut Palm Elementary",1288,1288,1349,1.05,0,2151,1.67]
[231,"Colbert Elementary",966,966,702,0.73,152,697,0.62]
[331,"Collins Elementary",437,437,359,0.82,0,425,0.97]
[1211,"Cooper City Elementary",987,987,1016,1.03,0,1130,1.14]
[1931,"Cooper City Senior High",2517,2391.15,2471,1.03,270,2603,0.98]
[3041,"Coral Park Elementary",918,918,895,0.97,38,792,0.83]
[2551,"Coral Springs Elementary",863,863,902,1.05,114,874,0.89]
[2561,"Coral Springs Middle",1736,1562.4,1090,0.7,158.4,1096,0.64]
[1151,"Coral Springs Senior High",2954,2806.3,2935,1.05,540,3065,0.92]
[3111,"Country Hills Elementary",1161,1161,1290,1.11,180,1255,0.94]
[2981,"Country Isles Elementary",977,977,955,0.98,114,817,0.75]
[901,"Cresthaven Elementary",865,865,826,0.95,38,888,0.98]
[221,"Croissant Park Elementary",1036,1036,796,0.77,0,884,0.85]
[3222,"Cross Creek School",211,211,166,0.79,0,166,0.79]
[1871,"Crystal Lake Middle",2140,1926,1767,0.92,118.8,1808,0.88]
[3623,"Cypress Bay Senior High",4888,4643.6,4270,0.92,540,4995,0.96]
[1781,"Cypress Elementary",880,880,787,0.89,76,847,0.89]
[2123,"Cypress Run Alternative Exceptional Center",180,180,123,0.68,0,123,0.68]
[101,"Dania Elementary",856,856,703,0.82,0,818,0.96]
[3651,"Dave Thomas Education Center",233,233,589,2.53,0,598,2.57]
[2801,"Davie Elementary",1030,1030,978,0.95,76,985,0.89]
[11,"Deerfield Beach Elementary",985,985,889,0.9,0,1003,1.02]
[911,"Deerfield Beach Middle",2201,1980.9,1725,0.87,118.8,1761,0.84]
[1711,"Deerfield Beach Senior High",3521,3344.95,2795,0.84,135,2912,0.84]
[391,"Deerfield Park Elementary",977,977,761,0.78,0,788,0.81]
[271,"Dillard Elementary",975,975,650,0.67,0,602,0.62]
[371,"Dillard Senior High",3277,3113.15,2148,0.69,0,1895,0.61]
[3221,"Drew Elementary",725,725,541,0.75,0,510,0.7]
[721,"Driftwood Elementary",1038,1038,764,0.74,0,772,0.74]
[861,"Driftwood Middle",2385,2146.5,1919,0.89,0,1662,0.77]
[1271,"Dwight D Eisenhower Elementary",995,995,1019,1.02,0,1000,1.01]
[3461,"Eagle Point Elementary",1219,1219,1374,1.13,76,1322,1.02]
[3441,"Eagle Ridge Elementary",1100,1100,1113,1.01,0,1141,1.04]
[3191,"Embassy Creek Elementary",982,982,1038,1.06,0,978,1]
[3301,"Endeavour Primary Learning Center",584,584,264,0.45,0,389,0.67]
[2942,"Everglades Elementary",1337,1337,1178,0.88,76,1183,0.84]
[3731,"Everglades Senior High",2976,2827.2,2374,0.84,0,3171,1.12]
[1641,"Fairway Elementary",1057,1057,1005,0.95,0,1032,0.98]
[3622,"Falcon Cove Middle",2858,2572.2,2649,1.03,0,2866,1.11]
[2541,"Flamingo Elementary",877,877,856,0.98,114,859,0.87]
[851,"Floranada Elementary",1085,1085,869,0.8,0,890,0.82]
[3051,"Forest Glen Middle",1677,1509.3,1312,0.87,79.2,1388,0.87]
[2631,"Forest Hills Elementary",857,857,818,0.95,0,973,1.14]
[951,"Fort Lauderdale Senior High",2706,2570.7,1795,0.7,0,1860,0.72]
[3531,"Fox Trail Elementary",1245,1245,1274,1.02,114,1397,1.03]
[3642,"Gator Run Elementary",1567,1567,1347,0.86,0,1392,0.89]
[2851,"Griffin Elementary",847,847,790,0.93,0,856,1.01]
[131,"Hallandale Elementary",1120,1120,1246,1.11,0,1521,1.36]
[403,"Hallandale Senior High",1930,1833.5,1618,0.88,0,1661,0.91]
[491,"Harbordale Elementary",490,490,460,0.94,0,479,0.98]
[3131,"Hawkes Bluff Elementary",1134,1134,1135,1,114,1103,0.88]
[1011,"Henry D Perry Middle",1882,1693.8,1465,0.86,158.4,1626,0.88]
[121,"Hollywood Central Elementary",1109,1109,1019,0.92,0,1240,1.12]
[111,"Hollywood Hills Elementary",843,843,909,1.08,228,938,0.88]
[1661,"Hollywood Hills Senior High",2367,2248.65,2406,1.07,540,2800,1]
[1761,"Hollywood Park Elementary",776,776,651,0.84,76,855,1]
[2531,"Horizon Elementary",920,920,1032,1.12,0,979,1.06]
[3471,"Indian Ridge Middle",2292,2062.8,2165,1.05,0,2333,1.13]
[3181,"Indian Trace Elementary",1167,1167,941,0.81,0,835,0.72]
[2751,"J P Taravella Senior High",3665,3481.75,3436,0.99,0,3832,1.1]
[1971,"James S Hunt Elementary",891,891,951,1.07,38,1072,1.15]
[2121,"James S Rickards Middle",1441,1296.9,1066,0.82,158.4,1154,0.79]
[3861,"JJJ High School",2254,2141.3,0,0,0,2000,0.93]
[831,"Lake Forest Elementary",1175,1175,862,0.73,0,810,0.69]
[3591,"Lakeside Elementary",1057,1057,1049,0.99,152,1036,0.86]
[405,"Lanier-James Education Center",225,225,229,1.02,0,229,1.02]
[621,"Larkdale Elementary",944,944,533,0.56,0,551,0.58]
[1701,"Lauderdale Lakes Middle",1513,1361.7,1012,0.74,39.6,1199,0.86]
[431,"Lauderdale Manors Elementary",959,959,777,0.81,0,767,0.8]
[1391,"Lauderhill Middle",1622,1459.8,1074,0.74,118.8,1301,0.82]
[1381,"Lauderhill-Paul Turner Elementary",1100,1100,866,0.79,0,888,0.81]
[3821,"Liberty Elementary",1120,1120,1110,0.99,76,1266,1.06]
[1091,"Lloyd Estates Elementary",807,807,634,0.79,0,635,0.79]
[3101,"Lyons Creek Middle",2239,2015.1,2061,1.02,237.6,2076,0.92]
[3841,"Manatee Bay Elementary",1120,1120,1161,1.04,0,1159,1.03]
[2741,"Maplewood Elementary",992,992,939,0.95,114,1005,0.91]
[1161,"Margate Elementary",1157,1157,1089,0.94,0,984,0.85]
[581,"Margate Middle",1892,1702.8,1274,0.75,0,1331,0.78]
[1611,"Martin Luther King Elementary",1108,1108,776,0.7,57,742,0.64]
[341,"Mary M Bethune Elementary",1221,1221,1027,0.84,133,994,0.73]
[241,"McArthur Senior High",3602,3421.9,2575,0.75,0,2777,0.81]
[841,"McNab Elementary",1096,1096,723,0.66,0,614,0.56]
[481,"McNicol Middle",1900,1710,1635,0.96,0,1756,1.03]
[761,"Meadowbrook Elementary",784,784,639,0.82,513,726,0.56]
[4772,"Millennium Middle",1592,1432.8,1516,1.06,158.4,1599,1]
[531,"Miramar Elementary",908,908,840,0.93,19,862,0.93]
[1751,"Miramar Senior High",2733,2596.35,2734,1.05,540,2919,0.93]
[1841,"Mirror Lake Elementary",962,962,740,0.77,0,767,0.8]
[3541,"Monarch Senior High",1607,1526.65,1040,0.68,0,1790,1.17]
[2691,"Morrow Elementary",906,906,850,0.94,76,1088,1.11]
[3911,"New Renaissance Middle",1990,1791,1679,0.94,0,1775,0.99]
[881,"New River Middle",2098,1888.2,1576,0.83,0,1643,0.87]
[2671,"Nob Hill Elementary",842,842,883,1.05,152,826,0.83]
[561,"Norcrest Elementary",1299,1299,831,0.64,0,836,0.64]
[521,"North Andrews Gardens Elementary",1416,1416,855,0.6,0,869,0.61]
[1191,"North Fork Elementary",831,831,544,0.65,0,621,0.75]
[2231,"North Lauderdale Elementary",1292,1292,1086,0.84,19,1049,0.8]
[41,"North Side Elementary",804,804,506,0.63,0,514,0.64]
[1241,"Northeast Senior High",2129,2022.55,2184,1.08,270,2171,0.95]
[1282,"Nova Blanche Forman Elementary",1030,1030,958,0.93,0,966,0.94]
[1311,"Nova Middle",1705,1534.5,1536,1,336.6,1500,0.8]
[1281,"Nova Senior High",2392,2272.4,2043,0.9,270,2100,0.83]
[31,"Oakland Park Elementary",696,696,673,0.97,228,571,0.62]
[461,"Oakridge Elementary",780,780,880,1.13,532,894,0.68]
[471,"Olsen Middle",2229,2006.1,2010,1,0,2144,1.07]
[711,"Orange Brook Elementary",791,791,852,1.08,0,834,1.05]
[1831,"Oriole Elementary",963,963,827,0.86,0,727,0.75]
[3311,"Palm Cove Elementary",1029,1029,1124,1.09,228,943,0.75]
[1131,"Palmview Elementary",689,689,634,0.92,76,739,0.97]
[3571,"Panther Run Elementary",1109,1109,952,0.86,0,835,0.75]
[3761,"Park Lakes Elementary",1085,1085,1205,1.11,19,1338,1.21]
[1951,"Park Ridge Elementary",903,903,662,0.73,114,788,0.77]
[3171,"Park Springs Elementary",875,875,968,1.11,114,1145,1.16]
[3781,"Park Trails Elementary",1210,1210,1139,0.94,76,1528,1.19]
[3631,"Parkside Elementary",1160,1160,1132,0.98,0,1112,0.96]
[701,"Parkway Middle",2414,2172.6,1864,0.86,158.4,2112,0.91]
[2071,"Pasadena Lakes Elementary",930,930,881,0.95,114,1063,1.02]
[2661,"Pembroke Lakes Elementary",899,899,841,0.94,0,818,0.91]
[1221,"Pembroke Pines Elementary",867,867,850,0.98,114,841,0.86]
[931,"Peters Elementary",953,953,863,0.91,152,766,0.69]
[653,"Pine Ridge Center",196,196,173,0.88,0,173,0.88]
[2861,"Pines Lakes Elementary",968,968,1020,1.05,0,958,0.99]
[1881,"Pines Middle",1762,1585.8,1452,0.92,1010,1295,0.5]
[2811,"Pinewood Elementary",1149,1149,1044,0.91,76,1156,0.94]
[2571,"Pioneer Middle",1921,1728.9,1761,1.02,158.4,1679,0.89]
[1901,"Piper Senior High",4266,4052.7,3433,0.85,0,3676,0.91]
[941,"Plantation Elementary",1085,1085,863,0.8,0,746,0.69]
[551,"Plantation Middle",1318,1186.2,1336,1.13,475.2,1274,0.77]
[1251,"Plantation Park Elementary",701,701,598,0.85,0,558,0.8]
[1451,"Plantation Senior High",3364,3195.8,3040,0.95,270,3105,0.9]
[751,"Pompano Beach Elementary",779,779,678,0.87,0,645,0.83]
[185,"Pompano Beach Institute Of International Studies",1581,1581,862,0.55,0,1500,0.95]
[21,"Pompano Beach Middle",1509,1358.1,1215,0.89,158.4,1161,0.77]
[3121,"Quiet Waters Elementary",1157,1157,1125,0.97,114,1174,0.92]
[2721,"Ramblewood Elementary",973,973,1035,1.06,0,1087,1.12]
[2711,"Ramblewood Middle",1928,1735.2,1574,0.91,237.6,1423,0.72]
[2891,"Riverglades Elementary",921,921,1047,1.14,0,1127,1.22]
[151,"Riverland Elementary",840,840,683,0.81,38,772,0.88]
[3031,"Riverside Elementary",1044,1044,903,0.86,0,818,0.78]
[1671,"Robert C Markham Elementary",788,788,679,0.86,57,757,0.9]
[3701,"Rock Island Elementary",795,795,713,0.9,0,593,0.75]
[1851,"Royal Palm Elementary",1608,1608,1055,0.66,38,802,0.49]
[891,"Sanders Park Elementary",1005,1005,624,0.62,38,785,0.75]
[3061,"Sandpiper Elementary",994,994,930,0.94,152,955,0.83]
[3401,"Sawgrass Elementary",1028,1028,1032,1,76,1178,1.07]
[3431,"Sawgrass Springs Middle",1689,1520.1,1330,0.87,0,1057,0.7]
[2871,"Sea Castle Elementary",942,942,942,1,0,1163,1.23]
[601,"Seagull School",1064,1064,426,0.4,0,426,0.4]
[1891,"Seminole Middle",1789,1610.1,1364,0.85,0,1365,0.85]
[1811,"Sheridan Hills Elementary",700,700,717,1.02,0,779,1.11]
[1321,"Sheridan Park Elementary",1103,1103,846,0.77,0,684,0.62]
[3371,"Silver Lakes Elementary",1085,1085,1025,0.94,0,1020,0.94]
[2971,"Silver Lakes Middle",1552,1396.8,1184,0.85,0,1169,0.84]
[3491,"Silver Palms Elementary",1207,1207,1169,0.97,228,1286,0.9]
[3081,"Silver Ridge Elementary",1038,1038,1079,1.04,114,1065,0.92]
[3581,"Silver Shores Elementary",1161,1161,1220,1.05,0,1038,0.89]
[3331,"Silver Trail Middle",2662,2395.8,2423,1.01,0,2607,1.09]
[171,"South Broward Senior High",2834,2692.3,2429,0.9,0,2565,0.95]
[2351,"South Plantation Senior High",2782,2642.9,2638,1,270,3044,1.05]
[921,"Stephen Foster Elementary",806,806,727,0.9,114,761,0.83]
[691,"Stirling Elementary",898,898,877,0.98,114,914,0.9]
[3011,"Stoneman Douglas Senior High",4398,4178.1,4373,1.05,0,5169,1.24]
[211,"Stranahan Senior High",2529,2402.55,2236,0.93,270,2208,0.83]
[611,"Sunland Park Elementary",673,673,441,0.66,0,381,0.57]
[251,"Sunrise Middle",1866,1679.4,1468,0.87,0,1442,0.86]
[3661,"Sunset Lakes Elementary",1120,1120,890,0.79,0,1002,0.89]
[422,"Sunset Learning Center",305,305,147,0.48,0,147,0.48]
[1171,"Sunshine Elementary",959,959,1042,1.09,114,1045,0.97]
[2621,"Tamarac Elementary",1146,1146,1250,1.09,0,1402,1.22]
[571,"Tedder Elementary",781,781,866,1.11,228,759,0.75]
[3151,"Tequesta Trace Middle",1869,1682.1,1725,1.03,158.4,1572,0.85]
[1021,"The Quest Center",263,263,116,0.44,0,116,0.44]
[3291,"Thurgood Marshall Elementary",986,986,665,0.67,0,595,0.6]
[3481,"Tradewinds Elementary",1199,1199,1083,0.9,76,1109,0.87]
[731,"Tropical Elementary",959,959,960,1,0,843,0.88]
[1621,"Village Elementary",1284,1284,1014,0.79,76,1105,0.81]
[3321,"Virginia Shuman Young Elementary",848,848,831,0.98,0,838,0.99]
[321,"Walker Elementary (Magnet)",1154,1154,947,0.82,304,899,0.62]
[3001,"Walter C Young Middle",2365,2128.5,1841,0.86,237.6,1934,0.82]
[511,"Watkins Elementary",1105,1105,943,0.85,0,870,0.79]
[2881,"Welleby Elementary",962,962,1023,1.06,114,1135,1.05]
[161,"West Hollywood Elementary",840,840,890,1.06,76,1022,1.12]
[2681,"Westchester Elementary",1350,1350,1235,0.91,114,1418,0.97]
[2831,"Western Senior High",2342,2224.9,2266,1.02,540,2430,0.88]
[3871,"Westglades Middle",1990,1791,1801,1.01,0,2132,1.19]
[2052,"Westpine Middle",1729,1556.1,1492,0.96,118.8,1422,0.85]
[631,"Westwood Heights Elementary",1000,1000,790,0.79,0,923,0.92]
[452,"Whiddon-Rogers Education Center",1773,1773,1323,0.75,0,1323,0.75]
[1752,"Whispering Pines Exceptional Education Center",166,166,274,1.65,0,274,1.65]
[1071,"William Dandy Middle",1847,1662.3,1381,0.83,0,996,0.6]
[191,"Wilton Manors Elementary",845,845,652,0.77,0,865,1.02]
[991,"Wingate Oaks Center",304,304,92,0.3,0,92,0.3]
[3091,"Winston Park Elementary",1223,1223,1273,1.04,152,1493,1.09]
[]
["2b2a","Broward Total",298103,286570.74999999994,257458,0.9,17783.6,271232,0.89]
[]
["2b2a1","Necessary offsite infrastructure requirements resulting from expansions or new schools.  "]
[null,"This section should include the same project information from 2b2."]
[null,"TBD"]
[]
[]
[]
["2b2b","Proposed location of planned facilities, whether those locations are consistent with the comprehensive plans of all affected local governments, and "]
[null,"recommendations for infrastructure and other improvements to land adjacent to existing facilities. Provisions of 1013.33(12), (13), and (14) and 1013.36"]
[null," must be addressed for new facilities planned within the 1st 3 years  of the plan"]
[null,"Consistent with Comp Plan?","Description"]
[null,"Yes"]
{"$rows_empty":66}
[{"$nulls":6},"# of Units","Projected "]
["2b2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2003-04","Owner","Student Stations","as classroom space","in 2007-08","units by 2007-08","Column \"C\""]
[1741,"ANDERSON, BOYD H. HIGH",6,"SBBC",162,5,0,6,235]
[1791,"APOLLO MIDDLE",7,"SBBC",239,2,0,7,143]
[2221,"ATLANTIC VOCATIONAL CENTER",13,"SBBC",397,10,2,11,363]
[2511,"ATLANTIC WEST ELEMENTARY",8,"SBBC",292,2,1,7,159]
[343,"ATTUCKS MIDDLE",0,"SBBC",0,0,0,0,0]
[2611,"BAIR MIDDLE",2,"Space Master",104,0,2,0,26]
[null,null,12,"SBBC",504,4,1,11,255]
[2001,"BANYAN ELEMENTARY",8,"SBBC",256,0,2,6,115]
[641,"BAYVIEW ELEMENTARY",0,"SBBC",0,0,0,0,0]
[201,"BENNETT ELEMENTARY",0,"SBBC",0,0,0,0,0]
[341,"BETHUNE, MARY M. ELEMENTARY",19,"SBBC",797,0,10,9,262]
[971,"BOULEVARD HEIGHTS ELEMENTARY",0,"SBBC",0,0,0,0,0]
[871,"BRIGHT HORIZONS CENTER",0,"SBBC",0,0,0,0,0]
[811,"BROADVIEW ELEMENTARY",4,"SBBC",152,3,0,4,112]
[501,"BROWARD ESTATES ELEMENTARY",7,"SBBC",279,0,5,2,93]
[1382,"CASTLE HILL ANNEX",0,"SBBC",0,0,0,0,0]
[1461,"CASTLE HILL ELEMENTARY",7,"SBBC",260,0,3,4,100]
[2641,"CENTRAL PARK ELEMENTARY",11,"SBBC",397,0,1,10,161]
[3771,"CHALLENGER ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2961,"CHAPEL TRAIL ELEMENTARY",11,"SBBC",370,3,7,4,172]
[1421,"COCONUT CREEK ELEMENTARY",3,"SBBC",114,1,0,3,61]
[1681,"COCONUT CREEK HIGH",11,"SBBC",498,9,1,10,418]
[3741,"COCONUT PALM ELEMENTARY",8,"SBBC",350,1,4,4,107]
[231,"COLBERT ELEMENTARY",7,"SBBC",419,3,2,5,177]
[331,"COLLINS ELEMENTARY",1,"SBBC",65,0,1,0,15]
[1211,"COOPER CITY ELEMENTARY",2,"SBBC",76,1,1,1,49]
[1931,"COOPER CITY HIGH",10,"SBBC",367,8,0,10,369]
[3041,"CORAL PARK ELEMENTARY",7,"SBBC",242,4,1,6,216]
[2551,"CORAL SPRINGS ELEMENTARY",2,"SBBC",70,0,1,1,31]
[1151,"CORAL SPRINGS HIGH",5,"SBBC",179,2,3,2,117]
[2561,"CORAL SPRINGS MIDDLE",1,"SBBC",37,1,0,1,44]
[3111,"COUNTRY HILLS ELEMENTARY",14,"SBBC",607,3,4,10,267]
[2981,"COUNTRY ISLES ELEMENTARY",7,"SBBC",260,1,2,5,121]
[901,"CRESTHAVEN ELEMENTARY",0,"SBBC",0,0,0,0,0]
[221,"CROISSANT PARK ELEMENTARY",5,"SBBC",228,3,2,3,52]
[3222,"CROSS CREEK SCHOOL",6,"SBBC",320,4,2,4,75]
[1871,"CRYSTAL LAKE MIDDLE",4,"SBBC",120,1,3,1,86]
[2913,"CYPRESS BAY HIGH ANNEX",31,"SBBC",951,11,7,24,640]
[3623,"CYPRESS BAY HIGH",5,"SBBC",214,0,2,3,54]
[1781,"CYPRESS ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2123,"CYPRESS RUN ALT CENTER",8,"SBBC",409,5,0,8,264]
[1071,"DANDY, WILLIAM  MIDDLE",10,"SBBC",300,7,0,10,314]
[101,"DANIA ELEMENTARY",4,"SBBC",152,1,1,3,69]
[2221,"DAVE THOMAS EDUCATION CENTER",9,"SBBC",282,7,0,9,340]
[2801,"DAVIE ELEMENTARY",4,"SBBC",102,2,0,4,56]
[11,"DEERFIELD BEACH ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1711,"DEERFIELD BEACH HIGH",9,"SBBC",462,4,2,7,246]
[911,"DEERFIELD BEACH MIDDLE",6,"SBBC",345,4,0,6,204]
[391,"DEERFIELD PARK ELEMENTARY",0,"SBBC",0,0,0,0,0]
[271,"DILLARD ELEMENTARY",2,"SBBC",76,0,2,0,21]
[371,"DILLARD HIGH",0,"SBBC",0,0,0,0,0]
[null,null,1,"GE/R",27,0,1,0,11]
[3221,"DREW, CHARLES ELEMENTARY",0,"SBBC",0,0,0,0,0]
[302,"DREW, CHARLES FAMILY RESOURCE CENTER ",8,"SBBC",507,1,8,0,115]
[null,"DREW RESOURCE TEEN PARENT PROGRAM",0,"SBBC",0,0,0,0,0]
[721,"DRIFTWOOD ELEMENTARY",9,"SBBC",342,3,4,5,215]
[861,"DRIFTWOOD MIDDLE",5,"SBBC",188,4,0,5,175]
[null,null,6,"Resun Leasing",310,0,5,1,73]
[null,null,11,"GE/R",597,0,7,4,137]
[3461,"EAGLE POINT ELEMENTARY",4,"SBBC",152,4,0,4,176]
[3441,"EAGLE RIDGE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[361,"ELY HIGH",8,"SBBC",327,5,0,8,231]
[null,null,2,"GE/R",78,0,0,2,25]
[3191,"EMBASSY CREEK ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2942,"EVERGLADES ELEMENTARY",1,"SBBC",37,0,1,0,5]
[3513,"EVERGLADES HIGH ANNEX",39,"SBBC",1230,9,30,9,619]
[3513,"EVERGLADES HIGH ANNEX AT SLVR LAKES",10,"SBBC",270,1,3,7,137]
[1641,"FAIRWAY ELEMENTARY",2,"SBBC",64,0,2,0,26]
[3622,"FALCON COVE MIDDLE",32,"SBBC",1027,8,18,14,566]
[2541,"FLAMINGO ELEMENTARY",4,"SBBC",323,0,1,3,52]
[3391,"FLANAGAN, CHARLES W. HIGH",10,"SBBC",357,3,7,3,147]
[851,"FLORANADA ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3051,"FOREST GLEN MIDDLE",3,"SBBC",90,0,0,3,42]
[2631,"FOREST HILLS ELEMENTARY",1,"SBBC",38,0,0,1,16]
[951,"FORT LAUDERDALE HIGH",15,"SBBC",465,3,8,7,223]
[921,"FOSTER, STEPHEN ELEMENTARY",2,"SBBC",127,1,0,2,34]
[3531,"FOX TRAIL ELEMENTARY",5,"SBBC",261,0,0,5,64]
[3642,"GATOR RUN ELEMENTARY",1,"SBBC",38,0,1,0,5]
[2851,"GRIFFIN ELEMENTARY",0,"SBBC",0,0,0,0,0]
[592,"HALLANDALE ADULT & COMMUNITY",18,"SBBC",351,9,18,0,247]
[131,"HALLANDALE ELEMENTARY",14,"SBBC",451,5,9,5,188]
[403,"HALLANDALE HIGH",0,"SBBC",0,0,0,0,0]
[491,"HARBORDALE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3131,"HAWKES BLUFF ELEMENTARY",7,"SBBC",260,2,3,4,143]
[102,"HOLLYWOOD CENTRAL ANNEX AT DANIA ELEM",10,"SBBC",320,0,10,0,10]
[121,"HOLLYWOOD CENTRAL ELEMENTARY",1,"SBBC",95,0,1,0,13]
[111,"HOLLYWOOD HILLS ELEMENTARY",14,"SBBC",444,1,9,5,192]
[1661,"HOLLYWOOD HILLS HIGH",12,"SBBC",354,7,2,10,319]
[1761,"HOLLYWOOD PARK ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2531,"HORIZON ELEMENTARY",3,"SBBC",64,2,1,2,39]
[1971,"HUNT, JAMES S. ELEMENTARY",1,"SBBC",32,0,1,0,16]
[3471,"INDIAN RIDGE MIDDLE",7,"SBBC",224,1,1,6,130]
[3181,"INDIAN TRACE ELEMENTARY",15,"SBBC",498,3,4,11,284]
[1611,"KING, MARTIN LUTHER ELEMENTARY",4,"SBBC",128,2,0,4,77]
[831,"LAKE FOREST ELEMENTARY",4,"SBBC",197,0,3,1,51]
[3591,"LAKESIDE ELEMENTARY",1,"SBBC",38,0,1,0,11]
[621,"LARKDALE ELEMENTARY",4,"SBBC",191,0,0,4,60]
[1701,"LAUDERDALE LAKES MIDDLE",5,"SBBC",150,3,1,4,143]
[431,"LAUDERDALE MANORS ELEMENTARY",1,"SBBC",38,0,0,1,13]
[1391,"LAUDERHILL MIDDLE",8,"SBBC",244,1,4,4,144]
[1381,"LAUDERHILL P. T.  ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1091,"LLOYD ESTATES ELEMENTARY",4,"SBBC",128,1,1,3,83]
[3101,"LYONS CREEK MIDDLE",7,"SBBC",231,1,0,7,124]
[2741,"MAPLEWOOD ELEMENTARY",7,"SBBC",422,0,7,0,94]
[1161,"MARGATE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[581,"MARGATE MIDDLE",3,"SBBC",90,0,1,2,29]
[1671,"MARKHAM, ROBERT C. ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3291,"MARSHALL, THURGOOD ELEMENTARY",0,"SBBC",0,0,0,0,0]
[241,"MCARTHUR HIGH",9,"SBBC",301,4,1,8,221]
[1291,"MCFATTER, WILLIAM T. VO-TECH HIGH",1,"SBBC",95,0,1,0,12]
[841,"MCNAB ELEMENTARY",7,"SBBC",275,0,0,7,100]
[481,"MCNICOL MIDDLE",0,"SBBC",0,0,0,0,0]
[761,"MEADOWBROOK ELEMENTARY",2,"Space Master",64,0,2,0,26]
[null,null,9,"SBBC",438,4,0,9,239]
[531,"MIRAMAR ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1751,"MIRAMAR HIGH",13,"SBBC",375,6,1,12,337]
[1841,"MIRROR LAKE ELEMENTARY",3,"SBBC",102,0,0,3,41]
[2691,"MORROW ELEMENTARY",2,"SBBC",64,0,1,1,26]
[881,"NEW RIVER MIDDLE",3,"SBBC",92,0,2,1,39]
[2671,"NOB HILL ELEMENTARY",3,"SBBC",96,0,0,3,41]
[561,"NORCREST ELEMENTARY",0,"SBBC",0,0,0,0,0]
[521,"NORTH ANDREWS GARDENS ELEMENTARY",19,"SBBC",677,2,0,19,323]
[3651,"NORTH AREA SCHOOL OF CHOICE",0,"SBBC",0,0,0,0,0]
[1191,"NORTH FORK ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2231,"NORTH LAUDERDALE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[41,"NORTH SIDE ELEMENTARY",1,"SBBC",95,1,0,1,44]
[1241,"NORTHEAST HIGH",3,"SBBC",81,0,0,3,42]
[1282,"NOVA BLANCHE FORMAN ELEM. (ESOL)",3,"SBBC",96,1,2,1,52]
[1271,"NOVA EISENHOWER D. D. ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1281,"NOVA HIGH",0,"SBBC",0,0,0,0,0]
[1311,"NOVA MIDDLE",20,"SBBC",547,18,2,18,668]
[31,"OAKLAND PARK ELEMENTARY",11,"SBBC",492,1,0,11,179]
[461,"OAKRIDGE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[471,"OLSEN MIDDLE",0,"SBBC",0,0,0,0,0]
[711,"ORANGE BROOK ELEMENTARY",4,"SBBC",134,3,1,3,142]
[1831,"ORIOLE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3311,"PALM COVE ELEMENTARY",9,"SBBC",330,2,0,9,166]
[1131,"PALMVIEW ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3571,"PANTHER RUN ELEMENTARY",1,"SBBC",32,0,0,1,16]
[1951,"PARK RIDGE ELEMENTARY",3,"SBBC",108,0,1,2,31]
[null,null,1,"Banc One",32,0,1,0,13]
[3171,"PARK SPRINGS ELEMENTARY",1,"SBBC",32,0,0,1,15]
[3781,"PARK TRAILS ELEMENTARY",6,"SBBC",204,2,0,6,123]
[3631,"PARKSIDE ELEMENTARY",2,"SBBC",76,0,2,0,28]
[701,"PARKWAY MIDDLE",16,"Space Master",480,0,16,0,208]
[null,null,10,"SBBC",437,1,3,7,148]
[null,null,2,"Resun Leasing",60,0,2,0,24]
[null,null,8,"GE/R",240,0,8,0,102]
[null,null,4,"GE Capital",120,0,4,0,48]
[2071,"PASADENA LAKES ELEMENTARY",6,"SBBC",192,1,1,5,103]
[2661,"PEMBROKE LAKES ELEMENTARY",4,"SBBC",128,0,0,4,60]
[1221,"PEMBROKE PINES ELEMENTARY",6,"SBBC",198,0,2,4,90]
[1631,"PERRY, ANNABEL C. ELEMENTARY",4,"SBBC",134,0,2,2,55]
[1011,"PERRY, HENRY D. MIDDLE",8,"SBBC",275,2,0,8,169]
[931,"PETERS ELEMENTARY",6,"SBBC",222,1,0,6,109]
[653,"PINE RIDGE CENTER",5,"SBBC",235,1,0,5,99]
[2861,"PINES LAKES ELEMENTARY",3,"SBBC",141,2,0,3,104]
[1881,"PINES MIDDLE",9,"SBBC",291,5,0,9,269]
[2811,"PINEWOOD ELEMENTARY",4,"SBBC",260,0,0,4,58]
[2571,"PIONEER MIDDLE",6,"SBBC",210,0,3,3,83]
[1901,"PIPER HIGH",34,"SBBC",918,11,0,34,760]
[null,null,6,"GE/R",162,0,6,0,67]
[3691,"PLANTATION ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1451,"PLANTATION HIGH SCHOOL ",16,"SBBC",577,7,0,16,410]
[null,null,5,"Resun Leasing",183,0,5,0,45]
[null,null,9,"GE/R",272,0,9,0,107]
[null,null,1,"GE Capital",32,0,1,0,13]
[551,"PLANTATION MIDDLE",8,"SBBC",312,4,0,8,222]
[1251,"PLANTATION PARK ELEMENTARY",0,"SBBC",0,0,0,0,0]
[751,"POMPANO BEACH ELEMENTARY",1,"SBBC",32,0,1,0,14]
[185,"POMPANO BEACH INSTITUTE FOR INTERNATIONAL STUDIES",0,"SBBC",0,0,0,0,0]
[21,"POMPANO BEACH MIDDLE",10,"SBBC",335,4,0,10,181]
[3121,"QUIET WATERS ELEMENTARY",13,"SBBC",488,4,1,12,294]
[2721,"RAMBLEWOOD ELEMENTARY",1,"SBBC",32,0,1,0,6]
[2711,"RAMBLEWOOD MIDDLE",7,"SBBC",210,3,1,6,163]
[2121,"RICKARDS MIDDLE",4,"SBBC",122,3,0,4,145]
[2891,"RIVERGLADES ELEMENTARY",2,"SBBC",133,1,0,2,57]
[151,"RIVERLAND ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3031,"RIVERSIDE ELEMENTARY",2,"SBBC",97,0,2,0,26]
[681,"ROCK ISLAND ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1851,"ROYAL PALM ELEMENTARY",15,"SBBC",570,2,7,8,273]
[891,"SANDERS PARK ELEMENTARY",1,"SBBC",38,0,1,0,15]
[3061,"SANDPIPER ELEMENTARY",7,"SBBC",254,1,0,7,131]
[3401,"SAWGRASS ELEMENTARY",0,"SBBC",0,0,0,0,0]
[3431,"SAWGRASS SPRINGS MIDDLE",2,"SBBC",60,1,0,2,59]
[2871,"SEA CASTLE ELEMENTARY",4,"SBBC",126,0,1,3,48]
[601,"SEAGULL SCHOOL",9,"SBBC",593,0,2,7,123]
[1891,"SEMINOLE MIDDLE",10,"SBBC",210,7,1,9,181]
[1811,"SHERIDAN HILLS ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1321,"SHERIDAN PARK ELEMENTARY",0,"SBBC",0,0,0,0,0]
[1051,"SHERIDAN VOCATIONAL CENTER",1,"GE/R",95,0,1,0,11]
[3371,"SILVER LAKES ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2971,"SILVER LAKES MIDDLE",4,"SBBC",120,3,0,4,147]
[3491,"SILVER PALMS ELEMENTARY",4,"SBBC",128,0,4,0,24]
[3081,"SILVER RIDGE ELEMENTARY",7,"SBBC",236,1,2,5,110]
[3581,"SILVER SHORES ELEMENTARY",2,"SBBC",64,1,0,2,59]
[3331,"SILVER TRAIL MIDDLE",19,"SBBC",547,12,3,16,461]
[405,"SOUTH AREA ALTERNATIVE CENTER",0,"SBBC",0,0,0,0,0]
[171,"SOUTH BROWARD HIGH",0,"SBBC",0,0,0,0,0]
[2351,"SOUTH PLANTATION HIGH",3,"SBBC",153,1,0,3,70]
[691,"STIRLING ELEMENTARY",3,"SBBC",102,1,2,1,69]
[3011,"STONEMAN DOUGLAS, MARJ.  HIGH ",30,"SBBC",973,8,0,30,598]
[211,"STRANAHAN HIGH",5,"SBBC",241,1,0,5,106]
[611,"SUNLAND PARK ELEMENTARY",1,"SBBC",32,1,0,1,33]
[251,"SUNRISE MIDDLE",7,"SBBC",210,3,0,7,170]
[422,"SUNSET SCHOOL",0,"SBBC",0,0,0,0,0]
[1171,"SUNSHINE ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2621,"TAMARAC ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2751,"TARAVELLA, J.P. HIGH",6,"SBBC",302,4,0,6,188]
[571,"TEDDER ELEMENTARY",7,"SBBC",290,4,1,6,214]
[3151,"TEQUESTA TRACE MIDDLE",9,"SBBC",270,3,3,6,195]
[1021,"THE QUEST CENTER",0,"SBBC",0,0,0,0,0]
[3481,"TRADEWINDS ELEMENTARY ",8,"SBBC",331,3,4,4,169]
[731,"TROPICAL ELEMENTARY",2,"SBBC",70,0,2,0,18]
[1621,"VILLAGE ELEMENTARY",6,"SBBC",216,0,0,6,87]
[321,"WALKER ELEMENTARY",1,"SBBC",38,0,0,1,16]
[511,"WATKINS ELEMENTARY",1,"SBBC",32,0,0,1,15]
[2881,"WELLEBY ELEMENTARY",5,"SBBC",178,2,0,5,137]
[161,"WEST HOLLYWOOD ELEMENTARY",0,"SBBC",0,0,0,0,0]
[2681,"WESTCHESTER ELEMENTARY",11,"SBBC",376,3,7,4,212]
[2831,"WESTERN HIGH",3,"SBBC",96,1,1,2,73]
[2052,"WESTPINE MIDDLE",4,"SBBC",120,1,0,4,62]
[631,"WESTWOOD HEIGHTS ELEMENTARY",0,"SBBC",0,0,0,0,0]
[452,"WHIDDON-ROGERS EDUCATION CENTER",7,"SBBC",357,4,0,7,201]
[1752,"WHISPERING PINES SCHOOL",2,"SBBC",190,1,2,0,57]
[191,"WILTON MANORS ELEMENTARY",0,"SBBC",0,0,0,0,0]
[991,"WINGATE OAKS CENTER",0,"SBBC",0,0,0,0,0]
[3091,"WINSTON PARK ELEMENTARY",10,"SBBC",368,0,2,8,143]
[3321,"YOUNG, VIRGINIA SHUMAN ELEM.",0,"SBBC",0,0,0,0,0]
[3001,"YOUNG, WALTER C. MIDDLE ",9,"SBBC",293,3,2,7,207]
[{"$nulls":7},0]
["2b2c1.","Broward Total",1206,null,43904,358,381,825,"Avg Age 19.87"]
[]
["2b2c1a.","Continuation of 2b2c1 - The year in which all long term (4 years or more) relocatables,listed in 2b2c1, which will be used as classrooms will meet standards"]
[null,"Location","Year"]
[null,"TBD"]
[]
[]
["2b2c1a.","Broward Maximum Year",0]
[]
[]
[]
["2b2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08","5 YEAR TOTAL"]
[1741,"ANDERSON, BOYD H. HIGH",6,6,0,0,0,0,6]
[1791,"APOLLO MIDDLE",7,7,0,0,0,0,7]
[2221,"ATLANTIC VOCATIONAL CENTER",11,11,0,0,0,0,11]
[2511,"ATLANTIC WEST ELEMENTARY",7,6,1,0,0,0,7]
[343,"ATTUCKS MIDDLE",0,0,0,0,0,0,0]
[2611,"BAIR MIDDLE",11,2,9,0,0,0,11]
[2001,"BANYAN ELEMENTARY",6,6,0,0,0,0,6]
[641,"BAYVIEW ELEMENTARY",0,0,0,0,0,0,0]
[201,"BENNETT ELEMENTARY",0,0,0,0,0,0,0]
[341,"BETHUNE, MARY M. ELEMENTARY",9,9,0,0,0,0,9]
[971,"BOULEVARD HEIGHTS ELEMENTARY",0,0,0,0,0,0,0]
[871,"BRIGHT HORIZONS CENTER",0,0,0,0,0,0,0]
[811,"BROADVIEW ELEMENTARY",4,4,0,0,0,0,4]
[501,"BROWARD ESTATES ELEMENTARY",2,2,0,0,0,0,2]
[1382,"CASTLE HILL ANNEX",0,0,0,0,0,0,0]
[1461,"CASTLE HILL ELEMENTARY",4,0,4,0,0,0,4]
[2641,"CENTRAL PARK ELEMENTARY",10,10,0,0,0,0,10]
[3771,"CHALLENGER ELEMENTARY",0,0,0,0,0,0,0]
[2961,"CHAPEL TRAIL ELEMENTARY",4,4,0,0,0,0,4]
[1421,"COCONUT CREEK ELEMENTARY",3,3,0,0,0,0,3]
[1681,"COCONUT CREEK HIGH",10,9,1,0,0,0,10]
[3741,"COCONUT PALM ELEMENTARY",4,4,0,0,0,0,4]
[231,"COLBERT ELEMENTARY",5,5,0,0,0,0,5]
[331,"COLLINS ELEMENTARY",0,0,0,0,0,0,0]
[1211,"COOPER CITY ELEMENTARY",1,1,0,0,0,0,1]
[1931,"COOPER CITY HIGH",10,10,0,0,0,0,10]
[3041,"CORAL PARK ELEMENTARY",6,6,0,0,0,0,6]
[2551,"CORAL SPRINGS ELEMENTARY",1,0,0,1,0,0,1]
[1151,"CORAL SPRINGS HIGH",2,2,0,0,0,0,2]
[2561,"CORAL SPRINGS MIDDLE",1,1,0,0,0,0,1]
[3111,"COUNTRY HILLS ELEMENTARY",10,10,0,0,0,0,10]
[2981,"COUNTRY ISLES ELEMENTARY",5,5,0,0,0,0,5]
[901,"CRESTHAVEN ELEMENTARY",0,0,0,0,0,0,0]
[221,"CROISSANT PARK ELEMENTARY",3,3,0,0,0,0,3]
[3222,"CROSS CREEK SCHOOL",4,4,0,0,0,0,4]
[1871,"CRYSTAL LAKE COMMUNITY SCHL",2,2,0,0,0,0,2]
[1871,"CRYSTAL LAKE MIDDLE",1,1,0,0,0,0,1]
[2913,"CYPRESS BAY HIGH ANNEX",24,23,0,1,0,0,24]
[3623,"CYPRESS BAY HIGH",3,3,0,0,0,0,3]
[1781,"CYPRESS ELEMENTARY",0,0,0,0,0,0,0]
[2123,"CYPRESS RUN ALT CENTER",8,8,0,0,0,0,8]
[1071,"DANDY, WILLIAM  MIDDLE",10,10,0,0,0,0,10]
[101,"DANIA ELEMENTARY",3,1,0,2,0,0,3]
[2221,"DAVE THOMAS ED CENTER",9,9,0,0,0,0,9]
[2801,"DAVIE ELEMENTARY",4,0,0,0,4,0,4]
[11,"DEERFIELD BEACH ELEMENTARY",0,0,0,0,0,0,0]
[1711,"DEERFIELD BEACH HIGH",7,7,0,0,0,0,7]
[911,"DEERFIELD BEACH MIDDLE",6,6,0,0,0,0,6]
[391,"DEERFIELD PARK ELEMENTARY",0,0,0,0,0,0,0]
[271,"DILLARD ELEMENTARY",0,0,0,0,0,0,0]
[371,"DILLARD HIGH",0,0,0,0,0,0,0]
[3221,"DREW, CHARLES ELEMENTARY",0,0,0,0,0,0,0]
[302,"DREW, CHARLES FAMILY RESOURCE CENTER ",0,0,0,0,0,0,0]
[302,"DREW RESOURCE TEEN PARENT PROGRAM",0,0,0,0,0,0,0]
[721,"DRIFTWOOD ELEMENTARY",5,5,0,0,0,0,5]
[861,"DRIFTWOOD MIDDLE",10,9,0,0,1,0,10]
[3461,"EAGLE POINT ELEMENTARY",4,4,0,0,0,0,4]
[3441,"EAGLE RIDGE ELEMENTARY",0,0,0,0,0,0,0]
[361,"ELY HIGH",10,10,0,0,0,0,10]
[3191,"EMBASSY CREEK ELEMENTARY ",0,0,0,0,0,0,0]
[2942,"EVERGLADES ELEMENTARY",0,0,0,0,0,0,0]
[3513,"EVERGLADES HIGH ANNEX",9,9,0,0,0,0,9]
[3513,"EVERGLADES HIGH ANNEX AT SILV RDGE",7,7,0,0,0,0,7]
[1641,"FAIRWAY ELEMENTARY",0,0,0,0,0,0,0]
[3622,"FALCON COVE MIDDLE",14,14,0,0,0,0,14]
[2541,"FLAMINGO ELEMENTARY",3,0,3,0,0,0,3]
[3391,"FLANAGAN   HIGH",3,3,0,0,0,0,3]
[851,"FLORANADA ELEMENTARY",0,0,0,0,0,0,0]
[3051,"FOREST GLEN MIDDLE",3,0,0,3,0,0,3]
[2631,"FOREST HILLS ELEMENTARY",1,0,0,1,0,0,1]
[951,"FORT LAUDERDALE HIGH",7,5,0,0,2,0,7]
[921,"FOSTER, STEPHEN ELEMENTARY",2,1,1,0,0,0,2]
[3531,"FOX TRAIL ELEMENTARY",5,1,0,4,0,0,5]
[3642,"GATOR RUN ELEMENTARY",0,0,0,0,0,0,0]
[2851,"GRIFFIN ELEMENTARY",0,0,0,0,0,0,0]
[592,"HALLANDALE ADULT & COMMUNITY",0,0,0,0,0,0,0]
[131,"HALLANDALE ELEMENTARY",5,4,0,1,0,0,5]
[403,"HALLANDALE HIGH",0,0,0,0,0,0,0]
[491,"HARBORDALE ELEMENTARY",0,0,0,0,0,0,0]
[3131,"HAWKES BLUFF ELEMENTARY",4,0,0,4,0,0,4]
[102,"HOLLYWOOD CENTRAL ANNEX",0,0,0,0,0,0,0]
[121,"HOLLYWOOD CENTRAL ELEMENTARY",0,0,0,0,0,0,0]
[111,"HOLLYWOOD HILLS ELEMENTARY",5,5,0,0,0,0,5]
[1661,"HOLLYWOOD HILLS HIGH",10,9,0,0,1,0,10]
[1761,"HOLLYWOOD PARK ELEMENTARY",0,0,0,0,0,0,0]
[2531,"HORIZON ELEMENTARY",2,2,0,0,0,0,2]
[1971,"HUNT, JAMES S. ELEMENTARY",0,0,0,0,0,0,0]
[3471,"INDIAN RIDGE MIDDLE",6,3,1,2,0,0,6]
[3181,"INDIAN TRACE ELEMENTARY",11,11,0,0,0,0,11]
[1611,"KING, MARTIN LUTHER ELEMENTARY",4,4,0,0,0,0,4]
[831,"LAKE FOREST ELEMENTARY",1,1,0,0,0,0,1]
[3591,"LAKESIDE ELEMENTARY",0,0,0,0,0,0,0]
[621,"LARKDALE ELEMENTARY",4,4,0,0,0,0,4]
[1701,"LAUDERDALE LAKES MIDDLE",4,4,0,0,0,0,4]
[431,"LAUDERDALE MANORS ELEMENTARY",1,1,0,0,0,0,1]
[1391,"LAUDERHILL MIDDLE",4,4,0,0,0,0,4]
[1381,"LAUDERHILL P. T.  ELEMENTARY",0,0,0,0,0,0,0]
[1091,"LLOYD ESTATES ELEMENTARY",3,3,0,0,0,0,3]
[3101,"LYONS CREEK MIDDLE",7,5,0,0,2,0,7]
[2741,"MAPLEWOOD ELEMENTARY",0,0,0,0,0,0,0]
[1161,"MARGATE ELEMENTARY",0,0,0,0,0,0,0]
[581,"MARGATE MIDDLE",2,2,0,0,0,0,2]
[1671,"MARKHAM, ROBERT C. ELEMENTARY",0,0,0,0,0,0,0]
[3291,"MARSHALL, THURGOOD ELEM.",0,0,0,0,0,0,0]
[241,"McARTHUR HIGH",8,8,0,0,0,0,8]
[1291,"McFATTER, WILLIAM T. VO-TECH HIGH",0,0,0,0,0,0,0]
[841,"McNAB ELEMENTARY",7,7,0,0,0,0,7]
[481,"McNICOL MIDDLE",0,0,0,0,0,0,0]
[761,"MEADOWBROOK ELEMENTARY",9,9,0,0,0,0,9]
[531,"MIRAMAR ELEMENTARY",0,0,0,0,0,0,0]
[1751,"MIRAMAR HIGH",12,12,0,0,0,0,12]
[1841,"MIRROR LAKE ELEMENTARY",3,3,0,0,0,0,3]
[2691,"MORROW ELEMENTARY",1,1,0,0,0,0,1]
[881,"NEW RIVER MIDDLE",0,0,0,0,0,0,0]
[2671,"NOB HILL ELEMENTARY",3,3,0,0,0,0,3]
[561,"NORCREST ELEMENTARY",0,0,0,0,0,0,0]
[521,"NORTH ANDREWS GARDENS ELEMENTARY",19,19,0,0,0,0,19]
[3651,"NORTH AREA SCHOOL OF CHOICE",0,0,0,0,0,0,0]
[1191,"NORTH FORK ELEMENTARY",0,0,0,0,0,0,0]
[2231,"NORTH LAUDERDALE ELEMENTARY",0,0,0,0,0,0,0]
[41,"NORTH SIDE ELEMENTARY",1,1,0,0,0,0,1]
[1241,"NORTHEAST HIGH",3,3,0,0,0,0,3]
[1282,"NOVA BLANCHE FORMAN ELEMENTARY",1,1,0,0,0,0,1]
[1271,"NOVA EISENHOWER D. D. ELEM. ",0,0,0,0,0,0,0]
[1281,"NOVA HIGH",0,0,0,0,0,0,0]
[1311,"NOVA MIDDLE",18,18,0,0,0,0,18]
[31,"OAKLAND PARK ELEMENTARY",11,6,0,5,0,0,11]
[461,"OAKRIDGE ELEMENTARY",0,0,0,0,0,0,0]
[471,"OLSEN MIDDLE",0,0,0,0,0,0,0]
[711,"ORANGE BROOK ELEMENTARY",3,3,0,0,0,0,3]
[1831,"ORIOLE ELEMENTARY",0,0,0,0,0,0,0]
[3311,"PALM COVE ELEMENTARY",9,9,0,0,0,0,9]
[1131,"PALMVIEW ELEMENTARY",0,0,0,0,0,0,0]
[3571,"PANTHER RUN ELEMENTARY",1,1,0,0,0,0,1]
[1951,"PARK RIDGE ELEMENTARY",2,2,0,0,0,0,2]
[3171,"PARK SPRINGS ELEMENTARY",1,1,0,0,0,0,1]
[3781,"PARK TRAILS ELEMENTARY",6,6,0,0,0,0,6]
[3631,"PARKSIDE ELEMENTARY",0,0,0,0,0,0,0]
[701,"PARKWAY MIDDLE",7,0,0,7,0,0,7]
[2071,"PASADENA LAKES ELEMENTARY",5,5,0,0,0,0,5]
[2661,"PEMBROKE LAKES ELEMENTARY",4,4,0,0,0,0,4]
[1221,"PEMBROKE PINES ELEMENTARY",4,0,0,4,0,0,4]
[1631,"PERRY, ANNABEL C. ELEMENTARY",2,2,0,0,0,0,2]
[1011,"PERRY, HENRY D. MIDDLE",8,8,0,0,0,0,8]
[931,"PETERS ELEMENTARY",6,6,0,0,0,0,6]
[653,"PINE RIDGE CENTER",5,5,0,0,0,0,5]
[2861,"PINES LAKES ELEMENTARY",3,3,0,0,0,0,3]
[1881,"PINES MIDDLE",9,0,0,0,9,0,9]
[2811,"PINEWOOD ELEMENTARY",4,4,0,0,0,0,4]
[2571,"PIONEER MIDDLE",3,2,0,1,0,0,3]
[1901,"PIPER HIGH",34,17,0,17,0,0,34]
[3691,"PLANTATION ELEMENTARY",0,0,0,0,0,0,0]
[1451,"PLANTATION HIGH",16,16,0,0,0,0,16]
[551,"PLANTATION MIDDLE",8,8,0,0,0,0,8]
[1251,"PLANTATION PARK ELEMENTARY",0,0,0,0,0,0,0]
[751,"POMPANO BEACH ELEMENTARY",0,0,0,0,0,0,0]
[185,"POMPANO BEACH INSTITUTE FOR INTERNATIONAL STUDIES",0,0,0,0,0,0,0]
[21,"POMPANO BEACH MIDDLE",10,10,0,0,0,0,10]
[3121,"QUIET WATERS ELEMENTARY",12,2,10,0,0,0,12]
[2721,"RAMBLEWOOD ELEMENTARY",0,0,0,0,0,0,0]
[2711,"RAMBLEWOOD MIDDLE",6,6,0,0,0,0,6]
[2121,"RICKARDS MIDDLE",4,4,0,0,0,0,4]
[2891,"RIVERGLADES ELEMENTARY",2,2,0,0,0,0,2]
[151,"RIVERLAND ELEMENTARY",0,0,0,0,0,0,0]
[3031,"RIVERSIDE ELEMENTARY",0,0,0,0,0,0,0]
[681,"ROCK ISLAND ELEMENTARY",0,0,0,0,0,0,0]
[1851,"ROYAL PALM ELEMENTARY",8,7,1,0,0,0,8]
[891,"SANDERS PARK ELEMENTARY",0,0,0,0,0,0,0]
[3061,"SANDPIPER ELEMENTARY",7,7,0,0,0,0,7]
[3401,"SAWGRASS ELEMENTARY",0,0,0,0,0,0,0]
[3431,"SAWGRASS SPRINGS MIDDLE",2,2,0,0,0,0,2]
[2871,"SEA CASTLE ELEMENTARY",3,3,0,0,0,0,3]
[601,"SEAGULL SCHOOL",7,7,0,0,0,0,7]
[1891,"SEMINOLE MIDDLE",9,9,0,0,0,0,9]
[1811,"SHERIDAN HILLS ELEMENTARY",0,0,0,0,0,0,0]
[1321,"SHERIDAN PARK ELEMENTARY",0,0,0,0,0,0,0]
[1051,"SHERIDAN VOCATIONAL CENTER",0,0,0,0,0,0,0]
[3371,"SILVER LAKES ELEMENTARY",0,0,0,0,0,0,0]
[2971,"SILVER LAKES MIDDLE",4,4,0,0,0,0,4]
[3491,"SILVER PALMS ELEMENTARY",0,0,0,0,0,0,0]
[3081,"SILVER RIDGE ELEMENTARY",5,5,0,0,0,0,5]
[3581,"SILVER SHORES ELEMENTARY",2,2,0,0,0,0,2]
[3331,"SILVER TRAIL MIDDLE ",16,16,0,0,0,0,16]
[405,"SOUTH AREA ALTERNATIVE CENTER",0,0,0,0,0,0,0]
[171,"SOUTH BROWARD HIGH",0,0,0,0,0,0,0]
[2351,"SOUTH PLANTATION HIGH",3,3,0,0,0,0,3]
[691,"STIRLING ELEMENTARY",1,1,0,0,0,0,1]
[3011,"STONEMAN DOUGLAS HIGH",30,24,0,6,0,0,30]
[211,"STRANAHAN HIGH",5,3,0,2,0,0,5]
[611,"SUNLAND PARK ELEMENTARY",1,1,0,0,0,0,1]
[251,"SUNRISE MIDDLE",7,7,0,0,0,0,7]
[422,"SUNSET SCHOOL",0,0,0,0,0,0,0]
[1171,"SUNSHINE ELEMENTARY",0,0,0,0,0,0,0]
[2621,"TAMARAC ELEMENTARY",0,0,0,0,0,0,0]
[2751,"TARAVELLA, J.P. HIGH",6,6,0,0,0,0,6]
[571,"TEDDER ELEMENTARY",6,6,0,0,0,0,6]
[3151,"TEQUESTA TRACE MIDDLE",6,6,0,0,0,0,6]
[1021,"THE QUEST CENTER",0,0,0,0,0,0,0]
[3481,"TRADEWINDS ELEMENTARY",4,0,4,0,0,0,4]
[731,"TROPICAL ELEMENTARY",0,0,0,0,0,0,0]
[1621,"VILLAGE ELEMENTARY",6,6,0,0,0,0,6]
[321,"WALKER ELEMENTARY",1,0,0,0,1,0,1]
[511,"WATKINS ELEMENTARY",1,1,0,0,0,0,1]
[2881,"WELLEBY ELEMENTARY",5,5,0,0,0,0,5]
[161,"WEST HOLLYWOOD ELEMENTARY",0,0,0,0,0,0,0]
[2681,"WESTCHESTER ELEMENTARY",4,4,0,0,0,0,4]
[2831,"WESTERN HIGH",2,2,0,0,0,0,2]
[2052,"WESTPINE MIDDLE",4,4,0,0,0,0,4]
[631,"WESTWOOD HEIGHTS ELEMENTARY",0,0,0,0,0,0,0]
[452,"WHIDDON-ROGERS EDUCATION CENTER",7,6,0,1,0,0,7]
[1752,"WHISPERING PINES SCHOOL",0,0,0,0,0,0,0]
[191,"WILTON MANORS ELEMENTARY",0,0,0,0,0,0,0]
[991,"WINGATE OAKS CENTER",0,0,0,0,0,0,0]
[3091,"WINSTON PARK ELEMENTARY",8,8,0,0,0,0,8]
[3321,"YOUNG, VIRGINIA SHUMAN ELEM.",0,0,0,0,0,0,0]
[3001,"YOUNG, WALTER C. MIDDLE ",7,7,0,0,0,0,7]
[{"$nulls":8},0]
["2b2c2.","Broward Total",826,709,35,62,20,0,826]
[]
["2b2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2003-04","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2007-08","FISH Stu. Sta.","# Years Leased "]
[2611,"BAIR MIDDLE",2,"Space Master",104,26,2,104,36]
[371,"Dillard High",1,"GE/R",27,11,1,27,16]
[861,"Driftwood Middle",11,"GE/R",597,137,7,405,120]
[861,"Driftwood Middle",6,"Resun Leasing",310,73,5,215,85]
[361,"Ely High",2,"GE/R",78,25,0,0,0]
[761,"Meadowbrook Elementary",2,"Space Master",64,26,2,64,36]
[1951,"Park Ridge Elementary",1,"Banc One",32,13,1,32,18]
[701,"Parkway Middle",4,"GE Capital",120,48,4,120,68]
[701,"Parkway Middle",8,"GE/R",240,102,8,240,142]
[701,"Parkway Middle",2,"Resun Leasing",60,24,2,60,34]
[701,"Parkway Middle",16,"Space Master",480,208,16,480,288]
[1901,"Piper High",6,"GE/R",162,67,6,162,97]
[1451,"Plantation High",1,"GE Capital",32,13,1,32,18]
[1451,"Plantation High",9,"GE/R",272,107,9,272,152]
[1451,"Plantation High",5,"Resun Leasing",183,45,5,183,70]
[1612,"Reading Center * (on M.l.king Site)",1,"Williams",65,15,1,65,20]
[1051,"Sheridan Technical Center",1,"GE/R",95,11,1,95,16]
[3341,"West Central Bus Compound Parking/District Main.",2,"GE/R",102,24,2,102,34]
[3341,"West Central Bus Compound Parking/District Main.",1,"Resun Leasing",51,12,1,51,17]
[]
[]
[2981,"Country Isles Elementary",null," "," "," "," "," "," "]
[null,"   Playfields",0,"City of Weston",0,40,0,0,0]
[3441,"Eagle Ridge Elementary"," "]
[null,"   Playfields",0,"City of Coral Springs",0,40,0,0,0]
[null,"Elementary \"M-91\" ",null," "," ",null," "," "," "]
[null,"   School site",0,"City of Coral Springs",0,50,0,0,0]
[3181,"Indian Trace Elementary",null," "," "," "," "," "," "]
[null,"   Playfields",0,"City of Weston",0,30,0,0,0]
[null,"Middle School \"HH\""]
[null,"   Playfields",0,"City of Coconut Creek",0,50,0,0,0]
[1901,"Piper High School",null," "," "," "," "," "," "]
[null,"   Athletic Fields",0,"City of Sunrise",0,30,0,0,0]
[3691,"Plantation Elementary",null," "," "," "," "," "," "]
[null,"   Playfields",0,"City of Plantation",0,20,0,0,0]
[3031,"Riverside Elementary"]
[null,"   Playfields",0,"City of Coral Springs",0,40,0,0,0]
[2621,"Tamarac Elementary"]
[null,"   Playfields",0,"City ofTamarac",0,40,0,0,0]
[2621,"Tamarac Elemementary",null," "," "," "," "," "," "]
[null,"   Multi-purpose Building",0,"City ofTamarac",0,50,0,0,0]
[2621,"Tamarac Elementary"," ",null," "," "," "," "," "]
[null,"   Multi-purpose classrooms",2,"City ofTamarac",0,1,0,0,0]
[3001,"Walter C. Young"," "," "," "," "," "," "," "]
[null,"   Middle school site",0,"City of Pem. Pines",0,50,0,0,0]
[]
["2b2c3.","Broward Total",83,null,3074,1428,74,2709,1267]
[]
[]
["2b2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2007-08"]
[null,"City of Pemb. Pines Charter Elementary",30,"City of Pembroke Pines","98/99",1800,1795,15,1795]
[null,"Central Charter"," 7 to 10","Assistance Unlimited Foundation, Rosa Lawson","97/98",630,580,10,580]
[null,"Chancellor @ North Lauderdale",null,"Learning Excellence Foundation of East Broward"," 01/02",600,514,5,514]
[null,"Chancellor @ N Lauderdale Middle",null,"Learning Excellence Foundation of East Broward"," 01/02",600,129,5,129]
[null,"Chancellor @ Weston",null,"Learning Excellence Foundation of West Broward"," 01/02",950,892,5,892]
[null,"Chancellor @ N. Broward",null,"Charter Foundation of North Broward","Withdrawn",750,0,15,0]
[null,"Chancellor @ S. Broward",null,"Charter Foundation of South Broward","Withdrawn",750,0,15,0]
[null,"Charter Foundation \"C\"",null,"The Charter Foundation, Inc.","Withdrawn",1050,0,15,0]
[null,"Charter Foundation \"D\"",null,"The Charter Foundation, Inc.","Withdrawn",1050,0,15,0]
[null,"Charter Foundation Academy East",null,"The Charter Foundation, Inc.","Withdrawn",600,0,15,0]
[null,"Charter School of Excellence","4 classrooms/ 2 relocatables","Charter School of Excellence, Inc., Hamilton Forman","97/98",310,295,10,295]
[null,"Eagle Academy",null,"Lauderdale Lakes Academy, Inc.","03/04",560,111,15,111]
[null,"North Broward Acad. of Excellence",null,"The Charter Foundation, Inc."," 01/02",250,179,15,179]
[null,"Performing Arts Inst.",null,"Tutoring Corner, Inc.","Deferred to 03/04",200,0,15,0]
[null,"Sommerset Ngh. School","2 relocatables/ plus 2 classrooms (8/98)","Somerset Academy, Inc.","97/98",75,75,10,75]
[null,"City of N. Laud. Charter","Not known at this date","City of North Lauderdale","98/99",874,738,15,738]
[null,"Smart School","11 to 14","Edward Miller Smart School","98/99",385,462,10,462]
[null,"Smart School High",null,"Edward Miller Smart School"," 03/04",1000,141,15,141]
[null,"Coral Springs Charter",68,"City of Coral Springs","99/00",1600,1604,15,1604]
[null,"Charter School Institute Training Center","2 classrooms / 3 relocatables","Joseph Valbrun","99/00",100,114,10,114]
[null,"City of Pembroke Pines Charter Middle",21,"City of Pembroke Pines","99/00",1200,1203,15,1203]
[null,"City of Pembroke Pines",null,"City of Pembroke Pines","00/01",1600,1594,15,1594]
[null,"Somerset  Academy","10 relocatables","Somerset Academy, Inc.","00/01",825,846,10,846]
[null,"Somerset Academy Middle",null,"Somerset Academy, Inc."," 01/02",600,529,15,529]
[null,"Somerset Academy High",null,"Somerset Academy, Inc."," 02/03",1200,166,15,166]
[null,"Parkway Academy",null,"The Automotive Technical Charter High School of Florida","01/02",650,462,null,462]
[null,"Somerset Acdademy Davie Charter",null,"Somerset Academy, Inc.","03/04",800,66,15,66]
[null,"Charter Institute Annex",null,"Joseph Valbrun","00/01",350,0,10,0]
[null,"Broward Community Charter (K-5)",null,"Broward Community Charter School, Inc.","04/05",400,null,null,261]
[null,"Broward Military Academy Charter (9-12)",null,"Broward Military Academy Charter, Inc.","04/05",500,null,null,375]
[null,"Downtown Academy of Technology and Arts (6-8)",null,"Downtown Academy of Technology and Arts, Inc.","04/05",200,null,null,154]
[null,"Northwest Broward Charter School                                            (K-8)",null,"The Charter Foundation, Inc.","04/05",1100,null,null,1100]
[null,"Osprey Charter Elementary (K-5)",null,"The Educational Charter Foundation of Florida, Inc.","04/05",700,null,null,665]
[null,"Somerset Academy @ Davie (East Campus)",null,"Somerset Academy, Inc.","04/05",500,null,null,150]
[null,"Touchdowns4Life Charter School  (6-8)",null,"Touchdowns4Life, Inc.","04/05",150,null,null,144]
[null,"Weston Charter School (9-12)",null,"The Charter Foundation, Inc.","04/05",1600,null,null,1600]
[null,"Oak Scholar (K-8)",null,"Oak Scholar Academy, Inc.","04/05",900,null,null,600]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b2c4.","Broward Total",119,null,null,27409,12495,340,12495]
[]
["Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop"]
[]
["2b2d.","Plans approved by the school board that reduce the need for permanent student stations such as acceptable school capacity levels, redistricting, "]
[null,"busing, year-round schools, charter schools, magnet schools, public-private partnerships, multitrack scheduling, grade level organization,"]
[null," block scheduling, or other alternatives."]
[]
[]
["STANDARDS FOR OVERCROWDED SCHOOLS (From School Board Policy 5000)"]
[]
["1.","After the 20 day count in September of each school year, each Area Superintendent will evaluate the impact of actual student enrollment and determine critically overcrowded schools."]
[]
["2.","Schools shall be deemed critically overcrowded when they exceed the enrollment limits reflected below or have special considerations (i.e., schools on small acreage, extremely limited FISH capacity, or school construction issues, or schools in areas of rapidly growing student populations or have program capacity issues). Schools shall be deemed approaching critically overcrowded when they exceed 95% of the enrollment limits reflected below."]
[]
[null,"a.","Elementary ",null,"capacity fewer than 900 ","175% of FISH* or exceeds 1200"]
[{"$nulls":4},"capacity 900 or greater ","150% of FISH*"]
[null,"b.","Middle ",null,"capacity fewer than 1500"," 140% of FISH* or exceeds 1700"]
[{"$nulls":4},"capacity 1500 or greater ","125% of FISH*"]
[null,"c.","High ",null,"capacity fewer than 2000 ","150% of FISH* or exceeds 2500"]
[{"$nulls":4},"capacity 2000 or greater ","125% of FISH*"]
[]
[null,"*For purposes of implementation of this policy, FISH (Florida Inventory of School Houses) means permanent capacity. Designated permanent portable facilities that have assigned attendance areas through the annual boundary process shall also be counted as capacity."]
[]
["3.","Schools for which the School Board has approved a boundary change moving students out of a critically overcrowded school or out of a school that is approaching the criteria for a critically overcrowded school, as defined in paragraph 2. above, shall be subject to the provisions of School Board Policy 5001, REASSIGNMENTS OF STUDENTS, Paragraph 5.c."]
[]
["4.","Criteria for determining alternative student enrollment options will include, but not be limited to, a review of the following criteria:"]
[]
[null,"a.","Welfare, health and safety of children and faculty/staff"]
[null,"b.","Impact on the overall facility (ingress and egress problems)"]
[null,"c.","Impact on support services, such as cafeteria and library"]
[null,"d.","Amount of funding dedicated to the classroom through the instructional allocation, including but not limited to, books, equipment, supplies, and educational materials."]
[null,"e.","Number of floating teachers"]
[null,"f.","Doubled classrooms"]
[null,"g.","Full classroom use of small rooms (i.e., resource rooms, conference rooms)"]
[null,"h.","Class size (student/teacher/paraprofessional ratio)"]
[null,"i.","Number of portables and the impact on student learning potential and teacher morale"]
[null,"j.","Acreage of site"]
[null,"k.","Playground area/sports/recreation"]
[null,"l.","Planned future renovations or replacement of facility"]
[null,"m.","Parking on campus"]
[null,"n.","Restroom facilities"]
[null,"o.","Impact of changes on diversity of school(s) and district"]
[null,"p.","Impact on community/neighborhood"]
[]
["5.","Schools required as a result of this review process to implement alternative student enrollment options will consider the following and provide prioritized options for addressing overcrowding to the Area Superintendent:"]
[]
[null,"a.","Additional portables (dependent upon available portables and/or available funds to purchase, move, and/or hookup portables to be provided by the school district and/or others, (including municipalities, developers, etc.)"]
[null,"b.","Enrollment capping (i.e. school will not accommodate any more students and new students are assigned to designated schools that are less crowded)"]
[null,"c.","Flexible school day/week/month/year (including, but not limited to) scheduling:"]
[null,null,"(1)","Extended school day"]
[null,null,null,"(a)","Multiple period high school day"]
[null,null,null,"(b)","Double sessions"]
[null,null,null,"(c) ","Merging of regular school day and community school schedule"]
[null,null,"(2)","Multi-track year-round education program"]
[null,null,"(3)","1/2 day kindergarten"]
[null,null,"(4)","Dual enrollment programs with institutions of higher learning"]
[null,null,"(5)","Other school day/week/month/year models that may be identified through this process"]
[]
[null,"d.","Boundary changes (in conjunction with the School Boundary Conferences process)"]
[null,"e.","Reconfigured grades/educational programs and sites, dependent on available capital funds to be provided by the school district and/or other individuals/groups/entities (including but not limited to):"]
[null,null,"(1)","Kindergarten Center"]
[null,null,"(2)","Primary Grade Center K-2"]
[null,null,"(3)","K-5 Center"]
[null,null,"(4)","Intermediate Center"]
[null,null,"(5)","Single Grade Center"]
[null,null,"(6)","Other reconfigurations that may be identified through this process"]
[]
[null,"f.","Other options that will achieve the desired result (i.e. relieve overcrowding without having to allocate additional capital resources that are not available). There is no limit to the number of options that may be suggested under this category."]
[]
["6.","Alternative student enrollment options recommended in paragraph.5. above that impact other schools must be recommended collaboratively by both sending and receiving schools."]
[]
["7.","The principal of each school under review will meet with elected parent leadership of and representatives of faculty/staff, i.e. building steward, and students to develop recommendations for consideration by the entire school and community."]
[]
["8.","The Area Superintendent will insure that the principal:"]
[null,"a.","Meets with the shareholders to review all options viewed as appropriate."]
[null,"b.","Schedules day, evening and night presentation(s) for shareholders with equal time for each option deemed appropriate."]
[null,"c.","Gains broad consensus on proposed alternative student enrollment options among staff, parents and other shareholders. If consensus cannot be reached, the Area Superintendent will make a recommendation to the Superintendent of Schools on a proposed alternative student enrollment option."]
[null,"d.","Observe the established deadline for a recommendation in this regard to the Area Superintendent."]
[]
["9.","The Area Superintendent will make a recommendation to the Superintendent of Schools during the annual boundary process."]
[]
["10.","The Superintendent of Schools will make a recommendation to the School Board prior to the Public Hearings."]
[]
["11.","This policy will be reviewed annually in June to review the enrollment-limits criteria for defining critically overcrowded schools"]
[]
[]
[]
[]
[]
["2b2e.","Average Class Size (5 years out -- 2007-08) that will result if the district facilities work plan is fully implemented."]
[{"$nulls":5},"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","# CLASSROOMS","Capacity (NOT Stu Sta)","2002-03 CO-FTE","2002-03 Class size","2007-08 CO-FTE","be added (removed)","2007-08 Class size"]
[1631,"Annabel C Perry Elementary",41,41,787,19.2,821,12,15.49]
[1791,"Apollo Middle",65,58.5,1475,22.69,1572,14,19.9]
[4702,"Arthur Robert Ashe, Jr Middle",54,48.6,1111,20.57,1303,0,24.13]
[2221,"Atlantic Technical Center",91,91,299,3.29,600,24,5.22]
[2511,"Atlantic West Elementary",47,47,1017,21.64,1131,8,20.56]
[343,"Attucks Middle",63,56.7,673,10.68,642,0,10.19]
[2611,"Bair Middle",81,72.9,1676,20.69,1804,12,19.4]
[2001,"Banyan Elementary",46,46,1002,21.78,885,8,16.39]
[641,"Bayview Elementary",29,29,636,21.93,682,0,23.52]
[201,"Bennett Elementary",34,34,450,13.24,556,0,16.35]
[361,"Blanche Ely Senior High",115,109.25,2792,24.28,3017,14,23.39]
[971,"Boulevard Heights Elementary",44,44,977,22.2,842,0,19.14]
[1741,"Boyd H Anderson Senior High",132,125.4,2691,20.39,2761,0,20.92]
[871,"Bright Horizons",34,34,148,4.35,148,0,4.35]
[811,"Broadview Elementary",51,51,974,19.1,1101,2,20.77]
[501,"Broward Estates Elementary",50,50,725,14.5,900,2,17.31]
[1461,"Castle Hill Elementary",42,42,738,17.57,788,4,17.13]
[1382,"Castle Hill Elementary Annex",20,20,752,37.6,752,0,37.6]
[2641,"Central Park Elementary",51,51,1157,22.69,1055,16,15.75]
[3771,"Challenger Elementary",48,48,1126,23.46,1113,0,23.19]
[2961,"Chapel Trail Elementary",63,63,1309,20.78,1335,0,21.19]
[3391,"Charles W Flanagan Senior High",132,125.4,3701,28.04,3337,0,25.28]
[1421,"Coconut Creek Elementary",48,48,868,18.08,764,0,15.92]
[1681,"Coconut Creek Senior High",99,94.05,2533,25.59,2636,0,26.63]
[3741,"Coconut Palm Elementary",55,55,1349,24.53,2151,0,39.11]
[231,"Colbert Elementary",43,43,702,16.33,697,8,13.67]
[331,"Collins Elementary",22,22,359,16.32,425,0,19.32]
[1211,"Cooper City Elementary",44,44,1016,23.09,1130,0,25.68]
[1931,"Cooper City Senior High",94,89.3,2471,26.29,2603,12,24.56]
[3041,"Coral Park Elementary",43,43,895,20.81,792,2,17.6]
[2551,"Coral Springs Elementary",42,42,902,21.48,874,6,18.21]
[2561,"Coral Springs Middle",60,54,1090,18.17,1096,8,16.12]
[1151,"Coral Springs Senior High",112,106.4,2935,26.21,3065,24,22.54]
[3111,"Country Hills Elementary",54,54,1290,23.89,1255,10,19.61]
[2981,"Country Isles Elementary",47,47,955,20.32,817,6,15.42]
[901,"Cresthaven Elementary",40,40,826,20.65,888,2,21.14]
[221,"Croissant Park Elementary",49,49,796,16.24,884,0,18.04]
[3222,"Cross Creek School",24,24,166,6.92,166,0,6.92]
[1871,"Crystal Lake Middle",80,72,1767,22.09,1808,6,21.02]
[3623,"Cypress Bay Senior High",174,165.3,4270,24.54,4995,24,25.23]
[1781,"Cypress Elementary",42,42,787,18.74,847,4,18.41]
[2123,"Cypress Run Alternative Exceptional Center",19,19,123,6.47,123,0,6.47]
[101,"Dania Elementary",40,40,703,17.58,818,0,20.45]
[3651,"Dave Thomas Education Center",22,22,589,26.77,598,0,27.18]
[2801,"Davie Elementary",49,49,978,19.96,985,4,18.58]
[11,"Deerfield Beach Elementary",51,51,889,17.43,1003,0,19.67]
[911,"Deerfield Beach Middle",86,77.4,1725,20.06,1761,6,19.14]
[1711,"Deerfield Beach Senior High",132,125.4,2795,21.17,2912,6,21.1]
[391,"Deerfield Park Elementary",46,46,761,16.54,788,0,17.13]
[271,"Dillard Elementary",50,50,650,13,602,0,12.04]
[371,"Dillard Senior High",115,109.25,2148,18.68,1895,0,16.48]
[3221,"Drew Elementary",35,35,541,15.46,510,0,14.57]
[721,"Driftwood Elementary",44,44,764,17.36,772,0,17.55]
[861,"Driftwood Middle",87,78.3,1919,22.06,1662,0,19.1]
[1271,"Dwight D Eisenhower Elementary",46,46,1019,22.15,1000,0,21.74]
[3461,"Eagle Point Elementary",58,58,1374,23.69,1322,4,21.32]
[3441,"Eagle Ridge Elementary",51,51,1113,21.82,1141,0,22.37]
[3191,"Embassy Creek Elementary",44,44,1038,23.59,978,0,22.23]
[3301,"Endeavour Primary Learning Center",26,26,264,10.15,389,0,14.96]
[2942,"Everglades Elementary",55,55,1178,21.42,1183,4,20.05]
[3731,"Everglades Senior High",170,161.5,2374,13.96,3171,0,18.65]
[1641,"Fairway Elementary",52,52,1005,19.33,1032,0,19.85]
[3622,"Falcon Cove Middle",107,96.3,2649,24.76,2866,0,26.79]
[2541,"Flamingo Elementary",40,40,856,21.4,859,6,18.67]
[851,"Floranada Elementary",48,48,869,18.1,890,0,18.54]
[3051,"Forest Glen Middle",61,54.9,1312,21.51,1388,4,21.35]
[2631,"Forest Hills Elementary",41,41,818,19.95,973,0,23.73]
[951,"Fort Lauderdale Senior High",97,92.15,1795,18.51,1860,0,19.18]
[3531,"Fox Trail Elementary",55,55,1274,23.16,1397,6,22.9]
[3642,"Gator Run Elementary",63,63,1347,21.38,1392,0,22.1]
[2851,"Griffin Elementary",40,40,790,19.75,856,0,21.4]
[592,"Hallandale Adult & Community Center",63,63,718,11.4,718,0,11.4]
[131,"Hallandale Elementary",45,45,1246,27.69,1521,0,33.8]
[403,"Hallandale Senior High",71,67.45,1618,22.79,1661,0,23.39]
[491,"Harbordale Elementary",23,23,460,20,479,0,20.83]
[3131,"Hawkes Bluff Elementary",55,55,1135,20.64,1103,6,18.08]
[1011,"Henry D Perry Middle",67,60.3,1465,21.87,1626,8,21.68]
[121,"Hollywood Central Elementary",51,51,1019,19.98,1240,0,24.31]
[111,"Hollywood Hills Elementary",40,40,909,22.73,938,12,18.04]
[1661,"Hollywood Hills Senior High",93,88.35,2406,25.87,2800,24,23.93]
[1761,"Hollywood Park Elementary",36,36,651,18.08,855,4,21.38]
[2531,"Horizon Elementary",42,42,1032,24.57,979,0,23.31]
[3471,"Indian Ridge Middle",87,78.3,2165,24.89,2333,0,26.82]
[3181,"Indian Trace Elementary",56,56,941,16.8,835,0,14.91]
[2751,"J P Taravella Senior High",132,125.4,3436,26.03,3832,0,29.03]
[1971,"James S Hunt Elementary",41,41,951,23.2,1072,2,24.93]
[2121,"James S Rickards Middle",54,48.6,1066,19.74,1154,8,18.61]
[3861,"JJJ High School",74,70.3,0,0,2000,2000,0.96]
[831,"Lake Forest Elementary",52,52,862,16.58,810,0,15.58]
[3591,"Lakeside Elementary",53,53,1049,19.79,1036,8,16.98]
[405,"Lanier-James Education Center",21,21,229,10.9,229,0,10.9]
[621,"Larkdale Elementary",46,46,533,11.59,551,0,11.98]
[1701,"Lauderdale Lakes Middle",55,49.5,1012,18.4,1199,2,21.04]
[431,"Lauderdale Manors Elementary",50,50,777,15.54,767,0,15.34]
[1391,"Lauderhill Middle",60,54,1074,17.9,1301,6,19.71]
[1381,"Lauderhill-Paul Turner Elementary",51,51,866,16.98,888,0,17.41]
[3821,"Liberty Elementary",47,47,1110,23.62,1266,4,24.82]
[1091,"Lloyd Estates Elementary",41,41,634,15.46,635,0,15.49]
[3101,"Lyons Creek Middle",84,75.6,2061,24.54,2076,12,21.63]
[3841,"Manatee Bay Elementary",47,47,1161,24.7,1159,0,24.66]
[2741,"Maplewood Elementary",48,48,939,19.56,1005,6,18.61]
[1161,"Margate Elementary",53,53,1089,20.55,984,0,18.57]
[581,"Margate Middle",77,69.3,1274,16.55,1331,0,17.29]
[1611,"Martin Luther King Elementary",52,52,776,14.92,742,3,13.49]
[341,"Mary M Bethune Elementary",58,58,1027,17.71,994,7,15.29]
[241,"McArthur Senior High",124,117.8,2575,20.77,2777,0,22.4]
[841,"McNab Elementary",53,53,723,13.64,614,0,11.58]
[481,"McNicol Middle",70,63,1635,23.36,1756,0,25.09]
[761,"Meadowbrook Elementary",41,41,639,15.59,726,27,10.68]
[4772,"Millennium Middle",52,46.8,1516,29.15,1599,8,26.65]
[531,"Miramar Elementary",41,41,840,20.49,862,1,20.52]
[1751,"Miramar Senior High",98,93.1,2734,27.9,2919,24,23.93]
[1841,"Mirror Lake Elementary",44,44,740,16.82,767,0,17.43]
[3541,"Monarch Senior High",51,48.45,1040,20.39,1790,0,35.1]
[2691,"Morrow Elementary",42,42,850,20.24,1088,4,23.65]
[3911,"New Renaissance Middle",72,64.8,1679,23.32,1775,0,24.65]
[881,"New River Middle",76,68.4,1576,20.74,1643,0,21.62]
[2671,"Nob Hill Elementary",39,39,883,22.64,826,8,17.57]
[561,"Norcrest Elementary",60,60,831,13.85,836,0,13.93]
[521,"North Andrews Gardens Elementary",66,66,855,12.95,869,0,13.17]
[1191,"North Fork Elementary",42,42,544,12.95,621,0,14.79]
[2231,"North Lauderdale Elementary",58,58,1086,18.72,1049,1,17.78]
[41,"North Side Elementary",41,41,506,12.34,514,0,12.54]
[1241,"Northeast Senior High",86,81.7,2184,25.4,2171,12,22.15]
[1282,"Nova Blanche Forman Elementary",47,47,958,20.38,966,0,20.55]
[1311,"Nova Middle",70,63,1536,21.94,1500,17,17.24]
[1281,"Nova Senior High",82,77.9,2043,24.91,2100,12,22.34]
[31,"Oakland Park Elementary",35,35,673,19.23,571,12,12.15]
[461,"Oakridge Elementary",40,40,880,22,894,28,13.15]
[471,"Olsen Middle",85,76.5,2010,23.65,2144,0,25.22]
[711,"Orange Brook Elementary",40,40,852,21.3,834,0,20.85]
[1831,"Oriole Elementary",47,47,827,17.6,727,0,15.47]
[3311,"Palm Cove Elementary",49,49,1124,22.94,943,12,15.46]
[1131,"Palmview Elementary",31,31,634,20.45,739,4,21.11]
[3571,"Panther Run Elementary",49,49,952,19.43,835,0,17.04]
[3761,"Park Lakes Elementary",48,48,1205,25.1,1338,1,27.31]
[1951,"Park Ridge Elementary",43,43,662,15.4,788,6,16.08]
[3171,"Park Springs Elementary",41,41,968,23.61,1145,6,24.36]
[3781,"Park Trails Elementary",54,54,1139,21.09,1528,4,26.34]
[3631,"Parkside Elementary",49,49,1132,23.1,1112,0,22.69]
[701,"Parkway Middle",94,84.6,1864,19.83,2112,8,20.71]
[2071,"Pasadena Lakes Elementary",46,46,881,19.15,1063,6,20.44]
[2661,"Pembroke Lakes Elementary",44,44,841,19.11,818,0,18.59]
[1221,"Pembroke Pines Elementary",39,39,850,21.79,841,6,18.69]
[931,"Peters Elementary",48,48,863,17.98,766,8,13.68]
[653,"Pine Ridge Center",23,23,173,7.52,173,0,7.52]
[2861,"Pines Lakes Elementary",47,47,1020,21.7,958,0,20.38]
[1881,"Pines Middle",72,64.8,1452,20.17,1295,51,10.53]
[2811,"Pinewood Elementary",54,54,1044,19.33,1156,4,19.93]
[2571,"Pioneer Middle",74,66.6,1761,23.8,1679,8,20.48]
[1901,"Piper Senior High",153,145.35,3433,22.44,3676,0,24.03]
[941,"Plantation Elementary",48,48,863,17.98,746,0,15.54]
[551,"Plantation Middle",55,49.5,1336,24.29,1274,24,16.13]
[1251,"Plantation Park Elementary",36,36,598,16.61,558,0,15.5]
[1451,"Plantation Senior High",129,122.55,3040,23.57,3105,12,22.02]
[751,"Pompano Beach Elementary",37,37,678,18.32,645,0,17.43]
[185,"Pompano Beach Institute Of International Studies",49,49,862,17.59,1500,0,30.61]
[21,"Pompano Beach Middle",58,52.2,1215,20.95,1161,8,17.59]
[3121,"Quiet Waters Elementary",56,56,1125,20.09,1174,6,18.94]
[2721,"Ramblewood Elementary",46,46,1035,22.5,1087,0,23.63]
[2711,"Ramblewood Middle",70,63,1574,22.49,1423,12,17.35]
[2891,"Riverglades Elementary",42,42,1047,24.93,1127,0,26.83]
[151,"Riverland Elementary",39,39,683,17.51,772,2,18.83]
[3031,"Riverside Elementary",49,49,903,18.43,818,0,16.69]
[1671,"Robert C Markham Elementary",37,37,679,18.35,757,3,18.93]
[3701,"Rock Island Elementary",33,33,713,21.61,593,0,17.97]
[1851,"Royal Palm Elementary",71,71,1055,14.86,802,2,10.99]
[891,"Sanders Park Elementary",50,50,624,12.48,785,2,15.1]
[3061,"Sandpiper Elementary",47,47,930,19.79,955,8,17.36]
[3401,"Sawgrass Elementary",49,49,1032,21.06,1178,4,22.23]
[3431,"Sawgrass Springs Middle",63,56.7,1330,21.11,1057,0,16.78]
[2871,"Sea Castle Elementary",44,44,942,21.41,1163,0,26.43]
[601,"Seagull School",41,41,426,10.39,426,0,10.39]
[1891,"Seminole Middle",66,59.4,1364,20.67,1365,0,20.68]
[1811,"Sheridan Hills Elementary",37,37,717,19.38,779,0,21.05]
[1321,"Sheridan Park Elementary",51,51,846,16.59,684,0,13.41]
[1051,"Sheridan Technical Center",66,66,0,0,0,0,0]
[3371,"Silver Lakes Elementary",48,48,1025,21.35,1020,0,21.25]
[2971,"Silver Lakes Middle",57,51.3,1184,20.77,1169,0,20.51]
[3491,"Silver Palms Elementary",60,60,1169,19.48,1286,12,17.86]
[3081,"Silver Ridge Elementary",50,50,1079,21.58,1065,6,19.02]
[3581,"Silver Shores Elementary",49,49,1220,24.9,1038,0,21.18]
[3331,"Silver Trail Middle",100,90,2423,24.23,2607,0,26.07]
[171,"South Broward Senior High",96,91.2,2429,25.3,2565,0,26.72]
[2351,"South Plantation Senior High",100,95,2638,26.38,3044,12,27.18]
[921,"Stephen Foster Elementary",38,38,727,19.13,761,6,17.3]
[691,"Stirling Elementary",42,42,877,20.88,914,6,19.04]
[3011,"Stoneman Douglas Senior High",156,148.2,4373,28.03,5169,0,33.13]
[211,"Stranahan Senior High",98,93.1,2236,22.82,2208,12,20.07]
[611,"Sunland Park Elementary",32,32,441,13.78,381,0,11.91]
[251,"Sunrise Middle",69,62.1,1468,21.28,1442,0,20.9]
[3661,"Sunset Lakes Elementary",47,47,890,18.94,1002,0,21.32]
[422,"Sunset Learning Center",26,26,147,5.65,147,0,5.65]
[1171,"Sunshine Elementary",45,45,1042,23.16,1045,6,20.49]
[2621,"Tamarac Elementary",55,55,1250,22.73,1402,0,25.49]
[571,"Tedder Elementary",41,41,866,21.12,759,12,14.32]
[3151,"Tequesta Trace Middle",70,63,1725,24.64,1572,8,20.15]
[1021,"The Quest Center",29,29,116,4,116,0,4]
[3291,"Thurgood Marshall Elementary",45,45,665,14.78,595,0,13.22]
[3481,"Tradewinds Elementary",59,59,1083,18.36,1109,4,17.6]
[731,"Tropical Elementary",45,45,960,21.33,843,0,18.73]
[1621,"Village Elementary",56,56,1014,18.11,1105,4,18.42]
[3321,"Virginia Shuman Young Elementary",40,40,831,20.78,838,0,20.95]
[321,"Walker Elementary (Magnet)",57,57,947,16.61,899,16,12.32]
[3001,"Walter C Young Middle",88,79.2,1841,20.92,1934,12,19.34]
[511,"Watkins Elementary",49,49,943,19.24,870,0,17.76]
[2881,"Welleby Elementary",44,44,1023,23.25,1135,6,22.7]
[161,"West Hollywood Elementary",39,39,890,22.82,1022,4,23.77]
[2681,"Westchester Elementary",62,62,1235,19.92,1418,6,20.85]
[2831,"Western Senior High",92,87.4,2266,24.63,2430,24,20.95]
[3871,"Westglades Middle",72,64.8,1801,25.01,2132,0,29.61]
[2052,"Westpine Middle",63,56.7,1492,23.68,1422,6,20.61]
[631,"Westwood Heights Elementary",51,51,790,15.49,923,0,18.1]
[452,"Whiddon-Rogers Education Center",60,60,1323,22.05,1323,0,22.05]
[1752,"Whispering Pines Exceptional Education Center",20,20,274,13.7,274,0,13.7]
[1071,"William Dandy Middle",68,61.2,1381,20.31,996,0,14.65]
[1291,"William T McFatter Technical Center",75,75,578,7.71,600,0,8]
[191,"Wilton Manors Elementary",37,37,652,17.62,865,0,23.38]
[991,"Wingate Oaks Center",37,37,92,2.49,92,0,2.49]
[3091,"Winston Park Elementary",58,58,1273,21.95,1493,8,22.62]
[]
["2b2e.","Broward Total",12814,12384.450000000004,259053,"District Avg 20",273150,2911,"District Avg 17"]
[]
[]
["2b2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[null,"Please see attached explanation of work plan for additional details"]
[null,"Site                              ",null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08","5 YEAR AVERAGE"]
[1741,"ANDERSON, BOYD H. HIGH",null,0,0,0,0,0,0]
[1791,"APOLLO MIDDLE",null,0,0,0,0,0,0]
[2221,"ATLANTIC VOCATIONAL CENTER",null,116,116,116,116,116,116]
[2511,"ATLANTIC WEST ELEMENTARY",null,76,38,38,38,38,45.6]
[343,"ATTUCKS MIDDLE",null,0,0,0,0,0,0]
[2611,"BAIR MIDDLE",null,548,141,141,141,141,222.4]
[2001,"BANYAN ELEMENTARY",null,64,64,64,64,64,64]
[641,"BAYVIEW ELEMENTARY",null,0,0,0,0,0,0]
[201,"BENNETT ELEMENTARY",null,0,0,0,0,0,0]
[341,"BETHUNE, MARY M. ELEMENTARY",null,407,407,407,407,407,407]
[971,"BOULEVARD HEIGHTS ELEMENTARY",null,0,0,0,0,0,0]
[871,"BRIGHT HORIZONS CENTER",null,0,0,0,0,0,0]
[811,"BROADVIEW ELEMENTARY",null,0,0,0,0,0,0]
[501,"BROWARD ESTATES ELEMENTARY",null,182,182,182,182,182,182]
[1382,"CASTLE HILL ANNEX",null,0,0,0,0,0,0]
[1461,"CASTLE HILL ELEMENTARY",null,260,114,114,114,114,143.2]
[2641,"CENTRAL PARK ELEMENTARY",null,32,32,32,32,32,32]
[3771,"CHALLENGER ELEMENTARY",null,0,0,0,0,0,0]
[2961,"CHAPEL TRAIL ELEMENTARY",null,230,230,230,230,230,230]
[1421,"COCONUT CREEK ELEMENTARY",null,0,0,0,0,0,0]
[1681,"COCONUT CREEK HIGH",null,54,27,27,27,27,32.4]
[3741,"COCONUT PALM ELEMENTARY",null,210,210,210,210,210,210]
[231,"COLBERT ELEMENTARY",null,127,127,127,127,127,127]
[331,"COLLINS ELEMENTARY",null,65,65,65,65,65,65]
[1211,"COOPER CITY ELEMENTARY",null,38,38,38,38,38,38]
[1931,"COOPER CITY HIGH",null,0,0,0,0,0,0]
[3041,"CORAL PARK ELEMENTARY",null,38,38,38,38,38,38]
[2551,"CORAL SPRINGS ELEMENTARY",null,70,70,32,32,32,47.2]
[1151,"CORAL SPRINGS HIGH",null,91,91,91,91,91,91]
[2561,"CORAL SPRINGS MIDDLE",null,0,0,0,0,0,0]
[3111,"COUNTRY HILLS ELEMENTARY",null,146,146,146,146,146,146]
[2981,"COUNTRY ISLES ELEMENTARY",null,70,70,70,70,70,70]
[901,"CRESTHAVEN ELEMENTARY",null,0,0,0,0,0,0]
[221,"CROISSANT PARK ELEMENTARY",null,190,190,190,190,190,190]
[3222,"CROSS CREEK SCHOOL",null,190,190,190,190,190,190]
[1871,"CRYSTAL LAKE MIDDLE",null,90,90,90,90,90,90]
[2913,"CYPRESS BAY HIGH ANNEX",null,265,265,238,238,238,248.8]
[3623,"CYPRESS BAY HIGH",null,88,88,88,88,88,88]
[1781,"CYPRESS ELEMENTARY",null,0,0,0,0,0,0]
[2123,"CYPRESS RUN ALT CENTER",null,0,0,0,0,0,0]
[1071,"DANDY, WILLIAM  MIDDLE",null,0,0,0,0,0,0]
[101,"DANIA ELEMENTARY",null,114,114,38,38,38,68.4]
[2221,"DAVE THOMAS EDUCATION CENTER",null,0,0,0,0,0,0]
[2801,"DAVIE ELEMENTARY",null,102,102,102,0,0,61.2]
[11,"DEERFIELD BEACH ELEMENTARY",null,0,0,0,0,0,0]
[1711,"DEERFIELD BEACH HIGH",null,146,146,146,146,146,146]
[911,"DEERFIELD BEACH MIDDLE",null,0,0,0,0,0,0]
[391,"DEERFIELD PARK ELEMENTARY",null,0,0,0,0,0,0]
[271,"DILLARD ELEMENTARY",null,76,76,76,76,76,76]
[371,"DILLARD HIGH",null,27,27,27,27,27,27]
[3221,"DREW, CHARLES ELEMENTARY",null,0,0,0,0,0,0]
[302,"DREW, CHARLES FAMILY RESOURCE CENTER ",null,507,507,507,507,507,507]
[302,"DREW RESOURCE TEEN PARENT CENTER\u000b@ DREW FAMILY RESOURCE",null,0,0,0,0,0,0]
[721,"DRIFTWOOD ELEMENTARY",null,152,152,152,152,152,152]
[861,"DRIFTWOOD MIDDLE",null,658,658,658,620,620,642.8]
[3461,"EAGLE POINT ELEMENTARY",null,0,0,0,0,0,0]
[3441,"EAGLE RIDGE ELEMENTARY",null,0,0,0,0,0,0]
[361,"ELY HIGH",null,0,0,0,0,0,0]
[3191,"EMBASSY CREEK ELEMENTARY ",null,0,0,0,0,0,0]
[2942,"EVERGLADES ELEMENTARY",null,37,37,37,37,37,37]
[3513,"EVERGLADES HIGH ANNEX",null,987,987,987,987,987,987]
[3513,"EVERGLADES HIGH ANNEX AT Silver Lks",null,81,81,81,81,81,81]
[1641,"FAIRWAY ELEMENTARY",null,64,64,64,64,64,64]
[3622,"FALCON COVE MIDDLE",null,600,600,600,600,600,600]
[2541,"FLAMINGO ELEMENTARY",null,323,95,95,95,95,140.6]
[3391,"FLANAGAN   HIGH",null,265,265,265,265,265,265]
[851,"FLORANADA ELEMENTARY",null,0,0,0,0,0,0]
[3051,"FOREST GLEN MIDDLE",null,90,90,0,0,0,36]
[2631,"FOREST HILLS ELEMENTARY",null,38,38,0,0,0,15.2]
[951,"FORT LAUDERDALE HIGH",null,325,325,325,249,249,294.6]
[921,"FOSTER, STEPHEN ELEMENTARY",null,95,0,0,0,0,19]
[3531,"FOX TRAIL ELEMENTARY",null,166,166,0,0,0,66.4]
[3642,"GATOR RUN ELEMENTARY",null,38,38,38,38,38,38]
[2851,"GRIFFIN ELEMENTARY",null,0,0,0,0,0,0]
[592,"HALLANDALE ADULT & COMMUNITY",null,351,351,351,351,351,351]
[131,"HALLANDALE ELEMENTARY",null,254,254,216,216,216,231.2]
[403,"HALLANDALE HIGH",null,0,0,0,0,0,0]
[491,"HARBORDALE ELEMENTARY",null,0,0,0,0,0,0]
[3131,"HAWKES BLUFF ELEMENTARY",null,260,260,114,114,114,172.4]
[102,"HOLLYWOOD CENTRAL ANNEX",null,320,320,320,320,320,320]
[121,"HOLLYWOOD CENTRAL ELEMENTARY",null,95,95,95,95,95,95]
[111,"HOLLYWOOD HILLS ELEMENTARY",null,284,284,284,284,284,284]
[1661,"HOLLYWOOD HILLS HIGH",null,106,106,106,68,68,90.8]
[1761,"HOLLYWOOD PARK ELEMENTARY",null,0,0,0,0,0,0]
[2531,"HORIZON ELEMENTARY",null,32,32,32,32,32,32]
[1971,"HUNT, JAMES S. ELEMENTARY",null,32,32,32,32,32,32]
[3471,"INDIAN RIDGE MIDDLE",null,120,90,30,30,30,60]
[3181,"INDIAN TRACE ELEMENTARY",null,146,146,146,146,146,146]
[1611,"KING, MARTIN LUTHER ELEMENTARY",null,0,0,0,0,0,0]
[831,"LAKE FOREST ELEMENTARY",null,165,165,165,165,165,165]
[3591,"LAKESIDE ELEMENTARY",null,38,38,38,38,38,38]
[621,"LARKDALE ELEMENTARY",null,0,0,0,0,0,0]
[1701,"LAUDERDALE LAKES MIDDLE",null,30,30,30,30,30,30]
[431,"LAUDERDALE MANORS ELEMENTARY",null,0,0,0,0,0,0]
[1391,"LAUDERHILL MIDDLE",null,122,122,122,122,122,122]
[1381,"LAUDERHILL P. T.  ELEMENTARY",null,0,0,0,0,0,0]
[1091,"LLOYD ESTATES ELEMENTARY",null,32,32,32,32,32,32]
[3101,"LYONS CREEK MIDDLE",null,81,81,81,0,0,48.6]
[2741,"MAPLEWOOD ELEMENTARY",null,422,422,422,422,422,422]
[1161,"MARGATE ELEMENTARY",null,0,0,0,0,0,0]
[581,"MARGATE MIDDLE",null,30,30,30,30,30,30]
[1671,"MARKHAM, ROBERT C. ELEMENTARY",null,0,0,0,0,0,0]
[3291,"MARSHALL, THURGOOD ELEM.",null,0,0,0,0,0,0]
[241,"MCARTHUR HIGH",null,38,38,38,38,38,38]
[1291,"MCFATTER, WILLIAM T. VO-TECH HIGH",null,95,95,95,95,95,95]
[841,"MCNAB ELEMENTARY",null,0,0,0,0,0,0]
[481,"MCNICOL MIDDLE",null,0,0,0,0,0,0]
[761,"MEADOWBROOK ELEMENTARY",null,64,64,64,64,64,64]
[531,"MIRAMAR ELEMENTARY",null,0,0,0,0,0,0]
[1751,"MIRAMAR HIGH",null,27,27,27,27,27,27]
[1841,"MIRROR LAKE ELEMENTARY",null,0,0,0,0,0,0]
[2691,"MORROW ELEMENTARY",null,32,32,32,32,32,32]
[881,"NEW RIVER MIDDLE",null,62,62,62,62,62,62]
[2671,"NOB HILL ELEMENTARY",null,0,0,0,0,0,0]
[561,"NORCREST ELEMENTARY",null,0,0,0,0,0,0]
[521,"NORTH ANDREWS GARDENS ELEMENTARY",null,0,0,0,0,0,0]
[3651,"NORTH AREA SCHOOL OF CHOICE",null,0,0,0,0,0,0]
[1191,"NORTH FORK ELEMENTARY",null,0,0,0,0,0,0]
[2231,"NORTH LAUDERDALE ELEMENTARY",null,0,0,0,0,0,0]
[41,"NORTH SIDE ELEMENTARY",null,0,0,0,0,0,0]
[1241,"NORTHEAST HIGH",null,0,0,0,0,0,0]
[1282,"NOVA BLANCHE FORMAN ELEMENTARY",null,64,64,64,64,64,64]
[1271,"NOVA EISENHOWER D. D. ELEMENTARY",null,0,0,0,0,0,0]
[1281,"NOVA HIGH",null,0,0,0,0,0,0]
[1311,"NOVA MIDDLE",null,60,60,60,60,60,60]
[31,"OAKLAND PARK ELEMENTARY",null,210,210,0,0,0,84]
[461,"OAKRIDGE ELEMENTARY",null,0,0,0,0,0,0]
[471,"OLSEN MIDDLE",null,0,0,0,0,0,0]
[711,"ORANGE BROOK ELEMENTARY",null,32,32,32,32,32,32]
[1831,"ORIOLE ELEMENTARY",null,0,0,0,0,0,0]
[3311,"PALM COVE ELEMENTARY",null,0,0,0,0,0,0]
[1131,"PALMVIEW ELEMENTARY",null,0,0,0,0,0,0]
[3571,"PANTHER RUN ELEMENTARY",null,0,0,0,0,0,0]
[1951,"PARK RIDGE ELEMENTARY",null,70,70,70,70,70,70]
[3171,"PARK SPRINGS ELEMENTARY",null,0,0,0,0,0,0]
[3781,"PARK TRAILS ELEMENTARY",null,0,0,0,0,0,0]
[3631,"PARKSIDE ELEMENTARY",null,76,76,76,76,76,76]
[701,"PARKWAY MIDDLE",null,1337,1337,990,990,990,1128.8]
[2071,"PASADENA LAKES ELEMENTARY",null,32,32,32,32,32,32]
[2661,"PEMBROKE LAKES ELEMENTARY",null,0,0,0,0,0,0]
[1221,"PEMBROKE PINES ELEMENTARY",null,198,198,64,64,64,117.6]
[1631,"PERRY, ANNABEL C. ELEMENTARY",null,70,70,70,70,70,70]
[1011,"PERRY, HENRY D. MIDDLE",null,0,0,0,0,0,0]
[931,"PETERS ELEMENTARY",null,0,0,0,0,0,0]
[653,"PINE RIDGE CENTER",null,0,0,0,0,0,0]
[2861,"PINES LAKES ELEMENTARY",null,0,0,0,0,0,0]
[1881,"PINES MIDDLE",null,291,291,291,0,0,174.6]
[2811,"PINEWOOD ELEMENTARY",null,0,0,0,0,0,0]
[2571,"PIONEER MIDDLE",null,134,134,104,104,104,116]
[1901,"PIPER HIGH",null,621,621,162,162,162,345.6]
[3691,"PLANTATION ELEMENTARY",null,0,0,0,0,0,0]
[1451,"PLANTATION HIGH",null,487,487,487,487,487,487]
[551,"PLANTATION MIDDLE",null,0,0,0,0,0,0]
[1251,"PLANTATION PARK ELEMENTARY",null,0,0,0,0,0,0]
[751,"POMPANO BEACH ELEMENTARY",null,32,32,32,32,32,32]
[185,"POMPANO BEACH INSTITUTE FOR INTERNATIONAL STUDIES",null,0,0,0,0,0,0]
[21,"POMPANO BEACH MIDDLE",null,0,0,0,0,0,0]
[3121,"QUIET WATERS ELEMENTARY",null,412,32,32,32,32,108]
[2721,"RAMBLEWOOD ELEMENTARY",null,32,32,32,32,32,32]
[2711,"RAMBLEWOOD MIDDLE",null,30,30,30,30,30,30]
[2121,"RICKARDS MIDDLE",null,0,0,0,0,0,0]
[2891,"RIVERGLADES ELEMENTARY",null,0,0,0,0,0,0]
[151,"RIVERLAND ELEMENTARY",null,0,0,0,0,0,0]
[3031,"RIVERSIDE ELEMENTARY",null,97,97,97,97,97,97]
[681,"ROCK ISLAND ELEMENTARY",null,0,0,0,0,0,0]
[1851,"ROYAL PALM ELEMENTARY",null,304,266,266,266,266,273.6]
[891,"SANDERS PARK ELEMENTARY",null,38,38,38,38,38,38]
[3061,"SANDPIPER ELEMENTARY",null,0,0,0,0,0,0]
[3401,"SAWGRASS ELEMENTARY",null,0,0,0,0,0,0]
[3431,"SAWGRASS SPRINGS MIDDLE",null,0,0,0,0,0,0]
[2871,"SEA CASTLE ELEMENTARY",null,30,30,30,30,30,30]
[601,"SEAGULL SCHOOL",null,116,116,116,116,116,116]
[1891,"SEMINOLE MIDDLE",null,30,30,30,30,30,30]
[1811,"SHERIDAN HILLS ELEMENTARY",null,0,0,0,0,0,0]
[1321,"SHERIDAN PARK ELEMENTARY",null,0,0,0,0,0,0]
[1051,"SHERIDAN VOCATIONAL CENTER",null,95,95,95,95,95,95]
[3371,"SILVER LAKES ELEMENTARY",null,0,0,0,0,0,0]
[2971,"SILVER LAKES MIDDLE",null,0,0,0,0,0,0]
[3491,"SILVER PALMS ELEMENTARY",null,128,128,128,128,128,128]
[3081,"SILVER RIDGE ELEMENTARY",null,76,76,76,76,76,76]
[3581,"SILVER SHORES ELEMENTARY",null,0,0,0,0,0,0]
[3331,"SILVER TRAIL MIDDLE ",null,127,127,127,127,127,127]
[405,"SOUTH AREA ALTERNATIVE CENTER",null,0,0,0,0,0,0]
[171,"SOUTH BROWARD HIGH",null,0,0,0,0,0,0]
[2351,"SOUTH PLANTATION HIGH",null,0,0,0,0,0,0]
[691,"STIRLING ELEMENTARY",null,70,70,70,70,70,70]
[3011,"STONEMAN DOUGLAS HIGH ",null,162,162,0,0,0,64.8]
[211,"STRANAHAN HIGH",null,102,102,0,0,0,40.8]
[611,"SUNLAND PARK ELEMENTARY",null,0,0,0,0,0,0]
[251,"SUNRISE MIDDLE",null,0,0,0,0,0,0]
[422,"SUNSET SCHOOL",null,0,0,0,0,0,0]
[1171,"SUNSHINE ELEMENTARY",null,0,0,0,0,0,0]
[2621,"TAMARAC ELEMENTARY",null,0,0,0,0,0,0]
[2751,"TARAVELLA, J.P. HIGH",null,0,0,0,0,0,0]
[571,"TEDDER ELEMENTARY",null,32,32,32,32,32,32]
[3621,"TEQUESTA TRACE ANNEX",null,0,0,0,0,0,0]
[3151,"TEQUESTA TRACE MIDDLE",null,90,90,90,90,90,90]
[1021,"THE QUEST CENTER",null,0,0,0,0,0,0]
[3481,"TRADEWINDS ELEMENTARY",null,331,152,152,152,152,187.8]
[731,"TROPICAL ELEMENTARY",null,70,70,70,70,70,70]
[1621,"VILLAGE ELEMENTARY",null,0,0,0,0,0,0]
[321,"WALKER/DILLARD COMMUNITY SCHL",null,95,95,95,95,95,95]
[321,"WALKER ELEMENTARY",null,38,38,38,0,0,22.8]
[511,"WATKINS ELEMENTARY",null,0,0,0,0,0,0]
[2881,"WELLEBY ELEMENTARY",null,0,0,0,0,0,0]
[161,"WEST HOLLYWOOD ELEMENTARY",null,0,0,0,0,0,0]
[2681,"WESTCHESTER ELEMENTARY",null,248,248,248,248,248,248]
[2831,"WESTERN HIGH",null,42,42,42,42,42,42]
[2913,"WESTERN HIGH 10TH GRADE CENTER",null,0,0,0,0,0,0]
[2911,"WESTERN HIGH 9TH GRADE CENTER",null,0,0,0,0,0,0]
[2052,"WESTPINE MIDDLE",null,0,0,0,0,0,0]
[631,"WESTWOOD HEIGHTS ELEMENTARY",null,0,0,0,0,0,0]
[452,"WHIDDON-ROGERS EDUCATION CENTER",null,51,51,0,0,0,20.4]
[1752,"WHISPERING PINES SCHOOL",null,190,190,190,190,190,190]
[191,"WILTON MANORS ELEMENTARY",null,0,0,0,0,0,0]
[991,"WINGATE OAKS CENTER",null,0,0,0,0,0,0]
[3091,"WINSTON PARK ELEMENTARY",null,70,70,70,70,70,70]
[3321,"YOUNG, VIRGINIA SHUMAN ELEM.",null,0,0,0,0,0,0]
[3001,"YOUNG, WALTER C. MIDDLE ",null,67,67,67,67,67,67]
[]
["2b2f1","Broward Total students in relocatables by year",null,18663,17095,14921,14257,14257,15838.6]
["2b2f2","Broward Total number of CO-FTE students projected by year",null,5665,5675,5685,5690,5695,5682]
["2b2f3","Broward Percent in relocatables by year",null,3.29,3.01,2.62,2.51,2.5,2.79]
[]
[]
["2b2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[]
[]
["2b2h.","Projects for which capital outlay and debt service funds accruing under s. 9(d), Art. XII of the State Constitution are to be used shall be identified "]
[null,"separately in priority order on a project priority list within the district facilities work program."]
[null,"Projects to be implemented with CO & DS funds in ranked order:"]
[null,"Project Description:"]
[]
[]
[null,"Elementary School \"X\"","Nine kindergarten classrooms (10,035 NSF)--225; seventeen"]
[null,"(Park Lakes Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3.420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); live ESE self contained"]
[null,null,"classrooms (6.225 NSF)--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1.781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); Food service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"S-91\"","Nine kindergarten classrooms (10,035 NSF)--225; seventeen"]
[null,"(Panther Run Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3,420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); live ESE sell contained"]
[null,null,"classrooms (6,225 NSF}--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); Food service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1.970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"Q-91\"","Nine kindergarten classrooms (10,035 NSF)--225; seventeen"]
[null,"(Silver Lakes Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3,420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); live ESE sell contained"]
[null,null,"classrooms (6,225 NSF)--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); loud service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"M-91\"","Nine kindergarten classrooms (10,035 NSF)-225; seventeen"]
[null,"(Parkside Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--289; six resource rooms (3,420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); live ESE sell contained"]
[null,null,"classrooms (6,225 NSF)--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); toed service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"N-91\"","Nine kindergarten classrooms (10.035 NSF)--225; seventeen"]
[null,"(Rock Island Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3,420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); five ESE self contained"]
[null,null,"classrooms (6.225 NSF)-50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,Th1 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); food service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"F-91\"","Nine kindergarten classrooms (10,035 NSF)--225; seventeen"]
[null,"(Challenger Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3,420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); five ESE sell contained"]
[null,null,"classrooms (6,225 NSF)--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); food service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"J-91\"","Nine kindergarten classrooms (10,035 NSF)--225; seventeen"]
[null,null,"primary classrooms (18.955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3.420 NSF); two"]
[null,null,"skill developmental labs (1,972 NSF); live ESE sell contained"]
[null,null,"classrooms (6,225 NSF)--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); Food service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Elementary School \"K-91\"","Nine kindergarten classrooms (10,035 NS9--225; seventeen"]
[null,"(Fox Trail Elementary)","primary classrooms (18,955 NSF)--425; ten intermediate"]
[null,null,"classrooms (10,260 NSF)--280; six resource rooms (3,420 NSF); two"]
[null,null,"skill developmental labs (1.972 NSF); five ESE sell contained"]
[null,null,"classrooms (6,225 NSF)--50; two supplemental instruction (790"]
[null,null,"NSF); music laboratory (1,781 NSF); art laboratory (1,401 NSF);"]
[null,null,"physical education storage (315 NSF); administration/student"]
[null,null,"services (8,472 NSF); custodial (1,733 NSF); food service (8,428"]
[null,null,"NSF); multipurpose (3,234 NSF); stage (1,970 NSF); textbook (343"]
[null,null,"NSF); media center (7,742 NSF); restrooms (2,058 NSF)."]
[]
[null,"Middle School \"GG\"","Thirty eight general classrooms (35,340 NSF)--1064; eight resource"]
[null,"(Arthur Ashe Middle)","classrooms (4,560 NSF)--120; three skills development laboratories"]
[null,null,"(2,958 NSF)--84; eleven science demo classrooms (13,101"]
[null,null,"NSF)--308; one art laboratory (1,541 NSF)--28; four USE"]
[null,null,"classrooms (5.040 NSF)--60; two supplemental (790 NSF); one"]
[null,null,"music classroom (2,371 NSF)--28; one band classroom (3,400"]
[null,null,"NSF)--50; physical education locker rooms ( 5,304 NSF); physical"]
[null,null,"education general space (14.644 NSF)--160; business education"]
[null,null,"(1,625 NSF)--24; home economics (2,160 NSF)--24; technology"]
[null,null,"education (3,855 NSF)--24; health occupations education (1,29"]
[null,null,"NSF)--24; administration student services (13,585 NSF); custodial"]
[null,null,"(2.633 NSF); food service (15.465 NSF); multipurpose (5,934 NSF);"]
[null,null,"stage (2,789 NSF); textbook (629 NSF); media center (14,206 NSF);"]
[null,null,"restrooms (3,778 NSF)"]
[]
[null,"Middle School \"HH\"","Thirty eight general classrooms (35340 NSF)--1064; eight resource"]
[null,"(Lyons Creek Middle)","classrooms (4,560 NSF)--1 20; three skills development laboratories"]
[null,null,"(2,958 NSF)--84; eleven science demo classrooms (13,101"]
[null,null,"NSF)--308; one art laboratory (1,541 NSF)--28; four ELSE"]
[null,null,"classrooms (5,040 NSF)--60; two supplemental (790 NSF); one"]
[null,null,"music classroom (2,371 NSF)-28; one band classroom (3,400"]
[null,null,"NSF)-50; physical education locker rooms ( 5,304 NSF); physical"]
[null,null,"education general space (14,644 NSF)-160; business education"]
[null,null,"(1,625 NSF)--24; home economics (2,160 NSF)-24; technology"]
[null,null,"education (3,855 NSF)--24; health occupations education (1,259"]
[null,null,"NSF)--24; administration/student services (13,585 NSF); custodial"]
[null,null,"(2,633 NSF); food service (15,465 NSF); multipurpose (5,934 NSF);"]
[null,null,"stage (2,789 NSF); textbook (629 NSF); media center (14,206 NSF);"]
[null,null,"restrooms (3,778 NSF)"]
[]
[null,"Middle School \"II\"","Thirty eight general classrooms (35,340 NSF)--1064; eight resource"]
[null,"(Millenium Middle)","classrooms (4,560 NSF)--1 20; three skills development laboratories"]
[null,null,"(2,958 NSF)--84; eleven science demo classrooms (13,101"]
[null,null,"NSF)-308; one art laboratory (1,541 NSF)--28; tour ESE"]
[null,null,"classrooms (5,040 NSF)--60; two supplemental (790 NSF); one"]
[null,null,"music classroom (2,371 NSF)--28; one band classroom (3,400"]
[null,null,"NSF)--50; physical education locker rooms ( 5,304 NSF); physical"]
[null,null,"education general space (14.644 NSF)-160; business education"]
[null,null,"(1,625 NSF)-24; home economics (2,160 NSF)-24; technology"]
[null,null,"education (3,855 NSF)--24; health occupations education (1,259"]
[null,null,"NSF)--24; administration/student services (13,585 NSF); custodial"]
[null,null,"(2,633 NSF); food service (15,465 NSF); multipurpose (5,934 NSF);"]
[null,null,"stage (2.789 NSF); textbook (629 NSF); media center (14,206 NSF);"]
[null,null,"restrooms (3,778 NSF)"]
[]
[null,"Middle School \"KK\"","Thirty eight general classrooms (35,340 NSF)--1064; eight resource"]
[null,"(Falcon Cove Middle)","classrooms (4,560 NSF)--120; three skills development laboratories"]
[null,null,"(2,958 NSF)-84; eleven science demo classrooms (13,101"]
[null,null,"NSF)--308; one art laboratory (1,541 NSF)-28; four ESE"]
[null,null,"classrooms (5.040 NSF)--60; two supplemental (790 NSF); one"]
[null,null,"music classroom (2,371 NSF)--28; one band classroom (3,400"]
[null,null,"NSF)-50; physical education locker rooms (5,304 NSF); physical"]
[null,null,"education general space (14,644 NSF)--160; business education"]
[null,null,"(4,625 NSF)--24; home economics (2,160 NSF)---24; technology"]
[null,null,"education (3,855 NSF)--24; health occupations education (1,259"]
[null,null,"NSF)--24; administration/student services (13,585 NSF); custodial"]
[null,null,"(2,633 NSF); food service (15,465 NSF); multipurpose (5,934 NSF);"]
[null,null,"stage (2,789 NSF); textbook (629 NSF); media center (14,206 NSF);"]
[null,null,"restrooms (3,778 NSF)"]
[]
[null,"High School \"FFF\"","Fifty six general education classroom (47,376 NSF)--1568; twelve"]
[null,null,"resource room (6,480 NSF); two skills development laboratories"]
[null,null,"(1,972 NSF)--56; eight science demonstration classrooms (17,660"]
[null,null,"NSF)--224; two art laboratory (3.374 NS9--48; four 1~SE classrooms"]
[null,null,"(5,280)-60; Four resource rooms (3,468 NSF); supplementary"]
[null,null,"instruction (790 NSF); musk (2,441 NSF)--50; band (3,654)"]
[null,null,"NSF)--50; physical education locker rooms (8,042 NSF); physical"]
[null,null,"education general space fl~ `10 NSF)--160; agricultural education"]
[null,null,"(4,140 NSF)-20; business education (9,858 NSF)--144;"]
[null,null,"distributive/diversified education (2,1% NSF)-48; small"]
[null,null,"distributive/diversified (3,760 NSF)--48; home economics (7,623"]
[null,null,"NSF)--72; small home economics (1.250 N59-20; large"]
[null,null,"home economics (2,740 NSF)--24; technology education (5,2%"]
[null,null,"NSF)---48; medium technology (11,355 NSF)-72; large technology"]
[null,null,"(5,145 NSF9--24; small industrial education (1,930 NSF)--24;"]
[null,null,"medium industrial (14,120 NSF)--80; large industrial (49.690"]
[null,null,"NSF)--160; health occupations education (1,499 NSF); public"]
[null,null,"service education (3,030 NSF)--20; administration (24,736 NSF);"]
[null,null,"custodial (3,673 NSF); food service (23,595 NSF) auditorium (8,231"]
[null,null,"NSF); multipurpose (9,054 NSF); stage (3,834 NSF); textbook"]
[null,null,"storage (960 NSF) student storage (1,372 NSF); public use facilities"]
[null,null,"(1,602 NSF); school media center (21,126 NSF); restrooms (5.762"]
[null,null,"NSF)"]
[]
[null,"High School \"GGG\"","Fifty six general education classroom (47,376 NSF)--1 568; twelve"]
[null,"(Monarch High)","resource room (6,480 NSF); two skills development laboratories"]
[null,null,"(1,972 NSF)-56; eight science demonstration classrooms (17,6W"]
[null,null,"NSF)--224; two art laboratory (3,374 NSF)-48; four ESE classrooms"]
[null,null,"(5.280)-60; four resource rooms (3,468 NSF); supplementary"]
[null,null,"instruction (790 NSF); music (2,441 NSF)-50; band (3,650"]
[null,null,"NJSF)--50; physical education locker rooms (8,042 NSF); physical"]
[null,null,"education general space (22,230 NS9-160; agricultural education"]
[null,null,"(4,140 NSF)--20; business education (9,858 NSF)-144;"]
[null,null,"distributive/diversified education (2,1% NSF)--48; small"]
[null,null,"distributive/diversified (3,760 NSF)--48; home economics (7,623"]
[null,null,"NSF)--72; small home economics (1,250 NSF)-20; large"]
[null,null,"home economics (2,740 NSF)--24; technology education (5,290"]
[null,null,"NSF)-48; medium technology (11,355 NSF)-72; large technology"]
[null,null,"(5,145 NSF)--24; small industrial education (1,930 NSF)--24;"]
[null,null,"medium industrial (14,120 NSF)--80; large industrial (49,690"]
[null,null,"NSF)--160; health occupations education (1,499 NSF); public"]
[null,null,"service education (3,030 NSF)--20; administration (24,736 NSF);"]
[null,null,"custodial (3,673 NSF); food service (23,595 NSF) auditorium (8,231"]
[null,null,"NSF); multipurpose (9,054 NSF); stage (3,834 NSF); textbook"]
[null,null,"storage (960 NSF) student storage (1,372 NSF); public use facilities"]
[null,null,"(1,602 NSF); school media center (21,126 NSF); restrooms (5,762"]
[null,null,"NSF)"]
[]
[null,"High School \"HHH\"","Fifty six general education classroom (47,376 NSF)--1568; twelve"]
[null,"(Cypress Bay High)","resource room (6,480 NSF); two skills development laboratories"]
[null,null,"(1,972 NSF)--56; eight science demonstration classrooms (17.660"]
[null,null,"NSF)--224; two art laboratory (3,374 NSF)--48; four ESE classrooms"]
[null,null,"(5,280)--60; Four resource rooms (3,468 NSF); supplementary"]
[null,null,"instruction (790 NSF); musk (2,441 NSF)-50; band (3,650"]
[null,null,"N59-50; physical education locker rooms (8,042 NSF); physical"]
[null,null,"education general space (22.230 NSF)--160; agricultural education"]
[null,null,"(4,140 NSF)--20; business education (9.858 NSF)-144;"]
[null,null,"distributive/diversified education (2.196 NSF)--48; small"]
[null,null,"distributive/diversified (3,760 NSF)--48; home economics (7,623"]
[null,null,"NSF)--72; small home economics (1,250 NSF)-20; large"]
[null,null,"home economics (2,740 NSF)--24; technology education (5,290"]
[null,null,"NSF)--4$; medium technology v (11.355 NSF)-72; large technology"]
[null,null,"(5.145 NSF)--24; small industrial education (1,930 NSF)--24;"]
[null,null,"medium industrial (14,120 NSF)-80; large industrial (49,690"]
[null,null,"NSF)--160; health occupations education (1,499 NSF); public"]
[null,null,"service education (3,030 NSF)-20; administration (24,736 NSF);"]
[null,null,"custodial (3,673 NSF); food service (23,595 NSF) auditorium (8,231"]
[null,null,"NSF); multipurpose (9,054 NSF); stage (3.834 NSF); textbook"]
[null,null,"storage (*0 NSF) student storage (1,372 NSF); public use Facilities"]
[null,null,"(1,602 NSF); school media center (21,126 NSF); restrooms (5,762"]
[null,null,"NSF)"]
[]
[null,"Stranahan High School","Renovations:"]
[null,null,"Renovate building(s) 02 (16fl5 NSF)."]
[]
[null,null,"New Construction:"]
[null,null,"Expand science building for magnet science (13350 NSF) --120;"]
[null,null,"media, home economics, business and vocational educational arid"]
[null,null,"physical education (21126 NSF) --; distributive/d diversified"]
[null,null,"education (5956 NSF) --96; home economics (2740 NSF) --24;"]
[null,null,"technology education (11355 NSF:) --72; industrial education"]
[null,null,"(14 120 NSF) --80; health occupations education (1499 NSF) --24;"]
[null,null,"public service education (3030 NSF) --20; business education (9858"]
[null,null,"NSF) --144."]
[]
[null,"McFatter Tech","Remodeling:"]
[null,null,"None"]
[]
[null,null,"Renovations:"]
[null,null,"None"]
[]
[null,null,"New Construction"]
[null,null,"Twenty senior high classrooms, four science demonstration"]
[null,null,"laboratories (21684 NSF) -720; media center (9907 NSF)."]
[]
[null,"Whiddon Rogers Ed Ctr","Remodeling:"]
[null,null,"Remodel building 03,04,05,06,07,08,09,11,13 to adult programs"]
[null,null,"(58086 NSF) --538; remodel building 15,16,17 to adult programs"]
[null,null,"(17698 NSF) --237; remodel building 10,12,14 to infant and child"]
[null,null,"care (12093 NSF) -Minus 276."]
[]
[]
[null,null,"Renovations:"]
[null,null,"Renovate building(s) 02, (Kitchen) (2367 NSF)."]
[]
[null,"Equipment","Additional or replacement of equipment for existing school"]
[null,null,"buildings recommended for continued use in this survey report"]
[null,null,"as provided in Section 2.1(4)(e)1 b.,SREF."]
[]
[null,"Site Acquisition","Purchase sites for educational and ancillary facilities for future use"]
[null,null,"beyond the projection period of this survey as provided in Section"]
[null,null,"1.4(1 )(2)(3)(4)(5), SREF."]
[]
[null,"Sunland Park Elementary School","Site Expansion - Six Acres"]
[]
[null,"Westwood Heights Elementary School","Remodeling"]
[null,null,"Convert building 06, rooms 606-606c to administration/teacher"]
[null,null,"plan. (2032 NSF); remodel building 11, rooms 929-930 & 933-934"]
[null,null,"to kindergarten classrooms (5468 NSF); remodel building"]
[null,null,"corridors 100a & 300 to (3584 NSF);"]
[]
[null,null,"Renovations"]
[null,null,"Renovate building(s) 02, 10,11, and 14 (31425 NSF)."]
[]
[null,null,"New Construction:"]
[null,null,"Stage (1970 NSF); eight primary classrooms (9280 NSF) --200; ten"]
[null,null,"intermediate classrooms (11600 NSF) --280; live ESE classrooms"]
[null,null,"(6225 NSF) --50; six resource rooms (3420 NSF); physical education"]
[null,null,"office and storage (315 NSF); multipurpose room (3234 NSF); food"]
[null,null,"service (8428 NSF); custodial (1733 NSF); music (1781 NSF)."]
[]
[null,"Sunshine Elementary School","New Construction"]
[null,null,"Stage/Support (1970 NSF); food service (8,428 NSF); multipurpose"]
[null,null,"(3234 NSF); physical education (370 NSF); custodial (1733 NSF);"]
[null,null,"two primary classrooms (2318 NSF)--5O; two kindergarten"]
[null,null,"classrooms (2318 NSF)--50."]
[]
[null,"Deerfield Beach Middle School","Remodeling:"]
[null,null,"Remodel building 03, rooms 161-162 to media (6538 NSF);"]
[null,null,"remodel building 04, rooms 165-165K to media (3418 NSF)."]
[]
[null,null,"Renovations:"]
[null,null,"Renovate building(s) 05 (6724 NSF); building(s) 01(28926 NSF)."]
[]
[null,null,"New Construction"]
[null,null,"Nineteen general classrooms (17670 NSF) --532; custodial (2367"]
[null,null,"NSF); physical education (1748 NSF); textbook storage (229 NSF);"]
[null,null,"skills development lab (1040 NSF) --30; public restrooms (360"]
[null,null,"NSF); administration (5732 NSF); art lab (1541 NSF) --28; physical"]
[null,null,"education lockers (7746 NSF) -160; student restrooms (1858 NSF);"]
[null,null,"Food service (15465 NSF); vocal music (2371 NSF) --28; expand"]
[null,null,"media (2050 NSF); start restrooms (634 NSF); band classroom"]
[null,null,"(3400 NSF) --50; multipurpose (5934 NSF); tour resource rooms"]
[null,null,"(2280 NSF) --60; stage (2789 NSF); six science demo classrooms"]
[null,null,"(7146 NSF) --168; three orientation/exploration labs (5044 NSF)"]
[]
[null,"Driftwood Middle School","Remodeling"]
[null,null,"Convert building 13 to Academy of Academics Weliness magnet"]
[null,null,"(3579 NSF) -59; remodel building 12 to custodial (3517 NSF)"]
[null,null,"--Minus 40; convert building 04 to media center, three"]
[null,null,"pie-vocational classrooms/labs, three skills development labs"]
[null,null,"(21136 NSF) -Minus 125; remodel building 14 to better utilize"]
[null,null,"space (14713 NSF)."]
[]
[null,null,"Renovations:"]
[null,null,"Renovate building(s) 14(14713 NSF)."]
[]
[null,null,"New Construction"]
[null,null,"Student restrooms (1462 NSF); exceptional education suite (4718"]
[null,null,"NSF) --45; raised platform (2639 NSF); teacher planning (1805"]
[null,null,"NSF); administration (4395 NSF); two regular resource rooms"]
[null,null,"(1160 NSF) --30; music suite (4490 NSF) --78; 32 classrooms (23400"]
[null,null,"NSF) --912; Academy of Academics & Wellness (Magnet) (1552"]
[null,null,"NSF); staff lounge/dining (865 NSF); student personnel services"]
[null,null,"(2100 NSF)."]
[]
[null,"McNicol Middle School","Remodeling:"]
[null,null,"Remodel building 01,02, and 03, rooms to area administration"]
[null,null,"offices (27672 NSF)."]
[]
[null,null,"New Construction"]
[null,null,"Thirty eight general classrooms (35340 NSF) --1064; Eight resource"]
[null,null,"classrooms (4560 NSF) --120; three skills development laboratories"]
[null,null,"(2958 NSF) -84; eleven science demo classrooms (13101 NSF)"]
[null,null,"-308; one art laboratory (1541 NSF) --28; four ESE classrooms"]
[null,null,"(5040 NSF) --60; two supplemental classrooms (790 NSF); one"]
[null,null,"music classroom (2371 NSF) --28; one band classroom (3400 NSF)"]
[null,null,"--50; physical education locker rooms (5304 NSF); physical"]
[null,null,"education general space (14644 NSF) --160; business ~education"]
[null,null,"(1625 NSF) --24; home economics (2160 NSF) --24; technology"]
[null,null,"education (3855 NSF) --24; health occupations education (1259"]
[null,null,"NSF) --24; administration/student services (13585 NSF); custodial"]
[null,null,"(2633 NSF); food service (15465 NSF); multipurpose 5934 NSF);"]
[null,null,"stage (2789 NSF); textbook (629 NSF); media center (14206 NSF);"]
[null,null,"restrooms (3778 NSF)."]
[]
[null,"Parkway Middle School","Remodeling:"]
[null,null,"Remodel building 02, rooms 105,104 to kitchen/dining (9465"]
[]
[]
[null,null,"Renovations:"]
[null,null,"Renovate building(s) 20,19(15311 NSF); building(s) 02, 10, 13,19,"]
[]
[]
[null,null,"New Construction:"]
[null,null,"One orientation/exploration lab (1259 NSF) --24; two"]
[null,null,"supplemental instruction (790 NSF); musk program (1000 NSF);"]
[null,null,"physical education locker rooms (475 NSF); gym seating (5354"]
[null,null,"NSF); seven science demonstration classrooms (8337 NSF) -1%;"]
[null,null,"eleven classrooms (10230 NSF) -308; textbook storage (629 NSF);"]
[null,null,"multipurpose/stage (8723 NSF); administrative spaces (1722"]
[null,null,"NSF); media center (8260 NSF); food service (8899 NSF); teacher"]
[null,null,"lounge (283 NSF); teacher planning (1774 NSF); tour resource"]
[null,null,"rooms (2280 NSF) --60."]
[]
[null,"Sunset School","New Construction:"]
[null,null,"Physical education (512 NSF); one general science lab (1643 NSF)"]
[null,null,"--12; [SE grades (N-12) (22095 NSF) -194; four resource rooms"]
[null,null,"(2100 NSF); three special vocational programs (3) (7114 NSF) --51;"]
[null,null,"two vocational resource spaces (2259 NSF) -22; media center (3120'"]
[null,null,"NSF); administration/ student services (11669 NSF); custodial"]
[null,null,"(1805 NSF); food service (3776 NSF); multipurpose room (3110"]
[null,null,"NSF); stage (1361 NSF); textbook Storage (149 NSF);"]
[null,null,"student/staff/public restrooms (3445 NSF)."]
[]
[null,"Plantation Elementary School","New Construction:"]
[null,null,"Nine kindergarten classrooms (11395 NSF) --225; administration"]
[null,null,"(4215 NSF); food service (6443 NSF); custodial (1753 NSF); staff"]
[null,null,"(766 NSF); stage/support (1978 NSF); media center (7675 NSF);"]
[null,null,"student personnel (1233 NSF); textbook storage (299 NSF); music"]
[null,null,"lab (2015 NSF); two student toilets (390 NSF); public restroom (200"]
[null,null,"NSF); 17 primary classrooms (19350 NSF) --425; 10 intermediate"]
[null,null,"classrooms (11505 NSF) --300; physical education (470 NSF);"]
[null,null,"exceptional education suite (6803 NSF) --48; six skills"]
[null,null,"development labs (6715 NSF); art lab (1595 NSF); multipurpose"]
[null,null,"room (3713 NSF)."]
[]
[]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["2b3","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2001,2001,2001,2001,2001,2001]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,96,127,247,11269,15778,23876]
[null,"2001 State-wide totals - Gross Sq Ft per student station: Elem low 96, avg 127, high 247; Middle low 107, avg 178, high 329; High School low 120, avg 143, high 182 ",{"$nulls":7},2,107,178,329,15083,25712,50508]
[null,"2001 State-wide totals - Cost per student station: Elem low 11,269, avg 15,778, high 23,876; Middle low 15,083 avg 25,712, high 50,508; High School low 14,229, avg 21,749, high  31,693 ",{"$nulls":7},3,120,143,182,14229,21749,31693]
[]
["2b3a.","2003-04 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2003-04 Projected",null," State Avg"," State Avg"," State Avg","2002 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Classroom Addition\tApollo Middle",null,3779789.79,308,15400,50,12272.04,null,0,0,0,12272.04,0,0,0]
[null,"Classroom Addition\tAtlantic Technical Center",null,5501370.18,568.421052631579,35000,61.57,9678.34,null,0,0,0,9678.34,0,0,0]
[null,"Med/Arts/Kitch/IEQ/HVAC\tBlanche Ely High",null,6850000,331.57894736842104,23250,70.12,20658.73,null,0,0,0,20658.73,0,0,0]
[null,"Classroom Addition\tBroadview Elementary",null,2500000,152,9120,60,16447.37,null,0,0,0,16447.37,0,0,0]
[null,"Classroom Addition\tCentral Park Elementary",null,3590270.45,304,18240,60,11810.1,null,0,0,0,11810.1,0,0,0]
[null,"Classroom Addition\tColbert Elementary",null,1296764,152,9120,60,8531.34,null,0,0,0,8531.34,0,0,0]
[null,"4 Class Addition/IEQ/HVAC/Intercom\tCooper City Elementary",null,372091.25,76,4560,60,4895.94,null,0,0,0,4895.94,0,0,0]
[null,"Classroom Addition\tCooper City High",null,5450000,284.2105263157895,20000,70.37,19175.93,null,0,0,0,19175.93,0,0,0]
[null,"Classroom Addition\tCoral Springs High",null,7000000,568.421052631579,39000,68.61,12314.81,null,0,0,0,12314.81,0,0,0]
[null,"Classroom Addition\tCypress Elementary",null,1537949.59,76,4560,60,20236.18,null,0,0,0,20236.18,0,0,0]
[null,"New School\tCypress Run Alternative / Exceptional Center",3,5359269,298,40500,135.91,17984.12,null,93,93,185,17984.12,12826,15024,22033]
[null,"24 Classrm/Addition \tDeerfield Beach High",null,10248388.03,672,45000,66.96,15250.58,null,0,0,0,15250.58,0,0,0]
[null,"New School - Area F\t\"Elementary School \"\"Y\"\" Formerly (Area F #1)\"",1,15000000,1112,128068,115.17,13489.21,null,82,82,146,13489.21,8756,12965,23176]
[null,"4 Classroom Addition\tEmbassy Creek Elementary",null,602633.13,76,4560,60,7929.38,null,0,0,0,7929.38,0,0,0]
[null,"Phased Replacement\tFort Lauderdale High",null,20178120.54,1022,145875,142.73,19743.76,null,0,0,0,19743.76,0,0,0]
[null,"Classroom Addition\tHallandale Adult/Community",null,3647802.21,336,23520,70,10856.55,null,0,0,0,10856.55,0,0,0]
[null,"Replacement School-Hallandale Elementary\tHallandale Elementary",null,12188337.02,1092,127250,116.53,11161.48,null,0,0,0,11161.48,0,0,0]
[null,"New School (West Central Region of Broward County)\t\"High School \"\"FFF\"\"\"",3,29804325,1574,198391,126.04,18935.4,null,93,93,185,18935.4,12826,15024,22033]
[null,"New School (Coral Springs)\t\"High School \"\"JJJ\"\"\"",3,41554498.8,2106,275000,130.58,19731.48,null,93,93,185,19731.48,12826,15024,22033]
[null,"Phased Replacement II of III\tHollywood Hills Elementary",null,3074728.96,228,13680,60,13485.65,null,0,0,0,13485.65,0,0,0]
[null,"Classroom Addition\tHollywood Hills High",null,5205381,568.421052631579,40000,70.37,9157.61,null,0,0,0,9157.61,0,0,0]
[null,"First Grade Class Size Reduction Classroom Addition\tLake Forest Elementary",null,1354807.6,144,8640,60,9408.39,null,0,0,0,9408.39,0,0,0]
[null,"Phased Replacement III of III\tMcArthur High",null,17287054.14,1698,205000,120.73,10180.83,null,0,0,0,10180.83,0,0,0]
[null,"Classroom Addition\tMiramar High",null,9113284.33,568.421052631579,38000,66.85,16032.63,null,0,0,0,16032.63,0,0,0]
[null,"Classroom Addition\tNob Hill Elementary",null,1529643.25,152,9120,60,10063.44,null,0,0,0,10063.44,0,0,0]
[null,"Classroom Addition\tNorth Andrews Gardens Elementary",null,647439.76,76,4560,60,8518.94,null,0,0,0,8518.94,0,0,0]
[null,"New school\tNorth Area Alternative High",3,12729282.28,616,89950,146.02,20664.42,null,93,93,185,20664.42,12826,15024,22033]
[null,"Classroom Addition\tNorth Fork Elementary",null,1175000,76,4560,60,15460.53,null,0,0,0,15460.53,0,0,0]
[null,"Classroom Addition\tNova High",null,5299838.02,284.2105263157895,20000,70.37,18647.58,null,0,0,0,18647.58,0,0,0]
[null,"Classroom Addition\tNova Middle",null,2755625,374,24310,65,7367.98,null,0,0,0,7367.98,0,0,0]
[null,"Classroom Addition\tOakland Park Elementary",null,1461008.51,228,13680,60,6407.93,null,0,0,0,6407.93,0,0,0]
[null,"Phased Replacement\tOrange Brook Elementary",null,8146401.49,745,65000,87.25,10934.77,null,0,0,0,10934.77,0,0,0]
[null,"Classroom Addition\tPalm Cove Elementary",null,1779131.49,228,13680,60,7803.21,null,0,0,0,7803.21,0,0,0]
[null,"Classroom Addition\tPasadena Lakes Elementary",null,963598,114,6840,60,8452.61,null,0,0,0,8452.61,0,0,0]
[null,"Classroom Addition\t\"Perry, Annabel Elementary\"",null,3478344.94,228,13680,60,15255.9,null,0,0,0,15255.9,0,0,0]
[null,"Classroom Addition & Renovation\tPeters Elementary",null,2650312.27,152,12000,78.95,17436.26,null,0,0,0,17436.26,0,0,0]
[null,"Classroom Addition\tPine Ridge Alternative Center",null,8404798.8,338,69227,204.81,24866.27,null,0,0,0,24866.27,0,0,0]
[null,"Replacement       \tPines Middle",null,22053115.75,1122.2222222222222,195000,173.76,19651.29,null,0,0,0,19651.29,0,0,0]
[null,"Classroom Addition\tPlantation Middle",null,7616719.35,528,34320,65,14425.6,null,0,0,0,14425.6,0,0,0]
[null,"Phased Replacement \tPompano Beach High School Institute of International Studies",null,27572270,1663,205000,123.27,16579.84,null,0,0,0,16579.84,0,0,0]
[null,"Classroom Addition\tPompano Beach Middle",null,3450000,176,11440,65,19602.27,null,0,0,0,19602.27,0,0,0]
[null,"Classroom Addition\tRamblewood Elementary",null,586027.66,228,13680,60,2570.3,null,0,0,0,2570.3,0,0,0]
[null,"Classroom Addition\tRamblewood Middle",null,2505000,264,17160,65,9488.64,null,0,0,0,9488.64,0,0,0]
[null,"6 Classroom Addition \tRiverside Elementary",null,743796.93,114,6840,60,6524.53,null,0,0,0,6524.53,0,0,0]
[null,"Classroom Addition\tSanders Park Elementary",null,116145.96,38,2280,60,3056.47,null,0,0,0,3056.47,0,0,0]
[null,"Classroom Addition\tSandpiper Elementary",null,1386383.57,152,9120,60,9120.94,null,0,0,0,9120.94,0,0,0]
[null,"Classroom Addition and Cafeteria Replacement\tSheridan Park Elementary",null,950000,76,8000,105.26,12500,null,0,0,0,12500,0,0,0]
[null,"12 Classroom/Addition\tSilver Lakes Middle",null,2628748.73,264,17160,65,9957.38,null,0,0,0,9957.38,0,0,0]
[null,"Classroom Addition\tSouth Plantation High",null,7000000,284.2105263157895,20000,70.37,24629.63,null,0,0,0,24629.63,0,0,0]
[null,"Classroom Addition\tStirling Elementary",null,972189.5,114,6840,60,8527.98,null,0,0,0,8527.98,0,0,0]
[null,"Classroom Addition\tStranahan High",null,1945147,284.2105263157895,20000,70.37,6844.04,null,0,0,0,6844.04,0,0,0]
[null,"Classroom Addition / Replacement\tTedder Elementary",null,3500000,228,56750,248.9,15350.88,null,0,0,0,15350.88,0,0,0]
[null,"Class Size Reduction \tTedder Elementary",null,1969298.82,228,13680,60,8637.28,null,0,0,0,8637.28,0,0,0]
[null,"Classroom Addition\tWalker Elementary",null,3852162.49,304,18240,60,12671.59,null,0,0,0,12671.59,0,0,0]
[null,"Classroom Addition\tWelleby Elementary",null,957334.27,114,6840,60,8397.67,null,0,0,0,8397.67,0,0,0]
[null,"Classroom Addition\tWestern High",null,12319672.24,568.421052631579,38000,66.85,21673.5,null,0,0,0,21673.5,0,0,0]
[null,"12 Classroom Addition \tWhiddon-Rogers Ed Center",null,6163881.84,336,23520,70,18344.89,null,0,0,0,18344.89,0,0,0]
[null,"Classroom Addition\tWinston Park Elementary",null,2500000,152,9120,60,16447.37,null,0,0,0,16447.37,0,0,0]
[]
["2b3a.","Broward Total 2003-04",null,374305182.94000006,25164.748538011696,2551331,101.39,14874.19,{"$nulls":4},14874.19]
[]
["2b3b.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05 ","2004-05 ","2004-05 ","2004-05 ","2004-05 Projected",null," State Avg"," State Avg"," State Avg","2003 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New School  - Area G\tElementary School (Area G #1)",1,15000000,1112,128068,115.17,13489.21,null,82,107,146,13489.21,8756,12965,23176]
[null,"New School (south central-west)\t\"Middle School \"\"NN\"\"\"",2,26764645,1945,221330,113.79,13760.74,null,84,119,161,13760.74,9899,13498,17138]
[null,"New School (southwest)\t\"Middle School \"\"OO\"\"\"",2,26764645,1945,221330,113.79,13760.74,null,84,119,161,13760.74,9899,13498,17138]
[null,"Phased Replacement\tNorcrest Elementary",null,7404041.48,700,62500,89.29,10577.2,null,0,0,0,10577.2,0,0,0]
[null,"Classroom Addition\tPark Springs Elementary",null,972573,114,6840,60,8531.34,null,0,0,0,8531.34,0,0,0]
[null,"Classroom Addition and General Renovations\tSeagull School",null,1850000,60,15000,250,30833.33,null,0,0,0,30833.33,0,0,0]
["2b3b","Broward Total 2004-05",null,78755904.48,5876,655068,111.48,13402.98,{"$nulls":4},13402.98]
[]
["2b3c.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2005-06 Projected",null," State Avg"," State Avg"," State Avg","2004 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"\"New School (south central-west)\" \"Elementary School (Area D #2) Formerly \"\"Y\"\"\"",2,14757788,1112,128068,115.17,13271.39,null,84,119,161,13271.39,9899,13498,17138]
[null,"New School - Area F\t\"High School \"\"LLL\"\" (Area F)\"",3,50000000,3002,378936,126.23,16655.56,null,93,112,185,16655.56,12826,15024,22033]
[null,"Completion of Phased Replacement\tMcArthur High",null,13325777,2649,145000,54.74,5030.49,null,0,0,0,5030.49,0,0,0]
[null,"Classroom Addition\tNortheast High",null,2237565,284.2105263157895,20000,70.37,7872.91,null,0,0,0,7872.91,0,0,0]
["2b3c","Broward Total 2005-06",null,80321130,7047.210526315789,20000,2.84,11397.58,{"$nulls":4},11397.58]
[]
["2b3d.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2006-07 Projected",null," State Avg"," State Avg"," State Avg","2005 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Classroom Addition  and Kitchen/Cafeteria  renovation\tCoral Springs Middle",null,3200000,176,11440,65,18181.82,null,0,0,0,18181.82,0,0,0]
[null,"24 classroom Addition\tCypress Bay High",null,8628165.39,568,38000,66.9,15190.43,null,0,0,0,15190.43,0,0,0]
[null,"New School - Area A\tElementary School (Area A #1)",1,15000000,1112,128068,115.17,13489.21,null,82,107,146,13489.21,8756,12965,23176]
["2b3d.","Broward Total 2006-07",null,26828165.39,1856,128068,69,14454.83,{"$nulls":4},14454.83]
[]
["2b3e","2007-2008 Year","Type of School (new schools only)  Others=0","2007-08","2007-08","2007-08","2007-08","2007-08 Projected",null," State Avg"," State Avg"," State Avg","2006 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New School - Area F Elementary School (Area F #2)",1,15000000,1112,128068,115.17,13489.21,null,82,107,146,13489.21,8756,12965,23176]
[]
["2b3e","Broward Total 2007-08",null,15000000,1112,128068,115.17,13489.21,{"$nulls":4},13489.21]
[]
["2b3f","Broward 5-Year Total",null,575210382.8100001,41055.959064327486,3482535]
[]
[]
[]
[]
["2b4","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,197555976.34829998,214743346.2906021,230226341.5581545,246181027.02813458,262281266.1957746,1150987957.4209657]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,410052571,214743346.2906021,230226341.5581545,246181027.02813458,262281266.1957746,1363484552.0726657,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,9975137,7234104,8936545,12692500,13096440,51934726,0.0380897062024302]
[null,"  less amount used to purchase other vehicles",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to op. bud for minor maint/repair projects",null,35000000,40000000,40000000,35000000,30000000,180000000,0.13201469699556]
[null,"  less amount trnsfrd to op bud for salaries assoc w/maintenance/repair projects",null,0,0,0,0,0,0,0]
[null,"  less amount used for minor maint/repair projects",null,156417796,42543298,34142491,35871673,25529947,294505205,0.215994530009391]
[null,"  less amount used to purchase capital outlay equipment",null,105960821,8382962,6751182,13020000,26620000,160734965,0.117885431672594]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,89828513,103358468,126470344,131828855,133595368,585081548,0.429107573760629]
[null,"  less other (please be specific)",null,9810287,11269650,13358468,15726119,17260711,67425235,0.049450677602108,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,3060017,1954864.290602088,567311.5581544936,2041880.0281345844,16178800.195774615,23802873.07266569,0.0174573837572874,0.02]
[null,"P E C O New Construction",null,36980133,7117084.709397912,11156055,10851236,10810993,76915501.70939791,null,0.06]
[null,"P E C O Maintenance Dollars",null,18530545,5950731,8954588,9499166,9969483,52904513,null,0.04]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,8088740,1621000,1000000,1000000,1000000,12709740,null,0.01]
[null,"C O & D S maximum potential bond proceeds",null,806942,0,0,0,0,806942,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,627162186,81401270,65242928,28944367.971865416,-5264964.195774615,797485787.7760909,null,0.66]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,20419688,20419688,20419688,20419688,20419688,102098440,null,0.08]
[null,"Effort Index Grants",null,16874032,0,0,0,0,16874032,null,0.01]
[null,"Classrooms for Kids",null,43226914,0,0,0,0,43226914,null,0.04]
[null,"District Equity Recognition",null,791603,0,0,0,0,791603,null,0]
[null,"Federal Grants",null,0,0,0,0,0,0,null,0]
[null,"Impact fees received",null,42825124,10000000,8000000,8000000,8000000,76825124,null,0.06]
[null,"Private donations",null,155000,155000,155000,155000,155000,775000,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["2b4","Broward Total",null,818920924,128619638,115495570.5581545,80911338,61269000,1205216470.5581546,0.9999999999999997,0.98]
[]
[]
[]
[]
["2b5","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[1741,"Classroom Addtion/Site Improvement","Anderson, Boyd H High ",272491,{"$nulls":4},272491]
[1791,"Classroom Addition","Apollo Middle",3779790,"","","","",3779790]
[3702,"New School (Fort Lauderdale)","Arthur Robert Ashe, Jr. Middle (\"GG\")",3747330,"","","","",3747330]
[2221,"Classroom Addition","Atlantic Technical Center",5501370,"","","","",5501370]
[641,"Phased Replacement II of III","Bayview Elementary",1254089,"","","","",1254089]
[341,"Phased Replacement II","Bethune, Mary M. Elementary",10373604,"","","","",10373604]
[361,"Med/Arts/Kitch/IEQ/HVAC","Blanche Ely High",21296660,"","","","",21296660]
[811,"Classroom Addition","Broadview Elementary",6478830,"","","","",6478830]
[501,"Classroom Addition","Broward Estates Elementary",146226,"","","","",146226]
[9612,"Long Range Facilities Master Plan","Capital Planning/Programming ",75245,{"$nulls":4},75245]
[1461,"Classroom Addition / New Cafeteria / Kitchen / Multipurpose area / Stage","Castle Hill Elementary",3483755,"","","","",3483755]
[2641,"Classroom Addition","Central Park Elementary",3590270,"","","","",3590270]
[3771,"New School F-91 Elementary","Challenger Elementary ",839152,{"$nulls":4},839152]
[3741,"New School E-6 ","Coconut Palm Elementary",582957,{"$nulls":4},582957]
[231,"Classroom Addition","Colbert Elementary",1296764,"","","","",1296764]
[231,"Phased Replacement I of II","Colbert Elementary",5634818,"","","","",5634818]
[1211,"4 Class Addition/IEQ/HVAC/Intercom","Cooper City Elementary ",372091,{"$nulls":4},372091]
[1931,"Classroom Addition","Cooper City High",17044682,"","","","",17044682]
[1151,"Classroom Addition","Coral Springs High",7000000,"","","","",7000000]
[2561,"Classroom Addition  and Kitchen/Cafeteria  renovation","Coral Springs Middle",null,"","",3200000,"",3200000]
[3623,"24 Classroom Addition ","Cypress Bay High",null,"",600000,5400000,"",6000000]
[3623,"New High School","Cypress Bay High",2628165,"",null,null,"",2628165]
[1781,"Classroom Addition","Cypress Elementary",1537950,"","","","",1537950]
[3891,"New School ","Cypress Run Alt Site ",527615,{"$nulls":4},527615]
[2123,"New School","Cypress Run Alternative / Exceptional Center",5359269,"","","","",5359269]
[11,"Phased Replacement ","Deerfield Beach Elementary ",207604,{"$nulls":4},207604]
[1711,"24 Classrm/Addition ","Deerfield Beach High",10248388,"","","","",10248388]
[911,"Classroom Addition","Deerfield Beach Middle",1020000,"","","","",1020000]
[911,"Phased Replacement ","Deerfield Beach Middle ",291071,{"$nulls":4},291071]
[371,"Phased Replacement & New Arts Center","Dillard High",8068795,"","","","",8068795]
[371,"50 Classroom Bldg ","Dillard High ",64651,{"$nulls":4},64651]
[0,"Contingency","District Wide",28392324,2098433,8640174,"","",39130931]
[0,"Special Appropriations","District Wide ",750000,{"$nulls":4},750000]
[721,"Phased Replacement II of II","Driftwood Elementary",1746200,"","","","",1746200]
[861,"Classroom Addition","Driftwood Middle",2226908,"","","","",2226908]
[861,"Phase II - IV Rebuild","Driftwood Middle ",265668,{"$nulls":4},265668]
[3701,"New School N-91 Elementary","Elementary N-91/GG",339797,{"$nulls":4},339797]
[30009,"New School - Area F","Elementary School \"Y\" Formerly (Area F #1)",12275000,2725000,"","","",15000000]
[30008,"New School - Area A","Elementary School (Area A #1)",null,"",1500000,10775000,2725000,15000000]
[2914,"New School\n(south central-west)","Elementary School (Area D #2) Formerly \"Y\"",null,1613932,13143856,"","",14757788]
[30010,"New School - Area F","Elementary School (Area F #2)",null,"","",1500000,13500000,15000000]
[30011,"New School  - Area G","Elementary School (Area G #1)",null,12275000,2725000,"","",15000000]
[3191,"4 Classroom Addition","Embassy Creek Elementary ",602633,{"$nulls":4},602633]
[3301,"New School","Endeavor Primary Learning Center",3437970,"","","","",3437970]
[3731,"New School (Miramar)","Everglades High School (\"III\")",16996082,"","","","",16996082]
[3622,"New School \"KK\"","Falcon Cove Middle ",32329,{"$nulls":4},32329]
[851,"Replacement School ","Floranada Elementary ",40523,{"$nulls":4},40523]
[951,"Phased Replacement","Fort Lauderdale High",20178121,"","","","",20178121]
[951,"Stadium Design","Fort Lauderdale High",150000,"","","","",150000]
[592,"Classroom Addition","Hallandale Adult/Community",3647802,"","","","",3647802]
[593,"Replacement School-Hallandale Elementary","Hallandale Elementary",12188337,{"$nulls":4},12188337]
[403,"Stadium Design","Hallandale High",150000,"","","","",150000]
[3131,"Class Size Reduction ","Hawkes Bluff Elementary ",52489,{"$nulls":4},52489]
[3681,"New High School \"FFF\"","High School \"FFF\"",1126363,{"$nulls":4},1126363]
[30004,"New School (West Central Region of Broward County)","High School \"FFF\"",27419979,2384346,"","","",29804325]
[3861,"New School (Coral Springs)","High School \"JJJ\"",41554499,"","","","",41554499]
[30007,"New School - Area F","High School \"LLL\" (Area F)",null,5000000,35970000,9030000,"",50000000]
[111,"Phased Replacement II of III","Hollywood Hills Elementary",3074729,"","","","",3074729]
[1661,"Classroom Addition","Hollywood Hills High",5205381,"","","","",5205381]
[831,"First Grade Class Size Reduction Classroom Addition","Lake Forest Elementary",1354808,"","","","",1354808]
[831,"Phased Replacement II of II","Lake Forest Elementary",7233926,"","","","",7233926]
[3821,"New School - Elem \"O\" ","Liberty Elementary \"O\"",2028361,{"$nulls":4},2028361]
[3101,"New School \"HH\"","Lyons Creek Middle (HH)",148558,{"$nulls":4},148558]
[3831,"New School - Elem \"P\" ","Manatee Bay Elem 'P' ",2836833,{"$nulls":4},2836833]
[1161,"12 Classroom Addition","Margate Elementary ",176713,{"$nulls":4},176713]
[1161,"8 Classroom Addition","Margate Elementary ",633937,{"$nulls":4},633937]
[581,"Classroom Addition","Margate Middle",941735,"","","","",941735]
[241,"Completion of Phased Replacement","McArthur High",null,1332578,11993199,"","",13325777]
[241,"Phased Replacement III of III","McArthur High",17287054,"","","","",17287054]
[841,"Phase III of III","McNab Elementary",5730654,"","","","",5730654]
[761,"Existing Project","Meadowbrook Elementary",5173261,"","","","",5173261]
[3881,"New Middle School \"NN\"","Middle School \"NN\"",2638991,{"$nulls":4},2638991]
[30005,"New School (south central-west)","Middle School \"NN\"",2638991,24125654,"","","",26764645]
[30006,"New School (southwest)","Middle School \"OO\"",2676465,24088180,"","","",26764645]
[30015,"New School - Design","Middle School (Area D #1)",null,"",2310000,"","",2310000]
[3772,"New School Middle \"II\"","Millenium Middle II",886462,{"$nulls":4},886462]
[4772,"New School Middle \"II\"","Millenium Middle II",10000,{"$nulls":4},10000]
[1751,"Classroom Addition","Miramar High",9113284,"","","","",9113284]
[3541,"New School (Coconut Creek)","Monarch High School (\"GGG\")",7855848,"","","","",7855848]
[3581,"New Elementary","New Elementary",10382548,{"$nulls":4},10382548]
[3661,"New Elementary","New Elementary",9069456,{"$nulls":4},9069456]
[3611,"Construction Middle \"LL\"","New Relief",1193294,{"$nulls":4},1193294]
[3671,"New School Middle \"MM\"","New Renaissance Mid \"MM\"",415181,{"$nulls":4},415181]
[2671,"Classroom Addition","Nob Hill Elementary",1529643,"","","","",1529643]
[561,"Phased Replacement","Norcrest Elementary",832025,6572016,"","","",7404041]
[521,"Classroom Addition","North Andrews Gardens Elementary",647440,"","","","",647440]
[521,"Phased Replacement ","North Andrews Gardens Elementary",15805525,"","","","",15805525]
[3811,"New school","North Area Alternative High",12729282,"","","","",12729282]
[9384,"North Area Superintendent Remodel/Renovation","North Central Superintendent ",799828,{"$nulls":4},799828]
[1191,"Classroom Addition","North Fork Elementary",2170577,"","","","",2170577]
[2231,"Class Size Reduction","North Lauderdale Elementary ",774436,{"$nulls":4},774436]
[41,"New Kitchen/Cafeteria","North Side Elementary ",1466857,{"$nulls":4},1466857]
[1241,"Classroom Addition","Northeast High",null,"",2237565,"","",2237565]
[1282,"Classroom Addition","Nova Blanche Forman Elementary",612663,"","","","",612663]
[1271,"Classroom Addition","Nova Eisenhower Elementary",719196,"","","","",719196]
[1281,"Classroom Addition","Nova High",5299838,"","","","",5299838]
[1281,"Stadium Design","Nova High",147712,"","","","",147712]
[1311,"Classroom Addition","Nova Middle",38582,"","","","",38582]
[31,"Classroom Addition","Oakland Park Elementary",1461009,"","","","",1461009]
[461,"Phased Replacement","Oakridge Elementary",null,"",770792,6937128,"",7707920]
[472,"Renovation","Olsen Middle Annex",7819884,"","","","",7819884]
[711,"Phased Replacement","Orange Brook Elementary",8146401,"","","","",8146401]
[1831,"Class Size Reduction","Oriole Elementary ",1337679,{"$nulls":4},1337679]
[3311,"Classroom Addition","Palm Cove Elementary",1779131,"","","","",1779131]
[3761,"New School \"X\"","Park Lakes Elementary-X",635196,{"$nulls":4},635196]
[1951,"Classroom Addition","Park Ridge Elementary",1079586,"","","","",1079586]
[3171,"Classroom Addition","Park Springs Elementary",null,972573,"","","",972573]
[3781,"New School \"D-6\" ","Park Trails Elementary",836927,{"$nulls":4},836927]
[2071,"Classroom Addition","Pasadena Lakes Elementary",963598,"","","","",963598]
[1631,"Classroom Addition","Perry, Annabel Elementary",3478345,"","","","",3478345]
[931,"Classroom Addition & Renovation","Peters Elementary",5650312,"","","","",5650312]
[653,"Classroom Addition","Pine Ridge Alternative Center",8404799,"","","","",8404799]
[2861,"6 Classroom Addition","Pines Lakes Elementary ",587679,{"$nulls":4},587679]
[1881,"Replacement       ","Pines Middle",22053116,"","","","",22053116]
[2811,"Class Size Reduction ","Pinewood Elementary ",81880,{"$nulls":4},81880]
[1901,"Classroom Addition","Piper High ",2837925,{"$nulls":4},2837925]
[3691,"New School ","Plantation Elem Replace Site ",18939,{"$nulls":4},18939]
[1451,"Existing Project","Plantation High",3055886,"","","","",3055886]
[1451,"24 Classroom Addition ","Plantation High ",458785,{"$nulls":4},458785]
[1451,"General Renovation/Addition  Phase II","Plantation High ",7166676,{"$nulls":4},7166676]
[551,"Classroom Addition","Plantation Middle",7616719,"","","","",7616719]
[9018,"Convert to International Studies","Pompano Admin Site ",102843,{"$nulls":4},102843]
[181,"Phased Replacement ","Pompano Beach HS",12558244,{"$nulls":4},12558244]
[21,"Classroom Addition","Pompano Beach Middle",4883963,"","","","",4883963]
[21,"Phased Replacement","Pompano Beach Middle",null,"",674443,6069987,"",6744430]
[9606,"New Middle School \"OO\"","Property Mgmt/Site Acquisition",2638991,{"$nulls":4},2638991]
[2721,"4 Classroom Addition ","Ramblewood Elementary ",586028,{"$nulls":4},586028]
[2711,"Classroom Addition","Ramblewood Middle",2505000,"","","","",2505000]
[3031,"6 Classroom Addition ","Riverside Elementary ",743797,{"$nulls":4},743797]
[1851,"Classroom Addition & Cafeteria / Kitchen / Multipurpose area / Stage","Royal Palm Elementary",3714264,"","","","",3714264]
[891,"Class Size Reduction ","Sanders Park Elementary ",116146,{"$nulls":4},116146]
[3061,"Classroom Addition","Sandpiper Elementary",1386384,"","","","",1386384]
[601,"Classroom Addition and General Renovations","Seagull School",null,2835703,"","","",2835703]
[1811,"Class Size Reduction ","Sheridan Hills Elementary ",16480,{"$nulls":4},16480]
[1321,"Classroom Addition and Cafeteria Replacement","Sheridan Park Elementary",6166616,"","","","",6166616]
[2971,"12 Classroom/Addition","Silver Lakes Middle",2628749,"","","","",2628749]
[3491,"Class Size Reduction ","Silver Palms Elementary ",14585,{"$nulls":4},14585]
[171,"Replacement School ","South Broward High ",8674925,{"$nulls":4},8674925]
[2351,"Classroom Addition","South Plantation High",17037919,"","","","",17037919]
[691,"Classroom Addition","Stirling Elementary",972190,"","","","",972190]
[3011,"Stadium Design","Stoneman Douglas High",150000,"","","","",150000]
[211,"Classroom Addition","Stranahan High",1945147,"","","","",1945147]
[211,"Medical Magnet Addition ","Stranahan High ",79095,{"$nulls":4},79095]
[211,"Science Magnet Addition ","Stranahan High ",12778,{"$nulls":4},12778]
[1171,"8 Classroom Addition","Sunshine Elementary ",661927,{"$nulls":4},661927]
[2621,"Classroom Building ","Tamarac Elementary ",1040799,{"$nulls":4},1040799]
[2751,"24 Classroom Addition ","Taravella J P High ",974879,{"$nulls":4},974879]
[571,"Classroom Addition / Replacement","Tedder Elementary",7715704,"","","","",7715704]
[571,"Class Size Reduction ","Tedder Elementary ",1969299,{"$nulls":4},1969299]
[731,"4 Classroom Addition-Driveway ","Tropical Elementary ",293521,{"$nulls":4},293521]
[9077,"2 Modular Units","Twin Lakes Complex ",200000,{"$nulls":4},200000]
[1621,"Joint Project with City of Sunrise","Village Elementary",950000,"","","","",950000]
[1621,"Classroom Bldg","Village Elementary ",258356,{"$nulls":4},258356]
[321,"Classroom Addition","Walker Elementary",3852162,"","","","",3852162]
[2881,"Classroom Addition","Welleby Elementary",957334,"","","","",957334]
[2681,"8 Classroom Addition ","Westchester Elementary ",1205265,{"$nulls":4},1205265]
[2831,"Classroom Addition","Western High",12319672,"","","","",12319672]
[631,"Phased Replacement ","Westwood Heights Elementary ",29520,{"$nulls":4},29520]
[452,"12 Classroom Addition ","Whiddon-Rogers Ed Center",6163882,"","","","",6163882]
[191,"Phased Replace/Covered Walkway","Wilton Manors Elementary ",1580677,{"$nulls":4},1580677]
[3091,"Classroom Addition","Winston Park Elementary",2906405,"","","","",2906405]
[0,"Class Size Reduction (Classrooms for Kids)","District Wide",43226914,{"$nulls":4},43226914]
[2511,"Land ","Atlantic West Elementary ",300000,{"$nulls":4},300000]
[811,"Land ","Broadview Elementary ",493770,{"$nulls":4},493770]
[3731,"Site Acquisition ","Country Lakes High School III",4811,{"$nulls":4},4811]
[3721,"Site Acquisition ","Country Lakes Mid Site ",340148,{"$nulls":4},340148]
[3891,"Site Acquisition ","Cypress Run Alt Site ",1225937,{"$nulls":4},1225937]
[1711,"Land ","Deerfield Beach High ",40116,{"$nulls":4},40116]
[0,"Lease Agreement - Baudhuin Preschool (Autism Center)","District Wide",280000,280000,280000,280000,280000,1400000]
[0,"Land","District Wide",9243149,1000000,1000000,1000000,1000000,13243149]
[0,"Future Site Development ","District Wide ",7000000,{"$nulls":4},7000000]
[0,"Land Acquisition ","District Wide ",2858955,{"$nulls":4},2858955]
[0,"Site Improvements ","District Wide ",251068,{"$nulls":4},251068]
[0,"Site Improvements ","District Wide ",71455,{"$nulls":4},71455]
[3521,"Site Aquisition ","Elem J-91 Site ",13883,{"$nulls":4},13883]
[3661,"Site Acquisition ","Elem Q Sunset Lakes Dev ",4257,{"$nulls":4},4257]
[30008,"Land","Elementary School (Area A #1)",null,2000000,"","","",2000000]
[30012,"Land","Elementary School (Area A #2)",null,"","","",2000000,2000000]
[30013,"Land","Elementary School (Area D #1)",null,"","","",2000000,2000000]
[30014,"Land","Elementary School (Area F #3)",null,"","","",2000000,2000000]
[30011,"Land","Elementary School (Area G #1)",5000000,5000000,"","","",10000000]
[3541,"Land Acquisition ","High School \"GGG\"",20477,{"$nulls":4},20477]
[3861,"Site Acquisition ","High School \"JJJ\"",1215,{"$nulls":4},1215]
[30007,"Land","High School \"LLL\" (Area F)",5000000,"","","","",5000000]
[121,"Site Expansion","Hollywood Central Elementary ",162700,{"$nulls":4},162700]
[2991,"Land Development ","Huntington Elementary Site ",948015,{"$nulls":4},948015]
[3821,"Site Acquisition ","Liberty Elemtary 'O' ",39872,{"$nulls":4},39872]
[1291,"ESOL Modulars--5 Yr Loan","McFatter Voc-Tech Center",284603,{"$nulls":4},284603]
[3881,"Land","Middle School \"NN\"",3000443,"","","","",3000443]
[3811,"Site Acquisition ","N Area Alternative High School",3000301,{"$nulls":4},3000301]
[41,"Land - Purchase Chuch Property","North Side Elementary ",1234700,{"$nulls":4},1234700]
[90001,"Land","Northwest Bus Lot/Maintenance Facility",3750000,3750000,"","","",7500000]
[31,"Site Acquisition ","Oakland Park Elementary ",1433214,{"$nulls":4},1433214]
[1881,"Land ","Pines Middle ",298,{"$nulls":4},298]
[1901,"Modular Portables ","Piper High ",18420,{"$nulls":4},18420]
[9380,"Plantation Middle - PAL Parking Lot","Plantation Middle Exchange-PAL",13746,{"$nulls":4},13746]
[1251,"Site Improvement ","Plantation Park Elementary ",19681,{"$nulls":4},19681]
[9606,"Facilities Div. Consolidation ","Property Mgmt/Site Acquisition",9000000,{"$nulls":4},9000000]
[9335,"Site Acquisition ","S/W Bus Parking Facilities ",1444464,{"$nulls":4},1444464]
[9005,"Hospital Homebound Program","Sailboat Bend Complex ",11206,{"$nulls":4},11206]
[601,"Hospital Homebound Prog. Move ","Seagull School ",207739,{"$nulls":4},207739]
[171,"Site Acquisition ","South Broward High ",1094613,{"$nulls":4},1094613]
[611,"Site Aquisition ","Sunland Park Elementary ",914672,{"$nulls":4},914672]
[571,"Site Acquisition ","Tedder Elementary ",780019,{"$nulls":4},780019]
[631,"Site Acquisition ","Westwood Heights Elementary ",230000,{"$nulls":4},230000]
[0,"Portables","District Wide",17078878,6000000,6000000,6000000,6000000,41078878]
[0,"Portables","District Wide",7621001,3000000,3000000,3000000,3000000,19621001]
[0,"Capitalized Cost","District Wide",43391096,14206000,14632000,15071000,15478000,102778096]
[0,"COLA","District Wide",1186103,3760223,6418542,9048223,9686000,30099091]
[0,"Legal & Contingency","District Wide",12618237,3600000,3600000,3600000,3600000,27018237]
[{"$nulls":8},0]
["2b5.","Broward Total",null,818920924,128619638,115495571,80911338,61269000,1205216471]
[]
[]
[]
[]
["2b6","Schedule of options for generation of additional revenues by the district for expenditure on projects identified in the district facilities work "]
[null,"program which are not funded under paragraph 5 above.  Additional anticipated revenues may include SIT Program awards and Classrooms First funds."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["2b6.","Broward Total",null,0,0,0,0,0,0]
[]
[]
[]
[]
["2b7","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[1791,"Remodel Media Center to expand for excessive capacity","Apollo Middle",{"$nulls":4},839520,839520]
[2221,"New Cafeteria / Kitchen due to excessive capacity","Atlantic Technical Center",{"$nulls":4},2820615,2820615]
[2511,"New Media Center due to excessive capacity","Atlantic West Elementary",{"$nulls":4},2658498,2658498]
[2511,"New Kitchen / Dining / Multipurpose / Stage","Atlantic West Elementary",{"$nulls":4},3758525,3758525]
[343,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Attucks Middle",{"$nulls":4},1477059,1477059]
[343,"New Media Center due to excessive capacity","Attucks Middle",{"$nulls":4},3108219,3108219]
[2611,"New Media Center due to excessive capacity","Bair Middle",{"$nulls":4},2832981,2832981]
[2611,"New Multipurpose","Bair Middle",{"$nulls":4},0,0]
[2001,"Expand Kitchen","Banyan Elementary",{"$nulls":4},607221,607221]
[201,"New Media Center due to excessive capacity","Bennett Elementary",{"$nulls":4},2651782,2651782]
[361,"New Media Center due to excessive capacity","Blanche Ely High",{"$nulls":4},4031710,4031710]
[971,"Remodel Media Center to expand for excessive capacity","Boulevard Heights Elementary",{"$nulls":4},705889,705889]
[1421,"New Cafeteria / Kitchen due to excessive capacity","Coconut Creek Elementary",{"$nulls":4},3877507,3877507]
[1681,"New Media Center due to excessive capacity","Coconut Creek High",{"$nulls":4},4514595,4514595]
[231,"New Cafeteria / Kitchen due to excessive capacity","Colbert Elementary",{"$nulls":4},3861603,3861603]
[3041,"New Cafeteria / Kitchen due to excessive capacity","Coral Park Elementary",{"$nulls":4},3875902,3875902]
[2551,"New Media Center due to excessive capacity","Coral Springs Elementary",{"$nulls":4},2657462,2657462]
[1151,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Coral Springs High",{"$nulls":4},2066176,2066176]
[0,"New Media Center due to excessive capacity","Coral Springs High",{"$nulls":4},4363213,4363213]
[2981,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Country Isles Elementary",{"$nulls":4},768921,768921]
[901,"New Cafeteria / Kitchen due to excessive capacity","Cresthaven Elementary",{"$nulls":4},3882043,3882043]
[1871,"Remodel Media Center to expand for excessive capacity","Crystal Lake Community Middle",{"$nulls":4},1275080,1275080]
[1781,"New Media Center due to excessive capacity","Cypress Elementary",{"$nulls":4},2663798,2663798]
[1071,"Remodel Media Center to expand for excessive capacity","Dandy, William Middle",{"$nulls":4},920325,920325]
[2801,"New Media Center due to excessive capacity","Davie Elementary",{"$nulls":4},2669204,2669204]
[1711,"Remodel Media Center to expand for excessive capacity","Deerfield Beach High",{"$nulls":4},1689540,1689540]
[911,"New Media Center due to excessive capacity","Deerfield Beach Middle",{"$nulls":4},3015818,3015818]
[301,"New Media Center due to excessive capacity","Drew Resource Center",{"$nulls":4},804088,804088]
[721,"New Media Center due to excessive capacity","Driftwood Elementary",{"$nulls":4},2665544,2665544]
[861,"New Cafeteria / Kitchen due to excessive capacity","Driftwood Middle",{"$nulls":4},3833144,3833144]
[861,"Remodel Media Center to expand for excessive capacity","Driftwood Middle",{"$nulls":4},1149665,1149665]
[3191,"4 Classroom Addition","Embassy Creek Elementary",{"$nulls":4},891135,891135]
[2541,"New Kitchen / Dining / Multipurpose / Stage","Flamingo Elementary",{"$nulls":4},4095961,4095961]
[3051,"New Media Center due to excessive capacity","Forest Glen Middle",{"$nulls":4},2618691,2618691]
[2631,"6 Classroom Addition","Forest Hills Elementary",{"$nulls":4},1336703,1336703]
[2631,"New Media Center due to excessive capacity","Forest Hills Elementary",{"$nulls":4},2662214,2662214]
[403,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Hallandale High",{"$nulls":4},1639845,1639845]
[403,"Remodel Media Center to expand for excessive capacity","Hallandale High",{"$nulls":4},1571136,1571136]
["TBA","New School","High School \"MMM\"",{"$nulls":4},63000000,63000000]
["TBA","New School","High School \"NNN\"",{"$nulls":4},63000000,63000000]
[121,"8 Classroom Addition","Hollywood Central Elementary",{"$nulls":4},1782270,1782270]
[121,"New Cafeteria / Kitchen due to excessive capacity","Hollywood Central Elementary",{"$nulls":4},3877413,3877413]
[121,"New Media Center due to excessive capacity","Hollywood Central Elementary",{"$nulls":4},2668929,2668929]
[1761,"New Cafeteria / Kitchen due to excessive capacity","Hollywood Park Elementary",{"$nulls":4},3875020,3875020]
[2531,"New Media Center due to excessive capacity","Horizon Elementary",{"$nulls":4},2662977,2662977]
[2531,"Expand Kitchen","Horizon Elementary",{"$nulls":4},637650,637650]
[621,"New Cafeteria / Kitchen due to excessive capacity","Larkdale Elementary",{"$nulls":4},3871116,3871116]
[621,"Remodel Media Center to expand for excessive capacity","Larkdale Elementary",{"$nulls":4},500745,500745]
[1701,"Remodel Media Center to expand for excessive capacity","Lauderdale Lakes Middle",{"$nulls":4},818553,818553]
[1701,"Expand Kitchen","Lauderdale Lakes Middle",{"$nulls":4},942321,942321]
[1391,"Remodel Cafeteria / Kitchen to expand for excessive capacity","Lauderhill Middle",{"$nulls":4},990010,990010]
[1391,"Remodel Media Center to expand for excessive capacity","Lauderhill Middle",{"$nulls":4},1113436,1113436]
[1091,"2 Classroom Addition & Remodel Existing Space to 2 Classrooms","Lloyd Estates Elementary",{"$nulls":4},662918,662918]
[2741,"3 Classroom Addition","Maplewood Elementary",{"$nulls":4},668351,668351]
[581,"Remodel Media Center to expand for excessive capacity","Margate Middle",{"$nulls":4},1116990,1116990]
[1291,"New Cafeteria / Kitchen due to excessive capacity","McFatter Technical Center",{"$nulls":4},2921351,2921351]
[1291,"New Media Center due to excessive capacity","McFatter Technical Center",{"$nulls":4},2223527,2223527]
[841,"Remodel Media Center to expand for excessive capacity","McNab Elementary",{"$nulls":4},705759,705759]
["TBA","New School","Middle School \"PP\"",{"$nulls":4},30863700,30863700]
["TBA","New School","Middle School \"QQ\"",{"$nulls":4},30863700,30863700]
["TBA","New School","Middle School \"RR\"",{"$nulls":4},30863700,30863700]
[1751,"New Cafeteria / Kitchen due to excessive capacity","Miramar High",{"$nulls":4},5646395,5646395]
[1841,"Remodel Existing Space to 4 Classrooms","Mirror Lake Elementary",{"$nulls":4},760725,760725]
[2691,"New Media Center due to excessive capacity","Morrow Elementary",{"$nulls":4},2664888,2664888]
[561,"New Media Center due to excessive capacity","Norcrest Elementary",{"$nulls":4},2538085,2538085]
[1191,"Remodel Cafeteria / Kitchen to expand for excessive capacity","North Fork Elementary",{"$nulls":4},733379,733379]
[2231,"New Media Center due to excessive capacity","North Lauderdale Elementary",{"$nulls":4},2451582,2451582]
[1282,"New Cafeteria / Kitchen due to excessive capacity","Nova Blanche Forman Elementary",{"$nulls":4},3879556,3879556]
[1271,"New Cafeteria / Kitchen due to excessive capacity","Nova Eisenhower Elementary",{"$nulls":4},3872247,3872247]
[1281,"New Media Center due to excessive capacity","Nova High",{"$nulls":4},3510500,3510500]
[1951,"Expand Kitchen / Dining / Multipurpose / Stage","Park Ridge Elementary",{"$nulls":4},1336431,1336431]
[701,"New Cafeteria / Kitchen due to excessive capacity","Parkway Middle",{"$nulls":4},4837924,4837924]
[701,"New Media Center due to excessive capacity","Parkway Middle",{"$nulls":4},3682287,3682287]
[1011,"Remodel Media Center to expand for excessive capacity","Perry, Henry D. Middle",{"$nulls":4},943608,943608]
[2811,"New Media Center due to excessive capacity","Pinewood Elementary",{"$nulls":4},2677723,2677723]
[2571,"New Media Center due to excessive capacity","Pioneer Middle",{"$nulls":4},2777936,2777936]
[1901,"New Cafeteria / Kitchen due to excessive capacity","Piper High",{"$nulls":4},7707614,7707614]
[1901,"New Media Center due to excessive capacity","Piper High",{"$nulls":4},5717975,5717975]
[551,"Expand Kitchen","Plantation Middle",{"$nulls":4},975303,975303]
[2721,"Remodel Existing Space to 4 Classrooms","Ramblewood Elementary",{"$nulls":4},760725,760725]
[2711,"Expand Multipurpose","Ramblewood Middle",{"$nulls":4},1833627,1833627]
[151,"4 Classroom Addition","Riverland Elementary",{"$nulls":4},891135,891135]
[151,"New Media Center due to excessive capacity","Riverland Elementary",{"$nulls":4},2658008,2658008]
[3031,"New Cafeteria / Kitchen due to excessive capacity","Riverside Elementary",{"$nulls":4},3887081,3887081]
[1851,"Expand Media","Royal Palm Elementary",{"$nulls":4},909390,909390]
[3431,"Remodel Media Center to expand for excessive capacity","Sawgrass Springs Middle",{"$nulls":4},915271,915271]
[1891,"New Media Center due to excessive capacity","Seminole Middle",{"$nulls":4},2577404,2577404]
[1891,"Expand Kitchen","Seminole Middle",{"$nulls":4},625832,625832]
[2971,"New Media Center due to excessive capacity","Silver Lakes Middle",{"$nulls":4},2606895,2606895]
[2351,"New Cafeteria / Kitchen due to excessive capacity","South Plantation High",{"$nulls":4},5842704,5842704]
[2351,"Remodel Media Center to expand for excessive capacity","South Plantation High",{"$nulls":4},1542213,1542213]
[211,"New Cafeteria / Kitchen due to excessive capacity","Stranahan High",{"$nulls":4},5543077,5543077]
[211,"New Media Center due to excessive capacity","Stranahan High",{"$nulls":4},4112190,4112190]
[2751,"New Cafeteria / Kitchen due to excessive capacity","Taravella J P High",{"$nulls":4},7358911,7358911]
[2751,"New Media Center due to excessive capacity","Taravella J P High",{"$nulls":4},5459286,5459286]
[731,"New Media Center due to excessive capacity","Tropical Elementary",{"$nulls":4},2672207,2672207]
[511,"Remodel Media Center to expand for excessive capacity","Watkins Elementary",{"$nulls":4},780009,780009]
[2681,"New Media Center due to excessive capacity","Westchester Elementary",{"$nulls":4},2663741,2663741]
[2681,"New Kitchen / Dining / Multipurpose / Stage","Westchester Elementary",{"$nulls":4},4239319,4239319]
[2831,"New Media Center due to excessive capacity","Western High",{"$nulls":4},3684873,3684873]
[631,"New Media Center due to excessive capacity","Westwood Heights Elementary",{"$nulls":4},2677013,2677013]
[412,"Remodel Media Center to expand for excessive capacity","Whiddon-Rogers Annex",{"$nulls":4},227285,227285]
[3001,"New Cafeteria / Kitchen due to excessive capacity","Young, Walter C. Middle",{"$nulls":4},3567096,3567096]
[{"$nulls":8},0]
["2b7","Broward Total",0,0,0,0,0,466241218,466241218]
[]
["NOTE: If the sum of the totals in paragraphs 2b5. and 2b7. above DO NOT equal the total in paragraph 2b2. above, the message \"Check Totals\" appears.   "]
[null,"-- They should balance ! !"]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
[]
[]
[]
[]
["Broward  SCHOOL DISTRICT - - FACILITIES TEN (10) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the next 5 years beyond the above 5-year work plan. (years 6-10)"]
[]
[null,null,null,"2008/09 - 2012/13"]
[null,"Project","Location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"HSS/Capital Improvement Program (Maintenance)","District Wide",181481265,{"$nulls":4},181481265]
[{"$nulls":8},0]
["2b1","Broward Total",null,181481265,{"$nulls":4},181481265]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the future 5 years beyond the above 5-year work plan."]
[]
[null,null,"Location - Community, quadrant,","2008/09 - 2012/13"]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"New Elem School ","Area A",15000000,{"$nulls":4},15000000]
[null,"New Elem School ","Area B",15000000,{"$nulls":4},15000000]
[null,"New Elem School ","Area F",15000000,{"$nulls":4},15000000]
["2b2","Broward Total",null,45000000,{"$nulls":4},45000000]
[]
["2b2a.","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2003-04","Actual 2002-03","Actual 2003-04","03/04 - 12/13         New Stu Capacity to","Projected 2012- 13","Projected 2012-13"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[null,"New Elem School  - Area A",0,0,0,null,1112,1112,1]
[null,"New Elem School  - Area B",0,0,0,null,1112,1112,1]
[null,"New Elem School  - Area  F",0,0,0,null,1112,1112,1]
["2b2a.","Broward Total",0,0,0,null,3336,3336,1]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the next 5 year period beyond the 5-year work plan above."]
[]
[]
["2b2g.","Plans for closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the next 5 year period beyond the 5-year plan above."]
[]
[]
[]
[]
[]
["Broward  SCHOOL DISTRICT - - FACILITIES TWENTY (20) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the 11 thru 20 out years."]
[]
[null,null,null,"2013/14-2022/23 ","Annual"]
[null,"Project","Location","Projected Cost","Average Cost",null,null,null,"10 YEAR TOTAL"]
[null,"HSS/Capital Improvement Program (Maintenance)","District Wide",471540056,47154005.6,null,null,null,471540056]
[{"$nulls":4},0,null,null,null,0]
["2b1","Broward Total",null,471540056,{"$nulls":4},471540056]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the 11 thru 20 out years."]
[]
[null,null,"Location - Community, quadrant,","2013/14-2022/23 "]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"10 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b2","Broward Total",null,0,{"$nulls":4},0]
[]
["2b2a","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2003-04","Actual 2002-03","Actual 2000-01","13/14 - 22/23         New Stu Capacity to","District Projected 2022-23","Projected 2022-23"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
["2b2a","Broward Total",0,0,0,null,0,0]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the 11 thru 20 out years. "]
[null,"Broward County is experiencing population growth that may continue to transform the region from a predominantly rural area to a higher percentage of urban communities.  Current preferences for low-density residential areas are given way to a higher density, more urban-like lifestyle.  There will be less available developable land.  Making it difficult to find suitable locations for new schools."]
[null,"Providing high quality schools with enough capacity will be an ongoing challenge for the school district.  However, technological advances and improvements in communications infrastructure could play a large role in providing education to students and future educational facilities will take advantage of that to benefit the Districts changing needs."]
[]
[]
["2b2g","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the 11 thru 20 out years."]
[]
[]
[]
[]
[]
[null,"To the extent available, the tentative district facilities work program shall be based on information produced by the demographic, revenue, and"]
[null,"education estimating conferences pursuant to 216.136."]
[null,"Provision shall be made for public comment concerning the tentative district educational facilities plan."]
[null,"The district school board shall coordinate with each affected local government to ensure consistency between the tentative district educational facilities plan and"]
[null,"the local government comprehensive plans of the affected local governments during the deveolpment of the tentative district educational facilities plan."]
[null,"The adopted district facilities work program shall:"]
[null,"Be a complete, balanced capital outlay financial plan for the district."]
[null,"Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities, including safe access ways from neighborhoods to schools."]
[null,"The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 1013.61."]
[null,"The adopted district educational facilities plan shall include the information required in subparagraphs (2) (b) 1., 2., and 3., based upon projects actually"]
[null,"funded in the plan with the exception of the 10 and 20 year portions."]
{"$rows_empty":9}
["Respectfully submitted this    5th    day of    December   , 2003."]
[]
[null,"SCHOOL BOARD OF BROWARD COUNTY "]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Franklin L. Till, Jr."]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ",{"$nulls":4},"I. Benjamin Leong",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  ",null,null,"Alexander Baum","Director, Capital Systems Reporting & Control",null,"754-321-0763","alex.baum@browardschools.com",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]
[]
[]
[]
[]
["Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop","Stop"]