{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":282,"n_cols":25,"rows_kept":282,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["CALHOUN  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["CALHOUN   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"CALHOUN","Date: ==>","2001-10-01",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety",{"$nulls":6},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"HVAC Upgrades",{"$nulls":6},0]
[null,"Return Air","Blountstown Elementary",35000,{"$nulls":4},35000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Waste Water Retention",{"$nulls":6},0]
[{"$nulls":8},0]
[null,"Roofing",{"$nulls":6},0]
[null,"Walkway Covers","Carr School",null,30000,null,null,null,30000]
[null,"Ag Building","Altha School",null,null,30000,null,null,30000]
[null,"Main Building","Altha School",120000,{"$nulls":4},120000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Other",{"$nulls":6},0]
[null,"Misc Projects",null,312313,{"$nulls":4},312313]
[null,"Maintenance, Repair, and Renovation Totals",null,467313,30000,30000,0,0,527313]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,312313]
["1.","CALHOUN Total",null,155000,30000,30000,0,0,527313]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Classrooms","Carr School",0,450000,0,0,0,450000]
[null,"Classrooms","Altha School",0,0,225000,0,0,225000]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["2 .",null,null,0,450000,225000,0,0,675000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Adult",102,102,45,0.44,0,60,0.59]
[null,"Altha",785,706,678,0.96,72,700,0.9]
[null,"Blountstown Elementary",1048,1048,565,0.54,0,620,0.59]
[null,"Carr ",380,342,298,0.87,64,325,0.8]
[null,"Blountstown High",693,554,373,0.67,0,400,0.72]
[null,"Blounstown Middle",477,429,276,0.64,0,300,0.7]
["2a.","CALHOUN Total",3485,3181,2235,0.7,136,2405,0.73]
[]
["2b.","Proposed Location of Planned Facilities"]
[]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,"Altha",3,"CCSB",82,0,3,0,4]
[null,"Blountstown Middle",2,"CCSB",45,0,2,0,22]
[null,"Carr",4,"CCSB",100,0,0,4,15]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
["2c1.","CALHOUN Total",9,null,227,0,5,4,"Avg Age 4.56"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"Altha",0,0,0,0,0,0,0]
[null,"Carr",4,0,4,0,0,0,4]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","CALHOUN Total",4,0,4,0,0,0,4]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2000-01","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[]
[]
["2c3.","CALHOUN Total",0,null,0,0,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c4.","CALHOUN Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"Adult",4,102,45,15,60,0,20]
[null,"Altha",32,706,678,21.19,700,2,24]
[null,"Blountstown Elementary",32,1048,565,17.66,620,0,18]
[null,"Carr",14,342,298,21.29,325,null,21]
[null,"Blountstown High",30,554,373,12.43,400,0,13]
[null,"Blountstown Middle",17,429,276,16.24,300,4,17]
["2e.","CALHOUN Total",129,3181,2235,"District Avg 17",2405,6,"District Avg 18"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR AVERAGE"]
[null,"Altha School",null,82,82,82,40,40,65.2,null,0]
[null,"Carr School",null,40,25,25,25,25,28]
[null,"Blountstown Middle School",null,45,45,45,45,45,45]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2f.","CALHOUN Total students in relocatables by year",null,167,152,152,110,110,138.2]
[null,"Total number of CO-FTE students projected by year",null,2257,2295,2345,2405,2405,2341.4]
[null,"Percent in relocatables by year",null,0.07,0.07,0.06,0.05,0.05,0.06]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","CALHOUN Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","CALHOUN Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","CALHOUN Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","CALHOUN Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","CALHOUN Total 2005-06",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","CALHOUN 5-Year Total",null,0,0,0]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,0,0,0,0,0,0]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,0,0,0,0,0,0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,0,0,0,0,0,0,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to purchase other vehicles",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used for maintenance/repair",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to purchase capital outlay equipment",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount to pay debt service for COP's ",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,{"$error":"#DIV/0!"},"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,0,0,0,0,0,{"$error":"#DIV/0!"},0]
[null,"P E C O New Construction",null,85964,72554,42979,36672,38161,276330,null,0.26]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,66000,66000,66000,66000,66000,330000,null,0.31]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,71453,71453,71453,71453,71453,357265,null,0.33]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Carryover",null,null,103417,null,null,null,103417]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","CALHOUN Total",null,223417,313424,180432,174125,175614,1067012,{"$error":"#DIV/0!"},0.9000000000000001]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Classrooms-Carr",null,0,291346,0,0,0,291346]
[null,"Classrooms-Altha",null,0,0,177501,0,0,177501]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["5.","CALHOUN Total",0,0,291346,177501,0,0,468847]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Special Maintenance",null,249795,213154,196820,190745,191285,1041799]
[null,"LCIF & Other Carryover",null,217518,{"$nulls":4},217518]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","CALHOUN Total",null,467313,213154,196820,190745,191285,1259317]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Classrooms-Carr",80,0,158654,0,0,0,158654]
[null,"Classrooms-Altha",40,0,0,47499,0,0,47499]
[null,null,null,0,0,0,0,0,0]
["7.","CALHOUN Total",120,0,158654,47499,0,0,206153]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this 11th day of September, 2001."]
[]
[null,"SCHOOL BOARD OF ","CALHOUN  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Wilson T. McClellan"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"Suzanne K. Mason",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Suzanne Mason","Finance Officer","(850) 674-8123",null,"mason_s@firn.edu",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}