{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":1060,"n_cols":25,"rows_kept":1060,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["DUVAL  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["DUVAL   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"DUVAL","Date: ==>","2000-10-01",null,"For fiscal years","  2000-2001 through 2004-2005"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Replace floor covering in multi-purpose, media, and adjacent space","ALDEN ROAD EXCEPTIONAL STUDENT CENTER",30000,{"$nulls":4},30000]
[null,"Relocate lockers to girls shower room. Disconnect girls showers","ALFRED I. duPONT MIDDLE SCHOOL",15000,{"$nulls":4},15000]
[null,"Repair/replace chill water piping and flush system","ALFRED I. duPONT MIDDLE SCHOOL",530000,{"$nulls":4},530000]
[null,"Install bus canopy","ALIMACANI ELEMENTARY",86000,{"$nulls":4},86000]
[null,"Correct drainage problem between buildings","ANDREW A. ROBINSON ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Replace football field lights","ANDREW JACKSON HIGH ",50000,{"$nulls":4},50000]
[null,"Replace unit ventilators and controls","ANDREW JACKSON HIGH ",800000,{"$nulls":4},800000]
[null,"Recontrol/replace AHU's and replace ductwork","ANNIE R. MORGAN ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Two way intercom system","ARLINGTON ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Correct drainage problem on walkway near bus area","ARLINGTON HEIGHTS ELEMENTARY",5000,{"$nulls":4},5000]
[null,"New heating/air conditioning system","ARLINGTON MIDDLE SCHOOL",1200000,{"$nulls":4},1200000]
[null,"Renovation of all student restrooms","ARLINGTON MIDDLE SCHOOL",200000,{"$nulls":4},200000]
[null,"Covered walkways connecting existing canopy to cafeteria and from main building to extended day room","ATLANTIC BEACH ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Replace all old GRM and built-up roofing","BALDWIN MIDDLE/HIGH",246000,{"$nulls":4},246000]
[null,"Correct and improve drainage.  Install irrigation and landscape","BEAUCLERC ELEMENTARY",55000,{"$nulls":4},55000]
[null,"Renovate/ remodel classroom bathrooms rms 81 & 85","BEAUCLERC ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace subfloor of first floor corridor","BEULAH BEAL YOUNG PARENTS CENTER",350000,{"$nulls":4},350000]
[null,"Provide A/C in auditorium","BEULAH BEAL YOUNG PARENTS CENTER",403550,{"$nulls":4},403550]
[null,"Replace plumbing in Building 2 and 3","BILTMORE ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Update lighting in hallways, replace drop ceiling","BROOKVIEW ELEMENTARY",175000,{"$nulls":4},175000]
[null,"Replace floor covering and marker boards","CARTER G. WOODSON ELEMENTARY",120000,{"$nulls":4},120000]
[null,"Add additional electrical outlets in all classrooms","CEDAR HILLS ELEMENTARY",125000,{"$nulls":4},125000]
[null,"Install drymarker boards in classrooms","CEDAR HILLS ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Renovate playground equipment","CEDAR HILLS ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Install stair treads","CENTRAL RIVERSIDE EL",18000,{"$nulls":4},18000]
[null,"Repair cracks in classroom walls","CHIMNEY LAKES ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Replace electric gate in bus area","CROWN POINT ELEMENTARY",12000,{"$nulls":4},12000]
[null,"Replace floor covering in multi-purpose room","CROWN POINT ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Provide additional shelving for media center","CRYSTAL SPRINGS EL",52500,{"$nulls":4},52500]
[null,"Replace all old roof shingles","CRYSTAL SPRINGS EL",441000,{"$nulls":4},441000]
[null,"Replace floor covering","CRYSTAL SPRINGS EL",315000,{"$nulls":4},315000]
[null,"Renovate music suite HVAC","D. ANDERSON SCHOOL OF THE ARTS",200000,{"$nulls":4},200000]
[null,"Repave/expand existing parking","D. ANDERSON SCHOOL OF THE ARTS",25000,{"$nulls":4},25000]
[null,"Replace fire alarm system","DARNELL-COOKMAN MIDDLE ",110000,{"$nulls":4},110000]
[null,"Renovate kitchen","DINSMORE ELEMENTARY",750000,{"$nulls":4},750000]
[null,"Two-way intercom system","DINSMORE ELEMENTARY",75000,{"$nulls":4},75000]
[null,"ADA requirements","DISTRICT WIDE",500000,500000,500000,1000000,null,2500000]
[null,"Asbestos abatement/management","DISTRICT WIDE",800000,600000,550000,550000,700000,3200000]
[null,"Bleacher Repair","DISTRICT WIDE",125000,125000,125000,125000,125000,625000]
[null,"Cabinet replacement / refacing","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Chiller extended warranty at various schools","DISTRICT WIDE",20000,20000,20000,20000,20000,100000]
[null,"Chiller inspection","DISTRICT WIDE",150000,150000,150000,150000,150000,750000]
[null,"Contingency for safety-to-life emergencies","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Drainage & sitework","DISTRICT WIDE",75000,75000,75000,75000,75000,375000]
[null,"EMCS maintenance/standardization","DISTRICT WIDE",400000,400000,400000,400000,400000,2000000]
[null,"Emergency contingency","DISTRICT WIDE",500000,500000,500000,500000,500000,2500000]
[null,"Environmental compliance and emergency response- indoor air quality, hazardous waste, industrial hygiene, underground tank mgmt","DISTRICT WIDE",225000,225000,225000,225000,225000,1125000]
[null,"Fencing","DISTRICT WIDE",15000,15000,15000,15000,15000,75000]
[null,"Finance/ purchase/ renovation  installment, relocatables","DISTRICT WIDE",500000,500000,null,null,null,1000000]
[null,"Fire supression hood systems","DISTRICT WIDE",66500,66500,66500,66500,66500,332500]
[null,"Gender equity/athletics/PE","DISTRICT WIDE",1500000,1500000,1500000,2000000,null,6500000]
[null,"Inhouse maintenance employees","DISTRICT WIDE",1600000,1600000,1600000,1600000,1600000,8000000]
[null,"Miscellaneous professional services","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Motorized bleachers","DISTRICT WIDE",75000,75000,75000,75000,75000,375000]
[null,"Natural gas conversions","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Relocatable phaseout/upgrade","DISTRICT WIDE",1500000,1500000,1500000,1500000,null,6000000]
[null,"Relocatable repairs","DISTRICT WIDE",150000,150000,150000,150000,150000,750000]
[null,"Repair & replace lockers","DISTRICT WIDE",300000,300000,300000,300000,300000,1500000]
[null,"Repair/replace gym floor","DISTRICT WIDE",250000,250000,250000,250000,250000,1250000]
[null,"Replace boiler and pumps at #208 & #66","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Replace chalkboard/markerboards","DISTRICT WIDE",200000,200000,200000,200000,200000,1000000]
[null,"Replace DX equipment, upgrade HVAC","DISTRICT WIDE",1325000,1325000,1325000,1325000,1325000,6625000]
[null,"Replace emergency generators at 96 & 212","DISTRICT WIDE",75000,75000,75000,75000,75000,375000]
[null,"Replace restroom partitions #216, 207, 116, 97, 229, 234, 241","DISTRICT WIDE",125000,125000,125000,125000,125000,625000]
[null,"Roof repair","DISTRICT WIDE",675000,675000,675000,675000,675000,3375000]
[null,"Rubberized tracks","DISTRICT WIDE",125000,125000,125000,125000,125000,625000]
[null,"Sealcoating, repaving, striping","DISTRICT WIDE",350000,350000,350000,350000,350000,1750000]
[null,"Sidewalks","DISTRICT WIDE",25000,25000,25000,25000,25000,125000]
[null,"Stage drapes","DISTRICT WIDE",55000,55000,55000,55000,55000,275000]
[null,"Technology for existing schools","DISTRICT WIDE",14006145,10854394,24197810,12740381,8746740,70545470]
[null,"Termite treatment","DISTRICT WIDE",100000,100000,100000,100000,100000,500000]
[null,"Waterproofing","DISTRICT WIDE",250000,250000,250000,250000,250000,1250000]
[null,"Window coverings & drapes","DISTRICT WIDE",25000,25000,25000,25000,25000,125000]
[null,"Move fume hoods in C1 and C2","DUNCAN FLETCHER HIGH ",15000,{"$nulls":4},15000]
[null,"Renovate auditorium seats","DUNCAN FLETCHER HIGH ",100000,{"$nulls":4},100000]
[null,"Install partition in old media center","DUNCAN U. FLETCHER MIDDLE ",35000,{"$nulls":4},35000]
[null,"Repipe domestic water lines in bldgs 2,3,4,6. Replace floor urinals in boys restroom, bldg 4, rm 29, 41A, bldg 2 rm 4A.  Provide new water service with backflow","DUNCAN U. FLETCHER MIDDLE ",150000,{"$nulls":4},150000]
[null,"Replace  divider between rooms 23a and b","DUNCAN U. FLETCHER MIDDLE ",25000,{"$nulls":4},25000]
[null,"Upgrade security lighting by gymnasium and Building 6","DUNCAN U. FLETCHER MIDDLE ",25000,{"$nulls":4},25000]
[null,"Replace floor covering in the exceptional education classroom wing","EDWARD WHITE HIGH SCHOOL",35000,{"$nulls":4},35000]
[null,"Restroom stalls","EDWARD WHITE HIGH SCHOOL",30000,{"$nulls":4},30000]
[null,"Additional parking","ENGLEWOOD ELEMENTARY",80000,{"$nulls":4},80000]
[null,"Replace stage floor in auditorium","ENGLEWOOD HIGH SCHOOL",100000,{"$nulls":4},100000]
[null,"Provide security lighting on outside of building","FIRST COAST HIGH SCHOOL",50000,{"$nulls":4},50000]
[null,"Repair/resurface driveway for SED buses","FIRST COAST HIGH SCHOOL",36000,{"$nulls":4},36000]
[null,"Covered walkways, mechanical improvements","FIRST COAST HIGH SCHOOL",{"$nulls":4},3137600,3137600]
[null,"Remodel girls and boys  restrooms","FISHWEIR ELEMENTARY",32000,{"$nulls":4},32000]
[null,"Repair auditorium floor, replace floor covering","FISHWEIR ELEMENTARY",3000,{"$nulls":4},3000]
[null,"Drainage/sitework","FORT CAROLINE ELEMENTARY",85000,{"$nulls":4},85000]
[null,"Increase A/C ducts","FORT CAROLINE ELEMENTARY",15000,{"$nulls":4},15000]
[null,"Replace gym lockers","FORT CAROLINE MIDDLE",65000,{"$nulls":4},65000]
[null,"Upgrade hall and restroom lighting systems","FORT CAROLINE MIDDLE",100000,{"$nulls":4},100000]
[null,"Replace existing HVAC control system","FRANK H. PETERSON ACADEMIES OF TECHNOLOGY",400000,{"$nulls":4},400000]
[null,"Two-way intercom system","GARDEN CITY ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Replace floor covering in designated rooms 12, 13, 25, 27, 28, 29, 1, 2 and 4","GEORGE WASHINGTON CARVER ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Install panic hardware with a delayed release and alarm on Autistic classroom doors  (rooms 1, 2, 3, and 4)","GREENFIELD ELEMENTARY",6250,{"$nulls":4},6250]
[null,"Install soundproofing materials in the walls and ceilings of rooms 2, 3, 4, and 5","GREENFIELD ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Replace floor covering in the K and 1st grade classroom/ office areas","GREENLAND PINES ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Install drymarker boards in classrooms","GREGORY DRIVE ELEMENTARY",60000,{"$nulls":4},60000]
[null,"Replace toilets, floor covering, doors and ventilation fans in 8 individual classroom bathrooms","GREGORY DRIVE ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Replace crank style windows, building 4","HENDRICKS AVENUE ELEMENTARY",187200,{"$nulls":4},187200]
[null,"Installation of outside lighting for main entrance, lower steps and parking area","HENRY F. KITE ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Two-way intercom system","HENRY F. KITE ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Replace floor covering in portables and modulars","HIGHLANDS MIDDLE SCHOOL",50000,{"$nulls":4},50000]
[null,"Replace floors in main building","HOGAN-SPRING GLEN ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Resurface basketball court and replace equipment","HOGAN-SPRING GLEN ELEMENTARY",80000,{"$nulls":4},80000]
[null,"Replace floor covering","HOLIDAY HILL ELEMENTARY",135000,{"$nulls":4},135000]
[null,"Two-way intercom system","HOLIDAY HILL ELEMENTARY",75000,{"$nulls":4},75000]
[null,"Drainage/sitework","HYDE GROVE ELEMENTARY",20000,{"$nulls":4},20000]
[null,"Replace floor covering in media center and several classrooms","HYDE GROVE ELEMENTARY",60000,{"$nulls":4},60000]
[null,"Replace main switchgear and stage wheel chair lift","HYDE PARK ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Replace domestic water piping and plumbing fixtures","J.E.B. STUART MIDDLE SCHOOL",250000,{"$nulls":4},250000]
[null,"Re-roof entire school","J.E.B. STUART MIDDLE SCHOOL",1942000,{"$nulls":4},1942000]
[null,"Renovate HVAC in administration and building 5. Recontrol piping & flush system","JACKSONVILLE HEIGHTS ELEMENTARY",500000,{"$nulls":4},500000]
[null,"Renovate restrooms","J W JOHNSON MIDDLE SCHOOL",65000,{"$nulls":4},65000]
[null,"Marker boards (chalkless) in all classrooms","JEAN RIBAULT HIGH SCHOOL",100000,{"$nulls":4},100000]
[null,"Repipe domestic water lines / renovate restrooms","JEAN RIBAULT HIGH SCHOOL",300000,{"$nulls":4},300000]
[null,"Replace student lockers located in Wing 6 and  for 6th grade area","JEAN RIBAULT MIDDLE SCHOOL",50000,{"$nulls":4},50000]
[null,"Replace domestic water lines throughout school","JEFFERSON DAVIS MIDDLE SCHOOL",500000,{"$nulls":4},500000]
[null,"Replace heating unit ventilators","JEFFERSON DAVIS MIDDLE SCHOOL",175000,{"$nulls":4},175000]
[null,"Renovate bathrooms","JEFFERSON DAVIS MIDDLE SCHOOL",{"$nulls":4},500000,500000]
[null,"Windows & doors","JOHN STOCKTON ELEMENTARY",350000,{"$nulls":4},350000]
[null,"Install sidewalks alongside parking lot on west side of building and from multi-purpose room on west end of building #3","JOSEPH FINEGAN ELEMENTARY",7500,{"$nulls":4},7500]
[null,"Replace floor covering in media center and bandroom","JOSEPH STILWELL MIDDLE ",50000,{"$nulls":4},50000]
[null,"Replace main switch gear","JOSEPH STILWELL MIDDLE ",200000,{"$nulls":4},200000]
[null,"Restroom renovation","JOSEPH STILWELL MIDDLE ",90000,{"$nulls":4},90000]
[null,"Two way intercom","JOSEPH STILWELL MIDDLE ",150000,{"$nulls":4},150000]
[null,"Repave parking, enlarge bus area, covered walkway","JOSEPH STILWELL MIDDLE ",{"$nulls":4},683610,683610]
[null,"Install acoustical panels in cafeteria","KINGS TRAIL ELEMENTARY",105000,{"$nulls":4},105000]
[null,"Replace windows in Buildings 1, 2, and 3","KINGS TRAIL ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Modify pump and piping to correct flow problems","KIRBY-SMITH MIDDLE SCHOOL",80000,{"$nulls":4},80000]
[null,"Replace domestic water piping, waste piping, and plumbing fixtures","LACKAWANNA  ALTERNATIVE EDUCATION CENTER",275000,{"$nulls":4},275000]
[null,"Install better security lighting in the open halls of building #9","LAKE FOREST ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Two-way intercom system","LAKE FOREST ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Install acoustical panels on walls in cafeteria","LAKE LUCINA ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Correct guidance HVAC problems","LANDMARK MIDDLE SCHOOL",75000,{"$nulls":4},75000]
[null,"Upgrade lights in front of school parking area (Abess entrance)","LANDMARK MIDDLE SCHOOL",20000,{"$nulls":4},20000]
[null,"Extend covered walkways from kindergarten buildings to the main entrance of the school","LONE STAR ELEMENTARY",40000,{"$nulls":4},40000]
[null,"Repipe domestic water lines in school (new bldg ok)","LONE STAR ELEMENTARY",125000,{"$nulls":4},125000]
[null,"Increase lighting at rear of complex","LONG BRANCH ELEMENTARY",35000,{"$nulls":4},35000]
[null,"Replace floor covering in multi purpose room","LONG BRANCH ELEMENTARY",7500,{"$nulls":4},7500]
[null,"Replace asbestos floor coverings, bldg. 1,2,3","LOVE GROVE ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Install emergency generator","M.V. RUTHERFORD ",60000,{"$nulls":4},60000]
[null,"Floor covering replacement","MANDARIN HIGH SCHOOL",250000,{"$nulls":4},250000]
[null,"Resurface basketball courts","MANDARIN MIDDLE SCHOOL",15000,{"$nulls":4},15000]
[null,"Clean inside brick walls","MARTIN LUTHER KING EL",5000,{"$nulls":4},5000]
[null,"Replace wallpaper throughout school","MATTHEW GILBERT MIDDLE SCHOOL",150000,{"$nulls":4},150000]
[null,"Place off-street parallel parking at entry side of school and provide drainage","MAYPORT ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Replace divider, cafeteria area","MAYPORT MIDDLE SCHOOL",20000,{"$nulls":4},20000]
[null,"Replace gym floor","MAYPORT MIDDLE SCHOOL",120000,{"$nulls":4},120000]
[null,"Replace floor covering in main building classrooms and office/clinic/lounge","MERRILL ROAD ELEMENTARY",50000,{"$nulls":4},50000]
[null,"Restructure wiring in computer lab to separate from classroom wiring","MERRILL ROAD ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Renovate and upgrade second floor restrooms to ADA code standards","Mt. HERMAN EXCEPTIONAL STUDENT CENTER",400000,{"$nulls":4},400000]
[null,"Upgrade main service and switchgear","Mt. HERMAN EXCEPTIONAL STUDENT CENTER",125000,{"$nulls":4},125000]
[null,"Renovate auditorium","NATHAN B. FORREST HIGH",225000,{"$nulls":4},225000]
[null,"Two way intercom","NATHAN B. FORREST HIGH",60000,{"$nulls":4},60000]
[null,"Replace floor covering in gym w/ padded linoleum","NEPTUNE BEACH ELEMENTARY",40000,{"$nulls":4},40000]
[null,"Renovate/remodel cafeteria","NORMANDY VILLAGE EL",55000,{"$nulls":4},55000]
[null,"Repipe the water line and replace plumbing fixtures in the school, building numbers 1, 2, 3, 4 and 5","OAK HILL ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Renovate bathrooms / replacement of classroom floor covering","OCEANWAY ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Replace auditorium seats","ORTEGA ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Repave driveway and walking trail (wheel chair access). Improve drainage","PALM AVENUE EXCEPTIONAL STUDENT CENTER",162000,{"$nulls":4},162000]
[null,"Replace floor covering in administration building","PALM AVENUE EXCEPTIONAL STUDENT CENTER",10000,{"$nulls":4},10000]
[null,"Replace boiler","PARKWOOD HEIGHTS EL",80000,{"$nulls":4},80000]
[null,"Upgrade switchgear, 1200 amp","PARKWOOD HEIGHTS EL",100000,{"$nulls":4},100000]
[null,"Covered walkway, retrofit lighting","PARKWOOD HEIGHTS EL",{"$nulls":4},1181600,1181600]
[null,"Repiping","PAXON HIGH SCHOOL",500000,{"$nulls":4},500000]
[null,"Exterior doors (all not included in renovation project) replace/paint","PAXON MIDDLE SCHOOL",150000,{"$nulls":4},150000]
[null,"Replace split systems and ducts in school  & chiller/AHU's in music building","PAXON MIDDLE SCHOOL",300000,{"$nulls":4},300000]
[null,"Replace cabinets","PICKETT ELEMENTARY",80000,{"$nulls":4},80000]
[null,"Resurface drive way and new parking lot","PINE ESTATES ELEMENTARY",70000,{"$nulls":4},70000]
[null,"Replace floor covering in main hallways and administration areas","PINE FOREST ELEMENTARY",50000,{"$nulls":4},50000]
[null,"New floor covering in multi-purpose room","PINEDALE ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Rework canopy and/or paving at the Exceptional Education Center, Bldg. No. 8","PINEDALE ELEMENTARY",65000,{"$nulls":4},65000]
[null,"Add sidewalk from eastside of building to the playground","R. V. DANIELS ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Replace A/C vent","R. V. DANIELS ELEMENTARY",400000,{"$nulls":4},400000]
[null,"External speakers for fire alarm system","RAMONA BOULEVARD ELEMENTARY",2500,{"$nulls":4},2500]
[null,"Two-way intercom system","RICHARD L. BROWN EL",40000,{"$nulls":4},40000]
[null,"Upgrade lights","ROBERT E. LEE HIGH SCHOOL",250000,{"$nulls":4},250000]
[null,"Replace damaged floor covering throughout school","RUFUS E. PAYNE ELEMENTARY",165000,{"$nulls":4},165000]
[null,"Replace toilets and upgrade all bathrooms in annex, building 2","RUTH N. UPSON ELEMENTARY",35000,{"$nulls":4},35000]
[null,"Replace emergency generator","RUTLEDGE H. PEARSON EL",40000,{"$nulls":4},40000]
[null,"Floor coverings for pre-k, media center, and room 12","S. A. HULL ELEMENTARY",35000,{"$nulls":4},35000]
[null,"Windows","S. A. HULL ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Replace floor covering in KG and Grade 1 classrooms","SABAL PALM ELEMENTARY",40000,{"$nulls":4},40000]
[null,"Replace doors and floorcovering, Building 1; provide two way intercom","SADIE TILLIS ELEMENTARY",65000,{"$nulls":4},65000]
[null,"Replace floor covering","SAINT CLAIR EVANS ACADEMY",5000,{"$nulls":4},5000]
[null,"Upgrade of playground equipment area","SAINT CLAIR EVANS ACADEMY",150000,{"$nulls":4},150000]
[null,"Fix A/C drain for cafeteria","SALLYE B. MATHIS EL",20000,{"$nulls":4},20000]
[null,"Upgrade restrooms","SAN JOSE ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Install boiler","SAN PABLO ELEMENTARY",30000,{"$nulls":4},30000]
[null,"Install covered walkway for bus loading area","SAN PABLO ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Repipe domestic water lines in school (new bldg.ok)  Provide new water service to school with backflow.  Remodel student restrooms","SAN PABLO ELEMENTARY",250000,{"$nulls":4},250000]
[null,"Clean heating and air conditioning duct system","SANDALWOOD HIGH SCHOOL",100000,{"$nulls":4},100000]
[null,"Add to existing plumbing project","SEABREEZE ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Handicapped ramps for east and west entrances to the school","SEABREEZE ELEMENTARY",4000,{"$nulls":4},4000]
[null,"Covered walkway for bus loading zone","SOUTHSIDE ESTATES ELEMENTARY",95000,{"$nulls":4},95000]
[null,"Repair hall lockers","SOUTHSIDE MIDDLE SCHOOL",50000,{"$nulls":4},50000]
[null,"Improved lighting in front parking lot and sides of school","SPRING PARK ELEMENTARY",25000,{"$nulls":4},25000]
[null,"Upgrade main service and subfeed panels","STANTON COLLEGE PREPARATORY",125000,{"$nulls":4},125000]
[null,"Provide 2 basketball hoops on existing court. Construct new basketball court. Provide additional fencing","SUSIE TOLBERT ELEMENTARY",45000,{"$nulls":4},45000]
[null,"Provide HVAC upgrade for satellite room and room 70","TEAM CENTER (KOGER)",50000,{"$nulls":4},50000]
[null,"Alleviate sewage odor in music suite","TERRY PARKER HIGH SCHOOL",50000,{"$nulls":4},50000]
[null,"Remove shared meter","TERRY PARKER HIGH SCHOOL",40000,{"$nulls":4},40000]
[null,"Renovate auditorium seats","TERRY PARKER HIGH SCHOOL",80000,{"$nulls":4},80000]
[null,"Replace windows","TERRY PARKER HIGH SCHOOL",500000,{"$nulls":4},500000]
[null,"Replace glazing","TERRY PARKER HIGH SCHOOL",{"$nulls":4},752890,752890]
[null,"Replace domestic waterpiping, cafeteria","THOMAS JEFFERSON ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Electrical upgrade, intercom, security lights","TIMUCUAN ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Fence area within bus loading zone","TWIN LAKES ACADEMY ELEMENTARY",7500,{"$nulls":4},7500]
[null,"Paint with a gloss paint which will be easier to clean","TWIN LAKES ACADEMY MIDDLE",200000,{"$nulls":4},200000]
[null,"Drainage/sitework","VENETIA ELEMENTARY",1000,{"$nulls":4},1000]
[null,"Covered walkways, upgrade fire alarm","VENETIA ELEMENTARY",{"$nulls":4},403250,403250]
[null,"Repair water damage to the main building and seal the areas that are leaking","WESCONNETT ELEMENTARY",40000,{"$nulls":4},40000]
[null,"Re-pipe school and renovate existing restrooms that were not renovated in past project","WEST JACKSONVILLE ELEMENTARY",400000,{"$nulls":4},400000]
[null,"Replace corridor ceilings and upgrade corridor lighting","WEST JACKSONVILLE ELEMENTARY",130000,{"$nulls":4},130000]
[null,"Replace floor covering in cafeteria/auditorium","WEST JACKSONVILLE ELEMENTARY",80000,{"$nulls":4},80000]
[null,"Provide railing for front steps","WEST RIVERSIDE ELEMENTARY",5000,{"$nulls":4},5000]
[null,"Replace floor covering for hallways, auditorium, and classrooms","WEST RIVERSIDE ELEMENTARY",120000,{"$nulls":4},120000]
[null,"Additional lockers","WILLIAM M. RAINES HIGH",13000,{"$nulls":4},13000]
[null,"Renovate restrooms","WILLIAM M. RAINES HIGH",352000,{"$nulls":4},352000]
[null,"Resurface drivers' education range","WILLIAM M. RAINES HIGH",21000,{"$nulls":4},21000]
[null,"Add to plumbing project","WINDY HILL ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Replace floor covering","WINDY HILL ELEMENTARY",105000,{"$nulls":4},105000]
[null,"Covered walkway,  replace plexiglas glazing","WINDY HILL ELEMENTARY",{"$nulls":4},726050,726050]
[null,"Construct sidewalk on east side of building","WOODLAND ACRES ELEMENTARY",10000,{"$nulls":4},10000]
[null,"Enlarge bus circle and staff/visitor parking","WOODLAND ACRES ELEMENTARY",150000,{"$nulls":4},150000]
[null,"Provide new water service to school with backflow device.  Repipe domestic water lines inside of school (new bldg ok).  Replace cafeteria boys restroom urinals and wastelines. Replace cabinetry","WOODLAND ACRES ELEMENTARY",300000,{"$nulls":4},300000]
[{"$nulls":8},0]
["1.","DUVAL Total",null,52726145,23235894,36029310,25571881,24613240,162176470]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Bayview Elementary, Convert media to kindergarten classroom",null,1931800,{"$nulls":4},1931800]
[null,"New media center"]
[null,"S.A. Hull Elementary, New media, remodel existing",null,1809300,{"$nulls":4},1809300]
[null,"Ortega Elementary, Remodel and expand cafeteria",null,1020900,{"$nulls":4},1020900]
[null,"Oceanway Elementary  (Conversion to Middle)",null,8473617,8837900,null,null,null,17311517]
[null,"Arlington Middle ESE improvements",null,null,3184500,null,null,null,3184500]
[null,"Andrew Jackson High, Relocatable repacement",null,null,1397500,null,null,null,1397500]
[null,"Seabreeze Elementary, New media center",null,null,2877600,null,null,null,2877600]
[null,"Fishweir Elementary, New Cafeteria, remodel admin, restrooms",null,null,null,2188900,null,null,2188900]
[null,"District wide ESE improvements",null,null,null,1500000,null,null,1500000]
[null,"Arlington Elementary, Relocatable replacement, expand media",{"$nulls":4},2127200,null,2127200]
[null,"Pickett Elementary, New media center, remodel and renovations",{"$nulls":4},2339000,null,2339000]
[null,"Northshore Elementary, Kindergarten classrooms",{"$nulls":4},741500,null,741500]
[null,"Wolfson High,  Expand media, food service",{"$nulls":4},4334486,null,4334486]
[null,"Ribault Middle ESE improvements",{"$nulls":4},1884650,null,1884650]
[null,"duPont Middle, Relocatable replacement",{"$nulls":4},2623000,null,2623000]
[null,"Terry Parker ESE facility",{"$nulls":4},2519800,null,2519800]
[null,"Arlington Middle, Remodel admin,restrooms",{"$nulls":5},3673147,3673147]
[null,"New Middle \"DD\"  (Westside/Argyle)  (1200 Students)",{"$nulls":5},21064806,21064806]
[null,"Cedar Hills Elementary, Convert classrooms to media",{"$nulls":5},2359400,2359400]
[null,"New High School \"AAA\"  (1800 Students)",{"$nulls":5},42972000,42972000]
[null,"Hogan Spring Glen Elementary, New cafeteria, remodel existing to classrooms",{"$nulls":5},2732380,2732380]
[null,"Arlington Heights Elementary, Expand admin and media",{"$nulls":5},2441100,2441100]
[null,"Forrest High, Expand media,school wide- renovation",{"$nulls":5},2734340,2734340]
[null,"Lee High, Remodel cafeteria, expand bus drive, renovate band room",{"$nulls":5},2750400,2750400]
[null,"J.E.B. Stuart Middle, remodel area under media to multipurpose",{"$nulls":5},1326340,1326340]
[]
["2 .","DUVAL Total",null,13235617,16297500,3688900,16569636,82053913,131845566]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1999-00 FISH Satisfactory","Actual 1999-00","Actual 1999-00","Actual 1999-00","New Stu Capacity to","Projected 2004-05","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"M.V. RUTHERFORD ",409,409,172,1,null,137,0.33]
[null,"J. ALLEN AXSON EL",394,394,378,1,null,350,0.89]
[null,"LACKAWANNA  ",19,19,119,1,null,106,5.58]
[null,"BEULAH BEAL ",52,52,178,1,null,158,3.04]
[null,"WEST RIVERSIDE EL",455,455,344,1,null,382,0.84]
[null,"LOLA M. CULVER EL",309,309,336,1,null,289,0.94]
[null,"GRAND PARK ",455,409,201,1,null,139,0.34]
[null,"BRENTWOOD ELEMENTARY",402,402,327,1,null,292,0.73]
[null,"ORTEGA ELEMENTARY",305,305,383,1,null,346,1.13]
[null,"CENTRAL RIVERSIDE EL",477,477,483,1,null,503,1.05]
[null,"RUTH N. UPSON EL",545,545,523,1,null,415,0.76]
[null,"FISHWEIR ELEMENTARY",399,399,379,1,null,355,0.89]
[null,"ANNIE R. MORGAN EL",519,519,481,1,null,500,0.96]
[null,"NORWOOD ELEMENTARY",223,223,191,1,null,210,0.94]
[null,"KIRBY-SMITH MIDDLE",978,880,1016,0.9,null,979,1.11]
[null,"LORETTO ELEMENTARY",1421,1421,1288,1,null,1275,0.9]
[null,"LANDON MIDDLE ",1314,1182,1248,0.9,null,500,0.42]
[null,"MARINE SCIENCE CENTER",146,131,34,1,null,30,0.23]
[null,"ROBERT E. LEE HIGH",1589,1509,1350,0.95,null,1152,0.76]
[null,"ANDREW JACKSON HIGH ",1361,1224,1447,0.9,null,1524,1.25]
[null,"HENRY F. KITE ELEMENTARY",343,343,358,1,null,363,1.06]
[null,"BALDWIN HIGH",569,512,457,0.9,null,458,0.89]
[null,"BALDWIN MIDDLE",525,472,422,0.9,null,422,0.89]
[null,"DINSMORE ELEMENTARY",515,515,447,1,null,490,0.95]
[null,"ARLINGTON ELEMENTARY",386,386,355,1,null,333,0.86]
[null,"THOMAS JEFFERSON",499,499,491,1,null,587,1.18]
[null,"WHITEHOUSE ELEMENTARY",579,579,630,1,null,560,0.97]
[null,"WESCONNETT ELEMENTARY",384,384,431,1,null,341,0.89]
[null,"GARDEN CITY ELEMENTARY",534,534,510,1,null,598,1.12]
[null,"OCEANWAY ELEMENTARY",824,824,747,1,null,803,0.97]
[null,"DUNCAN FLETCHER MIDDLE",1448,1303,1444,0.9,null,1729,1.33]
[null,"HOGAN-SPRING GLEN EL",570,570,547,1,45,504,0.82]
[null,"ATLANTIC BEACH EL",647,647,534,1,null,505,0.78]
[null,"ALFRED I. DUPONT MIDDLE ",1411,1269,1256,0.9,null,1252,0.99]
[null,"VENETIA ELEMENTARY",484,484,428,1,null,413,0.85]
[null,"LAKE SHORE MIDDLE ",1495,1345,1146,0.9,null,1062,0.79]
[null,"NORTH SHORE ELEMENTARY",710,710,517,1,null,436,0.61]
[null,"HENDRICKS AVENUE EL",571,571,592,1,null,599,1.05]
[null,"SPRING PARK ELEMENTARY",500,500,360,1,null,415,0.83]
[null,"JOHN LOVE ELEMENTARY",423,423,316,1,null,222,0.52]
[null,"LAKE FOREST ELEMENTARY",591,591,618,1,null,549,0.93]
[null,"PAXON HIGH ",1189,1010,996,0.85,null,1154,1.14]
[null,"SOUTHSIDE ESTATES EL",656,656,605,1,null,679,1.04]
[null,"HYDE PARK ELEMENTARY",649,649,618,1,null,557,0.86]
[null,"BILTMORE ELEMENTARY",520,520,373,1,null,338,0.65]
[null,"RAMONA BOULEVARD EL",611,611,481,1,null,449,0.73]
[null,"SAN PABLO ELEMENTARY",686,686,568,1,null,548,0.8]
[null,"LOVE GROVE ELEMENTARY",775,775,571,1,null,506,0.65]
[null,"SAN JOSE ELEMENTARY",767,767,763,1,null,829,1.08]
[null,"BAYVIEW ELEMENTARY",427,427,435,1,6,430,0.99]
[null,"LAKE LUCINA ELEMENTARY",580,580,579,1,null,535,0.92]
[null,"TERRY PARKER HIGH",1865,1771,2016,0.95,null,2069,1.17]
[null,"ENGLEWOOD ELEMENTARY",501,501,493,1,null,526,1.05]
[null,"JOHN STOCKTON EL",438,438,509,1,null,449,1.03]
[null,"WOODLAND ACRES EL",889,889,839,1,null,736,0.83]
[null,"ENGLEWOOD HIGH",1686,1601,1749,0.95,null,1859,1.16]
[null,"SALLYE B. MATHIS EL",537,537,472,1,null,354,0.66]
[null,"PAXON MIDDLE ",1149,1034,1001,0.9,null,987,0.95]
[null,"PINEDALE ELEMENTARY",862,862,675,1,null,670,0.78]
[null,"WINDY HILL ELEMENTARY",666,666,792,1,null,794,1.19]
[null,"RUTLEDGE H. PEARSON EL",571,571,349,1,null,346,0.61]
[null,"JEAN RIBAULT HIGH",1749,1661,1132,0.95,null,1249,0.75]
[null,"CEDAR HILLS ELEMENTARY",554,554,429,1,null,302,0.55]
[null,"TIMUCUAN ELEMENTARY",760,760,669,1,null,645,0.85]
[null,"HIGHLANDS ELEMENTARY",630,630,578,1,null,630,1]
[null,"LONG BRANCH ELEMENTARY",369,369,348,1,null,248,0.67]
[null,"DOUGLAS ANDERSON ",924,785,918,0.85,null,958,1.22]
[null,"SADIE TILLIS ELEMENTARY",538,538,452,1,null,519,0.96]
[null,"SAINT CLAIRE EVANS ACDMY",734,734,537,1,null,673,0.92]
[null,"SUSIE TOLBERT EL",598,598,596,1,null,588,0.98]
[null,"WEST JACKSONVILLE EL",416,416,379,1,null,429,1.03]
[null,"JACKSONVILLE BEACH EL",513,513,605,1,null,588,1.15]
[null,"DARNELL-COOKMAN MIDDLE",1052,946,1149,0.9,null,1177,1.24]
[null,"MATTHEW GILBERT MIDDLE",957,861,877,0.9,null,860,1]
[null,"RICHARD L. BROWN EL",861,861,827,1,null,680,0.79]
[null,"S.P. LIVINGSTON EL",982,982,694,1,null,589,0.6]
[null,"JAMES WELDON JOHNSON ",1027,924,1099,0.9,null,1190,1.29]
[null,"STANTON HIGH",1948,1850,1492,0.95,null,1509,0.82]
[null,"JOHN E. FORD ELEMENTARY",828,828,773,1,null,701,0.85]
[null,"NORTHWESTERN MIDDLE ",1044,939,840,0.9,null,787,0.84]
[null,"MARY McLEOD BETHUNE EL",728,728,610,1,null,381,0.52]
[null,"GEORGE W. CARVER EL",682,682,434,1,null,450,0.66]
[null,"PINE FOREST ELEMENTARY",453,453,373,1,null,340,0.75]
[null,"R. V. DANIELS ELEMENTARY",501,501,305,1,null,360,0.72]
[null,"RUFUS E. PAYNE EL",718,718,494,1,null,450,0.63]
[null,"Mt. HERMAN ",266,266,166,1,null,127,0.48]
[null,"WILLIAM M. RAINES HIGH ",1970,1871,1889,0.95,null,1680,0.9]
[null,"CARTER G. WOODSON EL",684,684,445,1,null,460,0.67]
[null,"EUGENE BUTLER MIDDLE ",1034,930,873,0.9,null,716,0.77]
[null,"S. A. HULL ELEMENTARY",444,444,335,1,null,355,0.8]
[null,"PALM AVENUE ",146,146,187,1,null,157,1.08]
[null,"REYNOLDS LANE EL",580,580,453,1,null,409,0.71]
[null,"KINGS TRAIL ELEMENTARY",653,653,488,1,null,404,0.62]
[null,"NORMANDY ELEMENTARY",339,339,220,1,null,208,0.61]
[null,"PICKETT ELEMENTARY",403,403,286,1,null,299,0.74]
[null,"BROOKVIEW ELEMENTARY",816,816,1019,1,null,1057,1.3]
[null,"J.E.B. STUART MIDDLE",1104,994,1053,0.9,null,975,0.98]
[null,"PARKWOOD HEIGHTS EL",645,645,541,1,null,616,0.96]
[null,"HOLIDAY HILL ELEMENTARY",609,609,579,1,null,500,0.82]
[null,"OAK HILL ELEMENTARY",827,827,659,1,null,543,0.66]
[null,"SOUTHSIDE MIDDLE",1305,1174,1208,0.9,null,1138,0.97]
[null,"JEAN RIBAULT MIDDLE ",1778,1660,1059,0.9,-229,1013,0.71]
[null,"ARLINGTON MIDDLE ",1048,943,1031,0.9,77,1012,0.99]
[null,"HYDE GROVE ELEMENTARY",543,543,606,1,null,527,0.97]
[null,"JUSTINA ROAD ELEMENTARY",510,510,443,1,null,440,0.86]
[null,"JEFFERSON DAVIS MIDDLE ",1706,1535,1563,0.9,null,1475,0.96]
[null,"SAN MATEO ELEMENTARY",562,562,697,1,null,609,1.08]
[null,"JOSEPH STILWELL MIDDLE ",1401,1260,1266,0.9,null,1140,0.9]
[null,"MARTIN LUTHER KING EL",806,806,570,1,null,569,0.71]
[null,"NORMANDY VILLAGE EL",769,769,708,1,null,690,0.9]
[null,"GREENFIELD ELEMENTARY",621,621,605,1,null,520,0.84]
[null,"DUNCAN U. FLETCHER HIGH ",2500,2375,2027,0.95,null,2086,0.88]
[null,"SAMUEL W. WOLFSON HIGH ",1812,1721,1799,0.95,null,1933,1.12]
[null,"SEABREEZE ELEMENTARY",605,605,642,1,null,549,0.91]
[null,"CRYSTAL SPRINGS EL",1276,1276,1235,1,null,1167,0.91]
[null,"MAYPORT ELEMENTARY",1092,1092,959,1,null,1001,0.92]
[null,"MERRILL ROAD EL",557,557,682,1,null,730,1.31]
[null,"JACKSONVILLE HEIGHTS EL",918,918,1010,1,null,921,1]
[null,"BEAUCLERC ELEMENTARY",1157,1157,1267,1,null,1217,1.05]
[null,"CHIMNEY LAKES EL",1244,1244,1194,1,null,1188,0.95]
[null,"LONE STAR ELEMENTARY",733,733,846,1,null,869,1.19]
[null,"STONEWALL JACKSON EL",387,387,352,1,null,303,0.78]
[null,"FORT CAROLINE EL",844,844,835,1,null,806,0.95]
[null,"MAMIE AGNES JONES EL",554,554,493,1,null,430,0.78]
[null,"SANDALWOOD HIGH",2806,2665,2825,0.95,-86,3432,1.33]
[null,"FORT CAROLINE MIDDLE ",1306,1176,1045,0.9,null,1007,0.86]
[null,"SABAL PALM ELEMENTARY",1281,1281,1382,1,null,1451,1.13]
[null,"ARLINGTON HEIGHTS EL",549,549,534,1,null,506,0.92]
[null,"NATHAN B. FORREST HIGH ",1835,1743,1708,0.95,null,1540,0.88]
[null,"LOUIS SHEFFIELD EL",590,590,645,1,null,730,1.24]
[null,"GREGORY DRIVE EL",685,685,711,1,null,605,0.88]
[null,"HIGHLANDS MIDDLE",1737,1563,1585,0.9,null,1565,1]
[null,"CROWN POINT ELEMENTARY",1380,1380,1300,1,null,1216,0.88]
[null,"NEPTUNE BEACH EL",1363,1363,1124,1,null,1022,0.75]
[null,"JOSEPH FINEGAN EL",815,815,535,1,null,550,0.67]
[null,"EDWARD WHITE HIGH",2117,2106,2084,0.95,null,2129,1.01]
[null,"GREENLAND PINES EL",821,821,713,1,null,749,0.91]
[null,"PINE ESTATES ELEMENTARY",390,390,322,1,null,209,0.54]
[null,"TWIN LAKES ACADEMY EL",1090,1090,838,1,null,1012,0.93]
[null,"ALDEN ROAD ",141,141,184,1,null,133,0.94]
[null,"TWIN LAKES ACDMY MIDDLE",1810,1629,1574,0.9,null,1776,1.09]
[null,"MAYPORT MIDDLE",1162,1045,1045,0.9,null,1000,0.96]
[null,"ENTERPRISE LEARNING ACDMY",1090,1090,686,1,null,799,0.73]
[null,"LANDMARK MIDDLE",1983,1784,1849,0.9,null,2296,1.29]
[null,"ALIMACANI ELEMENTARY",1236,1236,1173,1,null,1239,1]
[null,"MANDARIN OAKS EL",1293,1293,1247,1,null,1219,0.94]
[null,"MANDARIN MIDDLE",1900,1710,1520,0.9,null,1547,0.9]
[null,"MANDARIN HIGH",2474,2350,2266,0.95,null,2306,0.98]
[null,"ANDREW A. ROBINSON EL",1275,1275,952,1,null,880,0.69]
[null,"ABESS PARK ELEMENTARY",1090,1090,1015,1,null,1025,0.94]
[null,"CHETS CREEK ELEMENTARY",1090,1090,991,1,null,1590,1.46]
[null,"FIRST COAST HIGH ",1939,1842,1781,0.95,null,1669,0.91]
[null,"FRANK H. PETERSON ",1532,1455,827,0.95,null,1280,0.88]
[null,"A. PHILIP RANDOLPH ",1506,1430,622,0.95,null,1107,0.77]
[null,"LAVILLA PERFORMING ARTS",{"$nulls":4},850,905]
[]
["2a.","DUVAL Total",136904,131837,122351,null,663,122734,0.93]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary \"U\" (788 Capacity) Biscayne/Duval - North of Trout River, East of Duval County line, West of I-95, and East of Duval County line to accommodate growth"]
[null,"New Elementary \"V\" (788 Capacity) Oceanway Elementary Replacement"]
[null,"New Elementary \"W\" (788 Capacity) East Arlington Area - North of Butler Blvd., East of Southside Blvd., South of the St. Johns River, and West of the intercoastal to accommodate growth"]
[null,"New Elementary \"X\" (788 Capactiy) North Arlington"]
[null,"New Middle \"CC\" (1201 Capacity) Southside-North of Beach Blvd., East of Southside Blvd., West of Intercoastal and south of Atlantic Blvd. To accommodate growth."]
[null,"New Middle \"DD\" (1201 Capacity) Westside - West of I-295, South of I-10, North of Duval County line and East of Duval County line to accommodate growth."]
[null,"New Middle \"EE\" (1201 Capacity) Conversion of existing Oceanway Elementary school."]
[null,"New Middle \"FF\" (1201 Capacity) TBA."]
[null,"New High School \"AAA\" (1800 Capacity) North of Duval County line, East of Southside Blvd. South of the St. Johns River, West of intercoastal to accommodate growth."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"M.V. RUTHERFORD ",1,"DCSB",18,null,1,null,25]
[null,"J. ALLEN AXSON EL",1,"FED",0,1,null,-1,33]
[null,"LACKAWANNA ",2,"DCSB",19,null,2,null,52]
[null,"BEULAH BEAL",2,"DCSB",52,null,2,null,24]
[null,"LOLA M. CULVER EL",2,"FED",16,2,null,-2,16]
[null,"GRAND PARK ",10,"DCSB",243,null,10,null,237]
[null,"ORTEGA ELEMENTARY",4,"DCSB",68,null,4,null,48]
[null,"FISHWEIR ELEMENTARY",2,"DCSB",39,null,2,null,26]
[null,"ANNIE R. MORGAN EL",5,"DCSB",72,null,5,null,127]
[null,"NORWOOD ELEMENTARY",2,"DCSB",35,null,2,null,50]
[null,"LORETTO ELEMENTARY",9,"DCSB",95,2,7,-2,254]
[null,"LANDON MIDDLE",13,"DCSB",249,13,null,-13,192]
[null,"ANDREW JACKSON HIGH",4,"DCSB",116,4,null,-4,89]
[null,"HENRY F. KITE ELEMENTARY",1,"DCSB",8,null,1,null,12]
[null,"BALDWIN MIDDLE/HIGH",2,"DCSB",60,null,2,null,22]
[null,"ARLINGTON ELEMENTARY",2,"DCSB",26,2,null,-2,14]
[null,"THOMAS JEFFERSON EL",1,"DCSB",0,1,null,-1,54]
[null,"WHITEHOUSE ELEMENTARY",8,"DCSB",155,null,8,null,170]
[null,"WESCONNETT ELEMENTARY",3,"DCSB",26,null,3,null,36]
[null,"GARDEN CITY ELEMENTARY",2,"FED",0,2,null,-2,70]
[null,"HOGAN-SPRING GLEN EL",7,"DCSB",73,2,5,-2,164]
[null,"ATLANTIC BEACH EL",2,"DCSB",17,2,null,-2,52]
[null,"ALFRED I. duPONT MIDDLE ",10,"DCSB",360,10,null,-10,240]
[null,"VENETIA ELEMENTARY",1,"DCSB",30,null,1,null,24]
[null,"LAKE SHORE MIDDLE",20,"DCSB",437,2,18,-2,306]
[null,"HENDRICKS AVENUE EL",2,"DCSB",0,null,2,null,28]
[null,"JOHN LOVE ELEMENTARY",1,"DCSB",10,null,1,null,49]
[null,"SOUTHSIDE ESTATES EL",2,"DCSB",0,null,2,null,24]
[null,"HYDE PARK ELEMENTARY",3,"DCSB",8,3,null,-3,36]
[null,"BILTMORE ELEMENTARY",7,"DCSB",88,4,3,-4,123]
[null,"RAMONA BOULEVARD EL",2,"DCSB",28,null,2,null,50]
[null,"SAN PABLO ELEMENTARY",2,"DCSB",59,2,null,-2,52]
[null,"SAN JOSE ELEMENTARY",15,"DCSB",183,4,8,-4,228]
[null,"BAYVIEW ELEMENTARY",3,"DCSB",19,null,3,null,92]
[null,"LAKE LUCINA ELEMENTARY",2,"DCSB",22,null,2,null,48]
[null,"TERRY PARKER HIGH ",6,"DCSB",248,null,6,null,131]
[null,"ENGLEWOOD ELEMENTARY",1,"DCSB",0,null,1,null,12]
[null,"JOHN STOCKTON EL",6,"DCSB",38,null,6,null,108]
[null,"WOODLAND ACRES EL",17,"DCSB",158,16,1,-16,426]
[null,"ENGLEWOOD HIGH ",3,"DCSB",80,null,3,null,42]
[null,"PAXON MIDDLE",3,"DCSB",54,null,3,null,36]
[null,"WINDY HILL ELEMENTARY",10,"DCSB",56,null,10,null,175]
[null,"TIMUCUAN ELEMENTARY",6,"DCSB",40,null,6,null,126]
[null,"HIGHLANDS ELEMENTARY",3,"DCSB",21,null,3,null,62]
[null,"DOUGLAS ANDERSON ",8,"DCSB",225,7,1,-7,108]
[null,"SADIE TILLIS ELEMENTARY",1,"FED",0,1,null,-1,31]
[null,"SUSIE TOLBERT EL",4,"DCSB",16,null,4,null,52]
[null,"DARNELL-COOKMAN MIDDLE",5,"DCSB",109,null,2,null,116]
[null,"RICHARD L. BROWN EL",4,"DCSB",82,null,4,null,53]
[null,"STANTON HIGH",13,"DCSB",369,4,9,-4,178]
[null,"R. V. DANIELS ELEMENTARY",2,"FED",0,2,null,-2,48]
[null,"WILLIAM M. RAINES HIGH ",1,"DCSB",28,null,1,null,26]
[null,"PALM AVENUE ",4,"DCSB",16,null,4,null,50]
[null,"REYNOLDS LANE EL",7,"DCSB",56,4,3,-4,77]
[null,"KINGS TRAIL ELEMENTARY",5,"DCSB",80,null,5,null,112]
[null,"PICKETT ELEMENTARY",3,"DCSB",0,null,3,null,36]
[null,"BROOKVIEW ELEMENTARY",7,"DCSB",120,null,7,null,84]
[null,"JEB STUART",2,"DCSB",0,1,1,-1,42]
[null,"PARKWOOD HEIGHTS EL",5,"DCSB",92,null,5,null,107]
[null,"SOUTHSIDE MIDDLE ",10,"DCSB",242,2,8,-2,167]
[null,"JEAN RIBAULT MIDDLE ",14,"DCSB",420,null,14,null,104]
[null,"ARLINGTON MIDDLE ",5,"DCSB",49,null,5,null,79]
[null,"HYDE GROVE ELEMENTARY",12,"DCSB",0,3,9,-3,408]
[null,"JUSTINA ROAD ELEMENTARY",1,"DCSB",22,null,1,null,12]
[null,"JEFFERSON DAVIS MIDDLE",17,"DCSB",469,null,17,null,126]
[null,"SAN MATEO ELEMENTARY",6,"DCSB",62,null,6,null,115]
[null,"JOSEPH STILWELL MIDDLE ",11,"DCSB",273,null,11,null,142]
[null,"MARTIN LUTHER KING EL",2,"DCSB",22,null,2,null,50]
[null,"NORMANDY VILLAGE EL",3,"DCSB",30,null,3,null,36]
[null,"GREENFIELD ELEMENTARY",3,"DCSB",35,null,3,null,72]
[null,"DUNCAN U. FLETCHER HIGH",14,"DCSB",461,null,14,null,150]
[null,"SAMUEL W. WOLFSON HIGH",16,"DCSB",351,1,15,-1,397]
[null,"SEABREEZE ELEMENTARY",7,"DCSB",112,null,7,null,151]
[null,"MAYPORT ELEMENTARY",9,"DCSB",112,null,9,null,242]
[null,"MERRILL ROAD EL",6,"DCSB",110,null,6,null,145]
[null,"JACKSONVILLE HEIGHTS EL",2,"DCSB",47,null,2,null,49]
[null,"LONE STAR ELEMENTARY",4,"DCSB",40,1,1,-1,76]
[null,"STONEWALL JACKSON EL",1,"DCSB",22,null,1,null,12]
[null,"FORT CAROLINE EL",9,"DCSB",186,null,9,null,208]
[null,"MAMIE AGNES JONES EL",2,"DCSB",19,1,1,-1,62]
[null,"SANDALWOOD HIGH ",10,"DCSB",320,8,2,-8,216]
[null,"FORT CAROLINE MIDDLE ",13,"DCSB",277,null,13,null,206]
[null,"ARLINGTON HEIGHTS EL",4,"DCSB",30,null,4,null,48]
[null,"NATHAN B. FORREST HIGH",13,"DCSB",343,null,13,null,184]
[null,"LOUIS SHEFFIELD EL",3,"DCSB",18,null,3,null,51]
[null,"GREGORY DRIVE EL",7,"DCSB",106,null,7,null,128]
[null,"HIGHLANDS MIDDLE",19,"DCSB",522,null,19,null,266]
[null,"JOSEPH FINEGAN EL",3,"DCSB",57,null,3,null,75]
[null,"EDWARD WHITE HIGH ",9,"DCSB",231,null,9,null,151]
[null,"PINE ESTATES ELEMENTARY",4,"DCSB",30,null,4,null,73]
[null,"FRANK PETERSON",1,"FED",60,1,null,-1,28]
[null,"A. PHILIP RANDOLPH ",2,"DCSB",90,null,2,null,28]
[]
["2c1.","DUVAL Total",523,null,9687,108,407,-108,"Avg Age 18.28"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"J. ALLEN AXSON EL",1,null,1,null,null,null,1]
[null,"LOLA M. CULVER EL",2,null,2,null,null,null,2]
[null,"LORETTO ELEMENTARY",2,{"$nulls":4},2,2]
[null,"LANDON MIDDLE",13,null,null,13,null,null,13]
[null,"ANDREW JACKSON HIGH",4,null,null,null,4,null,4]
[null,"ARLINGTON ELEMENTARY",2,{"$nulls":4},2,2]
[null,"THOMAS JEFFERSON EL",1,null,null,1,null,null,1]
[null,"GARDEN CITY ELEMENTARY",2,null,null,2,null,null,2]
[null,"HOGAN-SPRING GLEN EL",2,null,null,2,null,null,2]
[null,"ATLANTIC BEACH EL",2,null,null,2,null,null,2]
[null,"LAKESHORE MIDDLE",2,{"$nulls":4},2,2]
[null,"ALFRED I. duPONT MIDDLE ",10,{"$nulls":4},10,10]
[null,"HYDE PARK ELEMENTARY",3,null,3,null,null,null,3]
[null,"BILTMORE ELEMENTARY",4,4,{"$nulls":4},4]
[null,"SAN PABLO ELEMENTARY",2,null,null,null,2,null,2]
[null,"SAN JOSE ELEMENTARY",4,null,4,null,null,null,4]
[null,"WOODLAND ACRES EL",16,null,16,null,null,null,16]
[null,"DOUGLAS ANDERSON",7,null,7,null,null,null,7]
[null,"SADIE TILLIS ELEMENTARY",1,{"$nulls":4},1,1]
[null,"STANTON HIGH",4,4,{"$nulls":4},4]
[null,"REYNOLDS LANE",4,4,{"$nulls":4},4]
[null,"R. V. DANIELS ELEMENTARY",2,{"$nulls":4},2,2]
[null,"SOUTHSIDE MIDDLE ",2,{"$nulls":4},2,2]
[null,"HYDE GROVE ELEMENTARY",3,{"$nulls":4},3,3]
[null,"SAMUEL W. WOLFSON HIGH",1,null,null,null,1,null,1]
[null,"LONE STAR ELEMENTARY",1,null,null,null,1,null,1]
[null,"JEB STUART",1,1,{"$nulls":4},1]
[null,"MAMIE AGNES JONES ELEM",1,{"$nulls":4},1,1]
[null,"SANDALWOOD HIGH ",8,null,null,8,null,null,8]
[null,"FRANK PETERSON",1,null,1,null,null,null,1]
[]
["2c2.","DUVAL Total",108,13,34,28,8,25,108]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05","FISH Stu. Sta.","# Years Leased "]
[null,"No Leased Facilities"]
[{"$nulls":8},1]
["2c3.","DUVAL Total",0,null,0,0,0,0,1]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2004-05"]
[null,"Daniel Payne Academy (6-8)",12,"Daniel Payne Academy, Inc.","1997-98",264,179,3,180]
[null,"Empowering Young Minds (6-8)",21,"Empowering Young Minds Acdy","1997-98",450,346,3,375]
[null,"SOS Academy (6-8)",22,"Schools of Success Academy, Inc.","1997-98",550,477,3,500]
[null,"Kreative Kids Academy (K-4)",5,"Kreative Kids Youth Foundation","1999-00",125,103,3,120]
[null,"Rader Schools (6-8)",6,"Rader School of Duval County","1999-00",135,154,3,180]
[null,"Horizons Unlimited (6-8)",10,"Horizons Unlimited","1999-00",220,97,3,240]
[null,"Cornerstone Academy (6-8)",13,"Cornerstone Academy","2000-01",250,null,3,250]
[null,"Wayman Academy of the Arts (K-5)",11,"Wayman Academy","2000-01",200,null,3,500]
[null,"Destiny Academy of Excellence (K-5)",9,"Destiny Ed. Acdmy. Of Excellance","2000-01",175,null,3,300]
[]
["2c4.","DUVAL Total",109,null,null,2369,1356,27,2645]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"M.V. RUTHERFORD ",20,18,172,8.6,137,null,6.85]
[null,"J. ALLEN AXSON EL",18,374,378,21,350,null,19.44]
[null,"LACKAWANNA  ",23,38,119,5.17,106,null,4.61]
[null,"BEULAH BEAL ",16,52,178,11.13,30,null,1.88]
[null,"WEST RIVERSIDE EL",20,433,344,17.2,382,null,19.1]
[null,"LOLA M. CULVER EL",13,276,336,25.85,289,null,22.23]
[null,"GRAND PARK ",18,185,201,11.17,54,null,3]
[null,"BRENTWOOD ELEMENTARY",20,402,327,16.35,292,null,14.6]
[null,"ORTEGA ELEMENTARY",15,259,383,25.53,346,null,23.07]
[null,"CENTRAL RIVERSIDE EL",21,470,483,23,503,null,23.95]
[null,"RUTH N. UPSON EL",25,545,523,20.92,415,null,16.6]
[null,"FISHWEIR ELEMENTARY",15,294,379,25.27,355,null,23.67]
[null,"ANNIE R. MORGAN EL",22,519,481,21.86,500,null,22.73]
[null,"NORWOOD ELEMENTARY",10,217,191,19.1,210,null,21]
[null,"KIRBY-SMITH MIDDLE",42,866,1016,24.19,979,null,23.31]
[null,"LORETTO ELEMENTARY",58,1381,1288,22.21,1275,null,21.98]
[null,"LANDON MIDDLE ",47,1021,1248,26.55,500,null,10.64]
[null,"MARINE SCIENCE CENTER",8,146,34,4.25,30,null,3.75]
[null,"ROBERT E. LEE HIGH",59,1509,1350,22.88,1152,null,19.53]
[null,"ANDREW JACKSON HIGH ",54,1197,1447,26.8,1524,null,28.22]
[null,"HENRY F. KITE ELEMENTARY",13,298,358,27.54,363,null,27.92]
[null,"BALDWIN HIGH",22,565,457,20.77,458,null,20.82]
[null,"BALDWIN MIDDLE",22,529,422,19.18,422,null,19.18]
[null,"DINSMORE ELEMENTARY",20,487,447,22.35,490,null,24.5]
[null,"ARLINGTON ELEMENTARY",16,350,355,22.19,333,null,20.81]
[null,"THOMAS JEFFERSON",22,488,491,22.32,587,null,26.68]
[null,"WHITEHOUSE ELEMENTARY",24,566,630,26.25,560,null,23.33]
[null,"WESCONNETT ELEMENTARY",17,374,431,25.35,341,null,20.06]
[null,"GARDEN CITY ELEMENTARY",22,534,510,23.18,598,null,27.18]
[null,"OCEANWAY ELEMENTARY",32,748,747,23.34,803,null,25.09]
[null,"DUNCAN FLETCHER MIDDLE",52,1273,1444,27.77,1729,null,33.25]
[null,"HOGAN-SPRING GLEN EL",25,540,547,21.88,504,null,20.16]
[null,"ATLANTIC BEACH EL",30,648,534,17.8,505,null,16.83]
[null,"ALFRED I. DUPONT MIDDLE ",48,1232,1256,26.17,1252,null,26.08]
[null,"VENETIA ELEMENTARY",21,461,428,20.38,413,null,19.67]
[null,"LAKE SHORE MIDDLE ",60,1319,1146,19.1,1062,null,17.7]
[null,"NORTH SHORE ELEMENTARY",31,655,517,16.68,436,5,12.11]
[null,"HENDRICKS AVENUE EL",24,536,592,24.67,599,null,24.96]
[null,"SPRING PARK ELEMENTARY",17,400,360,21.18,415,null,24.41]
[null,"JOHN LOVE ELEMENTARY",19,449,316,16.63,222,null,11.68]
[null,"LAKE FOREST ELEMENTARY",22,546,618,28.09,549,null,24.95]
[null,"PAXON HIGH ",58,971,996,17.17,1154,null,19.9]
[null,"SOUTHSIDE ESTATES EL",24,554,605,25.21,679,null,28.29]
[null,"HYDE PARK ELEMENTARY",25,591,618,24.72,557,null,22.28]
[null,"BILTMORE ELEMENTARY",20,443,373,18.65,338,null,16.9]
[null,"RAMONA BOULEVARD EL",23,588,481,20.91,449,null,19.52]
[null,"SAN PABLO ELEMENTARY",30,701,568,18.93,548,null,18.27]
[null,"LOVE GROVE ELEMENTARY",30,734,571,19.03,506,null,16.87]
[null,"SAN JOSE ELEMENTARY",27,672,763,28.26,829,null,30.7]
[null,"BAYVIEW ELEMENTARY",18,370,435,24.17,430,1,22.63]
[null,"LAKE LUCINA ELEMENTARY",21,532,579,27.57,535,null,25.48]
[null,"TERRY PARKER HIGH",72,1781,2016,28,2069,null,28.74]
[null,"ENGLEWOOD ELEMENTARY",22,496,493,22.41,526,null,23.91]
[null,"JOHN STOCKTON EL",18,389,509,28.28,449,null,24.94]
[null,"WOODLAND ACRES EL",39,784,839,21.51,736,null,18.87]
[null,"ENGLEWOOD HIGH",67,1548,1749,26.1,1859,null,27.75]
[null,"SALLYE B. MATHIS EL",19,457,472,24.84,354,null,18.63]
[null,"PAXON MIDDLE ",44,912,1001,22.75,987,null,22.43]
[null,"PINEDALE ELEMENTARY",29,722,675,23.28,670,null,23.1]
[null,"WINDY HILL ELEMENTARY",33,664,792,24,794,null,24.06]
[null,"RUTLEDGE H. PEARSON EL",24,559,349,14.54,346,null,14.42]
[null,"JEAN RIBAULT HIGH",66,1642,1132,17.15,1249,null,18.92]
[null,"CEDAR HILLS ELEMENTARY",21,451,429,20.43,302,null,14.38]
[null,"TIMUCUAN ELEMENTARY",30,715,669,22.3,645,null,21.5]
[null,"HIGHLANDS ELEMENTARY",27,590,578,21.41,630,2,21.72]
[null,"LONG BRANCH ELEMENTARY",23,369,348,15.13,248,null,10.78]
[null,"DOUGLAS ANDERSON ",33,691,918,27.82,958,9,22.81]
[null,"SADIE TILLIS ELEMENTARY",21,513,452,21.52,519,null,24.71]
[null,"SAINT CLAIRE EVANS ACDMY",29,734,537,18.52,673,null,23.21]
[null,"SUSIE TOLBERT EL",26,582,596,22.92,588,null,22.62]
[null,"WEST JACKSONVILLE EL",16,391,379,23.69,429,null,26.81]
[null,"JACKSONVILLE BEACH EL",21,505,605,28.81,588,null,28]
[null,"DARNELL-COOKMAN MIDDLE",38,940,1149,30.24,1177,null,30.97]
[null,"MATTHEW GILBERT MIDDLE",34,861,877,25.79,860,null,25.29]
[null,"RICHARD L. BROWN EL",34,805,827,24.32,680,null,20]
[null,"S.P. LIVINGSTON EL",35,863,694,19.83,589,null,16.83]
[null,"JAMES WELDON JOHNSON ",37,906,1099,29.7,1190,null,32.16]
[null,"STANTON HIGH",67,1850,1492,22.27,1509,4,21.25]
[null,"JOHN E. FORD ELEMENTARY",27,735,773,28.63,701,null,25.96]
[null,"NORTHWESTERN MIDDLE ",44,895,840,19.09,787,null,17.89]
[null,"MARY McLEOD BETHUNE EL",26,643,610,23.46,381,null,14.65]
[null,"GEORGE W. CARVER EL",29,682,434,14.97,450,null,15.52]
[null,"PINE FOREST ELEMENTARY",16,375,373,23.31,340,null,21.25]
[null,"R. V. DANIELS ELEMENTARY",25,501,305,12.2,360,null,14.4]
[null,"RUFUS E. PAYNE EL",30,673,494,16.47,450,null,15]
[null,"Mt. HERMAN ",0,0,166,0,69,null,0]
[null,"WILLIAM M. RAINES HIGH ",77,1861,1889,24.53,1680,null,21.82]
[null,"CARTER G. WOODSON EL",27,632,445,16.48,460,null,17.04]
[null,"EUGENE BUTLER MIDDLE ",38,833,873,22.97,716,null,18.84]
[null,"S. A. HULL ELEMENTARY",19,416,335,17.63,355,null,18.68]
[null,"PALM AVENUE ",0,0,187,0,27,null,0]
[null,"REYNOLDS LANE EL",22,516,453,20.59,409,null,18.59]
[null,"KINGS TRAIL ELEMENTARY",27,629,488,18.07,404,null,14.96]
[null,"NORMANDY ELEMENTARY",14,315,220,15.71,208,null,14.86]
[null,"PICKETT ELEMENTARY",16,368,286,17.88,299,null,18.69]
[null,"BROOKVIEW ELEMENTARY",32,782,1019,31.84,1057,null,33.03]
[null,"J.E.B. STUART MIDDLE",48,985,1053,21.94,975,null,20.31]
[null,"PARKWOOD HEIGHTS EL",27,633,541,20.04,616,null,22.81]
[null,"HOLIDAY HILL ELEMENTARY",22,542,579,26.32,500,null,22.73]
[null,"OAK HILL ELEMENTARY",38,849,659,17.34,543,null,14.29]
[null,"SOUTHSIDE MIDDLE",47,1125,1208,25.7,1138,null,24.21]
[null,"JEAN RIBAULT MIDDLE ",66,1600,1059,16.05,1013,null,15.35]
[null,"ARLINGTON MIDDLE ",41,879,1031,25.15,1012,1,24.1]
[null,"HYDE GROVE ELEMENTARY",32,543,606,18.94,527,null,16.47]
[null,"JUSTINA ROAD ELEMENTARY",22,472,443,20.14,440,null,20]
[null,"JEFFERSON DAVIS MIDDLE ",61,1453,1563,25.62,1475,null,24.18]
[null,"SAN MATEO ELEMENTARY",23,545,697,30.3,609,null,26.48]
[null,"JOSEPH STILWELL MIDDLE ",49,1116,1266,25.84,1140,null,23.27]
[null,"MARTIN LUTHER KING EL",32,749,570,17.81,569,null,17.78]
[null,"NORMANDY VILLAGE EL",33,748,708,21.45,690,null,20.91]
[null,"GREENFIELD ELEMENTARY",26,574,605,23.27,520,null,20]
[null,"DUNCAN U. FLETCHER HIGH ",91,2336,2027,22.27,2086,null,22.92]
[null,"SAMUEL W. WOLFSON HIGH ",73,1709,1799,24.64,1933,null,26.48]
[null,"SEABREEZE ELEMENTARY",28,605,642,22.93,549,null,19.61]
[null,"CRYSTAL SPRINGS EL",43,1152,1235,28.72,1167,null,27.14]
[null,"MAYPORT ELEMENTARY",48,1111,959,19.98,1001,null,20.85]
[null,"MERRILL ROAD EL",24,513,682,28.42,730,null,30.42]
[null,"JACKSONVILLE HEIGHTS EL",39,895,1010,25.9,921,null,23.62]
[null,"BEAUCLERC ELEMENTARY",51,1221,1267,24.84,1217,null,23.86]
[null,"CHIMNEY LAKES EL",47,1194,1194,25.4,1188,null,25.28]
[null,"LONE STAR ELEMENTARY",31,711,846,27.29,869,null,28.03]
[null,"STONEWALL JACKSON EL",18,387,352,19.56,303,null,16.83]
[null,"FORT CAROLINE EL",34,818,835,24.56,806,null,23.71]
[null,"MAMIE AGNES JONES EL",32,525,493,15.41,430,null,13.44]
[null,"SANDALWOOD HIGH",104,2654,2825,27.16,3432,null,33]
[null,"FORT CAROLINE MIDDLE ",52,1165,1045,20.1,1007,null,19.37]
[null,"SABAL PALM ELEMENTARY",42,1146,1382,32.9,1451,null,34.55]
[null,"ARLINGTON HEIGHTS EL",21,505,534,25.43,506,null,24.1]
[null,"NATHAN B. FORREST HIGH ",71,1679,1708,24.06,1540,null,21.69]
[null,"LOUIS SHEFFIELD EL",30,590,645,21.5,730,null,24.33]
[null,"GREGORY DRIVE EL",27,614,711,26.33,605,null,22.41]
[null,"HIGHLANDS MIDDLE",66,1543,1585,24.02,1565,null,23.71]
[null,"CROWN POINT ELEMENTARY",50,1353,1300,26,1216,null,24.32]
[null,"NEPTUNE BEACH EL",49,1332,1124,22.94,1022,null,20.86]
[null,"JOSEPH FINEGAN EL",35,815,535,15.29,550,null,15.71]
[null,"EDWARD WHITE HIGH",74,1942,2084,28.16,2129,null,28.77]
[null,"GREENLAND PINES EL",27,743,713,26.41,749,null,27.74]
[null,"PINE ESTATES ELEMENTARY",18,382,322,17.89,209,null,11.61]
[null,"TWIN LAKES ACADEMY EL",32,1045,838,26.19,1012,null,31.63]
[null,"ALDEN ROAD ",0,0,184,0,34,null,0]
[null,"TWIN LAKES ACDMY MIDDLE",61,1577,1574,25.8,1776,null,29.11]
[null,"MAYPORT MIDDLE",41,984,1045,25.49,1000,null,24.39]
[null,"ENTERPRISE LEARNING ACDMY",32,1045,686,21.44,799,null,24.97]
[null,"LANDMARK MIDDLE",65,1688,1849,28.45,2296,null,35.32]
[null,"ALIMACANI ELEMENTARY",47,1191,1173,24.96,1239,null,26.36]
[null,"MANDARIN OAKS EL",46,1194,1247,27.11,1219,null,26.5]
[null,"MANDARIN MIDDLE",61,1663,1520,24.92,1547,null,25.36]
[null,"MANDARIN HIGH",85,2309,2266,26.66,2306,null,27.13]
[null,"ANDREW A. ROBINSON EL",44,1180,952,21.64,880,null,20]
[null,"ABESS PARK ELEMENTARY",32,1045,1015,31.72,1025,null,32.03]
[null,"CHETS CREEK ELEMENTARY",32,1045,991,30.97,1590,null,49.69]
[null,"FIRST COAST HIGH ",65,1708,1781,27.4,1669,null,25.68]
[null,"FRANK H. PETERSON ",69,784,827,11.99,1280,null,18.55]
[null,"A. PHILIP RANDOLPH ",67,632,622,9.28,1107,null,16.52]
[]
["2e.","DUVAL Total",5324,123475,122351,"District Avg 23",121329,22,"District Avg 23"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR AVERAGE"]
[null,"M.V. RUTHERFORD ",null,18,18,18,18,18,18,null,0]
[null,"J. ALLEN AXSON EL",null,0,0,0,0,0,0]
[null,"LACKAWANNA ",null,19,19,19,19,19,19]
[null,"BEULAH BEAL",null,52,52,52,52,52,52]
[null,"LOLA M. CULVER EL",null,16,0,0,0,0,3.2]
[null,"GRAND PARK ",null,243,243,243,243,243,243]
[null,"ORTEGA ELEMENTARY",null,68,68,68,68,68,68]
[null,"FISHWEIR ELEMENTARY",null,39,39,39,39,39,39]
[null,"ANNIE R. MORGAN EL",null,72,72,72,72,72,72]
[null,"NORWOOD ELEMENTARY",null,35,35,35,35,35,35]
[null,"LORETTO ELEMENTARY",null,95,95,95,95,95,95]
[null,"LANDON MIDDLE",null,249,249,0,0,0,99.6]
[null,"ANDREW JACKSON HIGH",null,116,116,116,0,0,69.6]
[null,"HENRY F. KITE ELEMENTARY",null,8,8,8,8,8,8]
[null,"BALDWIN MIDDLE/HIGH",null,60,60,60,60,60,60]
[null,"ARLINGTON ELEMENTARY",null,26,26,26,26,0,20.8]
[null,"THOMAS JEFFERSON EL",null,0,0,0,0,0,0]
[null,"WHITEHOUSE ELEMENTARY",null,155,155,155,155,155,155]
[null,"WESCONNETT ELEMENTARY",null,26,26,26,26,26,26]
[null,"GARDEN CITY ELEMENTARY",null,0,0,0,0,0,0]
[null,"HOGAN-SPRING GLEN EL",null,73,73,53,53,53,61]
[null,"ATLANTIC BEACH EL",null,17,17,0,0,0,6.8]
[null,"ALFRED I. duPONT MIDDLE ",null,360,360,360,360,0,288]
[null,"VENETIA ELEMENTARY",null,30,30,30,30,30,30]
[null,"LAKE SHORE MIDDLE",null,437,437,437,437,381,425.8]
[null,"HENDRICKS AVENUE EL",null,0,0,0,0,0,0]
[null,"JOHN LOVE ELEMENTARY",null,10,10,10,10,10,10]
[null,"SOUTHSIDE ESTATES EL",null,0,0,0,0,0,0]
[null,"HYDE PARK ELEMENTARY",null,8,8,8,8,8,8]
[null,"BILTMORE ELEMENTARY",null,88,22,22,22,22,35.2]
[null,"RAMONA BOULEVARD EL",null,28,28,28,28,28,28]
[null,"SAN PABLO ELEMENTARY",null,59,59,59,19,19,43]
[null,"SAN JOSE ELEMENTARY",null,183,139,139,139,139,147.8]
[null,"BAYVIEW ELEMENTARY",null,19,19,19,19,19,19]
[null,"LAKE LUCINA ELEMENTARY",null,22,22,22,22,22,22]
[null,"TERRY PARKER HIGH ",null,248,248,248,248,248,248]
[null,"ENGLEWOOD ELEMENTARY",null,0,0,0,0,0,0]
[null,"JOHN STOCKTON EL",null,38,38,38,38,38,38]
[null,"WOODLAND ACRES EL",null,158,0,0,0,0,31.6]
[null,"ENGLEWOOD HIGH ",null,80,80,80,80,80,80]
[null,"PAXON MIDDLE",null,54,54,54,54,54,54]
[null,"WINDY HILL ELEMENTARY",null,56,56,56,56,56,56]
[null,"TIMUCUAN ELEMENTARY",null,40,40,40,40,40,40]
[null,"HIGHLANDS ELEMENTARY",null,21,21,21,21,21,21]
[null,"DOUGLAS ANDERSON ",null,225,0,0,0,0,45]
[null,"SADIE TILLIS ELEMENTARY",null,0,0,0,0,0,0]
[null,"SUSIE TOLBERT EL",null,16,16,16,16,16,16]
[null,"DARNELL-COOKMAN MIDDLE",null,109,109,109,109,109,109]
[null,"RICHARD L. BROWN EL",null,82,82,82,82,82,82]
[null,"STANTON HIGH",null,249,249,249,249,249,249]
[null,"R. V. DANIELS ELEMENTARY",null,0,0,0,0,0,0]
[null,"WILLIAM M. RAINES HIGH ",null,28,28,28,28,28,28]
[null,"PALM AVENUE ",null,16,16,16,16,16,16]
[null,"REYNOLDS LANE EL",null,16,16,16,16,16,16]
[null,"KINGS TRAIL ELEMENTARY",null,80,80,80,80,80,80]
[null,"PICKETT ELEMENTARY",null,0,0,0,0,0,0]
[null,"BROOKVIEW ELEMENTARY",null,120,120,120,120,120,120]
[null,"JEB STUART",null,0,0,0,0,0,0]
[null,"PARKWOOD HEIGHTS EL",null,92,92,92,92,92,92]
[null,"SOUTHSIDE MIDDLE ",null,242,242,242,242,189,231.4]
[null,"JEAN RIBAULT MIDDLE ",null,420,420,420,420,420,420]
[null,"ARLINGTON MIDDLE ",null,49,49,49,49,49,49]
[null,"HYDE GROVE ELEMENTARY",null,0,0,0,0,0,0]
[null,"JUSTINA ROAD ELEMENTARY",null,22,22,22,22,22,22]
[null,"JEFFERSON DAVIS MIDDLE",null,469,469,469,469,469,469]
[null,"SAN MATEO ELEMENTARY",null,62,62,62,62,62,62]
[null,"JOSEPH STILWELL MIDDLE ",null,273,273,273,273,273,273]
[null,"MARTIN LUTHER KING EL",null,22,22,22,22,22,22]
[null,"NORMANDY VILLAGE EL",null,30,30,30,30,30,30]
[null,"GREENFIELD ELEMENTARY",null,35,35,35,35,35,35]
[null,"DUNCAN U. FLETCHER HIGH",null,461,461,461,461,461,461]
[null,"SAMUEL W. WOLFSON HIGH",null,351,351,351,351,351,351]
[null,"SEABREEZE ELEMENTARY",null,112,112,112,112,112,112]
[null,"MAYPORT ELEMENTARY",null,112,112,112,112,112,112]
[null,"MERRILL ROAD EL",null,110,110,110,110,110,110]
[null,"JACKSONVILLE HEIGHTS EL",null,47,47,47,47,47,47]
[null,"LONE STAR ELEMENTARY",null,40,40,40,18,18,31.2]
[null,"STONEWALL JACKSON EL",null,22,22,22,22,22,22]
[null,"FORT CAROLINE EL",null,186,186,186,186,186,186]
[null,"MAMIE AGNES JONES EL",null,19,19,19,19,19,19]
[null,"SANDALWOOD HIGH ",null,320,320,60,60,60,164]
[null,"FORT CAROLINE MIDDLE ",null,277,277,277,277,277,277]
[null,"ARLINGTON HEIGHTS EL",null,30,30,30,30,30,30]
[null,"NATHAN B. FORREST HIGH",null,343,343,343,343,343,343]
[null,"LOUIS SHEFFIELD EL",null,18,18,18,18,18,18]
[null,"GREGORY DRIVE EL",null,106,106,106,106,106,106]
[null,"HIGHLANDS MIDDLE",null,522,522,522,522,522,522]
[null,"JOSEPH FINEGAN EL",null,57,57,57,57,57,57]
[null,"EDWARD WHITE HIGH ",null,281,281,281,281,281,281]
[null,"PINE ESTATES ELEMENTARY",null,30,30,30,30,30,30]
[null,"FRANK PETERSON",null,60,60,60,60,60,60]
[null,"A. PHILIP RANDOLPH ",null,90,90,90,90,90,90]
[]
["2f.","DUVAL Total students in relocatables by year",null,9577,9068,8522,8344,7849,8672]
[null,"Total number of CO-FTE students projected by year",null,123094,123875,124453,124958,125477,124371.4]
[null,"Percent in relocatables by year",null,0.08,0.07,0.07,0.07,0.06,0.07]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"Oceanway Elementary will be closed and converted to a Middle School on the same site."]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01 ","2000-01 ","2000-01 ","2000-01 ","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Bayview Elementary",0,1931800,0,3268,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"S.A. Hull Elementary",0,1809300,0,4956]
[null,"Ortega Elementary",0,1020900,0,3449,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Oceanway Elementary Conversion",2,8473617,1320,118965,90.13,88,88,180,6419.41,7226,13517,18473]
["3a.","DUVAL Total 2000-01",null,13235617,1320,130638,98.97,null,null,null,10026.98]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Oceanway Elementary ",2,8837900,1320,118965,90.13,88,90,180,6695.38,7226,13517,18473]
[null,"Arlington Middle ESE ",3,3184500,251,13350]
[null,"Andrew Jackson High",0,1397500,0,4808]
[null,"Seabreeze Elementary",0,2877600,0,11012]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","DUVAL Total 2001-02",null,16297500,1571,148135,94.29,null,null,null,10373.97]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Fishweir Elementary",0,2188900,0,5359]
[null,"District wide ESE ",3,1500000,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","DUVAL Total 2002-03",null,3688900,0,5359,{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Arlington Elementary",0,2127200,0,3138]
[null,"Pickett Elementary",0,2339000,0,5734]
[null,"Northshore Elementary",0,741500,0,7010]
[null,"Wolfson High",0,4334486,0,291609]
[null,"Ribault Middle ESE ",3,1884650,0,19589]
[null,"duPont Middle, ",0,2623000,0,13013]
[null,"Terry Parker ESE facility",3,2519800,0,7000]
[{"$nulls":4},0,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","DUVAL Total 2003-04",null,16569636,0,347093,{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Arlington Middle",0,3673147,0,9831]
[null,"New Middle \"DD\" ",2,21064806,1320,179112,135.69]
[null,"Cedar Hills Elementary",0,2359400,0,2000]
[null,"New High School \"AAA\" ",3,42972000,0,300781]
[null,"Hogan Spring Glen Elementary",0,2732380,0,7815]
[null,"Arlington Heights Elementary",0,2441100,0,8379]
[null,"Forrest High, Expand media",0,2734340,0,21022]
[null,"Lee High, Remodel cafeteria",0,2750400,0,0]
[null,"J.E.B. Stuart Middle",0,1326340,0,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","DUVAL Total 2004-05",null,82053913,1320,528940,{"$nulls":4},62162.06]
[]
["3f.","DUVAL 5-Year Total",null,131845566,4211,1160165]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,51525306,53207655,54940475,56725279,52892907,269291622]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,51525306,53207655,54940475,56725279,52892907,269291622,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase other vehicles",null,588000,0,0,0,0,588000,0.00218350647388503]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used for maintenance/repair",null,22431322,23104262,23797390,24511312,25246651,119090937,0.442237809388663]
[null,"  less amount used to purchase capital outlay equipment",null,0,0,0,0,0,0,0]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,0,0,0,0,0,0,0]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,28505984,30103393,31143085,32213967,27646256,149612685,0.555578684137452,0.52]
[null,"P E C O New Construction",null,3305477,1746717,3182169,2524728,2154036,12913127,null,0.05]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,51846246,0,0,0,64036806,115883052,null,0.4]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,8236936,0,0,0,0,8236936,null,0.03]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","DUVAL Total",null,91894643,31850110,34325254,34738695,93837098,286645800,1,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Bayview Elementary",null,1931800,null,null,0,0,1931800]
[null,"S.A. Hull Elementary",null,1809300,{"$nulls":4},1809300]
[null,"Ortega Elementary",null,1020900,{"$nulls":4},1020900]
[null,"Oceanway Elementary Conversion",1320,8473617,8837900,null,null,null,17311517]
[null,"Arlington Middle ESE ",251,null,3184500,null,null,null,3184500]
[null,"Andrew Jackson High",null,null,1397500,null,null,null,1397500]
[null,"Seabreeze Elementary",null,null,2877600,null,null,null,2877600]
[null,"Fishweir Elementary",null,null,null,2188900,null,null,2188900]
[null,"District wide ESE ",null,null,null,1500000,null,null,1500000]
[null,"Arlington Elementary",{"$nulls":4},2127200,null,2127200]
[null,"Pickett Elementary",{"$nulls":4},2339000,null,2339000]
[null,"Northshore Elementary",{"$nulls":4},741500,null,741500]
[null,"Wolfson High",{"$nulls":4},4334486,null,4334486]
[null,"Ribault Middle ESE ",{"$nulls":4},1884650,null,1884650]
[null,"duPont Middle",{"$nulls":4},2623000,null,2623000]
[null,"Terry Parker ESE",{"$nulls":4},2519800,null,2519800]
[null,"Arlington Middle",{"$nulls":5},3673147,3673147]
[null,"New Middle \"DD\"  ",1320,{"$nulls":4},21064806,21064806]
[null,"Cedar Hills Elementary",{"$nulls":5},2359400,2359400]
[null,"New High School \"AAA\" ",{"$nulls":5},42972000,42972000]
[null,"Hogan Spring Glen Elementary",{"$nulls":5},2732380,2732380]
[null,"Arlington Heights Elementary",{"$nulls":5},2441100,2441100]
[null,"Forrest High",{"$nulls":5},2734340,2734340]
[null,"Lee High, Remodel cafeteria",{"$nulls":5},2750400,2750400]
[null,"J.E.B. Stuart Middle",{"$nulls":5},1326340,1326340]
[null,null,null,0,0,0,null,null,0]
["5.","DUVAL Total",2891,13235617,16297500,3688900,16569636,82053913,131845566]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","DUVAL Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"NA",null,0,0,0,0,null,0]
[null,null,null,0,0,0,null,0,0]
["7.","DUVAL Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2000."]
[]
[null,"SCHOOL BOARD OF ","DUVAL  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}