{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","2004-05 TO 2008-09","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"2004-05 TO 2008-09","index":1,"n_rows":546,"n_cols":17,"rows_kept":546,"cut":false,"hidden":false,"merged":[[1,0,1,9]],"flags":["formulas_cached_only"]}
[]
["HARDEE  SCHOOL DISTRICT - - FACILITIES WORK PROGRAM"]
["HARDEE   SCHOOL  DISTRICT - -  WORKSHEET ",{"$nulls":8},"Last Revised"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the Office of Educational Facilities, and a copy submitted ",{"$nulls":8},"2004-11-09"]
["electronically in digital format, as you received it (not a fax), prior to November 22, 2004, and all data accurate as of July 15, 2004."]
["District: ====>",null,null,"HARDEE","Date: ==>","2004-11-16",null,"For fiscal years","  2004-05 through 2008-09"]
[]
["Section 1013.35 School district facilities 5 - Year work program; definitions; preparation, adoption, and amendment."]
[]
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["2b1","A schedule of major repair and renovation projects necessary to maintain the educational facilities and ancillary facilities"]
[null,"of the district."]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09"]
[null,"Project",null,"Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Carpet/ tile replacement",21,"Senior High",8000,{"$nulls":4},8000]
[null,"Construct 50 parking spaces",21,"Senior High",null,null,null,30000,null,30000]
[null,"Covered walkways",21,"Senior High",70000,{"$nulls":4},70000]
[null,"HVAC renovations",21,"Senior High",20389,{"$nulls":4},20389]
[null,"Remodel locker room",21,"Senior High",30000,{"$nulls":4},30000]
[null,"Roof replacement",21,"Senior High",959831,50000,50000,50000,50000,1159831]
[null,"Tree trimming/ removal",21,"Senior High",19097,{"$nulls":4},19097]
[null,"Carpet/ tile replacement",22,"Adult Ed",1500,{"$nulls":4},1500]
[null,"Roof replacement",22,"Adult Ed",38471,{"$nulls":4},38471]
[null,"Tree trimming/ removal",22,"Adult Ed",4645,{"$nulls":4},4645]
[null,"Air quality",31,"Junior High",36382,{"$nulls":4},36382]
[null,"Bathrooms for Annex",31,"Junior High",20000,{"$nulls":4},20000]
[null,"Carpet/ tile replacement",31,"Junior High",28999,{"$nulls":4},28999]
[null,"Covered walkways",31,"Junior High",65846,{"$nulls":4},65846]
[null,"HVAC renovations",31,"Junior High",2653,{"$nulls":4},2653]
[null,"Repairs, renovation after hurricanes",31,"Junior High",15630,{"$nulls":4},15630]
[null,"Roof replacement",31,"Junior High",615053,{"$nulls":4},615053]
[null,"Tree trimming/ removal",31,"Junior High",18088,{"$nulls":4},18088]
[null,"Air quality",41,"Bowling Green Elem",15000,{"$nulls":4},15000]
[null,"Carpet/ tile replacement",41,"Bowling Green Elem",19122,{"$nulls":4},19122]
[null,"Correct drainage",41,"Bowling Green Elem",null,null,50000,null,null,50000]
[null,"Covered walkways",41,"Bowling Green Elem",211386,{"$nulls":4},211386]
[null,"Develop 40 parking spaces",41,"Bowling Green Elem",{"$nulls":4},25000,25000]
[null,"Electrical upgrades",41,"Bowling Green Elem",115485,{"$nulls":4},115485]
[null,"Raze bldgs 1-8, 11, 12",41,"Bowling Green Elem",{"$nulls":4},125000,125000]
[null,"Renovate café into classrooms",41,"Bowling Green Elem",14000,{"$nulls":4},14000]
[null,"Repairs, renovation after hurricanes",41,"Bowling Green Elem",127814,{"$nulls":4},127814]
[null,"Roof replacement",41,"Bowling Green Elem",105611,{"$nulls":4},105611]
[null,"Tree trimming/ removal",41,"Bowling Green Elem",15773,{"$nulls":4},15773]
[null,"Air quality",61,"Zolfo Springs Elem.",114782,{"$nulls":4},114782]
[null,"Carpet/ tile replacement",61,"Zolfo Springs Elem.",6000,{"$nulls":4},6000]
[null,"Covered walkways",61,"Zolfo Springs Elem.",163296,{"$nulls":4},163296]
[null,"Electrical upgrades",61,"Zolfo Springs Elem.",121850,{"$nulls":4},121850]
[null,"HVAC renovations",61,"Zolfo Springs Elem.",15301,{"$nulls":4},15301]
[null,"Repairs, renovation after hurricanes",61,"Zolfo Springs Elem.",226126,{"$nulls":4},226126]
[null,"Tree trimming/ removal",61,"Zolfo Springs Elem.",3804,{"$nulls":4},3804]
[null,"Carpet/ tile replacement",81,"Pioneer Career Academy",4225,{"$nulls":4},4225]
[null,"Covered walkways",81,"Pioneer Career Academy",70000,{"$nulls":4},70000]
[null,"Tree trimming/ removal",81,"Pioneer Career Academy",4645,{"$nulls":4},4645]
[null,"Air quality",91,"Wauchula Elem.",31576,{"$nulls":4},31576]
[null,"Carpet/ tile replacement",91,"Wauchula Elem.",25900,{"$nulls":4},25900]
[null,"Construct 75 parking spaces",91,"Wauchula Elem.",null,null,null,37500,null,37500]
[null,"Covered walkways",91,"Wauchula Elem.",70000,null,null,45000,null,115000]
[null,"Electrical upgrades",91,"Wauchula Elem.",179281,{"$nulls":4},179281]
[null,"HVAC renovations",91,"Wauchula Elem.",50264,{"$nulls":4},50264]
[null,"Roof replacement",91,"Wauchula Elem.",420182,{"$nulls":4},420182]
[null,"Tree trimming/ removal",91,"Wauchula Elem.",10452,{"$nulls":4},10452]
[null,"Air quality",111,"North Wauchula Elem.",62671,{"$nulls":4},62671]
[null,"Carpet/ tile replacement",111,"North Wauchula Elem.",6000,{"$nulls":4},6000]
[null,"Covered walkways",111,"North Wauchula Elem.",30184,{"$nulls":4},30184]
[null,"Electrical upgrades",111,"North Wauchula Elem.",191275,{"$nulls":4},191275]
[null,"HVAC renovations",111,"North Wauchula Elem.",44978,{"$nulls":4},44978]
[null,"Repairs, renovation after hurricanes",111,"North Wauchula Elem.",220391,{"$nulls":4},220391]
[null,"Roof replacement",111,"North Wauchula Elem.",50000,{"$nulls":4},50000]
[null,"Tree trimming/ removal",111,"North Wauchula Elem.",6201,{"$nulls":4},6201]
[null,"Carpet/ tile replacement",9001,"District office",1500,{"$nulls":4},1500]
[null,"Covered walkways",9001,"District office",72944,{"$nulls":4},72944]
[null,"Renovate Ed Center, MIS bldgs",9001,"District office",280000,{"$nulls":4},280000]
[null,"Tree trimming/ removal",9001,"District office",6968,{"$nulls":4},6968]
[null,"Upgrade wireless tower",9001,"District office",3639,{"$nulls":4},3639]
[null,"Repairs, renovation after hurricanes",9004,"Stadium",1000000,{"$nulls":4},1000000]
[null,"Roof replacement",9005,"Transportation",8500,{"$nulls":4},8500]
[null,"Tree trimming/ removal",9005,"Transportation",7548,{"$nulls":4},7548]
[null,"Repairs, renovation after hurricanes",9006,"Maintenance",5472,{"$nulls":4},5472]
[null,"Tree trimming/ removal",9006,"Maintenance",7419,{"$nulls":4},7419]
[null,"Lighting",9008,"Recreation Complex",55000,{"$nulls":4},55000]
[null,"Pool renovations",9008,"Recreation Complex",183744,{"$nulls":4},183744]
[null,"Poolhouse, dugouts, concessions",9008,"Recreation Complex",160000,{"$nulls":4},160000]
[null,"Carpet/ tile replacement",9999,"All sites",null,40000,40000,40000,40000,160000]
[null,"Fencing",9999,"All sites",100000,{"$nulls":4},100000]
[null,"HVAC renovations",9999,"All sites",null,150000,150000,150000,150000,600000]
[null,"Repairs, renovation after hurricanes",9999,"All sites",96702,{"$nulls":4},96702]
[null,"Roof repairs as needed",9999,"All sites",null,0,null,80000,null,80000]
[null,"Roof replacement- 13 portables",9999,"All sites",52000,{"$nulls":4},52000]
[{"$nulls":9},0]
["2b1","HARDEE Total",null,null,6749595,240000,290000,432500,390000,8102095]
[{"$nulls":9},8102095]
["2b2","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09"]
[null,"Project Description",null,null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New K-8 School",{"$nulls":7},0]
[null,"New construction- new school and land (+1,884 stations, +73 classrooms)",null,null,19238921,16311079,3950000,null,null,39500000]
[{"$nulls":9},0]
[null,"Senior High",{"$nulls":7},0]
[null,"Transfer relocatables from Jr. HIgh (+112 stations, +4 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Transfer relocatables from PCA (+26 stations, +2 classrooms)",{"$nulls":5},0,null,0]
[null,"Destroy old relocatables (-110 stations, -4 classrooms)",{"$nulls":4},0,null,null,0]
[null,"New construction- classrooms (+90 stations, +3 buildings on FISH)",null,null,300000,{"$nulls":4},300000]
[{"$nulls":9},0]
[null,"Junior High",{"$nulls":7},0]
[null,"Transfer relocatables to Sr. HIgh (-112 stations, -4 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Destroy old relocatables  (-127 stations, -5 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Discontinue use of buildings 1-11 for educational purposes (-750 stations, -29 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Remodel building 15 to District administration",{"$nulls":5},1000000,null,1000000]
[null,"Discontinue use of buildings 1-13 for educational purposes (-686 stations, -30 classrooms)",{"$nulls":4},0,null,null,0]
[null,"New construction- classrooms (+112 stations, +4 buildings on FISH)",null,null,400000,{"$nulls":4},400000]
[{"$nulls":9},0]
[null,"Bowling Green Elementary",{"$nulls":7},0]
[null,"Destroy old relocatables (-54 stations, -3 classrooms)",null,null,0,{"$nulls":4},0]
[null,"End lease of relocatable (-25 stations, -1 classroom)",{"$nulls":5},0,null,0]
[null,"Discontinue use of buildings 1-8, 11, 12 (-402 stations, -18 classrooms)",{"$nulls":6},0,0]
[null,"Convert building 13 to Administration (-75 stations, -3 classrooms)",{"$nulls":6},271632.2,271632.2]
[null,"Convert building 14, rooms 1 and 3 to ESE (-25 stations - 2 classrooms)",{"$nulls":6},141497.65,141497.65]
[null,"Convert building 14, room 2 to ESE resource",{"$nulls":6},46913.37,46913.37]
[null,"New construction- classrooms (+176 stations, +8 classrooms on FISH)",null,null,780931,{"$nulls":4},780931]
[null,"PE covered play and storage",null,null,120847,{"$nulls":4},120847]
[{"$nulls":9},0]
[null,"Zolfo Springs Elementary",{"$nulls":7},0]
[null,"PE covered play and storage",null,null,91447,{"$nulls":4},91447]
[null,"Destroy old relocatables (-60 stations, -3 classrooms)",null,null,0,{"$nulls":4},0]
[{"$nulls":9},0]
[null,"Pioneer Career Academy",{"$nulls":7},0]
[null,"Destroy old relocatables (-54 stations, -4 classrooms)",null,null,0,null,null,null,0,0]
[null,"New construction- classrooms (+26 stations, +2 classrooms on FISH)",null,null,200000,{"$nulls":4},200000]
[null,"Transfer relocatables to Sr. High (-26 stations, -2 classrooms)",{"$nulls":5},0,null,0]
[null,"Destroy old relocatables (-51 stations, -3 classrooms)",{"$nulls":4},0,null,null,0]
[{"$nulls":9},0]
[null,"Wauchula Elementary",{"$nulls":7},0]
[null,"Discontinue use of building 7 for educational purposes (-25 stations, -1 classroom)",{"$nulls":5},0,null,0]
[null,"PE covered play and storage",null,null,118017,{"$nulls":4},118017]
[null,"New construction- classrooms (+88 stations, +4 classrooms on FISH)",null,null,400000,{"$nulls":4},400000]
[null,"North Wauchula Elementary",{"$nulls":7},0]
[null,"PE covered play and storage",null,null,91447,{"$nulls":4},91447]
[null,"District Office",{"$nulls":7},0]
[null,"New administrative offices",null,null,401930,{"$nulls":4},401930]
[{"$nulls":9},0]
["2b2","HARDEE Total",null,null,22143540,16311079,3950000,1000000,460043.22,43864662.22]
[{"$nulls":9},43864662.22]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2b2a","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,null,"2004-05 FISH Satisfactory","Actual 2004-05","Actual 2003-04","Actual 2004-05","New Stu Capacity to","Projected 2008-09","Projected 2008-09"]
[null,"Location",null,"Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Hardee Senior High",null,1786,1696,1185,0.7,112.1,1184,0.65]
[null,"Hardee Junior High/ new PCA location",null,1750,1575,1238,0.79,-1406.7,25,0.15]
[null,"New K-8 School",null,0,0,0,null,1696,1400,0.83]
[null,"Bowling Green Elementary",null,945,945,702,0.74,-405,410,0.76]
[null,"Zolfo Springs Elementary",null,917,917,609,0.66,-60,682,0.8]
[null,"Pioneer Career Academy",null,131,131,20,0.15,-131,0,0]
[null,"Wauchula Elementary",null,938,938,651,0.69,63,750,0.75]
[null,"North Wauchula Elementary",null,818,818,654,0.8,0,650,0.79]
[]
["2b2a","HARDEE Total",null,7285,7020,5059,0.72,-131.60000000000014,5101,0.74]
[{"$nulls":8},5101]
["2b2a1","Necessary offsite infrastructure requirements resulting from expansions or new schools.  "]
[null,"This section should include the same project information from 2b2."]
[null,"New K-8 School - water & sewer line extension, de-acceleration lane, sidewalks, upgrades to access roads."]
[]
["2b2b","Proposed location of planned facilities, whether those locations are consistent with the comprehensive plans of all affected local governments, and "]
[null,"recommendations for infrastructure and other improvements to land adjacent to existing facilities. Provisions of 1013.33(12), (13), and (14) and 1013.36"]
[null," must be addressed for new facilities planned within the 1st 3 years  of the plan"]
[null,"Consistent with Comp Plan?",null,"Description"]
[null,"Yes",null,"New K-8 School (1,884 Stu Sta) in the vicinity of Wauchula Hills in Wauchula to replace old schools.."]
[{"$nulls":7},"# of Units","Projected "]
["2b2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",{"$nulls":4},"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":6},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location",null,"Actual # of Units in 2004-05","Owner","Student Stations","as classroom space","in 2008-09","units by 2008-09","Column \"C\""]
[null,"Hardee Senior High",null,8,"HCSB",225,null,10,-2,92]
[null,"Hardee Junior High",null,2,"FED",50,null,0,2,40]
[null,"Hardee Junior High",null,7,"HCSB",189,null,0,7,91]
[null,"Bowling Green Elementary",null,1,"lease",25,null,0,1,9]
[null,"Bowling Green Elementary",null,11,"HCSB",230,null,8,3,32]
[null,"Zolfo Springs Elementary",null,4,"Fed",82,null,2,2,119]
[null,"Zolfo Springs Elementary",null,2,"HCSB",40,null,1,1,64]
[null,"Pioneer Career Academy",null,8,"HCSB",120,null,null,8,182]
[null,"Pioneer Career Academy",null,1,"FED",11,null,0,1,30]
[null,"Wauchula Elementary",null,5,"HCSB",106,null,5,0,10]
[]
["2b2c1.","HARDEE Total",null,49,null,1078,0,26,23,"Avg Age 13.65"]
[null,"***note:  21 of the relocatable classrooms (492 student stations) are concrete modular buildings purchased in 2004 after Hurricane Charley."]
[]
["2b2c1a.","Continuation of 2b2c1 - The year in which all long term (4 years or more) relocatables,listed in 2b2c1, which will be used as classrooms will meet standards"]
[null,"Location",null,"Year"]
[null,"Hardee Senior High",null,2008]
[null,"Hardee Junior High",null,2008]
[null,"Bowling Green Elementary",null,2008]
[null,"Pioneer Career Academy",null,2008]
[null,"Wauchula Elementary",null,2008]
[]
["2b2c1a.","HARDEE Maximum Year",null,2008]
[]
["2b2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location",null,"Total # Units to be replaced","2004-05 ","2005-06 ","2006-07","2007-08","2008-09","5 YEAR TOTAL"]
[null,"Hardee Senior High",null,-2,null,null,-2,null,null,-2]
[null,"Hardee Junior High",null,9,null,null,9,0,0,9]
[null,"Bowling Green Elementary",null,4,3,null,null,1,null,4]
[null,"Zolfo Springs Elementary",null,3,3,{"$nulls":4},3]
[null,"Pioneer Career Academy",null,9,4,0,null,5,null,9]
["2b2c2.","HARDEE Total",null,23,10,0,7,6,0,23]
[]
["2b2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location",null,"# of leased classrooms 2004-05","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2008-09","FISH Stu. Sta.","# Years Leased "]
[null,"Bowling Green Elementary",null,1,"lease",25,9,0,0,0]
[]
["2b2c3.","HARDEE Total",null,1,null,25,9,0,0,0]
[]
["2b2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":7},"Total charter students "]
[null,"Location-Type",null,"# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2007-08"]
[null,"None.",{"$nulls":7},0]
[]
["2b2c4.","HARDEE Total",null,0,null,null,0,0,0,0]
[]
["2b2d.","Plans approved by the school board that reduce the need for permanent student stations such as acceptable school capacity levels, redistricting, "]
[null,"busing, year-round schools, charter schools, magnet schools, public-private partnerships, multitrack scheduling, grade level organization,"]
[null," block scheduling, or other alternatives."]
[]
[]
[]
[]
["2b2e.","Average Class Size (5 years out -- 2008-09) that will result if the district facilities work plan is fully implemented."]
[{"$nulls":6},"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location",null,"# CLASSROOMS","Capacity (NOT Stu Sta)","2003-04 CO-FTE","2003-04 Class size","2008-09 CO-FTE","be added (removed)","2008-09 Class size"]
[null,"Hardee Senior High",null,67,1696,1185,17.69,1184,5,16.44]
[null,"Hardee Junior High/ new Pioneer Career",null,70,1575,1238,17.69,25,-64,4.17]
[null,"New K-8 School",null,null,0,0,0,1400,73,19.18]
[null,"Bowling Green Elementary",null,43,945,702,16.33,410,-19,17.08]
[null,"Zolfo Springs Elementary",null,43,917,609,14.16,682,-3,17.05]
[null,"Pioneer Career Academy",null,9,131,20,2.22,0,-9,0]
[null,"Wauchula Elementary",null,43,938,651,15.14,750,3,16.3]
[null,"North Wauchula Elementary",null,36,818,654,18.17,650,0,18.06]
[]
["2b2e.","HARDEE Total",null,311,7020,5059,"District Avg 16",5101,-14,"District Avg 17"]
[]
["2b2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[null,"Please see attached explanation of work plan for additional details"]
[null,"Site                              ",null,null,"2004-05 ","2005-06 ","2006-07","2007-08","2008-09","5 YEAR AVERAGE"]
[null,"Hardee Senior High",null,null,225,225,225,251,251,235.4]
[null,"Hardee Junior High",null,null,239,239,0,0,null,119.5]
[null,"Bowling Green Elementary",null,null,201,201,201,201,201,201]
[null,"Zolfo Springs Elementary",null,null,62,62,62,62,62,62]
[null,"Pioneer Career Academy",null,null,21,21,21,0,0,12.6]
[null,"Wauchula Elementary",null,null,106,106,106,106,106,106]
[]
["2b2f1","HARDEE Total students in relocatables by year",null,null,854,854,615,620,620,712.6]
["2b2f2","HARDEE Total number of CO-FTE students projected by year",null,null,5059,5040,5060,5080,5101,5068]
["2b2f3","HARDEE Percent in relocatables by year",null,null,0.17,0.17,0.12,0.12,0.12,0.14]
[null,"***note:  21 of the relocatable classrooms (492 student stations) are concrete modular buildings purchased in 2004 after Hurricane Charley."]
[]
["2b2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"The District plans to discontinue using certain buildings at Hardee Junior High School for educational purposes in FY 2006-07."]
[null,"The District plans to re-locate Pioneer Career Academy to the former Hardee Junior High School in FY 2008-09."]
[null,"The District plans to discontinue using certain buildings at Bowling Green Elementary School for educational purposes in FY 2008-09."]
[]
["2b2h.","Projects for which capital outlay and debt service funds accruing under s. 9(d), Art. XII of the State Constitution are to be used shall be identified "]
[null,"separately in priority order on a project priority list within the district faciliteis work program."]
[null,"Projects to be implementd with CO & DS funds in ranked order:"]
[null,"Project Description:"]
[null,"1.  New K-8 School"]
[]
[{"$nulls":11},"State Average","State Average","State Average","State Average","State Average","State Average"]
["2b3","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":8},"Year",2001,2001,2001,2001,2001,2001]
[{"$nulls":10},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":10},1,96,127,247,11269,15778,23876]
[null,"2001 State-wide totals - Gross Sq Ft per student station: Elem low 96, avg 127, high 247; Middle low 107, avg 178, high 329; High School low 120, avg 143, high 182 ",{"$nulls":8},2,107,178,329,15083,25712,50508]
[null,"2001 State-wide totals - Cost per student station: Elem low 11,269, avg 15,778, high 23,876; Middle low 15,083 avg 25,712, high 50,508; High School low 14,229, avg 21,749, high  31,693 ",{"$nulls":8},3,120,143,182,14229,21749,31693]
[]
["2b3a.","2004-2005 Year",null,"Type of School (new schools only)  Others=0","2004-05 ","2004-05 ","2004-05 ","2004-05 ","2004-05 Projected",null," State Avg"," State Avg"," State Avg","2002 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description",null,"Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None.",{"$nulls":5},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3a.","HARDEE Total 2004-05",null,null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3b.","2005-2006 Year",null,"Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2005-06 Projected",null," State Avg"," State Avg"," State Avg","2004 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description",null,"Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New K-8 school",null,2,39500000,1884,281490,149.41,20966.03,null,107,178,329,20966.03,15083,25712,50508]
[]
["2b3b","HARDEE Total 2005-06",null,null,39500000,1884,281490,149.41,20966.03,{"$nulls":4},20966.03]
[]
["2b3c.","2006-2007 Year",null,"Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2006-07 Projected",null," State Avg"," State Avg"," State Avg","2005 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description",null,"Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None"]
["2b3c","HARDEE Total 2006-07",null,null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3d.","2007-2008 Year",null,"Type of School (new schools only)  Others=0","2007-08","2007-08","2007-08","2007-08","2007-08 Projected",null," State Avg"," State Avg"," State Avg","2006 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description",null,"Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":5},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3d.","HARDEE Total 2007-08",null,null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3e","2008-2009 Year",null,"Type of School (new schools only)  Others=0","2008-09","2008-09","2008-09","2008-09","2008-09 Projected",null," State Avg"," State Avg"," State Avg","2007 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description",null,"Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"None",{"$nulls":5},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[]
["2b3e","HARDEE Total 2008-09",null,null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3f","HARDEE 5-Year Total",null,null,39500000,1884,281490]
[]
["2b4","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09"]
[{"$nulls":4},"Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millage projected for discretionary capital outlay per s.236.25",null,null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,null,2651622,3030500,3258500,3496000,3741100,16177722]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,null,2651622,3030500,3258500,3496000,3741100,16177722,"2 mill Expenditures"]
[{"$nulls":9},0,0]
[null,"2 mill capital outlay taxes committed to new K-8 school",null,null,1988716.5,2272875,2443875,null,null,6705466.5,0.414487682505609]
[null,"2 mill capital outlay taxes not committed to new K-8 school",null,null,662905.5,757625,814625,3496000,3741100,9472255.5,0.585512317494391]
[null,"Special Facility Construction Account",null,null,17250000,13735753.5,1500000,0,null,32485753.5,2.00805487323864]
[null,"P E C O New Construction",null,null,0,102174,103163,105494,106000,416831,0.025765741307707]
[null,"Interest income",null,null,15697,45000,45000,45000,45000,195697,0.0120966969267985]
[null,"C O & D S flow-through",null,null,35443,34000,34000,34000,34000,171443,0.0105974747248098]
[null,"Class Size Reduction transfer to capital",null,null,90845,{"$nulls":4},90845]
[null,"Classrooms for Kids allocation",null,null,1702695,0,0,0,0,1702695,0.105249366999878]
[null,"Estimated insurance recoveries from hurricane damage",null,null,4995000,0,0,0,0,4995000]
[null,null,null,"total revenues and recoveries",26741302,16947427.5,4940663,3680494,3926100,51240986.5]
[]
[null,"Unexpended PECO new construction",null,null,452400,{"$nulls":4},452400,0.0279643821299439]
[null,"Unexpended CO&DS funds",null,null,208680,{"$nulls":4},208680,0.0128992202981359,"ALL Capital Outlay Expenditures"]
[null,"Unexpended race track revenue bond funds",null,null,4952,{"$nulls":4},4952,0.000306099956471004,0]
[null,"Unexpended capital outlay tax funds from prior fiscal years",null,null,2807641,{"$nulls":4},2807641,3473673,0.07]
[null,null,null,"fund balances",3473673,{"$nulls":4},3473673,null,0.08]
[]
[null,"  less amount used to purchase school buses",null,null,0,0,75000,150000,150000,375000,null,0.01]
[null,"  less amount used to purchase other vehicles",null,null,48850,null,35000,35000,35000,153850,null,0]
[null,"  less amount used to purchase walk-in coolers",null,null,66070,{"$nulls":4},66070,null,0]
[null,"  less amount transferred to operating budget for maintenance/repair",null,null,456552,450000,450000,500000,525000,2381552,null,0.06]
[null,"  less amount used to purchase capital outlay equipment",null,null,87540,50000,50000,100000,100000,387540,null,0.01]
[null,"  less amount used to purchase technology infrastructure",null,null,436155,50000,50000,100000,100000,736155,null,0.02]
[null,"  less amount used on major repair and renovation projects- see (2)(a)1.",null,null,6749595,240000,290000,432500,390000,8102095,12202262,0.19]
[null,null,null,"other expenditures",7844762,790000,950000,1317500,1300000,12202262]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,null,22370213,16157427.5,3990663,2362994,2626100,42512397.5]
[]
["2b4","HARDEE Total",null,null,22370213,16157427.5,3990663,2362994,2626100,42512397.5,null,0.44000000000000006]
[]
["2b5","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09"]
[null,"Project Description",null,"Student Stations","Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New K-8 School",{"$nulls":7},0]
[null,"New construction- new school and land (+1,884 stations, +73 classrooms)",null,null,19238921,16311079,3950000,null,null,39500000]
[{"$nulls":9},0]
[null,"Senior High",{"$nulls":7},0]
[null,"Transfer relocatables from Jr. HIgh (+112 stations, +4 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Transfer relocatables from PCA (+26 stations, +2 classrooms)",{"$nulls":5},0,null,0]
[null,"Destroy old relocatables (-110 stations, -4 classrooms)",{"$nulls":4},0,null,null,0]
[null,"New construction- classrooms (+90 stations, +3 buildings on FISH)",null,null,300000,{"$nulls":4},300000]
[{"$nulls":9},0]
[null,"Junior High",{"$nulls":7},0]
[null,"Transfer relocatables to Sr. HIgh (-112 stations, -4 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Destroy old relocatables  (-127 stations, -5 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Discontinue use of buildings 1-11 for educational purposes (-750 stations, -29 classrooms)",{"$nulls":4},0,null,null,0]
[null,"Remodel building 15 to District administration",{"$nulls":5},1000000,null,1000000]
[null,"Discontinue use of buildings 1-13 for educational purposes (-686 stations, -30 classrooms)",{"$nulls":4},0,null,null,0]
[null,"New construction- classrooms (+112 stations, +4 buildings on FISH)",null,null,400000,{"$nulls":4},400000]
[{"$nulls":9},0]
[null,"Bowling Green Elementary",{"$nulls":7},0]
[null,"Destroy old relocatables (-54 stations, -3 classrooms)",null,null,0,{"$nulls":4},0]
[null,"End lease of relocatable (-25 stations, -1 classroom)",{"$nulls":5},0,null,0]
[null,"Discontinue use of buildings 1-8, 11, 12 (-402 stations, -18 classrooms)",{"$nulls":6},0,0]
[null,"Convert building 13 to Administration (-75 stations, -3 classrooms)",{"$nulls":6},271632.2,271632.2]
[null,"Convert building 14, rooms 1 and 3 to ESE (-25 stations - 2 classrooms)",{"$nulls":6},141497.65,141497.65]
[null,"Convert building 14, room 2 to ESE resource",{"$nulls":6},46913.37,46913.37]
[null,"New construction- classrooms (+176 stations, +8 classrooms on FISH)",null,null,780931,{"$nulls":4},780931]
[null,"PE covered play and storage",null,null,120847,{"$nulls":4},120847]
[{"$nulls":9},0]
[null,"Zolfo Springs Elementary",{"$nulls":7},0]
[null,"PE covered play and storage",null,null,91447,{"$nulls":4},91447]
[null,"Destroy old relocatables (-60 stations, -3 classrooms)",null,null,0,{"$nulls":4},0]
[{"$nulls":9},0]
[null,"Pioneer Career Academy",{"$nulls":7},0]
[null,"Destroy old relocatables (-54 stations, -4 classrooms)",null,null,0,null,null,null,0,0]
[null,"New construction- classrooms (+26 stations, +2 classrooms on FISH)",null,null,200000,{"$nulls":4},200000]
[null,"Transfer relocatables to Sr. High (-26 stations, -2 classrooms)",{"$nulls":5},0,null,0]
[null,"Destroy old relocatables (-51 stations, -3 classrooms)",{"$nulls":4},0,null,null,0]
[{"$nulls":9},0]
[null,"Wauchula Elementary",{"$nulls":7},0]
[null,"Discontinue use of building 7 for educational purposes (-25 stations, -1 classroom)",{"$nulls":5},0,null,0]
[null,"PE covered play and storage",null,null,118017,{"$nulls":4},118017]
[null,"New construction- classrooms (+88 stations, +4 classrooms on FISH)",null,null,400000,{"$nulls":4},400000]
[null,"North Wauchula Elementary",{"$nulls":7},0]
[null,"PE covered play and storage",null,null,91447,{"$nulls":4},91447]
[null,"District Office",{"$nulls":7},0]
[null,"New administrative offices",null,null,401930,{"$nulls":4},401930]
[{"$nulls":9},0]
["2b5.","HARDEE Total",null,0,22143540,16311079,3950000,1000000,460043.22,43864662.22]
[]
[null,null,null,"beginning unexpended balance",3473673,226673,73021.5,113684.5,1476678.5,3473673]
[null,null,null,"revenues",26741302,16947427.5,4940663,3680494,3926100,56235986.5]
[null,null,null,"expenditures",-29988302,-17101079,-4900000,-2317500,-1760043.22,-56066924.22,56066924.22]
[null,null,null,"ending unexpended balance",226673,73021.5,113684.5,1476678.5,3642735.2800000003,3642735.280000001]
[]
["2b6","Schedule of options for generation of additional revenues by the district for expenditure on projects identified in the district facilities work "]
[null,"program which are not funded under paragraph 5 above.  Additional anticipated revenues may include SIT Program awards and Classrooms First funds."]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09"]
[{"$nulls":4},"Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,null,0,0,0,0,0,0]
[null,"Other (specify)",null,null,0,0,0,0,0,0]
["2b6.","HARDEE Total",null,null,0,0,0,0,0,0]
[]
["2b7","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09"]
[null,"Project Description",null,"Student Stations","Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"None.",{"$nulls":7},0]
[]
["2b7","HARDEE Total",null,0,0,0,0,0,0,0]
[]
["NOTE: If the sum of the totals in paragraphs 2b5. and 2b7. above DO NOT equal the total in paragraph 2b2. above, the message \"Check Totals\" appears.   "]
[null,"-- They should balance ! !"]
[{"$nulls":4},"2004-05 ","2005-06 ","2006-07","2007-08","2008-09","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,null,"","","","","",""]
[]
[]
["HARDEE  SCHOOL DISTRICT - - FACILITIES TEN (10) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the next 5 years beyond the above 5-year work plan. (years 6-10)"]
[]
[{"$nulls":4},"2009-10 - 2013-14"]
[null,"Project",null,"Location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"Paving",null,"All sites",300000,{"$nulls":4},300000]
[null,"Roofing",null,"All sites",5000000,{"$nulls":4},5000000]
[null,"HVAC/ plumbing,/ electrical",null,"All sites",5000000,{"$nulls":4},5000000]
[null,"Flooring",null,"All sites",300000,{"$nulls":4},300000]
[]
["2b1","HARDEE Total",null,null,10600000,{"$nulls":4},10600000]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the future 5 years beyond the above 5-year work plan."]
[]
[null,null,null,"Location - Community, quadrant,","2009-10 - 2013-14"]
[null,"Project Description",null," or other general location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"New Elementary School A",null,"Wauchula Hills/ Ft. Green",16000000,{"$nulls":4},16000000]
[null,"Classroom (12) addition",null,"Hardee Senior High",2500000,{"$nulls":4},2500000]
[null,"Classroom (16) addition",null,"Bowling Green Elementary",3000000,{"$nulls":4},3000000]
[]
["2b2","HARDEE Total",null,null,21500000,{"$nulls":4},21500000]
[]
["2b2a.","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,null,"FISH Satisfactory","Actual 2004-05","Actual 2003-04","Actual 2004-05","04-05 - 13-14         New Stu Capacity to","Projected 2013-14","Projected 2013-14"]
[null,"Grade Level Projections",null,"Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[null,"Hardee Senior High",null,1786,1696.6999999999998,1185,0.7,397.1,1300,0.62]
[null,"Hardee Junior High/ new Pioneer Career",null,1750,1575,1238,0.79,-1406.7,25,0.15]
[null,"New K-8 School",null,0,0,0,0,1696,1300,0.77]
[null,"Bowling Green Elementary",null,945,945,702,0.74,-53,600,0.67]
[null,"Zolfo Springs Elementary",null,917,917,609,0.66,-60,625,0.73]
[null,"Pioneer Career Academy",null,131,131,20,0.15,-131,0,0]
[null,"Wauchula Elementary",null,938,938,651,0.69,63,625,0.62]
[null,"North Wauchula Elementary",null,818,818,654,0.8,0,625,0.76]
[null,"New Elementary School",null,0,null,0,null,600,450,0.75]
[]
["2b2a.","HARDEE Total",null,7285,7020.7,5059,0.72,1105.4,5550,0.68]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the next 5 year period beyond the 5-year work plan above."]
[null,"New Elementary School (600 Stu Sta) in the vicinity of Wauchula Hills/ Fort Green. to accommodate growth."]
[null,"Classroom addition at Hardee Senior High (300 Stu Sta)  to accommodate growth."]
[null,"Classroom addition at Bowling Green Elementary School (352 Stu Sta)  to accommodate growth."]
[]
["2b2g.","Plans for closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the next 5 year period beyond the 5-year plan above."]
[null,"None."]
[]
["HARDEE  SCHOOL DISTRICT - - FACILITIES TWENTY (20) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the 11 thru 20 out years."]
[]
[{"$nulls":4},"2014-15-2023-24 ","Annual"]
[null,"Project",null,"Location","Projected Cost","Average Cost",null,null,null,"10 YEAR TOTAL"]
[null,"Paving",null,"All sites",500000,50000,null,null,null,500000]
[null,"Roofing",null,"All sites",10000000,1000000,null,null,null,10000000]
[null,"HVAC/ plumbing,/ electrical",null,"All sites",10000000,1000000,null,null,null,10000000]
[null,"Flooring",null,"All sites",700000,70000,null,null,null,700000]
[]
["2b1","HARDEE Total",null,null,21200000,{"$nulls":4},21200000]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the 11 thru 20 out years."]
[]
[null,null,null,"Location - Community, quadrant,","2014/15 -2023/24 "]
[null,"Project Description",null," or other general location","Projected Cost",{"$nulls":4},"10 YEAR TOTAL"]
[null,"New Sr. High School A",null,"Fort Green/ Bowling Green",50000000,{"$nulls":4},50000000]
[null,"New Jr. High School A",null,"Fort Green/ Bowling Green",40000000,{"$nulls":4},40000000]
[null,"New Elementary School B",null,"Fort Green/ Bowling Green",17000000,{"$nulls":4},17000000]
[null,"New Elementary School C",null,"Wauchula",17000000,{"$nulls":4},17000000]
["2b2","HARDEE Total",null,null,124000000,{"$nulls":4},124000000]
[]
["2b2a","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,null,"FISH Satisfactory","Actual 2004-05","Actual 2003-04","Actual 2004-05","04/05 - 23/24         New Stu Capacity to","District Projected 2023/24","Projected 2023-24"]
[null,"Grade Level Projections",null,"Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[null,"Elementary - District Totals",null,3618,3618,2616,0.72,1724,3825,0.72]
[null,"Middle - District Totals",null,1750,1575,1238,0.79,-574,700,0.7]
[null,"High - District Totals",null,1786,1696.6999999999998,1185,0.7,1347.1,2200,0.72]
[null,"Other- K-8 School ",{"$nulls":5},1696,1325,0.78]
[null,"Other - Alternative School",null,131,131,20,0.15,-38,50,0.54]
["2b2a","HARDEE Total",null,7285,7020.7,5059,0.72,4155.1,8100,0.72]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the 11 thru 20 out years. "]
[null,"New Sr. High School A (1,000 Stu Sta) in the vicinity of Fort Green/ Bowling Green to accommodate growth."]
[null,"New Jr. High School A (900 Stu Sta) in the vicinity of Fort Green/ Bowling Green to accommodate growth."]
[null,"New Elementary School B (600 Stu Sta) in the vicinity of Fort Green/ Bowling Green to accommodate growth."]
[null,"New Elementary School C (600 Stu Sta) in the vicinity of Wauchula to accommodate growth."]
[]
["2b2g","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the 11 thru 20 out years."]
[null,"None."]
[]
[]
[null,"To the extent available, the tentative district facilities work program shall be based on information produced by the demographic, revenue, and"]
[null,"education estimating conferences pursuant to 216.136."]
[null,"Provision shall be made for public comment concerning the tentative district educational facilities plan."]
[null,"The district school board shall coordinate with each affected local government to ensure consistency between the tentative district educational facilities plan and"]
[null,"the local government comprehensive plans of the affected local governments during the deveolpment of the tentative district educational facilities plan."]
[null,"The adopted district facilities work program shall:"]
[null,"Be a complete, balanced capital outlay financial plan for the district."]
[null,"Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities, including safe access ways from neighborhoods to schools."]
[null,"The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 1013.61."]
[null,"The adopted district educational facilities plan shall include the information required in subparagraphs (2) (b) 1., 2., and 3., based upon projects actually"]
[null,"funded in the plan with the exception of the 10 and 20 year portions."]
{"$rows_empty":9}
["Respectfully submitted this 17th day of November 2004."]
[]
[null,"SCHOOL BOARD OF ",null,"HARDEE  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":5},"Dennis G. Jones",null,null,"2004-11-17"]
[null,null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":5},"Greg Harrelson",null,null,"2004-11-17"," "]
[null,null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,null,"Greg Harrelson","Finance Director","863 773-9058 ext 217",null,"gharrelson@hardee.k12.fl.us",null," "]
[{"$nulls":4},"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}