{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":279,"n_cols":25,"rows_kept":279,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["HENDRY  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["HENDRY   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"HENDRY","Date: ==>","2000-09-26",null,"For fiscal years","  2000-2001 through 2004-2005"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Roofing","All",10000,30000,10000,10000,10000,70000]
[null,"HVAC Replacement","All",150000,50000,50000,50000,50000,350000]
[null,"Fire Alarm/Safety","All",10000,20000,10000,20000,10000,70000]
[null,"ADA","All",20000,20000,20000,20000,20000,100000]
[null,"Carpet/Tile","All",20000,50000,50000,50000,50000,220000]
[null,"Painting","All",20000,50000,50000,50000,50000,220000]
[null,"Paving","All",0,0,50000,50000,0,100000]
[null,"Electrical","All",10000,10000,20000,30000,10000,80000]
[null,"Retro/Wiring","All",70000,20000,20000,20000,20000,150000]
[null,"Window Replacement","Edward A. Upthegrove Elementary",15000,0,0,0,0,15000]
[null,"Restroom Renovations","Edward A. Upthegrove Elementary",25000,0,0,0,0,25000]
[null,"Restroom Renovations","Clewiston 6th Grade Center",36000,0,0,0,0,36000]
[null,"Carpentry","All",10000,10000,10000,10000,10000,50000]
["1.","HENDRY Total",null,396000,260000,290000,310000,230000,1486000]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[]
[null,"New LMS Phase III",null,0,6000000,0,0,0,6000000]
[null,"New LMS Phase II Bldg #4",null,1353410,0,0,0,0,1353410]
[null,"New Elementary Clewiston \"B\"",null,0,9000000,0,0,0,9000000]
[null,"Edward A. Upthegrove Elementary Demo Bldg #2 & 10 & part of #6 & 9",null,100000,0,0,0,0,100000]
[null,"New Construction - Edward A. Upthegrove Elementary",null,1291254,0,0,0,0,1291254]
[null,"Renovate Edward A. Upthegrove Elementary",null,0,0,0,0,800000,800000]
[null,"CHS Reroofing Project",null,1400000,0,0,0,0,1400000]
[null,"Lease Portables",null,150000,150000,150000,50000,50000,550000]
["2 .","HENDRY Total",null,4294664,15150000,150000,50000,850000,20494664]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Edward A. Upthegrove Elemementary",227,337,251,0.74,149,350,0.72]
[null,"Clewiston Middle",1171,1053,978,0.93,0,1000,0.95]
[null,"LaBelle Elementary",863,863,760,0.88,-200,660,1]
[null,"Westside Elementary",730,730,667,0.91,0,715,0.98]
[null,"Eastside Elementary",932,932,670,0.72,0,715,0.77]
[null,"Central Elementary",527,527,658,1.25,0,715,1.36]
[null,"LaBelle High School",1172,996,781,0.78,0,910,0.91]
[null,"Clewiston High School",1108,941,949,1.01,0,1029,1.09]
[null,"LaBelle Middle School",510,434,507,1.17,251,800,1.17]
[null,"Country Oaks Elementary",1160,1160,902,0.78,-200,779,0.81]
["2a.","HENDRY Total",8400,7973,7123,0.89,0,7673,0.96]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School \"B\" (767 Student Stations) in West of Clewiston city limits in Clewiston, FL to accommodate growth."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"Westside Elementary ",3,"HCSB",25,0,3,0,57]
[null,"Central Elementary",4,"HCSB",55,0,4,0,96]
[null,"Edward A. Upthegrove Elementary",5,"HCSB",97,5,0,5,120]
[null,"Edward A. Upthegrove Elementary",1,"FED",0,0,1,0,34]
[null,"County Oaks Elementary",3,"FED",67,0,3,0,18]
[null,"LaBelle Elementary",12,"HCSB",271,0,12,0,288]
[null,"LaBelle Elementary",4,"FED",160,0,4,0,96]
[null,"Montura",1,"FED",0,0,1,0,34]
[null,"LYDA",4,"HCSB",80,0,2,0,76]
["2c1.","HENDRY Total",37,null,755,5,30,5,"Avg Age 22.14"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"Edward A. Upthegrove Elementary",0,5,0,0,0,0,5]
["2c2.","HENDRY Total",0,5,0,0,0,0,5]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Eastside Elementary",7,"LEASED",140,5,0,0,0]
[null,"Westside Elementary",2,"LEASED",40,5,0,0,0]
[null,"Central Elementary",1,"LEASED",20,5,0,0,0]
[null,"Country Oaks Elementary",7,"LEASED",140,4,0,0,0]
[null,"LaBelle Elementary",9,"LEASED",180,5,0,0,0]
[null,"CYDA",2,"LEASED",40,5,0,30,0]
[null,"LaBelle Middle School",5,"LEASED",75,4,5,75,8]
["2c3.","HENDRY Total",33,null,495,28,5,105,8]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2004-05"]
[null,"N/A"]
["2c4.","HENDRY Total",{"$error":"#REF!"},null,null,{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"Clewiston High",42,1207,949,24,1029,0,24.5]
[null,"Clewiston Middle",45,1127,978,26,1000,0,22.22]
[null,"Eastside Elementary",32,552,670,24,715,0,22.34]
[null,"Westside Elementary",31,538,667,24,715,0,23.06]
[null,"Central Elementary",31,451,658,24,700,0,22.58]
[null,"CYDA",3,60,0,12,0,-3,{"$error":"#DIV/0!"}]
[null,"Clewiston 6th Grade",15,311,0,0,0,0,0]
[null,"LaBelle High",37,1040,781,26,910,0,24.59]
[null,"Edward A. Upthegrove Elementary",30,337,507,22,350,-10,17.5]
[null,"LaBelle Middle School",9,461,251,23,750,30,19.23]
[null,"Country Oaks Elementary",65,1697,1585,24.38,1500,0,23.08]
[null,"LaBelle Elementary",34,474,760,27,610,0,17.94]
[null,"LYDA",3,60,0,15,0,0,0]
["2e.","HENDRY Total",377,8315,7806,"District Avg 21",8279,17,"District Avg 21"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR AVERAGE"]
[null,"Eastside Elementary",null,140,140,140,140,60,124,null,90]
[null,"Westside Elementary",null,100,100,100,100,60,92]
[null,"Country Oaks Elementary",null,220,220,220,220,80,192]
[null,"LaBelle Elementary",null,480,300,300,300,300,336]
[null,"Edward A. Upthegrove Elementary",null,0,0,0,0,0,0]
[null,"LaBelle Middle",null,140,140,140,140,0,112]
[null,"LYDA",null,100,100,100,100,140,108]
[null,"CYDA",null,0,0,0,0,0,0]
["2f.","HENDRY Total students in relocatables by year",null,1180,1000,1000,1000,640,964]
[null,"Total number of CO-FTE students projected by year",null,5665,5675,5685,5690,5695,5682]
[null,"Percent in relocatables by year",null,0.21,0.18,0.18,0.18,0.11,0.17]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01 ","2000-01 ","2000-01 ","2000-01 ","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New LMS Phase II Bldg. #4",2,1353410,99,12134,122.57,88,90,180,13670.81,7226,13517,18473]
[null,"EAU Elem Construct New Bldg.",0,1291254,200,10100,50.5,0,0,0,6456.27,0,0,0]
["3a.","HENDRY Total 2000-01",null,2644664,299,22234,74.36,null,null,null,8845.03]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Elem \"B\"",1,9000000,767,96000,125,null,107,174,11734.03,7485,11173,16419]
[null,"lms Phase III",2,6000000,900,125000,139,88,99]
["3b","HENDRY Total 2001-02",null,9000000,767,96000,125.16,null,null,null,11734.03]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"N/A",{"$nulls":5},0,0,0,null,0,0,0]
["3c","HENDRY Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","HENDRY Total 2003-04",null,0,0,0,0,null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
["3e","HENDRY Total 2004-05",null,0,0,0,0,0,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","HENDRY 5-Year Total",null,11644664,1066,118234]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,2710499.7,2710499.7,2710499.7,2710499.7,2710499.7,13552498.5]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,2710499.7,2710500,2710500,2710500,2710500,13552499.7,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,210000,210000,210000,210000,210000,1050000,0.0774764820692082]
[null,"  less amount used to purchase other vehicles",null,80000,0,0,0,0,80000,0.00590297006241587]
[null,"  less amount transferred to operating budget for maintenance/repair",null,201648,201648,201648,201648,201648,1008240,0.0743951316966272]
[null,"  less amount used for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase capital outlay equipment",null,30000,0,0,0,0,30000,0.00221361377340595]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,978277.5,978278,978278,978277,978277,4891387.5,0.36092142470219]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,1240574.2,1320574.2,1320574.2,1320574.2,1320574.2,6492872.199999999,0.479090377696153,0.88]
[null,"P E C O New Construction",null,217125,114735,209025,165840,141491,848216,null,0.12]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","HENDRY Total",null,1457699.2,1435309.2,1529599.2,1486414.2,1462065.2,7341088.199999999,1.0000000000000002,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Leased Portables",495,150000,150000,150000,50000,50000,550000]
[null,"New LMS Phase II Bldg #4",99,1353410,0,0,0,0,1353410]
[null,"EAU Demo Bldgs #2,10 Part of 6 & 9",-393,100000,0,0,0,0,100000]
[null,"EAU Construct new Bldg.",200,1291254,0,0,0,0,1291254]
["5.","HENDRY Total",401,2894664,150000,150000,50000,50000,3294664]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (Special Facilities) New Elem \"B\" Clewiston",770,0,9000000,0,0,0,9000000]
["6.","HENDRY Total",null,0,9000000,0,0,0,9000000]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"EAU Elem Renovate All Bldgs.",250,0,0,0,0,800000,800000]
[null,"CHS Reroofing Project",1091,1400000,0,0,0,0,1400000]
[null,"New LMS Phase III",99,0,6000000,0,0,0,6000000]
[null,"New Elem \"B\" Clewiston",770,0,9000000,0,0,0,9000000]
["7.","HENDRY Total",2210,1400000,15000000,0,0,800000,17200000]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2000."]
[]
[null,"SCHOOL BOARD OF ","HENDRY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Thomas W. Conner",null,null,"2000-09-26"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"B. Steven Stinnett",null,null,"2000-09-26"," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Jeanie Conklin","Exe Sec.","863-902-4244",null,"conklin_v@popmail.firn.edu",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}