{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","02_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"02_5YrWkPlan","index":1,"n_rows":300,"n_cols":25,"rows_kept":300,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["HENDRY  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["HENDRY   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to DOE, Office of Educational Facilities , and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format (email: janet.burns@fldoe.org), as you received it (not a fax), prior to October 1, 2002, and all data accurate as of July 15, 2002.",{"$nulls":8},"2002-09-25T09:51:57.730",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"HENDRY","Date: ==>","2002-10-01",null,"For fiscal years","  2002-2003 through 2006-2007"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"HVAC replacement","All",50000,50000,50000,50000,50000,250000]
[null,"fire alarm/safety","All",20000,20000,20000,20000,30000,110000]
[null,"ADA","All",10000,10000,10000,20000,10000,60000]
[null,"Carpet/Tile","All",20000,20000,20000,20000,20000,100000]
[null,"Painting","All",20000,20000,20000,20000,20000,100000]
[null,"Paving","All",10000,30000,10000,20000,20000,90000]
[null,"Electrical","All",10000,10000,10000,20000,20000,70000]
[null,"Carpentry","All",10000,16121,10000,40000,50000,126121]
[null,"Renovation","All",20000,40000,20000,20000,20000,120000]
[null,"Doors and Locks","All",6890,6890,6890,6890,6890,34450]
[null,"Restroom Renovations","All",20000,20000,24967,20000,20000,104967]
[null,"Roof Repair","All",20000,40000,10000,46958,57261,174219]
[null,"Fence and repair","All",10000,10000,10000,30000,30000,90000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
{"$rows_empty":7}
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Maintenance, Repair, and Renovation Totals",null,226890,293011,221857,333848,354151,1429757]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,226890,293011,221857,333848,354151,1429757]
["1.","HENDRY Total",null,226890,293011,221857,333848,354151,1429757]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"PHASE 111 LABELLE MIDDLE",{"$nulls":4},120163,6000000,6120163]
[null,"CHS RE-ROOF PROJECT",null,1600000,{"$nulls":4},1600000]
[null,"LEASE PORTABLES",null,195000,195000,195000,195000,195000,975000]
[null,"EASTSIDE/WESTSIDE RE-ROOF",null,null,1600000,702239,73119,null,2375358]
[null,"WAREHOUSE RE-ROOF",null,null,150000,null,null,null,150000]
[null,"CYDA RE-ROOF",null,null,null,151000,null,null,151000]
[null,"UPTHEGROVE GYM RE-ROOF",null,null,null,143000,null,null,143000]
[null,"LABELLE HIGH RE-ROOF",{"$nulls":5},1109000,1109000]
[null,"CENTRAL ELEM. RE-ROOF",{"$nulls":4},821000,null,821000]
["2 .","HENDRY Total",null,1795000,1945000,1191239,1209282,7304000,13444521]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2001-02 FISH Satisfactory","Actual 2001-02","Actual 2001-02","Actual 2001-02","New Stu Capacity to","Projected 2006-07","Projected 2006-07"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"UPTHEGROVE ELEM.",0,0,0,0,400,400,1]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2a.","HENDRY Total",0,0,0,{"$error":"#DIV/0!"},400,400,1]
[]
["2b.","Proposed Location of Planned Facilities"]
[]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2001-02","Owner","Student Stations","as classroom space","in 2006-07","units by 2006-07","Column \"C\""]
[null,"LABELLE ELEMENTARY",14,"HCSB",271,0,14,null,360]
[null,"COUNTRY OAKS ELEMENTARY",3,"HCSB",67,0,2,1,30]
[null,"CENTRAL ELEMENTARY",4,"HCSB",55,0,3,1,43]
[null,"LYDA",5,"HCSB",100,0,5,0,75]
[null,"LABELLE MIDDLE",3,"HCSB",75,0,3,0,43]
[null,"WESTSIDE ELEMENTARY",3,"HCSB",25,0,3,0,45]
["2c1.","HENDRY Total",32,null,593,0,30,2,"Avg Age 18.63"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"LABELLE ELEMENTARY",2,1,1,0,0,0,2]
[null,"CENTRAL ELEMENTARY",2,1,1,0,0,0,2]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","HENDRY Total",4,2,2,0,0,0,4]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2006-07","FISH Stu. Sta.","# Years Leased "]
[null,"LABELLE MIDDLE",10,"HATFIELD/WILLIAMS",240,10,10,240,16]
[null,"WESTSIDE ELEMENTARY",2,"HATFIELD",40,10,2,40,16]
[null,"COUNTRY OAKS ELEMENTARY",8,"HATFIELD",20,10,3,20,16]
[null,"LABELLE ELEMENTARY",5,"HATFIELD",200,10,5,200,16]
[null,"EASTSIDE ELEMENTARY",6,"HATFIELD",120,10,6,120,16]
[null,"CLEWISTON HIGH",1,"HATFIELD",null,5,1,0,8]
[null,"CENTRAL ELEMENTARY",3,"HATFIELD",60,10,3,60,16]
[null,"LYDA",2,"HATFIELD",40,10,2,40,16]
[]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c4.","HENDRY Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2006-07) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: You are no longer required to exclude exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2001-02 CO-FTE","2001-02 Class size","2006-07 CO-FTE","be added (removed)","2006-07 Class size"]
[null,"CLEWISTON HIGH",42,1207,999.42,24,1038,0,24]
[null,"CLEWISTON MIDDLE",47,1127,968.39,24,1127,0,24]
[null,"CENTRAL ELEMENTARY",31,451,588,24,688,0,24]
[null,"EASTSIDE ELEMENTARY",32,552,613,26,703,0,26]
[null,"WESTSIDE ELEMNTARY",31,538,608,26,678,0,26]
[null,"CYDA",6,100,94,18,94,0,18]
[null,"LYDA",5,80,58,16,76,0,16]
[null,"LABELLE HIGH",37,1040,851.7,26,972,0,26]
[null,"LABELLE MIDDLE",41,1183,853.59,24,925,0,24]
[null,"LABELLE ELEMENTARY",36,474,788,24,887,0,24]
[null,"UPTHEGROVE ELEMENTARY",26,420,0,24,420,23,24]
[null,"COUNTRY OAKS ELEMENTARY",65,1697,938,24,1045,0,24]
["2e.","HENDRY Total",399,8869,7360.1,"District Avg 18",8653,23,"District Avg 21"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR AVERAGE"]
[null,"LaBelle Middle",null,430,430,430,430,430,430]
[null,"LaBelle Elementary",null,105,105,105,105,105,105]
[null,"Upthegrove Elementary",null,72,72,72,72,72,72]
[null,"LYDA",null,66,66,66,66,66,66]
[null,"Central Elementary",null,105,105,105,105,105,105]
[null,"Eastside Elementary",null,169,169,169,169,169,169]
[null,"Westside Elementary",null,220,220,220,220,220,220]
["2f.","HENDRY Total students in relocatables by year",null,1167,1167,1167,1167,1167,1167]
[null,"Total number of CO-FTE students projected by year",null,1168,1168,1168,1168,1168,1168]
[null,"Percent in relocatables by year",null,1,1,1,1,1,1]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,82,107,146,8756,12965,23176]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,84,119,161,9899,13498,17138]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,93,112,185,12826,15024,22033]
[]
["3a.","2002-03 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"CHS Roof Replacement",3,1600000,1038,191452,184,93,112,185,1541.43,12826,15024,22033]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","HENDRY Total 2002-03",null,1600000,1038,191452,184.44,null,null,null,1541.43]
[]
["3b.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Eastside/Westside Re roof",1,1600000,1611,57025]
[null,"Warehouse R-roof project",0,150000,0,20025,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","HENDRY Total 2003-04",null,1750000,1611,77050,47.83,null,null,null,1086.28]
[]
["3c.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2004 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Upthegrove elem. Gym reroof",1,143000,420,12347,29.4,82,107,146,340.48,8756,12965,23176]
["3c","HENDRY Total 2004-05",null,143000,420,12347,29.4,null,null,null,340.48]
[]
["3d.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2005 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Central Elem. Re roof",1,821000,591,73981,125.18,82,107,146,1389.17,8756,12965,23176]
["3d.","HENDRY Total 2005-06",null,821000,591,73981,125.18,null,null,null,1389.17]
[]
["3e.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2000 State Avg","2000 State Avg","2000 State Avg","2006 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"LaBelle High Re roof",3,1108000,1172,143281,122.25,93,112,185,945.39,12826,15024,22033]
[null,"Phase 111 LaBelle Middle",2,6000000,825,null,0,84,119,161,7272.73,9899,13498,17138]
["3e","HENDRY Total 2006-07",null,7108000,1997,143281,71.75,null,null,null,3559.34]
[]
["3f.","HENDRY 5-Year Total",null,11422000,5657,498111]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",{"$nulls":6},0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,2841020,2841020,2841020,2841020,2841020,14205100,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,127191,220000,220000,220000,220000,1007191,0.0709034783282061]
[null,"  less amount used to purchase other vehicles",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",null,300000,300000,300000,300000,300000,1500000,0.105595877536941]
[null,"  less amount used for maintenance/repair",{"$nulls":6},0,0]
[null,"  less amount used to purchase capital outlay equipment",null,100537,234456,150000,150000,150000,784993,0.0552613497969039]
[null,"  less amount used to correct environmental problems",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for salaries",{"$nulls":6},0,0]
[null,"  less amount used to pay debt service for s.237 loans",{"$nulls":6},0,0]
[null,"  less amount to pay debt service for COP's ",null,978818,977893,979243,982754,238300,4157008,0.292641938458723]
[null,"  less other (please be specific)","Portables",null,195000,195000,195000,195000,780000,0.0549098563192093,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,1334474,913671,996777,993266,1737720,5975908,0.420687499560017,0.83]
[null,"P E C O New Construction",null,390915,175582,194462,216016,218108,1195083,null,0.17]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",{"$nulls":6},0,null,0]
[null,"C O & D S maximum potential bond proceeds",{"$nulls":6},0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,null,0]
[null,"Proceeds from a s.237 loan",{"$nulls":6},0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",{"$nulls":6},0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",{"$nulls":6},0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",{"$nulls":6},0,null,0]
[null,"Effort Index Grants",{"$nulls":6},0]
[null,"Impact fees received",{"$nulls":6},0,null,0]
[null,"Private donations",{"$nulls":6},0,null,0]
[null,"Grants from local governments or not-for-profit organizations",{"$nulls":6},0,null,0]
["4.","HENDRY Total",null,1725389,1089253,1191239,1209282,1955828,7170991,1.0000000000000002,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Lease Portables",null,195000,195000,195000,195000,195000,975000]
[null,"Clewiston High Re roof",null,1530389,69611,null,null,null,1600000]
[null,"Eastside/Westside re roof",null,null,824642,702239,73119,null,1600000]
[null,"CYDA re roof",null,null,null,151000,null,null,151000]
[null,"Central elem. Re roof",{"$nulls":4},821000,null,821000]
[null,"LaBelle Middle phase 111",{"$nulls":4},120163,652828,772991]
[null,"Upthegrove re-roof",null,null,null,143000,null,null,143000]
[null,"LaBelle High Re roof",{"$nulls":5},1108000,1108000]
["5.","HENDRY Total",0,1725389,1089253,1191239,1209282,1955828,7170991]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","HENDRY Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Phase 111 LaBelle Middle",{"$nulls":5},5348172,5348172]
[null,"Clewiston High re-roof",null,69611,{"$nulls":4},69611]
[null,"Warehouse re-roof",{"$nulls":6},0]
[null,"Eastside/Westside re-roof",null,null,855747,null,null,null,855747]
["7.","HENDRY Total",0,69611,855747,0,0,5348172,6273530]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2002."]
[]
[null,"SCHOOL BOARD OF ","HENDRY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"HOWARD BERRYMAN","DIRECTOR","(863) 674-4100",null,"BERRYMANH@HENDRY.K12.FL.US",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}