{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","2003-04_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"2003-04_5YrWkPlan","index":1,"n_rows":395,"n_cols":16,"rows_kept":395,"cut":false,"hidden":false,"merged":[[1,0,1,8]],"flags":["formulas_cached_only"]}
[]
["Hendry  SCHOOL DISTRICT - - TENTATIVE FACILITIES WORK PROGRAM"]
["Hendry   SCHOOL  DISTRICT - -  WORKSHEET ",{"$nulls":7},"Last Revised"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the Office of Educational Facilities, and a copy submitted ",{"$nulls":7},"2003-10-13"]
["electronically in digital format, as you received it (not a fax), prior to November 1, 2003, and all data accurate as of July 15, 2003."]
["District: ====>",null,"Hendry","Date: ==>","2003-11-01",null,"For fiscal years","  2003-2004 through 2007-2008"]
[]
["Section 1013.35 School district facilities 5 - Year work program; definitions; preparation, adoption, and amendment."]
[]
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["2b1","A schedule of major repair and renovation projects necessary to maintain the educational facilities and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"HVAC replacement","All",50000,50000,50000,50000,50000,250000]
[null,"fire alarm/safety","All",20000,20000,20000,20000,20000,100000]
[null,"ADA","All",10000,10000,10000,10000,10000,50000]
[null,"Carpet/Tile","All",20000,20000,20000,20000,20000,100000]
[null,"Painting","All",20000,20000,20000,20000,20000,100000]
[null,"Paving","All",10000,10000,10000,10000,10000,50000]
[null,"Electrical","All",10000,10000,10000,10000,10000,50000]
[null,"Carpentry","All",10000,10000,10000,10000,10000,50000]
[null,"Renovation","All",20000,20000,20000,20000,20000,100000]
[null,"Doors and Locks","All",7000,7000,7000,7000,7000,35000]
[null,"Restroom Renovations","All",20000,20000,20000,20000,20000,100000]
[null,"Roof repair","All",20000,20000,20000,20000,20000,100000]
[null,"Fence and repair","All",10000,10000,10000,10000,10000,50000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b1","Hendry Total",null,227000,227000,227000,227000,227000,1135000]
[]
["2b2","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Lease Portables",null,159000,159000,159000,159000,159000,795000]
[null,"Phase III LaBelle Middle",null,900000,500000,500000,500000,3600000,6000000]
[null,"Eastside/Westside Roof replace",null,300000,1300000,null,null,null,1600000]
[{"$nulls":8},0]
[null,"CYDA Re-roof",null,200000,{"$nulls":4},200000]
[null,"Upthegrove Gym Re-roof",null,null,40160,null,null,null,40160]
[null,"LaBelle High Re-roof",{"$nulls":4},1109000,null,1109000]
[null,"Central Elementary Re-roof",null,null,null,821000,null,null,821000]
[{"$nulls":8},0]
["2b2","Hendry Total",null,1559000,1999160,1480000,1768000,3759000,10565160]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2b2a","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2003-04 FISH Satisfactory","Actual 2003-04","Actual 2002-03","Actual 2003-04","New Stu Capacity to","Projected 2007-08","Projected 2007-08"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"LaBelle Middle School",1044,1127,856,0.9,0,null,0]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2b2a","Hendry Total",1044,1127,856,0.76,0,0,0]
[]
["2b2a1","Necessary offsite infrastructure requirements resulting from expansions or new schools.  "]
[null,"This section should include the same project information from 2b2."]
[]
[]
[]
[]
["2b2b","Proposed location of planned facilities, whether those locations are consistent with the comprehensive plans of all affected local governments, and "]
[null,"recommendations for infrastructure and other improvements to land adjacent to existing facilities. Provisions of 1013.33(12), (13), and (14) and 1013.36"]
[null," must be addressed for new facilities planned within the 1st 3 years  of the plan"]
[null,"Consistent with Comp Plan?","Description"]
[]
[]
[]
[{"$nulls":6},"# of Units","Projected "]
["2b2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2003-04","Owner","Student Stations","as classroom space","in 2007-08","units by 2007-08","Column \"C\""]
[null,"LaBelle Elementary",23,"15 owned",414,0,23,0,460]
[null,"Country Oaks Elementary",3,"2 owned",54,0,3,0,34]
[null,"Central Elementary",4,"1 owned",72,0,4,0,43]
[null,"LYDA",7,"5 owned",108,0,7,0,83]
[null,"LaBelle Middle ",12,"2 owned",220,0,12,0,166]
[null,"Westside Elementary",5,"3 owned",90,0,5,0,72]
["2b2c1.","Hendry Total",54,null,958,0,54,0,"Avg Age 15.89"]
[]
["2b2c1a.","Continuation of 2b2c1 - The year in which all long term (4 years or more) relocatables,listed in 2b2c1, which will be used as classrooms will meet standards"]
[null,"Location","Year"]
[null,"LaBelle Elementary",2008]
[null,"Country Oaks Elementary",2008]
[null,"Central Elementary",2008]
[null,"LYDA",2008]
[null,"LaBelle Middle ",2008]
[null,"Westside Elementary",2008]
["2b2c1a.","Hendry Maximum Year",2008]
[]
[]
[]
["2b2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b2c2.","Hendry Total",0,0,0,0,0,0,0]
[]
["2b2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2003-04","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2007-08","FISH Stu. Sta.","# Years Leased "]
[]
[]
["2b2c3.","Hendry Total",0,null,0,0,0,0,0]
[]
["2b2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2007-08"]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b2c4.","Hendry Total",0,null,null,0,0,0,0]
[]
["2b2d.","Plans approved by the school board that reduce the need for permanent student stations such as acceptable school capacity levels, redistricting, "]
[null,"busing, year-round schools, charter schools, magnet schools, public-private partnerships, multitrack scheduling, grade level organization,"]
[null," block scheduling, or other alternatives."]
[]
[]
[]
[]
["2b2e.","Average Class Size (5 years out -- 2007-08) that will result if the district facilities work plan is fully implemented."]
[{"$nulls":5},"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","# CLASSROOMS","Capacity (NOT Stu Sta)","2002-03 CO-FTE","2002-03 Class size","2007-08 CO-FTE","be added (removed)","2007-08 Class size"]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2b2e.","Hendry Total",0,0,0,{"$error":"#DIV/0!"},0,0,{"$error":"#DIV/0!"}]
[]
["2b2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[null,"Please see attached explanation of work plan for additional details"]
[null,"Site                              ",null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08","5 YEAR AVERAGE"]
[null,"LaBelle Area Schools",null,872,932,932,932,932,920]
[null,"Clewiston Area Schools",null,372,414,414,414,414,405.6]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2b2f1","Hendry Total students in relocatables by year",null,1244,1346,1346,1346,1346,1325.6]
["2b2f2","Hendry Total number of CO-FTE students projected by year",null,7498,7498,7498,7498,7498,7498]
["2b2f3","Hendry Percent in relocatables by year",null,0.17,0.18,0.18,0.18,0.18,0.18]
[]
["2b2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[]
[]
[]
["2b2h.","Projects for which capital outlay and debt service funds accruing under s. 9(d), Art. XII of the State Constitution are to be used shall be identified "]
[null,"separately in priority order on a project priority list within the district faciliteis work program."]
[null,"Projects to be implementd with CO & DS funds in ranked order:"]
[null,"Project Description:"]
[null,null,"$40,000 per year to fund LaBelle Middle Phase 111"]
[]
[]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["2b3","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2001,2001,2001,2001,2001,2001]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,96,127,247,11269,15778,23876]
[null,"2001 State-wide totals - Gross Sq Ft per student station: Elem low 96, avg 127, high 247; Middle low 107, avg 178, high 329; High School low 120, avg 143, high 182 ",{"$nulls":7},2,107,178,329,15083,25712,50508]
[null,"2001 State-wide totals - Cost per student station: Elem low 11,269, avg 15,778, high 23,876; Middle low 15,083 avg 25,712, high 50,508; High School low 14,229, avg 21,749, high  31,693 ",{"$nulls":7},3,120,143,182,14229,21749,31693]
[]
["2b3a.","2003-04 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2003-04 Projected",null," State Avg"," State Avg"," State Avg","2002 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3a.","Hendry Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3b.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05 ","2004-05 ","2004-05 ","2004-05 ","2004-05 Projected",null," State Avg"," State Avg"," State Avg","2003 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3b","Hendry Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3c.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2005-06 Projected",null," State Avg"," State Avg"," State Avg","2004 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3c","Hendry Total 2005-06",null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3d.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2006-07 Projected",null," State Avg"," State Avg"," State Avg","2005 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3d.","Hendry Total 2006-07",null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["2b3e","2007-2008 Year","Type of School (new schools only)  Others=0","2007-08","2007-08","2007-08","2007-08","2007-08 Projected",null," State Avg"," State Avg"," State Avg","2006 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"LaBelle Middle Phase III",2,6000000,120,13500,112.5,50000,null,107,178,329,50000,15083,25712,50508]
[{"$nulls":6},{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["2b3e","Hendry Total 2007-08",null,6000000,120,13500,112.5,50000,{"$nulls":4},50000]
[]
["2b3f","Hendry 5-Year Total",null,6000000,120,13500]
[]
["2b4","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",{"$nulls":6},0]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",{"$nulls":6},0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,2940815,2894180,2864613,2827796,2781367,14308771,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,307000,322350,338467,355390,373160,1696367,0.118554346840829]
[null,"  less amount used to purchase other vehicles",null,86000,null,40000,null,null,126000,0.00880578772278905]
[null,"  less amount transferred to op. bud for minor maint/repair projects",{"$nulls":6},0,0]
[null,"  less amount trnsfrd to op bud for salaries assoc w/maintenance/repair projects",{"$nulls":6},0,0]
[null,"  less amount used for minor maint/repair projects",{"$nulls":6},0,0]
[null,"  less amount used to purchase capital outlay equipment",null,114000,114000,114000,null,100000,442000,0.0308901442339108]
[null,"  less amount used to correct environmental problems",{"$nulls":6},0,0]
[null,"  less amount used to pay debt service for s.237 loans",{"$nulls":6},0,0]
[null,"  less amount to pay debt service for COP's ",null,999619,1004247,216260,null,null,2220126,0.155158398998768]
[null,"  less other (please be specific)",{"$nulls":6},0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,1434196,1453583,2155886,2472406,2308207,9824278,0.686591322203703,0.69]
[null,"P E C O New Construction",null,278557,194462,216016,218108,223035,1130178,null,0.08]
[null,"P E C O Maintenance Dollars",null,384283,221857,333848,354151,371685,1665824,null,0.12]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",{"$nulls":6},0,null,0]
[null,"C O & D S maximum potential bond proceeds",{"$nulls":6},0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,null,0]
[null,"Proceeds from a s.237 loan",{"$nulls":6},0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",{"$nulls":6},0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",{"$nulls":6},0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",{"$nulls":6},0,null,0]
[null,"Effort Index Grants",{"$nulls":6},0,null,0]
[null,"Classrooms for Kids",null,1620360,{"$nulls":4},1620360,null,0.11]
[null,"District Equity Recognition",{"$nulls":6},0,null,0]
[null,"Federal Grants",{"$nulls":6},0,null,0]
[null,"Impact fees received",{"$nulls":6},0,null,0]
[null,"Private donations",{"$nulls":6},0,null,0]
[null,"Grants from local governments or not-for-profit organizations",{"$nulls":6},0,null,0]
["2b4","Hendry Total",null,3717396,1869902,2705750,3044665,2902927,14240640,0.9999999999999998,0.9999999999999999]
[]
["2b5","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Leased Portables",null,159000,159000,159000,159000,159000,795000]
[null,"Eastside/Westside Re-roof",null,300000,1300000,null,null,null,1600000]
[null,"CYDA Re-roof",null,200000,{"$nulls":4},200000]
[null,"Upthegrove Gym Re-roof",null,null,40160,null,null,null,40160]
[null,"LaBelle High Re-roof",{"$nulls":4},1109000,null,1109000]
[null,"Central Elementary Re-roof",null,null,null,821000,null,null,821000]
["2b5.","Hendry Total",0,659000,1499160,980000,1268000,159000,4565160]
[]
["2b6","Schedule of options for generation of additional revenues by the district for expenditure on projects identified in the district facilities work "]
[null,"program which are not funded under paragraph 5 above.  Additional anticipated revenues may include SIT Program awards and Classrooms First funds."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["2b6.","Hendry Total",null,0,0,0,0,0,0]
[]
["2b7","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"LaBelle Middle Phase III",null,900000,500000,500000,500000,3600000,6000000]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b7","Hendry Total",0,900000,500000,500000,500000,3600000,6000000]
[]
["NOTE: If the sum of the totals in paragraphs 2b5. and 2b7. above DO NOT equal the total in paragraph 2b2. above, the message \"Check Totals\" appears.   "]
[null,"-- They should balance ! !"]
[null,null,null,"2003-04 ","2004-05 ","2005-06 ","2006-07","2007-08","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
[]
["Hendry  SCHOOL DISTRICT - - FACILITIES TEN (10) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the next 5 years beyond the above 5-year work plan. (years 6-10)"]
[]
[null,null,null,"2008/09 - 2012/13"]
[null,"Project","Location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"Replace Chiller","LaBelle High School",230000,{"$nulls":4},230000]
[null,"Replace Cooling towers","Clewiston Middle",200000,{"$nulls":4},200000]
[{"$nulls":8},0]
[]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b1","Hendry Total",null,430000,{"$nulls":4},430000]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the future 5 years beyond the above 5-year work plan."]
[]
[null,null,"Location - Community, quadrant,","2008/09 - 2012/13"]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"Portables","District Wide",159000,{"$nulls":4},159000]
[null,"HVAC repair and replacement","District Wide",500000,{"$nulls":4},500000]
[null,"Re-roof projects","District Wide",2000000,{"$nulls":4},2000000]
["2b2","Hendry Total",null,2659000,{"$nulls":4},2659000]
[]
["2b2a.","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2003-04","Actual 2002-03","Actual 2003-04","03/04 - 12/13         New Stu Capacity to","Projected 2012- 13","Projected 2012-13"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[null,"Elementary in LaBelle",2521,2853,1784,1,400,2184,0.67]
[null,"High School in LaBelle",1115,947,933,0.84,800,1733,0.99]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2b2a.","Hendry Total",3636,3800,2717,0.72,1200,3917,0.78]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the next 5 year period beyond the 5-year work plan above."]
[]
[]
["2b2g.","Plans for closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the next 5 year period beyond the 5-year plan above."]
[]
[]
["Hendry  SCHOOL DISTRICT - - FACILITIES TWENTY (20) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the 11 thru 20 out years."]
[]
[null,null,null,"2013/14-2022/23 ","Annual"]
[null,"Project","Location","Projected Cost","Average Cost",null,null,null,"10 YEAR TOTAL"]
[null,"Replace Chiller","Clewiston High",250000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":4},0,null,null,null,0]
[{"$nulls":4},0,null,null,null,0]
[]
[{"$nulls":4},0,null,null,null,0]
["2b1","Hendry Total",null,250000,{"$nulls":4},0]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the 11 thru 20 out years."]
[]
[null,null,"Location - Community, quadrant,","2013/14-2022/23 "]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"10 YEAR TOTAL"]
[null,"Portables","District wide",159000,159000,null,null,null,318000]
[null,"Roof Replacements","District wide",5000000,500000,null,null,null,5500000]
[null,"HVAC repairs and replacements","District wide",800000,80000,null,null,null,880000]
["2b2","Hendry Total",null,5959000,{"$nulls":4},6698000]
[]
["2b2a","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2003-04","Actual 2002-03","Actual 2000-01","13/14 - 22/23         New Stu Capacity to","District Projected 2022-23","Projected 2022-23"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[null,"3 Elementary Schools",2521,2853,1784,1,1200,3384,0.83]
[null,"1 Middle School",1044,939,856,0.9,600,1644,1.07]
[null,"1 High School",1115,947,933,0.85,800,1930,1.1]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2b2a","Hendry Total",4680,4739,3573,0.75,2600,6958,0.95]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the 11 thru 20 out years. "]
[null,"A feeder program consisting of 3 elementary, 1 middle and 1 high school within the district."]
[]
["2b2g","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the 11 thru 20 out years."]
[]
[]
[]
[]
[]
[null,"To the extent available, the tentative district facilities work program shall be based on information produced by the demographic, revenue, and"]
[null,"education estimating conferences pursuant to 216.136."]
[null,"Provision shall be made for public comment concerning the tentative district educational facilities plan."]
[null,"The district school board shall coordinate with each affected local government to ensure consistency between the tentative district educational facilities plan and"]
[null,"the local government comprehensive plans of the affected local governments during the deveolpment of the tentative district educational facilities plan."]
[null,"The adopted district facilities work program shall:"]
[null,"Be a complete, balanced capital outlay financial plan for the district."]
[null,"Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities, including safe access ways from neighborhoods to schools."]
[null,"The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 1013.61."]
[null,"The adopted district educational facilities plan shall include the information required in subparagraphs (2) (b) 1., 2., and 3., based upon projects actually"]
[null,"funded in the plan with the exception of the 10 and 20 year portions."]
{"$rows_empty":9}
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[null,"SCHOOL BOARD OF ","Hendry  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}