{"text_format":"2","workbook":"xls","n_sheets":17,"sheets":["*****","Pt 2-1","Pt 2","Pt 2a","Pt 2b","Pt 2c1","Pt 2c2","Pt 2c3 c4 2d","Pt 2e","Pt 2f 2g ","Pt 3","Pt 3 b","Pt 3 c","Pt 3 d-f","Pt 4","Pt 5","Pt 6 - End"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":2,"defined_names":46,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Pt 2-1","index":1,"n_rows":447,"n_cols":9,"rows_kept":447,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted "]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001."]
["District: ====>",null,"Hillsborough",null,"2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,null,"ELEMENTARY SCHOOLS"]
[null,"Renovate AC","ALEXANDER ELEMENTARY",280000,{"$nulls":4},280000]
[null,"Painting",null,null,null,130000,null,null,130000]
[null,"Renovate intercom",null,75000,{"$nulls":4},75000]
[null,"Replace fire alarm",null,100000,{"$nulls":4},100000]
[null,"Renovation/Remodeling","ANDERSON ELEMENTARY (FFF&E)",null,null,null,2389980,null,2389980]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation ","APOLLO BEACH ELEMENTARY (FFF&E)",{"$nulls":4},5148826,5148826]
[null,"Renovation/Remodeling","BALLAST POINT ELEMENTARY (FFF&E)",null,3150267,null,null,null,3150267]
[null,"Renovation/Remodeling","BAY CREST ELEMENTARY (FFF&E) ",null,1293611,2338845,null,null,3632456]
[null,"Renovation ","BELLAMY ELEMENTARY (FFF&E) ",{"$nulls":4},3674884,3674884]
[null,"Including intercom, phones ",{"$nulls":6},0]
[null,"Paint entire school","BING ELEMENTARY",null,100000,null,null,null,100000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Replace fire alarm",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Paint entire school","BOYETTE SPRINGS ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Replace intercom",null,75000,{"$nulls":4},75000]
[null,"Renovate fire alarm ",null,25000,{"$nulls":4},25000]
[null,"Correct drainage problems",{"$nulls":6},0]
[null,"Renovate intercom","BROOKER ELEMENTARY (FFF&E) (R&NC) ",null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,20000,null,null,null,20000]
[null,"Renovation/Remodeling","BROWARD ELEMENTARY (FFF&E) ",2132639,{"$nulls":4},2132639]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","BRYAN ELEMENTARY - PLANT CITY (FFF&E) ",3673148,{"$nulls":4},3673148]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Replace fire alarm","BUCKHORN ELEMENTARY ",{"$nulls":4},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","BURNEY-SIMMONS ",2145212,{"$nulls":4},2145212]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/remodeling","CAHOON ELEMENTARY (FFF&E) ",3200000,{"$nulls":4},3200000]
[null,"Including fire alarm, intercom",{"$nulls":6},0]
[null,"Paint","CANNELLA ELEMENTARY",{"$nulls":4},170000,170000]
[null,"Renovate intercom",null,null,25000,null,null,null,25000]
[null,"Replace telephones ",null,null,20000,null,null,null,20000]
[null,"Renovation/Remodeling","CARROLLWOOD ELEMENTARY (1) ",null,3605008,null,null,null,3605008]
[null,"Renovation","CHIARAMONTE ELEMENTARY (FFF&E)",{"$nulls":4},3039659,3039659]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","CITRUS PARK ELEMENTARY (FFF&E) ",null,3952920,null,null,null,3952920]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","CLAIR-MEL ELEMENTARY (FFF&E) ",null,3077216,null,null,null,3077216]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","CLEVELAND ELEMENTARY",null,1763888,null,null,null,1763888]
[null,"Renovate AC",{"$nulls":6},0]
[null,"Replace fie alarm in renovation",{"$nulls":5},150000,150000]
[null,"Replace intercom in renovation ",{"$nulls":5},150000,150000]
[null,"Renovate intercom and phones ","COLSON ELEMENTARY",null,75000,null,null,null,75000]
[null,"Replace fire alarm panel",null,null,25000,null,null,null,25000]
[null,"Interior/exterior painting",{"$nulls":5},150000,150000]
[null,"Renovation/Remodeling","CORK ELEMENTARY (FFF&E) ",{"$nulls":4},4386535,4386535]
[null,"Including fire alarm, intercom, phones, courts, water ",{"$nulls":6},0]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Renovation ","CRESTWOOD ELEMENTARY (FFF&E) ",{"$nulls":4},2418980,2418980]
[null,"Including intercom, phones ",{"$nulls":6},0]
[null,"Replace telephones ","CYPRESS CREEK ELEMENTARY",null,null,30000,null,null,30000]
[null,"Replace fire alarm",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Paint exterior& coping replacement",{"$nulls":4},230000,null,230000]
[null,"Storm drain repair",{"$nulls":5},10000,10000]
[null,"Renovation ","DESOTO ELEMENTARY (FFF&E)",{"$nulls":4},1363077,1363077]
[null,"Including fire alarm, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","DICKENSON ELEMENTARY (FFF&E) ",null,226712,null,null,null,226712]
[null,"Replace fire alarm ",{"$nulls":5},150000,150000]
[null,"Replace intercom ",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","DOVER ELEMENTARY (FFF&E) ",4118635,{"$nulls":4},4118635]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Replace intercom",null,null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Replace fire alarm ","DUNBAR ELEMENTARY",{"$nulls":4},150000,150000]
[null,"Replace intercome",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovate HVAC","EDISON ELEMENTARY (FFF&E) (R&NC) ",null,null,null,450000,null,450000]
[null,"Renovate bathrooms",{"$nulls":5},15000,15000]
[null,"Renovation/Remodeling","EGYPT LAKE ELEMENTARY",2131490,{"$nulls":4},2131490]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate intercom","ESSRIG ELEMENTARY",null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Replace fire alarm",null,null,150000,null,null,null,150000]
[null,"Paint exterior & interior",{"$nulls":4},120000,null,120000]
[null,"Renovate intercom","FOLSOM ELEMENTARY ",null,null,null,75000,null,75000]
[null,"Paint entire school",null,null,200000,null,null,null,200000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Replace fire alarm",{"$nulls":5},150000,150000]
[null,"Renovate fire alarm","FOREST HILLS ELEMENTARY",null,null,null,20000,null,20000]
[null,"Interior & exterior painting",{"$nulls":5},170000,170000]
[null,"Fencing",null,10000,{"$nulls":4},10000]
[null,"Renovation/Remodeling","FOSTER ELEMENTARY (FFF&E) ",null,3920511,null,null,null,3920511]
[null,"including intercom, telephones",{"$nulls":6},0]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Replace telephones ","GIBSONTON ELEMENTARY (1) (2) ",null,null,30000,null,null,30000]
[null,"Replace remaining AC",null,null,null,235000,null,null,235000]
[null,"Renovation/Remodeling","GORRIE ELEMENTARY",2367080,{"$nulls":4},2367080]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation / Remodeling","GRADY ELEMENTARY (FFF&E)",2585607,{"$nulls":4},2585607]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace remaining AC",{"$nulls":6},0]
[null,"Renovation/Remodeling","GRAHAM ELEMENTARY",null,1671830,null,null,null,1671830]
[null,"including fire alarm, intercom, telephones, irrigation",{"$nulls":6},0]
[null,"Renovate intercom","HUNTERS GREEN ELEMENTARY",null,null,null,75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovation/Remodeling","JACKSON ELEMENTARY (FFF&E) ",2295601,{"$nulls":4},2295601]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","JAMES ELEMENTARY",null,1997900,null,null,null,1997900]
[null,"including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/remodeling","KENLY ELEMENTARY (FFF&E) ",null,3139218,null,null,null,3139218]
[null,"including intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Renovation/ Remodeling","KINGSWOOD ELEMENTARY (FFF&E) ",null,null,null,3541346,null,3541346]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation","KNIGHTS ELEMENTARY (FFF&E) ",null,4522563,null,null,null,4522563]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Renovation/Remodeling","LAKE MAGDALENE ELEMENTARY",null,null,4009192,null,null,4009192]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","LANIER ELEMENTARY (FFF&E) ",null,null,null,2423758,null,2423758]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","LEE ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Paint interior",null,null,null,70000,null,null,70000]
[null,"Replace flooring",null,null,null,125000,null,null,125000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Interior and Exterior Painting","LEWIS ELEMENTARY",{"$nulls":4},170000,170000]
[null,"Renovation","LIMONA ELEMENTARY ",{"$nulls":4},3582223,3582223]
[null,"Special Projects",null,91615,{"$nulls":4},91615]
[null,"Renovate AC","LINCOLN ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Renovate restrooms",null,null,null,65000,null,null,65000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovate fire alarm",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Renovate fire alarm","LITHIA SPRINGS ELEMENTARY",null,null,20000,null,null,20000]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Resurface parking",null,null,50000,null,null,null,50000]
[null,"Replace telephones ",null,null,null,30000,null,null,30000]
[null,"Replace telephones ","LOCKHART ELEMENTARY",null,null,30000,null,null,30000]
[null,"Renovation/Remodeling","LOMAX ELEMENTARY",null,1500387,null,null,null,1500387]
[null,"including intercom, phones",{"$nulls":6},0]
[null,"Interior & exterior painting","LOPEZ ELEMETNARY ",{"$nulls":4},150000,150000]
[null,"Renovate intercom","LOWRY ELEMENTARY",null,null,75000,null,null,75000]
[null,"Replace telephones ",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","LUTZ ELEMENTARY (FFF&E) ",3686801,{"$nulls":4},3686801]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation","MABRY ELEMENTARY (FFF&E) ",null,null,3525527,null,null,3525527]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","MANGO ELEMENTARY",null,30000,null,null,null,30000]
[null,"Renovate fire alarm",null,125000,{"$nulls":4},125000]
[null,"Renovate intercom",null,null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovate fire alarm","MANISCALCO ELEMENTARY",null,null,20000,null,null,20000]
[null,"Replace HVAC",{"$nulls":5},1104000,1104000]
[null,"Paint interior & exterior",null,null,null,150000,null,null,150000]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Replace telephones ",null,null,null,30000,null,null,30000]
[null,"Renovation  ","MCDONALD ELEMENTARY (FFF&E) ",{"$nulls":4},3727184,3727184]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","MENDENHALL ELEMENTARY (FFF&E) ",null,2857969,null,null,null,2857969]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation /Remodeling","MILES ELEMENTARY",null,3398334,null,null,null,3398334]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC",null,null,260000,null,null,null,260000]
[null,"Renovate telephones","MINTZ ELEMENTARY",null,null,30000,null,null,30000]
[null,"Special Projects",null,260000,{"$nulls":4},260000]
[null,"Interior & exterior painting",{"$nulls":5},150000,150000]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Renovation/Remodeling","MITCHELL ELEMENTARY",null,1810490,null,null,null,1810490]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","MORGAN WOODS ELEMENTARY (FFF&E) ",null,3810710,null,null,null,3810710]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","MORT ELEMENTARY (FFF&E) ",null,3831950,null,null,null,3831950]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate intercom","NORTHWEST ELEMENTARY",null,null,null,75000,null,75000]
[null,"Replace AC controls",{"$nulls":5},768000,768000]
[null,"Paint interior & exterior",{"$nulls":4},150000,null,150000]
[null,"Replace roof flashing",null,null,100000,null,null,null,100000]
[null,"Replace telephones ",{"$nulls":4},20000,null,20000]
[null,"Replace fire alarm",{"$nulls":5},75000,75000]
[null,"Replace telephones ","OAK PARK ELEMENTARY",null,null,null,30000,null,30000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate intercom",{"$nulls":5},150000,150000]
[null,"Renovation/Remodeling","PALM RIVER ELEMENTARY (FFF&E) ",null,4465598,null,null,null,4465598]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation","PINECREST ELEMENTARY (FFF&E) ",{"$nulls":4},5158444,5158444]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Renovation/Remodeling","POTTER ELEMENTARY",null,2340516,null,null,null,2340516]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Reroofing","RIVERHILLS ELEMENTARY",{"$nulls":4},280000,280000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Renovation ","RIVERVIEW ELEMENTARY (FFF&E) ",{"$nulls":4},3761016,3761016]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate facility","ROBLES ELEMENTARY",2811784,{"$nulls":4},2811784]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Replace telephones ",{"$nulls":6},0]
[null,"Renovate AC","ROOSEVELT ELEMENTARY",null,300000,null,null,null,300000]
[null,"Replace fire alarm panel",null,null,null,7500,null,null,7500]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Replace clrm lighting",null,null,67740,null,null,null,67740]
[null,"Paint entire school",null,null,150000,null,null,null,150000]
[null,"Reroof auditorium",null,null,80000,null,null,null,80000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovation","RUSKIN ELEMENTARY",{"$nulls":4},4413729,4413729]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate intercom","SCHWARZKOPF ELEMENTARY",null,null,null,75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},20000,null,20000]
[null,"Interior & exterior painting",{"$nulls":5},150000,150000]
[null,"Renovate fire alarm","SEMINOLE ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovate HVAC",{"$nulls":4},600000,null,600000]
[null,"Renovate intercom",{"$nulls":4},75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovation/Remodeling","SHAW ELEMENTARY (FFF&E)  ",null,4721795,null,null,null,4721795]
[null,"Replace telephones ",{"$nulls":5},50000,50000]
[null,"Replace telephones ","SHORE ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovation","SPRINGHEAD ELEMENTARY (FFF&E) ",{"$nulls":4},2953726,2953726]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","SULPHUR SPRINGS ELEMENTARY   ",null,null,null,285000,null,285000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovate fire alarm",{"$nulls":4},20000,null,20000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Replace telephones ","SUMMERFIELD ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate AC",{"$nulls":6},0]
[null,"Interior & exterior painting","TAMPA BAY BOULEVARD  ELEMENTARY",{"$nulls":4},100000,100000]
[null,"Water proofing ",{"$nulls":6},0]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Renovate fire alarm","TAMPA PALMS ELEMENTARY",null,null,null,75000,null,75000]
[null,"Renovate intercom",{"$nulls":4},75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Remediate water intrusion",null,null,null,349000,null,null,349000]
[null,"Renovate AC","TEMPLE TERRACE ELEMENTARY",null,600000,null,null,null,600000]
[null,"Interiior & exterior painting ",{"$nulls":5},200000,200000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones ",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","THONOTOSASSA ELEMENTARY (FFF&E) ",null,3389746,null,null,null,3389746]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","TINKER ELEMENTARY (FFF&E) ",null,null,2855483,null,null,2855483]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","TOWN & COUNTRY ELEMENTARY (FFF&E) ",2895572,{"$nulls":4},2895572]
[null,"Renovation ","TRAPNELL ELEMENTARY",{"$nulls":4},3735711,3735711]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Replace telephones ","TWIN LAKES ELEMENTARY",null,null,null,30000,null,30000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones","VALRICO ELEMENTARY",null,null,30000,null,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},150000,150000]
[null,"Replace telephones ","WALDEN LAKE ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovate intercom",null,null,null,150000,null,150000,300000]
[null,"Renovate fire alarm",null,125000,null,null,20000,null,145000]
[null,"Renovation/Remodeling","WASHINGTON ELEMENTARY  (BOOKER T.)",null,3298903,null,null,null,3298903]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","WEST TAMPA ELEMENTARY",null,50000,null,null,null,50000]
[null,"Interior & exterior painting",{"$nulls":5},70000,70000]
[null,"Replace HVAC",{"$nulls":5},1266000,1266000]
[null,"Renovate intercom",null,null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Replace fire alarm panel",null,null,25000,null,null,null,25000]
[null,"Renovation /Remodeling","WESTSHORE ELEMENTARY",null,1681734,null,null,null,1681734]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","WILSON ELEMENTARY",null,30000,null,null,null,30000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","WIMAUMA ELEMENTARY",null,3802179,null,null,null,3802179]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones","WITTER ELEMENTARY",{"$nulls":4},30000,30000]
[null,"Renovation/Remodeling","WOODBRIDGE ELEMENTARY (FFF&E) ",null,3429994,null,null,null,3429994]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Paint interior & exterior","YATES ELEMENTARY",null,null,null,100000,null,100000]
[null,"Renovate fire alarm",{"$nulls":4},25000,null,25000]
[null,"Replace intercom",{"$nulls":4},75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},20000,null,20000]
[null,null,"MIDDLE SCHOOLS"]
[null,"Renovation/Remodeling","ADAMS  MIDDLE (FFF&E) ",null,5875965,null,null,null,5875965]
[null,"including fire alarm, intercom",{"$nulls":6},0]
[null,"Fencing",null,10000,{"$nulls":4},10000]
[null,"Renovation/Remodeling","BUCHANAN MIDDLE (FFF&E) ",7907453,{"$nulls":4},7907453]
[null,"including fire alarm, intercom",{"$nulls":6},0]
[null,"Replace fire alarm ","BURNS MIDDLE ",160000,{"$nulls":4},160000]
[null,"Replace intercom ",null,150000,{"$nulls":4},150000]
[null,"Renovate fire alarm","DOWDELL MIDDLE ",null,125000,null,null,null,125000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Renovation/Remodeling","EISENHOWER MIDDLE (FFF&E) ",null,5584078,null,null,null,5584078]
[null,"including intercom, phones",{"$nulls":6},0]
[null,"Renovate intercom","FERRELL MIDDLE",null,30000,null,null,null,30000]
[null,"Paint entire school",null,null,150000,null,null,null,150000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Renovation/Remodeling","FRANKLIN MIDDLE (FFF&E) ",null,4552820,null,null,null,4552820]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","GRECO MIDDLE (FFF&E) (R&NC) ",null,7742821,null,null,null,7742821]
[null,"Replace fire alarm ","HILL MIDDLE ",{"$nulls":4},150000,150000]
[null,"Replace intercom ",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},35000,35000]
[null,"Renovation/Remodeling","MADISON MIDDLE (FFF&E) ",5081698,{"$nulls":4},5081698]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Irrigation",{"$nulls":5},40000,40000]
[null,"Renovation/Remodeling","MANN MIDDLE",null,7310090,null,null,null,7310090]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace clrm flooring",null,150000,{"$nulls":4},150000]
[null,"Replace telephones","MARSHALL MIDDLE ",null,30000,null,null,null,30000]
[null,"Replace boilers/piping",null,null,null,25000,null,null,25000]
[null,"Renovation/Remodeling","MCLANE MIDDLE ",null,4554533,null,null,null,4554533]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones","MONROE MIDDLE ",null,30000,null,null,null,30000]
[null,"Paint interior & exterior",{"$nulls":4},170000,null,170000]
[null,"Replace HVAC",{"$nulls":5},170000,170000]
[null,"Replace telephones","PROGRESS VILLAGE MIDDLE ",30000,{"$nulls":4},30000]
[null,"Interior & exterior painting",{"$nulls":5},250000,250000]
[null,"Replace telephones","ROLAND PARK MIDDLE",null,null,null,30000,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},180000,180000]
[null,"Renovate intercom","SLIGH MIDDLE",null,120000,null,null,null,120000]
[null,"Replace fire alarm",null,null,150000,null,null,null,150000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovate restrooms",{"$nulls":4},60000,null,60000]
[null,"Replace telephones",null,30000,{"$nulls":4},30000]
[null,"Renovate fire alarm","STEWART MIDDLE ",null,null,null,25000,null,25000]
[null,"Renovate intercom",{"$nulls":4},120000,null,120000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},160000,160000]
[null,"Replace boilers/piping","TURKEY CREEK MIDDLE",null,null,30000,null,null,30000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Renovation/Remodeling","VAN BUREN MIDDLE (FFF&E) ",null,6400000,null,null,null,6400000]
[null,"Replace telephones","WALKER MIDDLE ",null,null,null,30000,null,30000]
[null,"Paint interior & exterior",{"$nulls":4},200000,null,200000]
[null,"Renovation/Remodeling","WEBB MIDDLE (FFF&E) ",null,6795806,null,null,null,6795806]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Replace telephones","WILLIAMS MIDDLE ",null,null,null,30000,null,30000]
[null,"Replace floors","WILSON MIDDLE ",null,60000,null,null,null,60000]
[null,"Interior & exterior painting",{"$nulls":5},120000,120000]
[null,"Renovate AC",null,840000,{"$nulls":4},840000]
[null,"Replace telephones",null,30000,{"$nulls":4},30000]
[null,"Replace intercom",null,150000,{"$nulls":4},150000]
[null,"Replace telephones","YOUNG MIDDLE",null,null,null,30000,null,30000]
[null,null,"HIGH SCHOOLS"]
[null,"Renovate fire alarm","ARMWOOD HIGH",null,null,null,175000,null,175000]
[null,"Special Projects",null,100000,{"$nulls":4},100000]
[null,"Renovate AC",{"$nulls":4},250000,null,250000]
[null,"Replace softball & baseball turf",null,null,128333,null,null,null,128333]
[null,"Renovate fire alarm","BLOOMINGDALE HIGH",null,null,175000,null,null,175000]
[null,"Replace intercom",{"$nulls":5},200000,200000]
[null,"Special Projects",null,500000,{"$nulls":4},500000]
[null,"Renovate auditorium PA ",null,null,20000,null,null,null,20000]
[null,"Renovate stage lighting",null,null,10000,null,null,null,10000]
[null,"Renovation/Remodeling","BRANDON HIGH (FFF&E) ",null,13254243,null,null,null,13254243]
[null,"Speical Projects",null,40000,{"$nulls":4},40000]
[null,"Resurface track ",null,25000,{"$nulls":4},25000]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Renovation/Remodeling","CHAMBERLAIN HIGH     (FF&E)",3525229,{"$nulls":4},3525229]
[null,"Replace telephones","DURANT HIGH  ",40000,{"$nulls":4},40000]
[null,"Renovation/Remodeling","EAST BAY HIGH (FFF&E) ",null,13254243,null,null,null,13254243]
[null,"including telephones",{"$nulls":6},0]
[null,"SB field repair",{"$nulls":5},60000,60000]
[null,"Renovate stadium PA ","GAITHER HIGH",null,10000,null,null,null,10000]
[null,"Renovate auditorium PA ",null,null,20000,null,null,null,20000]
[null,"Special Projects ",null,300000,{"$nulls":4},300000]
[null,"Resurface track ",{"$nulls":5},25000,25000]
[null,"Paint entire school",null,null,120000,null,null,null,120000]
[null,"Renovate drainage",{"$nulls":4},35000,null,35000]
[null,"Replace intercom","HILLSBOROUGH HIGH",250000,{"$nulls":4},250000]
[null,"Waterproofing ",null,2457255,{"$nulls":4},2457255]
[null,"Replace AC",null,null,null,4500000,null,null,4500000]
[null,"Replace gym lighting",null,null,67740,null,null,null,67740]
[null,"Replace baseball turf",null,null,75000,null,null,null,75000]
[null,"Replace softball turf",null,null,45000,null,null,null,45000]
[null,"Renovation/Remodeling","JEFFERSON HIGH ",null,10783371,null,null,null,10783371]
[null,"Renovation/Remodeling","KING HIGH (FFF&E) ",null,11807407,null,null,null,11807407]
[null,"Renovation/Remodeling","LETO HIGH (FFF&E) ",7691749,{"$nulls":4},7691749]
[null,"including fire alarm, intercom ",{"$nulls":6},0]
[null,"Renovation/ Remodeling","PLANT CITY HIGH (FFF&E) ",null,13254243,null,null,null,13254243]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation in process","PLANT HIGH (FFF&E)  ",5423709,{"$nulls":4},5423709]
[null,"Renovation in process","ROBINSON HIGH (FFF&E) ",3369774,{"$nulls":4},3369774]
[null,"Renovate intercom","SICKLES HIGH ",null,null,null,25000,null,25000]
[null,"Replace telephones",null,40000,{"$nulls":4},40000]
[null,"Renovation/Remodeling","TAMPA BAY TECHNICAL HIGH (FFF&E) ",null,8540649,null,null,null,8540649]
[null,"Replace intercom ",{"$nulls":6},0]
[null,"BB",null,75000,{"$nulls":4},75000]
[null,"Fencing",null,20000,{"$nulls":4},20000]
[null,null,"OTHER FACILITIES"]
[null,"Replace fire alarm ","BREWSTER TECHNICAL",{"$nulls":4},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones","CAMINITI EXCEPTIONAL",null,null,null,30000,null,30000]
[null,"Paint entire school",{"$nulls":4},150000,null,150000]
[null,"Renovate HVAC",{"$nulls":4},660000,null,660000]
[null,"Replace fire alarm ",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones","DOROTHY THOMAS CENTER ",30000,{"$nulls":4},30000]
[null,"Replace intercom",null,75000,{"$nulls":4},75000]
[null,"Renovate AC",{"$nulls":4},40000,null,40000]
[null,"Replace fire alarm","EISENHOWER EXCEPTIONAL CENTER",null,125000,null,null,null,125000]
[null,"Renovate AC",{"$nulls":4},80000,null,80000]
[null,"Renovation ","ERWIN TECHNICAL CENTER",{"$nulls":4},12407248,12407248]
[null,"Renovate AC ",null,null,300000,null,null,null,300000]
[null,"Replace telephones",null,null,150000,null,null,null,150000]
[null,"Renovation/Remodeling","JUST EARLY CHILDHOOD CENTER",null,1822159,null,null,null,1822159]
[null,"including intercom, phones",{"$nulls":6},0]
[null,"Renovate fire alarm","KIMBALL FULL SERVICE SCHOOL",null,null,null,20000,null,20000]
[null,"Replace telephones",{"$nulls":4},20000,null,20000]
[null,"Renovation","LAVOY EXCEPTIONAL",{"$nulls":4},2441620,2441620]
[null,"Replace fire alarm panel",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Renovate intercom","LEAREY TECHNICAL ",null,null,null,55000,null,55000]
[null,"Reroof","LIBRARY PROCESSING",null,null,null,70000,null,70000]
[null,"Roofing","MAINTENANCE FACILITY",null,null,null,25000,null,25000]
[null,"Renovation/Remodeling","MEACHAM EARLY CHILDHOOD",{"$nulls":4},1727191,1727191]
[null,"including intercom, phones ",{"$nulls":6},0]
[null,"Renovate AC","ROS SCHOOL ADMINISTRATIVE CENTER",null,3100000,null,null,null,3100000]
[null,"Renovate AC","TRANSPORTATION OFFICES",null,null,null,190000,null,190000]
[null,"Replace telephones","VELASCO",null,235000,null,null,null,235000]
[null,"Phased renovation","WATERS CENTER (GEO. WASHINGTON JR HI)",9485615,{"$nulls":4},9485615]
[null,"including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Cost to Retrofit Relocatables to Meet New Building Codes",null,2275566,{"$nulls":4},2275566]
["2.1","Hillsborough 2.1 Subtotal",null,86173232,206268190,19485547,13845084,76608053,402380106]

{"sheet":"Pt 2","index":2,"n_rows":102,"n_cols":9,"rows_kept":102,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough",null,"2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New High School GGG","Middleton High School 2505 SS",18841792,null,null," ",null,18841792]
[null,"New High School JJJ","New Tampa Area High School 2485 SS",19162325,{"$nulls":4},19162325]
[null,"New High School LLL","Southeast Brandon/Fish Hawk Area 2509 SS",15064788,22597183,null,null,null,37661971]
[null,"New High School PPP","South County/Ruskin Area 2509 SS",null,null,38074939,null,null,38074939]
[null,"New Middle School GG","North County Area Middle School 1511 SS",8170628,{"$nulls":4},8170628]
[null,"New Middle School JJ","New Tampa Area Middle School 1537 SS",8869641,{"$nulls":4},8869641]
[null,"New Middle School KK","South Ruskin Area Middle School 1550 SS",null,17743438,null,null,null,17743438]
[null,"New Middle School LL","Thonotosassa Area Middle School 1511 SS",16773736,{"$nulls":4},16773736]
[null,"New Middle School MM","West County Area Middle School 1550 SS",15280373,{"$nulls":4},15280373]
[null,"New Middle School NN","Valrico Area Middle School 1511 SS",16644345,{"$nulls":4},16644345]
[null,"New Middle School OO","New Tampa Area Middle School 1550 SS",null,null,18187023,null,null,18187023]
[null,"New Elem. School B","East Tampa Area Elem 600 SS",null,6774196,null,null,null,6774196]
[null,"New Elem. School C Downtown Workplace School","Downtown Area 600 SS",null,6576582,null,null,null,6576582]
[null,"New Elem. School D","Valrico Area Elem 901 SS",9459862,{"$nulls":4},9459862]
[null,"New Elem. School E","North Brandon Area Elem 961 SS",9459862,{"$nulls":4},9459862]
[null,"New Elem. School M","West County Area Elementary 946 SS",8462622,{"$nulls":4},8462622]
[null,"New Elem. School O","No County Elem School 500 SS",5559004,{"$nulls":4},5559004]
[null,"New Elem. School P","South Alafia Elem 941 SS",9586850,{"$nulls":4},9586850]
[null,"New Elem. School R","South Riverview Elem 901 SS",9319862,{"$nulls":4},9319862]
[null,"New Elem. School S","Heritage Isles Area Elem 961 SS",null,9608070,null,null,null,9608070]
[null,"New Elem. School T","Big Bend Area Elem 941 SS",null,null,9816422,null,null,9816422]
[null,"New Elem. School U","North West Area Elem 946 SS",9459862,{"$nulls":4},9459862]
[null,"New Elem. School V","Rivercrest Area Elem 941 SS",9319862,{"$nulls":4},9319862]
[null,"New Elem. School W","New Tampa Area Elem 946 SS",null,null,9816422,null,null,9816422]
[null,"New Elem. School X","Van Dyke/Gunn Area Elem 946 SS",null,null,9816422,null,null,9816422]
[null,"New Elem. School Y","Fish Hawk Area Elem 946 SS",null,null,9816422,null,null,9816422]
[null,"New Elem. School Z","Triple Creek, South County Area Elem 946 SS",null,null,9816422,null,null,9816422]
[null,"Adult Center East","Replaces Gary Adult Center",null,2666912,null,null,null,2666912]
[null,"Adult Technology Center","Sabal Park Area",null,3172050,null,null,null,3172050]
[null,"Career Center MMM","South County Career School 640 SS",5384900,{"$nulls":4},5384900]
[null,"Career Center NNN","North County Career School 570 SS",9994030,{"$nulls":4},9994030]
[null,"Career Center OOO","East County Career School 300 SS",4606998,{"$nulls":4},4606998]
[null,"Plant City ESE","16 CR, RR's Co-locate with OOO",2099089,{"$nulls":4},2099089]
[null,"Waters, D.W.","Career Center ",6323374,{"$nulls":4},6323374]
[null,"Various Sites","Site Acquisitions ",5847855,3500000,1500000,1500000,1500000,13847855]
[null,"Enhanced Hurricane Shelters","Required by DEP in all schools",8998802,2074153,2018074,null,null,13091029]
[null,"ELEMENTARY SCHOOLS"]
[null,"Alexander Elementary","Addition - 3 Kdg, 1 Pri CR's, (Class Size Reduction)",603346,{"$nulls":4},603346]
[null,"Broward Elementary","Addition - 8 CR",1286695,{"$nulls":4},1286695]
[null,"Bryan (PC) Elementary","Addition - 3 Kdg, 7 Pri CR's, (Class Size Reduction), Media Center ",1964036,{"$nulls":4},1964036]
[null,"Burney Simmons Elementary","Addition - 10 CR ",2016000,{"$nulls":4},2016000]
[null,"Clair Mel Elementary","Addition - 1 Kdg, 4 Pri CR's, (Class Size Reduction), 1 Int CR",889950,{"$nulls":4},889950]
[null,"Claywell Elementary","Addition - 12 CR",1779667,{"$nulls":4},1779667]
[null,"Cork Elementary","Addition - 4 CR",null,null,562275,null,null,562275]
[null,"DeSoto Elementary","Addition 1 Media Center, 6 CR",2019091,{"$nulls":4},2019091]
[null,"Dover Elementary ESE","Addition - 15 CR",1415126,{"$nulls":4},1415126]
[null,"Edison Elementary","Addition - 3 Kdg, 2 Pri CR's, (Class Size Reduction), 1 Int CR",930254,{"$nulls":4},930254]
[null,"Folsom Elementary","Addition - 6 CR",null,null,803190,null,null,803190]
[null,"Gorrie Elementary","Addition - 4 CR and Media Center, Convert existing Media Center to 2 CR ",1325678,{"$nulls":4},1325678]
[null,"Grady Elementary ","Addition - 2 Kdg, 1 Pri CR, 1 Int CR ",557376,{"$nulls":4},557376]
[null,"Graham Elementary","Addition - 1 Kdg, 4 Pri CR's, (Class Size Reduction), 1 Int CR",868548,{"$nulls":4},868548]
[null,"Jackson Elementary","Construct - 5 K CR's, Music CR, Media Center, Expand Dining Rm, ",1608183,{"$nulls":4},1608183]
[null,"James Elementary ","Addition - 14 CR, Media Center ",null,2400000,null,null,null,2400000]
[null,"Just Elementary ","Addition - 14 CR",null,1750000,null,null,null,1750000]
[null,"Kingswood Elementary","Addition - 8 CR",null,null,1070010,null,null,1070010]
[null,"Knights Elementary","Additition - 4 CR",null,null,562275,null,null,562275]
[null,"Lewis Elementary","Addition - 6 CR",1020052,{"$nulls":4},1020052]
[null,"Lomax Elementary ","Addition - 11 CR ",null,1965000,null,null,null,1965000]
[null,"Lopez Elementary ESE","Addition - 8 CR",1234459,{"$nulls":4},1234459]
[null,"Mabry Elementary","Addition - 4 CR",805720,{"$nulls":4},805720]
[null,"Morgan Woods Elementary ","Addition - 6 CR",1023435,{"$nulls":4},1023435]
[null,"Potter Elementary","Addition, 12 CR, Media Center ",null,2474000,null,null,null,2474000]
[null,"Riverview Elementary","Addition - 12 CR and 4 ESE Resource",1936346,{"$nulls":4},1936346]
[null,"Robles  Elementary","Addition - 2 Kdg CR's, (Class Size Reduction), 2 Int CR",589746,{"$nulls":4},589746]
[null,"Roosevelt Elementary","Addition - 1 Kdg, 3 Pri CR's, (Class Size Reduction)",556260,{"$nulls":4},556260]
[null,"Ruskin Elementary","Addition - 2 Kdg, 2 Pri CR's, (Class Size Reduction)",561731,{"$nulls":4},561731]
[null,"Tampa Bay Blvd Elem","Addition - 4 Pri CR's",613010,{"$nulls":4},613010]
[null,"Town & Country Elementary","Addition - 1 Kdg, 3 Pri CR's, (Class Size Reduction)",560179,{"$nulls":4},560179]
[null,"West Shore Elementary","Addition - 2 Kdg CR's, 2 Int CR, Media Center",1277760,{"$nulls":4},1277760]
[null,"West Tampa Elementary","Addition - 1 Kdg, 7 Pri CR's",{"$nulls":5},0]
[null,"Woodbridge Elementary","Addition - 4 CR",null,null,562275,null,null,562275]
[null,"MIDDLE SCHOOLS"]
[null,"Adams Middle","Addition - Gym, Locker Rooms, Remodel Locker Rooms to 4 CR",null,2537778,null,null,null,2537778]
[null,"Buchanan Middle ","Addition - Gym, 80 student stations",1090342,{"$nulls":4},1090342]
[null,"Eisenhower Middle ","Addition - Gym, 80 student stations",null,1188478,null,null,null,1188478]
[null,"Ferrell Middle ","Replacement of Gym, Addition -  8 CR",2221612,{"$nulls":4},2221612]
[null,"Franklin Middle ","Addition - Gym, 80 student stations",null,1188478,null,null,null,1188478]
[null,"Greco Middle ","Addition - Gym, 80 student stations",null,1188478,null,null,null,1188478]
[null,"Madison Middle","Addition - Gym, 80 student stations",1090342,{"$nulls":4},1090342]
[null,"Mann Middle","Addition - Gym, 80 student stations",null,1188478,null,null,null,1188478]
[null,"McLane Middle","Replacement - Gym, 80 student stations",null,1188478,null,null,null,1188478]
[null,"Van Buren Middle ","Addition - Gym, 80 student stations",1090342,{"$nulls":4},1090342]
[null,"Webb Middle","Addition - Gym, 80 student stations",null,1188478,null,null,null,1188478]
[null,"HIGH SCHOOLS"]
[null,"Armwood High","Addition - 15 CR's, 3 Bus Labs & Restrooms ",2653119,{"$nulls":4},2653119]
[null,"Durant High","Addition - 11 CR's, 3 Bus Labs & Restrooms ",1002540,{"$nulls":4},1002540]
[null,"OTHER FACILITIES"]
[null,"Gary Adult ","Replace facilities ",null,2837141,null,null,null,2837141]
[null,"MacFarlane Center","Replace portables & condemned building",2781982,{"$nulls":4},2781982]
[2.2,"Hillsborough 2.2 Subtotal",null,272063389,95807371,112422171,1500000,1500000,483292931]
[]
["2.1","Hillsborough 2.1 Subtotal",null,86173232,206268190,19485547,13845084,76608053,402380106]
[2.2,"Hillsborough 2.2 Subtotal",null,272063389,95807371,112422171,1500000,1500000,483292931]
[]
[2,"Hillsborough 2 Total",null,358236621,302075561,131907718,15345084,78108053,885673037]

{"sheet":"Pt 2a","index":3,"n_rows":220,"n_cols":9,"rows_kept":220,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"ELEMENTARY SCHOOLS"]
[14,"ALAFIA ELEMENTARY ",1184,1184,1254,1.06,-316,779,0.9]
[5,"ALEXANDER ELEMENTARY",887,887,758,0.85,-77,682,0.84]
[7,"ANDERSON ELEMENTARY",474,474,460,0.97,0,439,0.93]
[9,"APOLLO BEACH ELEMENTARY",745,745,663,0.89,0,737,0.99]
[10,"BALLAST POINT ELEMENTARY",468,468,413,0.88,0,410,0.88]
[12,"BAY CREST ELEMENTARY",861,861,817,0.95,-39,757,0.92]
[69,"BELLAMY ELEMENTARY",846,846,836,0.99,-82,671,0.88]
[205,"BEVIS ELEMENTARY",902,902,320,0.35,0,890,0.99]
[13,"BING ELEMENTARY",947,947,747,0.79,0,704,0.74]
[18,"BOYETTE SPRINGS ELEMENTARY",905,905,998,1.1,0,929,1.03]
[21,"BROOKER ELEMENTARY",1026,1026,1000,0.97,-181,863,1.02]
[22,"BROWARD ELEMENTARY",535,535,600,1.12,119,462,0.71]
[24,"BRYAN ELEM - PC",728,728,847,1.16,206,680,0.73]
[26,"BUCKHORN ELEMENTARY",807,807,902,1.12,-19,769,0.98]
[641,"BURNEY SIMMONS",265,265,0,0,250,406,0.79]
[30,"CAHOON ELEMENTARY",653,653,636,0.97,0,630,0.96]
[32,"CANNELLA ELEMENTARY",1004,1004,986,0.98,-103,818,0.91]
[33,"CARROLLWOOD ELEMENTARY",753,753,775,1.03,-40,682,0.96]
[36,"CHIARAMONTE ELEMENTARY",564,564,452,0.8,-44,453,0.87]
[210,"CHILES ELEMENTARY ",845,845,0,0,0,889,1.05]
[37,"CITRUS PARK ELEMENTARY",834,834,787,0.94,-54,571,0.73]
[38,"CLAIR-MEL ELEMENTARY",888,888,754,0.85,67,644,0.67]
[200,"CLARK ELEMENTARY",941,941,926,0.98,0,781,0.83]
[40,"CLAYWELL ELEMENTARY",910,910,1038,1.14,22,971,1.04]
[41,"CLEVELAND ELEMENTARY",435,435,431,0.99,0,322,0.74]
[43,"COLSON ELEMENTARY",895,895,690,0.77,-25,688,0.79]
[45,"CORK ELEMENTARY",828,828,820,0.99,41,774,0.89]
[46,"CRESTWOOD ELEMENTARY",933,933,1100,1.18,-27,860,0.95]
[47,"CYPRESS CREEK ELEMENTARY",982,982,849,0.86,-59,891,0.97]
[48,"DESOTO ELEMENTARY",338,338,300,0.89,150,375,0.77]
[49,"DICKENSON ELEMENTARY",765,765,725,0.95,0,699,0.91]
[50,"DOVER ELEMENTARY",1028,1028,732,0.71,102,674,0.6]
[51,"DUNBAR ELEMENTARY",369,369,420,1.14,0,361,0.98]
[54,"EDISON ELEMENTARY",651,651,421,0.65,117,691,0.9]
[55,"EGYPT LAKE ELEMENTARY",719,719,879,1.22,-196,461,0.88]
[57,"ESSRIG ELEMENTARY",992,992,1084,1.09,73,995,0.93]
[58,"FOLSOM ELEMENTARY ",998,998,973,0.97,-134,864,1]
[2,"FOREST HILLS ELEMENTARY",804,804,959,1.19,0,859,1.07]
[59,"FOSTER ELEMENTARY",936,936,718,0.77,-132,549,0.68]
[65,"GIBSONTON ELEMENTARY",905,905,636,0.7,-120,668,0.85]
[66,"GORRIE ELEMENTARY",456,456,562,1.23,126,549,0.94]
[67,"GRADY ELEMENTARY",581,581,541,0.93,32,518,0.85]
[68,"GRAHAM ELEMENTARY",446,446,362,0.81,125,533,0.93]
[73,"HUNTERS GREEN ELEMENTARY",980,980,778,0.79,0,732,0.75]
[74,"JACKSON ELEMENTARY",440,440,383,0.87,88,377,0.71]
[6502,"JAMES ELEMENTRY ",553,553,0,0,400,853,0.9]
[282,"JUST ELEMENTARY",291,291,118,0.41,381,589,0.88]
[76,"KENLY ELEMENTARY",620,620,530,0.85,0,349,0.56]
[78,"KINGSWOOD ELEMENTARY",811,811,849,1.05,-126,639,0.93]
[79,"KNIGHTS ELEMENTARY",903,903,746,0.83,-29,744,0.85]
[80,"LAKE MAGDALENE ELEMENTARY",1273,1273,1022,0.8,-297,801,0.82]
[81,"LANIER ELEMENTARY",595,595,505,0.85,-49,483,0.88]
[84,"LEE ELEMENTARY",433,433,449,1.04,0,452,1.04]
[88,"LEWIS ELEMENTARY",800,800,926,1.16,136,787,0.84]
[86,"LIMONA ELEMENTARY",990,990,925,0.93,-141,742,0.87]
[87,"LINCOLN ELEMENTARY",479,479,449,0.94,0,442,0.92]
[89,"LITHIA SPRINGS ELEMENTARY",1038,1038,962,0.93,-136,797,0.88]
[44,"LOCKHART ELEMENTARY",851,851,450,0.53,0,753,0.88]
[91,"LOMAX ELEMENTARY",337,337,222,0.66,275,543,0.89]
[92,"LOPEZ ELEMENTARY",946,946,671,0.71,89,645,0.62]
[93,"LOWRY ELEMENTARY",852,852,820,0.96,0,840,0.99]
[94,"LUTZ ELEMENTARY",688,688,652,0.95,0,613,0.89]
[95,"MABRY ELEMENTARY",687,687,723,1.05,47,711,0.97]
[98,"MANGO ELEMENTARY",790,790,832,1.05,0,633,0.8]
[99,"MANHATTAN ELEMENTARY",630,630,184,0.29,0,186,0.3]
[100,"MANISCALCO ELEMENTARY",848,848,802,0.95,-26,754,0.92]
[103,"MCDONALD ELEMENTARY",791,791,661,0.84,-31,601,0.79]
[209,"MCKITRICK ELEMENTARY",898,898,0,0,0,873,0.97]
[106,"MENDENHALL ELEMENTARY",816,816,913,1.12,0,660,0.81]
[108,"MILES ELEMENTARY",662,662,467,0.71,0,546,0.82]
[109,"MINTZ ELEMENTARY",1065,1065,1543,1.45,-105,885,0.92]
[110,"MITCHELL ELEMENTARY",500,500,559,1.12,0,564,1.13]
[111,"MORGAN WOODS ELEMENTARY",616,616,690,1.12,128,712,0.96]
[112,"MORT ELEMENTARY",911,911,830,0.91,-8,662,0.73]
[113,"NORTHWEST ELEMENTARY",924,924,897,0.97,-40,783,0.89]
[114,"OAK GROVE ELEMENTARY",986,986,0,0,0,805,0.82]
[115,"OAK PARK ELEMENTARY",740,740,630,0.85,-19,553,0.77]
[117,"PALM RIVER ELEMENTARY",727,727,547,0.75,-14,536,0.75]
[118,"PINECREST ELEMENTARY",775,775,689,0.89,0,682,0.88]
[202,"PIZZO ELEMENTARY ",1006,1006,946,0.94,0,894,0.89]
[3521,"POTTER ELEMENTARY ",396,396,198,null,300,690,0.99]
[208,"PRIDE ELEMENTARY",891,891,623,0.7,0,865,0.97]
[124,"RIVERHILLS ELEMENTARY",691,691,447,0.65,0,480,0.69]
[125,"RIVERVIEW ELEMENTARY",845,845,980,1.16,180,786,0.77]
[126,"ROBINSON ELEMENTARY",837,837,665,0.79,-39,582,0.73]
[128,"ROBLES ELEMENTARY",1035,1035,689,0.67,-200,761,0.91]
[132,"ROOSEVELT ELEMENTARY",463,463,521,1.13,56,495,0.95]
[133,"RUSKIN ELEMENTARY",763,763,737,0.97,37,794,0.99]
[134,"SCHWARZKOPF ELEMENTARY",964,964,1321,1.37,-95,829,0.95]
[135,"SEFFNER ELEMENTARY",926,926,768,0.83,0,683,0.74]
[136,"SEMINOLE ELEMENTARY",734,734,727,0.99,-76,546,0.83]
[137,"SHAW ELEMENTARY",992,992,1001,1.01,-85,864,0.95]
[138,"SHORE ELEMENTARY",467,467,494,1.06,0,470,1.01]
[141,"SPRINGHEAD ELEMENTARY",741,741,730,0.99,0,696,0.94]
[142,"SULPHUR SPRINGS ELEMENTARY",977,977,896,0.92,-51,757,0.82]
[143,"SUMMERFIELD ELEMENTARY",1141,1141,979,0.86,225,890,0.65]
[211,"SYMMES ELEMENTARY",961,961,0,0,0,902,0.94]
[146,"TAMPA BAY BOULEVARD  ELEM",620,620,706,1.14,34,591,0.9]
[147,"TAMPA PALMS ELEMENTARY",1122,1122,1166,1.04,-153,826,0.85]
[148,"TEMPLE TERRACE ELEMENTARY",847,847,751,0.89,-76,782,1.01]
[149,"THONOTOSASSA ELEMENTARY",609,609,738,1.21,0,419,0.69]
[150,"TINKER ELEMENTARY",779,779,560,0.72,0,549,0.7]
[151,"TOWN & COUNTRY ELEMENTARY",682,682,555,0.81,-54,540,0.86]
[153,"TRAPNELL ELEMENTARY",612,612,480,0.78,-19,429,0.72]
[155,"TWIN LAKES ELEMENTARY",947,947,979,1.03,0,862,0.91]
[193,"VALRICO ELEMENTARY",923,923,936,1.01,0,841,0.91]
[157,"WALDEN LAKE ELEMENTARY",1077,1077,1040,0.97,-160,898,0.98]
[null,"WASHINGTON ELEMENTARY ",null,null,0,null,705,510,0.72]
[160,"WEST SHORE ELEMENTARY",372,372,360,0.97,93,367,0.79]
[161,"WEST TAMPA ELEMENTARY",775,775,641,1.72,160,840,0.9]
[201,"WESTCHASE ELEMENTARY",1145,1145,1265,1.63,-207,894,0.95]
[164,"WILSON ELEMENTARY",477,477,383,0.8,-28,367,0.82]
[165,"WIMAUMA ELEMENTARY",762,762,602,0.79,-70,562,0.81]
[166,"WITTER ELEMENTARY",945,945,798,0.84,-58,625,0.7]
[167,"WOODBRIDGE ELEMENTARY",969,969,861,0.89,-26,761,0.81]
[168,"YATES ELEMENTARY",830,830,834,1,-23,903,1.12]
[null,"ELEMENTARY B",0,0,0,null,600,516,0.86]
[null,"ELEMENTARY D",0,0,0,null,901,790,0.88]
[null,"ELEMENTARY E",0,0,0,null,961,873,0.91]
[null,"ELEMENTARY M",0,0,0,null,946,920,0.97]
[null,"ELEMENTARY O",0,0,0,null,500,455,0.91]
[null,"ELEMENTARY P",0,0,0,null,941,864,0.92]
[null,"ELEMENTARY R",0,0,0,null,901,886,0.98]
[null,"ELEMENTARY S ",0,0,0,null,961,836,0.87]
[null,"ELEMENTARY T",0,0,0,null,961,787,0.82]
[null,"ELEMENTARY U",0,0,0,null,946,816,0.86]
[null,"ELEMENTARY V",0,0,0,null,941,878,0.93]
[null,"ELEMENTARY W",0,0,0,null,946,748,0.79]
[null,"ELEMENTARY X",0,0,0,null,946,752,0.79]
[null,"ELEMENTARY Y",0,0,0,null,946,742,0.78]
[null,"ELEMENTARY Z",0,0,0,null,946,801,0.85]
[null,"MIDDLE SCHOOLS"]
[1,"ADAMS  MIDDLE",1586,1427,1256,0.88,173,1127,0.7]
[194,"BENITO MIDDLE ",1943,1748,1703,0.97,-435,818,0.62]
[25,"BUCHANAN MIDDLE",1248,1123,1213,1.08,-12,1026,0.92]
[192,"BURNETT MIDDLE",1542,1387,1383,1,-293,1079,0.99]
[29,"BURNS MIDDLE",1516,1364,1441,1.06,-10,1134,0.84]
[42,"COLEMAN MIDDLE  ",1026,923,891,0.97,0,940,1.02]
[207,"DAVIDSEN MIDDLE",1374,1236,1296,1.05,0,1099,0.89]
[39,"DOWDELL MIDDLE ",1149,1034,858,0.83,0,843,0.82]
[53,"EISENHOWER MIDDLE ",1534,1534,1559,1.02,72,1486,0.93]
[107,"FERRELL MIDDLE",890,801,711,0.89,250,836,0.8]
[61,"FRANKLIN MIDDLE",957,861,720,0.84,72,843,0.9]
[70,"GRECO MIDDLE",1471,1323,1238,0.94,72,1064,0.76]
[71,"HILL MIDDLE",1488,1339,1135,0.85,0,1195,0.89]
[97,"MADISON MIDDLE ",1053,947,768,0.81,72,792,0.78]
[101,"MANN MIDDLE ",1395,1255,1107,0.88,72,1075,0.81]
[102,"MARSHALL MIDDLE ",1113,1001,899,0.9,0,823,0.82]
[3,"MEMORIAL MIDDLE",896,806,976,1.21,0,797,0.99]
[19,"MCLANE MIDDLE ",1665,1498,1361,0.91,0,1200,0.8]
[82,"MONROE MIDDLE ",1054,948,626,0.66,-6,592,0.63]
[116,"ORANGE GROVE MIDDLE",660,594,601,1.01,0,586,0.99]
[6,"PIERCE MIDDLE",1543,1389,1041,0.75,0,1066,0.77]
[123,"PROGRESS VILLAGE MIDDLE ",1138,1024,742,0.72,-9,928,0.91]
[206,"RANDALL MIDDLE",1406,1265,1051,0.83,0,1124,0.89]
[203,"RODGERS MIDDLE ",1482,1333,1341,1.01,-179,1186,1.03]
[129,"ROLAND PARK MIDDLE",1129,1016,912,0.9,0,783,0.77]
[60,"SLIGH MIDDLE",1240,1116,1003,0.9,-115,777,0.78]
[16,"STEWART MIDDLE ",1045,940,646,0.69,0,842,0.9]
[121,"TOMLIN MIDDLE ",1691,1522,1314,0.86,0,1319,0.87]
[154,"TURKEY CREEK MIDDLE",1738,1564,1213,0.78,-50,1309,0.86]
[31,"VAN BUREN MIDDLE",1068,961,821,0.85,72,833,0.81]
[195,"WALKER MIDDLE ",1525,1372,1473,1.07,-222,974,0.85]
[158,"WASHINGTON MIDDLE ",705,635,599,0.94,0,0,0]
[152,"WEBB MIDDLE ",1213,1109,999,0.9,72,967,0.82]
[196,"WILLIAMS MIDDLE ",1055,919,828,0.9,0,781,0.85]
[163,"WILSON MIDDLE ",616,554,611,1.1,0,635,1.15]
[169,"YOUNG MIDDLE",1260,1134,623,0.55,0,908,0.8]
[null,"MIDDLE SCHOOL GG",0,0,0,null,1374,1201,0.87]
[null,"MIDDLE SCHOOL JJ",0,0,0,null,1383,1188,0.86]
[null,"MIDDLE SCHOOL KK",0,0,0,null,1338,1230,0.92]
[null,"MIDDLE SCHOOL LL",0,0,0,null,1360,1151,0.85]
[null,"MIDDLE SCHOOL MM",0,0,0,null,1395,1142,0.82]
[null,"MIDDLE SCHOOL NN",0,0,0,null,1360,1194,0.88]
[null,"MIDDLE SCHOOL OO",0,0,0,null,1395,994,0.71]
[null,"HIGH SCHOOLS"]
[214,"ALONSO HIGH",2314,2198,0,0,0,1771,0.81]
[8,"ARMWOOD HIGH",1889,1794,1744,0.97,309,1942,0.92]
[199,"BLAKE HIGH ",2095,1990,1728,0.87,0,1714,0.86]
[140,"BLOOMINGDALE HIGH",2509,2410,2715,1.13,-129,2312,1.01]
[17,"BRANDON HIGH",2335,2218,1768,0.8,-59,1759,0.81]
[35,"CHAMBERLAIN HIGH",2227,2115,2280,1.08,-47,1874,0.91]
[190,"DURANT HIGH",2709,2573,2365,0.92,-125,2095,0.86]
[52,"EAST BAY HIGH ",2309,2186,2059,0.94,-80,1967,0.93]
[63,"GAITHER HIGH",2469,2345,2614,1.11,0,1859,0.79]
[72,"HILLSBOROUGH HIGH",2592,2376,2336,0.98,0,2086,0.88]
[131,"JEFFERSON HIGH",1183,1789,1554,0.87,-73,1498,0.87]
[77,"KING HIGH",2488,2363,2124,0.9,-163,1803,0.82]
[85,"LETO HIGH",2311,2195,2159,0.98,-34,1993,0.92]
[120,"PLANT CITY HIGH",2690,2555,2369,0.93,0,2221,0.87]
[119,"PLANT HIGH",1807,1717,1887,1.1,72,2063,1.15]
[204,"RIVERVIEW HIGH",2261,2264,2482,1.1,0,2327,1.03]
[127,"ROBINSON HIGH",1833,1741,1332,0.77,-27,1404,0.82]
[197,"SICKLES HIGH ",2595,2465,2987,1.21,-124,2265,0.97]
[144,"TAMPA BAY TECHNICAL HIGH",2055,1953,1734,0.89,486,1818,0.75]
[198,"WHARTON HIGH ",2712,2576,2419,0.94,-295,2460,1.08]
[null,"HIGH SCHOOL JJJ",0,0,0,null,2226,2108,0.95]
[null,"MIDDLETON ",0,0,0,null,2393,1902,0.79]
[null,"HIGH SCHOOL LLL ",0,0,0,null,2361,1903,0.81]
[null,"WATERS CENTER ",0,0,0,null,451,470,1.04]
[null,"EAST CTY CAREER CENTER",0,0,0,null,285,392,1.38]
[null,"CAREER CENTER MMM",0,0,0,null,608,521,0.86]
[null,"CAREER CENTER NNN",0,0,0,null,542,520,0.96]
[null,"UNGRADED"]
[null,"CAMINITI ESE",258,258,182,0.71,0,185,0.72]
[null,"CARVER ESE",123,123,124,1.01,0,132,1.07]
[null,"LAVOY ESE",180,180,104,0.58,0,102,0.57]
[null,"MENDEZ ESE",null,null,70,null,null,88]
[null,"PARKHILL ESE",null,null,49,null,null,46]
[null,"PLANT CITY ESE",154,154,95,0.62,46,91,0.46]
["2a.","Hillsborough Total",180960,175142,157067,155.46,31842,179067,0.87]

{"sheet":"Pt 2b","index":4,"n_rows":37,"n_cols":9,"rows_kept":37,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
["2b.",null,"Proposed Location of Planned Facilities"]
[null,1,"New High School GGG (Middleton) (2519 Student Stations) To accommodate growth and students in East Tampa and other areas."]
[null,2,"New High School JJJ (New Tampa Area) (2485 Student Stations) To relieve Wharton High School and accommodate growth in the New Tampa area."]
[null,3,"New High School LLL (Southeast Brandon/Fish Hawk Area) (2314 Student Stations) To relieve Durant High School and accommodate growth in the Fish Hawk area. "]
[null,4,"New High School PPP (South County/Ruskin Area) (2519 Student Stations) To accommodate growth in the South County area."]
[null,5,"New Middle School GG (North County Area) (1527 Student Stations) To relieve Walker and Hill Middle Schools and accommodate growth in the North County area."]
[null,6,"New Middle School JJ (New Tampa Area) (1537 Student Stations) To relieve Benito and Buchanan Middle Schools and relieve growth in the New Tampa area."]
[null,7,"New Middle School KK (S Ruskin Area) (1487 Student Stations) to relieve Eisenhower and Rodgers Middle Schools and accommodate growth in South Hills. County."]
[null,8,"New Middle School LL (Thonotosassa Area) (1511 Student Stations) to relieve Burnett and Tomlin Middle Schools and accommodate growth in East County."]
[null,9,"New Middle School MM (West County Area) (1550 Student Stations) to relieve Davidsen Middle School and accommodate growth in West County."]
[null,10,"New Middle School NN (Valrico Area) (1511 Student Stations) to relieve Burns, Rodgers, Turkey Creek Middle Schools and accommodate growth in East County area."]
[null,11,"New Middle School OO (New Tampa Area) (1550 Student Stations) to relieve Benito Middle School and accommodate growth in the New Tampa area."]
[null,12,"New Elementary School B (East Tampa Area) (600 Student Stations) To relieve Robles & Foster Elementary Schools and accommodate growth in the East Tampa area."]
[null,13,"New Downtown Workplace School C (600 Student Stations) To provide for growth in the downtown area"]
[null,14,"New Elementary School D (Valrico Area) (901 Student Stations) To relieve Valrico and Buckhorn Elementary School and accommodate growth in the Valrico area."]
[null,15,"New Elementary School E (North Brandon Area) (961 Student Stations) To relieve Limona Elementary School and accommodate growth in the North Brandon area."]
[null,16,"New Elementary School M (West County Area) (946 Student Stations) To relieve Westchase Elementary School and accommodate growth in the area."]
[null,17,"New Elementary School O (North County Area) (500 Student Stations) To relieve Mort, Pizzo and Shaw  Elementary Schools and accommodate growth in the area."]
[null,18,"New Elementary School P (South Alafia Area) (941 Student Stations) To relieve Alafia and Lithia Springs Elementary Schools and accommodate growth in the area."]
[null,19,"New Elementary School R (South Riverview Area) (901 Student Stations) To relieve Symmes Elementary School and accommodate growth in the area."]
[null,20,"New Elementary School S (Heritage Isles Area) (961 Student Stations) To relieve Hunters Green Elementary School and accommodate growth in the area."]
[null,21,"New Elementary School T (Big Bend Area) (941 Student Stations) To relieve Apollo Beach Elementary School and accommodate growth in the area."]
[null,22,"New Elementary School U (Northwest Area) (946 Student Stations) To relieve Claywell, Essrig, Cannella, and Crestwood Elementary Schools and accommodate growth in the area."]
[null,23,"New Elementary School V (Rivercrest Area) (941 Student Stations) To relieve Riverview Elementary School and accommodate growth in the area."]
[null,24,"New Elementary School W (New Tampa Area) (946 Student Stations) To relieve Clark and Pride Elementary Schools and accommodate growth in the area."]
[null,25,"New Elementary School X (Van Dyke/Gunn Area) (946 Student Stations) To relieve Elementary M and McKitrick Elementary Schools and accommodate growth in the area."]
[null,26,"New Elementary School Y (Fish Hawk Area) (946 Student Stations) To relieve Bevis Elementary School and accommodate growth in the area."]
[null,27,"New Elementary School Z (Triple Creek Area) (946 Student Stations) To relieve Summerfield Elementary School and accommodate growth in the South County area."]
[null,28,"Adult Center East Replaces Gary Adult."]
[null,29,"Adult Technology Center (Sabal Park) New adult technology center to accommodate technology education needs."]
[null,30,"New South County Area Career Center MMM (South County Area) (640 Student Stations) To accommodate growth and Career Education needs in the area."]
[null,31,"New University Area Career Center NNN (North County Area) (600 Student Stations) To accommodate growth and Career Education needs in the area."]
[null,32,"East County Area Career Center OOO (East County Area) To accommodate growth and Career Education needs in the area."]
[null,33,"Plant City ESE (East County Area) To accommodate ESE student needs in the area. "]

{"sheet":"Pt 2c1","index":5,"n_rows":215,"n_cols":9,"rows_kept":215,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2001-02","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,"ELEMENTARY SCHOOLS"]
[null,"ALAFIA ",16,"HCSB",316,0,0,16,96]
[null,"ALEXANDER ",7,"HCSB",153,0,0,7,42]
[null,"ANDERSON ",0,null,0,0,0,0,0]
[null,"APOLLO BEACH ",0,null,0,0,0,0,0]
[null,"BALLAST POINT ",0,null,0,0,0,0,0]
[null,"BAY CREST ",2,"HCSB",39,0,0,2,12]
[null,"BELLAMY ",5,"HCSB",82,0,0,5,30]
[null,"BEVIS",0,null,0,0,0,0,0]
[null,"BING ",0,null,0,0,0,0,0]
[null,"BOYETTE SPRINGS ",0,null,0,0,0,0,0]
[null,"BROOKER ",9,"HCSB",181,0,0,9,54]
[null,"BROWARD ",4,"HCSB",81,0,0,4,24]
[null,"BRYAN  - PC",1,"HCSB",19,0,0,1,6]
[null,"BRYAN - TAMPA",0,null,0,0,0,0,0]
[null,"BUCKHORN ",1,"HCSB",19,0,0,1,6]
[null,"BURNEY-SIMMONS ",0,null,0,0,0,0,0]
[null,"CAHOON ",0,null,0,0,0,0,0]
[null,"CANNELLA ",5,"HCSB",103,0,0,5,30]
[null,"CARROLLWOOD ",4,"HCSB",40,0,0,4,24]
[null,"CHIARAMONTE ",2,"HCSB",44,0,0,2,12]
[null,"CHILES ",0,null,0,0,0,0,0]
[null,"CITRUS PARK ",5,"HCSB",54,0,0,5,30]
[null,"CLAIR-MEL ",3,"HCSB",58,0,0,3,18]
[null,"CLARK ",0,null,0,0,0,0,0]
[null,"CLAYWELL ",11,"HCSB",158,0,0,11,66]
[null,"CLEVELAND ",0,null,0,0,0,0,0]
[null,"COLSON ",1,"HCSB",25,0,0,1,6]
[null,"CORK ",3,"HCSB",59,0,0,3,18]
[null,"CRESTWOOD ",2,"HCSB",27,0,0,2,12]
[null,"CYPRESS CREEK ",5,"HCSB",59,0,0,5,30]
[null,"DESOTO ",0,null,0,0,0,0,0]
[null,"DICKENSON ",0,null,0,0,0,0,0]
[null,"DOVER ",11,"HCSB",123,0,0,11,66]
[null,"DUNBAR ",0,null,0,0,0,0]
[null,"EDISON ",0,null,0,0,0,0,0]
[null,"EGYPT LAKE ",11,"HCSB",196,0,0,11,66]
[null,"ESSRIG ",8,"HCSB",127,0,0,8,48]
[null,"FOLSOM",6,"HCSB",134,0,0,6,36]
[null,"FOREST HILLS ",0,null,0,0,0,0,0]
[null,"FOSTER ",10,"HCSB",132,0,0,10,60]
[null,"GIBSONTON ",5,"HCSB",102,0,0,5,30]
[null,"GORRIE ",1,"HCSB",24,0,0,1,6]
[null,"GRADY ",3,"HCSB",33,0,0,3,18]
[null,"GRAHAM ",0,null,0,0,0,0,0]
[null,"HUNTERS GREEN ",0,null,0,0,0,0,0]
[null,"JACKSON ",3,"HCSB",37,0,0,3,18]
[null,"JAMES ELEMENTARY",0,null,0,0,0,0,0]
[null,"JUST",1,"HCSB",19,0,0,1,6]
[null,"KENLY ",0,null,0,0,0,0,0]
[null,"KINGSWOOD ",6,"HCSB",126,0,0,6,36]
[null,"KNIGHTS ",7,"HCSB",129,0,0,7,42]
[null,"LAKE MAGDALENE ELEMENTARY",16,"HCSB",297,0,0,16,96]
[null,"LANIER ",2,"HCSB",49,0,0,2,12]
[null,"LEE ",0,null,0,0,0,0]
[null,"LEWIS ",2,"HCSB",14,0,0,2,12]
[null,"LIMONA",9,"HCSB",141,0,0,9,54]
[null,"LINCOLN ",0,null,0,0,0,0,0]
[null,"LITHIA SPRINGS",7,"HCSB",136,0,0,7,42]
[null,"LOCKHART ",0,null,0,0,0,0,0]
[null,"LOMAX",0,null,0,0,0,0,0]
[null,"LOPEZ ",2,"HCSB",31,0,0,2,12]
[null,"LOWRY",0,null,0,0,0,0,0]
[null,"LUTZ ",0,null,0,0,0,0,0]
[null,"MABRY ",4,"HCSB",53,0,0,4,24]
[null,"MANGO ",0,null,94,0,0,0,0]
[null,"MANHATTAN ",0,null,0,0,0,0,0]
[null,"MANISCALCO ",2,"HCSB",26,0,0,2,12]
[null,"MCDONALD ",2,"HCSB",38,0,0,2,12]
[null,"MCKITRICK",0,null,0,0,0,0,0]
[null,"MENDENHALL ",6,"HCSB",124,0,0,6,36]
[null,"MILES ",0,null,0,0,0,0,0]
[null,"MINTZ ",5,"HCSB",105,0,0,5,30]
[null,"MITCHELL",1,"HCSB",19,0,1,0,6]
[null,"MORGAN WOODS ",4,"HCSB",28,0,0,4,24]
[null,"MORT ",1,"HCSB",8,0,0,1,6]
[null,"NORTHWEST ",2,"HCSB",40,0,0,2,12]
[null,"OAK GROVE  ",0,null,0,0,0,0,0]
[null,"OAK PARK",1,"HCSB",19,0,0,1,6]
[null,"PALM RIVER ",2,"HCSB",14,0,0,2,12]
[null,"PINECREST",0,"HCSB",0,0,0,0,0]
[null,"PIZZO ",0,null,0,0,0,0,0]
[null,"POTTER",0,null,0,0,0,0,0]
[null,"PRIDE",0,null,0,0,0,0,0]
[null,"RIVERHILLS",0,null,0,0,0,0,0]
[null,"RIVERVIEW ",12,"HCSB",80,0,0,12,72]
[null,"ROBINSON ",2,"HCSB",39,0,0,2,12]
[null,"ROBLES ",0,null,0,0,0,0,0]
[null,"ROOSEVELT ",1,"HCSB",24,0,0,1,6]
[null,"RUSKIN ",2,"HCSB",43,0,0,2,12]
[null,"SCHWARZKOPF ",5,"HCSB",95,0,0,5,30]
[null,"SEFFNER ",5,"HCSB",69,0,0,5,30]
[null,"SEMINOLE ",4,"HCSB",76,0,0,4,24]
[null,"SHAW ",5,"HCSB",85,0,0,5,30]
[null,"SHORE ",0,null,0,0,0,0,0]
[null,"SPRINGHEAD ",0,null,0,0,0,0,0]
[null,"SULPHUR SPRINGS",7,"HCSB",137,0,0,7,42]
[null,"SUMMERFIELD",13,"HCSB",225,0,0,13,78]
[null,"SYMMES",0,null,0,0,0,0]
[null,"TAMPA BAY BOULEVARD  ",7,"HCSB",66,0,0,7,42]
[null,"TAMPA PALMS",8,"HCSB",153,0,0,8,48]
[null,"TEMPLE TERRACE ",4,"HCSB",76,0,0,4,24]
[null,"THONOTOSASSA ",0,null,0,0,0,0,0]
[null,"TINKER ",0,null,0,0,0,0,0]
[null,"TOWN & COUNTRY",7,"HCSB",134,0,0,7,42]
[null,"TRAPNELL ",1,"HCSB",19,0,0,1,6]
[null,"TWIN LAKES ",0,null,0,0,0,0,0]
[null,"VALRICO",0,null,0,0,0,0,0]
[null,"WALDEN LAKE",8,"HCSB",160,0,0,8,48]
[null,"WEST TAMPA ",0,null,0,0,0,0,0]
[null,"WESTCHASE",13,"HCSB",207,0,0,13,78]
[null,"WESTSHORE ",3,"HCSB",59,0,0,3,18]
[null,"WILSON ",2,"HCSB",28,0,0,2,12]
[null,"WIMAUMA ",1,"HCSB",20,0,0,1,6]
[null,"WITTER ",3,"HCSB",58,0,0,3,18]
[null,"WOODBRIDGE ",10,"HCSB",174,0,0,10,60]
[null,"YATES",1,"HCSB",23,0,0,1,6]
[null,"ELEMENTARY B",0,null,0,0,0,0,0]
[null,"ELEMENTARY D",0,null,0,0,0,0,0]
[null,"ELEMENTARY E",0,null,0,0,0,0,0]
[null,"ELEMENTARY M",0,null,0,0,0,0,0]
[null,"ELEMENTARY O",0,null,0,0,0,0,0]
[null,"ELEMENTARY P",0,null,0,0,0,0,0]
[null,"ELEMENTARY R",0,null,0,0,0,0,0]
[null,"ELEMENTARY S ",0,null,0,0,0,0,0]
[null,"ELEMENTARY T",0,null,0,0,0,0,0]
[null,"ELEMENTARY U",0,null,0,0,0,0,0]
[null,"ELEMENTARY V",0,null,0,0,0,0,0]
[null,"ELEMENTARY W",0,null,0,0,0,0,0]
[null,"ELEMENTARY X",0,null,0,0,0,0,0]
[null,"ELEMENTARY Y",0,null,0,0,0,0,0]
[null,"ELEMENTARY Z",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOLS"]
[null,"ADAMS ",13,"HCSB",285,0,0,13,78]
[null,"BENITO ",20,"HCSB",483,0,0,20,120]
[null,"BUCHANAN ",5,"HCSB",93,0,0,5,30]
[null,"BURNETT ",13,"HCSB",325,0,0,13,78]
[null,"BURNS ",1,"HCSB",11,0,0,1,6]
[null,"COLEMAN   ",0,null,0,0,0,0,0]
[null,"DAVIDSEN",0,null,0,0,0,0,0]
[null,"DOWDELL",0,null,0,0,0,0,0]
[null,"EISENHOWER  ",3,"HCSB",75,0,0,3,18]
[null,"FERRELL",0,null,0,0,0,0,0]
[null,"FRANKLIN MIDDLE",3,"HCSB",0,0,0,3,18]
[null,"GRECO",2,"HCSB",18,0,0,2,12]
[null,"HILL",0,null,0,0,0,0,0]
[null,"MADISON ",0,null,0,0,0,0]
[null,"MANN  ",3,"HCSB",55,0,0,3,18]
[null,"MARSHALL  ",0,null,0,0,0,0,0]
[null,"MCLANE ",0,null,0,0,0,0,0]
[null,"MONROE ",1,"HCSB",7,0,0,1,6]
[null,"ORANGE GROVE ",0,null,0,0,0,0,0]
[null,"PIERCE ",5,"HCSB",102,0,0,5,30]
[null,"PROGRESS VILLAGE ",0,null,0,0,0,0,0]
[null,"RANDALL",0,null,0,0,0,0,0]
[null,"RODGERS",8,"HCSB",199,0,0,8,48]
[null,"ROLAND PARK ",0,null,0,0,0,0,0]
[null,"SLIGH ",5,"HCSB",125,0,0,5,30]
[null,"STEWART",0,null,0,0,0,0,0]
[null,"TOMLIN ",0,null,0,0,0,0,0]
[null,"TURKEY CREEK",3,"HCSB",55,0,0,3,18]
[null,"VAN BUREN",1,"HCSB",24,0,0,1,6]
[null,"WALKER",14,"HCSB",247,0,0,14,84]
[null,"WASHINGTON (B T)",0,null,0,0,0,0,0]
[null,"WEBB ",1,"HCSB",8,0,0,1,6]
[null,"WILLIAMS ",0,null,0,0,0,0,0]
[null,"WILSON ",0,null,0,0,0,0,0]
[null,"YOUNG ",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL GG",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL JJ",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL KK",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL LL",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL MM",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL NN",0,null,0,0,0,0,0]
[null,"MIDDLE SCHOOL OO",0,null,0,0,0,0,0]
[null,"HIGH SCHOOLS"]
[null,"ALONSO",0,null,0,0,0,0,0]
[null,"ARMWOOD ",6,"HCSB",166,0,0,6,36]
[null,"BLAKE",0,null,0,0,0,0,0]
[null,"BLOOMINGDALE",4,"HCSB",136,0,0,4,24]
[null,"BRANDON ",3,"HCSB",62,0,0,3,18]
[null,"CHAMBERLAIN",3,"HCSB",49,0,0,3,18]
[null,"DURANT ",5,"HCSB",132,0,0,5,30]
[null,"EAST BAY",6,"HCSB",84,0,0,6,36]
[null,"GAITHER ",0,null,0,0,0,0,0]
[null,"HILLSBOROUGH ",0,null,0,0,0,0,0]
[null,"JEFFERSON",5,"HCSB",77,0,0,5,30]
[null,"KING ",7,"HCSB",172,0,0,7,42]
[null,"LETO ",3,"HCSB",36,0,0,3,18]
[null,"PLANT CITY ",10,"HCSB",280,0,0,10,60]
[null,"PLANT ",3,"HCSB",81,3,0,3,18]
[null,"RIVERVIEW ",0,null,0,0,0,0,0]
[null,"ROBINSON ",1,"HCSB",28,0,0,1,6]
[null,"SICKLES ",5,"HCSB",131,0,0,5,30]
[null,"TAMPA BAY TECH",14,"HCSB",365,0,0,14,84]
[null,"WHARTON",13,"HCSB",311,0,0,13,78]
[null,"HIGH SCHOOL JJJ",0,null,0,0,0,0,0]
[null,"MIDDLETON ",0,null,0,0,0,0,0]
[null,"HIGH SCHOOL LLL ",0,null,0,0,0,0,0]
[null,"WATERS CENTER ",0,null,0,0,0,0,0]
[null,"EAST CTY CAREER CENTER",0,null,0,0,0,0,0]
[null,"CAREER CENTER MMM",0,null,0,0,0,0,0]
[null,"CAREER CENTER NNN",0,null,0,0,0,0,0]
[null,"OTHER FACILITIES"]
[null,"CAMINITI EXCEPT",0,null,0,0,0,0,0]
[null,"LAVOY EXCEPT",5,"HCSB",38,0,0,5,30]
[null,"MACFARLANE",4,"HCSB",109,0,0,4,24]
["2c1.","Hillsborough Total",548,null,10354,3,1,543,"Avg Age 5.96"]

{"sheet":"Pt 2c2","index":6,"n_rows":182,"n_cols":9,"rows_kept":182,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06","5 YEAR TOTAL"]
[null,"ELEMENTARY SCHOOLS"]
[null,"ALAFIA ",16,16,0,0,0,0,16]
[null,"ALEXANDER ",7,0,7,0,0,0,7]
[null,"ANDERSON ",0,0,0,0,0,0,0]
[null,"APOLLO BEACH ",0,0,0,0,0,0,0]
[null,"BALLAST POINT ",0,0,0,0,0,0,0]
[null,"BAY CREST ",2,0,2,0,0,0,2]
[null,"BELLAMY ",5,0,0,5,0,0,5]
[null,"BEVIS ",0,0,0,0,0,0,0]
[null,"BING ",0,0,0,0,0,0,0]
[null,"BOYETTE SPRINGS ",0,0,0,0,0,0,0]
[null,"BROOKER ",9,9,0,0,0,0,9]
[null,"BROWARD ",4,0,4,0,0,0,4]
[null,"BRYAN  - PC",1,1,0,0,0,0,1]
[null,"BRYAN - TAMPA",0,0,0,0,0,0,0]
[null,"BUCKHORN ",1,0,1,0,0,0,1]
[null,"BURNEY-SIMMONS ",0,0,0,0,0,0,0]
[null,"CAHOON ",0,0,0,0,0,0,0]
[null,"CANNELLA ",5,0,5,0,0,0,5]
[null,"CARROLLWOOD ",4,0,0,0,4,0,4]
[null,"CHIARAMONTE ",2,0,0,0,2,0,2]
[null,"CHILES",0,0,0,0,0,0,0]
[null,"CITRUS PARK ",5,0,0,5,0,0,5]
[null,"CLAIR-MEL ",3,3,0,0,0,0,3]
[null,"CLARK ",0,0,0,0,0,0,0]
[null,"CLAYWELL ",11,11,0,0,0,0,11]
[null,"CLEVELAND ",0,0,0,0,0,0,0]
[null,"COLSON ",1,1,0,0,0,0,1]
[null,"CORK ",3,0,0,3,0,0,3]
[null,"CRESTWOOD ",2,0,2,0,0,0,2]
[null,"CYPRESS CREEK ",5,0,5,0,0,0,5]
[null,"DESOTO ",0,0,0,0,0,0,0]
[null,"DICKENSON ",0,0,0,0,0,0,0]
[null,"DOVER ",11,11,0,0,0,0,11]
[null,"DUNBAR ",0,0,0,0,0,0,0]
[null,"EDISON ",0,0,0,0,0,0,0]
[null,"EGYPT LAKE ",11,11,0,0,0,0,11]
[null,"ESSRIG ",8,0,8,0,0,0,8]
[null,"FOLSOM",6,0,0,6,0,0,6]
[null,"FOREST HILLS ",0,0,0,0,0,0,0]
[null,"FOSTER ",10,10,0,0,0,0,10]
[null,"GIBSONTON ",5,5,0,0,0,0,5]
[null,"GORRIE ",1,1,0,0,0,0,1]
[null,"GRADY ",3,3,0,0,0,0,3]
[null,"GRAHAM ",0,0,0,0,0,0,0]
[null,"HUNTERS GREEN ",0,0,0,0,0,0,0]
[null,"JACKSON ",3,3,0,0,0,0,3]
[null,"JAMES CENTER",0,0,0,0,0,0,0]
[null,"JUST",1,0,1,0,0,0,1]
[null,"KENLY ",0,0,0,0,0,0,0]
[null,"KINGSWOOD ",6,0,0,6,0,0,6]
[null,"KNIGHTS ",7,0,0,7,0,0,7]
[null,"LAKE MAGDALENE ",16,0,0,0,16,0,16]
[null,"LANIER ",2,0,0,2,0,0,2]
[null,"LEE ",0,0,0,0,0,0,0]
[null,"LEWIS ",2,0,2,0,0,0,2]
[null,"LIMONA",9,0,9,0,0,0,9]
[null,"LINCOLN ",0,0,0,0,0,0,0]
[null,"LITHIA SPRINGS",7,7,0,0,0,0,7]
[null,"LOCKHART ",0,0,0,0,0,0,0]
[null,"LOMAX",0,0,0,0,0,0,0]
[null,"LOPEZ ",2,2,0,0,0,0,2]
[null,"LOWRY",0,0,0,0,0,0,0]
[null,"LUTZ ",0,0,0,0,0,0,0]
[null,"MABRY ",4,4,0,0,0,0,4]
[null,"MANGO ",0,0,0,0,0,0,0]
[null,"MANHATTAN ",0,0,0,0,0,0,0]
[null,"MANISCALCO ",2,0,0,2,0,0,2]
[null,"MCDONALD ",2,0,0,2,0,0,2]
[null,"MCKITRICK",0,0,0,0,0,0,0]
[null,"MENDENHALL ",6,6,0,0,0,0,6]
[null,"MILES ",0,0,0,0,0,0,0]
[null,"MINTZ ",5,0,5,0,0,0,5]
[null,"MITCHELL",1,0,0,1,0,0,1]
[null,"MORGAN WOODS ",4,4,0,0,0,0,4]
[null,"MORT ",1,0,1,0,0,0,1]
[null,"NORTHWEST ",2,0,2,0,0,0,2]
[null,"OAK GROVE  ",0,0,0,0,0,0,0]
[null,"OAK PARK",1,0,0,1,0,0,1]
[null,"PALM RIVER ",2,0,0,2,0,0,2]
[null,"PINECREST",0,0,0,0,0,0,0]
[null,"PIZZO ",0,0,0,0,0,0,0]
[null,"PRIDE",0,0,0,0,0,0,0]
[null,"RIVERHILLS",0,0,0,0,0,0,0]
[null,"RIVERVIEW ",12,12,0,0,0,0,12]
[null,"ROBINSON ",2,2,0,0,0,0,2]
[null,"ROBLES ",0,0,0,0,0,0,0]
[null,"ROOSEVELT ",1,0,0,1,0,0,1]
[null,"RUSKIN ",2,0,0,2,0,0,2]
[null,"SCHWARZKOPF ",5,0,0,5,0,0,5]
[null,"SEFFNER ",5,0,0,5,0,0,5]
[null,"SEMINOLE ",4,0,0,4,0,0,4]
[null,"SHAW ",5,0,5,0,0,0,5]
[null,"SHORE ",0,0,0,0,0,0,0]
[null,"SPRINGHEAD ",0,0,0,0,0,0,0]
[null,"SULPHUR SPRINGS",7,0,0,7,0,0,7]
[null,"SUMMERFIELD ",13,0,13,0,0,0,13]
[null,"SYMMES",0,0,0,0,0,0,0]
[null,"TAMPA BAY BOULEVARD  ",7,7,0,0,0,0,7]
[null,"TAMPA PALMS",8,8,0,0,0,0,8]
[null,"TEMPLE TERRACE ",4,0,0,4,0,0,4]
[null,"THONOTOSASSA ",0,0,0,0,0,0,0]
[null,"TINKER ",0,0,0,0,0,0,0]
[null,"TOWN & COUNTRY",7,7,0,0,0,0,7]
[null,"TRAPNELL ",1,0,0,1,0,0,1]
[null,"TWIN LAKES ",0,0,0,0,0,0,0]
[null,"VALRICO",0,0,0,0,0,0,0]
[null,"WALDEN LAKE",8,8,0,0,0,0,8]
[null,"WEST TAMPA ",0,0,0,0,0,0,0]
[null,"WESTCHASE",13,13,0,0,0,0,13]
[null,"WESTSHORE ",3,3,0,0,0,0,3]
[null,"WILSON ",2,2,0,0,0,0,2]
[null,"WIMAUMA ",1,0,0,1,0,0,1]
[null,"WITTER ",3,0,3,0,0,0,3]
[null,"WOODBRIDGE ",10,0,10,0,0,0,10]
[null,"YATES",1,0,0,1,0,0,1]
[]
[null,"MIDDLE SCHOOLS"]
[null,"ADAMS ",13,0,0,13,0,0,13]
[null,"BENITO ",20,20,0,0,0,0,20]
[null,"BUCHANAN ",5,5,0,0,0,0,5]
[null,"BURNETT ",13,0,13,0,0,0,13]
[null,"BURNS ",1,0,1,0,0,0,1]
[null,"COLEMAN   ",0,0,0,0,0,0,0]
[null,"DAVIDSEN",0,0,0,0,0,0,0]
[null,"DOWDELL",0,0,0,0,0,0,0]
[null,"EISENHOWER  ",3,0,0,3,0,0,3]
[null,"FERRELL",0,0,0,0,0,0,0]
[null,"FRANKLIN ",3,0,0,3,0,0,3]
[null,"GRECO",2,0,2,0,0,0,2]
[null,"HILL",0,0,0,0,0,0,0]
[null,"MADISON ",0,0,0,0,0,0,0]
[null,"MANN  ",3,0,0,3,0,0,3]
[null,"MARSHALL  ",0,0,0,0,0,0,0]
[null,"MCLANE ",0,0,0,0,0,0,0]
[null,"MONROE ",1,0,0,1,0,0,1]
[null,"ORANGE GROVE ",0,0,0,0,0,0,0]
[null,"PIERCE ",5,0,0,5,0,0,5]
[null,"PROGRESS VILLAGE ",0,0,0,0,0,0,0]
[null,"RANDALL",0,0,0,0,0,0,0]
[null,"RODGERS ",8,0,0,8,0,0,8]
[null,"ROLAND PARK ",0,0,0,0,0,0,0]
[null,"SLIGH ",5,0,5,0,0,0,5]
[null,"STEWART",0,0,0,0,0,0,0]
[null,"TOMLIN ",0,0,0,0,0,0,0]
[null,"TURKEY CREEK",3,3,0,0,0,0,3]
[null,"VAN BUREN",1,0,1,0,0,0,1]
[null,"WALKER",14,14,0,0,0,0,14]
[null,"WASHINGTON (B T)",0,0,0,0,0,0,0]
[null,"WEBB ",1,0,0,1,0,0,1]
[null,"WILSON ",0,0,0,0,0,0,0]
[null,"YOUNG ",0,0,0,0,0,0,0]
[null,"HIGH SCHOOLS"]
[null,"ALONSO",0,0,0,0,0,0,0]
[null,"ARMWOOD ",6,0,6,0,0,0,6]
[null,"BLAKE ",0,0,0,0,0,0,0]
[null,"BLOOMINGDALE",4,0,4,0,0,0,4]
[null,"BRANDON ",3,3,0,0,0,0,3]
[null,"CHAMBERLAIN",3,3,0,0,0,0,3]
[null,"DURANT ",5,5,0,0,0,0,5]
[null,"EAST BAY",6,0,0,6,0,0,6]
[null,"GAITHER ",0,0,0,0,0,0,0]
[null,"HILLSBOROUGH ",0,0,0,0,0,0,0]
[null,"JEFFERSON",5,5,0,0,0,0,5]
[null,"KING ",7,7,0,0,0,0,7]
[null,"LETO ",3,3,0,0,0,0,3]
[null,"PLANT CITY ",10,0,0,10,0,0,10]
[null,"PLANT ",3,3,0,0,0,0,3]
[null,"RIVERVIEW ",0,0,0,0,0,0,0]
[null,"ROBINSON ",1,1,0,0,0,0,1]
[null,"SICKLES ",5,5,0,0,0,0,5]
[null,"TAMPA BAY TECH",14,14,0,0,0,0,14]
[null,"WHARTON",13,13,0,0,0,0,13]
[null,"OTHER FACILITIES"]
[null,"CAMINITI EXCEPT",0,0,0,0,0,0,0]
[null,"LAVOY EXCEPT",5,0,5,0,0,0,5]
[null,"MACFARLANE",4,4,0,0,0,0,4]
["2c2.","Hillsborough Total",548,278,122,126,22,0,548]

{"sheet":"Pt 2c3 c4 2d","index":7,"n_rows":53,"n_cols":9,"rows_kept":53,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[".",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,"Bryan, PC",4,"GE Capital",80,1,0,0,0]
[null,"Clair Mel",8,"GE Capital",168,1,0,0,0]
[null,"Claywell",10,"GE Capital",210,1,0,0,0]
[null,"Dover ",8,"WmScot",64,1,0,0,0]
[null,"Grady",6,"WmScot",126,1,0,0,0]
[null,"Graham",4,"WmScot",84,1,0,0,0]
[null,"Jackson",12,"WmScot",252,1,0,0,0]
[null,"Limona",6,"WmScot",126,2,0,0,0]
[null,"Lutz",18,"GE Capital",360,2,0,0,0]
[null,"Mabry",4,"WmScot",84,1,0,0,0]
[null,"Robles",15,"GE Capital",300,2,0,0,0]
[null,"Ruskin",3,"GE Capital",60,1,0,0,0]
[null,"Symmes",12,"WmScot",240,1,0,0,0]
[null,"West Shore",6,"WmScot",120,1,0,0,0]
[null,"West Tampa",13,"GE Capital",260,1,0,0,0]
[null,"Westchase ",9,"GE Capital",180,1,0,0,0]
[null,"Buchanan",52,"GE Capital",1223,2,0,0,0]
[null,"Davidsen",8,"WmScot",224,1,0,0,0]
[null,"Chamberlain",34,"GE Capital",1088,1,0,0,0]
[null,"Durant",14,"GE Capital",448,1,0,0,0]
[null,"Leto",7,"GE Capital",224,2,0,0,0]
[null,"Plant",31,"GE Capital",992,1,0,0,0]
[null,"Robinson",12,"GE Capital",384,1,0,0,0]
[null,"Gaither",9,"WmScot",288,1,0,0,0]
[null,"MacFarlane",25,"GE Capital",500,1,0,0,0]
["2c3.","Hillsborough Total",330,0,8005,29,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"EASTSIDE MC","5 PERMANENT/6 RELOCATABLE","GLORIOUS CH","1997-98",250,250,9,300]
[null,"METRO MINISTRIES","1 PERMANENT","METRO MIN","1998-99",45,43,1,30]
[null,"RICHARDSON","10 PERMANENT","HORATIO ARIAS","1997-98",145,145,9,275]
[null,"TAMPA BAY ACADEMY","15 PERMANENT/4 RELOCATABLE","TBA","1997-98",160,156,9,400]
[null,"TAMPA UNITED METHODIST","17 PERMANENT","TUMC","1998-99",306,285,3,450]
[null,"TERRACE COMM","13 PERMANENT","LB SOWELL","1998-99",240,240,10,260]
[null,"USF","8 PERMANENT","MOSI","1998-99",null,160,5,170]
[null,"PEPIN ACADEMY","14 PERMANENT ","MARY HELP  ","1999-00",140,140,3,200]
[null,"REBIRTH","11 PERMANENT","REBIRTH","1999-00",132,92,3,130]
[null,"TRINITY","15 PERMANENT","N ROME BAP ","1999-00",356,356,9,500]
[null,"LEARNING GATE","6 PERMANENT/4 RELOCATABLE","Patti Girard","2000-01",210,195,4,360]
[null,"RCMA","4 PERMANENT","RCMA","2000-01",100,65,4,150]
[null,"VILLAGE OF EXCELLENCE","7 PERMANENT","Bible Based Fellowship of Temple Terrace","2000-01",100,100,4,215]
[null,"CENTRAL CITY ","6 PERMANENT","Central Park Village Youth Services","2001-02",130,125,5,500]
[null,"NORTH TAMPA ALT.  ","11 RELOCATABLE","Chancellor Academies","2001-02",220,130,10,150]
["2c4.","Hillsborough Total",73,null,null,2534,2482,88,4090]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]

{"sheet":"Pt 2e","index":8,"n_rows":213,"n_cols":9,"rows_kept":213,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"ELEMENTARY SCHOOLS"]
[14,"ALAFIA ELEMENTARY ",47,1160,1253,26.66,779,-16,25.13]
[5,"ALEXANDER ELEMENTARY",42,906,758,18.05,682,-3,17.49]
[7,"ANDERSON ELEMENTARY",20,474,460,23,439,0,21.95]
[9,"APOLLO BEACH ELEMENTARY",28,745,616,22,737,0,26.32]
[10,"BALLAST POINT ELEMENTARY",21,468,412,19.62,410,0,19.52]
[12,"BAY CREST ELEMENTARY",39,861,815,20.9,757,-2,20.46]
[69,"BELLAMY ELEMENTARY",33,816,812,24.61,671,-5,23.96]
[205,"BEVIS ELEMENTARY",34,837,320,9.41,890,0,26.18]
[13,"BING ELEMENTARY",36,938,686,19.06,704,0,19.56]
[18,"BOYETTE SPRINGS ELEMENTARY",33,857,996,30.18,929,0,28.15]
[21,"BROOKER ELEMENTARY",44,1026,977,22.2,1013,-9,28.94]
[22,"BROWARD ELEMENTARY",25,527,589,23.56,462,4,15.93]
[24,"BRYAN ELEM - PC",31,707,845,27.26,680,9,17]
[26,"BUCKHORN ELEMENTARY",33,878,902,27.33,669,-1,20.91]
[641,"BURNEY SIMMONS",null,null,0,null,406,10]
[30,"CAHOON ELEMENTARY",29,655,615,21.21,630,0,21.72]
[32,"CANNELLA ELEMENTARY",38,790,985,25.92,818,-5,24.79]
[33,"CARROLLWOOD ELEMENTARY",31,706,723,23.32,682,-4,25.26]
[36,"CHIARAMONTE ELEMENTARY",23,521,423,18.39,453,-2,21.57]
[210,"CHILES ELEMENTARY ",33,816,0,0,941,0,28.52]
[37,"CITRUS PARK ELEMENTARY",35,173,743,21.23,571,-5,19.03]
[38,"CLAIR-MEL ELEMENTARY",33,764,703,21.3,644,3,17.89]
[200,"CLARK ELEMENTARY",27,902,894,33.11,781,0,28.93]
[40,"CLAYWELL ELEMENTARY",38,878,968,25.47,971,1,24.9]
[41,"CLEVELAND ELEMENTARY",30,435,431,14.37,322,0,10.73]
[43,"COLSON ELEMENTARY",33,847,634,19.21,688,-1,21.5]
[45,"CORK ELEMENTARY",28,709,819,29.25,774,1,26.69]
[46,"CRESTWOOD ELEMENTARY",41,931,1054,25.71,860,-2,22.05]
[47,"CYPRESS CREEK ELEMENTARY",37,915,814,22,891,-5,27.84]
[48,"DESOTO ELEMENTARY",18,219,299,16.61,375,6,15.63]
[49,"DICKENSON ELEMENTARY",33,752,663,20.09,699,0,21.18]
[50,"DOVER ELEMENTARY",39,907,648,16.62,674,0,17.28]
[4251,"DOWNTOWN",6,130,161,26.83,174,0,29]
[51,"DUNBAR ELEMENTARY",17,327,420,24.71,451,0,26.53]
[54,"EDISON ELEMENTARY",23,526,385,16.74,691,6,23.83]
[55,"EGYPT LAKE ELEMENTARY",32,705,886,27.69,461,-11,21.95]
[57,"ESSRIG ELEMENTARY",40,930,1018,25.45,995,8,20.73]
[58,"FOLSOM ELEMENTARY ",39,989,899,23.05,864,0,22.15]
[2,"FOREST HILLS ELEMENTARY",38,927,899,23.66,859,0,22.61]
[59,"FOSTER ELEMENTARY",39,856,605,15.51,549,-10,18.93]
[65,"GIBSONTON ELEMENTARY",38,842,606,15.95,668,-5,20.24]
[66,"GORRIE ELEMENTARY",21,434,558,26.57,549,5,21.12]
[67,"GRADY ELEMENTARY",22,523,455,20.68,518,1,22.52]
[68,"GRAHAM ELEMENTARY",18,438,351,19.5,533,6,22.21]
[73,"HUNTERS GREEN ELEMENTARY",34,900,750,22.06,732,0,21.53]
[74,"JACKSON ELEMENTARY",19,426,376,19.79,377,2,17.95]
[4747,"JAMES ELEMENTARY",{"$nulls":4},853,14]
[282,"JUST ELEMENTARY",null,null,119,null,589,13]
[76,"KENLY ELEMENTARY",27,608,530,19.63,349,0,12.93]
[78,"KINGSWOOD ELEMENTARY",35,830,823,23.51,639,2,17.27]
[79,"KNIGHTS ELEMENTARY",35,857,746,21.31,744,-3,23.25]
[80,"LAKE MAGDALENE ELEMENTARY",55,1257,996,18.11,801,-16,20.54]
[81,"LANIER ELEMENTARY",25,615,504,20.16,483,-2,21]
[84,"LEE ELEMENTARY",18,409,449,24.94,452,0,25.11]
[88,"LEWIS ELEMENTARY",32,763,904,28.25,787,4,21.86]
[86,"LIMONA ELEMENTARY",43,969,899,20.91,742,-9,21.82]
[87,"LINCOLN ELEMENTARY",20,467,449,22.45,442,0,22.1]
[89,"LITHIA SPRINGS ELEMENTARY",40,1007,961,24.03,797,-7,24.15]
[44,"LOCKHART ELEMENTARY",37,816,396,10.7,753,0,20.35]
[2521,"LOMAX ELEMENTARY",17,337,193,11.35,543,0,31.94]
[92,"LOPEZ ELEMENTARY",36,915,565,15.69,645,11,13.72]
[93,"LOWRY ELEMENTARY",30,800,793,26.43,840,-2,30]
[94,"LUTZ ELEMENTARY",30,668,647,21.57,613,0,20.43]
[95,"MABRY ELEMENTARY",25,638,701,28.04,711,0,28.44]
[98,"MANGO ELEMENTARY",39,886,832,21.33,633,0,16.23]
[99,"MANHATTAN ELEMENTARY",27,595,184,6.81,186,0,6.89]
[100,"MANISCALCO ELEMENTARY",31,819,785,25.32,754,-2,26]
[103,"MCDONALD ELEMENTARY",30,761,639,21.3,601,-2,21.46]
[209,"MCKITRICK ELEMENTARY ",34,834,0,0,873,0,25.68]
[106,"MENDENHALL ELEMENTARY",32,793,924,28.88,660,-6,25.38]
[108,"MILES ELEMENTARY",28,635,466,16.64,546,0,19.5]
[109,"MINTZ ELEMENTARY",39,1005,1528,39.18,885,-5,26.03]
[110,"MITCHELL ELEMENTARY",25,500,559,22.36,564,-1,23.5]
[111,"MORGAN WOODS ELEMENTARY",26,564,651,25.04,712,2,25.43]
[112,"MORT ELEMENTARY",39,903,801,20.54,662,-1,17.42]
[113,"NORTHWEST ELEMENTARY",34,895,897,26.38,783,-2,24.47]
[114,"OAK GROVE ELEMENTARY",40,925,0,0,805,0,20.13]
[115,"OAK PARK ELEMENTARY",29,721,588,20.28,553,-1,19.75]
[117,"PALM RIVER ELEMENTARY",36,701,491,13.64,536,-2,15.76]
[118,"PINECREST ELEMENTARY",31,760,687,22.16,682,0,22]
[202,"PIZZO ELEMENTARY ",39,947,921,23.62,894,0,22.92]
[3521,"POTTER ELEMENTARY",null,null,197,null,690,12]
[208,"PRIDE ELEMENTARY",34,843,613,0,865,0,25.44]
[124,"RIVERHILLS ELEMENTARY",31,703,391,12.61,786,0,25.35]
[125,"RIVERVIEW ELEMENTARY",32,845,926,28.94,786,0,24.56]
[126,"ROBINSON ELEMENTARY",38,897,592,15.58,582,-2,16.17]
[128,"ROBLES ELEMENTARY",40,931,681,17.03,761,0,19.03]
[132,"ROOSEVELT ELEMENTARY",21,462,426,20.29,495,3,20.63]
[133,"RUSKIN ELEMENTARY",35,767,737,21.06,794,2,21.46]
[134,"SCHWARZKOPF ELEMENTARY",37,950,1320,27,829,-5,25.91]
[135,"SEFFNER ELEMENTARY",38,912,708,18.63,683,-5,20.7]
[136,"SEMINOLE ELEMENTARY",33,726,588,17.82,546,-4,18.83]
[137,"SHAW ELEMENTARY",45,964,940,20.89,864,-5,21.6]
[138,"SHORE ELEMENTARY",19,454,490,25.79,570,0,30]
[141,"SPRINGHEAD ELEMENTARY",31,741,730,23.55,696,0,22.45]
[142,"SULPHUR SPRINGS ELEMENTARY",42,1033,831,19.79,757,-7,21.63]
[143,"SUMMERFIELD ELEMENTARY",45,1092,931,20.69,890,-13,27.81]
[211,"SYMMES ELEMENTARY",34,876,0,0,902,0,26.53]
[146,"TAMPA BAY BOULEVARD  ELEM",26,544,632,24.31,591,-3,25.7]
[147,"TAMPA PALMS ELEMENTARY",42,1025,1108,26.38,826,-8,24.29]
[148,"TEMPLE TERRACE ELEMENTARY",35,822,738,21.09,782,-4,25.23]
[149,"THONOTOSASSA ELEMENTARY",27,585,427,15.81,419,0,15.52]
[150,"TINKER ELEMENTARY",34,779,550,16.18,549,0,16.15]
[151,"TOWN & COUNTRY ELEMENTARY",32,682,554,17.31,540,-3,18.62]
[153,"TRAPNELL ELEMENTARY",24,578,479,19.96,429,-1,18.65]
[155,"TWIN LAKES ELEMENTARY",38,977,979,25.76,862,0,22.68]
[193,"VALRICO ELEMENTARY",35,890,848,24.23,841,0,24.03]
[157,"WALDEN LAKE ELEMENTARY",42,1047,1002,23.86,898,-8,26.41]
[4601,"WASHINGTON ELEMENTARY",{"$nulls":4},510,0]
[160,"WEST SHORE ELEMENTARY",19,372,366,19.26,367,1,18.35]
[161,"WEST TAMPA ELEMENTARY",25,652,602,24.08,840,8,25.45]
[201,"WESTCHASE ELEMENTARY",50,1065,1252,25.04,894,-13,24.16]
[164,"WILSON ELEMENTARY",21,453,334,15.9,367,-2,19.32]
[165,"WIMAUMA ELEMENTARY",33,740,602,18.24,562,-1,17.56]
[166,"WITTER ELEMENTARY",39,735,798,20.46,625,-3,17.36]
[167,"WOODBRIDGE ELEMENTARY",43,928,753,17.51,761,-6,20.57]
[168,"YATES ELEMENTARY",33,821,784,23.76,903,-1,28.22]
[null,"ELEMENTARY B",null,null,0,null,516,20,25.8]
[null,"ELEMENTARY D",null,null,0,null,790,34,23.24]
[null,"ELEMENTARY E",null,null,0,null,873,34,25.68]
[null,"ELEMENTARY M",null,null,0,null,920,34,27.06]
[null,"ELEMENTARY O",null,null,0,null,455,20,22.75]
[null,"ELEMENTARY P",null,null,0,null,864,34,25.41]
[null,"ELEMENTARY R",null,null,0,null,886,34,26.06]
[null,"ELEMENTARY S ",null,null,0,null,836,34,24.59]
[null,"ELEMENTARY T",null,null,0,null,787,34,23.15]
[null,"ELEMENTARY U",null,null,0,null,816,45,18.13]
[null,"ELEMENTARY V",null,null,0,null,878,34,25.82]
[null,"ELEMENTARY W",null,null,0,null,748,34,22]
[null,"ELEMENTARY X",null,null,0,null,752,34,22.12]
[null,"ELEMENTARY Y",null,null,0,null,742,34,21.82]
[null,"ELEMENTARY Z",null,null,0,null,801,34,23.56]
[null,"MIDDLE SCHOOLS"]
[1,"ADAMS  MIDDLE",62,1415,1231,19.85,1127,-6,20.13]
[194,"BENITO MIDDLE ",64,1649,1650,25.78,818,-20,18.59]
[25,"BUCHANAN MIDDLE",48,1070,1164,24.25,1026,-2,22.3]
[192,"BURNETT MIDDLE",51,1360,1350,26.47,1079,-13,28.39]
[29,"BURNS MIDDLE",56,1343,1428,25.5,1134,-1,20.62]
[42,"COLEMAN MIDDLE  ",38,903,846,22.26,940,0,24.74]
[207,"DAVIDSEN MIDDLE",49,1207,1274,0,1099,0,22.43]
[39,"DOWDELL MIDDLE ",46,1016,837,18.2,843,0,18.33]
[53,"EISENHOWER MIDDLE ",63,1454,1484,23.56,1486,0,23.59]
[107,"FERRELL MIDDLE",33,801,709,21.48,836,11,19]
[61,"FRANKLIN MIDDLE",44,814,672,15.27,843,0,19.16]
[70,"GRECO MIDDLE",56,1276,1173,20.95,1064,1,18.67]
[71,"HILL MIDDLE",49,1317,1092,22.29,1195,0,24.39]
[97,"MADISON MIDDLE ",40,940,741,18.53,792,3,18.42]
[101,"MANN MIDDLE ",55,1210,1035,18.82,1075,0,19.55]
[102,"MARSHALL MIDDLE ",38,992,879,23.13,823,0,21.66]
[19,"MCLANE MIDDLE ",50,1173,1314,26.28,1200,3,22.64]
[3,"MEMORIAL MIDDLE",35,771,918,26.23,797,0,22.77]
[82,"MONROE MIDDLE ",39,917,605,15.51,592,-1,15.58]
[116,"ORANGE GROVE MIDDLE",30,594,590,19.67,586,0,19.53]
[6,"PIERCE MIDDLE",79,1859,1007,12.75,1066,-22,18.7]
[123,"PROGRESS VILLAGE MIDDLE ",41,1006,711,17.34,928,0,22.63]
[206,"RANDALL MIDDLE",49,1189,1050,0,1124,0,22.94]
[203,"ROGERS MIDDLE ",48,1306,1274,26.54,1186,-8,29.65]
[129,"ROLAND PARK MIDDLE",43,1007,884,20.56,783,0,18.21]
[60,"SLIGH MIDDLE",50,1083,954,19.08,777,-5,17.27]
[16,"STEWART MIDDLE ",40,902,623,15.58,842,0,21.05]
[121,"TOMLIN MIDDLE ",71,1586,1294,18.23,1319,0,18.58]
[154,"TURKEY CREEK MIDDLE",54,1364,1154,21.37,1309,-3,25.67]
[31,"VAN BUREN MIDDLE",43,922,763,17.74,833,2,18.51]
[195,"WALKER MIDDLE ",55,1426,1465,28,974,-14,23.76]
[158,"WASHINGTON MIDDLE ",35,635,599,0,0,0,0]
[152,"WEBB MIDDLE ",45,1051,944,20.98,967,2,20.57]
[196,"WILLIAMS MIDDLE ",40,941,765,19.13,781,0,19.53]
[163,"WILSON MIDDLE ",28,545,611,21.82,635,0,22.68]
[169,"YOUNG MIDDLE",51,1134,723,14.18,908,0,17.8]
[null,"MIDDLE SCHOOL GG",null,null,0,null,1201,46,26.11]
[null,"MIDDLE SCHOOL JJ",null,null,0,null,1188,46,25.83]
[null,"MIDDLE SCHOOL KK",null,null,0,null,1230,40,30.75]
[null,"MIDDLE SCHOOL LL",null,null,0,null,1151,46,25.02]
[null,"MIDDLE SCHOOL MM",null,null,0,null,1142,46,24.83]
[null,"MIDDLE SCHOOL NN",null,null,0,null,1194,46,25.96]
[null,"MIDDLE SCHOOL OO",null,null,0,null,994,36,27.61]
[null,"HIGH SCHOOLS"]
[214,"ALONSO HIGH",80,2136,0,0,1771,0,22.14]
[8,"ARMWOOD HIGH",72,1759,1720,23.89,1942,12,23.12]
[199,"BLAKE HIGH ",76,1936,1688,22.21,1714,0,22.55]
[140,"BLOOMINGDALE HIGH",97,2430,2694,27.77,2312,-4,24.86]
[17,"BRANDON HIGH",86,2212,1711,19.9,1759,-3,21.19]
[35,"CHAMBERLAIN HIGH",84,2098,2180,25.95,1874,-3,23.14]
[190,"DURANT HIGH",100,2499,2322,23.22,2095,9,19.22]
[52,"EAST BAY HIGH ",81,2123,1970,24.32,1967,-6,26.23]
[63,"GAITHER HIGH",84,2008,2548,30.33,1859,0,22.13]
[72,"HILLSBOROUGH HIGH",107,2338,2261,21.13,2086,0,19.5]
[131,"JEFFERSON HIGH",65,1767,1476,22.71,1498,-5,24.97]
[77,"KING HIGH",101,2320,2124,21.03,1803,-7,19.18]
[85,"LETO HIGH",97,2157,2089,21.54,1993,-3,21.2]
[119,"PLANT HIGH",67,1538,1860,27.76,2063,-3,32.23]
[120,"PLANT CITY HIGH",113,2756,2289,20.26,2221,-10,21.56]
[204,"RIVERVIEW HIGH",93,2511,2427,26.1,2327,0,25.02]
[127,"ROBINSON HIGH",69,1645,1291,18.71,1404,-1,20.65]
[197,"SICKLES HIGH ",74,2173,2960,40,2265,-5,32.83]
[144,"TAMPA BAY TECHNICAL HIGH",54,867,1696,31.41,1818,-14,45.45]
[198,"WHARTON HIGH ",71,2454,2337,32.92,2460,-13,42.41]
[null,"HIGH SCHOOL JJJ",null,null,0,null,2108,74,28.49]
[null,"MIDDLETON ",null,null,0,null,1902,74,25.7]
[null,"HIGH SCHOOL LLL ",null,null,0,null,1903,74,25.72]
[null,"WATERS CENTER ",null,null,61,null,470,32,14.69]
[null,"EAST CTY CAREER CENTER",null,null,0,null,292]
[null,"CAREER CENTER MMM",null,null,0,null,521,30,17.37]
[null,"CAREER CENTER NNN",null,null,0,null,520]
["2e.","Hillsborough Total",7004,166069,151280,"District Avg 22",179095,847,"District Avg 23"]

{"sheet":"Pt 2f 2g ","index":9,"n_rows":186,"n_cols":16,"rows_kept":186,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06","5 YEAR AVERAGE"]
[null,"ELEMENTARY SCHOOLS",{"$nulls":8},{"$error":"#REF!"}]
[14,"ALAFIA ELEMENTARY ",null,320,0,0,0,0,64]
[5,"ALEXANDER ELEMENTARY",null,140,140,0,0,0,56]
[7,"ANDERSON ELEMENTARY",null,0,0,0,0,0,0]
[9,"APOLLO BEACH ELEMENTARY",null,0,0,0,0,0,0]
[10,"BALLAST POINT ELEMENTARY",null,0,0,0,0,0,0]
[12,"BAY CREST ELEMENTARY",null,40,40,0,0,0,16]
[69,"BELLAMY ELEMENTARY",null,100,100,0,0,0,40]
[13,"BING ELEMENTARY",null,0,0,0,0,0,0]
[18,"BOYETTE SPRINGS ELEMENTARY",null,0,0,0,0,0,0]
[21,"BROOKER ELEMENTARY",null,180,180,0,0,0,72]
[22,"BROWARD ELEMENTARY",null,80,80,0,0,0,32]
[24,"BRYAN ELEM - PC",null,20,0,0,0,0,4]
[26,"BUCKHORN ELEMENTARY",null,20,20,0,0,0,8]
[30,"CAHOON ELEMENTARY",null,0,0,0,0,0,0]
[32,"CANNELLA ELEMENTARY",null,100,100,0,0,0,40]
[33,"CARROLLWOOD ELEMENTARY",null,80,80,80,0,0,48]
[36,"CHIARAMONTE ELEMENTARY",null,40,40,40,0,0,24]
[210,"CHILES ELEMENTARY",null,0,0,0,0,0,0]
[37,"CITRUS PARK ELEMENTARY",null,100,100,100,0,0,60]
[38,"CLAIR-MEL ELEMENTARY",null,60,0,0,0,0,12]
[200,"CLARK ELEMENTARY",null,0,0,0,0,0,0]
[40,"CLAYWELL ELEMENTARY",null,220,0,0,0,0,44]
[41,"CLEVELAND ELEMENTARY",null,68,0,0,0,0,13.6]
[43,"COLSON ELEMENTARY",null,20,0,0,0,0,4]
[45,"CORK ELEMENTARY",null,60,60,60,0,0,36]
[46,"CRESTWOOD ELEMENTARY",null,40,40,0,0,0,16]
[47,"CYPRESS CREEK ELEMENTARY",null,100,100,0,0,0,40]
[48,"DESOTO ELEMENTARY",null,93,0,0,0,0,18.6]
[49,"DICKENSON ELEMENTARY",null,0,0,0,0,0,0]
[50,"DOVER ELEMENTARY",null,220,0,0,0,0,44]
[51,"DUNBAR ELEMENTARY",null,0,0,0,0,0,0]
[54,"EDISON ELEMENTARY",null,0,0,0,0,0,0]
[55,"EGYPT LAKE ELEMENTARY",null,220,0,0,0,0,44]
[57,"ESSRIG ELEMENTARY",null,160,160,0,0,0,64]
[58,"FOLSOM ELEMENTARY ",null,120,120,120,0,0,72]
[2,"FOREST HILLS ELEMENTARY",null,0,0,0,0,0,0]
[59,"FOSTER ELEMENTARY",null,200,0,0,0,0,40]
[65,"GIBSONTON ELEMENTARY",null,100,0,0,0,0,20]
[66,"GORRIE ELEMENTARY",null,20,0,0,0,0,4]
[67,"GRADY ELEMENTARY",null,60,0,0,0,0,12]
[68,"GRAHAM ELEMENTARY",null,0,0,0,0,0,0]
[73,"HUNTERS GREEN ELEMENTARY",null,0,0,0,0,0,0]
[74,"JACKSON ELEMENTARY",null,60,0,0,0,0,12]
[76,"KENLY ELEMENTARY",null,0,0,0,0,0,0]
[78,"KINGSWOOD ELEMENTARY",null,120,120,120,0,0,72]
[79,"KNIGHTS ELEMENTARY",null,140,140,140,0,0,84]
[80,"LAKE MAGDALENE ELEMENTARY",null,320,320,320,0,0,192]
[81,"LANIER ELEMENTARY",null,40,40,40,0,0,24]
[84,"LEE ELEMENTARY",null,0,0,0,0,0,0]
[88,"LEWIS ELEMENTARY",null,40,40,0,0,0,16]
[86,"LIMONA ELEMENTARY",null,180,180,0,0,0,72]
[87,"LINCOLN ELEMENTARY",null,0,0,0,0,0,0]
[89,"LITHIA SPRINGS ELEMENTARY",null,140,0,0,0,0,28]
[44,"LOCKHART ELEMENTARY",null,0,0,0,0,0,0]
[2521,"LOMAX ELEMENTARY",null,0,0,0,0,0,0]
[92,"LOPEZ ELEMENTARY",null,40,0,0,0,0,8]
[93,"LOWRY ELEMENTARY",null,0,0,0,0,0,0]
[94,"LUTZ ELEMENTARY",null,0,0,0,0,0,0]
[95,"MABRY ELEMENTARY",null,80,0,0,0,0,16]
[98,"MANGO ELEMENTARY",null,0,0,0,0,0,0]
[99,"MANHATTAN ELEMENTARY",null,0,0,0,0,0,0]
[100,"MANISCALCO ELEMENTARY",null,40,40,40,0,0,24]
[103,"MCDONALD ELEMENTARY",null,40,40,40,0,0,24]
[209,"MCKITRICK ELEMENTARY",null,0,0,0,0,0,0]
[106,"MENDENHALL ELEMENTARY",null,120,0,0,0,0,24]
[108,"MILES ELEMENTARY",null,0,0,0,0,0,0]
[109,"MINTZ ELEMENTARY",null,100,100,0,0,0,40]
[110,"MITCHELL ELEMENTARY",null,20,20,20,0,0,12]
[111,"MORGAN WOODS ELEMENTARY",null,80,0,0,0,0,16]
[112,"MORT ELEMENTARY",null,20,20,0,0,0,8]
[113,"NORTHWEST ELEMENTARY",null,40,40,0,0,0,16]
[114,"OAK GROVE ELEMENTARY",null,0,0,0,0,0,0]
[115,"OAK PARK ELEMENTARY",null,20,20,20,0,0,12]
[117,"PALM RIVER ELEMENTARY",null,40,40,40,0,0,24]
[118,"PINECREST ELEMENTARY",null,0,0,0,0,0,0]
[202,"PIZZO ELEMENTARY ",null,0,0,0,0,0,0]
[124,"RIVERHILLS ELEMENTARY",null,0,0,0,0,0,0]
[125,"RIVERVIEW ELEMENTARY",null,240,0,0,0,0,48]
[126,"ROBINSON ELEMENTARY",null,40,0,0,0,0,8]
[128,"ROBLES ELEMENTARY",null,0,0,0,0,0,0]
[132,"ROOSEVELT ELEMENTARY",null,20,20,20,0,0,12]
[133,"RUSKIN ELEMENTARY",null,40,40,40,0,0,24]
[134,"SCHWARZKOPF ELEMENTARY",null,100,100,100,0,0,60]
[135,"SEFFNER ELEMENTARY",null,100,100,100,0,0,60]
[136,"SEMINOLE ELEMENTARY",null,80,80,80,0,0,48]
[137,"SHAW ELEMENTARY",null,100,100,0,0,0,40]
[138,"SHORE ELEMENTARY",null,0,0,0,0,0,0]
[141,"SPRINGHEAD ELEMENTARY",null,0,0,0,0,0,0]
[142,"SULPHUR SPRINGS ELEMENTARY",null,140,140,140,0,0,84]
[143,"SUMMERFIELD ELEMENTARY",null,200,200,0,0,0,80]
[211,"SYMMES ELEMENTARY",null,0,0,0,0,0,0]
[146,"TAMPA BAY BOULEVARD  ELEM",null,140,0,0,0,0,28]
[147,"TAMPA PALMS ELEMENTARY",null,160,0,0,0,0,32]
[148,"TEMPLE TERRACE ELEMENTARY",null,80,80,80,0,0,48]
[149,"THONOTOSASSA ELEMENTARY",null,0,0,0,0,0,0]
[150,"TINKER ELEMENTARY",null,0,0,0,0,0,0]
[151,"TOWN & COUNTRY ELEMENTARY",null,140,0,0,0,0,28]
[153,"TRAPNELL ELEMENTARY",null,20,20,20,0,0,12]
[155,"TWIN LAKES ELEMENTARY",null,0,0,0,0,0,0]
[193,"VALRICO ELEMENTARY",null,0,0,0,0,0,0]
[157,"WALDEN LAKE ELEMENTARY",null,160,0,0,0,0,32]
[161,"WEST TAMPA ELEMENTARY",null,0,0,0,0,0,0]
[201,"WESTCHASE ELEMENTARY",null,260,0,0,0,0,52]
[160,"WESTSHORE ELEMENTARY",null,60,0,0,0,0,12]
[164,"WILSON ELEMENTARY",null,40,0,0,0,0,8]
[165,"WIMAUMA ELEMENTARY",null,20,20,20,0,0,12]
[166,"WITTER ELEMENTARY",null,60,60,0,0,0,24]
[167,"WOODBRIDGE ELEMENTARY",null,200,200,0,0,0,80]
[168,"YATES ELEMENTARY",null,20,20,20,0,0,12]
[null,"MIDDLE SCHOOLS"]
[1,"ADAMS  MIDDLE",null,260,260,260,0,0,156]
[194,"BENITO MIDDLE ",null,400,0,0,0,0,80]
[25,"BUCHANAN MIDDLE",null,100,0,0,0,0,20]
[192,"BURNETT MIDDLE",null,260,260,0,0,0,104]
[29,"BURNS MIDDLE",null,20,20,0,0,0,8]
[42,"COLEMAN MIDDLE  ",null,0,0,0,0,0,0]
[1080,"DAVIDSEN MIDDLE ",null,0,0,0,0,0,0]
[39,"DOWDELL MIDDLE ",null,0,0,0,0,0,0]
[53,"EISENHOWER MIDDLE ",null,60,60,60,0,0,36]
[107,"MIDDLETON MIDDLE ",null,0,0,0,0,0,0]
[61,"FRANKLIN MIDDLE",null,60,60,60,0,0,36]
[70,"GRECO MIDDLE",null,40,40,0,0,0,16]
[71,"HILL MIDDLE",null,0,0,0,0,0,0]
[97,"MADISON MIDDLE ",null,0,0,0,0,0,0]
[101,"MANN MIDDLE ",null,60,60,60,0,0,36]
[102,"MARSHALL MIDDLE ",null,0,0,0,0,0,0]
[19,"MCLANE MIDDLE ",null,0,0,0,0,0,0]
[82,"MONROE MIDDLE ",null,20,20,20,0,0,12]
[116,"ORANGE GROVE MIDDLE",null,0,0,0,0,0,0]
[6,"PIERCE MIDDLE",null,100,100,100,0,0,60]
[123,"PROGRESS VILLAGE MIDDLE ",null,0,0,0,0,0,0]
[203,"RODGERS MIDDLE ",null,160,160,160,0,0,96]
[129,"ROLAND PARK MIDDLE",null,0,0,0,0,0,0]
[60,"SLIGH MIDDLE",null,100,100,0,0,0,40]
[16,"STEWART MIDDLE ",null,0,0,0,0,0,0]
[121,"TOMLIN MIDDLE ",null,0,0,0,0,0,0]
[154,"TURKEY CREEK MIDDLE",null,60,0,0,0,0,12]
[31,"VAN BUREN MIDDLE",null,20,20,0,0,0,8]
[195,"WALKER MIDDLE ",null,280,0,0,0,0,56]
[158,"WASHINGTON MIDDLE ",null,0,0,0,0,0,0]
[152,"WEBB MIDDLE ",null,20,20,20,0,0,12]
[196,"WILLIAMS MIDDLE ",null,40,40,0,0,0,16]
[163,"WILSON MIDDLE ",null,38,0,0,0,0,7.6]
[169,"YOUNG MIDDLE",null,0,0,0,0,0,0]
[null,"HIGH SCHOOLS"]
[214,"ALONSO HIGH ",null,60,60,60,0,0,0]
[8,"ARMWOOD HIGH",null,60,60,60,0,0,36]
[199,"BLAKE HIGH ",null,0,0,0,0,0,0]
[140,"BLOOMINGDALE HIGH",null,0,0,0,0,0,0]
[17,"BRANDON HIGH",null,60,60,60,0,0,36]
[35,"CHAMBERLAIN HIGH",null,60,0,0,0,0,12]
[190,"DURANT HIGH",null,100,0,0,0,0,20]
[52,"EAST BAY HIGH ",null,120,120,120,0,0,72]
[63,"GAITHER HIGH",null,0,0,0,0,0,0]
[131,"JEFFERSON HIGH",null,100,0,0,0,0,20]
[77,"KING HIGH",null,140,0,0,0,0,28]
[85,"LETO HIGH",null,60,0,0,0,0,12]
[120,"PLANT CITY HIGH",null,200,200,200,0,0,120]
[119,"PLANT HIGH",null,60,0,0,0,0,12]
[204,"RIVERVIEW HIGH",null,0,0,0,0,0,0]
[127,"ROBINSON HIGH",null,20,0,0,0,0,4]
[197,"SICKLES HIGH ",null,100,0,0,0,0,20]
[144,"TAMPA BAY TECHNICAL HIGH",null,280,0,0,0,0,56]
[198,"WHARTON HIGH ",null,260,0,0,0,0,52]
["2f.","Hillsborough Total students in relocatables by year",null,10859,5420,3040,0,0,3863.8]
[null,"Total number of CO-FTE students projected by year",null,157726,161818,165357,168944,164923,163753.6]
[null,"Percent in relocatables by year",null,0.07,0.03,0.02,0,0,0.02]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"No schools are planned to be closed."]
[]
[]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
[{"$nulls":9},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[{"$nulls":9},2,88,90,180,7226,13517,18473]
[{"$nulls":9},3,117,130,144,16957,19232,21507]

{"sheet":"Pt 3","index":10,"n_rows":63,"n_cols":16,"rows_kept":63,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
[]
[]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863, avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02 ","2001-02 ","2001-02 ","2001-02 ","2001-02 ","2000 State Avg","2000 State Avg","2000  Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New High School GGG Middleton High School ",3,37683684,2519,242357,96.21,68,128,222,14959.78,14900,18106,26448]
[null,"New High School JJJ New Tampa Area High School  ",3,38561861,2485,254000,102.21,68,128,222,15517.85,14900,18106,26448]
[null,"New High School LLL Southeast Brandon/Fish Hawk Area High School  ",3,38789932,2314,232107,100.31,68,128,222,16763.15,14900,18106,26448]
[null,"New Middle School GG North County Area Middle School ",2,16341256,1537,129434,84.21,86,113,165,10631.92,9863,13571,18853]
[null,"New Middle School JJ New Tampa Area Middle School ",2,17739281,1537,118827,77.31,86,113,165,11541.5,9863,13571,18853]
[null,"New Middle School MM West County Area Middle School ",2,17539768,1550,132842,85.7,86,113,165,11315.98,9863,13571,18853]
[null,"New Middle School NN Valrico Area ",2,16644345,1511,128536,85.07,86,113,165,11015.45,9863,13571,18853]
[null,"New Elem. Schol M\nWest County Area Elementary",1,9956026,946,77203,81.61,79,110,156,10524.34,9213,12712,22844]
[null,"New Elem. School P South Alafia Elementary",1,9586850,941,80402,85.44,79,110,156,10187.94,9213,12712,22844]
[null,"New Elem. School U Bellamy Claywell Area ",1,9456862,946,77023,81.42,79,110,156,9996.68,9213,12712,22844]
[null,"New Elem. School V Rivercrest Area",1,9319862,941,80356,85.39,79,110,156,9904.21,9213,12712,22844]
[null,"Career Center MMM\nSouth County Career School",0,10769800,640,71606,111.88,0,0,0,16827.81,0,0,0]
[null,"Career Center NNN\nNorth County Career School",0,9994030,600,65877,109.8,0,0,0,16656.72,0,0,0]
[null,"ELEMENTARY SCHOOLS"]
[null,"Alexander Elementary",null,603346,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Broward Elementary",null,1286695,null,null,null,0,0,0,{"$error":"#REF!"},0,0,0]
[null,"Bryan (PC) Elementary",null,1964036,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Burney Simmons Elementary",null,2014000,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Clair Mel Elementary",null,889950,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Claywell Elementary",null,1779667,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"DeSoto Elementary",null,2019091,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Dover Elementary ESE",null,1415126,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Edison Elementary",null,930254,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Gorrie Elementary",null,1325678,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Grady Elementary ",null,557376,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Graham Elementary",null,868548,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Jackson Elementary",null,1608183,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Lewis Elementary",null,1020052,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Lopez Elementary ESE",null,1234459,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Mabry Elementary",null,805720,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Morgan Woods Elementary ",null,1023435,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Riverview Elementary",null,1936346,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Robles  Elementary",null,589746,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Roosevelt Elementary",null,556260,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Ruskin Elementary",null,561731,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Tampa Bay Blvd Elem",null,613010,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Town & Country Elementary",null,560179,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"West Shore Elementary",null,1277700,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"MIDDLE SCHOOLS"]
[null,"Buchanan Middle ",null,1090342,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Ferrell Middle ",null,2221612,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Madison Middle",null,1090342,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Van Buren Middle ",null,1090342,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"HIGH SCHOOLS"]
[null,"Armwood High ",null,2653119,null,null,null,0,0,0,{"$error":"#DIV/0!"},0]
[null,"Durant High",null,1002540,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"OTHER FACILITIES"]
[null,"MacFarlane Center",null,2781982,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Various Sites",null,5847855,null,null,null,0,0,0,{"$error":"#DIV/0!"}]
[null,"Enhanced Hurricane Shelters",null,8998802,null,null,null,0,0,0,{"$error":"#DIV/0!"}]
["3a.","Hillsborough Total 2001-02",null,281754424,18467,1690570,91.55,0,0,0,15257.18]

{"sheet":"Pt 3 b","index":11,"n_rows":38,"n_cols":16,"rows_kept":38,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
[]
[]
[{"$nulls":9},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[{"$nulls":9},2,86,113,165,9863,13571,18853]
[{"$nulls":9},3,68,128,222,14900,18106,26448]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 "," State Avg"," State Avg"," State Avg","2001 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Middle School LL Thonotosassa Area Middle School",2,16773736,1537,129434,84.21,86,113,165,10913.3,9863,13571,18853]
[null,"New Elem. School B East Tampa Area ",1,6774192,600,55098,91.83,79,110,156,11290.32,9213,12712,22844]
[null,"New Elem. School C Downtown Workplace School",1,6576582,600,55098,91.83,79,110,156,10960.97,9213,12712,22844]
[null,"New Elem. School D Valrico Area",1,9459862,901,74034,82.17,79,110,156,10499.29,9213,12712,22844]
[null,"New Elem. School E North Brandon Area ",1,9459862,961,79096,82.31,79,110,156,9843.77,9213,12712,22844]
[null,"New Elem.  School O\nNo County Elem School of Choice",1,5559004,500,55098,110.2,79,110,156,11118.01,9213,12712,22844]
[null,"New Elem. School R Oak Crest Area",1,9319862,901,80356,89.19,79,110,156,10343.91,9213,12712,22844]
[null,"New Elem. School S East Meadows/Heritage Isle Area ",1,9608070,961,77055,80.18,79,110,156,9997.99,9213,12712,22844]
[null,"New Elem. School U North West Area ",1,9459862,946,77023,81.42,79,110,156,9999.85,9213,12712,22844]
[null,"Adult Center East",0,2666912,0,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Adult Technology Center",0,3172050,0,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"James Elementary ",null,2400000,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Just Elementary ",null,1750000,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Lomax Elementary ",null,1955000,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Potter Elementary",null,2474000,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Adams Middle",null,2537778,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Eisenhower Middle ",null,1188478,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Franklin Middle ",null,1188478,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Greco Middle ",null,1188478,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Mann Middle",null,1188478,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"McLane Middle",null,1188478,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Webb Middle",null,1188478,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Gary Adult ",null,2837141,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Various Sites",null,3500000,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Enhanced Hurricane Shelters",null,2074153,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b.","Hillsborough Total 2002-03",null,109914781,7907,682292,86.29,null,null,null,13900.95]

{"sheet":"Pt 3 c","index":12,"n_rows":28,"n_cols":16,"rows_kept":28,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
[]
[]
[{"$nulls":9},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[{"$nulls":9},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863, avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04"," State Avg"," State Avg"," State Avg","2002 Projected"," State Avg"," State Avg"," State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New High School PPP South County/Ruskin Area",3,38074939,2519,242357,96.21,68,128,222,15115.1,14900,18106,26448]
[null,"New Middle School KK ",2,17743438,1487,132842,89.34,86,113,165,11932.37,9863]
[null,"New Middle School OO",2,18187023,1550,132842,85.7,86,113,165,11733.56,9863,13571,18853]
[null,"New Elem. School T",1,9816422,600,55098,91.83,79,110,156,16360.7,9213,12712,22844]
[null,"New Elem. School W",1,9816422,946,77055,81.45,79,110,156,10376.77,9213,12712,22844]
[null,"New Elem. School X",1,9816422,946,77055,81.45,79,110,156,10376.77,9213,12712,22844]
[null,"New Elem. School Y",1,9816422,946,77055,81.45,79,110,156,10376.77,9213,12712,22844]
[null,"New Elem. School Z",1,9816422,946,77055,81.45,79,110,156,10376.77,9213,12712,22844]
[null,"Cork Elementary",null,562275,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Folsom Elementary",null,803190,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Kingswood Elementary",null,1070010,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Knights Elementary",null,562275,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Woodbridge Elementary",null,562275,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Various Sites",null,1500000]
[null,"Enhanced Hurricane Shelters",null,2018074,null,null,null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c.","Hillsborough Total 2003-04",null,130165609,9940,871359,87.66,0,0,null,13095.13]

{"sheet":"Pt 3 d-f","index":13,"n_rows":23,"n_cols":16,"rows_kept":23,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
[]
[]
[{"$nulls":9},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2004-2005",null,2,86,113,165,9863,13571,18853]
[{"$nulls":9},3,68,128,222,14900,18106,26448]
[]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Various Sites",null,1500000]
["3d.","Hillsborough Total 2004-05",null,1500000,0,0,0,0,0,null,{"$error":"#DIV/0!"}]
[]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2004 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Various Sites",null,1500000]
["3e","Hillsborough Total 2005-06",null,1500000,0,0,0,0,0,null,{"$error":"#DIV/0!"}]
[]
[]
["3f.","Hillsborough 5-Year Total",null,524834814,36314,3244221,265.5,0,0,0,{"$error":"#DIV/0!"},0,0,0]

{"sheet":"Pt 4","index":14,"n_rows":54,"n_cols":11,"rows_kept":54,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,81417965,85488863,89763306,94251472,98964045,449885651]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,81417965,85488863,89763306,94251472,98964045,449885651,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,5310617,10600000,4050000,4050000,4050000,28060617,0.06]
[null,"  less amount used to purchase other vehicles",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",{"$nulls":6},0,0]
[null,"  less amount used for maintenance/repair",null,18730458,21048574,29938526,35280736,37637023,142635317,0.32]
[null,"  less amount used to purchase capital outlay equipment",null,5150000,1850000,2350000,null,null,9350000,0.02]
[null,"  less amount used to correct enviornmental projects",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for salaries",{"$nulls":6},0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,1517908,1450857,748127,0,0,3716892,0.01]
[null,"  less amount to pay debt service for COP's (1 mill)",null,40708983,42744432,44881653,47125736,49482023,224942827,0.5]
[null,"  less amount used for site purchases",null,10000000,7795000,7795000,7795000,7795000,41180000,0.09,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,0,0,0,-1,-2,0,0]
[null,"2 Mill revenues - Carryforward*",null,17947389,{"$nulls":4},17947389,null,0.02]
[null,"P E C O New Construction",null,14073367,12834180,7602642,6486987,6750297,47747473,null,0.05]
[null,"PECO Maintenance ",null,10242604,6747699,6230617,6038314,6055408,35314642,null,0.04]
[null,"P E C O New Construction - Carryforward*",null,11879403,{"$nulls":4},11879403,null,0.01]
[null,"PECO Maintenance - Carryforward",null,4938737,{"$nulls":4},4938737,null,0.01]
[null,"C O & D S   Bond Proceeds - Carryforward*",null,14124755,{"$nulls":4},14124755,null,0.02]
[null,"C O & D S maximum potential bond proceeds",{"$nulls":6},0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,null,0]
[null,"Local governmental infrastructure sales surtax Bond Issue**",null,258496738,{"$nulls":4},258496738,null,0.27]
[null,"Proceeds from local governmental infrastructure sales surtax",null,19350000,20000000,20600000,21218000,21854540,103022540,null,0.11]
[null,"(Less Debt service for local governmental infrastructure sales surtax)",null,-19350000,-20000000,-20600000,-21218000,-21854540,-103022540,null,-0.11]
[null,"Proceeds from Sales Tax Revenue bonds - Carryforward*",null,35113929,{"$nulls":4},35113929,null,0.04]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0,null,0]
[null,"Proceeds from Certificates of Participation (COPs)**",null,68042655,null,112000000,null,null,180042655,null,0.19]
[null,"Proceeds from Certificates of Participation (COPs) - Carryforward*",null,161056443,{"$nulls":4},161056443,null,0.17]
[null,"Interest Earnings on COPs",null,2000000,1000000,1000000,1000000,1000000,6000000,null,0.01]
[null,"Proceeds from Racetrack Revenue bonds/QZABs ",null,9600000,{"$nulls":4},9600000,null,0.01]
[null,"Proceeds from QZABs Carryforward*",null,9715380,{"$nulls":4},9715380,null,0.01]
[null,"Classrooms First Bond proceeds - Carryforward*",null,47016846,{"$nulls":4},47016846,null,0.05]
[null,"Effort Index Grants",{"$nulls":6},0,null,0]
[null,"Effort Index Grants - Carryforward*",null,22350435,{"$nulls":4},22350435,null,0.02]
[null,"Class Size Reduction - Carryforward*",null,6201604,{"$nulls":4},6201604,null,0.01]
[null,"School Infrastructure Thrift Awards",null,11400000,24500000,9650000,2300000,null,47850000,null,0.05]
[null,"School Infrastructure Thrift Awards - Carryforward*",null,9758317,{"$nulls":4},9758317,null,0.01]
[null,"Special Appropriations - Carryforward*",null,8077326,{"$nulls":4},8077326,null,0.01]
[null,"Impact fees received",null,1562250,1562250,1562250,1562250,1562250,7811250,null,0.01]
[null,"Private donations",{"$nulls":6},0,null,0]
[null,"Grants from local governments or not-for-profit organizations",{"$nulls":6},0,null,0]
["4.","Hillsborough Total",null,723598178,46644129,138045509,17387551,15367954,"$941,043,320***",1,1.0100000000000002]
[null,"*    Funds pledged for projects in the pre-construction phase (schematic design, design development, etc.)"]
[null,"**  Estimates based on current and projected revenue and therefore subject to change."]
[null,"*** $66,153,654 represents a contingency to be used to cover prospective additional construction costs associated with the implementation of the new Florida Building Code.  "]

{"sheet":"Pt 5","index":15,"n_rows":521,"n_cols":9,"rows_kept":521,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New High School GGG",2519,18841792,null,null," ",null,18841792]
[null,"New High School JJJ",2485,19162325,{"$nulls":4},19162325]
[null,"New High School LLL",2314,15064788,22597183,null,null,null,37661971]
[null,"New High School PPP",2519,null,null,38074939,null,null,38074939]
[null,"New Middle School GG",1537,8170628,{"$nulls":4},8170628]
[null,"New Middle School JJ",1537,8869641,{"$nulls":4},8869641]
[null,"New Middle School KK",1487,null,17743438,null,null,null,17743438]
[null,"New Middle School LL",1537,16773736,{"$nulls":4},16773736]
[null,"New Middle School MM",1550,15280373,{"$nulls":4},15280373]
[null,"New Middle School NN",1511,16644345,{"$nulls":4},16644345]
[null,"New Middle School OO",1550,null,null,18187023,null,null,18187023]
[null,"New Elem. School B",600,null,6774196,null,null,null,6774196]
[null,"New Elem. School C Downtown Workplace School",600,null,6576582,null,null,null,6576582]
[null,"New Elem. School D",901,9459862,{"$nulls":4},9459862]
[null,"New Elem. School E",961,9459862,{"$nulls":4},9459862]
[null,"New Elem. School M",946,8462622,{"$nulls":4},8462622]
[null,"New Elem. School O",500,5559004,{"$nulls":4},5559004]
[null,"New Elem. School P",951,9586850,{"$nulls":4},9586850]
[null,"New Elem. School R",901,9319862,{"$nulls":4},9319862]
[null,"New Elem. School S",961,null,9608070,null,null,null,9608070]
[null,"New Elem. School T",941,null,null,9816422,null,null,9816422]
[null,"New Elem. School U",946,9459862,{"$nulls":4},9459862]
[null,"New Elem. School V",946,9319862,{"$nulls":4},9319862]
[null,"New Elem. School W",946,null,null,9816422,null,null,9816422]
[null,"New Elem. School X",946,null,null,9816422,null,null,9816422]
[null,"New Elem. School Y",946,null,null,9816422,null,null,9816422]
[null,"New Elem. School Z",946,null,null,9816422,null,null,9816422]
[null,"Adult Center East",0,null,2666912,null,null,null,2666912]
[null,"Adult Technology Center",0,null,3172050,null,null,null,3172050]
[null,"Career Center MMM",640,5384900,{"$nulls":4},5384900]
[null,"Career Center NNN",600,9994030,{"$nulls":4},9994030]
[null,"Career Center OOO",300,4606998,{"$nulls":4},4606998]
[null,"Plant City ESE",240,2099089,{"$nulls":4},2099089]
[null,"Waters, D.W.",475,6323374,{"$nulls":4},6323374]
[null,"Various Sites","Site Acquisition",5847855,3500000,1500000,1500000,1500000,13847855]
[null,"Enhanced Hurricane Shelters",null,8998802,2074153,2018074,null,null,13091029]
[null,"ELEMENTARY SCHOOLS",{"$nulls":6},0]
[null,"Alexander Elementary",80,603346,{"$nulls":4},603346]
[null,"Broward Elementary",200,1286695,{"$nulls":4},1286695]
[null,"Bryan (PC) Elementary",200,1964036,{"$nulls":4},1964036]
[null,"Burney Simmons Elementary",250,2016000,{"$nulls":4},2016000]
[null,"Clair Mel Elementary",125,889950,{"$nulls":4},889950]
[null,"Claywell Elementary",300,1779667,{"$nulls":4},1779667]
[null,"Cork Elementary",100,null,null,562275,null,null,562275]
[null,"DeSoto Elementary",150,2019091,{"$nulls":4},2019091]
[null,"Dover Elementary ESE",225,1415126,{"$nulls":4},1415126]
[null,"Edison Elementary",125,930254,{"$nulls":4},930254]
[null,"Folsom Elementary",150,null,null,803190,null,null,803190]
[null,"Gorrie Elementary",150,1325678,{"$nulls":4},1325678]
[null,"Grady Elementary ",100,557376,{"$nulls":4},557376]
[null,"Graham Elementary",125,868548,{"$nulls":4},868548]
[null,"Jackson Elementary",125,1608183,{"$nulls":4},1608183]
[null,"James Elementary ",350,null,2400000,null,null,null,2400000]
[null,"Just Elementary ",350,null,1750000,null,null,null,1750000]
[null,"Kingswood Elementary",200,null,null,1070010,null,null,1070010]
[null,"Knights Elementary",100,null,null,562275,null,null,562275]
[null,"Lewis Elementary",150,1020052,{"$nulls":4},1020052]
[null,"Lomax Elementary ",275,null,1965000,null,null,null,1965000]
[null,"Lopez Elementary ESE",120,1234459,{"$nulls":4},1234459]
[null,"Mabry Elementary",200,805720,{"$nulls":4},805720]
[null,"Morgan Woods Elementary ",125,1023435,{"$nulls":4},1023435]
[null,"Potter Elementary",300,null,2474000,null,null,null,2474000]
[null,"Riverview Elementary",348,1936346,{"$nulls":4},1936346]
[null,"Robles  Elementary",90,589746,{"$nulls":4},589746]
[null,"Roosevelt Elementary",80,556260,{"$nulls":4},556260]
[null,"Ruskin Elementary",80,561731,{"$nulls":4},561731]
[null,"Tampa Bay Blvd Elem",100,613010,{"$nulls":4},613010]
[null,"Town & Country Elementary",80,560179,{"$nulls":4},560179]
[null,"West Shore Elementary",100,1277760,{"$nulls":4},1277760]
[null,"West Tampa Elementary",200,{"$nulls":5},0]
[null,"Woodbridge Elementary",100,null,null,562275,null,null,562275]
[null,"MIDDLE SCHOOLS",{"$nulls":6},0]
[null,"Adams Middle",192,null,2537778,null,null,null,2537778]
[null,"Buchanan Middle ",80,1090342,{"$nulls":4},1090342]
[null,"Eisenhower Middle ",80,null,1188478,null,null,null,1188478]
[null,"Ferrell Middle ",304,2221612,{"$nulls":4},2221612]
[null,"Franklin Middle ",80,null,1188478,null,null,null,1188478]
[null,"Greco Middle ",80,null,1188478,null,null,null,1188478]
[null,"Madison Middle",80,1090342,{"$nulls":4},1090342]
[null,"Mann Middle",80,null,1188478,null,null,null,1188478]
[null,"McLane Middle",80,null,1188478,null,null,null,1188478]
[null,"Van Buren Middle ",80,1090342,{"$nulls":4},1090342]
[null,"Webb Middle",80,null,1188478,null,null,null,1188478]
[null,"HIGH SCHOOLS",{"$nulls":6},0]
[null,"Armwood High",480,2653119,{"$nulls":4},2653119]
[null,"Durant High",360,1002540,{"$nulls":4},1002540]
[null,"OTHER FACILITIES",{"$nulls":6},0]
[null,"Gary Adult ",0,null,2837141,null,null,null,2837141]
[null,"MacFarlane Center",0,2781982,{"$nulls":4},2781982]
[null,null,"ELEMENTARY SCHOOLS",{"$nulls":5},0]
[null,"Renovate AC","ALEXANDER ELEMENTARY",280000,{"$nulls":4},280000]
[null,"Painting",null,null,null,130000,null,null,130000]
[null,"Renovate intercom",null,75000,{"$nulls":4},75000]
[null,"Replace fire alarm",null,100000,{"$nulls":4},100000]
[null,"Renovation/Remodeling","ANDERSON ELEMENTARY (FFF&E)",null,null,null,2389980,null,2389980]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation","APOLLO BEACH ELEMENTARY (FFF&E)",{"$nulls":4},5148826,5148826]
[null,"Renovation/Remodeling","BALLAST POINT ELEMENTARY (FFF&E)",null,3150267,null,null,null,3150267]
[null,"Renovation/Remodeling","BAY CREST ELEMENTARY (FFF&E) ",null,1293611,2338845,null,null,3632456]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation ","BELLAMY ELEMENTARY (FFF&E) ",{"$nulls":4},3674884,3674884]
[null,"Including intercom, phones ",{"$nulls":6},0]
[null,"Paint entire school","BING ELEMENTARY",null,100000,null,null,null,100000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Replace fire alarm",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Paint entire school","BOYETTE SPRINGS ELEMENTARY",100000,{"$nulls":4},100000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Replace intercom",null,75000,{"$nulls":4},75000]
[null,"Renovate fire alarm ",null,25000,{"$nulls":4},25000]
[null,"Correct drainage problems",{"$nulls":6},0]
[null,"Renovate intercom","BROOKER ELEMENTARY (FFF&E) (R&NC) ",null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,20000,null,null,null,20000]
[null,"Renovation/Remodeling","BROWARD ELEMENTARY (FFF&E) ",2132639,{"$nulls":4},2132639]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","BRYAN ELEMENTARY - PLANT CITY (FFF&E) ",3673148,{"$nulls":4},3673148]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Replace fire alarm","BUCKHORN ELEMENTARY ",{"$nulls":4},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","BURNEY-SIMMONS ",2145212,{"$nulls":4},2145212]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/remodeling","CAHOON ELEMENTARY (FFF&E) ",3200000,{"$nulls":4},3200000]
[null,"Including fire alarm, intercom",{"$nulls":6},0]
[null,"Paint","CANNELLA ELEMENTARY",{"$nulls":4},170000,170000]
[null,"Renovate intercom",null,null,25000,null,null,null,25000]
[null,"Replace telephones ",null,null,20000,null,null,null,20000]
[null,"Renovation/Remodeling","CARROLLWOOD ELEMENTARY (1) ",null,3605008,null,null,null,3605008]
[null,"Renovation ","CHIARAMONTE ELEMENTARY (FFF&E)",{"$nulls":4},3039659,3039659]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","CITRUS PARK ELEMENTARY (FFF&E) ",null,3952920,null,null,null,3952920]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","CLAIR-MEL ELEMENTARY (FFF&E) ",null,3077216,null,null,null,3077216]
[null,"Including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","CLEVELAND ELEMENTARY",null,1763888,null,null,null,1763888]
[null,"Renovate AC",{"$nulls":6},0]
[null,"Replace fie alarm in renovation",{"$nulls":5},150000,150000]
[null,"Replace intercom in renovation ",{"$nulls":5},150000,150000]
[null,"Renovate intercom and phones ","COLSON ELEMENTARY",null,75000,null,null,null,75000]
[null,"Replace fire alarm panel",null,null,25000,null,null,null,25000]
[null,"Interior/exterior painting",{"$nulls":5},150000,150000]
[null,"Renovation/Remodeling","CORK ELEMENTARY (FFF&E) ",{"$nulls":4},4386535,4386535]
[null,"Including fire alarm, intercom, phones, courts, water ",{"$nulls":6},0]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Renovation ","CRESTWOOD ELEMENTARY (FFF&E) ",{"$nulls":4},2418980,2418980]
[null,"Including intercom, phones ",{"$nulls":6},0]
[null,"Replace telephones ","CYPRESS CREEK ELEMENTARY",null,null,30000,null,null,30000]
[null,"Replace fire alarm",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Paint exterior& coping replacement",{"$nulls":4},230000,null,230000]
[null,"Storm drain repair",{"$nulls":5},10000,10000]
[null,"Renovation ","DESOTO ELEMENTARY (FFF&E)",{"$nulls":4},1363077,1363077]
[null,"Including fire alarm, phones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","DICKENSON ELEMENTARY (FFF&E) ",null,226712,null,null,null,226712]
[null,"Replace fire alarm ",{"$nulls":5},150000,150000]
[null,"Replace intercom ",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","DOVER ELEMENTARY (FFF&E) ",4118635,{"$nulls":4},4118635]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Replace intercom",null,null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Replace fire alarm ","DUNBAR ELEMENTARY",{"$nulls":4},150000,150000]
[null,"Replace intercome",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovate HVAC","EDISON ELEMENTARY (FFF&E) (R&NC) ",null,null,null,450000,null,450000]
[null,"Renovate bathrooms",{"$nulls":5},15000,15000]
[null,"Renovation/Remodeling","EGYPT LAKE ELEMENTARY",2131490,{"$nulls":4},2131490]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate intercom","ESSRIG ELEMENTARY",null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Replace fire alarm",null,null,150000,null,null,null,150000]
[null,"Paint exterior & interior",{"$nulls":4},120000,null,120000]
[null,"Renovate intercom","FOLSOM ELEMENTARY ",null,null,null,75000,null,75000]
[null,"Paint entire school",null,null,200000,null,null,null,200000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Replace fire alarm",{"$nulls":5},150000,150000]
[null,"Renovate fire alarm","FOREST HILLS ELEMENTARY",null,null,null,20000,null,20000]
[null,"Interior & exterior painting",{"$nulls":5},170000,170000]
[null,"Fencing",null,10000,{"$nulls":4},10000]
[null,"Renovation/Remodeling","FOSTER ELEMENTARY (FFF&E) ",null,3920511,null,null,null,3920511]
[null,"including intercom, telephones",{"$nulls":6},0]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Replace telephones ","GIBSONTON ELEMENTARY (1) (2) ",null,null,30000,null,null,30000]
[null,"Replace remaining AC",null,null,null,235000,null,null,235000]
[null,"Renovation/Remodeling","GORRIE ELEMENTARY",2367080,{"$nulls":4},2367080]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation / Remodeling","GRADY ELEMENTARY (FFF&E)",2585607,{"$nulls":4},2585607]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace remaining AC",{"$nulls":6},0]
[null,"Renovation/Remodeling","GRAHAM ELEMENTARY",null,1671830,null,null,null,1671830]
[null,"including fire alarm, intercom, telephones, irrigation",{"$nulls":6},0]
[null,"Renovate intercom","HUNTERS GREEN ELEMENTARY",null,null,null,75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovation/Remodeling","JACKSON ELEMENTARY (FFF&E) ",2295601,{"$nulls":4},2295601]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","JAMES ELEMENTARY",null,1997900,null,null,null,1997900]
[null,"including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Renovation/remodeling","KENLY ELEMENTARY (FFF&E) ",null,3139218,null,null,null,3139218]
[null,"including intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Renovation/ Remodeling","KINGSWOOD ELEMENTARY (FFF&E) ",null,null,null,3541346,null,3541346]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation","KNIGHTS ELEMENTARY (FFF&E) ",null,4522563,null,null,null,4522563]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Renovation/Remodeling","LAKE MAGDALENE ELEMENTARY",null,null,4009192,null,null,4009192]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","LANIER ELEMENTARY (FFF&E) ",null,null,null,2423758,null,2423758]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","LEE ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Paint interior",null,null,null,70000,null,null,70000]
[null,"Replace flooring",null,null,null,125000,null,null,125000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Interior and Exterior Painting","LEWIS ELEMENTARY",{"$nulls":4},170000,170000]
[null,"Renovation  ","LIMONA ELEMENTARY (FFF&E) ",{"$nulls":4},3582223,3582223]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Special Projects",null,91615,{"$nulls":4},91615]
[null,"Renovate AC","LINCOLN ELEMENTARY",300000,{"$nulls":4},300000]
[null,"Renovate restrooms",null,null,null,65000,null,null,65000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovate fire alarm",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Renovate fire alarm","LITHIA SPRINGS ELEMENTARY",null,null,20000,null,null,20000]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Resurface parking",null,null,50000,null,null,null,50000]
[null,"Replace telephones ",null,null,null,30000,null,null,30000]
[null,"Replace telephones ","LOCKHART ELEMENTARY",null,null,30000,null,null,30000]
[null,"Renovation/Remodeling","LOMAX ELEMENTARY",null,1500387,null,null,null,1500387]
[null,"including intercom, phones",{"$nulls":6},0]
[null,"Interior & exterior painting","LOPEZ ELEMETNARY ",{"$nulls":4},150000,150000]
[null,"Renovate intercom","LOWRY ELEMENTARY",null,null,75000,null,null,75000]
[null,"Replace telephones ",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","LUTZ ELEMENTARY (FFF&E) ",3686801,{"$nulls":4},3686801]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation","MABRY ELEMENTARY (FFF&E) ",null,null,3525527,null,null,3525527]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","MANGO ELEMENTARY",null,30000,null,null,null,30000]
[null,"Renovate fire alarm",null,125000,{"$nulls":4},125000]
[null,"Renovate intercom",null,null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovate fire alarm","MANISCALCO ELEMENTARY",null,null,20000,null,null,20000]
[null,"Replace HVAC",{"$nulls":5},1104000,1104000]
[null,"Paint interior & exterior",null,null,null,150000,null,null,150000]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Replace telephones ",null,null,null,30000,null,null,30000]
[null,"Renovation  ","MCDONALD ELEMENTARY (FFF&E) ",{"$nulls":4},3727184,3727184]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","MENDENHALL ELEMENTARY (FFF&E) ",null,2857969,null,null,null,2857969]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation /Remodeling","MILES ELEMENTARY",null,3398334,null,null,null,3398334]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC",null,null,260000,null,null,null,260000]
[null,"Renovate telephones","MINTZ ELEMENTARY",null,null,30000,null,null,30000]
[null,"Special Projects",null,260000,{"$nulls":4},260000]
[null,"Interior & exterior painting",{"$nulls":5},150000,150000]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Renovation/Remodeling","MITCHELL ELEMENTARY",null,1810490,null,null,null,1810490]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones ",{"$nulls":6},0]
[null,"Renovation/Remodeling","MORGAN WOODS ELEMENTARY (FFF&E) ",null,3810710,null,null,null,3810710]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","MORT ELEMENTARY (FFF&E) ",null,3831950,null,null,null,3831950]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate intercom","NORTHWEST ELEMENTARY",null,null,null,75000,null,75000]
[null,"Replace AC controls",{"$nulls":5},768000,768000]
[null,"Paint interior & exterior",{"$nulls":4},150000,null,150000]
[null,"Replace roof flashing",null,null,100000,null,null,null,100000]
[null,"Replace telephones ",{"$nulls":4},20000,null,20000]
[null,"Replace fire alarm",{"$nulls":5},75000,75000]
[null,"Replace telephones ","OAK PARK ELEMENTARY",null,null,null,30000,null,30000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate intercom",{"$nulls":5},150000,150000]
[null,"Renovation/Remodeling","PALM RIVER ELEMENTARY (FFF&E) ",null,4465598,null,null,null,4465598]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation","PINECREST ELEMENTARY (FFF&E) ",{"$nulls":4},5158444,5158444]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Renovation/Remodeling","POTTER ELEMENTARY",null,2340516,null,null,null,2340516]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Reroofing","RIVERHILLS ELEMENTARY",{"$nulls":4},280000,280000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Renovation","RIVERVIEW ELEMENTARY (FFF&E) ",{"$nulls":4},3761016,3761016]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate facility","ROBLES ELEMENTARY",2811784,{"$nulls":4},2811784]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Replace telephones ",{"$nulls":6},0]
[null,"Renovate AC","ROOSEVELT ELEMENTARY",null,300000,null,null,null,300000]
[null,"Replace fire alarm panel",null,null,null,7500,null,null,7500]
[null,"Renovate intercom",null,null,null,75000,null,null,75000]
[null,"Replace clrm lighting",null,null,67740,null,null,null,67740]
[null,"Paint entire school",null,null,150000,null,null,null,150000]
[null,"Reroof auditorium",null,null,80000,null,null,null,80000]
[null,"Replace telephones ",null,null,null,20000,null,null,20000]
[null,"Renovation","RUSKIN ELEMENTARY",{"$nulls":4},4413729,4413729]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate intercom","SCHWARZKOPF ELEMENTARY",null,null,null,75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},20000,null,20000]
[null,"Interior & exterior painting",{"$nulls":5},150000,150000]
[null,"Renovate fire alarm","SEMINOLE ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovate HVAC",{"$nulls":4},600000,null,600000]
[null,"Renovate intercom",{"$nulls":4},75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovation/Remodeling","SHAW ELEMENTARY (FFF&E)  ",null,4721795,null,null,null,4721795]
[null,"Replace telephones ",{"$nulls":5},50000,50000]
[null,"Replace telephones ","SHORE ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovation","SPRINGHEAD ELEMENTARY (FFF&E) ",{"$nulls":4},2953726,2953726]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","SULPHUR SPRINGS ELEMENTARY   ",null,null,null,285000,null,285000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovate fire alarm",{"$nulls":4},20000,null,20000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Replace telephones ","SUMMERFIELD ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate AC",{"$nulls":6},0]
[null,"Interior & exterior painting","TAMPA BAY BOULEVARD  ELEMENTARY",{"$nulls":4},100000,100000]
[null,"Water proofing ",{"$nulls":6},0]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Renovate fire alarm","TAMPA PALMS ELEMENTARY",null,null,null,75000,null,75000]
[null,"Renovate intercom",{"$nulls":4},75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},30000,null,30000]
[null,"Remediate water intrusion",null,null,null,349000,null,null,349000]
[null,"Renovate AC","TEMPLE TERRACE ELEMENTARY",null,600000,null,null,null,600000]
[null,"Interiior & exterior painting ",{"$nulls":5},200000,200000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones ",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","THONOTOSASSA ELEMENTARY (FFF&E) ",null,3389746,null,null,null,3389746]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","TINKER ELEMENTARY (FFF&E) ",null,null,2855483,null,null,2855483]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","TOWN & COUNTRY ELEMENTARY (FFF&E) ",2895572,{"$nulls":4},2895572]
[null,"Renovation","TRAPNELL ELEMENTARY",{"$nulls":4},3735711,3735711]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Upgrade potable water ",{"$nulls":5},60000,60000]
[null,"Replace telephones ","TWIN LAKES ELEMENTARY",null,null,null,30000,null,30000]
[null,"Renovate fire alarm ",{"$nulls":5},150000,150000]
[null,"Renovate intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones","VALRICO ELEMENTARY",null,null,30000,null,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},150000,150000]
[null,"Replace telephones ","WALDEN LAKE ELEMENTARY",null,null,null,20000,null,20000]
[null,"Renovate intercom",null,null,null,150000,null,150000,300000]
[null,"Renovate fire alarm",null,125000,null,null,20000,null,145000]
[null,"Renovation/Remodeling","WASHINGTON ELEMENTARY  (BOOKER T.)",null,3298903,null,null,null,3298903]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","WEST TAMPA ELEMENTARY",null,50000,null,null,null,50000]
[null,"Interior & exterior painting",{"$nulls":5},70000,70000]
[null,"Replace HVAC",{"$nulls":5},1266000,1266000]
[null,"Renovate intercom",null,null,75000,null,null,null,75000]
[null,"Replace telephones ",null,null,30000,null,null,null,30000]
[null,"Replace fire alarm panel",null,null,25000,null,null,null,25000]
[null,"Renovation /Remodeling","WESTSHORE ELEMENTARY",null,1681734,null,null,null,1681734]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovate AC","WILSON ELEMENTARY",null,30000,null,null,null,30000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},30000,30000]
[null,"Renovation/Remodeling","WIMAUMA ELEMENTARY",null,3802179,null,null,null,3802179]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones","WITTER ELEMENTARY",{"$nulls":4},30000,30000]
[null,"Renovation/Remodeling","WOODBRIDGE ELEMENTARY (FFF&E) ",null,3429994,null,null,null,3429994]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Paint interior & exterior","YATES ELEMENTARY",null,null,null,100000,null,100000]
[null,"Renovate fire alarm",{"$nulls":4},25000,null,25000]
[null,"Replace intercom",{"$nulls":4},75000,null,75000]
[null,"Replace telephones ",{"$nulls":4},20000,null,20000]
[null,null,"MIDDLE SCHOOLS",{"$nulls":5},0]
[null,"Renovation/Remodeling","ADAMS  MIDDLE (FFF&E) ",null,5875965,null,null,null,5875965]
[null,"including fire alarm, intercom",{"$nulls":6},0]
[null,"Fencing",null,10000,{"$nulls":4},10000]
[null,"Renovation/Remodeling","BUCHANAN MIDDLE (FFF&E) ",7907453,{"$nulls":4},7907453]
[null,"including fire alarm, intercom",{"$nulls":6},0]
[null,"Replace fire alarm ","BURNS MIDDLE ",160000,{"$nulls":4},160000]
[null,"Replace intercom ",null,150000,{"$nulls":4},150000]
[null,"Renovate fire alarm","DOWDELL MIDDLE ",null,125000,null,null,null,125000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Renovation/Remodeling","EISENHOWER MIDDLE (FFF&E) ",null,5584078,null,null,null,5584078]
[null,"including intercom, phones",{"$nulls":6},0]
[null,"Renovate intercom","FERRELL MIDDLE",null,30000,null,null,null,30000]
[null,"Paint entire school",null,null,150000,null,null,null,150000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Renovation/Remodeling","FRANKLIN MIDDLE (FFF&E) ",null,4552820,null,null,null,4552820]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation/Remodeling","GRECO MIDDLE (FFF&E) (R&NC) ",null,7742821,null,null,null,7742821]
[null,"Replace fire alarm ","HILL MIDDLE ",{"$nulls":4},150000,150000]
[null,"Replace intercom ",{"$nulls":5},150000,150000]
[null,"Replace telephones",{"$nulls":5},35000,35000]
[null,"Renovation/Remodeling","MADISON MIDDLE (FFF&E) ",5081698,{"$nulls":4},5081698]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Irrigation",{"$nulls":5},40000,40000]
[null,"Renovation/Remodeling","MANN MIDDLE",null,7310090,null,null,null,7310090]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace clrm flooring",null,150000,{"$nulls":4},150000]
[null,"Replace telephones","MARSHALL MIDDLE ",null,30000,null,null,null,30000]
[null,"Replace boilers/piping",null,null,null,25000,null,null,25000]
[null,"Renovation/Remodeling","MCLANE MIDDLE ",null,4554533,null,null,null,4554533]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones","MONROE MIDDLE ",null,30000,null,null,null,30000]
[null,"Paint interior & exterior",{"$nulls":4},170000,null,170000]
[null,"Replace HVAC",{"$nulls":5},170000,170000]
[null,"Replace telephones","PROGRESS VILLAGE MIDDLE ",30000,{"$nulls":4},30000]
[null,"Interior & exterior painting",{"$nulls":5},250000,250000]
[null,"Replace telephones","ROLAND PARK MIDDLE",null,null,null,30000,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},180000,180000]
[null,"Renovate intercom","SLIGH MIDDLE",null,120000,null,null,null,120000]
[null,"Replace fire alarm",null,null,150000,null,null,null,150000]
[null,"Interior & exterior painting",{"$nulls":5},200000,200000]
[null,"Renovate restrooms",{"$nulls":4},60000,null,60000]
[null,"Replace telephones",null,30000,{"$nulls":4},30000]
[null,"Renovate fire alarm","STEWART MIDDLE ",null,null,null,25000,null,25000]
[null,"Renovate intercom",{"$nulls":4},120000,null,120000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Interior & exterior painting",{"$nulls":5},160000,160000]
[null,"Replace boilers/piping","TURKEY CREEK MIDDLE",null,null,30000,null,null,30000]
[null,"Replace telephones",null,null,30000,null,null,null,30000]
[null,"Renovation/Remodeling","VAN BUREN MIDDLE (FFF&E) ",null,6400000,null,null,null,6400000]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Replace telephones","WALKER MIDDLE ",null,null,null,30000,null,30000]
[null,"Paint interior & exterior",{"$nulls":4},200000,null,200000]
[null,"Renovation/Remodeling","WEBB MIDDLE (FFF&E) ",null,6795806,null,null,null,6795806]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Replace telephones","WILLIAMS MIDDLE ",null,null,null,30000,null,30000]
[null,"Replace floors","WILSON MIDDLE ",null,60000,null,null,null,60000]
[null,"Interior & exterior painting",{"$nulls":5},120000,120000]
[null,"Renovate AC",null,840000,{"$nulls":4},840000]
[null,"Replace telephones",null,30000,{"$nulls":4},30000]
[null,"Replace intercom",null,150000,{"$nulls":4},150000]
[null,"Replace telephones","YOUNG MIDDLE",null,null,null,30000,null,30000]
[null,null,"HIGH SCHOOLS",{"$nulls":5},0]
[null,"Renovate fire alarm","ARMWOOD HIGH",null,null,null,175000,null,175000]
[null,"Special Projects",null,100000,{"$nulls":4},100000]
[null,"Renovate AC",{"$nulls":4},250000,null,250000]
[null,"Replace softball & baseball turf",null,null,128333,null,null,null,128333]
[null,"Renovate fire alarm","BLOOMINGDALE HIGH",null,null,175000,null,null,175000]
[null,"Replace intercom",{"$nulls":5},200000,200000]
[null,"Special Projects",null,500000,{"$nulls":4},500000]
[null,"Renovate auditorium PA ",null,null,20000,null,null,null,20000]
[null,"Renovate stage lighting",null,null,10000,null,null,null,10000]
[null,"Renovation/Remodeling","BRANDON HIGH (FFF&E) ",null,13254243,null,null,null,13254243]
[null,"Speical Projects",null,40000,{"$nulls":4},40000]
[null,"Resurface track ",null,25000,{"$nulls":4},25000]
[null,"Replace intercom",{"$nulls":6},0]
[null,"Renovation/Remodeling","CHAMBERLAIN HIGH     (FF&E)",3525229,{"$nulls":4},3525229]
[null,"Replace telephones","DURANT HIGH  ",40000,{"$nulls":4},40000]
[null,"Renovation/Remodeling","EAST BAY HIGH (FFF&E) ",null,13254243,null,null,null,13254243]
[null,"including telephones",{"$nulls":6},0]
[null,"SB field repair",{"$nulls":5},60000,60000]
[null,"Renovate stadium PA ","GAITHER HIGH",null,10000,null,null,null,10000]
[null,"Renovate auditorium PA ",null,null,20000,null,null,null,20000]
[null,"Special Projects ",null,300000,{"$nulls":4},300000]
[null,"Resurface track ",{"$nulls":5},25000,25000]
[null,"Paint entire school",null,null,120000,null,null,null,120000]
[null,"Renovate drainage",{"$nulls":4},35000,null,35000]
[null,"Replace intercom","HILLSBOROUGH HIGH",250000,{"$nulls":4},250000]
[null,"Waterproofing ",null,2457255,{"$nulls":4},2457255]
[null,"Replace AC",null,null,null,4500000,null,null,4500000]
[null,"Replace gym lighting",null,null,67740,null,null,null,67740]
[null,"Replace baseball turf",null,null,75000,null,null,null,75000]
[null,"Replace softball turf",null,null,45000,null,null,null,45000]
[null,"Renovation/Remodeling","JEFFERSON HIGH",null,10783371,null,null,null,10783371]
[null,"Renovation/Remodeling","KING HIGH (FFF&E) ",null,11807407,null,null,null,11807407]
[null,"Renovation/Remodeling","LETO HIGH (FFF&E) ",7691749,{"$nulls":4},7691749]
[null,"including fire alarm, intercom ",{"$nulls":6},0]
[null,"Renovation/ Remodeling","PLANT CITY HIGH (FFF&E) ",null,13254243,null,null,null,13254243]
[null,"including fire alarm, intercom, telephones",{"$nulls":6},0]
[null,"Renovation in process","PLANT HIGH (FFF&E)  ",5423709,{"$nulls":4},5423709]
[null,"Renovation in process","ROBINSON HIGH (FFF&E) ",3369774,{"$nulls":4},3369774]
[null,"Renovate intercom","SICKLES HIGH ",null,null,null,25000,null,25000]
[null,"Replace telephones",null,40000,{"$nulls":4},40000]
[null,"Renovation/Remodeling","TAMPA BAY TECHNICAL HIGH (FFF&E) ",null,8540649,null,null,null,8540649]
[null,"Replace intercom ",{"$nulls":6},0]
[null,"BB",null,75000,{"$nulls":4},75000]
[null,"Fencing",null,20000,{"$nulls":4},20000]
[null,null,"OTHER FACILITIES",{"$nulls":5},0]
[null,"Replace fire alarm ","BREWSTER TECHNICAL",{"$nulls":4},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones","CAMINITI EXCEPTIONAL",null,null,null,30000,null,30000]
[null,"Paint entire school",{"$nulls":4},150000,null,150000]
[null,"Renovate HVAC",{"$nulls":4},660000,null,660000]
[null,"Replace fire alarm ",{"$nulls":5},150000,150000]
[null,"Replace intercom",{"$nulls":5},150000,150000]
[null,"Replace telephones","DOROTHY THOMAS CENTER ",30000,{"$nulls":4},30000]
[null,"Replace intercom",null,75000,{"$nulls":4},75000]
[null,"Renovate AC",{"$nulls":4},40000,null,40000]
[null,"Replace fire alarm","EISENHOWER EXCEPTIONAL CENTER",null,125000,null,null,null,125000]
[null,"Renovate AC",{"$nulls":4},80000,null,80000]
[null,"Renovation ","ERWIN TECHNICAL CENTER",{"$nulls":4},12407248,12407248]
[null,"Renovate AC ",null,null,300000,null,null,null,300000]
[null,"Replace telephones",null,null,150000,null,null,null,150000]
[null,"Renovation/Remodeling","JUST EARLY CHILDHOOD CENTER",null,1822159,null,null,null,1822159]
[null,"including intercom, phones",{"$nulls":6},0]
[null,"Renovate fire alarm","KIMBALL FULL SERVICE SCHOOL",null,null,null,20000,null,20000]
[null,"Replace telephones",{"$nulls":4},20000,null,20000]
[null,"Renovation","LAVOY EXCEPTIONAL",{"$nulls":4},2441620,2441620]
[null,"Replace fire alarm panel",{"$nulls":6},0]
[null,"Replace telephones",{"$nulls":6},0]
[null,"Renovate intercom","LEAREY TECHNICAL ",null,null,null,55000,null,55000]
[null,"Reroof","LIBRARY PROCESSING",null,null,null,70000,null,70000]
[null,"Roofing","MAINTENANCE FACILITY",null,null,null,25000,null,25000]
[null,"Renovation/Remodeling","MEACHAM EARLY CHILDHOOD",{"$nulls":4},1727191,1727191]
[null,"including intercom, phones ",{"$nulls":6},0]
[null,"Renovate AC","ROS SCHOOL ADMINISTRATIVE CENTER",null,3100000,null,null,null,3100000]
[null,"Renovate AC","TRANSPORTATION OFFICES",null,null,null,190000,null,190000]
[null,"Replace telephones","VELASCO",null,235000,null,null,null,235000]
[null,"Phased renovation","WATERS CENTER (GEO. WASHINGTON JR HI)",9485615,{"$nulls":4},9485615]
[null,"including fire alarm, intercom, phones ",{"$nulls":6},0]
[null,"Cost to Retrofit Relocatables to Meet New Building Codes",null,2275566,{"$nulls":4},2275566]
[5,"HILLSBOROUGH Total",4712,358236621,302075561,131907718,15345084,78108053,885673037]

{"sheet":"Pt 6 - End","index":16,"n_rows":54,"n_cols":11,"rows_kept":54,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["District: ====>",null,"Hillsborough","Date: ==>","2001-09-04",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
[]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,11400000,24500000,9650000,2300000,0,56571184]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","Hillsborough Total",null,11400000,24500000,9650000,2300000,0,56571184]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,null,null,0,0,0,0,0,0]
["7.","Hillsborough Total",null,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[null,"SCHOOL BOARD OF ","Hillsborough  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Earl J. Lennard "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ",{"$nulls":4},"Michael K. Bookman ",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  ",null,null,"James P. Hamilton","Deputy Superintendent","813 272-4101 ",null,"Hamilton_J01@popmail.firn.edu",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]