{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":587,"n_cols":25,"rows_kept":587,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["LEE  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["LEE   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"LEE","Date: ==>","2001-10-01",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Transportation facilities upgrade","Refueling Bus Depot South",2227783,{"$nulls":4},2227783]
[null,"Life Safety",{"$nulls":6},0]
[null,"Safety Modification/Code compliane","Cypress Lake High",1778349,{"$nulls":4},1778349]
[null,"Safety Modification/Code compliane","Riverdale High",2000000,{"$nulls":4},2000000]
[null,"Safety Modification/Code compliane","San Carlos Park Elementary",175000,{"$nulls":4},175000]
[null,"Safety Modification/Code compliane","District wide",3226137,3350000,10628131,3647000,1500000,22351268]
[null,"HVAC Upgrades",{"$nulls":6},0]
[null,"Cape Coral High",null,491237,{"$nulls":4},491237]
[null,"High Tech Center Central",null,4875199,{"$nulls":4},4875199]
[null,"Districtwide HVAC",null,1704095,1410500,1200000,1200000,1200000,6714595]
[{"$nulls":8},0]
[null,"Roofing","District wide",671230,500000,500000,500000,500000,2671230]
[{"$nulls":8},0]
[null,"Maintenance Projects","District wide",6460393,4705078,4891031,4914533,4765710,25736745]
[{"$nulls":8},0]
[null,"Construction Services Projects","District wide",2000000,1940000,1940000,2040000,1940000,9860000]
[{"$nulls":8},0]
[null,"Safety & Inspections","District wide",244830,244000,255000,268000,236000,1247830]
[{"$nulls":8},0]
[null,"Upgrade Portables","District wide",2824714,2320000,240000,240000,240000,5864714]
[{"$nulls":8},0]
[null,"Technology","District wide",3123464,2360000,2500000,2630000,2761500,13374964]
[null,"Maintenance, Repair, and Renovation Totals",null,29574648,16829578,22154162,15439533,13143210,97141131]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,3184726,2724750,2515950,2438297,2445200,13308923]
["1.","LEE Total",null,26389922,14104828,19638212,13001236,10698010,83832208]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Completion of (2) elementary school projects",null,353696,{"$nulls":4},353696]
[null,"Completion of (3) middle school projects",null,1071084,{"$nulls":4},1071084]
[null,"Completion of (3) high school projects",null,842655,{"$nulls":4},842655]
[null,"Cape Coral High Addition",null,3527033,{"$nulls":4},3527033]
[null,"The Sanibel School","Remodel/Renovation/New Construction",6990530,{"$nulls":4},6990530]
[null,"NFMAA Elem/Middle K-8 Conversion",null,19091555,{"$nulls":4},19091555]
[null,"Lee Middle ESE Suite",null,1249275,{"$nulls":4},1249275]
[null,"Lehigh Senior High; Build out 2nd floor",null,399370,{"$nulls":4},399370]
[null,"New Dunbar High School and Athletics",null,9957464,{"$nulls":4},9957464]
[null,"New East Zone Middle School",null,15562920,{"$nulls":4},15562920]
[null,"Land-East Zone schools",null,500000,{"$nulls":4},500000]
[null,"Mirror Lakes Elementary Addition","Buildout additional wing",3201250,{"$nulls":4},3201250]
[null,"land-South Zone High School",null,6000000,{"$nulls":4},6000000]
[null,"South Zone High School",null,23314800,{"$nulls":4},23314800]
[null,"Land-West Zone High School",null,3200000,{"$nulls":4},3200000]
[null,"West Zone High School",null,23314800,{"$nulls":4},23314800]
[null,"Land-South Zone Middle",null,null,3900000,null,null,null,3900000]
[null,"South Zone Middle",null,null,10547600,null,null,null,10547600]
[null,"Land-West Zone Middle",null,null,2080000,null,null,null,2080000]
[null,"West Zone Middle",null,null,10547600,null,null,null,10547600]
[null,"East Zone Elementary",null,null,6571000,null,null,null,6571000]
[null,"Land-South Zone Elementary",null,null,2433600,null,null,null,2433600]
[null,"South Zone Elementary",null,null,6571000,null,null,null,6571000]
[null,"East Zone High",null,null,null,18425700,null,null,18425700]
[null,"Land-South Zone Elementary",null,null,null,2433600,null,null,2433600]
[null,"South Zone Elementary",null,null,null,6747000,null,null,6747000]
[null,"Land-West Zone High School",{"$nulls":4},3600000,null,3600000]
[null,"West Zone High School",{"$nulls":4},18906300,null,18906300]
[null,"Land-East Zone Middle",{"$nulls":5},1462350,1462350]
[null,"East Zone Middle",{"$nulls":5},11400000,11400000]
[null,"Land-South Zone Elementary",{"$nulls":5},2632200,2632200]
[null,"South Zone Elementary",{"$nulls":5},7100000,7100000]
[{"$nulls":8},0]
["2 .","LEE Total",null,118576432,42650800,27606300,22506300,22594550,233934382]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Allen Park Elementary",964,964,759,0.79,0,937,0.97]
[null,"Alva Elementary",390,390,379,0.97,null,434,1.11]
[null,"Bayshore Elementary",544,544,519,0.95,0,513,0.94]
[null,"Bonita Springs Elementary",431,431,326,0.76,0,365,0.85]
[null,"Caloosa Elementary",989,977,997,1.02,null,965,0.99]
[null,"Cape Elementary",944,944,946,1,null,921,0.98]
[null,"Colonial Elementary",914,914,753,0.82,null,978,1.07]
[null,"Diplomat Elementary",1024,1024,961,0.94,null,861,0.84]
[null,"Edgewood Renaissance Academy",896,896,849,0.95,null,1046,1.17]
[null,"Edison Park Elementary",616,616,511,0.83,null,740,1.2]
[null,"Franklin Park Elementary",821,821,436,0.53,null,828,1.01]
[null,"Ft. Myers Beach Elementary",234,234,197,0.84,null,289,1.24]
[null,"Gateway Elementary",979,979,914,0.93,null,1089,1.11]
[null,"Gulf Elementary",1026,1026,983,0.96,null,940,0.92]
[null,"Hancock Creek Elementary",961,961,899,0.94,null,914,0.95]
[null,"Heights Elementary",837,837,754,0.9,null,921,1.1]
[null,"J. Colin English Elementary",1026,1026,731,0.71,null,753,0.73]
[null,"Lehigh Elementary",985,985,919,0.93,null,971,0.99]
[null,"Littleton Elementary",964,964,926,0.96,null,941,0.98]
[null,"Michigan Montessori K-8",976,879,636,0.72,null,1044,1.19]
[null,"Mirror Lakes Elementary",803,803,838,1.04,null,844,1.05]
[null,"NFM Academy for the Arts K-8",1560,1404,1152,0.82,null,1218,0.87]
[null,"Orange River Elementary",906,906,749,0.83,null,808,0.89]
[null,"Orangewood Elementary",822,822,774,0.94,null,857,1.04]
[null,"Pelican Elementary",1050,1050,995,0.95,null,930,0.89]
[null,"Pine Island Elementary",471,471,452,0.96,null,544,1.15]
[null,"Pinewoods Elementary",1167,1167,914,0.78,null,1047,0.9]
[null,"San Carlos Elementary",994,994,935,0.94,null,1053,1.06]
[null,"Skyline Elementary",1054,1054,995,0.94,null,868,0.82]
[null,"Spring Creek Elementary",955,955,912,0.95,null,1010,1.06]
[null,"Sunshine Elementary",1115,1115,926,0.83,null,1029,0.92]
[null,"Tanglewood Riverside Elementary",752,752,574,0.76,null,842,1.12]
[null,"The Sanibel School K-8",447,403,415,1.03,null,441,1.09]
[null,"Three Oaks Elementary",1040,1040,908,0.87,null,978,0.94]
[null,"Tice Elementary",939,939,644,0.69,null,719,0.77]
[null,"Tropic Isles Elementary",1056,1056,936,0.89,null,884,0.84]
[null,"Villas Elementary",946,946,780,0.82,null,885,0.94]
[null,"Alva Middle",842,757,686,0.91,null,736,0.97]
[null,"Bonita Springs Middle",1215,1093,1025,0.94,null,1161,1.06]
[null,"Caloosa Middle",1269,1142,1159,1.01,null,1241,1.09]
[null,"Cypress Lake Middle",1306,1175,1120,0.95,null,1110,0.94]
[null,"Diplomat Middle",1298,1168,1091,0.93,null,1271,1.09]
[null,"Ft Myers Middle Academy",1068,961,810,0.84,null,970,1.01]
[null,"Gulf Middle",1352,1216,1158,0.95,null,1258,1.03]
[null,"Lee Middle",1249,1124,1001,0.89,null,1340,1.19]
[null,"Lehigh Acres Middle",1615,1453,1290,0.89,null,1597,1.1]
[null,"P. L. Dunbar Middle",1258,1133,1037,0.92,null,1202,1.06]
[null,"Three Oaks Middle",1181,1062,1064,1,null,1129,1.06]
[null,"Trafalgar Middle",1455,1309,1281,0.98,null,1220,0.93]
[null,"Cape Coral High",1870,1776,1819,1.02,null,2307,1.3]
[null,"Cypress Lake High",2057,1954,1793,0.92,null,1710,0.88]
[null,"Dunbar High",1433,1289,272,0.21,null,1030,0.8]
[null,"Estero High",2243,2130,1758,0.83,null,1632,0.77]
[null,"Fort Myers High",1917,1821,1944,1.07,null,1612,0.89]
[null,"Lehigh Senior High 6-12",1593,1434,1463,1.02,null,2461,1.72]
[null,"Mariner High",2010,1909,1782,0.93,null,2406,1.26]
[null,"North Fort Myers High",1951,1853,1775,0.96,null,2336,1.26]
[null,"Riverdale High 6-12",1783,1604,1515,0.94,null,2789,1.74]
[null,"High Tech Center Central",825,990,127,0.13,null,139,0.14]
[null,"New Directions/LAMP",676,676,410,0.61,null,825,1.22]
[null,"High Tech Center North",367,367,73,0.2,null,82,0.22]
[null,"Royal Palm Exceptional",215,215,182,0.85,null,200,0.93]
[null,"Buckingham Exceptional",88,88,83,0.94,null,90,1.02]
[null,"Ft. Myers Edison Center",130,130,140,1.08,null,153,1.18]
[]
["2a.","LEE Total",66864,64118,56152,0.88,0,65414,1.02]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New East Zone middle school in 2000/01 (1060 proposed student stations)adjacent to Lehigh Senior High School in Lehigh to accommodate growth."]
[null,"Addition to Mirror Lakes Elementary in Lehigh in 2001/02 to alleviate overcrowding and accommodate growth (250 student stations)."]
[null,"New South Zone High school in 2001/02 (1200 proposed student stations) to relieve overcrowding and accomondate growth."]
[null,"New West Zone High school in 2001/02 (1200 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New East Zone elementary school in 2002/03 (500 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New South Zone elementary school in 2002/03 (500 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New South Zone middle school in 2002/03 (700 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New West Zone Middle school in 2002/03 (700 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New East Zone High school in 2003/04 (900 propsoed student stations) to relieve overcrowding and accommodate growth."]
[null,"New South Zone elementary school in 2003/04 (500 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New West Zone High school in 2004/05 (900 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New East Zone Middle school in 2005/06 (700 proposed student stations) to relieve overcrowding and accommodate growth."]
[null,"New South Zone Elementary school in 2005/06 (500 proposed student stations to relieve overcrowding and accommodate growth.",{"$nulls":4},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,"Allen Park Elementary",5,"LCSD/ Federal",112,null,5,0,54]
[null,"Bayshore Elementary",4,"LCSD/Federal",83,null,4,0,71]
[null,"Bonita Springs Elementary",4,"LCSD",99,null,4,0,50]
[null,"Caloosa Elementary",1,"Federal",30,null,1,0,6]
[null,"Colonial Elementary",2,"Federal",50,null,2,0,18]
[null,"Diplomat Elementary",7,"LCSD/Federal",166,null,7,0,106]
[null,"Edgewood Renaissance Academy",1,"Federal",25,null,2,1,3]
[null,"Franklin Park Elementary",4,"LCSD/Federal",93,null,4,0,50]
[null,"Gulf Elementary",3,"Federal",87,null,3,0,39]
[null,"Hancock Creek Elementary",2,"Federal",50,null,2,0,12]
[null,"J. Colin English Elementary",7,"LCSD/Federal",256,null,6,1,36]
[null,"Lehigh Elementary",3,"LCSD/Federal",75,null,3,0,30]
[null,"Littleton Elementary",1,"Federal",30,null,2,-1,3]
[null,"Michigan Montessori K-8",8,"Federal",273,null,8,0,37]
[null,"Mirror Lakes Elementary",2,"LCSD",44,null,2,0,19]
[null,"NFM Academy for Arts K-8",6,"LCSD/ Federal",108,null,0,6,138]
[null,"Orange River Elementary",9,"LCSD/ Federal",180,null,9,0,131]
[null,"Orangewood Elementary",2,"LCSD/ Federal",43,null,2,0,33]
[null,"Pelican Elementary",6,"LCSD",98,null,6,0,138]
[null,"Pine Island Elementary",1,"LCSD",25,null,1,0,5]
[null,"Pinewoods Elementary",7,"Federal",240,null,7,0,91]
[null,"San Carlos Park Elementary",1,"LCSD",37,null,1,0,3]
[null,"Skyline Elementary",9,"LCSD/ Federal",165,null,7,2,95]
[null,"Spring Creek Elementary",2,"Federal",74,null,1,1,6]
[null,"Sunshine Elementary",7,"LCSD/ Federal",190,null,7,0,92]
[null,"The Sanibel School  K-8",13,"LCSD",269,null,11,2,191]
[null,"Three Oaks Elementary",6,"LCSD/ Federal",151,null,6,0,83]
[null,"Tice Elementary",7,"LCSD/ Federal",171,null,7,0,59]
[null,"Tropic Isles Elementary",7,"Federal",150,null,6,1,117]
[null,"Villas Elementary",5,"Federal",142,null,5,0,45]
[null,"Alva Middle",6,"LCSD",144,null,6,0,114]
[null,"Cypress Lake Middle",8,"LCSD",192,null,8,0,124]
[null,"Fort Myers Middle Academy",4,"LCSD",96,null,0,4,76]
[null,"Gulf Middle",4,"LCSD",76,null,4,0,83]
[null,"Lee Middle",5,"LCSD",144,null,0,5,65]
[null,"Lehigh Acres Middle",17,"LCSD",426,null,13,4,152]
[null,"Trafalgar Middle",12,"LCSD",208,null,12,0,122]
[null,"Cape Coral High",1,"LCSD",17,null,1,0,23]
[null,"Cypress Lake High",3,"LCSD",78,null,3,0,48]
[null,"Fort Myers High",2,"LCSD",52,null,2,0,23]
[null,"High Tech Center Central",15,"LCSD",140,null,15,0,164]
[]
["2c1.","LEE Total",219,null,5089,0,195,26,"Avg Age 12.58"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"Ft Myers Middle",4,4,0,0,0,0,4]
[null,"Lee Middle",5,5,0,0,0,0,5]
[null,"The Sanibel School K-8",1,1,0,0,0,0,1]
[null,"J. Colin English Elementary",1,1,0,0,0,0,1]
[null,"Lehigh Acres Middle",4,4,0,0,0,0,4]
[null,"Spring Creek Elementary",1,1,0,0,0,0,1]
[null,"Tropic Isles Elementary",1,1,0,0,0,0,1]
[null,"Skyline Elementary",2,2,0,0,0,0,2]
[]
[]
["2c2.","LEE Total",19,19,0,0,0,0,19]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2000-01","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,"Allen Park Elementary",3,"Leased",65,9,3,65,2]
[null,"Bayshore Elementary",1,"Leased",25,9,1,25,2]
[null,"Caloosa Elementary",1,"Leased",25,2,1,25,3]
[null,"Colonial Elementary",1,"Leased",25,6,3,25,3]
[null,"Diplomat Elementary",4,"Leased",100,8,4,100,2]
[null,"Franklin Park Elementary",2,"Leased",50,8,2,50,2]
[null,"Gulf Elementary",2,"Leased",62,2,2,62,2]
[null,"J. Colin English Elementary",2,"Leased",60,1,2,60,2]
[null,"Lehigh Elementary",1,"Leased",45,9,1,25,2]
[null,"Mirror Lakes Elementary",1,"Leased",30,1,1,30,2]
[null,"Orange River Elementary",3,"Leased",75,11,3,75,2]
[null,"Pine Island Elementary",1,"Leased",25,3,1,25,2]
[null,"Pinewoods Elementary",1,"Leased",25,4,1,25,2]
[null,"San Carlos Park Elementary",1,"Leased",30,1,1,30,2]
[null,"Skyline Elementary",1,"Leased",25,2,0,0,0]
[null,"Spring Creek Elementary",1,"Leased",25,4,0,0,0]
[null,"Sunshine Elementary",2,"Leased",48,2,2,48,2]
[null,"Three Oak Elementary",2,"Leased",60,4,2,60,2]
[null,"Tice Elementary",5,"Leased",80,3,2,55,2]
[null,"Tropic Isles Elementary",2,"Leased",35,4,0,0,0]
[null,"Caloosa Middle",5,"Leased",120,1,0,0,0]
[null,"Ft Myers Middle Academy",1,"Leased",30,6,1,30,6]
[null,"Gulf Middle",1,"Leased",25,3,0,0,0]
[null,"Lehigh Acres Middle",4,"Leased",120,1,0,0,0]
[null,"Trafalgar Middle",2,"Leased",30,3,1,30,2]
[null,"Estero High",6,"Leased",172,4,0,0,0]
[null,"NFM Academy of the Arts K-8",3,"Leased",75,5,0,0,0]
[null,"The Sanibel School  K-8",3,"Leased",90,5,2,60,5]
[]
[]
[]
["2c3.","LEE Total",62,null,1577,121,36,905,49]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"Richard Milburn Academy",6,"Richard Milburn Acad/FL Inc.","2001-02",125,30,5,150]
[null,"The Island School",2,"Learn It, Inc.","2000-01",30,40,5,80]
["2c4.","LEE Total",8,null,null,155,70,10,230]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
{"$rows_empty":8}
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"Allen Park Elementary",34,806,601,17.676470588235293,779,null,22.91]
[null,"Alva Elementary",15,353,342,22.8,397,null,26.47]
[null,"Bayshore Elementary",20,498,473,23.65,467,null,23.35]
[null,"Bonita Springs Elementary",18,429,324,18,363,2,18.15]
[null,"Caloosa Elementary",35,925,945,27,913,null,26.09]
[null,"Cape Elementary",35,916,918,26.228571428571428,893,null,25.51]
[null,"Colonial Elementary",33,845,684,20.727272727272727,909,null,27.55]
[null,"Diplomat Elementary",38,948,885,23.289473684210527,785,null,20.66]
[null,"Edgewood Renaissance Academy",33,827,780,23.636363636363637,977,null,29.61]
[null,"Edison Park Elementary",24,580,475,19.791666666666668,704,null,29.33]
[null,"Franklin Park Elementary",31,778,393,12.67741935483871,785,null,25.32]
[null,"Ft Myers Beach Elementary",12,234,197,16.416666666666668,289,null,24.08]
[null,"Gateway Elementary",37,945,880,23.783783783783782,1055,null,28.51]
[null,"Gulf Elementary",37,973,930,25.135135135135137,887,null,23.97]
[null,"Hancock Creek Elementary",35,894,832,23.771428571428572,847,null,24.2]
[null,"Heights Elementary",33,803,720,21.818181818181817,887,null,26.88]
[null,"J. Colin English Elementary",30,763,468,15.6,490,null,16.33]
[null,"Lehigh Elementary",36,882,816,22.666666666666668,868,null,24.11]
[null,"Littleton Elementary",36,922,884,24.555555555555557,899,null,24.97]
[null,"Michigan Montessori K-8",32,727,484,15.125,892,null,27.88]
[null,"Mirror Lakes Elementary",30,739,774,25.8,780,10,19.5]
[null,"NFM Academy for Arts K-8",84,1994,1742,20.738095238095237,1808,null,21.52]
[null,"Orange River Elementary",32,768,611,19.09375,670,null,20.94]
[null,"Orangewood Elementary",32,753,705,22.03125,788,null,24.63]
[null,"Pelican Elementary",42,1031,976,23.238095238095237,911,null,21.69]
[null,"Pine Island Elementary",16,400,381,23.8125,473,null,29.56]
[null,"Pinewoods Elementary",38,966,713,18.763157894736842,846,null,22.26]
[null,"San Carlos Park Elementary",34,912,853,25.08823529411765,971,null,28.56]
[null,"Skyline Elementary",38,942,883,23.236842105263158,756,null,19.89]
[null,"Spring Creek Elementary",34,899,856,25.176470588235293,954,null,28.06]
[null,"Sunshine Elementary",39,1004,815,20.897435897435898,918,null,23.54]
[null,"Tanglewood Riverside Elementary",30,698,520,17.333333333333332,788,null,26.27]
[null,"The Sanibel School K-8",20,342,354,17.7,380,null,19]
[null,"Three Oaks Elementary",34,863,731,21.5,801,null,23.56]
[null,"Tice Elementary",35,716,421,12.028571428571428,496,null,14.17]
[null,"Tropic Isles Elementary",41,977,857,20.902439024390244,805,null,19.63]
[null,"Villas Elementary",37,849,683,18.45945945945946,788,null,21.3]
[null,"Alva Middle",30,757,686,22.866666666666667,736,null,24.53]
[null,"Bonita Springs Middle",41,1054,986,24.048780487804876,1122,null,27.37]
[null,"Caloosa Middle",44,1070,1087,24.704545454545453,1169,null,26.57]
[null,"Cypress Lake Middle",42,1128,1073,25.547619047619047,1063,null,25.31]
[null,"Diplomat Middle",44,1099,1022,23.227272727272727,1202,null,27.32]
[null,"Ft Myers Middle Academy",46,961,810,17.608695652173914,970,null,21.09]
[null,"Gulf Middle",41,1050,992,24.195121951219512,1092,null,26.63]
[null,"Lee Middle",39,1085,962,24.666666666666668,1301,null,33.36]
[null,"Lehigh Acres Middle",47,1269,1106,23.53191489361702,1413,null,30.06]
[null,"P. L. Dunbar Middle",43,1038,942,21.906976744186046,1107,null,25.74]
[null,"Three Oaks Middle",38,1016,1018,26.789473684210527,1083,null,28.5]
[null,"Trafalgar Middle",48,1252,1224,25.5,1163,null,24.23]
[null,"Cape Coral High",68,1702,1745,25.66176470588235,2233,null,32.84]
[null,"Cypress Lake High",80,1886,1725,21.5625,1642,null,20.53]
[null,"Dunbar High",52,1289,272,5.230769230769231,1030,null,19.81]
[null,"Estero High",79,2043,1671,21.151898734177216,1545,null,19.56]
[null,"Ft Myers High",70,1779,1902,27.17142857142857,1570,null,22.43]
[null,"Lehigh Senior High 6-12",63,1503,1532,24.317460317460316,2530,null,40.16]
[null,"Mariner High",64,1843,1716,26.8125,2340,null,36.56]
[null,"North Fort Myers High",68,1799,1721,25.308823529411764,2282,null,33.56]
[null,"Riverdale High 6-12",61,1541,1452,23.80327868852459,2726,null,44.69]
[null,"High Tech Center Central",63,990,127,2.015873015873016,139,null,2.21]
[null,"New Directions/LAMP",32,592,326,10.1875,741,null,23.16]
[null,"High Tech Center North",18,367,73,4.055555555555555,82,null,4.56]
[]
["2e.","LEE Total",2441,60014,52076,"District Avg 21",61300,12,"District Avg 25"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR AVERAGE"]
[null,"Allen Park Elementary",null,112,112,112,112,112,112,null,{"$error":"#REF!"}]
[null,"Bayshore Elementary",null,83,83,83,83,83,83]
[null,"Bonita Springs Elementary",null,99,99,99,99,99,99]
[null,"Caloosa Elementary",null,30,30,30,30,30,30]
[null,"Colonial Elementary",null,50,50,50,50,50,50]
[null,"Diplomat Elementary",null,166,166,166,166,166,166]
[null,"Edgewood Renaissance Academy",null,25,50,50,50,50,45]
[null,"Franklin Park Elementary",null,93,93,93,93,93,93]
[null,"Gulf Elementary",null,87,87,87,87,87,87]
[null,"Hancock Creek Elementary",null,50,50,50,50,50,50]
[null,"J. Colin English Elementary",null,256,220,220,220,220,227.2]
[null,"Lehigh Elementary",null,75,75,75,75,75,75]
[null,"Littleton Elementary",null,30,60,60,60,60,54]
[null,"Michigan Montessori K-8",null,273,273,273,273,273,273]
[null,"Mirror Lakes Elementary",null,44,44,44,44,44,44]
[null,"NFM Academy for Arts K-8",null,108,0,0,0,0,21.6]
[null,"Orange River Elementary",null,180,180,180,180,180,180]
[null,"Orangewood Elementary",null,43,43,43,43,43,43]
[null,"Pelican Elementary",null,98,98,98,98,98,98]
[null,"Pine Island Elementary",null,25,25,25,25,25,25]
[null,"Pinewoods Elementary",null,240,240,240,240,240,240]
[null,"San Carlos Park Elementary",null,37,37,37,37,37,37]
[null,"Skyline Elementary",null,165,129,129,129,129,136.2]
[null,"Spring Creek Elementary",null,74,37,37,37,37,44.4]
[null,"Sunshine Elementary",null,190,190,190,190,190,190]
[null,"The Sanibel School  K-8",null,269,229,229,229,229,237]
[null,"Three Oaks Elementary",null,151,151,151,151,151,151]
[null,"Tice Elementary",null,171,171,171,171,171,171]
[null,"Tropic Isles Elementary",null,150,129,129,129,129,133.2]
[null,"Villas Elementary",null,142,142,142,142,142,142]
[null,"Alva Middle",null,144,144,144,144,144,144]
[null,"Cypress Lake Middle",null,192,192,192,192,192,192]
[null,"Fort Myers Middle Academy",null,96,0,0,0,0,19.2]
[null,"Gulf Middle",null,76,76,76,76,76,76]
[null,"Lee Middle",null,144,0,0,0,0,28.8]
[null,"Lehigh Acres Middle",null,426,326,326,326,326,346]
[null,"Trafalgar Middle",null,208,208,208,208,208,208]
[null,"Cape Coral High",null,17,17,17,17,17,17]
[null,"Cypress Lake High",null,78,78,78,78,78,78]
[null,"Fort Myers High",null,52,52,52,52,52,52]
[null,"High Tech Center Central",null,140,140,140,140,140,140]
[]
["2f.","LEE Total students in relocatables by year",null,5089,4526,4526,4526,4526,4638.6]
[null,"Total number of CO-FTE students projected by year",null,57847,59717,61583,63480,65414,61608.2]
[null,"Percent in relocatables by year",null,0.09,0.08,0.07,0.07,0.07,0.08]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"The Sanibel School K-8","new Dining, Rem Bldg 01; 3 new CR",6990530,394,35000,88.83,0,0,0,17742.46,0,0,0]
[null,"New East Zone Middle",2,15562920,1060,141366,133.36,86,86,165,14682,9863,13571,18853]
[null,"Mirror Lakes Elementary","Build out additional wing",3201250,250,15000,60,0,0,0,12805,0,0,0]
[null,"South Zone High School",3,23314800,1200,140000,116.67,68,68,222,19429,14900,18106,26448]
[null,"West Zone High ",3,23314800,1200,140000,116.67,68,68,222,19429,14900,18106,26448]
[]
["3a.","LEE Total 2001-02",null,72384300,4104,471366,114.86,null,null,null,17637.5]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"South Zone Middle",2,10547600,700,90000,128.57,86,86,165,15068,9863,13571,18853]
[null,"West Zone Middle",2,10547600,700,140000,200,86,86,165,15068,9863,13571,18853]
[null,"East Zone Elementary",1,6571000,500,55000,110,79,79,156,13142,9213,12712,22844]
[null,"South Zone Elementary",1,6571000,500,55000,110,79,79,156,13142,9213,12712,22844]
["3b","LEE Total 2002-03",null,34237200,2400,340000,141.67,null,null,null,14265.5]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"East Zone High",3,18425700,900,140000,155.56,68,68,222,20473,14900,18106,26448]
[null,"South Zone Elementary",1,6747000,500,55000,110,79,79,156,13494,9213,12712,22844]
[{"$nulls":7},0,0,0,null,0,0,0]
["3c","LEE Total 2003-04",null,25172700,1400,195000,139.29,null,null,null,17980.5]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"West Zone High",3,18906300,900,140000,155.56,68,68,222,21007,14900,18106,26448]
[{"$nulls":11},0,0,0]
["3d.","LEE Total 2004-05",null,18906300,900,140000,155.56,null,null,null,21007]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"East Zone Middle",2,11400000,700,90000,128.57,86,86,165,16285.71,9863,13571,18853]
[null,"South Zone Elementary",1,7100000,500,55000,110,79,79,156,14200,9213,12712,22844]
[{"$nulls":11},0,0,0]
[{"$nulls":11},0,0,0]
["3e","LEE Total 2005-06",null,18500000,1200,145000,120.83,null,null,null,15416.67]
[]
["3f.","LEE 5-Year Total",null,169200500,10004,1291366]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,60458620,62272379,64140550,66064767,68046710,320983026]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,60458620,62272379,64140550,66064767,68046710,320983026,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,3234750,3396488,3566312,3744627,3931859,17874036,0.06]
[null,"  less amount used to purchase other vehicles",null,552500,550000,550000,550000,550000,2752500,0.01]
[null,"  less amount transferred to operating budget for maintenance/repair",null,3117259,1246903,null,null,null,4364162,0.01]
[null,"less amount transferred to Charter Schools",null,19394,{"$nulls":4},19394,0]
[null,"  less amount used for maintenance/repair",null,6460393,4705078,4891031,4914533,4765710,25736745,0.08]
[null,"less amount for construction services projects",null,2000000,1940000,1940000,2040000,1940000,9860000,0.03]
[null,"less amount for safety & inspections",null,244830,244000,255000,268000,236000,1247830,0]
[null,"  less amount used to purchase capital outlay equipment",null,3262247,3304595,355085,3493811,3691001,14106739,0.04]
[null,"  less amount transferred to operating budget for salaries",null,5208999,5521538,5852831,6204000,6576240,29363608,0.09]
[null,"less amount used for county-wide roof replacement",null,671230,500000,500000,500000,500000,2671230,0.01]
[null,"less amount used to upgrade portables",null,2824714,2320000,240000,240000,240000,5864714,0.02]
[null,"  less amount used to pay debt service for s.237 loans",null,7004496,3600000,3450000,3300000,3150000,20504496,0.06]
[null,"  less amount to pay debt service for COP's ",null,19391635,19778254,19774216,19776700,19773426,98494231,0.31]
[null,"less amount used for transportation facilities upgrades",null,2247783,{"$nulls":4},2247783,0.01]
[null,"less amount used to upgrade technology",null,3123464,2360000,2500000,2630000,2761500,13374964,0.04]
[null,"less amount used for county-wide HVAC",null,7070531,1410500,1200000,1200000,1200000,12081031,0.04]
[null,"less amount used for safety to life corrections",null,7179486,3350000,10628131,3647000,1500000,26304617,0.08]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,-13155091,8045023,8437944,13556096,17230974,34114946,0.11,0.11]
[null,"Carried over funds",null,59734242,15787589,33312860,46128291,66963167,221926149]
[null,"P E C O New Construction",null,6104721,4478485,2652939,2263631,2355514,17855290,null,0.06]
[null,"PECO maintenance",null,3184726,2724750,2515950,2438297,2445200,13308923,null,0.04]
[null,"PECO Carryover  ",null,388723,{"$nulls":4},388723]
[null,"Interest & Miscellaneous Revnue",null,3417394,1562500,1597800,1690055,1686550,9954299]
[null,"C O & D S maximum potential bond proceeds",null,604299,714514,805798,886798,913402,3924811,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,null,0]
[null,"Proceeds from a s.237 loan",{"$nulls":6},0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",{"$nulls":6},0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",{"$nulls":6},0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",{"$nulls":6},0,null,0]
[null,"Effort Index Grants",{"$nulls":6},0]
[null,"Impact fees received",{"$nulls":6},0,null,0]
[null,"Private donations",{"$nulls":6},0,null,0]
[null,"Grants from local governments or not-for-profit organizations",{"$nulls":6},0,null,0]
["4.","LEE Total",null,60279014,33312861,49323291,66963168,91594807,301473141,1,0.22]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Completion of (2)Elementary School projects",null,353696,{"$nulls":4},353696]
[null,"Completion of (3) Middle School projects",null,1071084,{"$nulls":4},1071084]
[null,"Completion of (3) High School projects",null,842655,{"$nulls":4},842655]
[null,"Cape Coral High",70,3527033,{"$nulls":4},3527033]
[null,"The Sanibel School",394,6990530,{"$nulls":4},6990530]
[null,"NFMAA K-8",1404,19091555,{"$nulls":4},19091555]
[null,"Lee Middle",50,1249275,{"$nulls":4},1249275]
[null,"Lehigh Sr. High",336,399370,{"$nulls":4},399370]
[null,"New Dunbar High",1130,9957464,{"$nulls":4},9957464]
[null,"East Zone Middle",1060,1000000,{"$nulls":4},1000000]
[null,"Land-East Zone Schools",null,500000,{"$nulls":4},500000]
[]
["5.","LEE Total",4444,44982662,0,0,0,0,44982662]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","LEE Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"East Zone Middle",1060,14562920,{"$nulls":4},14562920]
[null,"Mirror Lakes Addition",250,3201250,{"$nulls":4},3201250]
[null,"Land-South Zone High",null,6000000,{"$nulls":4},6000000]
[null,"South Zone High",1200,23314800,{"$nulls":4},23314800]
[null,"Land-West Zone High",null,3200000,{"$nulls":4},3200000]
[null,"West Zone High",1200,23314800,{"$nulls":4},23314800]
[null,"Land-South Zone Middle",null,null,3900000,null,null,null,3900000]
[null,"South Zone Middle",700,null,10547600,null,null,null,10547600]
[null,"land-West Zone Middle",null,null,2080000,null,null,null,2080000]
[null,"West Zone Middle",null,null,10547600,null,null,null,10547600]
[null,"East Zone Elementary",500,null,6571000,null,null,null,6571000]
[null,"Land-South Zone Elementary",null,null,2433600,null,null,null,2433600]
[null,"South Zone Elementary",500,null,6571000,null,null,null,6571000]
[null,"East Zone High",900,null,null,18425700,null,null,18425700]
[null,"Land-South Zone Elementary",null,null,null,2433600,null,null,2433600]
[null,"South Zone Elementary",500,null,null,6747000,null,null,6747000]
[null,"Land-West Zone High",{"$nulls":4},3600000,null,3600000]
[null,"West Zone High",900,null,null,null,18906300,null,18906300]
[null,"Land-South Zone Elementary",{"$nulls":5},2632200,2632200]
[null,"South Zone Elementary",500,{"$nulls":4},7100000,7100000]
[null,"Land-East Zone Middle",{"$nulls":5},1462350,1462350]
[null,"East Zone Middle",700,{"$nulls":4},11400000,11400000]
[{"$nulls":8},0]
["7.","LEE Total",7850,73593770,42650800,27606300,22506300,22594550,188951720]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[null,"SCHOOL BOARD OF ","LEE  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"John W. Sanders, Ed. D."]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"Robert C. Spencer",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  ______________________________________________________________________________________________________________________________",null,null,"Michael Olliff","Budget Director","(941) 337-8217",null,null,null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}