{"text_format":"2","workbook":"xls","n_sheets":5,"sheets":["*****","XXXXXXX","0000000","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"XXXXXXX","index":1,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"0000000","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":3,"n_rows":275,"n_cols":25,"rows_kept":275,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["LIBERTY  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["LIBERTY   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"LIBERTY","Date: ==>","2001-12-11",null,"For fiscal years","2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-2002","2002-2003","2003-2004","2004-2005","2005-2006"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"HVAC UPGRADES",{"$nulls":6},0]
[{"$nulls":8},0]
[null,"Install HVAC in Main Building","Hosford Pre-K-8",null,null,75000,null,null,75000]
[null,"Install HVAC ","District Bus Barn",null,null,null,93492,null,93492]
[null,"Building Preservation",{"$nulls":6},0]
[null,"Siding on main classroom Bldg.","Hosford Pre-K-8",null,null,50000,null,null,50000]
[null,"Renovation of Facilities",{"$nulls":6},0]
[null,"Re-Roof ROTC Building","LCHS",null,50000,null,null,null,50000]
[{"$nulls":8},0]
[null,"Other",{"$nulls":6},0]
[null,"Build Library","Hosford School",{"$nulls":4},330000,330000]
[null,"Surface Water Drain Vocation Wing","LCHS",null,30000,null,null,null,30000]
[null,"Build New Bus Garage","County Wide",null,null,300000,null,null,300000]
[null,"Build New Pump House","Hosford School",26000,{"$nulls":4},26000]
[null,"Build Ag Tractor Shed","LCHS",null,null,null,80000,null,80000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["1.","LIBERTY Total",null,26000,80000,425000,173492,330000,1034492]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Build ESE Suite ","Hosford School",null,null,250000,null,null,250000]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2 .","LIBERTY Total",null,0,0,250000,0,0,250000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2001-02 FISH  Satisfactory","Actura 2001-02","Acutal 2001-02","Actual 2001-02","New Stu Capacity to","Projected 2005-06","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Tolar School",722,722,580,0.8,0,750,1.04]
[null,"Liberty County High",688,668,null,0,104,700,0.91]
[null,"Hosford K-8",265,265,null,0,0,275,1.04]
[{"$nulls":5},{"$error":"#DIV/0!"},0,0,{"$error":"#DIV/0!"}]
[{"$nulls":5},{"$error":"#DIV/0!"},300,0,0]
["2a.","LIBERTY Total",1675,1655,580,0.35,404,1725,0.84]
[]
["2b.","Proposed Location of Planned Facilities"]
[]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"County Office",3,"LCSB",150,0,0,0,30]
[null,"Liberty County High",2,"LCSB",100,0,0,-2,20]
[null,"Hosford K-8",1,"LCSB",30,0,0,-1,10]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
["2c1.","LIBERTY Total",6,null,280,0,0,-3,"Avg Age 10"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"Tolar School",0,0,0,0,0,0,0]
[null,"Liberty County High",2,0,0,0,2,0,2]
[null,"Hosford K-8",1,0,0,0,1,0,1]
[{"$nulls":8},0]
["2c2.","LIBERTY Total",3,0,0,0,3,0,3]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05","FISH Stu. Sta.","# Years Leased "]
[null,"None"]
[]
["2c3.","LIBERTY Total",0,null,0,0,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2004-05"]
[null,"None",{"$nulls":6},0]
[{"$nulls":8},0]
["2c4.","LIBERTY Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[null,"The Liberty County School Board plans for milti-track scheduling or any other alternatives to reduce the need for permanent student stations."]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2001-02 CO-FTE","1999-00 Class size","2005-06  CO-FTE","be added (removed)","2005-06 Class Sixe"]
[null,"Tolar School",29,722,580,20,750,null,25.86]
[null,"Liberty County High",25,450,299,11.96,500,null,20]
[null,"Hosford K-8",16,204,227,14.19,250,null,15.63]
[{"$nulls":5},{"$error":"#DIV/0!"},null,null,{"$error":"#DIV/0!"}]
[{"$nulls":5},{"$error":"#DIV/0!"},null,null,{"$error":"#DIV/0!"}]
["2e.","LIBERTY Total",70,1376,1106,"District Avg 16",1500,0,"District Avg 21"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-2002","2002-2003","2003-2004","2004-2005","2005-2006","5 YEAR AVERAGE"]
[null,"Tolar School",null,0,0,0,0,0,0,null,0]
[null,"Liberty County High",null,60,0,0,0,0,12]
[null,"Hosford K-8",null,30,0,0,0,0,6]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2f.","LIBERTY Total students in relocatables by year",null,90,0,0,0,0,18]
[null,"Total number of CO-FTE students projected by year",null,1124,1124,1137,1142,1312,1167.8]
[null,"Percent in relocatables by year",null,0.08,0,0,0,0,0.02]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01","2001-02","2002-03","2003-04","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No planned projects for new student stations.",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","LIBERTY Total 2000-01",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No planned projects for new student stations.",{"$nulls":5},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","LIBERTY Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No planned projects for new student stations.",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","LIBERTY Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No planned projects for new student stations.",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","LIBERTY Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No planned projects for new student stations.",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","LIBERTY Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","LIBERTY 5-Year Total",null,0,0,0]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,null,0,0,0,0,0]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,null,0,0,0,0,0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,null,0,0,0,0,0,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to purchase other vehicles",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used for maintenance/repair",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to purchase capital outlay equipment",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less amount to pay debt service for COP's ",null,0,0,0,0,0,0,{"$error":"#DIV/0!"}]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,{"$error":"#DIV/0!"},"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,0,0,0,0,0,{"$error":"#DIV/0!"},0]
[null,"P E C O New Construction",null,43436,27136,21998,18770,19532,130872,null,1]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","LIBERTY Total",null,43436,27136,21998,18770,19532,130872,{"$error":"#DIV/0!"},1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"None",{"$nulls":6},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["5.","LIBERTY Total",0,0,0,0,0,0,0]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,null,0,0,0,0,0]
["6.","LIBERTY Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02","2002-03","2003-04","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"None",{"$nulls":6},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["7.","LIBERTY Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02","2002-03","2003-04","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","Check Totals","","","Check Totals"]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
[null,"Respectfully submitted this 15th day of August, 2000","of September 2000"]
[]
[null,"SCHOOL BOARD OF ","LIBERTY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Anthony L. Anderson"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"Sam Carnley",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Glenn Moore","Director of Administarion","(850)643-2275","ext.236","anderson_t2@popmail.firn.edu",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":4,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}