{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":292,"n_cols":25,"rows_kept":292,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Madison  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Madison   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Madison","Date: ==>","2000-09-19",null,"For fiscal years","  2000-2001 through 2004-2005"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety",{"$nulls":6},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"HVAC Upgrades",{"$nulls":6},0]
[null,"Replace Chiller/Convert Air Handler",{"$nulls":6},0]
[null,"to be in compliance with CAA","Madison County High School",null,607193,null,null,null,607193]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Waste Water Retention",{"$nulls":6},0]
[{"$nulls":8},0]
[null,"Roofing",{"$nulls":6},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"EPA Fuel Tank Replacement",{"$nulls":6},0]
[null,"Flooring",{"$nulls":6},0]
[{"$nulls":8},0]
[null,"Other",{"$nulls":6},0]
[{"$nulls":8},0]
["1.","Madison Total",null,0,607193,0,0,0,607193]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Completion of Greenville Elementary School (Greenville Middle)",null,566052,0,0,0,0,566052]
[null,"Completion of Madison K-08 School",null,13500845,0,0,0,0,13500845]
[null,"New Elementary School \"C\" (Lee Elementary School)",null,4434485,0,0,0,0,4434485]
[null,"Payback to DOE for SFTF",null,0,572692,631356,635260,645640,2484948]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["2 .","Madison Total",null,18501382,572692,631356,635260,645640,20986330]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1999-00 FISH Satisfactory","Actual 1999-00","Actual 1999-00","Actual 1999-00","New Stu Capacity to","Projected 2004-05","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Madison County High School",1257,1131,921,0.81,0,1004,0.89]
[null,"Madison K-08 School",0,0,null,{"$error":"#DIV/0!"},1617,1396,0.86]
[null,"Madison Primary School",956,956,751,0.79,-956,null,{"$error":"#DIV/0!"}]
[null,"Madison Middle School",1078,970,594,0.61,-970,null,{"$error":"#DIV/0!"}]
[null,"Greenville Primary School",200,200,175,0.88,-200,null,{"$error":"#DIV/0!"}]
[null,"Greenville Elementary School",447,402,214,0.53,-142,260,1]
[null,"Lee Elementary School",340,306,272,0.89,-306,null,{"$error":"#DIV/0!"}]
[null,"Pinetta Elementary School",266,239,239,1,-39,125,0.63]
[null,"New Elementary School \"C\"",null,null,null,{"$error":"#DIV/0!"},200,200,1]
["2a.","Madison Total",4544,4204,3166,0.75,-796,2985,0.88]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Comb. School \"AA\" (Madison K-08) in Madison, FL to replace Madison Primary, Madison Middle and take 6th, 7th, and 8th grades from Pinetta, Greenville, and Lee."]
[null,"New Elementary School \"C\" in Lee, FL to replace Lee Junior High School"]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"Madison County High School",2,"MCSB",59,null,2,0,38]
[null,"Madison Primary School",13,"MCSB",289,44,null,13,528]
[null,"Greenville Primary School",4,"MCSB",88,88,null,4,120]
[null,"Lee Elementary School",2,"MCSB",45,null,null,2,44]
[null,"Pinetta Elementary School",2,"MCSB",43,null,null,2,46]
[{"$nulls":7},0]
["2c1.","Madison Total",23,null,524,132,2,21,"Avg Age 33.74"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"None",{"$nulls":6},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","Madison Total",0,0,0,0,0,0,0]
[]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05","FISH Stu. Sta.","# Years Leased "]
[null,"Lee Elementary School",2,"LEASED",50,1,0,0,0]
[null,"Greenville Elementary School",6,"LEASED",150,1,0,0,0]
["2c3.","Madison Total",8,null,200,2,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2004-05"]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c4.","Madison Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[null,"The Madison County High School has utilized block scheduling for the past four years and will continue for the 2000-2001 school year"]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"Madison County High School",48,1131,921,19.19,1004,0,20.92]
[null,"Madison Primary School",41,956,708,17.27,null,null,0]
[null,"Madison Middle School",43,970,594,13.81,null,null,0]
[null,"Greenville Primary School",10,200,165,16.5,null,null,0]
[null,"Greenville Elementary School",17,402,214,12.59,260,0,15.29]
[null,"Lee Elementary School",15,306,270,18,null,0,0]
[null,"Pinetta Elementary School",10,239,239,23.9,125,0,12.5]
[null,"Madison K-08 School",43,null,null,0,1396,null,32.47]
[null,"New Elementary School \"C\"",14,null,null,0,200,0,14.29]
["2e.","Madison Total",241,4204,3111,"District Avg 13",2985,0,"District Avg 12"]
{"$rows_empty":7}
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR AVERAGE"]
[null,"Madison County High School",null,50,50,50,50,50,50,null,70]
[null,"Madison Primary School",null,200,0,0,0,0,40]
[null,"Greenville Elementary School",null,150,0,0,0,0,30]
[null,"Lee Elementary School",null,50,0,0,0,0,10]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["2f.","Madison Total students in relocatables by year",null,450,50,50,50,50,130]
[null,"Total number of CO-FTE students projected by year",null,3184,3162,3135,3072,3046,3119.8]
[null,"Percent in relocatables by year",null,0.14,0.02,0.02,0.02,0.02,0.04]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"Madison Primary School","Will close after Madison K-08 opens."]
[null,"Madison Middle School","Will close after Madison K-08 opens."]
[null,"Greenville Primary School","This facility is closed.  Students are now attending Greenville Elementary School"]
[null,"Lee Elementary School","Will close after New Elementary School \"C\" opens.",{"$nulls":7},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01 ","2000-01 ","2000-01 ","2000-01 ","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Greenville Elementary School",1,3441986,230,26653,115.88,70,107,174,14965.16,7485,11173,16419]
[null,"Madison K-08 School",2,25783310,1797,215000,119.64,88,88,180,14347.97,7226,13517,18473]
[null,"New Elementary School \"C\"",1,3700000,200,39500,197.5,70,70,174,18500,7485,11173,16419]
["3a.","Madison Total 2000-01",null,32925296,2227,281153,126.25,null,null,null,14784.6]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","Madison Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","Madison Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","Madison Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","Madison Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","Madison 5-Year Total",null,32925296,2227,281153]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,666629,675000,710000,735000,760000,3546629]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,666629,675000,710000,735000,760000,3546629,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,166657,168750,177500,183750,190000,886657,0.24999992951053]
[null,"  less amount used to purchase other vehicles",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",{"$nulls":6},0,0]
[null,"  less amount used for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase capital outlay equipment",null,0,0,0,0,0,0,0]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",{"$nulls":6},0,0]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,499972,506250,532500,551250,570000,2659972,0.75000007048947,0.13]
[null,"P E C O New Construction",{"$nulls":6},0,null,0]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,null,39442,71856,57010,48640,216948,null,0.01]
[null,"C O & D S Distributed to District",null,58765,27000,27000,27000,27000,166765,null,0.01]
[null,"General Revenue",null,65731,0,0,0,0,65731,null,0]
[null,"Principal State School Trust Fund",null,8971,0,0,0,0,8971,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,null,0,0,0,0,0,null,0]
[null,"Effort Index Grants Cash Carryover",null,196639,0,0,0,0,196639]
[null,"Smart Schools Clearinghouse Cash Carryover",null,134927,0,0,0,0,134927,null,0.01]
[null,"Special Facilities Trust Fund Cash Carryover & Interest",null,435720,0,0,0,0,435720,null,0.02]
[null,"Special Facilities Trust Fund",null,17100657,0,0,0,0,17100657,null,0.81]
["4.","Madison Total",null,18501382,572692,631356,635260,645640,20986330,1,0.9900000000000001]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Completion of Madison K-08 School",1617,13500845,0,0,0,0,13500845]
[null,"New Elementary School \"C\"",200,4434485,0,0,0,0,4434485]
[null,"Completion of Greenville Elementary School",260,566052,0,0,0,0,566052]
[null,"Payback to DOE for SFTF",null,0,572692,631356,635260,645640,2484948]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["5.","Madison Total",2077,18501382,572692,631356,635260,645640,20986330]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","Madison Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,null,null,0,0,0,0,null,0]
[null,null,null,0,0,null,0,0,0]
[null,null,null,0,0,0,null,0,0]
["7.","Madison Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2000."]
[]
[null,"SCHOOL BOARD OF ","Madison  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}