{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":2,"defined_names":4,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":629,"n_cols":26,"rows_kept":629,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["MARION COUNTY  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["MARION COUNTY   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":9},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":9},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"MARION COUNTY","Date: ==>","2001-10-01",null,"For fiscal years",null,"  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ",null,"2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost",null,"Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety",{"$nulls":7},0]
[null,"   ADA Compliance","Districe-wide",300000,200000,200000,200000,null,200000,1100000]
[null,"   Safety-to-life","Districe-wide",218963,187338,172982,167643,null,168118,915044]
[null,"Repairs"]
[null,"   General Repairs","Districe-wide",1700000,1350000,1350000,1350000,null,1350000,7100000]
[null,"HVAC/ROOFING",{"$nulls":7},0]
[null,"Re-roofing","Anthony                     ",null,206000,{"$nulls":4},206000]
[null,"HVAC","Anthony                    ",null,null,null,260000,null,null,260000]
[null,"HVAC/Reroofing","AV/ITV              ",75000,{"$nulls":5},75000]
[null,"HVAC/Reroofing","Belleview El        ",null,385000,{"$nulls":4},385000]
[null,"HVAC","Belleview El             ",null,null,365000,null,null,null,365000]
[null,"HVAC","Belleview Santos",500000,{"$nulls":5},500000]
[null,"HVAC","Belleview Santos        ",null,null,260000,null,null,null,260000]
[null,"HVAC/Reroofing","Central Warehouse ",null,217000,{"$nulls":4},217000]
[null,"HVAC","Dr. N. H. Jones      ",null,null,null,150000,null,null,150000]
[null,"Re-roofing","Dr. N. H. Jones         ",{"$nulls":5},315000,315000]
[null,"HVAC/Reroofing","Dunnellon Mid.   ",null,null,null,300000,null,null,300000]
[null,"HVAC","Dunnellon Mid.           ",null,150000,{"$nulls":4},150000]
[null,"Re-roofing","Dunnellon Mid.          ",{"$nulls":5},340000,340000]
[null,"Re-roofing","Dunnellon Hi.             ",1400000,{"$nulls":5},1400000]
[null,"HVAC","Dunnellon Hi.             ",null,297000,{"$nulls":4},297000]
[null,"HVAC","Dunnellon Hi.             ",null,null,260000,null,null,null,260000]
[null,"HVAC","East Marion               ",446000,{"$nulls":5},446000]
[null,"HVAC/Reroofing","Eighth Street, Caf",null,139000,{"$nulls":4},139000]
[null,"HVAC","EMS Controls            ",25000,{"$nulls":5},25000]
[null,"Re-roofing","Facilities Complex      ",null,null,null,365000,null,null,365000]
[null,"HVAC","Fessenden                ",null,null,null,460000,null,null,460000]
[null,"Re-roofing","Forest                       ",{"$nulls":5},1550000,1550000]
[null,"HVAC","Fort King                   ",null,89000,{"$nulls":4},89000]
[null,"HVAC","Fort McCoy                ",{"$nulls":5},220000,220000]
[null,"HVAC","Hillcrest                     ",{"$nulls":5},40000,40000]
[null,"HVAC","Howard Academy      ",{"$nulls":5},275000,275000]
[null,"HVAC","Lake Weir Hi.            ",540000,{"$nulls":5},540000]
[null,"HVAC","Lake Weir Mid.           ",null,null,325000,null,null,null,325000]
[null,"HVAC","Lake Weir Mid.           ",{"$nulls":5},110000,110000]
[null,"HVAC","North Marion Hi.        ",null,null,null,55000,null,null,55000]
[null,"HVAC","North Marion Mid.       ",null,null,285000,null,null,null,285000]
[null,"HVAC/Reroofing","Oakcrest          ",null,null,280000,null,null,null,280000]
[null,"HVAC","Oakcrest                   ",{"$nulls":5},310000,310000]
[null,"HVAC/Reroofing","South Ocala       ",null,380000,{"$nulls":4},380000]
[null,"Re-roofing","South Ocala              ",null,null,null,780000,null,null,780000]
[null,"HVAC","South Ocala              ",{"$nulls":5},400000,400000]
[null,"HVAC/Reroofing","Sparr              ",null,275000,{"$nulls":4},275000]
[null,"HVAC","Sparr                        ",{"$nulls":5},205000,205000]
[null,"HVAC","Stanton-Weirsdale    ",null,null,null,305000,null,null,305000]
[null,"HVAC","Vanguard                 ",212000,{"$nulls":5},212000]
[null,"HVAC/Reroofing","Ward-Highlands ",null,null,900000,null,null,null,900000]
[null,"HVAC/Reroofing","Wyomina Park  ",null,null,300000,null,null,null,300000]
[null,"HVAC","Portable Classrooms ",44000,{"$nulls":5},44000]
[null,"MAJOR MAINTENANCE",{"$nulls":7},0]
[null,"Paint","Belleview Mid.                    ",null,10000,{"$nulls":4},10000]
[null,"Paint","Belleview Hi.                       ",null,null,10000,null,null,null,10000]
[null,"Paint","County Office                      ",null,12000,{"$nulls":4},12000]
[null,"Paint","Dunnellon El.                     ",null,null,38000,null,null,null,38000]
[null,"Paint","Dunnellon Mid.                     ",null,null,4500,null,null,null,4500]
[null,"Doors","Dunnellon Hi.                      ",12000,{"$nulls":5},12000]
[null,"Paint","Emerald Shores                  ",null,null,6500,null,null,null,6500]
[null,"Paint","Facilities Complex               ",null,null,100000,null,null,null,100000]
[null,"Paint","Fessenden                         ",null,null,20000,null,null,null,20000]
[null,"Interior","Fessenden                               ",null,null,175000,null,null,null,175000]
[null,"Doors","Fessenden                         ",null,null,null,50000,null,null,50000]
[null,"Doors","Forest                               ",null,null,50000,null,null,null,50000]
[null,"Plumbing","Forest                               ",null,12500,{"$nulls":4},12500]
[null,"Electrical","Forest                               ",{"$nulls":5},1000000,1000000,null,null,1000000]
[null,"Plumbing","Fort King                           ",7500,{"$nulls":5},7500]
[null,"Paint","Howard Mid.                       ",160000,{"$nulls":5},160000]
[null,"Plumbing","Howard Mid.                      ",null,null,14000,null,null,null,14000]
[null,"Plumbing","Howard Mid.                       ",7500,{"$nulls":5},7500]
[null,"Carpet","Lake Weir Hi.                     ",100000,{"$nulls":5},100000]
[null,"Plumbing","Lake Weir Hi.                    ",null,7500,{"$nulls":4},7500]
[null,"Plumbing","Lake Weir Mid.                  ",{"$nulls":5},5000,5000,null,null,5000]
[null,"Carpentry","North Marion Hi.             ",25000,{"$nulls":5},25000]
[null,"Plumbing","North Marion Hi.                    ",null,null,13500,null,null,null,13500]
[null,"Hardware","North Marion Hi.                ",null,25000,{"$nulls":4},25000]
[null,"Paint","North Marion Mid.              ",162000,{"$nulls":5},162000,null,"Exterior"]
[null,"Floor","North Marion Mid.               ",60000,{"$nulls":5},60000]
[null,"Electrical","Oakcrest                           ",{"$nulls":5},30000,30000,null,null,30000]
[null,"Paint","Oakcrest                         ",45000,{"$nulls":5},45000]
[null,"Canopy","Ocala Springs                     ",null,null,125000,null,null,null,125000]
[null,"Doors","Osceola Mid.                      ",15000,{"$nulls":5},15000]
[null,"Paint","Reddick-Collier                    ",null,10000,{"$nulls":4},10000]
[null,"Drainage","Romeo                               ",null,null,15000,null,null,null,15000]
[null,"Lights","South Ocala                       ",null,170624,{"$nulls":4},170624]
[null,"Drainage","South Ocala                       ",{"$nulls":5},100000,100000,null,null,100000]
[null,"Electrical","South Ocala                       ",null,null,null,100000,null,null,100000]
[null,"Paint","Stanton-Weirsdale               ",30000,{"$nulls":5},30000]
[null,"Ceilings","Stanton-Weirsdale               ",null,null,null,20000,null,null,20000]
[null,"Paint","Thelma Parker Center          ",48000,{"$nulls":5},48000]
[null,"Plumbing","Vanguard                          ",null,5000,{"$nulls":4},5000]
[null,"Electrical","Ward-Highlands                  ",null,null,null,50000,null,null,50000,null,"Service Change"]
[null,"Plumbing","Wyomina Park                  ",null,null,15000,null,null,null,15000]
[null,"RENOVATIONS",{"$nulls":7},0]
[null,null,"Anthony                        ",null,null,33000]
[null,null,"Belleview El                  ",null,42000]
[null,null,"Belleview El                  ",null,null,150000]
[null,null,"Dr. N. H. Jones              ",50000]
[null,null,"Dr. N. H. Jones              ",null,null,40000]
[null,null,"Eighth Street(carry over)                ",250000]
[null,null,"Fessenden                    ",null,34000]
[null,null,"Hillcrest",null,250000]
[null,null,"Howard Academy",null,null,null,13000]
[null,null,"Howard Mid.                ",92500]
[null,null,"LPC                              ",200000]
[null,null,"North Marion Hi.             ",null,231028]
[null,null,"North Marion Mid.            ",3000000]
[null,null,"North Marion Mid.            ",null,50000]
[null,null,"Oakcrest                        ",null,null,115000]
[null,null,"Oakcrest-  Fire alarm/PA",null,null,50000]
[null,null,"Portables- Vinyl                     ",37836]
[null,null,"Portables- Alarms/DCA",200000]
[null,null,"South Ocala                      ",null,null,50000]
[null,null,"Sparr                            ",null,null,25000]
[null,null,"Stanton-Weirsdale- Alarm/PA",null,50000]
[null,null,"Ward-Highlands--alarm/PA",null,null,50000]
[]
[{"$nulls":9},0]
["1.","MARION COUNTY TOTAL",null,9963299,4784990,5797482,4625643,null,6618118,26776168]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ",null,"2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost",null,"Projected Cost","5 YEAR TOTAL"]
[null,"Classroom wing addition","Anthony",1750000,{"$nulls":5},1750000]
[null,"Fieldhouse","Belleview Hi.             ",125000,{"$nulls":5},125000]
[null,"Media/caf/classrooms","Dunnellon Mid.",null,null,4000000,null,null,null,4000000]
[null,"Classroom wing addition","East Marion",2400000,{"$nulls":5},2400000]
[null,"Cafeteria/classrooms","Eighth Street ",{"$nulls":5},4000000,4000000]
[null,"Replacement Facility Site","Forest Hi.",1500000,{"$nulls":5},1500000]
[null,"Replacement Facility","Forest Hi. ",100000,34900000,5000000,null,null,null,40000000]
[null,"Greenhouse","Fort King Middle",30000,{"$nulls":5},30000]
[null,"Classroom wing addition","Hillcrest",4000000,{"$nulls":5},4000000]
[null,"Classroom wing addition","North Marion Hi",3850000,250000,{"$nulls":4},4100000]
[null,"Cafeteria","North Marion Mid",{"$nulls":5},1000000,1000000]
[null,"Classroom wing addition","Oakcrest",null,3500000,{"$nulls":4},3500000]
[null,"Playgrounds","Playgrounds",50000,{"$nulls":5},50000]
[null,"Cafeteria/classrooms","Stanton-Weirsdale",null,2500000,{"$nulls":4},2500000]
[null,"Equip. Storage Shed","Technical Services    ",100000,{"$nulls":5},100000]
[null,"Classroom wing addition","Ward-Highlands",null,null,3500000,null,null,null,3500000]
[null,"Equipment","West Port Hi.  ",200000,{"$nulls":5},200000]
[null,"Equipment","West Port Mid.  ",100000,{"$nulls":5},100000]
[{"$nulls":9},0]
["2 .","MARION COUNTY Total",null,14205000,41150000,12500000,0,null,5000000,72855000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-2001","New Stu Capacity to",null,"Projected 2005-06","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)",null,"CO-FTE ","Utilization"]
[null,"   ELEMENTARY"]
[null,"Anthony",379,379,322,0.85,35,414,308,0.74]
[null,"Belleview",1281,1281,747,0.58,-357,924,714,0.77]
[null,"Belleview-Santos",852,852,750,0.88,-112,740,717,0.97]
[null,"College Park",762,762,534,0.7,-62,700,511,0.73]
[null,"Dr. N. H. Jones",983,983,572,0.58,-208,775,547,0.71]
[null,"Dunellon ",765,765,630,0.82,-59,706,602,0.85]
[null,"East Marion",831,831,793,0.95,-67,764,758,0.99]
[null,"Eighth Street",757,757,397,0.52,-400,357,380,1.06]
[null,"Emeral Shores",753,753,704,0.93,-82,671,673,1]
[null,"Evergreen",848,848,745,0.88,-91,757,712,0.94]
[null,"Fessenden",653,653,558,0.85,-228,425,533,1.25]
[null,"Greenway",776,776,705,0.91,-40,736,674,0.92]
[null,"Jarbor View",798,798,695,0.87,-72,726,664,0.91]
[null,"Madison Street",558,558,487,0.87,0,558,466,0.84]
[null,"Maplewood",856,856,735,0.86,-90,766,703,0.92]
[null,"Oakcrest",762,762,625,0.82,-119,643,598,0.93]
[null,"Ocala Springs",821,821,683,0.83,-222,599,653,1.09]
[null,"Reddick-Collier",879,879,553,0.63,-179,700,529,0.76]
[null,"Romeo",835,835,757,0.91,-61,774,724,0.94]
[null,"Saddlewood",699,699,772,1.1,0,699,738,1.06]
[null,"Shady Hill",748,748,675,0.9,-46,702,645,0.92]
[null,"Soputh Ocala",1062,1062,571,0.54,-463,599,546,0.91]
[null,"Sparr",554,554,582,1.05,-132,422,477,1.13]
[null,"Stanton Weirsdale",627,627,499,0.8,79,706,556,0.79]
[null,"Sunrise",923,923,911,0.99,-174,749,871,1.16]
[null,"Ward-Highlands",772,772,778,1.01,-85,687,744,1.08]
[null,"Wyomenia Park",586,586,563,0.96,-101,485,538,1.11]
[null,"   MIDDLE"]
[null,"Belleview",1884,1696,1303,0.77,-312,1415,1203,0.85]
[null,"Dunellon ",1303,1173,1023,0.87,488,1612,944,0.59]
[null,"Fort King",1773,1596,781,0.49,-383,1251,721,0.58]
[null,"Howard",1881,1693,1232,0.73,-307,1417,1137,0.8]
[null,"Lake Weir",1848,1663,1317,0.79,-198,1485,1216,0.82]
[null,"North Marion",1382,1244,913,0.73,-234,1033,843,0.82]
[null,"Osceola",1350,1215,1113,0.92,-320,927,1028,1.11]
[null,"West Port",1269,1142,355,0.31,0,1142,955,0.84]
[null,"   HIGH"]
[null,"Belleview",2589,2460,1855,0.75,-735,1761,2080,1.18]
[null,"Dunellon ",1816,1634,1208,0.74,-425,1321,1354,1.02]
[null,"Forest",2311,2195,1711,0.78,-791,1444,1918,1.33]
[null,"Lake Weir",2221,2110,1513,0.72,-316,1810,1699,0.94]
[null,"North Marion",1970,1872,1364,0.73,-42,1832,1529,0.83]
[null,"Vanguard",2743,2606,1661,0.64,-969,1685,1862,1.11]
[null,"West Port",1371,1302,354,0.27,0,1234,1464,1.19]
[null,"   OTHER SCHOOLS"]
[null,"Fort McCoy",1717,1545,1293,0.84,-172,1391,1216,0.87]
[null,"Hillcrest",139,139,154,1.11,36,175,163,0.93]
[null,"Pheonix Center",376,338,239,0.71,0,376,246,0.65]
[null,"Community Education",825,990,40,0.04,null,990,100,0.1]
[]
["2a.","MARION COUNTY TOTAL",51888,49733,36772,0.74,-8016,42085,38259]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"Forest High School Replacement Facility,   South East Mericamp Road, Ocala, Florida"]
[{"$nulls":6},"# of Units",null,"Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected",null,"( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use",null,"decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2005-06",null,"units by 2005-06","Column \"C\""]
[null,"   ELEMENTARY"]
[null,"Anthony",10,"School Board",140,0,0,-10,-10,372]
[null,"Belleview",19,"School Board",357,0,0,-19,-19,680]
[null,"Belleview-Santos",2,"School Board",0,0,0,-2,-2,39]
[null,"College Park",0,"School Board",0,0,0,0,0]
[null,"Dr. N. H. Jones",9,"School Board",172,0,0,-9,-9,192]
[null,"Dunellon ",0,"School Board",0,0,0,0,0]
[null,"East Marion",18,"School Board",239,0,0,-18,-18,338]
[null,"Eighth Street",32,"School Board",463,0,0,-32,-32,281]
[null,"Emeral Shores",1,"School Board",0,0,0,-1,-1,8]
[null,"Evergreen",5,"School Board",91,0,0,-5,-5,48]
[null,"Fessenden",7,"School Board",117,0,0,-7,-7,67]
[null,"Greenway",0,"School Board",0,0,0,-8,0]
[null,"Harbour View",3,"School Board",47,0,0,0,-3,35]
[null,"Madison Street",0,"School Board",0,0,0,-3,0]
[null,"Maplewood",0,"School Board",0,0,0,0,0]
[null,"Oakcrest",14,"School Board",164,0,0,0,-14,268]
[null,"Ocala Springs",6,"School Board",96,0,0,-14,-6,75]
[null,"Reddick-Collier",1,"School Board",0,0,0,-6,-1,8]
[null,"Romeo",3,"School Board",61,0,0,-1,-3,17]
[null,"Saddlewood",0,"School Board",0,0,0,-3,0]
[null,"Shady Hill",2,"School Board",46,0,0,0,-2,26]
[null,"South Ocala",9,"School Board",100,0,0,-2,-9,173]
[null,"Sparr",2,"School Board",20,0,0,-9,-2,62]
[null,"Stanton Weirsdale",11,"School Board",107,0,0,-2,-11,233]
[null,"Sunrise",9,"School Board",174,0,0,-11,-9,95]
[null,"Ward-Highlands",20,"School Board",179,0,0,-9,-20,434]
[null,"Wyomenia Park",12,"School Board",101,0,0,-20,12,266]
[null,"   MIDDLE",{"$nulls":5},-20]
[null,"Belleview",15,"School Board",312,0,0,-15,-15,343]
[null,"Dunellon ",2,"School Board",56,0,0,-2,-2,42]
[null,"Fort King",18,"School Board",295,0,0,-18,-18,525]
[null,"Howard",12,"School Board",307,0,0,-12,-12,122]
[null,"Lake Weir",12,"School Board",178,0,0,-12,-12,273]
[null,"North Marion",6,"School Board",39,0,0,-6,6,130]
[null,"Osceola",14,"School Board",320,0,0,-14,-14,267]
[null,"West Port",0,"School Board",0,0,0,0,0]
[null,"   HIGH"]
[null,"Belleview",33,"School Board",825,0,0,-33,-33,636]
[null,"Dunellon ",16,"School Board",425,0,0,-16,-16,375]
[null,"Forest",26,"School Board",683,0,0,-26,-26,776]
[null,"Lake Weir",11,"School Board",215,0,0,-11,-11,237]
[null,"North Marion",26,"School Board",522,0,0,-26,-26,598]
[null,"Vanguard",41,"School Board",969,0,0,-41,-41,747]
[null,"West Port",0,"School Board",0,0,0,0,0]
[null,"   OTHER SCHOOLS"]
[null,"Fort McCoy",8,"School Board",152,0,0,null,-8,132]
[null,"Hillcrest",16,"School Board",116,0,0,-16,-16,475]
[null,"Pheonix Center",2,"School Board",57,0,0,-2,-2,62]
[null,"Community Education",13,"School Board",313,0,0,-13,-13,276]
[]
["2c1","MARION COUNTY TOTAL",466,null,8458,0,0,null,-430,"Avg Age 20.89"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasasble 5-year district work program"]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05 ",null,"2005-06","5 YEAR TOTAL"]
[null,"ELEMENTARY",{"$nulls":7},0]
[null,"Anthony",10,8,1,1,0,null,null,10]
[null,"Belleview",19,14,2,2,1,null,null,19]
[null,"Belleview Santos",2,{"$nulls":5},2,2]
[null,"College Park",0,{"$nulls":6},0]
[null,"Dr. N. H. Jones",9,9,{"$nulls":5},9]
[null,"Dunnellon ",0,{"$nulls":6},0]
[null,"East Marion",18,null,null,10,6,null,2,18]
[null,"Eighth Street",32,28,{"$nulls":4},4,32]
[null,"Emerald Shores",1,{"$nulls":5},1,1]
[null,"Evergreen",5,null,2,2,1,null,null,5]
[null,"Fessenden",7,null,null,5,1,null,1,7]
[null,"Fort McCoy",8,null,null,5,2,null,1,8]
[null,"Greenway",0,{"$nulls":6},0]
[null,"Harbour View",3,null,null,null,2,null,1,3]
[null,"Madison Street",0,{"$nulls":6},0]
[null,"Maplewood",0,{"$nulls":6},0]
[null,"Oakcrest",14,null,null,10,2,null,2,14]
[null,"Ocala Springs",6,null,2,2,2,null,null,6]
[null,"Reddick-Collier",1,{"$nulls":5},1,1]
[null,"Romeo",3,null,1,1,1,null,null,3]
[null,"Saddlewood",0,{"$nulls":6},0]
[null,"Shady Hill",2,null,null,1,1,null,null,2]
[null,"South Ocala",9,7,1,1,null,null,null,9]
[null,"Sparr",11,null,4,4,2,null,1,11]
[null,"Stanton-Weirsdale",2,null,null,2,null,null,null,2]
[null,"Sunrise",9,null,2,2,2,null,3,9]
[null,"Ward-Highlands",20,5,5,5,5,null,null,20]
[null,"Wyomina Park",12,null,null,4,4,null,4,12]
[null,"MIDDLE",{"$nulls":7},0]
[null,"Belleview",15,null,null,10,3,null,2,15]
[null,"Dunnellon",2,null,null,2,null,null,null,2]
[null,"Fort King",18,16,{"$nulls":4},2,18]
[null,"Howard",12,null,null,4,4,null,4,12]
[null,"Lake Weir",12,null,null,4,4,null,4,12]
[null,"North Marion",6,null,null,null,4,null,2,6]
[null,"Osceola",14,4,3,3,4,null,null,14]
[null,"West Port",0,{"$nulls":6},0]
[null,"HIGH",{"$nulls":7},0]
[null,"Belleview",33,3,10,5,5,null,10,33]
[null,"Dunnellon",16,4,4,4,4,null,null,16]
[null,"Forest",26,null,null,20,6,null,null,26]
[null,"Lake Weir.",11,null,3,3,3,null,2,11]
[null,"North Marion",26,null,20,4,2,null,null,26]
[null,"Vanguard",41,12,10,10,9,null,null,41]
[null,"West Port",0,{"$nulls":6},0]
[null,"OTHER",{"$nulls":7},0]
[null,"Hillcrest",16,null,16,{"$nulls":4},16]
[null,"Phoenix Center",2,{"$nulls":5},2,2]
[null,"Community Ed.",0,{"$nulls":6},0]
[{"$nulls":9},0]
["2c2.","MARION COUNTY TOTAL",453,110,86,126,80,null,51,453]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05",null,"FISH Stu. Sta.","# Years Leased "]
[null,"None",0]
[]
["2c3.","MARION COUNTY TOTAL",0,null,0,0,0,null,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":7},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled",null,"Years in Contract","projected for 2004-05"]
[null,"Ocala",6,"Marion Charter Sch. Inc.","2000-2001",200,142,null,4,230]
[null,"Ocala",4,"Future Leaders of the world Academy","2001-2002",50,32,null,5,120]
[{"$nulls":9},0]
["2c4.","MARION COUNTY TOTAL",10,null,null,250,174,null,9,350]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected",null,"New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-2001 CO-FTE","2000-2001 Class size","2005-06 CO-FTE",null,"be added (removed)","2005-06 Class size"]
[null,"   ELEMENTARY"]
[null,"Anthony",16,239,322,20,308,12,null,12]
[null,"Belleview",40,924,747,19,714,null,null,19]
[null,"Belleview-Santos",30,834,750,25,717,null,null,25]
[null,"College Park",28,730,534,19,511,null,null,19]
[null,"Dr. N. H. Jones",34,811,572,17,547,null,null,17]
[null,"Dunellon ",27,745,630,23,602,null,null,23]
[null,"East Marion",23,561,793,34,758,12,12,22]
[null,"Eighth Street",15,294,397,26,380,null,null,26]
[null,"Emeral Shores",28,733,704,25,673,null,null,25]
[null,"Evergreen",28,737,745,27,712,null,null,27]
[null,"Fessenden",23,524,558,24,533,null,null,24]
[null,"Greenway",24,756,705,29,674,null,null,29]
[null,"Jarbor View",28,725,695,25,664,null,null,25]
[null,"Madison Street",21,558,487,23,466,null,null,23]
[null,"Maplewood",22,613,735,33,703,null,null,33]
[null,"Oakcrest",25,575,625,25,598,12,12,17]
[null,"Ocala Springs",27,696,683,25,653,null,null,25]
[null,"Reddick-Collier",32,847,553,17,529,null,null,17]
[null,"Romeo",25,754,757,30,724,null,null,30]
[null,"Saddlewood",24,671,772,32,738,null,null,32]
[null,"Shady Hill",26,662,675,26,645,null,null,26]
[null,"Soputh Ocala",41,962,571,14,546,null,null,14]
[null,"Sparr",21,522,582,28,556,null,null,28]
[null,"Stanton Weirsdale",23,520,499,22,477,null,null,22]
[null,"Sunrise",28,729,911,33,871,null,null,33]
[null,"Ward-Highlands",25,564,778,31,744,12,12,20]
[null,"Wyomenia Park",20,471,563,28,538,null,null,28]
[null,"   MIDDLE"]
[null,"Belleview",56,1381,1303,23,1203,null,null,23]
[null,"Dunellon ",44,1094,1023,23,944,null,null,23]
[null,"Fort King",49,1305,781,16,721,null,null,16]
[null,"Howard",52,1381,1232,24,1137,null,null,24]
[null,"Lake Weir",55,1805,1317,24,1216,null,null,24]
[null,"North Marion",48,1180,913,19,843,null,null,19]
[null,"Osceola",39,927,1113,29,1028,null,null,29]
[null,"West Port",37,1276,355,10,955,null,null,10]
[null,"   HIGH"]
[null,"Belleview",66,1711,1855,28,2080,null,null,28]
[null,"Dunellon ",49,1371,1208,25,1354,null,null,25]
[null,"Forest",68,1628,1711,25,1918,null,null,25]
[null,"Lake Weir",73,1554,1513,21,1699,null,null,21]
[null,"North Marion",41,1448,1364,33,1529,16,16,33]
[null,"Vanguard",62,1774,1661,27,1862,null,null,27]
[null,"West Port",46,1276,354,8,1464,null,0,8]
[null,"   OTHER SCHOOLS"]
[null,"Fort McCoy",62,1525,1293,21,1216,null,null,21]
[null,"Hillcrest",0,0,154,0,163,22,16,10]
[null,"Community Education",0,0,239,0,246,null,"NA","NA"]
[null,"Pheonix Center",16,512,40,3,41,null,null,3]
[]
["2e.","MARION COUNTY TOTAL",1567,40905,36772,"District Avg 23",38200,null,68,"District Avg 23"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year.",{"$nulls":6},136]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05 ",null,"2005-06","5 YEAR AVERAGE"]
[null,"   ELEMENTARY"]
[null,"Anthony",null,140,0,0,0,null,0,28]
[null,"Belleview",null,0,0,0,0,null,0,0]
[null,"Belleview-Santos",null,0,0,0,0,null,0,0]
[null,"College Park",null,0,0,0,0,null,0,0]
[null,"Dr. N. H. Jones",null,0,0,0,0,null,0,0]
[null,"Dunellon ",null,0,0,0,0,null,0,0]
[null,"East Marion",null,239,0,0,0,null,0,47.8]
[null,"Eighth Street",null,83,80,80,82,null,86,82.2]
[null,"Emeral Shores",null,0,0,0,0,null,0,0]
[null,"Evergreen",null,0,0,0,0,null,0,0]
[null,"Fessenden",null,0,0,0,0,null,0,0]
[null,"Greenway",null,47,0,0,0,null,0,9.4]
[null,"Jarbor View",null,0,0,0,0,null,0,0]
[null,"Madison Street",null,0,0,0,0,null,0,0]
[null,"Maplewood",null,164,0,0,0,null,0,32.8]
[null,"Oakcrest",null,96,0,0,0,null,0,19.2]
[null,"Ocala Springs",null,0,0,0,0,null,0,0]
[null,"Reddick-Collier",null,61,0,0,0,null,0,12.2]
[null,"Romeo",null,143,28,27,32,null,39,53.8]
[null,"Saddlewood",null,46,0,0,0,null,0,9.2]
[null,"Shady Hill",null,0,0,0,0,null,0,0]
[null,"Soputh Ocala",null,107,28,28,31,null,36,46]
[null,"Sparr",null,174,109,108,114,null,0,101]
[null,"Stanton Weirsdale",null,20,0,0,0,null,0,4]
[null,"Sunrise",null,179,179,179,179,null,179,179]
[null,"Ward-Highlands",null,101,101,101,101,null,101,101]
[null,"Wyomenia Park",null,101,0,0,0,null,0,20.2]
[null,"   MIDDLE"]
[null,"Belleview",null,312,0,0,0,null,0,62.4]
[null,"Dunellon ",null,56,0,0,0,null,0,11.2]
[null,"Fort King",null,0,0,0,0,null,0,0]
[null,"Howard",null,307,0,0,0,null,0,61.4]
[null,"Lake Weir",null,178,0,0,0,null,0,35.6]
[null,"North Marion",null,39,0,0,0,null,0,7.8]
[null,"Osceola",null,320,47,29,14,null,0,82]
[null,"West Port",null,0,0,0,0,null,0,0]
[null,"   HIGH"]
[null,"Belleview",null,170,157,190,260,null,316,218.6]
[null,"Dunellon ",null,0,0,0,0,null,0,0]
[null,"Forest",null,156,144,173,239,null,290,200.4]
[null,"Lake Weir",null,0,0,0,0,null,0,0]
[null,"North Marion",null,0,0,0,41,null,81,24.4]
[null,"Vanguard",null,0,0,0,39,null,88,25.4]
[null,"West Port",null,0,0,5,53,null,94,30.4]
[null,"   OTHER SCHOOLS",{"$nulls":9},0]
[null,"Fort McCoy",null,0,0,0,0,null,0,0]
[null,"Hillcrest",null,116,0,0,0,null,0,23.2]
[null,"Community Education",null,0,0,0,0,null,0,0]
[null,"Pheonix Center",null,313,313,313,313,null,313,313]
[]
["2f.","MARION COUNTY Total students in relocatables by year",null,3668,1186,1233,1498,0,1623,1841.6000000000004]
[null,"Total number of CO-FTE students projected by year",null,36899,37102,37453,37853,null,38200,37501.4]
[null,"Percent in relocatables by year",null,0.1,0.03,0.03,0.04,null,0.04,0.05]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":8},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":10},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":10},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":8},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":8},3,117,130,144,16957,19232,21507]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-2002","2001-2002","2001-2002","2001-2002","2001-2002","2001-2002","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Anthony Elem. Addition",0,1750000,288,19933,69.21,null,0,0,0,6076.39,0,0,0]
[null,"Hillcrest School Addition",0,3000000,160,30240,189,null,0]
[null,"North Marion Hi. Addition",0,3850000,480,26153,54.49,null,0]
[null,"East Marion Elem. Addition",0,3500000,288,19933,69.21,null,0]
["3a.","MARION COUNTY Total 2000-01",null,12100000,1216,96259,79.16,{"$nulls":4},9950.66]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-2003","2002-2003","2002-2003","2002-2003","2002-2003","2002-2003","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Oakcrest El. Addition",0,3500000,288,20000,69.44,null,0,0,0,12152.78,0,0,0]
[null,"Stanton Weirsdale Addition",0,600000,100,5000,50,null,0]
[null,"Forest Hi. Replacement",3,35000000,2000,210000,105,null,117]
[{"$nulls":8},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","MARION COUNTY Total 2001-02",null,39100000,2388,235000,98.41,{"$nulls":4},16373.53]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04 ","2002-03 ","2002-03 ","2002-03 ",null,"2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Ward-Highlands Addition",0,3500000,288,20000,69.44]
[null,"Dunellon Middle Addition",0,4000000,382,34000,89.01]
[{"$nulls":8},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","MARION COUNTY Total 2002-03",null,7500000,670,54000,80.6,{"$nulls":4},11194.03]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-2005","2004-2005","2004-2005","2004-2005",null,"1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Eighth St. El. Addition",0,4000000,200,18000,90,null,0,0,0,20000,0,0,0]
[]
["3d.","MARION COUNTY Total 2003-04",null,4000000,200,18000,90,{"$nulls":4},20000]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-2006","2005-2006","2005-2006","2005-2006",null,"1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"NONE"]
[{"$nulls":6},{"$error":"#DIV/0!"},null,0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","MARION COUNTY Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3f.","MARION COUNTY 5-Year Total",null,62700000,4474,403259]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-2002","2002-2003","2003-2004","2004-2005",null,"2005-2006"]
[null,null,null,"Actual Budget","Projected","Projected","Projected",null,"Projected","5 YEAR TOTAL"]
[null,"Fund Balance",null,8828242,{"$nulls":5},8828242]
[null,"SIT Awards",null,700000,{"$nulls":5},700000]
[null,"Revenue Bonds",null,1800000,{"$nulls":5},1800000]
[null,"Interest",null,200000,200000,200000,200000,200000,200000,1200000]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,2,12]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,15957812,16356757,16765676,17184818,17614438,17614438,101493939]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,15159921,15538919,15927392,16325577,16733716,16733716,96419241,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,850000,1700000,1700000,1700000,1700000,1700000,9350000,0.1]
[null,"  less amount used to purchase other vehicles",null,0,400000,400000,400000,400000,400000,2000000,0.02]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,1350000,1350000,1350000,1350000,1350000,6750000,0.07]
[null,"  less amount used for maintenance/repair",null,4175000,2529000,4115000,2850000,2700000,2700000,19069000,0.2]
[null,"  less amount used to purchase capital outlay equipment",null,2565000,1150000,1150000,6150000,1150000,1150000,13315000,0.14]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,70000,0,0,0,0,0,70000,0]
[null,"  less amount to pay debt service for COP's ",null,3800000,2736000,2736000,2736000,2736000,2736000,17480000,0.18]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,3699921,5673919,4476392,1139577,6697716,6697716,28385241,0.29,0.68]
[null,"P E C O New Construction",null,3801532,2722682,1612846,1376168,1432027,1432027,12377282,null,0.29]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,200000,200000,200000,200000,200000,200000,1200000,null,0.03]
[null,"C O & D S maximum potential bond proceeds",null,"?","?","?","?","?","?",0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,0,0,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0,0]
[null,"Impact fees received",null,0,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,0,null,0]
["4.","MARION COUNTY Total",null,7701453,8596601,6289238,2715745,8329743,8329743,41962523,1,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-2002","2002-2003","2003-2004","2004-2005",null,"2005-2006"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected",null,"Projected","5 YEAR TOTAL"]
[null,"Anthony Elementary Addition",288,1750000,{"$nulls":5},1750000]
[null,"Belleview Hi. Fieldhouse",0,125000,{"$nulls":5},125000]
[null,"Dunnellon Middle Addition",382,null,null,4000000,null,null,null,4000000]
[null,"East Marion Elem. Addition",288,3400000,{"$nulls":5},3400000]
[null,"Eighth Street Elementary Addition",200,{"$nulls":5},4000000,4000000]
[null,"New Forest Hi. Site ",0,1500000,{"$nulls":5},1500000]
[null,"Forest Hi. Planning",0,100000,{"$nulls":5},100000]
[null,"Forest High School Replacement",2000,null,34900000,{"$nulls":4},34900000]
[null,"Forest High Equipment",0,null,null,5000000,null,null,null,5000000]
[null,"Fort King Mid.  Greenhouse",0,30000,{"$nulls":5},30000]
[null,"Hillcrest ESE Addition",288,3000000,{"$nulls":5},3000000]
[null,"North Marion High Addition",480,3850000,250000,{"$nulls":4},4100000]
[null,"North Marion Mid. Cafeteria",0,{"$nulls":4},1000000,1000000,1000000]
[null,"Oakcrest Elementary Addition",288,null,3500000,{"$nulls":4},3500000]
[null,"Playgrounds",0,50000,{"$nulls":5},50000]
[null,"Stanton Weirsdale Elem. Addition",100,null,2500000,{"$nulls":4},2500000]
[null,"Technical Services Shed",0,100000,{"$nulls":5},100000]
[null,"Ward Highlands Addition",288,null,null,3500000,null,null,null,3500000]
[null,"West Port Hi. Equipment",0,200000,{"$nulls":5},200000]
[null,"West Port Mid. Equipment",0,100000,{"$nulls":5},100000]
[{"$nulls":9},0]
["5.","MARION COUNTY Total",4602,14205000,41150000,12500000,0,null,5000000,72855000]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-2002","2002-2003","2003-2004","2004-2005",null,"2005-2006"]
[null,null,null,"Actual Budget","Projected","Projected","Projected",null,"Projected","5 YEAR TOTAL"]
[null,"NONE",null,0,0,0,0,null,0,0]
[null,"Other (specify)",null,0,0,0,0,null,0,0]
["6.","MARION COUNTY Total",null,0,0,0,0,null,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-2002","2002-2003","2003-2004","2004-2005",null,"2005-2006"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected",null,"Projected","5 YEAR TOTAL"]
[null,"NONE",{"$nulls":7},0]
[{"$nulls":9},0]
["7.","MARION COUNTY Total",0,0,0,0,0,null,0,0]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ",null,"2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","",null,"",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
[]
[]
[]
[]
[]
[]
["Respectfully submitted this _1st_______ day of __October________, 2001."]
[]
[null,"SCHOOL BOARD OF ","MARION COUNTY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"James M. Warford",null,null,null,"2001-10-01"]
[null,null,"Signature",null,null,"Name Printed",null,null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"Stephen Barrett",null,null,null,"2001-10-01"," "]
[null,null,"Signature",null,null,"Name Printed",null,null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:",null,null,"David G. Cowart","Facilities Coordinator","352-671-6900",null,null,"cowartd@marionk12.fl.us",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}