{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":602,"n_cols":25,"rows_kept":602,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["MARION COUNTY SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["MARION COUNTY   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":23},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":23},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"MARION COUNTY","Date: ==>","2002-08-30",null,"For fiscal years","  2002-2003 through 2006-2007"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2002-03","2003-04 ","2004-05 ","2005-06","2006-07"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"ADA Compliance","District Wide",200000,200000,200000,200000,200000,1000000]
[null,"Safety-To-Life","District Wide",135362,174809,132359,199172,211285,852987]
[null,"District Wide Repairs","District Wide",1350000,1350000,1350000,1350000,1350000,6750000]
[null,"Carpet Replacement","District Wide",0,500000,0,0,0,500000]
[null,"Gym Lighting","District Wide",20000,0,0,0,0,20000]
[null,"Lighting Retrofit","District Wide",200000,0,0,0,0,200000]
[null,"Playgrounds","District Wide",300000,0,0,0,0,300000]
[null,"Portables - Vinyl Siding","District Wide",37000,0,0,0,0,37000]
[null,"Programable Stats.","District Wide",100000,0,0,0,0,100000]
[null,"Technology Renovation","District Wide",1500000,750000,750000,750000,750000,4500000]
[null,"HVAC Upgrades","Anthony Elem.",0,0,0,400000,0,400000]
[null,"Renovations","Anthony Elem.",0,0,40000,0,0,40000]
[null,"Re-Roof","Anthony Elem.",206000,0,0,0,0,206000]
[null,"HVAC Upgrade & Re-Roof","Belleview Elem.",0,0,735000,0,0,735000]
[null,"Renovations","Belleview Elem.",0,100000,0,0,0,100000]
[null,"HVAC Upgrade & Re-Roof","Belleview Elem. - K-Wing",385000,0,0,0,0,385000]
[null,"Paint","Belleview High",0,50000,0,0,0,50000]
[null,"HVAC Upgrades / Make up Air","Belleview Middle",250000,0,0,0,0,250000]
[null,"Paint","Belleview Middle",10000,0,0,0,0,10000]
[null,"HVAC Upgrade / Chiller","Belleview-Santos Elem.",0,0,350000,0,0,350000]
[null,"Renovations","Belleview-Santos Elem.",0,200000,0,0,0,200000]
[null,"HVAC Upgrade & Re-Roof","Central Warehouse",217000,0,0,0,0,217000]
[null,"Paint","County Office",12000,0,0,0,0,12000]
[null,"Parent Center","County Office",30000,0,0,0,0,30000]
[null,"Parking","County Office",100000,0,0,0,0,100000]
[null,"HVAC Upgrade & Re-Roof","Dr. NH Jones",0,0,0,530000,0,530000]
[null,"Renovations","Dr. NH Jones",0,50000,0,0,0,50000]
[null,"HVAC Upgrade","Dr. NH Jones - K-Wing",0,0,0,210000,0,210000]
[null,"Paint","Dunnellon Elem.",0,50000,0,0,0,50000]
[null,"HVAC - Add Chiller & Controls","Dunnellon High",0,500000,0,0,0,500000]
[null,"HVAC - Replace Chillers","Dunnellon High",297000,0,0,0,0,297000]
[null,"Re-Roof","Dunnellon High",1400000,0,0,0,0,1400000]
[null,"Historic Grant","Dunnellon Middle",270000,0,0,0,0,270000]
[null,"HVAC Upgrade","Dunnellon Middle",150000,0,0,0,0,150000]
[null,"HVAC Upgrade & Re-Roof","Dunn. Middle - K-Wing",0,300000,0,0,0,300000]
[null,"Paint","Dunnellon Middle",0,50000,0,0,0,50000]
[null,"Re-Roof","Dunnellon Middle",0,0,0,0,400000,400000]
[null,"HVAC Upgrades","East Marion Elem.",400000,0,0,0,0,400000]
[null,"Renovation","Eight Street Expansion",null,null,500000,null,null,500000]
[null,"HVAC Upgrade & Re-Roof","Eighth Street - Cafeteria",100000,0,0,0,0,100000]
[null,"Paint","Emerald Shores Elem.",0,14500,0,0,0,14500]
[null,"Paint","Facilities Complex",0,50000,0,0,0,50000]
[null,"Re-Roof","Facilities Complex",0,0,0,165000,0,165000]
[null,"Doors / Hardware","Fessenden Elem.",0,0,50000,0,0,50000]
[null,"HVAC Upgrade","Fessenden Elem.",0,0,0,980000,0,980000]
[null,"Renovations","Fessenden Elem.",0,0,0,175000,0,175000]
[null,"Paint","Fessenden Elem.",0,100000,0,0,0,100000]
[null,"Doors / Hardware","Forest High",0,100000,0,0,0,100000]
[null,"Electric Upgrades","Forest High",0,0,0,100000,0,100000]
[null,"Plumbing (Fixtures)","Forest High",0,25000,0,0,0,25000]
[null,"Renovations (Locks)","Forest High",12500,0,0,0,0,12500]
[null,"Re-Roof","Forest High",0,0,0,0,1295000,1295000]
[null,"Renovation","Forest High",null,null,4000000,null,null,4000000]
[null,"HVAC - Ducting","Ft. King Middle",89000,0,0,0,0,89000]
[null,"HVAC Upgrades","Ft. McCoy School",0,0,0,0,220000,220000]
[null,"HVAC Upgrades","Hillcrest School",0,0,0,0,40000,40000]
[null,"Renovations","Hillcrest School",260000,0,0,0,0,260000]
[null,"HVAC Upgrades","Howard Academy",0,0,0,0,375000,375000]
[null,"Renovations","Howard Academy",0,0,20000,0,0,20000]
[null,"Plumbing (Fixtures)","Howard Middle",0,25000,0,0,0,25000]
[null,"HVAC Upgrades","L W Middle-Media & Café.",0,0,615000,0,0,615000]
[null,"Partitions (Toilets)","Lake Weir High",7500,0,0,0,0,7500]
[null,"HVAC - Cooling Tower","Lake Weir Middle",0,0,0,0,150000,150000]
[null,"Plumbing (Fixtures)","Lake Weir Middle",0,0,0,5000,0,5000]
[null,"Carpet / VCT","North Marion High",0,200000,0,0,0,200000]
[null,"Hardware / Locks","North Marion High",25000,0,0,0,0,25000]
[null,"HVAC Upgrade / Fan Coils","North Marion High",0,0,55000,0,0,55000]
[null,"Plumbing (Fixtures)","North Marion High",0,25000,0,0,0,25000]
[null,"Renovations","North Marion High",231028,0,0,0,0,231028]
[null,"Gym Floor","North Marion Middle",60000,0,0,0,0,60000]
[null,"HVAC - Roof Top Units","North Marion Middle",0,0,490000,0,0,490000]
[null,"Renovations","North Marion Middle",1500000,0,0,0,0,1500000]
[null,"Ceiling / Lights","Oakcrest Elem.",0,0,115000,0,0,115000]
[null,"Electric Upgrades","Oakcrest Elem.",0,0,0,30000,0,30000]
[null,"HVAC Upgrades","Oakcrest Elem.",0,0,0,0,500000,500000]
[null,"Paint (Exterior)","Oakcrest Elem.",45000,0,0,0,0,45000]
[null,"Plumbing (Fixtures)","Oakcrest Elem.",0,50000,0,0,0,50000]
[null,"Bus Canopy","Ocala Springs Elem.",0,125000,0,0,0,125000]
[null,"Renovation","Osceola Middle",null,null,1000000,null,null,1000000]
[null,"Doors (Bldg. 2)","Osceola Middle",0,200000,0,0,0,200000]
[null,"Paint","Reddick-Collier Elem.",10000,0,0,0,0,10000]
[null,"Drainage","Romeo Elem.",0,50000,0,0,0,50000]
[null,"Ceiling / Lights","South Ocala Elem.",0,0,0,320000,0,320000]
[null,"Electric Upgrades","South Ocala Elem.",0,0,0,100000,0,100000]
[null,"HVAC Upgrade & Re-Roof","South Ocala Elem.",0,0,0,1260000,0,1260000]
[null,"Ceilings & Lights","Sparr Elem.",0,250000,0,0,0,250000]
[null,"HVAC Upgrades","Sparr Elem.",0,0,0,0,500000,500000]
[null,"HVAC Upgrades","Stanton-Weirsdale",0,0,0,525000,0,525000]
[null,"Shed","Technical Services",100000,0,0,0,0,100000]
[null,"Plumbing (Fixtures)","Vanguard High",5000,0,0,0,0,5000]
[null,"HVAC Upgrades","Vanguard High",150000,0,0,0,0,150000]
[null,"Greenhouse","Vanguard High",30000,0,0,0,0,30000]
[null,"Electric Upgrades","Ward-Highlands Elem.",0,0,50000,0,0,50000]
[null,"HVAC Upgrade & Re-Roof","Ward-Highlands Elem.",0,1000000,0,0,0,1000000]
[null,"HVAC Upgrade & Re-Roof","Wyom. Park Elem-K-Wing",0,0,300000,0,0,300000]
[null,"Plumbing (Fixtures)","Wyomina Park Elem.",0,50000,0,0,0,50000]
[null,"Maintenance, Repair, and Renovation Totals",null,10194390,6539309,10752359,7299172,5991285,40776515]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,1353613,1748084,1323585,1991714,2112842,8529838]
["1.","MARION COUNTY Total",null,8840777,4791225,9428774,5307458,3878443,32246677]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Dunnellon Midddle School","classroom wing addition",0,4000000,0,0,0,4000000]
[null,"East Marion Elementary School","classroom wing addition",3000000,0,0,0,0,3000000]
[null,"Forest High School","replacement school\"CCC\"",35000000,0,0,0,0,35000000]
[null,"Hillcrest School","classroom wing addition",500000,0,0,0,0,500000]
[null,"North Marion High School","classroom/tech/crt yd addition",1000000,0,0,0,0,1000000]
[null,"North Marion Middle School","cafeteria addition",0,0,1000000,0,0,1000000]
[null,"Oakcrest Elementary School","classroom wing addition",3000000,0,0,0,0,3000000]
[null,"Stanton-Weirsdale -Elementary","classroom wing and cafeteria addition",2500000,0,0,0,0,2500000]
[null,"Ward-Highlands Elementary","classroom wing addition",0,3000000,0,0,0,3000000]
[null,"New Elementary School","new school",0,0,0,9000000,0,9000000]
[null,"New High School","new school",{"$nulls":4},40000000,40000000]
[null,"New El / Mid / HS Land","purchase land",1000000,{"$nulls":4},1000000]
["2 .","MARION COUNTY Total",null,46000000,7000000,1000000,9000000,40000000,103000000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2001-02 FISH Satisfactory","Actual 2001-02","Actual 2001-02","Actual 2001-02","New Stu Capacity to","Projected 2006-07","Projected 2006-07"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"ELEMENTARY"]
[null,"Anthony",667,667,302,0.45,-140,312,0.59]
[null,"Belleview",970,970,720,0.74,-144,716,0.87]
[null,"Belleview-Santos",814,814,713,0.88,null,717,0.88]
[null,"College Park",762,762,536,0.7,0,547,0.72]
[null,"Dr. N.H. Jones",859,859,566,0.66,-48,573,0.71]
[null,"Dunnellon",756,756,616,0.81,-20,610,0.83]
[null,"East Marion",842,842,740,0.88,-16,759,0.92]
[null,"Eighth Street",399,399,369,0.92,-91,287,0.93]
[null,"Emerald Shores",794,794,692,0.87,-41,655,0.87]
[null,"Evergreen",848,848,698,0.82,-91,689,0.91]
[null,"Fessenden",708,708,505,0.71,-153,524,0.94]
[null,"FT. McCoy",694,694,635,0.91,null,612,0.88]
[null,"Greenway",733,733,657,0.9,0,660,0.9]
[null,"Harbour View",822,822,696,0.85,-71,678,0.9]
[null,"Madison Street Academy",558,558,494,0.89,0,501,0.9]
[null,"Maplewood",1052,1052,753,0.72,0,738,0.7]
[null,"Oakcrest",796,796,531,0.67,92,649,0.73]
[null,"Ocala Springs",833,833,651,0.78,-108,654,0.9]
[null,"Reddick-Collier",879,879,464,0.53,0,476,0.54]
[null,"Romeo",818,818,707,0.86,-73,639,0.86]
[null,"Saddlewood",835,835,820,0.98,-137,685,0.98]
[null,"Shady Hill",761,761,681,0.89,-46,670,0.94]
[null,"South Ocala",968,968,583,0.6,-24,573,0.61]
[null,"Sparr",554,554,479,0.86,-20,484,0.91]
[null,"Stanton-Weirsdale",588,588,575,0.98,37,567,0.91]
[null,"Sunrise",923,923,841,0.91,-174,709,0.95]
[null,"Ward-Highlands",877,877,778,0.89,4,759,0.86]
[null,"Wyomina Park",618,618,530,0.86,-113,438,0.87]
[null,"New Elementary School \"T\"",0,0,0,{"$error":"#DIV/0!"},600,550,0.92]
[null,"MIDDLE"]
[null,"Belleview",1899,1709,1305,0.76,-312,876,0.63]
[null,"Dunnellon",1318,1186,1009,0.85,276,1285,0.88]
[null,"Fort King",1438,1294,820,0.63,0,787,0.61]
[null,"Fort McCoy (6-8)",1031,928,637,0.69,null,580,0.63]
[null,"Howard",1861,1674,1181,0.71,-307,1121,0.82]
[null,"Lake Weir",1855,1669,1303,0.78,-251,1214,0.86]
[null,"North Marion",1817,1635,951,0.58,-459,908,0.77]
[null,"Osceola",1345,1210,1082,0.89,-334,985,1.12]
[null,"West Port",1241,1117,812,0.73,0,959,0.86]
[null,"HIGH"]
[null,"Belleview",2593,2463,1926,0.78,-825,1367,0.83]
[null,"Dunnellon",1907,1811,1244,0.69,-545,820,0.65]
[null,"Forest",2352,2234,1797,0.8,-234,1913,0.96]
[null,"Lake Weir",2369,2250,1650,0.73,-363,1205,0.64]
[null,"North Marion",2450,2327,1464,0.63,-522,1507,0.83]
[null,"Vanguard",2743,2605,1725,0.66,-969,1432,0.88]
[null,"West Port",1654,1572,749,0.48,0,1470,0.94]
[null,"New High School \"DDD\"",0,0,0,{"$error":"#DIV/0!"},2000,1900,0.95]
[null,"OTHER SCHOOLS"]
[null,"Hillcrest",325,325,163,0.5,-124,167,0.83]
[null,"Community Education",1060,1590,58,0.04,null,49,0.03]
[null,"Phoenix Center",434,0,0,{"$error":"#DIV/0!"},-89,244,-2.74]
["2a.","MARION COUNTY Total",53420,51327,37208,0.72,-3835,38220,0.8]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School (600 Stu Sta) in the vicinity of the SW 103rd Street Road and SW 66th Street area in the Southwestern part of Ocala, FL, to accommodate growth."]
[null,"New High School (replacement school) in the Southeast section of Ocala off Maricamp Road."]
[null,"New High School (2,000 Stu Sta) in the Central section of Ocala  to accommodate students being moved from portables that will be discontinued.",{"$nulls":4},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2001-02","Owner","Student Stations","as classroom space","in 2006-07","units by 2006-07","Column \"C\""]
[null,"ELEMENTARY"]
[null,"Anthony",1,"Marion Co. Schools",12,0,0,-1,32]
[null,"Belleview",6,"Marion Co. Schools",112,0,0,-6,256]
[null,"Belleview-Santos",4,"Marion Co. Schools",8,0,0,-4,75]
[null,"College Park",0,"Marion Co. Schools",0,0,0,0,0]
[null,"Dr. N.H. Jones",2,"Marion Co. Schools",48,0,0,-2,64]
[null,"Dunnellon",1,"Marion Co. Schools",20,0,0,-1,17]
[null,"East Marion",19,"Marion Co. Schools",304,0,0,-19,356]
[null,"Eighth Street",5,"Marion Co. Schools",91,0,0,-5,145]
[null,"Emerald Shores",6,"Marion Co. Schools",95,0,0,-6,140]
[null,"Evergreen",5,"Marion Co. Schools",91,0,0,-5,37]
[null,"Fessenden",9,"Marion Co. Schools",153,0,0,-9,146]
[null,"FT. McCoy",8,"Marion Co. Schools",160,0,0,-8,155]
[null,"Greenway",0,"Marion Co. Schools",0,0,0,0,0]
[null,"Harbour View",4,"Marion Co. Schools",71,0,0,-4,55]
[null,"Madison Street Academy",0,"Marion Co. Schools",0,0,0,0,0]
[null,"Maplewood",2,"Marion Co. Schools",42,0,0,-2,24]
[null,"Oakcrest",12,"Marion Co. Schools",196,0,0,-12,265]
[null,"Ocala Springs",6,"Marion Co. Schools",108,0,0,-6,88]
[null,"Reddick-Collier",0,"Marion Co. Schools",0,0,0,0,0]
[null,"Romeo",5,"Marion Co. Schools",81,0,0,-5,61]
[null,"Saddlewood",6,"Marion Co. Schools",137,0,0,-6,24]
[null,"Shady Hill",2,"Marion Co. Schools",46,0,0,-2,28]
[null,"South Ocala",3,"Marion Co. Schools",24,0,0,-3,96]
[null,"Sparr",2,"Marion Co. Schools",20,0,0,-2,64]
[null,"Stanton-Weirsdale",10,"Marion Co. Schools",107,0,0,-10,235]
[null,"Sunrise",10,"Marion Co. Schools",194,0,0,-10,108]
[null,"Ward-Highlands",22,"Marion Co. Schools",284,0,0,-22,432]
[null,"Wyomina Park",12,"Marion Co. Schools",153,0,0,-12,296]
[null,"MIDDLE"]
[null,"Belleview",15,"Marion Co. Schools",312,0,0,-15,358]
[null,"Dunnellon",5,"Marion Co. Schools",106,0,0,-5,59]
[null,"Fort King",0,"Marion Co. Schools",0,0,0,0,0]
[null,"Ft. McCoy (6-8)",0,"Marion Co. Schools",0,0,0,0,0]
[null,"Howard",10,"Marion Co. Schools",258,0,0,-10,86]
[null,"Lake Weir",11,"Marion Co. Schools",251,0,0,-11,253]
[null,"North Marion",5,"Marion Co. Schools",123,0,0,-5,66]
[null,"Osceola",11,"Marion Co. Schools",258,0,0,-11,216]
[null,"West Port",0,"Marion Co. Schools",0,0,0,0,0]
[null,"HIGH"]
[null,"Belleview",32,"Marion Co. Schools",825,0,0,-32,675]
[null,"Dunnellon",19,"Marion Co. Schools",545,0,0,-19,412]
[null,"Forest",28,"Marion Co. Schools",739,0,0,-28,866]
[null,"Lake Weir",15,"Marion Co. Schools",363,0,0,-15,363]
[null,"North Marion",10,"Marion Co. Schools",226,0,0,-10,328]
[null,"Vanguard",38,"Marion Co. Schools",918,0,0,-38,739]
[null,"West Port",0,"Marion Co. Schools",0,0,0,0,0]
[null,"OTHER SCHOOLS"]
[null,"Hillcrest",10,"Marion Co. Schools",76,0,0,-10,195]
[null,"Community Education",13,"Marion Co. Schools",313,0,0,-13,271]
[null,"Phoenix Center",7,"Marion Co. Schools",176,0,0,-7,179]
[]
["2c1.","MARION COUNTY Total",391,null,8046,0,0,-391,"Avg Age 21.14"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07","5 YEAR TOTAL"]
[null,"ELEMENTARY"]
[null,"Anthony",1,0,0,1,0,0,1]
[null,"Belleview",6,2,2,2,0,0,6]
[null,"Belleview-Santos",4,0,3,1,0,0,4]
[null,"College Park",0,0,0,0,0,0,0]
[null,"Dr. N.H. Jones",2,0,2,0,0,0,2]
[null,"Dunnellon",1,0,1,0,0,0,1]
[null,"East Marion",19,0,17,2,0,0,19]
[null,"Eighth Street",5,0,0,0,5,0,5]
[null,"Emerald Shores",6,0,3,3,0,0,6]
[null,"Evergreen",5,0,2,3,0,0,5]
[null,"Fessenden",9,0,4,3,2,0,9]
[null,"FT. McCoy",8,0,0,4,2,2,8]
[null,"Greenway",0,0,0,0,0,0,0]
[null,"Harbour View",4,0,0,4,0,0,4]
[null,"Madison Street Academy",0,0,0,0,0,0,0]
[null,"Maplewood",2,0,0,0,2,0,2]
[null,"Oakcrest",12,0,8,4,0,0,12]
[null,"Ocala Springs",6,0,0,5,1,0,6]
[null,"Reddick-Collier",0,0,0,0,0,0,0]
[null,"Romeo",5,0,3,0,0,2,5]
[null,"Saddlewood",6,0,0,0,0,6,6]
[null,"Shady Hill",2,0,0,0,2,0,2]
[null,"South Ocala",3,0,0,3,0,0,3]
[null,"Sparr",2,0,0,2,0,0,2]
[null,"Stanton-Weirsdale",10,0,10,0,0,0,10]
[null,"Sunrise",10,0,0,0,0,10,10]
[null,"Ward-Highlands",22,0,0,22,0,0,22]
[null,"Wyomina Park",12,0,0,3,0,9,12]
[null,"MIDDLE"]
[null,"Belleview",15,0,0,7,0,8,15]
[null,"Dunnellon",5,0,0,4,1,0,5]
[null,"Fort King",0,0,0,0,0,0,0]
[null,"Ft. McCoy (6-8)",0,0,0,0,0,0,0]
[null,"Howard",10,0,2,5,3,0,10]
[null,"Lake Weir",11,0,0,5,6,0,11]
[null,"North Marion",5,2,2,1,0,0,5]
[null,"Osceola",11,0,0,0,0,11,11]
[null,"West Port",0,0,0,0,0,0,0]
[null,"HIGH"]
[null,"Belleview",32,0,0,15,0,5,20]
[null,"Dunnellon",19,0,0,0,19,0,19]
[null,"Forest",28,0,0,0,28,0,28]
[null,"Lake Weir",15,0,0,10,0,5,15]
[null,"North Marion",10,10,0,0,0,0,10]
[null,"Vanguard",38,0,0,0,0,30,30]
[null,"West Port",0,0,0,0,0,0,0]
[null,"OTHER SCHOOLS"]
[null,"Hillcrest",10,10,0,0,0,0,10]
[null,"Community Education",13,0,0,0,0,0,0]
[null,"Phoenix Center",7,0,0,0,5,2,7]
[{"$nulls":8},0]
["2c2.","MARION COUNTY Total",391,24,59,109,76,90,358]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2006-07","FISH Stu. Sta.","# Years Leased "]
[null,"None",0,"NA",0,0,0,0,0]
[]
["2c3.","MARION COUNTY Total",0,null,0,0,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter stu"]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","proj for 2006-07"]
[null,"Marion Charter",10,"Leased",2000,200,147,4,147]
[null,"Future Leaders Of The World Ac.",10,"Leased",2001,null,41,5,41]
["2c4.","MARION COUNTY Total",20,null,null,200,188,9,188]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2006-07) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","# CLASSROOMS","Capacity(NOT Stu Sta)","2001-02 CO-FTE","2001-02 Class size","2006-07 CO-FTE","be added (removed)","2006-07 Class size"]
[null,"ELEMENTARY"]
[null,"Anthony",24,667,302,12.58,312,-1,13.57]
[null,"Belleview",44,970,720,16.36,716,-6,18.84]
[null,"Belleview-Santos",32,814,713,22.28,717,-4,25.61]
[null,"College Park",31,762,536,17.29,547,0,17.65]
[null,"Dr. N.H. Jones",36,859,566,15.72,573,-2,16.85]
[null,"Dunnellon",30,756,616,20.53,610,-1,21.03]
[null,"East Marion",39,842,740,18.97,759,-3,21.08]
[null,"Eighth Street",21,399,369,17.57,287,1,13.05]
[null,"Emerald Shores",33,794,692,20.97,655,-6,24.26]
[null,"Evergreen",34,848,698,20.53,689,-5,23.76]
[null,"Fessenden",33,708,505,15.3,524,-9,21.83]
[null,"FT. McCoy",28,694,635,22.68,612,-8,30.6]
[null,"Greenway",26,733,657,25.27,660,0,25.38]
[null,"Harbour View",34,822,696,20.47,678,-4,22.6]
[null,"Madison Street Academy",21,558,494,23.52,501,0,23.86]
[null,"Maplewood",45,1052,753,16.73,738,-2,17.16]
[null,"Oakcrest",37,796,531,14.35,649,-4,19.67]
[null,"Ocala Springs",36,833,651,18.08,654,-6,21.8]
[null,"Reddick-Collier",35,879,464,13.26,476,0,13.6]
[null,"Romeo",31,818,707,22.81,639,-5,24.58]
[null,"Saddlewood",33,835,820,24.85,685,-6,25.37]
[null,"Shady Hill",32,761,681,21.28,670,-2,22.33]
[null,"South Ocala",42,968,583,13.88,573,-3,14.69]
[null,"Sparr",23,554,479,20.83,484,-2,23.05]
[null,"Stanton-Weirsdale",26,588,575,22.12,567,-2,23.63]
[null,"Sunrise",39,923,841,21.56,709,-10,24.45]
[null,"Ward-Highlands",42,877,778,18.52,759,-6,21.08]
[null,"Wyomina Park",28,618,530,18.93,438,-12,27.38]
[null,"New Elementary School \"T\"",30,0,0,0,550,0,18.33]
[null,"MIDDLE"]
[null,"Belleview",42,1709,1305,31.07,876,-15,32.44]
[null,"Dunnellon",38,1186,1009,26.55,1285,11,26.22]
[null,"Fort King",32,1294,820,25.63,787,0,24.59]
[null,"Ft. McCoy (6-8)",21,928,637,30.33,580,0,27.62]
[null,"Howard",46,1674,1181,25.67,1121,-10,31.14]
[null,"Lake Weir",30,1669,1303,43.43,1214,-11,63.89]
[null,"North Marion",44,1635,951,21.61,908,-5,23.28]
[null,"Osceola",38,1210,1082,28.47,985,-11,36.48]
[null,"West Port",32,1117,812,25.38,959,0,29.97]
[null,"HIGH"]
[null,"Belleview",65,2463,1926,29.63,1367,-32,41.42]
[null,"Dunnellon",38,1811,1244,32.74,820,-19,43.16]
[null,"New Forest",80,2000,1797,22.46,1913,0,23.91]
[null,"Lake Weir",52,2250,1650,31.73,1205,-15,32.57]
[null,"North Marion",63,2327,1464,23.24,1507,-10,28.43]
[null,"Vanguard",69,2605,1725,25,1432,-38,46.19]
[null,"West Port",32,1572,749,23.41,1470,0,45.94]
[null,"New High School \"DDD\"",66,null,null,0,1900,0,28.79]
[null,"OTHER SCHOOLS"]
[null,"Hillcrest",35,325,163,4.66,167,-10,6.68]
[null,"Community Education",23,1590,58,2.52,49,-13,4.9]
[null,"Phoenix Center",14,0,0,0,244,-7,34.86]
[]
["2e.","MARION COUNTY Total",1805,51093,37208,"District Avg 21",38220,-293,"District Avg 25"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07","5 YEAR AVG"]
[null,"ELEMENTARY"]
[null,"Anthony",null,12,12,0,0,0,4.8]
[null,"Belleview",null,75,38,0,0,0,22.6]
[null,"Belleview-Santos",null,8,8,0,0,0,3.2]
[null,"College Park",null,0,0,0,0,0,0]
[null,"Dr. N.H. Jones",null,48,0,0,0,0,9.6]
[null,"Dunnellon",null,20,0,0,0,0,4]
[null,"East Marion",null,336,32,0,0,0,73.6]
[null,"Eighth Street",null,91,91,91,0,0,54.6]
[null,"Emerald Shores",null,95,48,0,0,0,28.6]
[null,"Evergreen",null,91,37,0,0,0,25.6]
[null,"Fessenden",null,153,85,32,0,0,54]
[null,"FT. McCoy",null,160,160,80,40,0,88]
[null,"Greenway",null,0,0,0,0,0,0]
[null,"Harbour View",null,71,71,0,0,0,28.4]
[null,"Madison Street Academy",null,0,0,0,0,0,0]
[null,"Maplewood",null,42,42,42,0,0,25.2]
[null,"Oakcrest",null,196,65,0,0,0,52.2]
[null,"Ocala Springs",null,108,108,18,0,0,46.8]
[null,"Reddick-Collier",null,0,0,0,0,0,0]
[null,"Romeo",null,81,32,32,32,0,35.4]
[null,"Saddlewood",null,137,137,137,137,0,109.6]
[null,"Shady Hill",null,46,46,46,0,0,27.6]
[null,"South Ocala",null,24,24,0,0,0,9.6]
[null,"Sparr",null,20,20,0,0,0,8]
[null,"Stanton-Weirsdale",null,107,0,0,0,0,21.4]
[null,"Sunrise",null,194,194,194,194,0,155.2]
[null,"Ward-Highlands",null,284,284,0,0,0,113.6]
[null,"Wyomina Park",null,153,153,115,115,0,107.2]
[null,"MIDDLE"]
[null,"Belleview",null,312,312,166,166,0,191.2]
[null,"Dunnellon",null,106,106,21,0,0,46.6]
[null,"Fort King",null,0,0,0,0,0,0]
[null,"Ft.McCoy (6-8)",null,0,0,0,0,0,0]
[null,"Howard",null,258,206,77,0,0,108.2]
[null,"Lake Weir",null,251,251,137,0,0,127.8]
[null,"North Marion",null,74,25,0,0,0,19.8]
[null,"Osceola",null,258,258,258,258,0,206.4]
[null,"West Port",null,0,0,0,0,0,0]
[null,"HIGH"]
[null,"Belleview",null,825,825,438,438,309,567]
[null,"Dunnellon",null,545,545,545,0,0,327]
[null,"Forest",null,739,739,739,0,0,443.4]
[null,"Lake Weir",null,363,363,121,121,0,193.6]
[null,"North Marion",null,0,0,0,0,0,0]
[null,"Vanguard",null,918,918,918,918,193,773]
[null,"West Port",null,0,0,0,0,0,0]
[null,"OTHER SCHOOLS"]
[null,"Hillcrest",null,0,0,0,0,0,0]
[null,"Community Education",null,313,313,313,313,313,313]
[null,"Phoenix Center",null,176,176,176,50,0,115.6]
[]
["2f.","MARION COUNTY Total students in relocatables by year",null,7690,6724,4696,2782,815,4541.4]
[null,"Total number of CO-FTE students projected by year",null,37535,37661,37765,37990,38228,37835.8]
[null,"Percent in relocatables by year",null,0.2,0.18,0.12,0.07,0.02,0.12]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2002-03 Year","Type of School (new schools only)  Others=0","2002-03","2002-03 ","2002-03","2002-03","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"East Marion El. Clsrm add.",0,3000000,288,19933,69.21,0,0,0,10416.67,0,0,0]
[null,"Forest High Sch. Repl.",3,35000000,2000,210000,105,68,68,222,17500,14900,18106,26448]
[null,"North Marion HS Clsrm add.",0,1000000,0,0,"NA",0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Oakcrest El. Classrm add.",0,3000000,288,20000,69.44,0,0,0,10416.67,0,0,0]
[null,"St-W'dale El. Clsrm & Cafadd.",0,2500000,0,15000,"NA",0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"New El / Mid / HS Land",0,1000000,{"$nulls":6},{"$error":"#DIV/0!"}]
["3a.","MARION COUNTY Total 2002-03",null,45500000,2576,264933,102.85,null,null,null,17663.04]
[]
["3b.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04 ","20032-04 ","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Dunnellon Mid. Clsrm add.",0,4000000,382,34000,89.01,0,0,0,10471.2,0,0,0]
[null,"Ward-Hghds. Clsrm &Cafadd.",0,3000000,288,20000,69.44,0,0,0,10416.67,0,0,0]
["3b","MARION COUNTY Total 2003-04",null,7000000,670,54000,80.6,null,null,null,10447.76]
[]
["3c.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"North Marion Mid. Cafadd.",0,1000000,0,0,"NA",0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","MARION COUNTY Total 2004-05",null,1000000,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Elementary School",1,9000000,600,66000,110,79,110,156,15000,9213,12712,22844]
["3d.","MARION COUNTY Total 2005-06",null,9000000,600,66000,110,null,null,null,15000]
[]
["3e.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New High School",3,40000000,2000,256000,128,68,128,222,20000,14900,18106,26448]
["3e","MARION COUNTY Total 2006-07",null,40000000,2000,256000,128,null,null,null,20000]
[]
["3f.","MARION COUNTY 5-Year Total",null,102500000,5846,640933]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,2]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,16523260,17349423,18216894,19127739,20084126,91301442]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,16523260,17349423,18216894,19127739,20084126,91301442,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,2550000,3400000,1700000,1700000,1700000,11050000,0.121027661315579]
[null,"  less amount used to purchase other vehicles",{"$nulls":6},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",{"$nulls":6},0,0]
[null,"  less amount used for maintenance/repair",null,4094000,4115000,2920000,4850000,2930000,18909000,0.207105162698307]
[null,"  less amount used to purchase capital outlay equipment",null,400000,400000,400000,400000,400000,2000000,0.0219054590616433]
[null,"  less amount used to correct environmental problems",null,null,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,null,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,36470,{"$nulls":4},36470,0.000399446045989066]
[null,"  less amount to pay debt service for COP's ",null,4903530,5200000,5700000,5700000,5700000,27203530,0.297952906373593]
[null,"  less amount used for school renovations",null,2261028,0,0,0,0,2261028,0.0247644281456146,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,2278232,4234423,7496894,6477739,9354126,29841414,0.326844936359275,0.25]
[null,"P E C O New Construction",null,3465147,1667867,1847208,2051949,2071819,11103990,null,0.09]
[null,"Fund Balance Carry Forward from Prior Year",null,9447000,{"$nulls":4},9447000,null,0.08]
[null,"Interest Earnings",null,200000,200000,200000,200000,200000,1000000,null,0.01]
[null,"C O & D S maximum potential bond proceeds",null,200000,200000,200000,200000,200000,1000000,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,35000000,0,0,0,30000000,65000000,null,0.55]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,null,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0,null,0]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","MARION COUNTY Total",null,50590379,6302290,9744102,8929688,41825945,117392404,1.000000000000001,0.99]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Dunnellon Mid. Clsrm add",382,0,4000000,0,0,0,4000000]
[null,"E. Marion El. Clsrm add",288,3000000,0,0,0,0,3000000]
[null,"Forest HS replacement",2000,35000000,0,0,0,0,35000000]
[null,"Hillcrest Sch. Addition",0,500000,0,0,0,0,500000]
[null,"N. Marion HS Clsrm add",0,1000000,0,0,0,0,1000000]
[null,"N. Marion Mid. Cafet. Add",0,0,0,1000000,0,0,1000000]
[null,"Oakcrest El. Clsrm add",288,3000000,0,0,0,0,3000000]
[null,"Stanton-Wd El. Clsrm add",0,2500000,0,0,0,0,2500000]
[null,"Ward-Hds El. Clsrm add",288,0,3000000,0,0,0,3000000]
[null,"New Elementary \"T\"",600,0,0,0,9000000,0,9000000]
[null,"New High School \"DDD\"",2000,0,0,0,0,40000000,40000000]
[null,"New El / Mid / HS Land",null,1000000]
["5.","MARION COUNTY Total",5846,46000000,7000000,1000000,9000000,40000000,102000000]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","MARION COUNTY Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["7.","MARION COUNTY Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2002-03 ","2003-04 ","2004-05 ","2005-06","2006-07","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","","Check Totals"]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2002."]
[]
[null,"SCHOOL BOARD OF ","MARION COUNTY  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}