{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","99_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"99_5YrWkPlan","index":1,"n_rows":363,"n_cols":10,"rows_kept":363,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Okeechobee  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Okeechobee   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised"]
["electronically in digital format, as you received it (not a fax), prior to September 15, 1999, and all data accurate as of July 15, 1999.",{"$nulls":8},"1999-08-05"]
["District: ====>",null,"Okeechobee","Date: ==>","2000-09-12",null,"For fiscal years","  1999-2000 through 2003-2004"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[1,"ces replace flooring","CES",15000]
[1,"ces replace wooden chalkboards","CES",12000]
[1,"ces paint door jams","CES",6500]
[1,"ces restroom renovation","CES",15000]
[1,"districtwide contingency","DISTRICT",239045]
[1,"districtwide telephone systems","DISTRICT",159000]
[1,"ees replace carpet","EES",110314]
[1,"ees replace toggle switches air handlers","EES",6000]
[1,"ees strip paint window sills","EES",0]
[1,"ees paint remaining classrooms","EES",50000]
[1,"nehs renovation","NEHS",20000]
[1,"nes replace carpet","NES",154292]
[1,"nes paint interior door jams","NES",0]
[1,"ofc extend phone and cable","OFC",671]
[1,"ohs boys and girls RR b6 replace ceiling","OHS",2928]
[1,"ohs refurbish commons benches and planters","OHS",0]
[1,"ohs repair sidewalk front of auditorium","OHS",5000]
[1,"ohs softball batting cages","OHS",0]
[1,"ohs replace boiler","OHS",15000]
[1,"ohs drainage improvements","OHS",30000]
[1,"ohs new football stadium","OHS",1232614]
[1,"ohs paint exterior of voc bldg.","OHS",0]
[1,"ohs roof repair","OHS",47000]
[1,"ohs new blinds for chorus room","OHS",0]
[1,"ohs b6 and b7 new window treatment all rooms","OHS",28000]
[1,"oms fire rate mezz b8","OMS",0]
[1,"sem replace grilled covers to air handlers","SEM",6000]
[1,"sou playground equipment","SOUTH",59408]
[1,"trans environmental cleanup","TRANS",150000]
[1,"trans covered area","TRANS",35000]
[1,"yms interior wall repairs","YMS",40000]
[2,"ces resurface/extend asphalt play area","CES",null,12000]
[2,"district office pave rear entrance/parking","DISTRICT",null,60000]
[2,"districtwide contingency","DISTRICT",null,250000]
[2,"districtwide lighting retrofit","DISTRICT",null,293164]
[2,"ohs repave all asphalt areas as needed","OHS",null,200000]
[2,"ohs new doors and frames vocational building","OHS",null,40000]
[2,"ohs replace floor tile in hallways of b6 ","OHS",null,20000]
[2,"ohs replace asbestos tile b14","OHS",null,86187]
[2,"ohs b700 recarpet all rooms","OHS",null,20000]
[2,"ohs replace floor tile in band and chorus","OHS",null,12500]
[2,"ohs paint and retile back rooms and hall L.H.","OHS",null,8000]
[2,"ohs repair floor at expansion joint b203 and b201","OHS",null,5000]
[2,"ohs new ceiling tiles in band and chorus","OHS",null,8000]
[2,"ohs replace skylights in b7","OHS",null,4500]
[2,"ohs replace skylights in b6 stairwells","OHS",null,3500]
[2,"ohs drainage project","OHS",null,259860]
[2,"ohs restroom renovation","OHS",null,50000]
[2,"ohs barn roof repair","OHS",null,20000]
[2,"osc gym safety repairs","OMS",null,11500]
[2,"sem replace office and media center carpet","SEM",null,30000]
[2,"sem paint interior classroom walls","SEM",null,50000]
[2,"trans environmental cleanup","TRANS",null,420000]
[2,"trans replace rusted perlins  ","TRANS",null,50000]
[2,"yms install classroom doors in pods","YMS",null,120000]
[2,"yms carpet and vinyl replacement","YMS",null,70000]
[3,"ces seal office windows replace a/c","CES",null,null,20000]
[3,"ces replace classroom doors","CES",null,null,40000]
[3,"ces refinish dining area floor","CES",null,null,6500]
[3,"ces new sewage lines","CES",null,null,25000]
[3,"ces new water lines","CES",null,null,20000]
[3,"ces cover or paint tectum hallway ceiling","CES",null,null,17500]
[3,"ces replace old playground equipment","CES",null,null,22000]
[3,"districtwide contingency","DISTRICT",null,null,250000]
[3,"districtwide exhaust fans","DISTRICT",null,null,25000]
[3,"districtwide elementary covered PE areas","DISTRICT",null,null,120000]
[3,"ees replace kindergarten fencing","EES",null,null,4000]
[3,"ees roof replacement","EES",null,null,400000]
[3,"nes install insulation","NES",null,null,20000]
[3,"ohs replace gym air handlers","OHS",null,null,50000]
[3,"ohs replace doors office media b6 b7","OHS",null,null,30000]
[3,"ohs replace ext hall tile b6 b7","OHS",null,null,25000]
[3,"ohs replace all flooring in science bldg.","OHS",null,null,20000]
[3,"ohs drainage project","OHS",null,null,450000]
[3,"ohs repair fencing campuswide","OHS",null,null,10000]
[3,"ohs b7 remove carpet/treat walls","OHS",null,null,15000]
[3,"ohs paint remainder of exterior","OHS",null,null,55397]
[3,"ohs office renovation","OHS",null,null,70000]
[3,"ohs ag shop replace rusted steel","OHS",null,null,10000]
[3,"ohs ag b7 reroof and reside","OHS",null,null,10000]
[3,"ohs ag b8 replace rusted steel","OHS",null,null,5500]
[3,"sem replace classroom carpet","SEM",null,null,125000]
[3,"sem paint classroom doors","Sem",null,null,10000]
[3,"trans environmental cleanup","TRANS",null,null,200000]
[3,"yms replace restroom doors","YMS",null,null,20000]
[3,"yms ceiling tile/insulation replacement all pods","YMS",null,null,40000]
[3,"yms replace concrete downspouts","YMS",null,null,30000]
[3,"yms renovation of boys locker room","YMS",null,null,90000]
[4,"ces replace cafeteria a/c","CES",null,null,null,40000]
[4,"ces replace media center carpet","CES",null,null,null,20000]
[4,"districtwide repaving and restriping","DISTRICT",null,null,null,400000]
[4,"districtwide contingency","DISTRICT",null,null,null,150000]
[4,"districtwide replace exhaust fans","DISTRICT",null,null,null,100000]
[4,"ees install TEKNET","EES",null,null,null,100000]
[4,"nes repair air handlers","NES",null,null,null,10000]
[4,"nes install TEKNET","NES",null,null,null,100000]
[4,"ohs replace chiller","OHS",null,null,null,350000]
[4,"ohs install TEKNET","OHS",null,null,null,150000]
[4,"oms replace mezzanine stairs","OMS",null,null,null,35000]
[4,"sem extend k playground fence","SEM",null,null,null,10000]
[4,"sem strip paint from exterior window sills","SEM",null,null,null,4000]
[4,"sem roof replacement","SEM",null,null,null,400000]
[4,"trans environmental cleanup","TRANS",null,null,null,100000]
[4,"yms replace gym flooring","YMS",null,null,null,40000]
[4,"yms repaint hall lockers","YMS",null,null,null,15000]
[4,"yms add isolation valves all restrooms","YMS",null,null,null,12007]
[4,"yms install TEKNET","YMS",null,null,null,100000]
[5,"ces install TEKNET","CES",{"$nulls":4},80000]
[5,"districtwide contingency","DISTRICT",{"$nulls":4},194889]
[5,"district office install exterior stair railings","DISTRICT",{"$nulls":4},5000]
[5,"sem install TEKNET","SEM",{"$nulls":4},100000]
[5,"trans environmental cleanup","TRANS",{"$nulls":4},100000]
[5,"yms replace a/c","YMS",{"$nulls":4},200000]
[5,"yms remove wall carpet BR/CH/GYM","YMS",{"$nulls":4},100000]
["1.","Okeechobee Total",null,2438772,2104211,2235897,2136007,779889,0]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01","2001-02","2002-03","2003-04","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New Elementary C (South Elem)",{"$nulls":6},0]
[null,"Central Elementary Addition",{"$nulls":5},1317468,1317468]
["2 .","Okeechobee Total",{"$nulls":5},1317468,1317468]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1999-00 FISH Satisfactory","Actual 1999-00","Actual 1999-00","Actual 1999-00","New Stu Capacity to","Projected 2004-05","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"North Elementary",820,820,665,0.81,-245,600,1.04]
[null,"Central Elementary",708,708,510,0.72,-307,500,1.25]
[null,"South Elementary",589,589,530,0.9,-561,0]
[null,"Everglades Elementary",851,851,770,0.9,-195,700,1.07]
[null,"Seminole Elementary",854,854,710,0.83,-178,650,0.96]
[null,"Yearling Middle",1074,966.6,650,0.67,-224,650,0.88]
[null,"Osceola Middle",981,882.9,825,0.93,-385,800,1.61]
[null,"Freshman Campus",133,126.35,450,3.56,297,403,0.95]
[null,"Okeechobee High",2006,1905.6999999999998,1150,0.6,-545,1051,0.77]
[null,"Elementary 'C'",0,0,null,null,720,680,0.94]
[null,"ACE PreK",18,18,40,null,-5,15,1.15]
["2a.","Okeechobee Total",8034,7721.55,6300,0.82,-1628,6049,0.99]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"Elementary 'C', on the same property as South Elementary, south of Highway 70 and west of US441."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2003-04","Column \"C\""]
[null,"Freshman Campus",0,"district",0,0,0,0,0]
[null,"Okeechobee High School",8,"district",0,8,0,8,160]
[null,"Okeechobee High School","0","federal",0,"0",0,"0",0]
[null,"Yearling Middle School","2","district",0,"2",0,"2",48]
[null,"North Elementary","2","district",38,"0",0,"2",25]
[null,"North Elementary","1","federal",27,"0",0,"1",19]
[null,"Central Elementary","7","district",155,"0",0,"7",172]
[null,"Central Elementary","2","federal",42,"0",0,"2",50]
[null,"South Elementary","1","district",0,"1",0,"1",25]
[null,"South Elementary","2","federal",24,"1",0,"2",38]
[null,"Everglades Elementary","2","district",38,"0",0,"2",25]
[null,"Everglades Elementary","1","federal",22,"0",0,"1",19]
[null,"Seminole Elementary","2","district",50,"0",0,"2",14]
["2c1.","Okeechobee Total",30,null,null,0,0,30,"Avg Age 19.83"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01","2001-02","2002-03","2003-04","2004-05","5 YEAR TOTAL"]
[null,"Freshman Campus","0","0","0","0","0","0","1"]
[null,"Okeechobee High School","8","8","0","0","0","0","18"]
[null,"Yearling Middle School","2","2","0","0","0","0","2"]
[null,"North Elementary","3","0","3","0","0","0","3"]
[null,"Central Elementary","9","0","9","0","0","0","9"]
[null,"South Elementary","3","0","3","0","0","0","3"]
[null,"Everglades Elementary","3","0","3","0","0","0","3"]
[null,"Seminole Elementary","2","0","2","0","0","0","2"]
["2c2.","Okeechobee Total",30,10,20,0,0,0,30]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1998-99","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2003-04","FISH Stu. Sta.","# Years Leased "]
[null,"None"]
["2c3.","Okeechobee Total",0,null,0,0,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2003-04"]
[null,"None"]
["2c4.","Okeechobee Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-2000 CO-FTE","1999-2000 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"North Elementary",28,820,665,23.75,600,-5,26.09]
[null,"Central Elementary",29,708,510,17.59,500,-11,27.78]
[null,"South Elementary",26,589,530,20.38,0,-26]
[null,"Everglades Elementary",28,851,770,27.5,700,-4,29.17]
[null,"Seminole Elementary",28,854,710,25.36,650,-4,27.08]
[null,"Yearling Middle",29,967,650,22.41,650,-7,29.55]
[null,"Osceola Middle",29,883,825,28.45,800,0,27.59]
[null,"Freshman Campus",6,126,450,75,403,6,33.58]
[null,"Okeechobee High",54,1906,1150,21.3,1051,-23,33.9]
[null,"New Elementary \"C'",null,0,null,null,680,35,19.43]
[null,"ACE PreK",null,18,40,null,15]
["2e.","Okeechobee Total",257,7722,6300,"District Avg 25",6049,-39,"District Avg 28"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2000-01","2001-02","2002-03","2003-04","2004-05","5 YEAR AVERAGE"]
[null,"Okeechobee Center",null,0,0,0,0,0,0]
[null,"Okeechobee High School",null,0,0,0,0,0,0]
[null,"Yearling Middle School",null,0,0,0,0,0,0]
[null,"Osceola Middle School",null,0,0,0,0,0,0]
[null,"North Elementary",null,0,0,0,0,0,0]
[null,"Central Elementary",null,0,0,0,0,0,0]
[null,"South Elementary",null,0,0,0,0,0,0]
[null,"Everglades Elementary",null,0,0,0,0,0,0]
[null,"Seminole Elementary",null,0,0,0,0,0,0]
["2f.","Okeechobee Total students in relocatables by year",null,0,0,0,0,0,0]
[null,"Total number of CO-FTE students projected by year",null,6369,6288,6214,6159,6049,6215.8]
[null,"Percent in relocatables by year",null,0,0,0,0,0,0]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"The ACE Pre-K site will be sold."]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year"]
[{"$nulls":9},"Type of School"]
[{"$nulls":9},1]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 127, avg 150, high 178 ",{"$nulls":7},2]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 13,985, avg 20,182, high  28,785 ",{"$nulls":7},3]
[]
["3a.","2000-2001 Year","Type of School (new schools only)  Others=0","1999-00","1999-00","1999-00","1999-00",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta"]
[null,"None"]
["3a.","Okeechobee Total 1999-00",null,0,0,0,{"$error":"#DIV/0!"}]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2000-01","2000-01","2000-01","2000-01",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta"]
[null,"None"]
["3b","Okeechobee Total 2000-01",null,0,0,0]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta"]
[null,"None"]
["3c","Okeechobee Total 2001-02",null,1317468,0,16329]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta"]
[null,"None"]
["3d.","Okeechobee Total 2002-03",null,0,0,0]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04",{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta"]
[null,"Central Elementary Addition",0,1317468,0,16329,null,0,0,0]
["3e","Okeechobee Total 2003-04",null,{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[]
["3f.","Okeechobee 5-Year Total",null,{"$error":"#REF!"},{"$error":"#REF!"},{"$error":"#REF!"}]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01","2001-2002","2002-03","2003-04","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,1845218,1843000,1843000,1843000,1843000,9217218]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,1845218,1843000,1843000,1843000,1843000,9217218,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,283000,330000,330000,350000,350000,1643000]
[null,"  less amount used to purchase other vehicles",null,40000,40000,40000,40000,40000,200000]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,1522218,1473000,1473000,1453000,1453000,7374218]
[null,"PECO General Revenue",null,146022,182121,331788,263240,224590]
[null,"PECO School Trust Fund",null,19928]
[null,"Interest",null,20500,10000,10000,10000,10000]
[null,"Interest OUA Mortgage",null,6670.83,7500,7500,7500,7500]
[null,"PECO Maintenance",null,562674,421590,403609,392267,392267,2172407,0.235690096512852]
[null,"CO and DS Flow Thru",null,18862,{"$nulls":4},18862,0.00204638753255049]
[null,"Fuel Tax Refund",null,10000,10000,10000,10000,10000,50000]
[null,"Racing Revenue",null,131897]
[null,"Reserves for Encumbrances",null,900344.86,0,0,0,0]
[null,"Fund Balance Brought Forward",null,462160.63,0,0,0,0]
["4.","Okeechobee Total",null,3801277.32,2104211,2235897,2136007,2097357,68862,0.23773648404540249]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01","2001-02","2002-03","2003-04","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Elementary C (South Elem)",null,0]
[null,"Central Elementary Addition",{"$nulls":5},1317468]
["5.","Okeechobee Total",null,0,null,null,null,1317468,1317468]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01","2001-02","2002-03","2003-04","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Effort Index Grants"]
[null,"SIT Program awards"]
[null,"Other (specify)"]
["6.","Okeechobee Total"]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01","2001-02","2002-03","2003-04","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"None"]
["7.","Okeechobee Total",null,0,0,0,0,0,0]
[]
[null,"Project Description",null,"2000-01","2001-02","2002-03","2003-04","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this 15th day of September, 2000."]
[]
[null,"SCHOOL BOARD OF ","Okeechobee  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Phoebe Raulerson"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":4},"Connie Trent",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Lee Dixon","Assistant Superintendent","761.5000X259 761-5000",null,"dixon@ocsb.okee.k12.fl.us",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address"]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}