{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"00_5YrWkPlan","index":1,"n_rows":1643,"n_cols":25,"rows_kept":1643,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["ORANGE  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["ORANGE   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},36602,{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"ORANGE","Date: ==>","2001-01-16",null,"For fiscal years","  2000-2001 through 2004-2005"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety"]
[null,"Building Envelope &","West Orange HS ",5503000," ",null,null,null,5503000]
[null," Life-Safety","Apopka HS ",5578000,{"$nulls":4},5578000]
[null,null,"Winter Park 9th Gr Ctr  ",1292000,{"$nulls":4},1292000]
[null,null,"Orlo Vista ES ",1486000,{"$nulls":4},1486000]
[null,null,"Cheney ",1618000,{"$nulls":4},1618000]
[null,null,"Rock Lake ES ",1774000,null,null," ",null,1774000]
[null,null,"Washington Shores ES ",1726000,{"$nulls":4},1726000]
[null,null,"Lee MS ",5202000,{"$nulls":4},5202000]
[null,null,"Robinswood MS ",1401000,{"$nulls":4},1401000]
[null,null,"Colonial 9th Grade Ctr ",420000,{"$nulls":4},420000]
[null,null,"Meadowbrook MS ",5427000,{"$nulls":4},5427000]
[null,null,"Engelwood ES ",2253000,{"$nulls":4},2253000]
[null,null,"Evans 9th Grade Ctr ",1234000,{"$nulls":4},1234000]
[null,null,"Conway ES ",2399000,{"$nulls":4},2399000]
[null,null,"Lakemont ES ",325000,{"$nulls":4},325000]
[null,null,"Wheatley ES ",2288000,{"$nulls":4},2288000]
[null,null,"Lake Silver ES ",2924000,{"$nulls":4},2924000]
[null,null,"Hiawassee ES ",2401000,{"$nulls":4},2401000]
[null,null,"Orange Center ES ",3779000,{"$nulls":4},3779000]
[null,null,"McCoy ES ",1574000,{"$nulls":4},1574000]
[null,null,"Dr. Phillps HS ",2497000,{"$nulls":4},2497000]
[null,null,"Apopka ES ",1701000,{"$nulls":4},1701000]
[null,null,"Ridgewood Park ES ",3222000,null,null,null," ",3222000]
[null,null,"Kaley ES ",3041000,{"$nulls":4},3041000]
[null,null,"Ocoee ES ",3456000,{"$nulls":4},3456000]
[null,null,"Columbia ES ",585000,null,null,null," ",585000]
[null,null,"Windermere ES ",44000,null,null,null," ",44000]
[null,null,"Dommerich ES ",1336000,{"$nulls":4},1336000," "]
[{"$nulls":8},0]
[null,"Environmental Projects","District-wide",1749880,400000,400000,400000,400000,3349880," "]
[{"$nulls":8},0]
[null,"Misc. Life-Safety Projects","District-wide",4179536,2400000,1800000,1350000,1250000,10979536]
[{"$nulls":8},0]
[null,"Security/Safety Projects","District-wide",1288058,400000,400000,400000,400000,2888058]
[{"$nulls":8},0]
[null,"Emergency Shelter","Walker MS",50592," ",null,null,null,50592,null," "]
[null,"   Retro-fit Projects","Cypress Creek HS",66593," ",null,null,null,66593]
[null,null,"University HS",62477,{"$nulls":4},62477]
[null,null,"Dr. Phillips HS",69787,{"$nulls":4},69787,null," "]
[null,null,"Union Park MS",54762,{"$nulls":4},54762]
[null,null,"Endeavor ES",18634,{"$nulls":4},18634]
[null,null,"Lakeville ES",18431,{"$nulls":4},18431]
[null,null,"Lawton Chiles ES",25379,{"$nulls":4},25379]
[null,null,"Other Sites Based on Priority",1738759,400000,400000,400000,400000,3338759]
[{"$nulls":8},0]
[null,"Ancilary Facilities","District-wide",119823,0,0,0,0,119823]
[{"$nulls":8},0]
[null,"Capital Maintenance","District-wide",10096733,7565104,7242445,7038992,7038992,38982266,null," "]
[null,null,"Portable Repairs",1033397,400000,400000,400000,400000,2633397]
[null,"Technology","Network Technology",1614000,1664000,1174000,1184000,1184000,6820000]
[null,null,"District-wide Retrofits",3795672,1000000,1000000,1000000,1000000,7795672]
[{"$nulls":8},0]
[null,"Schools Allocation","District-wide Minor Projects",1986774,2052603,2102603,2102603,2102603,10347186]
[{"$nulls":8},0]
[null,"Portable Installations","District-wide",7895095,6300000,5600000,4900000,4900000,29595095]
[{"$nulls":8},0]
[null,"Portable Leasing","District-wide",7155627,6300000,6300000,6300000,6300000,32355627]
[{"$nulls":8},0]
["1.","ORANGE Total",null,109506009,28881707,26819048,25475595,25375595,216057954]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety",{"$nulls":6}," "]
[null,"Building Envelope &","West Orange HS ",5503000,{"$nulls":4},5503000]
[null," Life-Safety","Apopka HS ",5578000,{"$nulls":4},5578000]
[null,null,"Winter Park 9th Gr Ctr  ",1292000,{"$nulls":4},1292000]
[null,null,"Orlo Vista ES ",1486000,null,null," ",null,1486000]
[null,null,"Cheney ",1618000,{"$nulls":4},1618000]
[null,null,"Rock Lake ES ",1774000,null," ",null,null,1774000]
[null,null,"Washington Shores ES ",1726000,{"$nulls":4},1726000]
[null,null,"Lee MS ",5202000,{"$nulls":4},5202000]
[null,null,"Robinswood MS ",1401000,{"$nulls":4},1401000]
[null,null,"Colonial 9th Grade Ctr ",420000,{"$nulls":4},420000]
[null,null,"Meadowbrook MS ",5427000,{"$nulls":4},5427000]
[null,null,"Engelwood ES ",2253000,{"$nulls":4},2253000]
[null,null,"Evans 9th Grade Ctr ",1234000,{"$nulls":4},1234000]
[null,null,"Conway ES ",2399000,{"$nulls":4},2399000]
[null,null,"Lakemont ES ",325000,{"$nulls":4},325000]
[null,null,"Wheatley ES ",2288000,{"$nulls":4},2288000]
[null,null,"Lake Silver ES ",2924000,{"$nulls":4},2924000]
[null,null,"Hiawassee ES ",2401000,{"$nulls":4},2401000]
[null,null,"Orange Center ES ",3779000,null,null,null," ",3779000]
[null,null,"McCoy ES ",1574000,{"$nulls":4},1574000]
[null,null,"Dr. Phillps HS ",2497000,{"$nulls":4},2497000]
[null,null,"Apopka ES ",1701000,{"$nulls":4},1701000]
[null,null,"Ridgewood Park ES ",3222000,{"$nulls":4},3222000]
[null,null,"Kaley ES ",3041000,{"$nulls":4},3041000]
[null,null,"Ocoee ES ",3456000,{"$nulls":4},3456000]
[null,null,"Columbia ES ",585000,{"$nulls":4},585000]
[null,null,"Windermere ES ",44000,{"$nulls":4},44000]
[null,null,"Dommerich ES ",1336000,{"$nulls":4},1336000]
[null,null,null,456000,{"$nulls":4},456000]
[null,"Environmental Projects","District-wide",1749880,400000,400000,400000,400000,3349880]
[{"$nulls":8},0]
[null,"Misc. Life-Safety Projects","District-wide",4179536,2400000,1800000,1350000,1250000,10979536]
[{"$nulls":8},0]
[null,"Security/Safety Projects","District-wide",1288058,400000,400000,400000,400000,2888058]
[{"$nulls":8},0]
[null,"Emergency Shelter","Walker MS",50592," ",null,null,null,50592]
[null,"   Retro-fit Projects","Cypress Creek HS",66593," ",null,null,null,66593]
[null,null,"University HS",62477,{"$nulls":4},62477]
[null,null,"Dr. Phillips HS",69787,{"$nulls":4},69787]
[null,null,"Union Park MS",54762,{"$nulls":4},54762]
[null,null,"Endeavor ES",18634,null,null," ",null,18634]
[null,null,"Lakeville ES",18431,{"$nulls":4},18431]
[null,null,"Lawton Chiles ES",25379,{"$nulls":4},25379]
[null,null,"Other Sites Based on Priority",1738759,400000,400000,400000,400000,3338759]
[{"$nulls":8},0]
[null,"Ancilary Facilities","District-wide",119823," "," "," ",null,119823]
[{"$nulls":8},0]
[null,"Capital Maintenance","District-wide",10096733,7565104,7242445,7038992,7038992,38982266]
[null,null,"Portable Repairs",1033397,400000,400000,400000,400000,2633397]
[{"$nulls":8},0]
[null,"Technology","Network Technology",1614000,1664000,1174000,1184000,1184000,6820000]
[null,null,"District-wide Retrofits",3795672,1000000,1000000,1000000,1000000,7795672]
[{"$nulls":8},0]
[null,"Schools Allocation","District-wide Minor Projects",1986774,2052603,2102603,2152603,2152603,10447186]
[{"$nulls":8},0]
[null,"Portable Installations","District-wide",7895095,6300000,5600000,4900000,4900000,29595095]
[{"$nulls":8},0]
[null,"Portable Leasing","District-wide",7155627,6300000,6300000,6300000,6300000,32355627]
[{"$nulls":8},0]
[null,"Comprehensive Projects",{"$nulls":4}," ",null,0]
[null,"(Renovation, remodeling, ",null,null," ",null,null,null,0," "]
[null,"new additions, ADA, Tech-","Master Planning District-Wide",860000,{"$nulls":4},860000]
[null,"nology retro-fit)","Boone HS ",2011865,{"$nulls":4},2011865]
[null,null,"Jones HS ",35198000,{"$nulls":4},35198000]
[null,null,"Winter Park HS ",24038000,{"$nulls":4},24038000]
[null,null,"Howard MS",26588723,{"$nulls":4},26588723]
[null,null,"Colonial HS ",46854037,{"$nulls":4},46854037]
[null,null,"Lakeview MS ",15460000,{"$nulls":4},15460000,null," "]
[null,null,"Palmetto ES ",3299465,{"$nulls":4},3299465]
[null," ","Colonial 9th MS Conversion",null,15600000,null,null,null,15600000]
[null,null,"West Orange HS Reconstruct'n ",null,null,null,63200000,null,63200000]
[null,null,"W. Orange 9th MS Conversion",{"$nulls":4},18000000,18000000]
[]
[null,"Comprehensive Projects","Cherokee Exceptional Ed.",{"$nulls":4},4626000,4626000]
[null,"Unfunded","Silver Star Center",{"$nulls":4},2499999,2499999]
[null,null,"Mid FL Tech",{"$nulls":4},23493000,23493000]
[null,null,"Princeton ES",{"$nulls":4},3826000,3826000]
[null,null,"Edgewater HS",{"$nulls":4},8542000,8542000]
[null,null,"Gateway Ex Ed.",{"$nulls":4},5468000,5468000]
[null,null,"Westridge MS",{"$nulls":4},10659000,10659000]
[null,null,"Pine Castle ES",{"$nulls":4},5237000,5237000]
[null,null,"Winter Park 9th GC",{"$nulls":4},16986000,16986000]
[null,null,"Rolling Hills ES",{"$nulls":4},6149000,6149000]
[null,null,"Audubon Park Es",{"$nulls":4},8778000,8778000]
[null,null,"Magnolia School",{"$nulls":4},6543000,6543000]
[null,null,"Union Park ES",{"$nulls":4},4631000,4631000]
[null,null,"Evans HS",{"$nulls":4},6824000,6824000]
[null,null,"Lake Weston ES",{"$nulls":4},4553000,4553000]
[null,null,"Azalea Park ES",{"$nulls":4},7598000,7598000]
[null,null,"Orlo Vista ES",{"$nulls":4},17231000,17231000]
[null,null,"Orlando Tech",{"$nulls":4},8994000,8994000]
[null,null,"Cheney ES",{"$nulls":4},9677000,9677000]
[null,null,"Hillcrest ES",{"$nulls":4},3026000,3026000]
[null,null,"Oakridge HS",{"$nulls":4},19924000,19924000]
[null,null,"Memorial MS",{"$nulls":4},10612000,10612000]
[null,null,"Cypress Park ES",{"$nulls":4},7589000,7589000]
[null,null,"Riverside ES",{"$nulls":4},6825000,6825000]
[null,null,"Winter Park Tech",{"$nulls":4},48333000,48333000]
[null,null,"Carver MS",{"$nulls":4},8906000,8906000]
[null,null,"Chicksaw ES",{"$nulls":4},8125000,8125000]
[null,null,"Hungerford ES",{"$nulls":4},3704000,3704000]
[null,null,"Zellwood ES",{"$nulls":4},5884000,5884000]
[null,null,"Rock Lake ES",{"$nulls":4},5318000,5318000]
[null,null,"Washington Shores ES",{"$nulls":4},7092000,7092000]
[null,null,"Grand Avenue ES",{"$nulls":4},5000000,5000000]
[null,null,"Lee MS",{"$nulls":4},13299000,13299000]
[null,null,"Lockhart MS",{"$nulls":4},8990000,8990000]
[null,null,"Maitland MS",{"$nulls":4},8369000,8369000]
[null,null,"Lancaster ES",{"$nulls":4},7276000,7276000]
[null,null,"Mollie Ray ES",{"$nulls":4},6268000,6268000]
[null,null,"Pine Hills ES",{"$nulls":4},12849000,12849000]
[null,null,"Pineloch ES",{"$nulls":4},7164000,7164000]
[null,null,"Metrowest ES",{"$nulls":4},5870000,5870000]
[null,null,"Lockhart ES",{"$nulls":4},6093000,6093000]
[null,null,"Oakhill ES",{"$nulls":4},7493000,7493000]
[null,null,"Walker MS",{"$nulls":4},16500000,16500000]
[null,null,"Westside Tech",{"$nulls":4},33153000,33153000]
[null,null,"Conway MS",{"$nulls":4},12496000,12496000]
[null,null,"Robinswood MS",{"$nulls":4},7510000,7510000]
[null,null,"Dover Shores ES",{"$nulls":4},9814000,9814000]
[null,null,"Pershing ES",{"$nulls":4},3252000,3252000]
[null,null,"Killarney ES",{"$nulls":4},9383000,9383000]
[null,null,"Fern Creek ES",{"$nulls":4},3995000,3995000]
[null,null,"Catalina ES",{"$nulls":4},5255000,5255000]
[null,null,"Meadowbrook MS",{"$nulls":4},11416000,11416000]
[null,null,"Engelwood ES",{"$nulls":4},8771000,8771000]
[null,null,"Evans 9th GC",{"$nulls":4},5641000,5641000]
[null,null,"Conway ES",{"$nulls":4},7309000,7309000]
[null,null,"Lakemont ES",{"$nulls":4},6799000,6799000]
[null,null,"Wheatley ES",{"$nulls":4},7434000,7434000]
[null,null,"Cypress Creek HS",{"$nulls":4},11677000,11677000]
[null,null,"Hungerford Prep HS",{"$nulls":4},16776000,16776000]
[null,null,"Sadler ES",{"$nulls":4},10473000,10473000]
[null,null,"Lake Silver ES",{"$nulls":4},7745000,7745000]
[null,null,"Eccleston ES",{"$nulls":4},5662000,5662000]
[null,null,"Hiawassee ES",{"$nulls":4},9811000,9811000]
[null,null,"Richmond Heights ES",{"$nulls":4},6753000,6753000]
[null,null,"Dream Lake ES",{"$nulls":4},8274000,8274000]
[null,null,"Brookshire ES",{"$nulls":4},6784000,6784000]
[null,null,"Spring Lake ES",{"$nulls":4},6793000,6793000]
[null,null,"Orange Center ES",{"$nulls":4},5793000,5793000]
[null,null,"Union Park MS",{"$nulls":4},11642000,11642000]
[null,null,"Jackson MS",{"$nulls":4},14401000,14401000]
[null,null,"Tangelo Park ES",{"$nulls":4},7336000,7336000]
[null,null,"McCoy ES",{"$nulls":4},9138000,9138000]
[null,null,"Dr. Phillips HS",{"$nulls":4},12917000,12917000]
[null,null,"Maxey ES",{"$nulls":4},3865000,3865000]
[null,null,"Lake Como ES",{"$nulls":4},4760000,4760000]
[null,null,"Apopka ES",{"$nulls":4},9426000,9426000]
[null,null,"Ridgewood Park ES",{"$nulls":4},8733000,8733000]
[null,null,"Kaley ES",{"$nulls":4},3983000,3983000]
[null,null,"Pinar ES",{"$nulls":4},8469000,8469000]
[null,null,"Dr. Phillips ES",{"$nulls":4},8375000,8375000]
[null,null,"Dillard St. ES",{"$nulls":4},6164000,6164000]
[null,null,"Bonneville ES",{"$nulls":4},7761000,7761000]
[null,null,"Ocoee ES",{"$nulls":4},7502000,7502000]
[null,null,"Columbia ES",{"$nulls":4},6317000,6317000]
[null,null,"Windermere ES",{"$nulls":4},6013000,6013000]
[null,null,"Dommerich ES",{"$nulls":4},8349000,8349000]
[null,null,"Tildeville ES",{"$nulls":4},7161000,7161000]
[null,null,"Lake Sybelia ES",{"$nulls":4},4465000,4465000]
[null,null,"Dr. Phillips 9th GC",{"$nulls":4},7342000,7342000]
[null,null,"Ivey Lane ES",{"$nulls":4},5604000,5604000]
[null,null,"Lovell ES",{"$nulls":4},3867000,3867000]
[null,null,"Meadow Woods ES",{"$nulls":4},7642000,7642000]
[null,null,"Winegard ES",{"$nulls":4},6911000,6911000]
[null,null,"Liberty MS ",{"$nulls":4},7508000,7508000]
[null,null,"Aloma ES",{"$nulls":4},5068000,5068000]
[null,null,"Clarcona Es",{"$nulls":4},3889000,3889000]
[null,null,"Little River ES",{"$nulls":4},7740000,7740000]
[null,null,"Southwest MS",{"$nulls":4},3535000,3535000]
[null,null,"Apopka MS",{"$nulls":4},7996000,7996000]
[null,null,"Clay Springs ES",{"$nulls":4},7753000,7753000]
[null,null,"Hidden Oaks ES",{"$nulls":4},7455000,7455000]
[null,null,"Ventura ES",{"$nulls":4},10528000,10528000]
[null,null,"Durrance ES",{"$nulls":4},8689000,8689000]
[null,null,"Gotha MS",{"$nulls":4},8183000,8183000]
[null,null,"University HS",{"$nulls":4},17773000,17773000]
[null,null,"Frangus ES",{"$nulls":4},8932000,8932000]
[null,null,"Shenandoah ES",{"$nulls":4},5989000,5989000]
[null,null,"Palm Lake ES",{"$nulls":4},7979000,7979000]
[null,null,"Deerwood ES",{"$nulls":4},4793000,4793000]
[null,null,"Arbor Ridge ES",{"$nulls":4},9785000,9785000]
[null,null,"Hunter's Creek MS",{"$nulls":4},3425000,3425000]
[null,null,"Bay Meadows ES",{"$nulls":4},8731000,8731000]
[null,null,"Waterford ES",{"$nulls":4},3384000,3384000]
[null,null,"Apopka 9th GC",{"$nulls":4},18900000,18900000]
[null,null,"Waterbridge ES",{"$nulls":4},10894000,10894000]
[null,null,"John Young ES",{"$nulls":4},7973000,7973000]
[null,null,"Rock Springs ES",{"$nulls":4},8504000,8504000]
[null,null,"Shingle Creek ES",{"$nulls":4},7629000,7629000]
[null,null,"Windy Ridge ES",{"$nulls":4},9979000,9979000]
[null,null,"Hunter's Creek ES",{"$nulls":4},8724000,8724000]
[null,null,"Piedmont Lake MS",{"$nulls":4},2942000,2942000]
[null,null,"Cypress Springs ES",{"$nulls":4},8059000,8059000]
[null,null,"Discovery MS",{"$nulls":4},1520000,1520000]
[null,null,"Lake Whitnery ES",{"$nulls":4},1377000,1377000]
[null,null,"Rosemont ES",{"$nulls":4},1834000,1834000]
[null,null,"Southwood ES",{"$nulls":4},683000,683000]
[null,null,"Sunrise ES",{"$nulls":4},2542000,2542000]
[null,null,"Lakeville ES",{"$nulls":4},357000,357000]
[null,null,"Riverdale ES",{"$nulls":4},645000,645000]
[null,null,"Corner Lakes MS",{"$nulls":4},957000,957000]
[null,null,"Meadow Woods MS",{"$nulls":4},270000,270000]
[]
[null,"New Schools","New School Project Carry-0ver",13010093,null," ",null,null,13010093]
[null,"New Schools In Progress","New ES \"A\" (ColumbiaSunrise)",11800000,null," ",null,null,0]
[null,null,"New ES \"B\" (Hunters Creek)",2906851,{"$nulls":4},0]
[null,null,"New ES \"C\" (Frangus/Ocoee)",3234689,{"$nulls":4},3234689]
[null,null,"New ES \"D\" (Ventura/Pinar)",10974208,{"$nulls":4},10974208]
[null,null,"New ES \"E\" (East/West)",10734739]
[null,null,"New ES \"F\" (Blankner Repl K-8",17800000]
[null,null,"New ES \"G\" (Lake Whitney)",12100000]
[null,null,"Ocoee Dem.MS (add'l capacity)",13553823,{"$nulls":4},13553823]
[null,null,"New MS \"BB\" (Liberty/Conway)",21662788,{"$nulls":4},21662788]
[null,null,"New HS \"AAA\"(W.Or/Dr.Philips)",41775408,{"$nulls":4},41775408]
[null,null,"New HS \"BBB\" (University)",41186291,{"$nulls":4},41186291]
[]
[null,"New Schools Planned","New ES \"H\" (Northwest)",null,12600000,null,null,null,12600000]
[null,null,"New ES \"I\" (West/North)"," ",12600000,null,null,null,12600000]
[null,null,"New ES \"J\" (NTC Site)",null,null,null,12800000]
[null," ","New MS \"AA\"(Glen Ridge Repl)"," ",21700000," "," ",null,21700000]
[null,null,"New MS \"BB\"(Discovery)",null,22300000]
[null,null,"New MS \"CC\" (South/West)",null,22300000]
[null," ","New HS \"CCC\" (Cypress Crk)"," ",58400000," "," ",null,58400000]
[null," ","New HS \"DDD\"(West/North)"," "," ",59800000," ",null,59800000]
[null," ","New HS \"EEE\"(W.Orange Repl)"," "," "," ",63200000,null,63200000]
[null,"New School Payments","Northlake Park ES (Lake Nona)"," "," ",8700000," ",null,8700000," "]
[{"$nulls":8},0]
[null,"Unfunded New Schools","Horizon's West ES Relief",null,null,null," ",null,0]
[null,null,"Lake Nona Or Meadow Woods ES Relief",null,null,null," ",null,0]
[null,null,"Hunter's Creek ES Relief",null,null,null," ",null,0]
[null,null,"East Area MS Relief",null,null,null," ",null,0]
[null,null,"Horizon's West or Lakeview/Ocoee/Piedmont Lakes MS Relief",null,null,null," ",null,0]
[null,null,"Southeast or Southwest HS Relief ",null,null,null," ",null,0]
[null,null,"North Area HS Relief"]
[null,null," ",null,null," ",null,null,0]
[null,"Portable Replacement w/","Tildenville ES",2240000,{"$nulls":4},2240000]
[null,"Permanent Construction","Ventura ES",1120000,{"$nulls":4},1120000]
[null,null,"Azalea Park ES",1120000," ",null,null,null,1120000]
[null,null,"Chickasaw ES",1120000," "," ",null,null,1120000]
[null,null,"Mollie Ray ES",1120000,{"$nulls":4},1120000]
[null,null,"Lockhart ES ",1680000,{"$nulls":4},1680000]
[null,null,"Dover Shores ES",1120000,{"$nulls":4},1120000]
[null,null,"Richmond Heights ES",3360000,{"$nulls":4},3360000]
[null,null,"Ridgewood Park ES",1120000,{"$nulls":4},1120000]
[null,null,"Pinar ES",2240000,null,null," ",null,2240000]
[null,null,"Bonneville ES",2240000]
[null,null,"Orlo Vista ES",2240000]
[null,null,"Columbia ES",1120000,{"$nulls":4},1120000]
[null,null,"Cypress Park ES",2240000]
[null,null,"Dream Lake ES",2240000]
[null,"Unfunded Portable"," ",{"$nulls":5},0]
[null,"Replacement Projects","Engelwood ES",{"$nulls":4},424024,424024]
[null,null,"Rock Springs ES",{"$nulls":4},4200000,4200000]
[null,null,"Lakemont ES",{"$nulls":4},1200000,1200000]
[null,null,"Dillard Street ES",{"$nulls":4},840000,840000]
[null,null,"Windermere ES",null,null," ",null,1320000,1320000]
[null,null,"Shenandoah ES"," ",null,null,null,480000,480000]
[null,null,"Palm Lake ES",{"$nulls":4},4680000,4680000]
[null,null,"MetroWest ES",null,null," ",null,3840000,3840000]
[{"$nulls":8},0]
[null,"Permanent Construction ","Rock Springs ES",{"$nulls":4},706707,706707]
[null,"For Class Size Reduction","Lakemont ES",{"$nulls":4},848049,848049]
[null,"Unfunded ","Dillard Street ES",{"$nulls":4},706707,706707]
[null,null,"Bonneville ES",{"$nulls":4},848049,848049]
[null,null,"Windermere ES",{"$nulls":4},706707,706707]
[null,null,"Shenandoah ES",{"$nulls":4},565366,565366]
[null,null,"Palm Lake ES",null," ",null,null,706707,706707]
[null,null,"Englewood ES",{"$nulls":4},424024,424024]
[null,null,"MetroWest ES",null,null," ",null,1130731,1130731]
[{"$nulls":8},0]
[null,"Site Acquisition","District-wide",12997326,5812500,6825000,3000000,3000000,31634826]
[null," ",null," "," "," "," ",null,0]
["2 .","Orange Totals",null,504328315,200194207,102144048,167725595,1132712665,2107104830]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:",null,null," "]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1999-00 FISH Satisfactory","Actual 1999-00","Actual 1999-00","Actual 1999-00","New Stu Capacity to","Projected 2004-05","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Aloma ES ",677,677,618,0.91,-12,606,0.91]
[null,"Apopka ES ",1019,1019,563,0.55,79,642,0.58]
[null,"Arbor Ridge ES ",1166,1166,1058,0.91,-118,940,0.9]
[null,"Audubon Park ES ",853,853,557,0.65,-12,545,0.65]
[null,"Azalea Park ES ",1119,1119,1032,0.92,-45,987,0.92]
[null,"Bay Meadows ES",1292,1292,988,0.76,118,1106,0.78]
[null,"Blankner ES",1111,1111,628,0.57,434,1062,0.69]
[null,"Bonneville ES ",923,923,939,1.02,86,1025,1.02]
[null,"Brookshire ES ",742,742,543,0.73,31,574,0.74]
[null,"Catalina ES ",1086,1086,723,0.67,80,803,0.69," "]
[null,"Cheney ES ",852,852,738,0.87,-22,716,0.86]
[null,"Chickasaw ES ",1059,1059,830,0.78,120,950,0.81]
[null,"Citrus ES",905,905,1015,1.12,-5,1010,1.12]
[null,"Clarcona ES ",905,905,739,0.82,39,778,0.82]
[null,"Clay Springs ES ",941,941,764,0.81,18,782,0.82]
[null,"Columbia ES ",951,951,854,0.9,84,938,0.91]
[null,"Conway ES ",1007,1007,747,0.74,46,793,0.75," "]
[null,"Cypress Park ES ",454,454,356,0.78,40,396,0.8]
[null,"Cypress Springs ES ",1199,1199,807,0.67,95,902,0.7]
[null,"Deerwood ES ",851,851,621,0.73,9,630,0.73]
[null,"Dillard St. ES ",747,747,718,0.96,117,835,0.97]
[null,"Dommerich ES ",890,890,738,0.83,51,789,0.84]
[null,"Dover Shores ES ",1066,1066,759,0.71,61,820,0.73]
[null,"Dr. Phillips ES ",992,992,727,0.73,-48,679,0.72]
[null,"Dream Lake ES ",1147,1147,714,0.62,27,741,0.63]
[null,"Durrance ES ",794,794,456,0.57,-72,384,0.53]
[null,"Eccleston ES",792,792,486,0.61,7,493,0.62]
[null,"Endeavor ES",905,905,685,0.76,345,1030,0.82]
[null,"Engelwood ES",1039,1039,622,0.6,-60,562,0.57]
[null,"Fern Creek ES",792,792,392,0.49,49,441,0.52]
[null,"Frangus ES",1099,1099,567,0.52,127,694,0.57]
[null,"Grand Avenue ES",862,862,449,0.52,34,483,0.54]
[null,"Hiawassee ES",1044,1044,804,0.77,246,1050,0.81]
[null,"Hidden Oaks ES",969,969,713,0.74,-36,677,0.73]
[null,"Hillcrest ES",741,741,419,0.57,-25,394,0.55]
[null,"Hungerford ES",1211,1211,289,0.24,76,365,0.28]
[null,"Hunters Creek ES",1383,1383,945,0.68,521,1466,0.77]
[null,"Ivey Lane ES",779,779,508,0.65,-19,489,0.64]
[null,"John Young ES",1135,1135,933,0.82,56,989,0.83]
[null,"Kaley ES",602,602,317,0.53,-28,289,0.5]
[null,"Killarney ES",968,968,725,0.75,3,728,0.75," "]
[null,"Lake Como ES",640,640,311,0.49,-22,289,0.47]
[null,"Lake Gem ES",817,817,713,0.87,60,773,0.88]
[null,"Lake George ES",864,864,757,0.88,-40,717,0.87]
[null,"Lake Silver ES",987,987,786,0.8,-11,775,0.79]
[null,"Lake Sybelia ES",744,744,665,0.89,10,675,0.9]
[null,"Lake Weston ES",844,844,781,0.93,12,793,0.93]
[null,"Lake Whitney ES",966,966,1042,1.08,95,1137,1.07]
[null,"Lakemont ES",1009,1009,886,0.88,-22,864,0.88]
[null,"Lakeville ES",801,801,930,1.16,-26,904,1.17]
[null,"Lancaster ES",1534,1534,796,0.52,-7,789,0.52]
[null,"Lawton Chiles ES",903,903,1082,1.2,-168,914,1.24]
[null,"Little River ES",1015,1015,896,0.88,63,959,0.89]
[null,"Lockhart ES",895,895,598,0.67,14,612,0.67]
[null,"Lovell ES",836,836,705,0.84,103,808,0.86]
[null,"Maxey ES",584,584,192,0.33,61,253,0.39]
[null,"McCoy ES",1331,1331,849,0.64,-60,789,0.62]
[null,"Meadow Woods ES",1404,1404,600,0.43,356,956,0.54]
[null,"Metrowest ES",2170,2170,1413,0.65,105,1518,0.67," "]
[null,"Northlake Park ES",704,704,482,0.68,87,569,0.72," "]
[null,"Oak Hill ES",756,756,693,0.92,-32,661,0.91," "]
[null,"Oakshire ES",894,894,707,0.79,216,923,0.83]
[null,"Ocoee ES",890,890,595,0.67,239,834,0.74]
[null,"Orange Center ES",1017,1017,592,0.58,109,701,0.62]
[null,"Orlo Vista ES",903,903,691,0.77,-51,640,0.75," "]
[null,"Palm Lake ES",1161,1161,847,0.73,-47,800,0.72]
[null,"Palmetto ES",2098,2098,1287,0.61,-46,1241,0.6]
[null,"Pershing ES",906,906,615,0.68,45,660,0.69]
[null,"Pinar ES",863,863,849,0.98,-25,824,0.98]
[null,"Pine Castle ES",629,629,492,0.78,-39,453,0.77]
[null,"Pine Hills ES",2101,2101,909,0.43,22,931,0.44]
[null,"Pineloch ES",934,934,594,0.64,-39,555,0.62]
[null,"Pinewood ES",864,864,923,1.07,11,934,1.07]
[null,"Princeton ES",438,438,427,0.97,43,470,0.98]
[null,"Ray, Mollie ES",1253,1253,720,0.57,-6,714,0.57]
[null,"Richmond Hgts ES",864,864,534,0.62,8,542,0.62]
[null,"Ridgewood Park ES",1205,1205,865,0.72,15,880,0.72]
[null,"Riverdale ES",801,801,873,1.09,80,953,1.08]
[null,"Riverside ES",1027,1027,767,0.75,-47,720,0.73]
[null,"Rock Lake ES",784,784,425,0.54,-36,389,0.52]
[null,"Rock Springs ES",1071,1071,839,0.78,50,889,0.79]
[null,"Rolling Hills ES",1510,1510,709,0.47,34,743,0.48]
[null,"Rosemont ES",983,983,951,0.97,-18,933,0.97]
[null,"Sadler ES",1124,1124,837,0.74,135,972,0.77]
[null,"Shenandoah ES",902,902,651,0.72,58,709,0.74]
[null,"Shingle Creek ES",1091,1091,815,0.75,96,911,0.77]
[null,"Southwood ES",872,872,929,1.07,218,1147,1.05]
[null,"Spring Lake ES",1209,1209,604,0.5,106,710,0.54]
[null,"Sunrise ES",900,900,1390,1.54,514,1904,1.35]
[null,"Tangelo Park ES",660,660,404,0.61,136,540,0.68]
[null,"Tildenville ES",1043,1043,799,0.77,32,831,0.77]
[null,"Union Park ES",1616,1616,755,0.47,4,759,0.47]
[null,"Ventura ES",1606,1606,998,0.62,-52,946,0.61]
[null,"Washington Shores ES",1013,1013,523,0.52,21,544,0.53]
[null,"Waterbridge ES",1108,1108,885,0.8,37,922,0.81]
[null,"Waterford ES",1114,1114,752,0.68,57,809,0.69]
[null,"Wheatley ES",1013,1013,491,0.48,-4,487,0.48]
[null,"Windermere ES",898,898,887,0.99,5,892,0.99]
[null,"Windy Ridge ES",1294,1294,1042,0.81,117,1159,0.82]
[null,"Winegard ES",1153,1153,476,0.41,-75,401,0.37]
[null,"Zellwood ES",952,952,652,0.68,62,714,0.7]
[null,"Apopka MS",1763,1586.7,1445,0.91,270,1715,0.92]
[null,"Carver MS",1585,1426.5,1020,0.72,0,1020,0.72]
[null,"Chain of Lakes MS",1510,1359,1351,0.99,181,1532,0.99]
[null,"Conway MS",1891,1701.9,1566,0.92,19,1585,0.92]
[null,"Corner Lake MS",1622,1459.8,1204,0.82,316,1520,0.86]
[null,"Discovery MS",1847,1662.3,1752,1.05,588,2340,1.04]
[null,"Glenridge MS",1496,1346.4,1289,0.96,-11,1278,0.96]
[null,"Gotha MS",2037,1833.3,1322,0.72,158,1480,0.74]
[null,"Howard MS",1094,984.6,934,0.95,-28,906,0.95]
[null,"Hunters Creek MS",1806,1625.4,1662,1.02,228,1890,1.02]
[null,"Jackson MS",1677,1509.3,1321,0.88,104,1425,0.88," "]
[null,"Lakeview MS",1094,984.6,983,1,517,1500,1]
[null,"Lee MS",1792,1612.8,1297,0.8,142,1439,0.82]
[null,"Liberty MS",1680,1512,1496,0.99,203,1699,0.99]
[null,"Lockhart MS",1396,1256.4,1244,0.99,201,1445,0.99]
[null,"Maitland MS",1494,1344.6,1179,0.88,39,1218,0.88]
[null,"Meadow Woods MS",1660,1494,1290,0.86,85,1375,0.87]
[null,"Meadowbrook MS",1646,1481.4,1264,0.85,179,1443,0.87]
[null,"Memorial MS",1709,1538.1,927,0.6,12,939,0.61]
[null,"Ocoee MS",1425,1282.5,1246,0.97,217,1463,0.98]
[null,"Piedmont Lakes MS",1748,1573.2,1626,1.03,154,1780,1.03]
[null,"Robinswood MS",1556,1400.4,1341,0.96,157,1498,0.96]
[null,"Southwest MS",1690,1521,1205,0.79,460,1665,0.84]
[null,"Union Park MS",1844,1659.6,1352,0.81,224,1576,0.84]
[null,"Walker MS",1360,1224,987,0.81,98,1085,0.82]
[null,"Westridge MS",1484,1335.6,1268,0.95,137,1405,0.95]
[null,"Apopka HS",2552,2424.4,1921,0.79,649,2570,0.84]
[null,"Apopka 9th GC",1237,1175.15,1379,1.17,221,1600,1.15]
[null,"Boone HS",2456,2333.2,2910,1.25,294,3204,1.22]
[null,"Colonial HS",2887,2742.65,2175,0.79,1655,3830,0.87]
[null,"Colonial 9th GC",1185,1125.75,1248,1.11,-1248,0,0]
[null,"Cypress Creek HS",3610,3429.5,3833,1.12,58,3891,1.12]
[null,"Dr. Phillips HS",4577,4348.15,4330,1,981,5311,1]
[null,"Edgewater HS",2834,2692.3,3133,1.16,2071,5204,1.09]
[null,"Evans HS",2705,2569.75,1866,0.73,1119,2985,0.81]
[null,"Evans 9th GC",1128,1071.6,1527,1.42,1123,2650,1.21]
[null,"Jones HS",1818,1727.1,1332,0.77,115,1447,0.79]
[null,"Oak Ridge HS",3435,3263.25,2370,0.73,477,2847,0.76," "]
[null,"Robert Hungerford HS",873,829.3499999999999,339,0.41,791,1130,0.7]
[null,"University HS",5337,5070.15,4761,0.94,919,5680,0.95," "]
[null,"West Orange HS",3259,3096.0499999999997,2722,0.88,994,3716,0.91]
[null,"W. Orange 9th GC",1274,1210.3,1585,1.31,165,1750,1.27]
[null,"Winter Park HS",2868,2724.6,2353,0.86,-113,2240,0.86]
[null,"Winter Park 9th GC",1055,1002.25,996,0.99,54,1050,0.99]
[null,"Cherokee ",245,245,103,0.42,2,105,0.43]
[null,"Gateway",373,373,166,0.45,-2,164,0.44]
[null,"Magnolia",528,523,219,0.42,-13,206,0.4]
[null,"Silver Star",142,142,159,1.12,18,177,1.11]
["2a.","ORANGE Total",189921,183470.9,148362,0.81,20040,168402,0.83]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New ES \"H\" (934 student stations) to be located in the Town of Ocoee along Clarcona Ocoee Road to accommodate growth"]
[null,"New ES \"I\" (934 student stations) to be located east of Kirkman Road in the MetroWest area of Orange County, FL to accommodate growth"]
[null,"New ES \"J\" (934 student stations) to be loacted in the City of Orlado on a site to be identifed within the planned development on the former Naval Training Center to accommodate growth  "]
[null,"New MS \"AA\" (1510 student stations) replacement school for Glenridge MS to be located south of Glenridge Way on the old NTC property being developed by Orlando Partners"]
[null,"New MS \"BB\" (1510 student stations) Discovery Relief to be located along Avalon Road in east Orange County to accommodate growth"]
[null,"New MS \"CC\" (1510 student stations) Southwest Relief to be located o a site that has not as yet identified in the southwest sector of Orange County to accommodate growth "]
[null,"New HS \"CCC\" (3029 student stations) to be located in the vicinity of John Young and Central Florida Parkways in south Orange County, FL to accommodate growth"]
[null,"New HS \"DDD\" (3029 student stations) to be located in the Town of Ocoee near Lake Apopka in northwest Orange County, FL to accommodate growth"]
[null,"New HS \"EEE\" (3029 student stations) reconstruction of West Orange High School to replace unsatisfactory student stations and to accommodate growth",{"$nulls":6}," "]
[null,"New HS \"FFF\" (3029 student stations) reconstruction of Apopka High School to replace unsatisfactory student stations and to accommodate growth"]
[]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"Aloma ES",7,"OCPS",130,0,7,0,98]
[null,null,5,"Williams",0,0,5,0,30]
[null," ",2,"GE",48,0,2,0,6]
[null,"Apokpa 9th",40,"OCPS",1134,4,40,0,546]
[null,"Apopka ES",9,"OCPS",192,0,9,0,70]
[null,null,8,"Williams",162,0,8,0,48,"  "]
[null,null,1,"Resun",25,0,1,0,2]
[null,null,3,"GE",62,0,2,1,9," "]
[null,"Apopka High",14,"OCPS",403,0,0,14,126]
[null,null,6,"Williams",0,3,0,6,45]
[null,null,5,"GE",140,0,0,5,15]
[null,"Apopka Middle",5,"OCPS",90,0,5,0,70]
[null,null,5,"GE",105,0,1,4,2]
[null,null,5,"Williams",50,2,4,1,35]
[null,"Arbor Ridge ES",12,"Williams",0,13,0,12,70]
[null,null,1,"Resun",25,0,1,0,2]
[null,null,55,"OCPS",961,6,0,55,672]
[null,"Audubon Park ES",2,"OCPS",15,2,2,0,42]
[null,null,2,"Williams ",0,6,2,0,30]
[null,"Azalea Park ES",10,"OCPS",125,2,2,8,56]
[null,null,15,"GE",75,4,15,0,32]
[null,null,10,"Williams",150,13,0,10,70]
[null,"Bay Meadows ES",37,"OCPS",780,4,34,3,476]
[null,null,9,"GE",25,8,6,3,16]
[null,null,10,"Williams",0,11,0,10,55]
[null,"Blankner ES",10,"OCPS",185,2,0,10,140]
[null,null,2,"GE",50,0,0,2,6]
[null,null,17,"Williams ",75,13,0,17,65]
[null,"Bonneville ES",6,"OCPS",45,3,3,3,112," "]
[null,null,7,"Resun",130,0,7,0,7]
[null,null,7,"GE",130,0,7,0,21]
[null,null,27,"Williams ",341,1,1,26,90]
[null,"Boone HS",3,"OCPS",56,3,0,3,70]
[null,null,20,"Williams ",0,28,0,20,140]
[null,null,13,"GE",26,14,0,13,28]
[null,"Brookshire ES",8,"OCPS",150,2,8,0,112]
[null,null,6,"Williams ",0,5,2,4,25]
[null,null,1,"GE",0,1,0,1,2]
[null,"Carver MS",1,"OCPS ",15,0,1,0,14]
[null,null,6,"Williams ",112,16,6,0,80]
[null,"Catalina ES",12,"OCPS ",145,5,5,7,168]
[null,null,6,"GE",138,0,6,0,18]
[null,null,20,"Williams ",0,18,12,8,90]
[null,"Chain of Lakes MS",2,"Resun",30,0,2,0,4]
[null,"Cheney ES",3,"OCPS",60,2,2,1,84]
[null,null,12,"Williams ",25,11,8,4,55]
[null,null,6,"Resun",120,0,6,0,12]
[null,null,1,"GE",20,1,0,1,2]
[null,"Chicksaw ES ",8,"OCPS",95,4,8,0,168]
[null,null,17,"Williams ",90,14,0,17,70]
[null,null,7,"GE",99,2,7,0,14]
[null,"Citrus ES",10,"Resun",150,0,10,0,20]
[null,"Clarcona ES",4,"OCPS",81,0,4,0,56]
[null,null,5,"Williams ",20,4,2,3,20]
[null,"Clay Springs ES",35,"OCPS",749,5,0,35,490]
[null,null,7,"GE ",75,4,0,7,8]
[null,null,1,"Resun",25,0,1,0,2]
[null,null,6,"Williams ",0,8,0,6,40]
[null,"Colonial 9th",72,"OCPS",1168,8,0,72,728]
[null,null,4,"Williams",112,0,0,4,24]
[null,"Columbia",5,"OCPS",65,1,1,4,56]
[null,null,19,"Williams ",310,18,0,19,70]
[null,"Conway ES",8,"OCPS",190,1,8,0,112]
[null,null,16,"Williams ",0,17,11,5,85]
[null,"Conway Middle",31,"OCPS",714,5,25,6,448]
[null,null,1,"Williams ",0,1,0,1,5]
[null,"Cypress Creek HS",22,"GE",616,0,0,22,44]
[null,null,28,"Williams",588,9,0,28,150]
[null,"Cypress Park ES",4,"OCPS",70,1,4,0,56]
[null,null,5,"GE",100,0,4,1,8]
[null,null,18,"Williams",160,6,8,10,70]
[null,"Cypress Springs ES",47,"OCPS",1008,5,0,47,616]
[null,null,4,"GE",80,0,0,4,8]
[null,null,1,"Resun",25,0,1,0,2]
[null,null,2,"Williams",45,0,0,2,10]
[null,"Deerwood ES",16,"OCPS",312,1,14,2,238]
[null,null,4,"GE",0,1,0,4,2]
[null,"Dillard St. ES",4,"OCPS",55,1,0,4,56]
[null,null,2,"GE",25,2,0,2,6]
[null,null,8,"Williams",70,1,0,8,5]
[null,"Discovery MS",16,"Williams",308,0,8,8,55]
[null,null,2,"GE",56,0,0,2,6]
[null,null,20,"Resun",504,2,0,20,40]
[null,"Dommerich ES",1,"OCPS",25,0,1,0,14]
[null,null,1,"GE",0,1,0,1,2]
[null,null,17,"Williams",300,2,13,4,85]
[null,"Dover Shores ES",6,"OCPS",55,4,6,0,112]
[null,null,21,"Williams",420,1,7,14,95]
[null,"Dr. Phillips 9th",7,"GE",140,0,5,2,10]
[null,null,63,"OCPS",1168,0,63,0,945]
[null,null,11,"Williams",308,0,7,4,55]
[null,"Dr. Phillips ES",11,"OCPS",285,1,11,0,168]
[null,null,1,"Resun",25,0,1,0,2]
[null,null,12,"Williams",250,1,7,5,65]
[null,"Dr. Phillips HS",9,"Resun",252,0,0,9,2]
[null,null,2,"Williams",56,1,0,2,15]
[null,"Dream Lake ES",21,"OCPS",259,4,15,6,210]
[null,null,7,"GE",80,1,0,7,4]
[null,null,6,"Williams",100,0,6,0,60]
[null,"Durrance ES",8,"OCPS",110,1,8,0,112]
[null,null,1,"GE",10,0,0,1,2]
[null,null,3,"Williams",20,0,0,3,10]
[null,"Eccelston ES",7,"OCPS",45,5,7,0,98]
[null,null,2,"GE",10,1,1,1,4]
[null,null,1,"Williams",0,1,0,1,5]
[null,"Edgewater HS",2,"OCPS",58,0,2,0,28]
[null,null,17,"GE",420,0,6,11,12]
[null,null,9,"Williams",280,0,5,4,45]
[null,"Engelwood ES",5,"OCPS",25,4,5,0,84]
[null,null,1,"GE",25,0,1,0,3]
[null,null,15,"Williams",205,6,10,5,75]
[null,"Evans 9th",49,"OCPS",1005,8,0,49,686]
[null,"Evans HS",1,"OCPS",0,1,0,1,14]
[null,null,3,"GE",90,0,0,3,6]
[null,"Fern Creek ES",1,"OCPS",0,1,1,0,14]
[null,null,4,"Williams",65,2,4,0,25]
[null,"Frangus ES",41,"OCPS",910,5,0,41,560]
[null,"Gateway School",5,"OCPS",75,1,5,0,98]
[null,null,11,"Williams",133,0,5,6,45]
[null,"Glenridge MS",2,"OCPS",60,0,0,2,28]
[null,null,2,"GE",60,0,0,2,4]
[null,"Gotha MS",9,"Williams",245,1,9,0,140]
[null,"Grand Ave ES",12,"OCPS ",205,2,11,1,154]
[null,null,15,"Williams",185,5,9,6,75]
[null,"Hanging Moss",7,"OCPS",0,6,6,1,84]
[null,null,3,"Williams",0,3,3,0,15]
[null,"Hiawassee ES",5,"OCPS",50,2,5,0,70]
[null,null,2,"GE",0,1,0,2,2]
[null,null,21,"Williams",425,0,17,4,115]
[null,"Hidden Oaks ES",29,"OCPS",593,4,29,0,406]
[null,null,2,"GE",35,0,0,2,4]
[null,null,17,"Williams",290,3,8,9,90]
[null,"Hillcrest ES",2,"GE",45,0,0,2,4]
[null,null,1,"Williams",25,1,0,1,70]
[null,"Howard MS",2,"Resun",60,0,0,2,15]
[null,"Hungerford Prep",4,"OCPS",0,1,1,3,14]
[null,null,1,"Williams",28,0,1,0,6]
[null,"Hungerford ES",1,"Williams",0,1,1,0,6]
[null,null,1,"GE",0,1,1,0,3]
[null,null,2,"Resun",0,2,2,0,4]
[null,"Hunters Cr. MS",3,"OCPS",56,2,0,3,56]
[null,null,17,"Williams",323,5,0,17,95]
[null,"Hunters Creek ES",48,"OCPS",445,7,0,48,672]
[null,null,8,"GE",140,0,0,8,22]
[null,null,4,"Williams",80,2,0,4,40]
[null,"Ivey Lane ES",8,"OCPS",170,3,8,0,126]
[null,null,5,"GE",125,0,0,5,2]
[null,null,4,"Williams",60,1,2,2,20]
[null,"Jackson MS",13,"OCPS",344,0,13,0,182]
[null,null,19,"Williams",445,2,10,9,90]
[null,null,1,"Resun",28,0,1,0,2]
[null,"John Young ES",43,"OCPS",975,4,0,43,602]
[null,null,9,"GE",135,1,0,9,6]
[null,null,2,"Williams",45,0,0,2,10]
[null,"Jones HS",1,"OCPS",30,1,0,1,84]
[null,null,3,"Williams",85,3,0,3,55]
[null,"Kaley ES",1,"OCPS",0,2,1,0,28]
[null,null,8,"Williams",124,2,8,0,50]
[null,"Killarney ES",3,"OCPS",15,2,3,0,42]
[null,null,9,"Williams",48,4,6,3,40]
[null,null,2,"GE",45,0,2,0,6]
[null,"Lake Como ES",2,"OCPS",45,2,2,0,70]
[null,"Lake Silver ES",4,"OCPS",70,0,4,0,56]
[null,null,4,"Wiliams",44,1,2,2,20]
[null,null,1,"GE",20,0,1,0,3]
[null,"Lake Sybelia ES",3,"OCPS",0,3,3,0,42]
[null,null,6,"GE",0,1,1,5,2]
[null,null,5,"Williams",40,3,3,2,15]
[null,"Lake Weston",9,"OCPS",90,3,3,6,42]
[null,null,7,"GE",68,0,3,4,6]
[null,null,3,"Williams",0,8,3,0,55]
[null,"Lake Whitney ES",10,"GE",150,6,0,10,28]
[null,"Lakemont  ES",8,"OCPS",120,2,8,0,112]
[null,null,1,"GE",25,0,1,0,6]
[null,null,8,"Williams",134,0,3,5,35]
[null,"Lakeview MS",3,"OCPS",90,0,0,3,42]
[null,null,3,"GE",56,1,0,3,9]
[null,null,3,"Resun",45,1,0,3,6]
[null,"Lancaster ES",8,"OCPS ",45,4,5,3,70]
[null,null,19,"Williams",140,13,19,0,125]
[null,null,2,"GE",40,0,2,0,6]
[null,null,5,"Resun",105,0,5,0,10]
[null,"Lawton Chiles ES",12,"Resun",276,0,0,12,24]
[null,null,4,"OCPS",0,0,0,4,60]
[null,"Lee MS",3,"OCPS",75,1,0,3,56]
[null,null,5,"GE",50,2,2,3,4]
[null,null,12,"Williams",270,2,8,4,60]
[null,null,4,"Resun",112,0,4,8,8]
[null,"Liberty MS",5,"OCPS",150,0,0,5,70]
[null,null,10,"Williams",295,1,0,10,55]
[null,"Little River ES",36,"OCPS",553,8,35,1,490]
[null,null,10,"Williams",180,1,0,10,60]
[null,null,13,"GE",195,9,9,4,39]
[null,null,1,"Resun",20,1,1,0,2]
[null,"Lockhart ES",4,"OCPS",45,2,3,1,42]
[null,null,8,"Williams",140,1,7,1,45]
[null,null,1,"GE",25,0,1,0,3]
[null,"Lockhart Middle",6,"OCPS",120,0,6,0,84]
[null,null,10,"Williams",250,1,6,4,50]
[null,"Lovell ES",4,"OCPS",0,3,4,0,56]
[null,null,14,"Williams",148,1,8,6,55]
[null,null,3,"Resun",60,0,3,0,6]
[null,"Magnolia Special",5,"OCPS",0,5,0,5,70]
[null,"Maitland Middle",3,"OCPS",45,0,0,3,42]
[null,null,8,"Williams",135,0,0,8,40]
[null,null,1,"GE",28,0,1,0,3]
[null,"Maxey ES ",6,"OCPS",20,5,6,0,84]
[null,null,6,"Williams",35,2,1,5,15]
[null,null,2,"Resun",40,0,2,0,4]
[null,"McCoy ES",5,"OCPS",40,2,2,3,28]
[null,null,18,"Williams",295,2,12,6,80]
[null,null,2,"GE",50,0,2,0,6]
[null,null,6,"Resun",135,0,6,0,12]
[null,"Meadow Woods ES",47,"OCPS",840,9,47,0,658]
[null,null,1,"Resun",25,0,1,0,2]
[null,"Meadowbrook Middle",5,"Williams",140,0,5,0,95]
[null,null,7,"GE",180,0,7,0,21]
[null,null,1,"Resun",28,0,1,0,2]
[null,"Memorial Middle",5,"OCPS",120,1,5,0,70]
[null,null,6,"Williams",110,3,6,0,55]
[null,"Metrowest ES",41,"OCPS",560,9,0,41,504]
[null,null,2,"Williams",50,0,0,2,10]
[null,"Mid Florida Tech",13,"OCPS",44,2,13,0,182]
[null,null,11,"Williams",440,2,11,0,75]
[null,null,1,"GE",30,0,1,0,3]
[null,"Mollie Ray ES",13,"OCPS",125,5,12,1,168]
[null,null,4,"GE",100,0,2,2,8]
[null,null,16,"Williams",240,6,0,16,90]
[null,null,3,"Resun",45,1,3,0,6]
[null,"Oak Hill ES",5,"OCPS",15,4,5,0,70]
[null,null,4,"Williams",15,2,1,3,15]
[null,null,3,"GE",45,1,3,0,9]
[null,null,2,"Resun",40,0,2,0,4]
[null,"Oakridge High",29,"OCPS",720,5,23,6,406]
[null,"Ocoee ES",4,"OCPS",95,1,5,-1,70]
[null,null,9,"GE",100,0,5,4,10]
[null,null,7,"Williams",155,3,6,1,50]
[null,"Ocoee Middle",8,"OCPS",225,0,0,8,112]
[null,"Orange Center ES",12,"OCPS ",150,4,12,0,168]
[null,null,10,"Williams",45,7,5,5,50]
[null,null,7,"GE",60,4,7,0,21]
[null,"Orlo Vista ES",2,"OCPS",25,1,2,0,28]
[null,null,10,"GE",85,2,6,4,12]
[null,null,21,"Williams",300,4,12,9,85]
[null,"Palm Lake ES ",37,"OCPS",605,8,8,29,518]
[null,null,2,"GE",40,0,0,2,4]
[null,null,14,"Williams",225,2,0,14,75]
[null,"Palmetto ES",1,"OCPS",165,3,0,1,140]
[null,"Pershing ES",2,"OCPS",0,2,2,0,28]
[null,null,3,"GE",30,1,3,0,6]
[null,null,9,"Williams",100,5,7,2,50]
[null,"Piedmont Lakes MS",14,"GE",210,6,7,7,14]
[null,null,5,"Williams",60,1,2,3,70]
[null,null,11,"Resun",165,3,11,0,22]
[null,"Pinar ES",7,"OCPS",85,3,0,7,112]
[null,null,9,"Williams",175,0,0,9,45]
[null,null,2,"Resun",45,0,0,2,4]
[null,"Pine Castle ES",5,"OCPS",40,3,4,1,70]
[null,null,1,"GE",25,0,1,0,3]
[null,"Pine Hills ES",1,"OCPS",15,4,5,-4,70]
[null,null,29,"Williams",465,14,5,24,185]
[null,null,1,"GE",20,0,1,0,3]
[null,"Pineloch ES",5,"OCPS",25,2,3,2,42]
[null,null,3,"GE",40,1,3,0,6]
[null,null,15,"Williams",105,7,9,6,65]
[null,null,3,"Resun",70,0,3,0,6]
[null,"Pinewood ES",4,"Resun",45,3,4,0,8]
[null,null,7,"GE",145,6,7,0,21]
[null,"Princeton ES",5,"OCPS",45,2,5,0,80]
[null,null,6,"GE",60,3,6,0,18]
[null,"Richmond Heights ES",12,"OCPS",245,2,0,12,168]
[null,null,5,"GE",25,2,3,2,15]
[null,null,11,"Williams",90,4,0,11,66]
[null,null,2,"Resun",40,2,1,1,4]
[null,"Ridgewood Park ES",10,"OCPS",150,4,10,0,150]
[null,null,20,"Williams",375,4,12,8,115]
[null,null,1,"GE",20,1,1,0,3]
[null,null,1,"Resun",20,1,1,0,2]
[null,"Riverdale ES",4,"GE",45,2,4,0,12]
[null,null,1,"Resun",20,1,1,0,2]
[null,"Riverside ES",4,"OCPS",25,4,4,0,84]
[null,null,17,"Williams",400,0,17,0,105]
[null,null,1,"GE",25,0,1,0,3]
[null,null,2,"Resun",50,0,2,0,2]
[null,"Robinswood MS",1,"OCPS",30,0,1,0,14]
[null,null,10,"Williams",223,0,8,2,35]
[null,null,1,"GE",28,0,1,0,3]
[null,"Rock Lake ES",5,"OCPS",15,5,6,-1,84]
[null,null,12,"Williams",125,5,8,4,60]
[null,"Rock Springs ES",42,"OCPS",780,6,8,34,588]
[null,null,8,"GE",160,0,8,0,16]
[null,null,6,"Williams",115,0,0,6,30]
[null,"Rolling Hills ES",3,"GE",100,0,4,-1,8]
[null,"Rosemont ES",13,"GE",205,2,13,0,39]
[null,null,3,"Williams",45,1,3,0,18]
[null,"Sadler ES",4,"OCPS",65,1,4,0,56]
[null,null,4,"GE",0,4,4,0,8]
[null,null,24,"Williams",320,8,16,8,110]
[null,"Shenandoah ES",11,"OCPS",270,0,0,11,154]
[null,null,2,"Williams",15,1,0,2,10]
[null,"Shingle Creek ES",44,"OCPS",675,7,34,10,546]
[null,null,3,"GE",35,1,3,0,6]
[null,null,7,"Williams",165,0,0,7,25]
[null,"Silver Star Center",1,"OCPS",0,1,8,-7,14]
[null,null,3,"Resun",35,0,0,3,6]
[null,null,5,"GE",75,0,0,5,15]
[null,null,2,"Williams",40,0,0,2,12]
[null,"Southwest MS",2,"Williams",60,0,1,1,10]
[null,"Southwood ES",7,"GE",120,1,0,7,21]
[null,null,12,"Resun",200,2,0,12,24]
[null,"Spring Lake ES",4,"OCPS",45,2,3,1,42]
[null,null,2,"GE",40,0,2,0,4]
[null,null,15,"Williams",365,0,10,5,110]
[null,"Sunrise ES",18,"GE",55,2,0,18,10]
[null,null,25,"Resun",585,3,null,25,50]
[null,"Tampa Ave ",1,"GE",0,1,0,1,2]
[null,"Tangelo Park ES",1,"OCPS",0,1,1,0,14]
[null,null,8,"Williams",65,5,6,2,30]
[null,null,1,"GE",25,0,1,0,3]
[null,"Tildenville ES",10,"OCPS",120,6,2,8,168]
[null,null,6,"GE",15,2,3,3,6]
[null,null,16,"Williams",150,8,0,16,70]
[null,"Union Park MS",2,"OCPS ",15,0,1,1,14]
[null,null,21,"Williams",540,1,16,5,105]
[null,"University 9th Grade Ctr.",54,"OCPS",1470,5,40,14,756]
[null,null,16,"Williams",480,0,0,16,75]
[null,"Unveristy High",17,"OCPS",450,2,10,7,238]
[null,null,17,"Williams",450,2,0,17,85]
[null,"Ventura ES",49,"OCPS",790,12,0,49,700]
[null,null,14,"Williams",240,1,0,14,90]
[null,"Walker MS",3,"OCPS",75,1,4,-1,56]
[null,null,2,"GE",15,0,1,1,2]
[null,null,6,"Williams",150,2,5,1,40]
[null,"Washington Shores ES",3,"OCPS",0,3,3,0,42]
[null,null,3,"GE",15,2,3,0,6]
[null,null,6,"Williams",0,9,6,0,45]
[null,null,4,"Resun",45,2,4,0,8]
[null,"Waterbridge ES",39,"OCPS",575,13,40,-1,560]
[null,null,4,"GE",65,0,4,0,8]
[null,null,10,"Williams",180,2,0,10,55]
[null,"Waterford ES",18,"OCPS",210,13,8,10,270]
[null,"West Orange 9th",40,"OCPS",1020,4,40,0,560]
[null,"West Orange High",16,"OCPS",585,1,20,-4,294]
[null,null,10,"GE",85,0,0,10,6]
[null,null,12,"Williams",200,5,0,12,60]
[null,"Westridge MS",10,"GE",230,2,10,0,30]
[null,"Westside VO TECH",13,"OCPS",132,7,13,0,182]
[null,null,10,"Williams",150,3,6,4,30]
[null,null,6,"GE",170,0,6,0,18]
[null,"Windermere ES",12,"OCPS",80,5,3,9,126]
[null,null,4,"GE",40,1,0,4,6]
[null,null,7,"Williams",115,1,0,7,35]
[null,"Windy Ridge ES",43,"OCPS",625,11,42,1,588]
[null,null,17,"Williams",105,2,8,9,40]
[null,null,12,"GE",15,0,1,11,2]
[null,"Winegard ES",3,"OCPS",20,2,3,0,42]
[null,null,6,"Williams",120,8,12,-6,75]
[null,"Winter Park Adult",22,"OCPS ",342,5,0,22,546]
[null,null,4,"Williams",0,4,0,4,30]
[null,null,22,"Resun",330,4,0,22,44]
[null,"Winter Park High",1,"OCPS ",0,1,0,1,14]
[null,null,3,"Williams",30,2,0,3,10]
[null,null,5,"GE",85,2,0,5,15]
[null,"Zellwood ES",5,"OCPS",100,1,5,0,75," "]
[null,null,1,"Resun",25,0,1,0,2]
[null,null,8,"Williams",120,3,5,3,48]
["2c1.","ORANGE Total",3530,null,58404,948,1733,1805,"Avg Age 8.89"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[" ","Rolling hills ES",24,24,{"$nulls":4},24]
[" ","Union Park ES",16,16,{"$nulls":4},16]
[" ","Hungerford ES",12,12,{"$nulls":4},12]
[" ","Pine Hills ES",32,32," ",null,null,null,32]
[null,"Waterford ES",40,40,{"$nulls":4},40]
[" ","Azalea Park ES",8,8,{"$nulls":4},8]
[" ","Chickasaw ES",8,8,null,null," ",null,8]
[" ","Mollie Ray ES",8,8,{"$nulls":4},8]
[null,"Lockhart ES",12,12,{"$nulls":4},12]
[" ","Dover Shores ES",8,8,{"$nulls":4},8]
[null,"Hillcrest ES",24,24,{"$nulls":4},24]
[null,"Richmond Heights ES",24,24,null," ",null,null,24]
[" ","Ridgewood Park ES",8,8," ",null," ",null,8]
[null,"Pinar ES",16,16,{"$nulls":4},16]
[null,"Columbia ES",8,8,{"$nulls":4},8]
[" ","Tildenville ES",24,24," "," "," ",null,24]
[null,"Ventura ES",8,8," "," ",null,null,8]
[null,"Cypress Park ES",16,16,{"$nulls":4},16]
[null,"Dream Lake ES",16,16,{"$nulls":4},16]
[null,"Orlo Vista ES",16,16,{"$nulls":4},16]
[null,"Boone HS",55,null,null,55,null,null,55]
[null,"Blankner ES",26,null,26,null,null,null,26]
[null,"Jones HS",16,null,16,null,null,null,16]
[null,"Lakeview MS",3,null,3,null,null,null,3]
[null,"Glenridge MS",4,null,4,null,null,null,4]
[null,"West Orange HS",39,{"$nulls":4},39,39]
[null,"Winter Park HS",8,null,null,null,8,null,8]
[" ","Edgewater HS",12,null,12,null,null,null,12]
[null,"Colonial HS",44," ",28,16,null,null,44]
["2c2.","ORANGE Total",535,328,89,71,8,39,535]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05","FISH Stu. Sta.","# Years Leased "]
[null,"Aloma ES",5,"Williams ",0,25,3,0,30]
[null,"Apopka ES",3,"GE",62,6,3,62,21]
[null,null,8,"Williams",162,40,4,81,36]
[null,"Apopka High",9,"Williams",0,45,5,0,50]
[null,"Apopka Middle",1,"GE",15,2,1,15,7]
[null,null,7,"Williams",75,35,4,0,40]
[null,"Arbor Ridge ES",14,"Williams",6,70,0,0,0]
[null,"Audubon Park",6,"Williams ",0,30,4,0,40]
[null,"Azalea Park",16,"GE",50,32,16,50,112]
[null,null,14,"Williams",250,70,0,0,0]
[null,"Bay Meadows",8,"GE",0,16,6,0,56]
[null,null,11,"Williams",0,55,0,0,0]
[null,"Blankner ES",13,"Williams ",0,65,0,0,0]
[null,"Bonneville ES",7,"Resun",130,7,7,130,42]
[null,null,21,"Williams ",341,90,1,25,10]
[null,"Boone HS",28,"Williams ",0,140,0,0,0]
[null,null,14,"GE",26,28,0,0,0]
[null,"Brookshire ES",5,"Williams ",0,25,2,0,20]
[null,null,1,"GE",0,2,0,0,0]
[null,"Carver MS",16,"Williams ",0,80,12,0,120]
[null,"Catalina ES",18,"Williams ",0,90,12,0,120]
[null,"Cheney ES",11,"Williams ",0,55,8,0,80]
[null,null,1,"GE",0,2,0,0,0]
[null,"Chicksaw ES ",14,"Williams ",0,70,0,0,0]
[null,null,7,"GE",99,14,7,99,49]
[null,"Clarcona ES",4,"Williams ",0,20,2,0,20]
[null,"Clay Springs ES",4,"GE ",0,8,0,0,0]
[null,null,8,"Williams ",0,40,0,0,0]
[null,"Colonial HS",5,"Williams ",0,25,0,0,0]
[null,"Columbia",18,"Williams ",310,70,0,0,0]
[null,"Conway ES",17,"Williams ",0,85,11,0,110]
[null,"Conway Middle",1,"Williams ",0,5,0,0,0]
[null,"Cypress Creek HS",22,"GE",616,44,0,0,0]
[null,null,30,"Williams",588,150,0,0,0]
[null,"Cypress Park ES",4,"GE",100,8,4,100,28]
[null,null,14,"Williams",160,70,8,120,80]
[null,"Cypress Springs ES",4,"GE",80,8,0,0,0]
[null,null,2,"Williams",45,10,0,0,0]
[null,"Deerwood ES",1,"GE",0,2,0,0,0]
[null,"Dillard St. ES",3,"GE",25,6,0,0,0]
[null,null,3,"Resun",50,3,0,0,0]
[null,null,1,"Williams",0,5,0,0,0]
[null,"Discovery MS",11,"Williams",308,55,8,224,80]
[null,"Dommerich ES",1,"GE",0,2,0,0,0]
[null,null,17,"Williams",300,85,13,230,130]
[null,"Dover Shores ES",19,"Williams",420,95,7,154,70]
[null,"Dr. Phillips 9th",5,"GE",140,10,5,140,35]
[null,null,11,"Williams",308,55,7,196,70]
[null,"Dr. Phillips ES",13,"Williams",250,65,7,135,70]
[null,"Dr. Phillips HS",3,"Williams",70,15,0,0,0]
[null,"Dream Lake ES",2,"GE",25,4,0,0,0]
[null,null,12,"Williams",165,60,7,96,70]
[null,"Durrance ES",1,"GE",10,2,0,0,0]
[null,null,2,"Williams",20,10,0,0,0]
[null,"Eccelston ES",2,"GE",10,4,1,0,0]
[null,null,1,"Williams",0,5,0,0,0]
[null,"Edgewater HS",6,"GE",210,12,6,210,42]
[null,null,9,"Williams",280,45,5,155,50]
[null,"Engelwood ES",15,"Williams",205,75,10,138,100]
[null,"Evans HS",3,"GE",90,6,0,0,0]
[null,"Fern Creek ES",5,"Williams",45,25,4,25,40]
[null,"Frangus ES",7,"Williams",150,35,0,0,0]
[null,null,5,"GE",65,10,0,0,0]
[null,"Gateway School",9,"Williams",133,45,5,74,50]
[null,"Glenridge MS",2,"GE",60,4,0,0,0]
[null,"Gotha MS",28,"Williams",696,140,21,522,210]
[null,"Grand Ave ES",15,"Williams",185,75,9,110,90]
[null,"Hiawassee ES",1,"GE",0,2,0,0,0]
[null,null,23,"Williams",425,115,17,314,170]
[null,"Hidden Oaks ES",2,"GE",35,4,0,0,0]
[null,null,18,"Williams",290,90,8,128,80]
[null,"Hillcrest ES",2,"GE",45,4,0,0,0]
[null,null,14,"Williams",275,70,0,0,0]
[null,"Howard MS",3,"Williams",105,15,0,0,0]
[null,"Hunters Cr. MS",19,"Williams",379,95,0,0,0]
[null,"Hunters Creek ES",11,"GE",250,22,0,0,0]
[null,null,8,"Williams",140,40,0,0,0]
[null,"Ivey Lane ES",1,"GE",25,2,0,0,0]
[null,null,4,"Williams",60,20,2,30,20]
[null,"Jackson MS",18,"Williams",445,90,10,247,100]
[null,"John Young ES",3,"GE",45,6,0,0,0]
[null,null,2,"Williams",45,10,0,0,0]
[null,"Jones HS",11,"Williams",225,55,0,0,0]
[null,"Kaley ES",10,"Williams",144,50,8,115,80]
[null,"Killarney ES",8,"Williams",48,40,6,0,60]
[null,"Lake Silver ES",4,"Wiliams",44,20,2,0,20]
[null,"Lake Sybelia ES",1,"GE",0,2,1,0,7]
[null,null,5,"Williams",40,15,3,25,30]
[null,"Lake Weston",3,"GE",32,6,3,32,42]
[null,null,11,"Williams",36,55,7,36,70]
[null,"Lake Whitney ES",14,"GE",180,28,0,0,0]
[null,"Lakemont  ES",3,"GE",70,6,3,70,21]
[null,null,7,"Williams",134,35,3,57,30]
[null,"Lancaster ES",25,"Williams",240,125,19,182,190]
[null,"Lee MS",2,"GE",0,4,2,0,0]
[null,null,12,"Williams",270,60,8,180,80]
[null,"Liberty MS",11,"Williams",295,55,0,0,0]
[null,"Little River ES",12,"Williams",200,60,0,0,0]
[null,"Lockhart ES",9,"Williams",165,45,7,128,70]
[null,"Lockhart Middle",10,"Williams",250,50,6,150,60]
[null,"Lovell ES",11,"Williams",148,55,8,108,80]
[null,"Maitland Middle",8,"Williams",135,40,0,0,0]
[null,"Maxey ES ",3,"Williams",20,15,1,0,10]
[null,"McCoy ES",16,"Williams",295,80,12,221,120]
[null,"Meadow Woods ES",3,"GE",20,6,0,0,0]
[null,null,18,"Williams",350,90,0,0,0]
[null,"Meadowbrook Middle",19,"Williams",435,95,15,343,150]
[null,"Memorial Middle",3,"GE",60,6,3,60,21]
[null,null,11,"Williams",210,55,7,134,70]
[null,"Metrowest ES",2,"Williams",50,10,0,0,0]
[null,"Mid Florida Tech",17,"Williams",440,75,11,285,110]
[null,"Mollie Ray ES",4,"GE",100,8,2,50,14]
[null,null,18,"Williams",240,90,0,0,0]
[null,"Oak Hill ES",3,"Williams",15,15,1,15,10]
[null,"Ocoee ES",5,"GE",100,10,5,100,35]
[null,null,10,"Williams",155,50,6,93,60]
[null,"Ocoee Middle",6,"Williams",120,30,0,0,0]
[null,"Orange Center ES",10,"Williams",45,50,5,45,50]
[null,"Orlo Vista ES",6,"GE",85,12,6,85,42]
[null,null,17,"Williams",300,85,12,212,120]
[null,"Palm Lake ES ",2,"GE",40,4,0,0,0]
[null,null,13,"Williams",225,75,0,0,0]
[null,"Palmetto ES",22,"GE",425,110,0,0,0]
[null,null,26,"Williams",560,130,0,0,0]
[null,"Pershing ES",3,"GE",30,6,3,30,21]
[null,null,10,"Williams",100,50,7,100,70]
[null,"Piedmont Lakes MS",7,"GE",210,14,7,210,49]
[null,null,5,"Williams",60,70,2,0,20]
[null,"Pinar ES",1,"GE",0,2,0,0,0]
[null,null,9,"Williams",175,45,0,0,0]
[null,"Pine Hills ES",37,"Williams",465,185,5,62,50]
[null,"Pineloch ES",3,"GE",40,6,3,40,21]
[null,null,13,"Williams",105,65,9,73,90]
[null,"Richmond Heights ES",3,"GE",25,6,3,25,21]
[null,null,8,"Williams",90,40,0,0,0]
[null,"Ridgewood Park ES",23,"Williams",375,115,0,0,0]
[null,"Riverside ES",21,"Williams",475,105,15,339,150]
[null,"Robinswood MS",7,"Williams",195,35,5,139,50]
[null,"Rock Lake ES",12,"Williams",125,60,8,83,80]
[null,"Rock Springs ES",8,"GE",160,16,8,160,56]
[null,null,6,"Williams",115,30,0,0]
[null,"Rolling Hills ES ",4,"GE",100,8,4,100,28]
[null,null,19,"Williams",290,95,0,0,0]
[null,"Rosemont ES",8,"GE",145,16,6,108,42]
[null,"Sadler ES",4,"GE",0,8,4,0,29]
[null,null,22,"Williams",320,110,16,233,160]
[null,"Shenandoah ES",2,"Williams",15,10,0,0,0]
[null,"Shingle Creek ES",3,"GE",35,6,3,35,21]
[null,null,5,"Williams",165,25,0,0,0]
[null,"Southwest MS",2,"Williams",60,10,1,30,10]
[null,"Southwood ES",3,"GE",60,6,2,40,14]
[null,"Spring Lake ES",2,"GE",40,4,2,40,14]
[null,null,22,"Williams",490,110,10,223,100]
[null,"Sunrise ES",5,"GE",55,10,0,0,0]
[null,"Tangelo Park ES",6,"Williams",20,30,4,20,40]
[null,"Tildenville ES",3,"GE",15,6,3,15,21]
[null,null,14,"Williams",150,70,0,0,0]
[null,"Union Park ES",14,"Williams",225,70,0,0,0]
[null,"Union Park MS",21,"Williams",540,105,16,411,160]
[null,"University 9th Grade Ctr.",15,"Williams",480,75,0,0,0]
[null,"Unveristy High",17,"Williams",450,85,0,0,0]
[null,"Ventura ES",18,"Williams",240,90,0,0,0]
[null,"Walker MS",1,"GE",15,2,1,15,7]
[null,null,8,"Williams",150,40,5,94,50]
[null,"Washington Shores ES",3,"GE",15,6,3,15,21]
[null,null,9,"Williams",0,45,6,0,60]
[null,"Waterbridge ES",4,"GE",65,8,4,65,28]
[null,null,11,"Williams",180,55,0,0,0]
[null,"Waterford ES",9,"GE",0,18,0,0,0]
[null,null,5,"Williams",45,25,0,0,0]
[null,"West Orange High",3,"GE",85,6,0,0,0]
[null,null,12,"Williams",200,60,0,0,0]
[null,"Westside VO TECH",6,"GE",170,12,6,170,42]
[null,null,10,"Williams",150,30,6,90,60]
[null,"Windermere ES",3,"GE",40,6,0,0,0]
[null,null,7,"Williams",115,35,0,0,0]
[null,"Windy Ridge ES",8,"Williams",105,40,8,105,80]
[null,null,1,"GE",15,2,1,15,7]
[null,"Winegard ES",15,"Williams",120,75,12,96,120]
[null,"Winter Park Adult",6,"Williams",25,30,0,0,0]
[null,"Winter Park High",2,"Williams",0,10,0,0,0]
[null,"Hungerford Prep. High",4,"Williams",105,20,0,0,0]
[null,"Zellwood ES",8,"Williams",120,40,5,75,50]
["2c3.","ORANGE Total",1663,null,25205,7448,647,9792,6042]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","Projected                   for 2004-05"]
[null,"1550 East Crown Point Rd., Winter Garden, FL","TBD","Hope Charter, Inc.",2001,80,0,5,80]
[null,"Lee Road, Orlando, FL","TBD","Cyper High, Inc.",2001,105,0,3,100]
[null,"14450 Estrella Drive, Orlando, FL","TBD","Hunters Creek Charter, Inc.",2001,722,0,10,700]
[null,"TBD","TBD","KOTA, Inc.",2001,400,0,5,400]
[null,"649 W. Livingston Street, Orlando, FL 32801","TBD","Nap Ford Community School, Inc.",2001,126,0,5,126,null," "]
[null,"Conway Gardens Road, Orlando, FL  3206","TBD","Passport High Charter, Inc.",2001,63,0,5,60]
[null,"3305 S. Orange Avenue, Orlando, FL  32806","TBD","UCP, Inc.",2001,139,0,3,139]
[null,"135 N. Magnolia Avenue Orlando, FL",14,"Lake Eola Charter School, Inc.","1998-99",220,218,3,220]
[null,"1890 Conway Gardens Road, Orlando, FL",5,"Passport School., Inc","1997-98",124,124,3,140]
[null,"630 W. Princeton Street, Orlando, FL",10,"Princeton House","1998-99",63,61,3,75]
[null,"2210 S. Rio Grande Avenue, Orlando FL",6,"Rio Grande Charter School of Excellence, Inc","1999-00",112,112,1,350]
[null,"441 S. Wymore Road, Maitland, FL",10,"Summit Charter Schools, Inc","1997-98",160,160,3,200]
["2c4.","ORANGE Total",45,null,null,2314,675,49,2590]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations.",{"$nulls":6}," "]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented.",{"$nulls":4}," "]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"Aloma ES ",36,537,618,17.17,606,-4,18.94]
[null,"Apopka ES ",39,600,563,14.44,642,-8,20.71]
[null,"Arbor Ridge ES ",40,595,1058,26.45,940,0,23.5]
[null,"Audubon Park ES ",30,671,557,18.57,545,0,18.17]
[null,"Azalea Park ES ",41,645,1032,25.17,987,0,24.07]
[null,"Bay Meadows ES",31,595,988,31.87,1106,8,28.36]
[null,"Blankner ES",35,609,628,17.94,1062,-35,"N/A"]
[null,"Bonneville ES ",39,562,939,24.08,1025,0,26.28]
[null,"Brookshire ES ",24,547,543,22.63,574,0,23.92]
[null,"Catalina ES ",33,560,723,21.91,803,4,21.7]
[null,"Cheney ES ",36,580,738,20.5,716,-5,23.1]
[null,"Chickasaw ES ",30,536,830,27.67,950,4,27.94]
[null,"Clarcona ES ",47,754,739,15.72,778,-1,16.91]
[null,"Clay Springs ES ",26,595,764,29.38,782,8,23]
[null,"Columbia ES ",48,493,854,17.79,938,-4,21.32]
[null,"Conway ES ",42,511,747,17.79,793,-8,23.32]
[null,"Cypress Park ES ",11,63,356,32.36,396,2,30.46]
[null,"Cypress Springs ES ",33,637,807,24.45,902,0,27.33]
[null,"Deerwood ES ",28,612,621,22.18,630,0,22.5]
[null,"Dillard St. ES ",30,564,718,23.93,835,-3,30.93]
[null,"Dommerich ES ",34,511,738,21.71,789,-4,26.3]
[null,"Dover Shores ES ",48,627,759,15.81,820,-4,18.64]
[null,"Dr. Phillips ES ",41,441,727,17.73,679,-4,18.35]
[null,"Dream Lake ES ",29,632,714,24.62,741,0,25.55]
[null,"Durrance ES ",27,607,456,16.89,384,-8,20.21]
[null,"Eccleston ES",27,712,486,18,493,-4,21.43]
[null,"Engelwood ES",35,639,622,17.77,562,0,16.06]
[null,"Fern Creek ES",28,669,392,14,441,-6,20.05]
[null,"Frangus ES",37,597,567,15.32,694,0,18.76]
[null,"Grand Avenue ES",29,341,449,15.48,483,-4,19.32]
[null,"Hiawassee ES",57,496,804,14.11,1050,-16,25.61]
[null,"Hidden Oaks ES",22,595,713,32.41,677,4,26.04]
[null,"Hillcrest ES",33,440,419,12.7,394,-16,23.18]
[null,"Hungerford ES",15,365,289,19.27,365,0,24.33]
[null,"Hunters Creek ES",36,595,945,26.25,1466,16,28.19]
[null,"Ivey Lane ES",33,590,508,15.39,489,-1,15.28]
[null,"John Young ES",35,595,933,26.66,989,4,25.36]
[null,"Kaley ES",29,373,317,10.93,289,0,9.97]
[null,"Killarney ES",36,676,725,20.14,728,-1,20.8]
[null,"Lake Como ES",25,589,311,12.44,289,-8,17]
[null,"Lake Gem ES",36,784,713,19.81,773,-4,24.16]
[null,"Lake George ES",37,820,757,20.46,717,-4,21.73]
[null,"Lake Silver ES",42,826,786,18.71,775,-2,19.38]
[null,"Lake Sybelia ES",22,563,665,30.23,675,0,30.68]
[null,"Lake Weston ES",26,608,781,30.04,793,1,29.37]
[null,"Lake Whitney ES",34,769,1042,30.65,1137,15,23.2]
[null,"Lakemont ES",40,665,886,22.15,864,-6,25.41]
[null,"Lakeville ES",33,806,930,28.18,904,0,27.39]
[null,"Lancaster ES",44,571,796,18.09,789,-6,20.76]
[null,"Lawton Chiles ES",33,903,1082,32.79,914,0,27.7]
[null,"Little River ES",32,595,896,18.69,959,7,24.59]
[null,"Lockhart ES",45,630,598,15.67,612,-16,21.1]
[null,"Lovell ES",48,597,705,4,808,-16,25.25]
[null,"Maxey ES",18,371,192,47.17,253,-8,25.3]
[null,"McCoy ES",51,650,849,11.76,789,-20,25.45]
[null,"Meadow Woods ES",48,595,600,29.44,956,-16,29.88]
[null,"Metrowest ES",45,595,1413,31.4,1518,5,30.36]
[null,"Northlake Park ES",33,704,482,14.61,569,0,17.24]
[null,"Oak Hill ES",30,652,693,23.1,661,0,22.03]
[null,"Oakshire ES",34,894,707,20.79,923,0,27.15]
[null,"Ocoee ES",31,450,595,19.19,834,0,26.9]
[null,"Orange Center ES",27,516,592,21.93,701,-1,26.96]
[null,"Orlo Vista ES",34,421,691,20.32,640,0,18.82]
[null,"Palm Lake ES",36,637,847,23.53,800,-4,25]
[null,"Palmetto ES",40,1240,1287,32.18,1241,6,26.98]
[null,"Pershing ES",31,568,615,19.84,660,-2,22.76]
[null,"Pinar ES",37,640,849,22.95,824,-4,24.97]
[null,"Pine Castle ES",25,525,492,19.68,453,-1,18.88]
[null,"Pine Hills ES",49,1006,909,18.55,931,-4,20.69]
[null,"Pineloch ES",35,617,594,16.97,555,-1,16.32]
[null,"Pinewood ES",37,820,923,24.95,934,3,23.35]
[null,"Princeton ES",18,353,427,23.72,470,1,24.74]
[null,"Ray, Mollie ES",45,590,720,16,714,-1,16.23]
[null,"Richmond Hgts ES",31,417,534,17.23,542,-3,19.36]
[null,"Ridgewood Park ES",56,606,865,15.45,880,-3,16.6]
[null,"Riverdale ES",33,806,873,26.45,953,3,26.47]
[null,"Riverside ES",50,416,767,15.34,720,-5,16]
[null,"Rock Lake ES",25,507,425,17,389,1,14.96]
[null,"Rock Springs ES",37,595,839,22.68,889,-4,26.94]
[null,"Rolling Hills ES",35,950,709,20.26,743,-1,21.85]
[null,"Rosemont ES",36,784,951,26.42,933,5,22.76]
[null,"Sadler ES",45,467,837,18.6,972,-6,24.92]
[null,"Shenandoah ES",39,593,651,16.69,709,-1,18.66]
[null,"Shingle Creek ES",34,597,815,23.97,911,-4,30.37]
[null,"Southwood ES",36,769,929,25.81,1147,6,27.31]
[null,"Spring Lake ES",70,505,604,8.63,710,-24,15.43]
[null,"Sunrise ES",33,769,1390,42.12,1904,40,26.08]
[null,"Tangelo Park ES",24,515,404,16.83,540,0,22.5]
[null,"Tildenville ES",44,533,799,18.16,831,-8,23.08]
[null,"Union Park ES",57,714,755,13.25,759,-20,20.51]
[null,"Ventura ES",58,637,998,17.21,946,-12,20.57]
[null,"Washington Shores ES",33,717,523,15.85,544,-8,21.76]
[null,"Waterbridge ES",34,595,885,26.03,922,4,24.26]
[null,"Waterford ES",41,978,752,18.34,809,-8,24.52]
[null,"Wheatley ES",56,1180,491,8.77,487,-32,20.29]
[null,"Windermere ES",42,590,887,21.12,892,-8,26.24]
[null,"Windy Ridge ES",26,595,1042,40.08,1159,12,30.5]
[null,"Winegard ES",14,665,476,34,401,0,28.64]
[null,"Zellwood ES",31,491,652,21.03,714,-4,26.44]
[null,"Apopka MS",47,1363,1445,30.74,1715,8,31.18]
[null,"Carver MS",47,1102,1020,21.7,1020,-4,23.72]
[null,"Chain of Lakes MS",55,1359,1351,24.56,1532,4,25.97]
[null,"Conway MS",60,1139,1566,26.1,1585,8,23.31]
[null,"Corner Lake MS",54,1468,1204,22.3,1520,0,28.15]
[null,"Discovery MS",85,1344,1752,20.61,2340,-16,33.91]
[null,"Glenridge MS",54,1242,1289,23.87,1278,0,23.67]
[null,"Gotha MS",69,1207,1322,19.16,1480,-16,27.92]
[null,"Howard MS",50,940,934,18.68,906,-8,21.57]
[null,"Hunters Creek MS",77,1068,1662,21.58,1890,-12,29.08]
[null,"Jackson MS",55,977,1321,24.02,1425,0,25.91]
[null,"Lakeview MS",51,962,983,19.27,1500,4,27.27]
[null,"Lee MS",60,1182,1297,21.62,1439,-8,27.67]
[null,"Liberty MS",61,1180,1496,24.52,1699,-4,29.81]
[null,"Lockhart MS",46,918,1244,27.04,1445,-2,32.84]
[null,"Maitland MS",46,1151,1179,25.63,1218,-2,27.68]
[null,"Meadow Woods MS",56,1499,1290,23.04,1375,0,24.55]
[null,"Meadowbrook MS",50,1128,1264,25.28,1443,4,26.72]
[null,"Memorial MS",56,1039,927,16.55,939,-16,23.48]
[null,"Ocoee MS",52,984,1246,23.96,1463,0,28.13]
[null,"Piedmont Lakes MS",48,1238,1626,33.88,1780,8,31.79]
[null,"Robinswood MS",54,1197,1341,24.83,1498,-8,32.57]
[null,"Southwest MS",61,1177,1205,19.75,1665,-12,33.98]
[null,"Union Park MS",65,1186,1352,20.8,1576,-12,29.74]
[null,"Walker MS",50,995,987,19.74,1085,-12,28.55]
[null,"Westridge MS",51,1184,1268,24.86,1405,-4,29.89]
[null,"Apopka HS",95,2012,1921,20.22,2570,-12,30.96]
[null,"Apopka 9th GC",36,1024,1379,38.31,1600,8,36.36]
[null,"Boone HS",103,2068,2910,28.25,3204,4,29.94]
[null,"Colonial HS",93,2144,2175,23.39,3830,36,29.69]
[null,"Colonial 9th GC",37,962,1248,33.73,0,-37,"N/A"]
[null,"Cypress Creek HS",115,2234,3833,33.33,3891,20,28.82]
[null,"Dr. Phillips HS",165,4609,4330,26.24,5311,-4,32.99]
[null,"Edgewater HS",104,2398,3133,30.13,5204,40,36.14]
[null,"Evans HS",102,2557,1866,18.29,2985,-20,36.4]
[null,"Evans 9th GC",33,1011,1527,46.27,2650,40,36.3]
[null,"Jones HS",68,1363,1332,19.59,1447,-12,25.84]
[null,"Oak Ridge HS",122,2594,2370,19.43,2847,0,23.34]
[null,"Robert Hungerford HS",30,773,339,11.3,1130,0,37.67]
[null,"University HS",166,2070,4761,28.68,5680,-12,36.88]
[null,"West Orange HS",117,2316,2722,23.26,3716,-4,32.88]
[null,"W. Orange 9th GC",40,1024,1585,39.63,1750,8,36.46]
[null,"Winter Park HS",95,2546,2353,24.77,2240,-8,25.75]
[null,"Winter Park 9th GC",41,893,996,24.29,1050,-4,28.38]
[null,"Cherokee ",34,245,103,3.03,105,-16,5.83]
[null,"Gateway",30,373,166,5.53,164,-4,6.31]
[null,"Magnolia",49,523,219,4.47,206,-12,5.57]
[null,"Silver Star",12,142,159,13.25,177,6,9.83]
["2e.","ORANGE Total",6678,127438,146662,"District Avg 22",166362,-335,"District Avg 26"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year.",{"$nulls":5}," "]
[]
[null,"Site                              ",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR AVERAGE"]
[null,"Aloma ES ",null,124,117.8,111.6,105.39999999999999,99.2,111.6]
[null,"Apopka ES ",null,300,285,270,255,240,270]
[null,"Arbor Ridge ES ",null,919,873.05,827.0999999999999,781.1499999999999,735.2,827.0999999999998]
[null,"Audubon Park ES ",null,67,63.65,60.3,56.949999999999996,53.6,60.3]
[null,"Azalea Park ES ",null,285,285,213,213,213,241.8]
[null,"Bay Meadows ES",null,694,659.3,624.5999999999999,589.8999999999999,555.2,624.6]
[null,"Blankner ES",null,185,185,185,0,0,111]
[null,"Bonneville ES ",null,471,471,471,282,282,395.4]
[null,"Brookshire ES ",null,143,135.85,128.7,121.54999999999998,114.4,128.7]
[null,"Catalina ES ",null,138,131.1,124.19999999999999,117.29999999999998,110.4,124.2]
[null,"Cheney ES ",null,100,95,90,85,80,90]
[null,"Chickasaw ES ",null,115,115,115,115,115,115]
[null,"Clarcona ES ",null,77,73.15,69.30000000000001,65.45000000000002,61.6,69.30000000000001]
[null,"Clay Springs ES ",null,712,676.4,640.8,605.1999999999999,569.6,640.8]
[null,"Columbia ES ",null,375,375,0,0,0,150]
[null,"Conway ES ",null,181,171.95,162.89999999999998,153.84999999999997,144.8,162.89999999999995]
[null,"Cypress Park ES ",null,314,298.3,282.6,266.90000000000003,251.20000000000002,282.6]
[null,"Cypress Springs ES ",null,1076,1022.2,968.4000000000001,914.6000000000001,860.8000000000001,968.4]
[null,"Deerwood ES ",null,296,281.2,266.4,251.59999999999997,236.8,266.4]
[null,"Dillard St. ES ",null,130,0,0,0,0,26]
[null,"Dommerich ES ",null,309,293.55,278.1,262.65000000000003,247.20000000000002,278.1]
[null,"Dover Shores ES ",null,130,130,130,130,130,130]
[null,"Dr. Phillips ES ",null,508,482.6,457.20000000000005,431.80000000000007,406.40000000000003,457.2000000000001]
[null,"Dream Lake ES ",null,365,346.75,328.5,310.25,292,328.5]
[null,"Durrance ES ",null,133,126.35,119.69999999999999,113.04999999999998,106.4,119.7]
[null,"Eccleston ES",null,52,49.4,46.8,44.199999999999996,41.6,46.8]
[null,"Engelwood ES",null,219,208.05,197.10000000000002,186.15000000000003,175.20000000000002,197.10000000000005]
[null,"Fern Creek ES",null,43,40.85,38.7,36.550000000000004,34.4,38.7]
[null,"Frangus ES",null,1069,1015.55,962.0999999999999,908.6499999999999,855.2,962.1]
[null,"Grand Avenue ES",null,371,352.45,333.9,315.34999999999997,296.8,333.9]
[null,"Hiawassee ES",null,451,428.45,405.9,383.34999999999997,360.8,405.9]
[null,"Hidden Oaks ES",null,872,828.4,784.8,741.1999999999999,697.6,784.8]
[null,"Hillcrest ES",null,468,0,0,0,0,93.6]
[null,"Hungerford ES",null,0,0,0,0,0,0]
[null,"Hunters Creek ES",null,793,753.35,713.7,674.0500000000001,634.4000000000001,713.7]
[null,"Ivey Lane ES",null,242,229.9,217.8,205.70000000000002,193.60000000000002,217.8]
[null,"John Young ES",null,1012,961.4,910.8,860.1999999999999,809.6,910.8]
[null,"Kaley ES",null,137,130.15,123.30000000000001,116.45000000000002,109.60000000000001,123.3]
[null,"Killarney ES",null,60,57,54,51,48,54]
[null,"Lake Como ES",null,43,40.85,38.7,36.550000000000004,34.4,38.7]
[null,"Lake Gem ES",null,0,0,0,0,0,0]
[null,"Lake George ES",null,0,0,0,0,0,0]
[null,"Lake Silver ES",null,108,102.6,97.19999999999999,91.79999999999998,86.4,97.19999999999997]
[null,"Lake Sybelia ES",null,38,36.1,34.2,32.300000000000004,30.400000000000002,34.2]
[null,"Lake Weston ES",null,65,61.75,58.5,55.25,52,58.5]
[null,"Lake Whitney ES",null,180,180,180,0,0,108]
[null,"Lakemont ES",null,308,292.6,277.20000000000005,261.80000000000007,246.4,277.20000000000005]
[null,"Lakeville ES",null,0,0,0,0,0,0]
[null,"Lancaster ES",null,247,234.65,222.3,209.95000000000002,197.60000000000002,222.3]
[null,"Little River ES",null,715,679.25,643.5,607.75,572,643.5]
[null,"Lockhart ES",null,181,171.95,162.89999999999998,153.84999999999997,144.8,162.89999999999995]
[null,"Lovell ES",null,141,133.95,126.89999999999999,119.85,112.80000000000001,126.9]
[null,"Maxey ES",null,38,36.1,34.2,32.300000000000004,30.400000000000002,34.2]
[null,"McCoy ES",null,280,266,252,238,224,252]
[null,"Meadow Woods ES",null,1150,1092.5,1035,977.5,920,1035]
[null,"Metrowest ES",null,610,610,610,0,0,366]
[null,"Northlake Park ES",null,0,0,0,0,0,0]
[null,"Oak Hill ES",null,29,27.55,26.1,24.650000000000002,23.200000000000003,26.1]
[null,"Ocoee ES",null,338,321.1,304.20000000000005,287.30000000000007,270.40000000000003,304.20000000000005]
[null,"Orange Center ES",null,185,175.75,166.5,157.25,148,166.5]
[null,"Orlo Vista ES",null,390,370.5,351,331.5,312,351]
[null,"Palm Lake ES",null,870,139,139,139,139,285.2]
[null,"Palmetto ES",null,1150,0,0,0,0,230]
[null,"Pershing ES",null,124,117.8,111.6,105.39999999999999,99.2,111.6]
[null,"Pinar ES",null,260,0,0,0,0,52]
[null,"Pine Castle ES",null,38,36.1,34.2,32.300000000000004,30.400000000000002,34.2]
[null,"Pine Hills ES",null,15,15,15,0,0,9]
[null,"Pineloch ES",null,162,153.9,145.8,137.70000000000002,129.6,145.8]
[null,"Pinewood ES",null,0,0,0,0,0,0]
[null,"Princeton ES",null,90,85.5,81,76.5,72,81]
[null,"Ray, Mollie ES",null,186,186,186,186,186,186]
[null,"Richmond Hgts ES",null,360,54,54,54,54,115.2]
[null,"Ridgewood Park ES",null,565,565,152,152,152,317.2]
[null,"Riverdale ES",null,0,0,0,0,0,0]
[null,"Riverside ES",null,475,451.25,427.5,403.75,380,427.5]
[null,"Rock Lake ES",null,133,126.35,119.69999999999999,113.04999999999998,106.4,119.7]
[null,"Rock Springs ES",null,180,180,180,180,180,180]
[null,"Rolling Hills ES",null,0,0,0,0,0,0]
[null,"Rosemont ES",null,138,131.1,124.19999999999999,117.29999999999998,110.4,124.2]
[null,"Sadler ES",null,366,347.7,329.4,311.09999999999997,292.8,329.4]
[null,"Shenandoah ES",null,285,285,285,0,0,171]
[null,"Shingle Creek ES",null,831,789.45,747.9000000000001,706.3500000000001,664.8000000000001,747.9000000000002]
[null,"Southwood ES",null,57,54.15,51.3,48.449999999999996,45.6,51.3]
[null,"Spring Lake ES",null,523,496.85,470.70000000000005,444.55000000000007,418.40000000000003,470.7000000000001]
[null,"Sunrise ES",null,52,49.4,46.8,44.199999999999996,41.6,46.8]
[null,"Tangelo Park ES",null,19,18.05,17.1,16.150000000000002,15.200000000000001,17.1]
[null,"Tildenville ES",null,285,285,285,57,57,193.8]
[null,"Union Park ES",null,119,119,119,119,119,119]
[null,"Ventura ES",null,1030,860,860,0,0,550]
[null,"Washington Shores ES",null,14,13.3,12.600000000000001,11.900000000000002,11.200000000000001,12.600000000000003]
[null,"Waterbridge ES",null,779,740.05,701.0999999999999,662.1499999999999,623.2,701.0999999999998]
[null,"Waterford ES",null,226,226,226,226,226,226]
[null,"Wheatley ES",null,0,0,0,0,0,0]
[null,"Windermere ES",null,335,335,335,0,0,201]
[null,"Windy Ridge ES",null,708,672.6,637.2,601.8000000000001,566.4,637.2]
[null,"Winegard ES",null,133,126.35,119.69999999999999,113.04999999999998,106.4,119.7]
[null,"Zellwood ES",null,209,198.55,188.10000000000002,177.65000000000003,167.20000000000002,188.10000000000005]
[null,"Apopka MS",null,171,162.45,153.89999999999998,145.34999999999997,136.8,153.9]
[null,"Carver MS",null,14,13.3,12.600000000000001,11.900000000000002,11.200000000000001,12.600000000000003]
[null,"Conway MS",null,678,644.1,610.2,576.3000000000001,542.4,610.2]
[null,"Corner Lake MS",null,0,0,0,0,0,0]
[null,"Discovery MS",null,293,278.35,263.70000000000005,249.05000000000004,234.4,263.70000000000005]
[null,"Glenridge MS",null,120,120,0,0,0,48]
[null,"Gotha MS",null,661,627.95,594.9000000000001,561.8500000000001,528.8000000000001,594.9000000000001]
[null,"Howard MS",null,105,105,0,0,0,42]
[null,"Hunters Creek MS",null,435,435,0,0,0,174]
[null,"Jackson MS",null,789,789,0,0,0,315.6]
[null,"Lakeview MS",null,90,90,0,0,0,36]
[null,"Lee MS",null,328,311.6,295.20000000000005,278.80000000000007,262.40000000000003,295.20000000000005]
[null,"Liberty MS",null,445,445,0,0,0,178]
[null,"Lockhart MS",null,352,334.4,316.79999999999995,299.19999999999993,281.6,316.8]
[null,"Maitland MS",null,171,162.45,153.89999999999998,145.34999999999997,136.8,153.9]
[null,"Meadow Woods MS",null,0,0,0,0,0,0]
[null,"Meadowbrook MS",null,413,392.35,371.70000000000005,351.05000000000007,330.40000000000003,371.7000000000001]
[null,"Memorial MS",null,390,370.5,351,331.5,312,351]
[null,"Ocoee MS",null,0,0,0,0,0,0]
[null,"Piedmont Lakes MS",null,257,244.15,231.3,218.45000000000002,205.60000000000002,231.3]
[null,"Robinswood MS",null,214,203.3,192.60000000000002,181.90000000000003,171.20000000000002,192.60000000000005]
[null,"Southwest MS",null,86,81.7,77.4,73.10000000000001,68.8,77.4]
[null,"Union Park MS",null,527,500.65,474.29999999999995,447.94999999999993,421.6,474.3]
[null,"Walker MS",null,228,216.6,205.2,193.79999999999998,182.4,205.2]
[null,"Westridge MS",null,0,0,0,0,0,0]
[null,"Apopka HS",null,240,228,216,204,192,216]
[null,"Apopka 9th GC",null,1077,1023.15,969.3,915.4499999999999,861.6,969.3]
[null,"Boone HS",null,82,82,0,0,0,32.8]
[null,"Colonial HS",null,479,319,0,0,0,159.6]
[null,"Colonial 9th GC",null,1168,0,0,0,0,233.6]
[null,"Cypress Creek HS",null,1204,1204,1204,0,0,722.4]
[null,"Dr. Phillips HS",null,350,0,0,0,0,70]
[null,"Dr. Phillips 9th GC",null,448,0,0,0,0,89.6]
[null,"Edgewater HS",null,521,494.95,468.9,442.84999999999997,416.8,468.9]
[null,"Evans HS",null,86,81.7,77.4,73.10000000000001,68.8,77.4]
[null,"Evans 9th GC",null,955,907.25,859.5,811.75,764,859.5]
[null,"Jones HS",null,360,360,0,0,0,144]
[null,"Oak Ridge HS",null,684,649.8,615.5999999999999,581.3999999999999,547.2,615.6]
[null,"Robert Hungerford HS",null,356,338.2,320.4,302.59999999999997,284.8,320.4]
[null,"University HS",null,900,0,0,0,0,180]
[null,"University 9th GC",null,1950,1024,1024,1024,1024,1209.2]
[null,"West Orange HS",null,870,0,0,0,0,174]
[null,"W. Orange 9th GC",null,1020,1020,1020,1020,1020,1020]
[null,"Winter Park HS",null,0,0,0,0,0,0]
[null,"Winter Park 9th GC",null,0,0,0,0,0,0]
[null,"Cherokee ",null,0,0,0,0,0,0]
[null,"Gateway",null,198,188.1,178.2,168.29999999999998,158.4,178.2]
[null,"Magnolia",null,0,0,0,0,0,0]
[null,"Silver Star",null,0,0,0,0,0,0]
["2f.","ORANGE Total students in relocatables by year",null,49414,39887.79999999999,34793.600000000006,29213.399999999994,27724.2,36206.6]
[null,"Total number of CO-FTE students projected by year",null,143614,148086,152966,157070,161169,152581]
[null,"Percent in relocatables by year",null,0.34,0.27,0.23,0.19,0.17,0.24]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01 ","2000-01 ","2000-01 ","2000-01 ","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New ES \"A\" (ColumSunrse)",1,11800000,934,95384,102.12,70,107,174,12633.83,7485,11173,16419]
[null,"New ES \"B\" (Hunters Crk)",1,11043333,934,95384,102.12,70,107,174,11823.7,7485,11173,16419]
[null,"New ES \"C\" (Frangus)",1,11109498,934,95384,102.12,70,107,174,11894.54,7485,11173,16419]
[null,"New ES \"D\" (Ventura)",1,11071533,934,95384,102.12,70,107,174,11853.89,7485,11173,16419]
[null,"New ES \"E\" (East/West)",1,10999999,934,95384,102.12,70,107,174,11777.3,7485,11173,16419]
[null,"New ES \"F\" (Blankner K-8)",2,17800000,1252,138956,110.99,88,90,180,14217.25,7226,13517,18473]
[null,"New ES \"G\" (Lake Whitney)",1,12100000,934,95384,102.12,70,107,174,12955.03,7485,11173,16419]
[null,"Ocoee Dem. MS",2,22234014,1687,145686,86.36,88,90,180,13179.62,7226,13517,18473]
[null,"New MS \"BB\" (Liberty)",2,21662788,1504,171532,114.05,88,90,180,14403.45,7226,13517,18473]
[null,"New HS \"AAA\" (W.Orange)",3,55140016,3029,350754,115.8,117,130,144,18204.03,16957,19232,21507]
[null,"New HS \"BBB\" (University)",3,55176545,3029,350754,115.8,117,117,144,18216.09,16957,19232,21507]
["3a.","ORANGE Total 2000-01",null,240137726,16105,1729986,107.42,null,null,null,14910.76]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New ES \"H\"(Northwest)",1,12600000,934,95384,102.12,70,107,174,13490.36,7485,11173,16419]
[null,"New ES \"I\" (West/North)",1,12600000,934,95384,102.12,70,107,174,13490.36,7485,11173,16419]
[null,"New MS \"AA\" (Glenridge)",2,21700000,1530,168047,109.83,88,90,180,14183.01,7226,13517,18473]
[null,"New MS \"CC\" (Discovery)",2,22300000,1504,171532,114.05,88,90,180,14827.13,7226,13517,18473]
[null,"New MS \"DD\" (South/West)",2,22300000,1504,171532,114.05,88,90,180,14827.13,7226,13517,18473]
[null,"New HS \"CCC\" (Cypress)",3,58400000,3029,350754,115.8,117,130,144,19280.29,16957,19232,21507]
["3b","ORANGE Total 2001-02",null,149900000,9435,1052633,111.57,null,null,null,15887.65]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New HS \"DDD\"(West/North)",3,59800000,3029,350754,115.8,117,130,144,19742.49,16957,19232,21507]
["3c","ORANGE Total 2002-03",null,59800000,3029,350754,115.8,null,null,null,19742.49]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New ES \"J\" (NTC Site)",1,12800000,934,95384,102.12,70,107,174,13704.5,7485,11173,16419]
[null,"New HS \"EEE\" (W.Orange)",3,63200000,3029,350754,115.8,117,130,144,20864.97,16957,19232,21507]
["3d.","ORANGE Total 2003-04",null,76000000,3963,446138,112.58,null,null,null,19177.39]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New MS \"DD\" (W.Orange)",2,18000000,1504,171532,114.05,88,90,180,11968.09,7226,13517,18473]
[null,"New HS \"FFF\" (Apopka)",3,67100000,3029,350754,115.8,117,130,144,22152.53,16957,19232,21507]
["3e","ORANGE Total 2004-05",null,85100000,4533,522286,115.22,null,null,null,18773.44]
[]
["3f.","ORANGE 5-Year Total",null,610937726,37065,4101797]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"," "]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,97696949,103558766,109772292,116358630,123340148,550726785]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,97696949,103558766,109772292,116358630,123340148,550726785,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,20370088,0,0,0,0,20370088,0.03699]
[null,"  less amount used to purchase other vehicles",null,1881917,0,0,0,0,1881917,0.00342]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used for maintenance/repair",null,135596568,0,0,0,0,135596568,0.24621]
[" ","  less amount used to purchase capital outlay equipment",null,471244,0,0,0,0,471244,0.00086]
[null,"  less amount used to correct environmental problems",null,1749880,400000,400000,400000,400000,3349880,0.00608]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,62400000,108100000,170500000,0.30959]
[null,"  less amount to pay debt service for COP's ",null,25605000,46385322,50182619,53665597,60654338,236492876,0.42942]
[null,"  less other (site acquisition)",null,12997328,5812500,6825000,3000000,3000000,31634828,0.05744]
[null,"  less other (emergency shelter retrofits)",null,2105414,400000,400000,400000,400000,3705414,0.00673]
[null,"  less other (life safety contingency)",null,4179536,2400000,1800000,1350000,1250000,10979536,0.01994]
[null,"  less other (security systems installations)",null,1288068,400000,400000,400000,400000,2888068,0.00524]
[null,"  less other (portable leasing)",null,7155627,6300000,6300000,6300000,6300000,32355627,0.05875]
[null,"  less other (portable moves and installations)",null,7895095,6300000,5600000,4900000,4900000,29595095,0.05374]
[null,"  less other (portable repairs)",null,1033397,400000,400000,400000,400000,2633397,0.00478]
[null,"  less other (portable replacement with permanent construction)",null,28070749,3500000,0,0,0,31570749,0.05733]
[null,"  less other (educational technology retrofits)",null,3795672,1000000,1000000,1000000,1000000,7795672,0.01416]
[null,"  less other (network technology)",null,1614000,1664000,1174000,1184000,1184000,6820000,0.01238]
[null,"  less other (schools allocation)",null,1986774,2052603,2102603,2152603,2152603,10447186,0.01897]
[null,"  less other (ancillary facilities)",null,119823,0,0,0,0,119823,0.00022]
[null,"  less other (equipment lease payments)",null,1983861,4128010,6272159,6272159,6272159,24928348,0.04526]
[null,"  less other (project management)",null,7456332,7572070,7572070,7572070,7572070,37744612,0.06854]
[null,"  less other (contingency reserve)",null,3253308,6897014,10977229,11635863,12334015,45097429,0.08189]
[null,"  less other (future project reserve)",null,0,-127266361,96257211,-87928289,-20768392,-139705831,-0.25368]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,-172912732,135213608,-87890599,41254627,-72210645,-156545741,-0.28425,-0.26]
[null,"P E C O New Construction",null,12417458,6561777,11954244,9484478,8091924,48509881,null,0.08]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,1231420,1268362,1306415,1437056,1480167,6723420,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,170500000,0,0,0,0,170500000,null,0.28]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,171000000,0,120000000,0,123200000,414200000,null,0.69]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,21802186,22456253,23129940,23823839,24538554,115750772,null,0.19]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","ORANGE Total",null,204038332,165500000,68500000,76000000,85100000,599138332,1.00001,0.99]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New ES \"A\" (Col/Sunnrise)",934,11800000," "," "," "," ",11800000]
[null,"New ES \"B\"(Hunters Creek)",934,2906851]
[null,"New ES \"C\"(Frangus/Ocoe)",934,3234689]
[null,"New ES \"D\" (Ventura/Pinar)",934,10974208]
[null,"New ES \"E\" (East/West)",934,10734739]
[null,"New ES \"F\" (Blankner K8)",1252,17800000]
[null,"New ES \"G\" (Lake Whitney)",934,12100000]
[null,"Ocoee Dem. MS",1687,13553823]
[null,"New MS \"BB\"(Liberty/Con)",1504,21662788]
[null,"New HS \"AAA\"(W.Or./Dr. Ph)",3029,41775408]
[null,"New HS \"BBB\"(University)",3029,41186291]
[null,"New ES \"H\" (Northwest)",934,null,12600000]
[null,"New ES \"I\" (West/North)",934,null,12600000]
[null,"New MS \"AA\"(GlenRidge)",1530,null,21700000]
[null,"New MS \"CC\" (Discovery)",1504,null,22300000]
[null,"New MS \"DD\" (South/West)",1504,null,22300000]
[null,"New HS \"CCC\" (Cypress)",3029," ",58400000," "," "," ",58400000]
[null,"New HS \"DDD\" (West/North)",3029," "," ",59800000," "," ",59800000]
[null,"New ES \"J\" (NTC Site)",934," "," "," ",12800000," ",12800000]
[null,"New HS \"EEE\" (W. Orange)",3029," "," "," ",63200000," ",63200000]
["5.","ORANGE Total",32532,187728797,149900000,59800000,76000000,0,206000000]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,3150000,0,0,0,0,3150000]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","ORANGE Total",null,3150000,0,0,0,0,3150000]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null," "," ",0,0,0,0," ",0]
[null,"None"," ",0,0,0,0,0,0]
[null," "," ",0,0,0," ",0,0]
["7.","ORANGE Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[]
[]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"Check Totals","Check Totals","Check Totals","Check Totals","Check Totals","Check Totals"]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this 23rd day of January, 2001."]
[]
[null,"SCHOOL BOARD OF ","ORANGE  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Ron Blocker"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ",{"$nulls":4},"Henry Boekhoff",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,null,"Jon (Terry) Adsit","Facilities Executive Director",null,"(407) 317-3733","adsitt@ocps,k12.fl.us"," "]
[null,null,"Signature",null,"Name Printed","Job Title",null,"Phone number(s)","E-Mail Address",null," "]
[]
[]
[]
[null,null,"to remove all comments after final edit"]
[]
[]
[]
[]
[null,null,"edited to this point"]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}