{"text_format":"2","workbook":"xls","n_sheets":4,"sheets":["*****","Sheet1","00_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":4,"comments":2,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"Sheet1","index":1,"n_rows":86,"n_cols":11,"rows_kept":86,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,"Project Description","Desc 2","5 YEAR TOTAL","year","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"96-A, Jupiter Area Elem School",null,849040,0,849040,{"$nulls":4},849040]
[null,"96-B, Acreage Area Elem",null,1000000,0,1000000,{"$nulls":4},1000000]
[null,"96-BB, Boynton/Delray Area Middle",null,1010690,0,1010690," "," ",null,null,1010690]
[null,"96-FF, Jupiter Area Middle",null,1500000,0,1500000," "," ",null,null,1500000]
[null,"96-H, West Boca Raton Elem",null,1000000,0,1000000,{"$nulls":4},1000000]
[null,"96-II, Mid/High Holding School",null,6905628,0,6905628,{"$nulls":4},6905628]
[null,"96-III, Boynton Beach High",null,1073074,0,1073074,{"$nulls":4},1073074]
[null,"96-K, WPB Area Elem",null,1304838,0,1304838,{"$nulls":4},1304838]
[null,"96-L, Wellington Area Elem",null,1000000,0,1000000,null," ",null,null,1000000]
[null,"96-M, Boynton/Delray Area Elem",null,1000000,0,1000000," "," ",null,null,1000000]
[null,"96-N, Pleasant City Area Elem",null,1320911,0,1320911,{"$nulls":4},1320911]
[null,"Boca Raton Elem Modernization",null,9353700,0,9353700,{"$nulls":4},9353700]
[null,"Career Academies Modifications",null,2000000,0,1000000,1000000,null,null,null,2000000]
[null,"Forest Hill Elem Modernization",null,11651453,0,11651453,{"$nulls":4},11651453]
[null,"West Gate Elem Replacement",null,2332228,0,2332228,{"$nulls":4},2332228]
[null,"96-D, Elementary Holding School",1,12010540,1,12010540,{"$nulls":4},12010540]
[null,"96-DD, Lantana Middle Replacement",2,18531752,1,18531752,{"$nulls":4},18531752]
[null,"96-EE, WPB Area Middle",2,20975544,1,1258533,18367011,1350000,null,null,20975544]
[null,"96-GG, Boca Raton Area Middle",2,20020929,1,1201256,17719673,1100000,null,null,20020929]
[null,"96-I, Boynton/Delray Area Elem",1,12093960,1,12093960,{"$nulls":4},12093960]
[null,"96-J, Western Communities Elem",1,12142460,1,12142460,null," ",null,null,12142460]
[null,"96-JJJ, Central WPB Area High",3,48760169,1,48760169," "," ",null,null,48760169]
[null,"Atlantic High Modernization",0,51009039,1,100000,2960542,45448497,2500000,null,51009039]
[null,"Belvedere Elementary Modernization",0,100000,1,100000,{"$nulls":4},100000]
[null,"Boca Raton High School Modernization",0,46088286,1,112641,43475645,2500000,null,null,46088286]
[null,"Central Bus Compound",0,3025000,1,275000,2750000,null,null,null,3025000]
[null,"Dreyfoos SOA Addition",0,195000,1,195000,{"$nulls":4},195000]
[null,"Forest Hill High Modernization",0,39691445,1,2095240,null,37596205,null,null,39691445]
[null,"Future School Modernizations",0,140199004,1,1678505,33791911,28587035,54994771,21146782,140199004]
[null,"Greenacres Elem Modernization",0,100000,1,100000,{"$nulls":4},100000]
[null,"H.L. Watkins Middle School Modernization",0,100000,1,100000,{"$nulls":4},100000]
[null,"Jupiter Elem Modernization",0,11221024,1,104561,11116463,null,null,null,11221024]
[null,"Lake Worth High School Addition",0,4524000,1,4524000,{"$nulls":4},4524000]
[null,"Palm Beach Public Modernization",0,6994526,1,201710,6792816,null,null,null,6994526]
[null,"Palm Springs Elementary Modernization",0,100000,1,100000,{"$nulls":4},100000]
[null,"Roosevelt Elementary Modernization",0,100000,1,100000,{"$nulls":4},100000]
[null,"U.B. Kinsey/Palmview Elem. Modernization",0,100000,1,100000,{"$nulls":4},100000]
[null,"Village Academy Secondary Level",0,100000,1,100000,{"$nulls":4},100000]
[null,"96-HH, Acreage Area Middle",2,20541282,2,null,100000,19246282,1195000,null,20541282]
[null,"Conniston Mid Modernization",0,19117126,2,null,19117126,null,null,null,19117126]
[null,"Feasibilty Studies",0,525000,2,null,525000,null,null,null,525000]
[null,"Indian Pines Addition",0,100000,2,null,100000,null,null,null,100000]
[null,"South Olive Modernization",0,8007207,2,null,8007207,null,null,null,8007207]
[null,"96-Q, Acreage Area Elem",1,13032920,3,null,null,100000,12932920,null,13032920]
[null,"John I Leonard High Modernization",0,52014051,3,null,null,100000,3062843,48851208,52014051]
[null,"Jupiter High Modernization",0,2750000,3,null,null,2750000,null,null,2750000]
[null,"96-EEE, West Boynton High",3,51924538,4,null,null,null,3295472,48629066,51924538]
{"$rows_empty":35}
[null,null,148203056]
[null,null,158286889]
[null,null,-10083833]

{"sheet":"00_5YrWkPlan","index":2,"n_rows":1105,"n_cols":25,"rows_kept":1105,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Palm Beach County  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Palm Beach County   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2000, and all data accurate as of July 15, 2000.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Palm Beach County","Date: ==>","2000-10-01",null,"For fiscal years","  2000-2001 through 2004-2005"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"ADA Compliance","Various Schools",865000,897000,933000,969000,1015000,4679000]
[null,"Facilities Mgmt Projects","Various Schools",200000,{"$nulls":4},200000]
[null,"Facility Support","Various Schools",8000000,8000000,8000000,8000000,8000000,40000000]
[null,"Fire & Life Safety","Various Schools",1238000,1178000,1161000,1138000,1000000,5715000]
[null,"Health Clinic Compliance","Various Schools",500000,500000,300000,100000,100000,1500000]
[null,"HVAC","Various Schools",2163000,2250000,2340000,3430000,2800000,12983000]
[null,"Kitchen HVAC","Various Schools",1500000,1500000,null,null,null,3000000]
[null,"Major Renov.& Systems Replmnt.","Various Schools",7500000,7500000,7500000,7500000,7500000,37500000]
[null,"Masonry Remediation Project","Various Schools",1622290,{"$nulls":4},1622290]
[null,"Minor Bldg. Add./Space Renov.","Various Schools",5842000,5979000,5113000,5329000,5614000,27877000]
[null,"Playground Replacement","Various Schools",500000,350000,250000,100000,100000,1300000]
[null,"Portable Leasing","Various Schools",1915000,1300000,1000000,700000,500000,5415000]
[null,"Portable Relocation","Various Schools",3000000,2750000,2500000,2000000,2000000,12250000]
[null,"Roof Replacement","Various Schools",5152271,4560000,6726000,7291200,7291200,31020671]
[null,"Title 9 Gender Equity","Various Schools",500000,250000,100000,50000,50000,950000]
[null,"Traffic Improvements","Various Schools",650000,650000,500000,500000,500000,2800000]
[null,"Vegetation Removal","Various Schools",150000,150000,200000,null,null,500000]
["1.","Palm Beach County Total",null,41297561,37814000,36623000,37107200,36470200,189311961]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Atlantic High Modernization",null,100000,2960542,45448497,2500000,null,51009039]
[null,"Belvedere Elementary Modernization",null,100000,{"$nulls":4},100000]
[null,"Boca Raton Elem - expand media, dining & kitchen; 16 new classrooms",null,9353700,{"$nulls":4},9353700]
[null,"Boca Raton High School - Modernization",null,112641,43475645,2500000,null,null,46088286]
[null,"Career Academies Modifications",null,1000000,1000000,null,null,null,2000000]
[null,"Central Bus Compound",null,275000,2750000,null,null,null,3025000]
[null,"Conniston Mid Modernization",null,null,19117126,null,null,null,19117126]
[null,"Dreyfoos SOA Addition",null,195000,{"$nulls":4},195000]
[null,"Feasibilty Studies",null,null,525000,null,null,null,525000]
[null,"Forest Hill Elem  - expand media, dining & kitchen; 12 new classrooms",null,11651453,{"$nulls":4},11651453]
[null,"Forest Hill High Modernization",null,2095240,null,37596205,null,null,39691445]
[null,"Future School Modernizations",null,1678505,33791911,28587035,54994771,21146782,140199004]
[null,"Greenacres Elem Modernization",null,100000,{"$nulls":4},100000]
[null,"H.L. Watkins Middle School Modernization",null,100000,{"$nulls":4},100000]
[null,"Indian Pines Addition",null,null,100000,null,null,null,100000]
[null,"John I Leonard High Modernization",null,null,null,100000,3062843,48851208,52014051]
[null,"Jupiter Elem - expand dining & kitchen;  12 new classrooms",null,104561,11116463,null,null,null,11221024]
[null,"Jupiter High Modernization",null,null,null,2750000,null,null,2750000]
[null,"Lake Worth High School Addition",null,4524000,{"$nulls":4},4524000]
[null,"New Elem School \"A\"","Jupiter Area Elem School",849040,{"$nulls":4},849040]
[null,"New Elem School \"B\"","Acreage Area Elem",1000000,{"$nulls":4},1000000]
[null,"New Elem School \"D\"","Elementary Holding School",12010540,{"$nulls":4},12010540]
[null,"New Elem School \"H\"","West Boca Raton Elem",1000000,{"$nulls":4},1000000]
[null,"New Elem School \"I\"","Boynton/Delray Area Elem",12093960,{"$nulls":4},12093960]
[null,"New Elem School \"J\"","Western Communities Elem",12142460,null," ",null,null,12142460]
[null,"New Elem School \"K\"","WPB Area Elem",1304838,{"$nulls":4},1304838]
[null,"New Elem School \"L\"","Wellington Area Elem",1000000,null," ",null,null,1000000]
[null,"New Elem School \"M\"","Boynton/Delray Area Elem",1000000," "," ",null,null,1000000]
[null,"New Elem School \"N\"","Pleasant City Area Elem",1320911,{"$nulls":4},1320911]
[null,"New Elem School \"Q\"","Acreage Area Elem",null,null,100000,12932920,null,13032920]
[null,"New High School \"EEE\"","West Boynton High",null,null,null,3295472,48629066,51924538]
[null,"New High School \"III\"","Boynton Beach High",1073074,{"$nulls":4},1073074]
[null,"New High School \"JJJ\"","Central WPB Area High",48760169," "," ",null,null,48760169]
[null,"Village Academy Secondary Level",null,100000,{"$nulls":4},100000]
[null,"New Mid School \"BB\"","Boynton/Delray Area Middle",1010690," "," ",null,null,1010690]
[null,"New Mid School \"DD\"","Lantana Middle Replacement",18531752,{"$nulls":4},18531752]
[null,"New Mid School \"EE\"","WPB Area Middle",1258533,18367011,1350000,null,null,20975544]
[null,"New Mid School \"FF\"","Jupiter Area Middle",1500000," "," ",null,null,1500000]
[null,"New Mid School \"GG\"","Boca Raton Area Middle",1201256,17719673,1100000,null,null,20020929]
[null,"New Mid School \"HH\"","Acreage Area Middle",null,100000,19246282,1195000,null,20541282]
[null,"New Mid School \"II\"","Mid/High Holding School",6905628,{"$nulls":4},6905628]
[null,"Palm Beach Public Modernization",null,201710,6792816,null,null,null,6994526]
[null,"Palm Springs Elementary Modernization",null,100000,{"$nulls":4},100000]
[null,"Roosevelt Elementary Modernization",null,100000,{"$nulls":4},100000]
[null,"South Olive Modernization",null,null,8007207,null,null,null,8007207]
[null,"U.B. Kinsey/Palmview Elem. Modernization",null,100000,{"$nulls":4},100000]
[null,"West Gate Elem - expand media;  12 new classrooms",null,2332228,{"$nulls":4},2332228]
["2 .","Palm Beach County Total",null,158286889,165823394,138778019,77981006,118627056,659496364]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1999-00 FISH Satisfactory","Actual 1999-00","Actual 1999-00","Actual 1999-00","New Stu Capacity to","Projected 2004-05","Projected 2004-05"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Acreage Pines Elem",1283,1283,1437,1.12,-300,997,1.01]
[null,"Addison Mizner Elem",909,909,888,0.98,-175,678,0.92]
[null,"Allamanda Elem",944,944,685,0.73,0,783,0.83]
[null,"Banyan Creek Elem",1339,1339,1067,0.8,-525,801,0.98]
[null,"Barton Elem",1443,1443,901,0.62,-704,713,0.96]
[null,"Belle Glade Elem",1020,1020,802,0.79,0,831,0.81]
[null,"Belvedere Elem",890,890,835,0.94,-305,603,1.03]
[null,"Berkshire Elem",1085,1085,893,0.82,-413,686,1.02]
[null,"Binks Forest Elem",1000,1000,374,0.37,75,1082,1.01]
[null,"Boca Raton Elem",453,453,306,0.68,40,488,0.99]
[null,"C.O.Taylor/Kirklane Elem",1133,1133,1069,0.94,-260,890,1.02]
[null,"Calusa Elem",779,779,630,0.81,0,784,1.01]
[null,"Citrus Cove Elem",1498,1498,1397,0.93,-675,834,1.01]
[null,"Coral Reef Elem",1000,1000,812,0.81,50,1069,1.02]
[null,"Coral Sunset Elem",1128,1128,1012,0.9,-331,782,0.98]
[null,"Crystal Lakes Elem",1003,1003,952,0.95,-231,787,1.02]
[null,"Cypress Trails Elem",943,943,893,0.95,-153,803,1.02]
[null,"D.D. Eisenhower Elem",920,920,544,0.59,-24,331,0.37]
[null,"Del Prado Elem",1273,1273,1249,0.98,-450,821,1]
[null,"Dr. Mary McLeod Bethune Elem",970,970,0,0,0,1008,1.04]
[null,"Egret Lake Elem",830,830,785,0.95,0,859,1.03]
[null,"Forest Hill Elem",1138,1138,1119,0.98,-138,984,0.98]
[null,"Forest Park Elem",942,942,672,0.71,-275,610,0.91]
[null,"Galaxy Elem",682,682,774,1.13,0,659,0.97]
[null,"Glade View Elem",941,941,627,0.67,-278,577,0.87]
[null,"Golden Grove Elem",1095,1095,1088,0.99,75,1174,1]
[null,"Gove Elem",1293,1293,820,0.63,-461,831,1]
[null,"Greenacres Elem",864,864,784,0.91,100,972,1.01]
[null,"Grove Park Elem",773,773,723,0.94,25,796,1]
[null,"H.L. Johnson Elem",1322,1322,1184,0.9,-500,826,1]
[null,"Hagen Road Elem",736,736,566,0.77,25,725,0.95]
[null,"Hammock Pointe Elem",869,869,919,1.06,-25,847,1]
[null,"Heritage Elem",992,992,0,0,150,1178,1.03]
[null,"Highland Elem",848,848,959,1.13,25,873,1]
[null,"Indian Pines Elem",1001,1001,928,0.93,-100,899,1]
[null,"J.C. Mitchell Elem",883,883,768,0.87,-104,770,0.99]
[null,"Jerry Thomas Elem",790,790,754,0.95,-11,762,0.98]
[null,"Jupiter Elem",723,723,623,0.86,100,830,1.01]
[null,"Jupiter Farms Elem",783,783,807,1.03,50,844,1.01]
[null,"K.E. Cunningham/Canal Point Elem",874,874,685,0.78,-107,639,0.83]
[null,"Lake Park Elem",599,599,640,1.07,-5,595,1]
[null,"Lantana Elem",796,796,848,1.07,-170,624,1]
[null,"Liberty Park Elem",1439,1439,1475,1.03,-475,989,1.03]
[null,"Lighthouse Elem",1339,1339,1229,0.92,-525,832,1.02]
[null,"Limestone Creek Elem",1004,1004,997,0.99,0,1022,1.02]
[null,"Lincoln Elem",1519,1519,1220,0.8,-47,1078,0.73]
[null,"Loxahatchee Groves Elem",908,908,849,0.94,-135,787,1.02]
[null,"Manatee Elem",1165,1165,1168,1,0,1169,1]
[null,"Meadow Park Elem",782,782,712,0.91,-139,641,1]
[null,"Melaleuca Elem",1101,1101,1023,0.93,-292,822,1.02]
[null,"Morikami Park Elem",1025,1025,942,0.92,0,1016,0.99]
[null,"New Horizons Elem",1636,1636,1134,0.69,-696,940,1]
[null,"North Grade Elem",790,790,520,0.66,0,799,1.01]
[null,"North Palm Beach Elem",834,834,654,0.78,0,776,0.93]
[null,"Northboro Elem",1040,1040,792,0.76,-152,809,0.91]
[null,"Northmore Elem",1761,1761,664,0.38,-872,882,0.99]
[null,"Orchard View Elem",1034,1034,941,0.91,0,993,0.96]
[null,"Pahokee (K-6) Elem",1373,1373,792,0.58,-607,741,0.97]
[null,"Palm Beach Gardens Elem",711,711,702,0.99,-23,662,0.96]
[null,"Palm Beach Public Elem",435,435,377,0.87,50,485,1]
[null,"Palm Springs Elem",926,926,925,1,0,950,1.03]
[null,"Palmetto Elem",678,678,597,0.88,190,871,1]
[null,"Panther Run Elem",1435,1435,1382,0.96,-500,967,1.03]
[null,"Pine Grove Elem",1080,1080,737,0.68,-352,665,0.91]
[null,"Pioneer Park Elem",1045,1045,729,0.7,0,677,0.65]
[null,"Plumosa Elem",708,708,599,0.85,-37,632,0.94]
[null,"Poinciana Elem",922,922,740,0.8,0,907,0.98]
[null,"Rolling Green Elem",1197,1197,860,0.72,-575,625,1]
[null,"Roosevelt Elem",1019,1019,1068,1.05,35,1066,1.01]
[null,"Rosenwald Elem",752,752,540,0.72,-44,461,0.65]
[null,"S.D. Spady Elem",649,649,621,0.96,-75,571,0.99]
[null,"Sandpiper Shores Elem",1186,1186,1180,0.99,-280,918,1.01]
[null,"Seminole Trails Elem",943,943,898,0.95,-117,828,1]
[null,"South Grade Elem",793,793,0,0,55,858,1.01]
[null,"South Olive Elem",1021,1021,1006,0.99,-275,755,1.01]
[null,"Starlight Cove Elem",1359,1359,1228,0.9,-394,990,1.03]
[null,"Timber Trace Elem",1053,1053,843,0.8,-228,825,1]
[null,"U.B.Kinsey/Palmview Elem",893,893,638,0.71,-176,691,0.96]
[null,"Verde Elem",896,896,845,0.94,-100,806,1.01]
[null,"Village Academy",490,490,0,0,0,490,1]
[null,"Washington Elem",727,727,632,0.87,-125,615,1.02]
[null,"Waters Edge Elem",1050,1050,750,0.71,0,1022,0.97]
[null,"Wellington Elem",1120,1120,1138,1.02,-168,967,1.02]
[null,"West Gate Elem",861,861,731,0.85,130,988,1]
[null,"West Riviera Elem",1130,1130,828,0.73,-290,852,1.01]
[null,"Westward Elem",802,802,682,0.85,-61,756,1.02]
[null,"Whispering Pines Elem",1227,1227,929,0.76,-325,908,1.01]
[null,"Wynnebrook Elem",1107,1107,956,0.86,-300,826,1.02]
[null,"Bear Lakes Middle",2145,1930,1354,0.7,-375,1563,1.01]
[null,"Boca Raton Middle",1623,1460,1189,0.81,-171,1303,1.01," "]
[null,"Carver Middle",2143,1928,1657,0.86,-313,1624,1.01]
[null,"Christa McAuliffe Middle",1651,1243,1315,1.06,350,1620,1.02," "]
[null,"Congress Middle",1891,1701,1242,0.73,-197,1491,0.99]
[null,"Conniston Middle",1626,1463,1031,0.7,-150,1310,1," "]
[null,"Crestwood Middle",2004,1803,1627,0.9,-300,1514,1.01," "]
[null,"Eagles Landing Middle",1723,1550,1373,0.89,275,1860,1.02]
[null,"H.L. Watkins Middle",1487,1338,1364,1.02,100,1460,1.02]
[null,"J.F. Kennedy Middle",2017,1815,1422,0.78,-353,1484,1.02," "]
[null,"Jefferson Davis Middle",1981,1782,1534,0.86,-135,1651,1]
[null,"Jupiter Middle",1984,1785,1500,0.84,-350,1449,1.01]
[null,"Lake Shore Middle",1662,1496,1181,0.79,0,1421,0.95," "]
[null,"Lake Worth Middle",2207,1986,1528,0.77,-275,1703,1]
[null,"Lantana Middle",941,846,789,0.93,175,1052,1.03]
[null,"Loggers Run Middle",1720,1548,1389,0.9,275,1881,1.03]
[null,"Middle School of the Arts",1860,1674,1231,0.74,-500,1200,1.02]
[null,"Okeeheelee Middle",1862,1675,1441,0.86,-242,1466,1.02]
[null,"Omni Middle",1696,1526,1229,0.81,-175,1360,1.01]
[null,"Polo Park Middle",1300,1170,0,0,525,1752,1.03]
[null,"Roosevelt Middle",1726,1553,1673,1.08,-100,1475,1.02]
[null,"Watson B. Duncan Middle",1745,1570,1451,0.92,0,1574,1]
[null,"Wellington Landings Middle",2054,1848,1911,1.03,-425,1422,1]
[null,"Western Pines Middle",1572,1414,1312,0.93,150,1574,1.01]
[null,"Woodlands Middle",1741,1566,1549,0.99,125,1715,1.01]
[null,"Atlantic High",2424,2302,2769,1.2,1425,3788,1.02]
[null,"Boca Raton High",2372,2253,1943,0.86,250,2564,1.02]
[null,"Dreyfoos School of the Arts",1474,1326,1209,0.91,0,1225,0.92]
[null,"Forest Hill High",1820,1729,1673,0.97,70,1982,1.1]
[null,"Glades Central High",1710,1624,1500,0.92,-30,1456,0.91]
[null,"J.I. Leonard High",3312,3146,2922,0.93,350,3687,1.05]
[null,"Jupiter High",2706,2570,1723,0.67,0,2587,1.01]
[null,"Lake Worth High",3041,2888,2913,1.01,0,3082,1.07]
[null,"Olympic Heights High",2279,2165,2607,1.2,725,3074,1.06]
[null,"Palm Beach Gardens High",2496,2371,2393,1.01,250,2739,1.05]
[null,"Palm Beach Lakes High",3090,2935,2799,0.95,100,3163,1.04]
[null,"Pahokee Mid/Sr.  (7-12)",1480,1332,1002,0.75,-26,962,0.74]
[null,"Royal Palm Beach High",2625,2493,2157,0.87,250,2893,1.05]
[null,"Santaluces High",3771,3582,3524,0.98,450,4096,1.02]
[null,"Spanish River High",3036,2884,2378,0.82,175,3186,1.04]
[null,"Suncoast High",1164,989,1292,1.31,200,1225,1.03]
[null,"W.T. Dwyer High",2148,2040,2063,1.01,275,2416,1.04]
[null,"Wellington High",2882,2737,3012,1.1,575,3438,1.04]
["2a.","Palm Beach County Total",175943,168788,145263,0.86,-10977,157062,1]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School \"A\" (970 Stu Sta) in the Jupiter area to accommodate growth."]
[null,"New Elementary School \"B\" (970 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New Elementary School \"D\" (970 Stu Sta) in the Okeechobee corridor area, West Palm Beach to accommodate growth."]
[null,"New Elementary School \"E\" (970 Stu Sta) Bent Creek Road, Wellington to accommodate growth."]
[null,"New Elementary School \"H\" (970 Stu Sta) Kimberly Blvd.  and Coral Ridge Drive, western Boca Raton to accommodate growth."]
[null,"New Elementary School \"I\" (970 Stu Sta) in the west Boca Raton/Delray Beach area to accommodate growth."]
[null,"New Elementary School \"J\" (970 Stu Sta) in the Royal Palm Beach area to accommodate growth."]
[null,"New Elementary School \"K\" (970 Stu Sta) in the West Palm Beach area to accommodate growth."]
[null,"New Elementary School \"L\" (970 Stu Sta) in the Wellington area to accommodate growth."]
[null,"New Elementary School \"M\" (970 Stu Sta) in the Boynton Beach/Delray Beach area to accommodate growth."]
[null,"New Elementary School \"N\" (500 Stu Sta) in the eastern West Palm Beach area to accommodate growth."]
[null,"New Elementary School \"Q\" (970 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New Middle School \"BB\" (1300 Stu Sta) in the Boynton Beach/Delray Beach area to accommodate growth."]
[null,"New Middle School \"DD\" (1300 Stu Sta) in the Lake Worth area to accommodate growth."]
[null,"New Middle School \"EE\" (1300 Stu Sta) in the West Palm Beach area to accommodate growth."]
[null,"New Middle School \"FF\" (1300 Stu Sta) in the Jupiter area to accommodate growth."]
[null,"New Middle School \"GG\" (1300 Stu Sta) in the Boca Raton area to accommodate growth."]
[null,"New Middle School \"HH\" (1300 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New High School \"EEE\" (2500 Stu Sta) Jog Road in the western Boynton Beach area to accommodate growth."]
[null,"New High School \"III\" (2500 Stu Sta) N.W. 22nd Ave., Quantum Park, Boynton Beach area to accommodate growth."]
[null,"New High School \"JJJ\" (2500 Stu Sta) in the west central West Palm Beach area to accommodate growth."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1999-00","Owner","Student Stations","as classroom space","in 2004-05","units by 2004-05","Column \"C\""]
[null,"Acreage Pines Elem",21,"PBCSD/Leased",521,0,3,18,0]
[null,"Addison Mizner Elem",10,"PBCSD/Leased",252,0,2,8,0]
[null,"Allamanda Elem",6,"PBCSD/Leased",93,0,0,6,0]
[null,"Banyan Creek Elem",25,"PBCSD/Leased",562,0,0,25,0]
[null,"Barton Elem",33,"PBCSD/Leased",704,0,15,18,0]
[null,"Belle Glade Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Belvedere Elem",14,"PBCSD/Leased",305,1,2,12,0]
[null,"Berkshire Elem",19,"PBCSD/Leased",413,3,1,18,0]
[null,"Boca Raton Elem",12,"PBCSD/Leased",228,0,0,12,0]
[null,"C.O.Taylor/Kirklane Elem",16,"PBCSD/Leased",260,5,1,15,0]
[null,"Calusa Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Citrus Cove Elem",30,"PBCSD/Leased",724,0,2,28,0]
[null,"Coral Reef Elem",0,"PBCSD/Leased",0,0,4,-4]
[null,"Coral Sunset Elem",15,"PBCSD/Leased",331,1,1,14,0]
[null,"Crystal Lakes Elem",9,"PBCSD/Leased",213,0,0,9,0]
[null,"Cypress Trails Elem",6,"PBCSD/Leased",153,0,0,6,0]
[null,"D.D. Eisenhower Elem",3,"PBCSD/Leased",24,0,0,3,0]
[null,"Del Prado Elem",21,"PBCSD/Leased",506,0,2,19,0]
[null,"Egret Lake Elem",2,"PBCSD/Leased",45,0,3,-1,0]
[null,"Forest Hill Elem",22,"PBCSD/Leased",455,1,3,19,0]
[null,"Forest Park Elem",12,"PBCSD/Leased",323,0,2,10,0]
[null,"Galaxy Elem",2,"PBCSD/Leased",30,0,0,2,0]
[null,"Glade View Elem",18,"PBCSD/Leased",278,1,7,11,0]
[null,"Golden Grove Elem",3,"PBCSD/Leased",85,0,2,1,0]
[null,"Gove Elem",21,"PBCSD/Leased",486,1,8,13,0]
[null,"Greenacres Elem",13,"PBCSD/Leased",212,1,2,11,0]
[null,"Grove Park Elem",3,"PBCSD/Leased",41,0,0,3,0]
[null,"H.L. Johnson Elem",30,"PBCSD/Leased",521,0,0,30,0]
[null,"Hagen Road Elem",2,"PBCSD/Leased",23,0,0,2,0]
[null,"Hammock Pointe Elem",4,"PBCSD/Leased",94,0,3,1,0]
[null,"Highland Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Indian Pines Elem",11,"PBCSD/Leased",232,1,0,11,0]
[null,"J.C. Mitchell Elem",7,"PBCSD/Leased",104,3,3,4,0]
[null,"Jerry Thomas Elem",1,"PBCSD/Leased",11,0,0,1,0]
[null,"Jupiter Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Jupiter Farms Elem",0,"PBCSD/Leased",0,0,1,-1,0]
[null,"K.E. Cunningham/Canal Point Elem",7,"PBCSD/Leased",107,0,0,7,0]
[null,"Lake Park Elem",9,"PBCSD/Leased",205,0,0,9,0]
[null,"Lantana Elem",8,"PBCSD/Leased",170,0,1,7,0]
[null,"Liberty Park Elem",30,"PBCSD/Leased",637,0,2,28,0]
[null,"Lighthouse Elem",21,"PBCSD/Leased",549,0,0,21,0]
[null,"Limestone Creek Elem",7,"PBCSD/Leased",187,0,0,7,0]
[null,"Lincoln Elem",2,"PBCSD/Leased",47,0,0,2,0]
[null,"Loxahatchee Groves Elem",7,"PBCSD/Leased",135,0,0,7,0]
[null,"Manatee Elem",9,"PBCSD/Leased",187,1,3,6,0]
[null,"Meadow Park Elem",8,"PBCSD/Leased",139,0,2,6,0]
[null,"Melaleuca Elem",14,"PBCSD/Leased",292,1,1,13,0]
[null,"Morikami Park Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"New Horizons Elem",36,"PBCSD/Leased",886,0,1,35,0]
[null,"North Grade Elem",0,"PBCSD/Leased",0,0,1,-1,0]
[null,"North Palm Beach Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Northboro Elem",10,"PBCSD/Leased",152,3,8,2,0]
[null,"Northmore Elem",42,"PBCSD/Leased",872,0,0,42,0]
[null,"Orchard View Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Pahokee (K-6) Elem",32,"PBCSD/Leased",607,5,1,31,0]
[null,"Palm Beach Gardens Elem",4,"PBCSD/Leased",23,0,0,4,0]
[null,"Palm Beach Public Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Palm Springs Elem",22,"PBCSD/Leased",332,0,1,21,0]
[null,"Palmetto Elem",24,"PBCSD/Leased",416,3,0,24,0]
[null,"Panther Run Elem",30,"PBCSD/Leased",645,2,3,27,0]
[null,"Pine Grove Elem",15,"PBCSD/Leased",352,0,12,3,0]
[null,"Pioneer Park Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Plumosa Elem",3,"PBCSD/Leased",37,0,0,3,0]
[null,"Poinciana Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Rolling Green Elem",23,"PBCSD/Leased",595,0,1,22,0]
[null,"Roosevelt Elem",15,"PBCSD/Leased",223,0,4,11,0]
[null,"Rosenwald Elem",2,"PBCSD/Leased",44,0,0,2,0]
[null,"S.D. Spady Elem",9,"PBCSD/Leased",208,0,2,7,0]
[null,"Sandpiper Shores Elem",17,"PBCSD/Leased",396,2,1,16,0]
[null,"Seminole Trails Elem",9,"PBCSD/Leased",117,0,0,9,0]
[null,"South Olive Elem",18,"PBCSD/Leased",339,1,0,18,0]
[null,"Starlight Cove Elem",16,"PBCSD/Leased",394,0,1,15,0]
[null,"Timber Trace Elem",9,"PBCSD/Leased",228,0,0,9,0]
[null,"U.B.Kinsey/Palmview Elem",11,"PBCSD/Leased",17,0,0,11,0]
[null,"Verde Elem",7,"PBCSD/Leased",137,0,1,6,0]
[null,"Washington Elem",7,"PBCSD/Leased",155,0,2,5,0]
[null,"Waters Edge Elem",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Wellington Elem",19,"PBCSD/Leased",168,8,0,19,0]
[null,"West Gate Elem",26,"PBCSD/Leased",491,0,0,26,0]
[null,"West Riviera Elem",15,"PBCSD/Leased",290,3,8,7,0]
[null,"Westward Elem",5,"PBCSD/Leased",61,0,5,0,0]
[null,"Whispering Pines Elem",18,"PBCSD/Leased",402,0,0,18,0]
[null,"Wynnebrook Elem",22,"PBCSD/Leased",402,3,2,20,0]
[null,"Bear Lakes Middle",33,"PBCSD/Leased",829,0,0,33,0]
[null,"Boca Raton Middle",19,"PBCSD/Leased",271,5,5,14,0]
[null,"Carver Middle",26,"PBCSD/Leased",613,0,0,26,0]
[null,"Christa McAuliffe Middle",11,"PBCSD/Leased",269,0,3,8,0]
[null,"Congress Middle",17,"PBCSD/Leased",397,0,0,17,0]
[null,"Conniston Middle",15,"PBCSD/Leased",281,1,0,15,0]
[null,"Crestwood Middle",32,"PBCSD/Leased",671,1,1,31,0]
[null,"Eagles Landing Middle",9,"PBCSD/Leased",245,0,3,6,0]
[null,"H.L. Watkins Middle",16,"PBCSD/Leased",300,3,0,16,0]
[null,"J.F. Kennedy Middle",26,"PBCSD/Leased",653,0,0,26,0]
[null,"Jefferson Davis Middle",26,"PBCSD/Leased",435,8,0,26,0]
[null,"Jupiter Middle",26,"PBCSD/Leased",544,3,1,25,0]
[null,"Lake Shore Middle",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Lake Worth Middle",37,"PBCSD/Leased",842,0,6,31,0]
[null,"Lantana Middle",14,"PBCSD/Leased",384,0,3,11,0]
[null,"Loggers Run Middle",13,"PBCSD/Leased",368,0,1,12,0]
[null,"Middle School of the Arts",29,"PBCSD/Leased",791,0,3,26,0]
[null,"Okeeheelee Middle",16,"PBCSD/Leased",442,0,0,16,0]
[null,"Omni Middle",16,"PBCSD/Leased",305,1,5,11,0]
[null,"Roosevelt Middle",8,"PBCSD/Leased",224,0,2,6,0]
[null,"Watson B. Duncan Middle",18,"PBCSD/Leased",423,0,0,18,0]
[null,"Wellington Landings Middle",30,"PBCSD/Leased",797,0,1,29,0]
[null,"Western Pines Middle",3,"PBCSD/Leased",82,0,1,2,0]
[null,"Woodlands Middle",5,"PBCSD/Leased",137,0,10,-5,0]
[null,"Atlantic High",28,"PBCSD/Leased",585,6,0,28,0]
[null,"Boca Raton High",9,"PBCSD/Leased",249,0,0,9,0]
[null,"Dreyfoos School of the Arts",5,"PBCSD/Leased",0,0,0,5,0]
[null,"Forest Hill High",13,"PBCSD/Leased",142,4,2,11,0]
[null,"Glades Central High",2,"PBCSD/Leased",30,0,0,2,0]
[null,"J.I. Leonard High",25,"PBCSD/Leased",558,2,3,22,0]
[null,"Jupiter High",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Lake Worth High",42,"PBCSD/Leased",1084,4,0,42,0]
[null,"Olympic Heights High",10,"PBCSD/Leased",300,0,7,3,0]
[null,"Palm Beach Gardens High",5,"PBCSD/Leased",149,0,4,1,0]
[null,"Palm Beach Lakes High",12,"PBCSD/Leased",360,0,6,6,0]
[null,"Pahokee Mid/Sr.  (7-12)",1,"PBCSD/Leased",26,0,0,1,0]
[null,"Royal Palm Beach High",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Santaluces High",42,"PBCSD/Leased",1152,1,10,32,0]
[null,"Spanish River High",18,"PBCSD/Leased",532,0,9,9,0]
[null,"Suncoast High",2,"PBCSD/Leased",0,2,2,0,0]
[null,"W.T. Dwyer High",5,"PBCSD/Leased",103,0,0,5,0]
[null,"Wellington High",9,"PBCSD/Leased",209,2,9,0,0]
["2c1.","Palm Beach County Total",1652,null,35655,93,227,1425,"Avg Age 0"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"Acreage Pines Elem",18,null,10,null,null,8,18]
[null,"Addison Mizner Elem",8,null,null,null,8,null,8]
[null,"Allamanda Elem",6,4,null,2,null,null,6]
[null,"Banyan Creek Elem",25,3,6,11,5,null,25]
[null,"Barton Elem",18,null,12,2,2,2,18]
[null,"Belvedere Elem",12,0,null,null,12,null,12]
[null,"Berkshire Elem",18,null,null,10,3,5,18]
[null,"Boca Raton Elem",12,null,null,null,12,null,12]
[null,"C.O.Taylor/Kirklane Elem",15,null,null,6,null,9,15]
[null,"Citrus Cove Elem",28,null,6,14,8,null,28]
[null,"Coral Sunset Elem",14,null,7,5,2,null,14]
[null,"Crystal Lakes Elem",9,null,null,6,3,null,9]
[null,"Cypress Trails Elem",6,null,null,4,2,null,6]
[null,"D.D. Eisenhower Elem",3,null,null,3,null,null,3]
[null,"Del Prado Elem",19,null,12,7,null,null,19]
[null,"Forest Hill Elem",19,null,null,19,null,null,19]
[null,"Forest Park Elem",10,null,null,7,3,null,10]
[null,"Galaxy Elem",2,null,null,2,null,null,2]
[null,"Glade View Elem",11,null,null,null,6,5,11]
[null,"Golden Grove Elem",1,{"$nulls":4},1,1]
[null,"Gove Elem",13,null,null,null,7,6,13]
[null,"Greenacres Elem",11,6,null,null,5,null,11]
[null,"Grove Park Elem",3,2,1,null,null,null,3]
[null,"H.L. Johnson Elem",30,null,null,15,6,9,30]
[null,"Hagen Road Elem",2,null,null,2,null,null,2]
[null,"Hammock Pointe Elem",1,null,1,null,null,null,1]
[null,"Indian Pines Elem",11,{"$nulls":4},11,11]
[null,"J.C. Mitchell Elem",4,null,null,2,1,1,4]
[null,"Jerry Thomas Elem",1,null,1,null,null,null,1]
[null,"K.E.Cunningham/Canal Point Elem",7,null,null,null,4,3,7]
[null,"Lake Park Elem",9,null,null,9,null,null,9]
[null,"Lantana Elem",7,null,null,5,2,null,7]
[null,"Liberty Park Elem",28,2,null,20,6,null,28]
[null,"Lighthouse Elem",21,null,14,7,null,null,21]
[null,"Limestone Creek Elem",7,null,null,null,5,2,7]
[null,"Lincoln Elem",2,2,{"$nulls":4},2]
[null,"Loxahatchee Groves Elem",7,null,null,2,5,null,7]
[null,"Manatee Elem",6,null,null,4,2,null,6]
[null,"Meadow Park Elem",6,null,null,4,2,null,6]
[null,"Melaleuca Elem",13," ",null,9,4,null,13]
[null,"New Horizons Elem",35,30,5,null,null,null,35]
[null,"Northboro Elem",2,null,null,2,null,null,2]
[null,"Northmore Elem",42,42,{"$nulls":4},42]
[null,"Pahokee (K-6) Elem",31,null,22,9,null,null,31]
[null,"Palm Beach Gardens Elem",4,2," ",2,null,null,4]
[null,"Palm Springs Elem",21,6,null,5,null,10,21]
[null,"Palmetto Elem",24,null,null,24,null,null,24]
[null,"Panther Run Elem",27,null,18,9,null,null,27]
[null,"Pine Grove Elem",3,null,null,3,null,null,3]
[null,"Plumosa Elem",3,null,null,3,null,null,3]
[null,"Rolling Green Elem",22,null,7,10,5,null,22]
[null,"Roosevelt Elem",11,null,null,null,2,9,11]
[null,"Rosenwald Elem",2,null,null,2,null,null,2]
[null,"S.D. Spady Elem",7,{"$nulls":4},7,7]
[null,"Sandpiper Shores Elem",16,null,11,5,null,null,16]
[null,"Seminole Trails Elem",9,null,null,2,4,3,9]
[null,"South Olive Elem",18,null,null,null,15,3,18]
[null,"Starlight Cove Elem",15,7,3,3,2,null,15]
[null,"Timber Trace Elem",9,6,3,null,null,null,9]
[null,"U.B.Kinsey/Palmview Elem",11," ",null,null,null,11,11]
[null,"Verde Elem",6,null,4,2,null,null,6]
[null,"Washington Elem",5,null,5,null,null,null,5]
[null,"Wellington Elem",19,7,4,2,3,3,19]
[null,"West Gate Elem",26,null,26,null,null,null,26]
[null,"West Riviera Elem",7,null,4,3,null,null,7]
[null,"Whispering Pines Elem",18,3,9,6,null,null,18]
[null,"Wynnebrook Elem",20,null,null,2,4,14,20]
[null,"Bear Lakes Middle",33,4,null," ",26,3,33]
[null,"Boca Raton Middle",14,null,4,3,5,2,14]
[null,"Carver Middle",26,null,16,10,null,null,26]
[null,"Christa McAuliffe Middle",8,null,5,3,null,null,8]
[null,"Congress Middle",17,null,10,7,null,null,17]
[null,"Conniston Middle",15,null,null,null,11,4,15]
[null,"Crestwood Middle",31,5,1,null,null,25,31]
[null,"Eagles Landing Middle",6,null,null,null,4,2,6]
[null,"H.L. Watkins Middle",16,null," ",9,null,7,16]
[null,"J.F. Kennedy Middle",26,null," ",null,26,null,26]
[null,"Jefferson Davis Middle",26,null,null,null,17,9,26]
[null,"Jupiter Middle",25,null,null,19,6,null,25]
[null,"Lake Worth Middle",31,null,null,null,4,27,31]
[null,"Lantana Middle",11,null,null,11,null,null,11]
[null,"Loggers Run Middle",12," ",null,null,7,5,12]
[null,"Middle School of the Arts",26,null,8,null,null,18,26]
[null,"Okeeheelee Middle",16,null,null,null,11,5,16]
[null,"Omni Middle",11," ",2,null,6,3,11]
[null,"Roosevelt Middle",6,null,null,null,4,2,6]
[null,"Watson B. Duncan Middle",18,null,null,10,8,null,18]
[null,"Wellington Landings Middle",29,18,6,null,null,5,29]
[null,"Western Pines Middle",2,{"$nulls":4},2,2]
[null,"Atlantic High",28,null,9,4,null,15,28]
[null,"Boca Raton High",9,null,null,null,9,null,9]
[null,"Dreyfoos School of the Arts",5,null,null,null,5,null,5]
[null,"Forest Hill High",11,{"$nulls":4},11,11]
[null,"Glades Central High",2,null,null,null,2,null,2]
[null,"J.I. Leonard High",22,null,null,null,17,5,22]
[null,"Lake Worth High",42,18,24,null,null,null,42]
[null,"Olympic Heights High",3,null,null,null,3,null,3]
[null,"Palm Beach Gardens High",1,null,null,null,1,null,1]
[null,"Palm Beach Lakes High",6,null,null,null,6,null,6]
[null,"Pahokee Mid/Sr. (7-12)",1,{"$nulls":4},1,1]
[null,"Santaluces High",32,null,20,12,null,null,32]
[null,"Spanish River High",9,null,null,null,5,4,9]
[null,"Wellington High",9,null,null,null,5,4,9]
["2c2.","Palm Beach County Total",1441,167,296,359,338,281,1441]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1999-00","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2004-05","FISH Stu. Sta.","# Years Leased "]
[null,"Acreage Pines Elem",1,"Leased",25,12,0,0,0]
[null,"Addison Mizner Elem",4,"Leased",100,12,0,0,0]
[null,"Allamanda Elem",0,"Leased",0,12,0,0,0]
[null,"Banyan Creek Elem",10,"Leased",250,12,0,0,0]
[null,"Barton Elem",11,"Leased",275,12,0,0,0]
[null,"Belle Glade Elem",0,"Leased",0,12,0,0,0]
[null,"Belvedere Elem",0,"Leased",0,12,0,0,0]
[null,"Berkshire Elem",1,"Leased",25,12,0,0,0]
[null,"Boca Raton Elem",3,"Leased",75,12,0,0,0]
[null,"C.O.Taylor/Kirklane Elem",2,"Leased",50,1,0,0,0]
[null,"Calusa Elem",0,"Leased",0,12,0,0,0]
[null,"Citrus Cove Elem",10,"Leased",250,12,0,0,0]
[null,"Coral Sunset Elem",2,"Leased",50,12,0,0,0]
[null,"Crystal Lakes Elem",1,"Leased",25,12,0,0,0]
[null,"Cypress Trails Elem",0,"Leased",0,12,0,0,0]
[null,"D.D. Eisenhower Elem",0,"Leased",0,12,0,0,0]
[null,"Del Prado Elem",5,"Leased",125,12,0,0,0]
[null,"Egret Lake Elem",1,"Leased",25,12,0,0,0]
[null,"Forest Hill Elem",5,"Leased",125,12,0,0,0]
[null,"Forest Park Elem",4,"Leased",100,12,0,0,0]
[null,"Galaxy Elem",0,"Leased",0,12,0,0,0]
[null,"Glade View Elem",6,"Leased",150,12,0,0,0]
[null,"Golden Grove Elem",0,"Leased",0,12,0,0,0]
[null,"Gove Elem",11,"Leased",275,12,0,0,0]
[null,"Greenacres Elem",1,"Leased",25,12,0,0,0]
[null,"Grove Park Elem",0,"Leased",0,12,0,0,0]
[null,"H.L. Johnson Elem",4,"Leased",100,12,0,0,0]
[null,"Hagen Road Elem",0,"Leased",0,12,0,0,0]
[null,"Hammock Pointe Elem",0,"Leased",0,12,0,0,0]
[null,"Highland Elem",0,"Leased",0,12,0,0,0]
[null,"Indian Pines Elem",5,"Leased",125,12,0,0,0]
[null,"J.C. Mitchell Elem",0,"Leased",0,12,0,0,0]
[null,"Jerry Thomas Elem",0,"Leased",0,12,0,0,0]
[null,"Jupiter Elem",0,"Leased",0,12,0,0,0]
[null,"Jupiter Farms Elem",0,"Leased",0,12,0,0,0]
[null,"K.E. Cunningham/Canal Point Elem",0,"Leased",0,12,0,0,0]
[null,"Lake Park Elem",4,"Leased",100,12,0,0,0]
[null,"Lantana Elem",0,"Leased",0,12,0,0,0]
[null,"Liberty Park Elem",7,"Leased",175,12,0,0,0]
[null,"Lighthouse Elem",5,"Leased",125,12,0,0,0]
[null,"Limestone Creek Elem",3,"Leased",75,12,0,0,0]
[null,"Lincoln Elem",0,"Leased",0,12,0,0,0]
[null,"Loxahatchee Groves Elem",3,"Leased",75,12,0,0,0]
[null,"Manatee Elem",4,"Leased",100,12,0,0,0]
[null,"Meadow Park Elem",3,"Leased",75,12,0,0,0]
[null,"Melaleuca Elem",3,"Leased",75,12,0,0,0]
[null,"Morikami Park Elem",0,"Leased",0,12,0,0,0]
[null,"New Horizons Elem",0,"Leased",0,12,0,0,0]
[null,"North Grade Elem",0,"Leased",0,12,0,0,0]
[null,"North Palm Beach Elem",0,"Leased",0,12,0,0,0]
[null,"Northboro Elem",1,"Leased",25,12,0,0,0]
[null,"Northmore Elem",42,"Leased",1050,12,0,0,0]
[null,"Orchard View Elem",0,"Leased",0,12,0,0,0]
[null,"Pahokee (K-6) Elem",12,"Leased",300,12,0,0,0]
[null,"Palm Beach Gardens Elem",0,"Leased",0,12,0,0,0]
[null,"Palm Beach Public Elem",0,"Leased",0,12,0,0,0]
[null,"Palm Springs Elem",5,"Leased",125,12,0,0,0]
[null,"Palmetto Elem",6,"Leased",150,12,0,0,0]
[null,"Panther Run Elem",12,"Leased",300,12,0,0,0]
[null,"Pine Grove Elem",4,"Leased",100,12,0,0,0]
[null,"Pioneer Park Elem",0,"Leased",0,12,0,0,0]
[null,"Plumosa Elem",0,"Leased",0,12,0,0,0]
[null,"Poinciana Elem",0,"Leased",0,12,0,0,0]
[null,"Rolling Green Elem",2,"Leased",50,12,0,0,0]
[null,"Roosevelt Elem",7,"Leased",175,12,0,0,0]
[null,"Rosenwald Elem",2,"Leased",50,12,0,0,0]
[null,"S.D. Spady Elem",2,"Leased",50,12,0,0,0]
[null,"Sandpiper Shores Elem",9,"Leased",225,12,0,0,0]
[null,"Seminole Trails Elem",1,"Leased",25,12,0,0,0]
[null,"South Olive Elem",3,"Leased",75,12,0,0,0]
[null,"Starlight Cove Elem",5,"Leased",125,12,0,0,0]
[null,"Timber Trace Elem",0,"Leased",0,12,0,0,0]
[null,"U.B.Kinsey/Palmview Elem",0,"Leased",0,12,0,0,0]
[null,"Verde Elem",0,"Leased",0,12,0,0,0]
[null,"Washington Elem",1,"Leased",25,12,0,0,0]
[null,"Waters Edge Elem",0,"Leased",0,12,0,0,0]
[null,"Wellington Elem",0,"Leased",0,12,0,0,0]
[null,"West Gate Elem",11,"Leased",275,12,0,0,0]
[null,"West Riviera Elem",0,"Leased",0,12,0,0,0]
[null,"Westward Elem",2,"Leased",50,12,0,0,0]
[null,"Whispering Pines Elem",2,"Leased",50,12,0,0,0]
[null,"Wynnebrook Elem",8,"Leased",200,12,0,0,0]
[null,"Bear Lakes Middle",3,"Leased",75,12,0,0,0]
[null,"Boca Raton Middle",5,"Leased",125,12,0,0,0]
[null,"Carver Middle",21,"Leased",525,12,0,0,0]
[null,"Christa McAuliffe Middle",8,"Leased",200,12,0,0,0]
[null,"Congress Middle",3,"Leased",75,12,0,0,0]
[null,"Conniston Middle",0,"Leased",0,12,0,0,0]
[null,"Crestwood Middle",5,"Leased",125,12,0,0,0]
[null,"Eagles Landing Middle",7,"Leased",175,12,0,0,0]
[null,"H.L. Watkins Middle",2,"Leased",50,12,0,0,0]
[null,"J.F. Kennedy Middle",15,"Leased",375,12,0,0,0]
[null,"Jefferson Davis Middle",0,"Leased",0,12,0,0,0]
[null,"Jupiter Middle",11,"Leased",275,12,0,0,0]
[null,"Lake Shore Middle",0,"Leased",0,12,0,0,0]
[null,"Lake Worth Middle",8,"Leased",200,12,0,0,0]
[null,"Lantana Middle",4,"Leased",100,12,0,0,0]
[null,"Loggers Run Middle",5,"Leased",125,1,0,0,0]
[null,"Middle School of the Arts",21,"Leased",525,12,0,0,0]
[null,"Okeeheelee Middle",1,"Leased",25,12,0,0,0]
[null,"Omni Middle",2,"Leased",50,12,0,0,0]
[null,"Roosevelt Middle",8,"Leased",200,12,0,0,0]
[null,"Watson B. Duncan Middle",2,"Leased",50,12,0,0,0]
[null,"Wellington Landings Middle",11,"Leased",275,12,0,0,0]
[null,"Western Pines Middle",2,"Leased",50,12,0,0,0]
[null,"Woodlands Middle",2,"Leased",50,12,0,0,0]
[null,"Atlantic High",2,"Leased",50,12,0,0,0]
[null,"Boca Raton High",2,"Leased",50,12,0,0,0]
[null,"Dreyfoos School of the Arts",3,"Leased",75,12,0,0,0]
[null,"Forest Hill High",0,"Leased",0,12,0,0,0]
[null,"Glades Central High",0,"Leased",0,12,0,0,0]
[null,"J.I. Leonard High",2,"Leased",50,12,0,0,0]
[null,"Jupiter High",0,"Leased",0,12,0,0,0]
[null,"Lake Worth High",8,"Leased",200,12,0,0,0]
[null,"Olympic Heights High",10,"Leased",250,12,0,0,0]
[null,"Palm Beach Gardens High",2,"Leased",50,12,0,0,0]
[null,"Palm Beach Lakes High",4,"Leased",100,12,0,0,0]
[null,"Pahokee Mid/Sr.  (7-12)",0,"Leased",0,12,0,0,0]
[null,"Royal Palm Beach High",0,"Leased",0,12,0,0,0]
[null,"Santaluces High",23,"Leased",575,12,0,0,0]
[null,"Spanish River High",2,"Leased",50,12,0,0,0]
[null,"Suncoast High",0,"Leased",0,12,0,0,0]
[null,"W.T. Dwyer High",1,"Leased",25,12,0,0,0]
[null,"Wellington High",11,"Leased",275,1,0,0,0]
["2c3.","Palm Beach County Total",472,null,11800,1455,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2004-05"]
[null,"Edventure - High, ESE",8,"Edventure Charter School, Inc","1998-99",40,35,3,50]
[null,"Potentials - Elem, ESE",2,"The Arc","1998-99",30,21,3,30]
[null,"Partnership Academy - Elem",5,"The Partnership Academy of the Glades, Inc","1998-99",100,97,3,200]
[null,"Delray Beach Academy - Midd",3,"Delray Beach Academy","1998-99",66,66,3,65]
[null,"Palm Beach Maritime Academy",null,"Palm Beach Maritime Museum, Inc.","1999-2000",null,100,5,500]
[null,"Academy Charter School of Boca Raton",null,"Academy School of Florida, Inc.","2000-2001",null,269,5,360]
[null,"Nguzo Saba - Elem",5,"Joseph Littels - Nguzo Saba Charter School, Inc","1998-99",125,108,5,200]
[null,"Renaissance Learning Center - Elem, ESE",1,"Renaissance Learning Center","1999-00",10,6,3,10]
[null,"St. Mary's Preschool Autism Center - Elem, ESE",4,"St. Mary's Inc.","1999-00",40,22,5,40]
["2c4.","Palm Beach County Total",28,null,null,411,724,35,724]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2004-05) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1999-00 CO-FTE","1999-00 Class size","2004-05 CO-FTE","be added (removed)","2004-05 Class size"]
[null,"Acreage Pines Elem",52,1283,1437,27.63,997,-10,23.74]
[null,"Addison Mizner Elem",36,909,888,24.67,678,-5,21.87]
[null,"Allamanda Elem",38,944,685,18.03,783,0,20.61]
[null,"Banyan Creek Elem",56,1339,1067,19.05,801,-18,21.08]
[null,"Barton Elem",65,1443,901,13.86,713,-23,16.98]
[null,"Belle Glade Elem",42,1020,802,19.1,831,0,19.79]
[null,"Belvedere Elem",40,890,835,20.88,603,-10,20.1]
[null,"Berkshire Elem",49,1085,893,18.22,686,-14,19.6]
[null,"Binks Forest Elem",41,1000,374,9.12,1082,2.5,24.87]
[null,"Boca Raton Elem",19,453,306,16.11,488,1,24.4]
[null,"C.O.Taylor/Kirklane Elem",32,1133,1069,33.41,890,3,25.43]
[null,"Calusa Elem",36,779,630,17.5,784,0,21.78]
[null,"Citrus Cove Elem",61,1498,1397,22.9,834,-23,21.95]
[null,"Coral Reef Elem",43,1000,812,18.88,1069,2,23.76]
[null,"Coral Sunset Elem",46,1128,1012,22,782,-11,22.34]
[null,"Crystal Lakes Elem",39,1003,952,24.41,787,-8,25.39]
[null,"Cypress Trails Elem",37,943,893,24.14,803,-5,25.09]
[null,"D.D. Eisenhower Elem",21,920,544,25.9,331,-1,16.55]
[null,"Del Prado Elem",52,1273,1249,24.02,821,-15,22.19]
[null,"Dr. Mary McLeod Bethune Elem",43,970,0,0,1008,0,23.44]
[null,"Egret Lake Elem",33,830,785,23.79,859,0,26.03]
[null,"Forest Hill Elem",52,1138,1119,21.52,984,-5,20.94]
[null,"Forest Park Elem",41,942,672,16.39,610,-9.166666666666666,19.16]
[null,"Galaxy Elem",34,682,774,22.76,659,0,19.38]
[null,"Glade View Elem",40,941,627,15.68,577,-9.266666666666667,18.77]
[null,"Golden Grove Elem",46,1095,1088,23.65,1174,2.5,24.21]
[null,"Gove Elem",54,1293,820,15.19,831,-15.366666666666667,21.51]
[null,"Greenacres Elem",47,864,784,16.68,972,3.3333333333333335,19.31]
[null,"Grove Park Elem",35,773,723,20.66,796,0,22.74]
[null,"H.L. Johnson Elem",54,1322,1184,21.93,826,-16.666666666666668,22.13]
[null,"Hagen Road Elem",31,736,566,18.26,725,0,23.39]
[null,"Hammock Pointe Elem",34,869,919,27.03,847,0,24.91]
[null,"Heritage Elem",43,992,0,0,1178,5,24.54]
[null,"Highland Elem",34,848,959,28.21,873,1,24.94]
[null,"Indian Pines Elem",42,1001,928,22.1,899,-3,23.05]
[null,"J.C. Mitchell Elem",46,883,768,16.7,770,-4,18.33]
[null,"Jerry Thomas Elem",34,801,754,22.18,762,0,22.41]
[null,"Jupiter Elem",40,723,623,15.58,830,0,20.75]
[null,"Jupiter Farms Elem",31,783,807,26.03,844,2,25.58]
[null,"K.E. Cunningham/Canal Point Elem",35,874,685,19.57,639,-3,19.97]
[null,"Lake Park Elem",26,599,640,24.62,595,0,22.88]
[null,"Lantana Elem",31,796,848,27.35,624,-5,24]
[null,"Liberty Park Elem",62,1439,1475,23.79,989,-15.833333333333334,21.42]
[null,"Lighthouse Elem",53,1339,1229,23.19,832,-17.5,23.44]
[null,"Limestone Creek Elem",39,1004,997,25.56,1022,0,26.21]
[null,"Lincoln Elem",67,1519,1220,18.21,1078,-2,16.58]
[null,"Loxahatchee Groves Elem",37,908,849,22.95,787,-4,23.85]
[null,"Manatee Elem",49,1165,1168,23.84,1169,0,23.86]
[null,"Meadow Park Elem",35,782,712,20.34,641,-4,20.68]
[null,"Melaleuca Elem",47,1101,1023,21.77,822,-9.733333333333333,22.06]
[null,"Morikami Park Elem",43,1025,942,21.91,1016,0,23.63]
[null,"New Horizons Elem",66,1636,1134,17.18,940,-23.2,21.96]
[null,"North Grade Elem",41,790,520,12.68,799,0,19.49]
[null,"North Palm Beach Elem",35,834,654,18.69,776,0,22.17]
[null,"Northboro Elem",44,1040,792,18,809,-5,20.74]
[null,"Northmore Elem",72,1761,664,9.22,882,-29.066666666666666,20.54]
[null,"Orchard View Elem",43,1034,941,21.88,993,0,23.09]
[null,"Pahokee (K-6) Elem",66,1373,792,12,741,-20.233333333333334,16.19]
[null,"Palm Beach Gardens Elem",32,711,702,21.94,662,-1,21.35]
[null,"Palm Beach Public Elem",24,435,377,15.71,485,0,20.21]
[null,"Palm Springs Elem",46,926,925,20.11,950,0,20.65]
[null,"Palmetto Elem",38,678,597,15.71,871,6,19.8]
[null,"Panther Run Elem",60,1435,1382,23.03,967,-16.666666666666668,22.32]
[null,"Pine Grove Elem",45,1080,737,16.38,665,-11.733333333333333,19.99]
[null,"Pioneer Park Elem",41,1045,729,17.78,677,0,16.51]
[null,"Plumosa Elem",32,708,599,18.72,632,-1,20.39]
[null,"Poinciana Elem",35,922,740,21.14,907,0,25.91]
[null,"Rolling Green Elem",39,1197,860,22.05,625,-15,26.04]
[null,"Roosevelt Elem",49,1019,1068,21.8,1066,1,21.32]
[null,"Rosenwald Elem",32,752,540,16.88,461,-2,15.37]
[null,"S.D. Spady Elem",27,649,621,23,571,-3,23.79]
[null,"Sandpiper Shores Elem",47,1186,1180,25.11,918,-9.333333333333334,24.37]
[null,"Seminole Trails Elem",47,943,898,19.11,828,-6,20.2]
[null,"South Grade Elem",33,793,0,0,858,1,25.24]
[null,"South Olive Elem",47,1021,1006,21.4,755,-9.166666666666666,19.96]
[null,"Starlight Cove Elem",55,1359,1228,22.33,990,-13.133333333333333,23.65]
[null,"Timber Trace Elem",41,1053,843,20.56,825,-7.6,24.7]
[null,"U.B.Kinsey/Palmview Elem",44,893,638,14.5,691,-5.866666666666666,18.12]
[null,"Verde Elem",38,896,845,22.24,806,-3,23.03]
[null,"Village Academy",21,490,0,0,490,0,23.33]
[null,"Washington Elem",30,727,632,21.07,615,-4,23.65]
[null,"Waters Edge Elem",43,1050,750,17.44,1022,0,23.77]
[null,"Wellington Elem",57,1120,1138,19.96,967,-9,20.15]
[null,"West Gate Elem",42,861,731,17.4,988,4,21.48]
[null,"West Riviera Elem",50,1130,828,16.56,852,-9,20.78]
[null,"Westward Elem",39,802,682,17.49,756,-2,20.43]
[null,"Whispering Pines Elem",50,1227,929,18.58,908,-10,22.7]
[null,"Wynnebrook Elem",52,1107,956,18.38,826,-10,19.67]
[null,"Bear Lakes Middle",77,1930,1354,17.58,1563,-10.714285714285714,23.58]
[null,"Boca Raton Middle",66,1460,1189,18.02,1303,-5.7,21.61]
[null,"Carver Middle",77,1928,1657,21.52,1624,-8.942857142857143,23.86]
[null,"Christa McAuliffe Middle",56,1485,1315,23.48,1620,10,24.55]
[null,"Congress Middle",68,1701,1242,18.26,1491,-5.628571428571429,23.91]
[null,"Conniston Middle",63,1463,1031,16.37,1310,-4.285714285714286,22.31]
[null,"Crestwood Middle",73,1803,1627,22.29,1514,-8.571428571428571,23.5]
[null,"Eagles Landing Middle",59,1550,1373,23.27,1860,7.857142857142857,27.82]
[null,"H.L. Watkins Middle",64,1338,1364,21.31,1460,2.857142857142857,21.84]
[null,"J.F. Kennedy Middle",78,1815,1422,18.23,1484,-10.085714285714285,21.85]
[null,"Jefferson Davis Middle",93,1782,1534,16.49,1651,-4.5,18.66]
[null,"Jupiter Middle",70,1785,1500,21.43,1449,-10,24.15]
[null,"Lake Shore Middle",58,1496,1181,20.36,1421,0,24.5]
[null,"Lake Worth Middle",80,1986,1528,19.1,1703,-7.857142857142857,23.61]
[null,"Lantana Middle",38,846,789,20.76,1052,5,24.47]
[null,"Loggers Run Middle",57,1548,1389,24.37,1881,9.166666666666666,28.43]
[null,"Middle School of the Arts",71,1674,1231,17.34,1200,-14.285714285714286,21.16]
[null,"Okeeheelee Middle",65,1675,1441,22.17,1466,-6.914285714285715,25.24]
[null,"Omni Middle",68,1526,1229,18.07,1360,-5,21.59]
[null,"Polo Park Middle",52,1300,0,0,1752,15,26.15]
[null,"Roosevelt Middle",63,1726,1673,26.56,1475,-3,24.58]
[null,"Watson B. Duncan Middle",63,1570,1451,23.03,1574,0,24.98]
[null,"Wellington Landings Middle",78,1848,1911,24.5,1422,-12.142857142857142,21.59]
[null,"Western Pines Middle",53,1414,1312,24.75,1574,5,27.14]
[null,"Woodlands Middle",57,1566,1549,27.18,1715,4,28.11]
[null,"Atlantic High",105,2302,2769,26.37,3788,47.5,24.84]
[null,"Boca Raton High",92,2253,1943,21.12,2564,8.333333333333334,25.55]
[null,"Dreyfoos School of the Arts",57,1326,1209,21.21,1225,0,21.49]
[null,"Forest Hill High",74,1729,1673,22.61,1982,2,26.08]
[null,"Glades Central High",69,1624,1500,21.74,1456,-1,21.41]
[null,"J.I. Leonard High",139,3146,2922,21.02,3687,10,24.74]
[null,"Jupiter High",100,2570,1723,17.23,2587,0,25.87]
[null,"Lake Worth High",116,2888,2913,25.11,3082,0,26.57]
[null,"Olympic Heights High",92,2165,2607,28.34,3074,24.166666666666668,26.46]
[null,"Palm Beach Gardens High",96,2371,2393,24.93,2739,8.333333333333334,26.25]
[null,"Palm Beach Lakes High",113,2935,2799,24.77,3163,3,27.27]
[null,"Pahokee Mid/Sr.  (7-12)",62,1332,1002,16.16,962,0,15.52]
[null,"Royal Palm Beach High",94,2493,2157,22.95,2893,8.333333333333334,28.27]
[null,"Santaluces High",136,3582,3524,25.91,4096,15,27.13]
[null,"Spanish River High",111,2884,2378,21.42,3186,5.833333333333333,27.27]
[null,"Suncoast High",47,989,1292,27.49,1225,6.666666666666667,22.83]
[null,"W.T. Dwyer High",88,2040,2063,23.44,2416,10.833333333333334,24.45]
[null,"Wellington High",104,2737,3012,28.96,3438,21.666666666666668,27.36]
["2e.","Palm Beach County Total",7088,169344,145263,"District Avg 20",157062,-346.2809523809524,"District Avg 23"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR AVERAGE"]
[null,"Acreage Pines Elem",null,521,271,271,271,79,282.6,null,70]
[null,"Addison Mizner Elem",null,252,252,252,52,52,172]
[null,"Allamanda Elem",null,31,31,0,0,0,12.4]
[null,"Banyan Creek Elem",null,496,364,117,0,0,195.4]
[null,"Barton Elem",null,704,452,410,368,323,451.4]
[null,"Belle Glade Elem",null,0,0,0,0,0,0]
[null,"Belvedere Elem",null,305,305,305,41,41,199.4]
[null,"Berkshire Elem",null,413,413,193,127,17,232.6]
[null,"Binks Forest Elem",null,0,0,0,0,0,0]
[null,"Boca Raton Elem",null,252,252,252,0,0,151.2]
[null,"C.O.Taylor/Kirklane Elem",null,260,260,161,161,13,171]
[null,"Calusa Elem",null,0,0,0,0,0,0]
[null,"Citrus Cove Elem",null,724,580,244,52,52,330.4]
[null,"Coral Reef Elem",null,0,100,100,100,100]
[null,"Coral Sunset Elem",null,331,177,67,23,23,124.2]
[null,"Crystal Lakes Elem",null,213,213,71,0,0,99.4]
[null,"Cypress Trails Elem",null,153,153,51,0,0,71.4]
[null,"D.D. Eisenhower Elem",null,24,24,0,0,0,9.6]
[null,"Del Prado Elem",null,506,218,50,50,50,174.8]
[null,"Dr. Mary McLeod Bethune Elem",null,0,0,0,0,0,0]
[null,"Egret Lake Elem",null,45,45,67,67,67,58.2]
[null,"Forest Hill Elem",null,455,455,63,63,63,219.8]
[null,"Forest Park Elem",null,323,323,134,53,53,177.2]
[null,"Galaxy Elem",null,30,30,0,0,0,12]
[null,"Glade View Elem",null,278,278,278,186,111,226.2]
[null,"Golden Grove Elem",null,85,85,85,85,57,79.4]
[null,"Gove Elem",null,486,486,486,325,187,394]
[null,"Greenacres Elem",null,115,115,115,32,32,81.8]
[null,"Grove Park Elem",null,15,0,0,0,0,3]
[null,"H.L. Johnson Elem",null,521,521,261,159,0,292.4]
[null,"Hagen Road Elem",null,23,23,0,0,0,9.2]
[null,"Hammock Pointe Elem",null,94,71,71,71,71,75.6]
[null,"Heritage Elem",null,0,0,0,0,0,0]
[null,"Highland Elem",null,0,0,0,0,0,0]
[null,"Indian Pines Elem",null,232,232,232,232,0,185.6]
[null,"J.C. Mitchell Elem",null,104,104,76,61,47,78.4]
[null,"Jerry Thomas Elem",null,11,0,0,0,0,2.2]
[null,"Jupiter Elem",null,0,0,0,0,0,0]
[null,"Jupiter Farms Elem",null,0,0,21,21,21,12.6]
[null,"K.E. Cunningham/Canal Point Elem",null,107,107,107,47,0,73.6]
[null,"Lake Park Elem",null,205,205,0,0,0,82]
[null,"Lantana Elem",null,170,170,65,21,21,89.4]
[null,"Liberty Park Elem",null,593,593,173,41,41,288.2]
[null,"Lighthouse Elem",null,549,183,0,0,0,146.4]
[null,"Limestone Creek Elem",null,187,187,187,57,0,123.6]
[null,"Lincoln Elem",null,0,0,0,0,0,0]
[null,"Loxahatchee Groves Elem",null,135,135,97,0,0,73.4]
[null,"Manatee Elem",null,187,187,107,65,65,122.2]
[null,"Meadow Park Elem",null,139,139,70,36,36,84]
[null,"Melaleuca Elem",null,292,292,103,23,23,146.6]
[null,"Morikami Park Elem",null,0,0,0,0,0,0]
[null,"New Horizons Elem",null,136,16,16,16,16,40]
[null,"North Grade Elem",null,0,0,0,0,21,4.2]
[null,"North Palm Beach Elem",null,0,0,0,0,0,0]
[null,"Northboro Elem",null,152,152,122,122,122,134]
[null,"Northmore Elem",null,0,0,0,0,0,0]
[null,"Orchard View Elem",null,0,0,0,0,0,0]
[null,"Pahokee (K-6) Elem",null,607,211,22,22,22,176.8]
[null,"Palm Beach Gardens Elem",null,13,13,0,0,0,5.2]
[null,"Palm Beach Public Elem",null,0,0,0,0,0,0]
[null,"Palm Springs Elem",null,242,242,167,167,0,163.6]
[null,"Palmetto Elem",null,416,416,0,0,0,166.4]
[null,"Panther Run Elem",null,645,267,74,74,74,226.8]
[null,"Pine Grove Elem",null,352,352,282,282,282,310]
[null,"Pioneer Park Elem",null,0,0,0,0,0,0]
[null,"Plumosa Elem",null,37,37,0,0,0,14.8]
[null,"Poinciana Elem",null,0,0,0,0,0,0]
[null,"Rolling Green Elem",null,595,409,150,25,25,240.8]
[null,"Roosevelt Elem",null,223,223,223,194,60,184.6]
[null,"Rosenwald Elem",null,44,44,0,0,0,17.6]
[null,"S.D. Spady Elem",null,208,208,208,208,46,175.6]
[null,"Sandpiper Shores Elem",null,396,143,28,28,28,124.6]
[null,"Seminole Trails Elem",null,117,117,91,49,0,74.8]
[null,"South Olive Elem",null,339,339,339,57,0,214.8]
[null,"Starlight Cove Elem",null,222,150,78,30,30,102]
[null,"Timber Trace Elem",null,78,0,0,0,0,15.6]
[null,"U.B.Kinsey/Palmview Elem",null,17,17,17,17,0,13.6]
[null,"Verde Elem",null,137,58,19,19,19,50.4]
[null,"Village Academy",null,0,0,0,0,0,0]
[null,"Washington Elem",null,155,45,45,45,45,67]
[null,"Waters Edge Elem",null,0,0,0,0,0,0]
[null,"Wellington Elem",null,105,73,56,32,0,53.2]
[null,"West Gate Elem",null,491,0,0,0,0,98.2]
[null,"West Riviera Elem",null,290,214,156,156,156,194.4]
[null,"Westward Elem",null,61,61,61,61,61,61]
[null,"Whispering Pines Elem",null,336,138,0,0,0,94.8]
[null,"Wynnebrook Elem",null,402,402,366,294,38,300.4]
[null,"Bear Lakes Middle",null,729,729,729,76,0,452.6]
[null,"Boca Raton Middle",null,271,215,173,103,74,167.2]
[null,"Carver Middle",null,613,236,0,0,0,169.8]
[null,"Christa McAuliffe Middle",null,269,149,74,74,74,128]
[null,"Congress Middle",null,397,167,0,0,0,112.8]
[null,"Conniston Middle",null,281,281,281,75,75,198.6]
[null,"Crestwood Middle",null,566,545,545,545,21,444.4]
[null,"Eagles Landing Middle",null,245,245,245,136,82,190.6]
[null,"H.L. Watkins Middle",null,300,300,132,132,0,172.8]
[null,"J.F. Kennedy Middle",null,653,653,653,0,0,391.8]
[null,"Jefferson Davis Middle",null,435,435,435,163,0,293.6]
[null,"Jupiter Middle",null,544,544,146,20,20,254.8]
[null,"Lake Shore Middle",null,0,0,0,0,0,0]
[null,"Lake Worth Middle",null,842,842,842,750,129,681]
[null,"Lantana Middle",null,384,384,82,82,82,202.8]
[null,"Loggers Run Middle",null,368,368,368,170,29,260.6]
[null,"Middle School of the Arts",null,791,575,575,575,89,521]
[null,"Okeeheelee Middle",null,442,442,442,138,0,292.8]
[null,"Omni Middle",null,305,267,267,153,96,217.6]
[null,"Polo Park Middle",null,0,0,0,0,0,0]
[null,"Roosevelt Middle",null,224,224,224,112,56,168]
[null,"Watson B. Duncan Middle",null,423,423,188,0,0,206.8]
[null,"Wellington Landings Middle",null,319,163,163,163,33,168.2]
[null,"Western Pines Middle",null,82,82,82,82,28,71.2]
[null,"Woodlands Middle",null,137,191,219,273,273,218.6]
[null,"Atlantic High",null,585,405,321,321,0,326.4]
[null,"Boca Raton High",null,249,249,249,0,0,149.4]
[null,"Dreyfoos School of the Arts",null,0,0,0,0,0,0]
[null,"Forest Hill High",null,142,142,142,142,21,117.8]
[null,"Glades Central High",null,30,30,30,0,0,18]
[null,"J.I. Leonard High",null,558,558,558,179,69,384.4]
[null,"Jupiter High",null,0,0,0,0,0,0]
[null,"Lake Worth High",null,619,0,0,0,0,123.8]
[null,"Olympic Heights High",null,300,300,300,210,210,264]
[null,"Palm Beach Gardens High",null,149,149,149,119,119,137]
[null,"Palm Beach Lakes High",null,360,360,360,180,180,288]
[null,"Pahokee Mid/Sr.  (7-12)",null,26,26,26,26,0,20.8]
[null,"Royal Palm Beach High",null,0,0,0,0,0,0]
[null,"Santaluces High",null,1152,612,283,283,283,522.6]
[null,"Spanish River High",null,532,532,532,382,264,448.4]
[null,"Suncoast High",null,0,0,0,0,0,0]
[null,"W.T. Dwyer High",null,103,103,103,103,103,103]
[null,"Wellington High",null,209,209,209,93,0,144]
["2f.","Palm Beach County Total students in relocatables by year",null,32016,25513,17989,10648,5100,18253.2]
[null,"Total number of CO-FTE students projected by year",null,5665,5675,5685,5690,5695,5682]
[null,"Percent in relocatables by year",null,5.65,4.5,3.16,1.87,0.9,3.21]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1999,1999,1999,1999,1999,1999]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","2000-01 Year","Type of School (new schools only)  Others=0","2000-01 ","2000-01 ","2000-01 ","2000-01 ","2000-01 ","1999 State Avg","1999 State Avg","1999 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"96-D, Elementary Holding School",1,12010540,970,115368,118.94,70,107,174,12382,7485,11173,16419]
[null,"96-DD, Lantana Middle Replacement",2,19567427,1111,152194,136.99,88,90,180,17612.45,7226,13517,18473]
[null,"98-I, Boynton/Delray Area Elem",1,12093960,970,115368,118.94,70,107,174,12468,7485,11173,16419]
[null,"96-J, Western Communities Elem",1,12142460,970,115368,118.94,70,107,174,12518,7485,11173,16419]
[null,"96-JJJ, Central WPB Area High",3,48760169,2642,344838,130.52,117,130,144,18455.78,16957,19232,21507]
[null,"Atlantic High Modernization",0,51009039,2642,344838,130.52,0,0,0,19306.98,0,0,0]
[null,"Boca Raton School Modernization",0,46088286,2642,344838,130.52,0,0,0,17444.47,0,0,0]
[null,"Forest Hill High Modernization",0,39691445,1895,303903,160.37,0,0,0,20945.35,0,0,0]
[null,"Lake Worth High School Addition",0,4524000,538,38165,70.94,0,0,0,8408.92,0,0,0]
[null,"Palm Beach Public Modernization",0,6994526,490,71049,145,0,0,0,14274.54,0,0,0]
["3a.","Palm Beach County Total 2000-01",null,252881852,14870,1945929,130.86,null,null,null,17006.18]
[]
["3b.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2001-02","1999 State Avg","1999 State Avg","2000 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"98-EE, WPB Area Middle",2,20975544,1449,189295,130.64,88,90,180,14475.88,7226,13517,18473]
[null,"96-GG, Boca Raton Area Middle",2,20020929,1111,152194,136.99,88,90,180,18020.64,7226,13517,18473]
[null,"Conniston Mid Modernization",0,19117126,1449,189295,130.64,0,0,0,13193.32,0,0,0]
[null,"Jupiter Elem Modernization",0,11221024,970,115368,118.94,0,0,0,11568.07,0,0,0]
[null,"South Olive Modernization",0,8007207,656,81288,123.91,0,0,0,12206.11,0,0,0]
["3b","Palm Beach County Total 2001-02",null,79341830,5635,727440,129.09,null,null,null,14080.18]
[]
["3c.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2002-03","1999 State Avg","1999 State Avg","2001 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"96-HH, Acreage Area Middle",2,20541282,1449,189295,130.64,88,90,180,14176.18,7226,13517,18473]
[null,"Jupiter High Modernization",0,2750000,2642,344838,130.52,0,0,0,1040.88,0,0,0]
["3c","Palm Beach County Total 2002-03",null,23291282,4091,534133,130.56,null,null,null,5693.3]
[]
["3d.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1999 State Avg","1999 State Avg","1999 State Avg","2002 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"00-Q, Acreage Area Elem",1,13032920,970,115368,118.94,70,107,174,13436,7485,11173,16419]
["3d.","Palm Beach County Total 2003-04",null,13032920,970,115368,118.94,null,null,null,13436]
[]
["3e.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","1999 State Avg","1999 State Avg","1999 State Avg","2003 Projected","1999 State Avg","1999 State Avg","1999 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"John I Leonard High Modernization",0,52014051,2642,344838,130.52,0,0,0,19687.38,0,0,0]
[null,"91-EEE, West Boynton High",3,51924538,1895,303903,160.37,117,130,144,27400.81,16957,19232,21507]
["3e","Palm Beach County Total 2004-05",null,51924538,1895,303903,160.37,null,null,null,27400.81]
[]
["3f.","Palm Beach County 5-Year Total",null,420472422,27461,3626773]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,142044747,144710800,151974500,159323225,163952922,762006194]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,142044747,144710800,151974500,159323225,163952922,762006194,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,4520000,6160000,6160000,6184445,6190000,29214445,0.0383388550251076]
[null,"  less amount used to purchase other vehicles",null,440000,440000,440000,415555,410000,2145555,0.00281566608892946]
[null,"  less amount transferred to operating budget for maintenance/repair",null,12914707,30000000,30000000,30000000,30000000,132914707,0.174427331492269]
[null,"  less amount used for maintenance/repair",null,41297561,37814000,36623000,37107200,36470200,189311961,0.248438874238337]
[null,"  less amount used to purchase capital outlay equipment",null,22485000,21423866,23472000,18959760,18776660,105117286,0.137948072899785]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,32286349,39284304,42287649,42283936,42287739,198429977,0.260404677235471]
[null," less amount used to purchase land",null,17454969,9500000,8000000,6500000,6500000,47954969,0.0629325186298945]
[null,"  less other (please be specific)",null,null,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,10646161,88630,4991851,17872329,23318323,56917294,0.0746940043902058,0.08]
[null,"P E C O New Construction",null,8499185,5506335,10031442,7958929,6790364,38786255,null,0.06]
[null,"C O & D S   Bond Proceeds",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,1000000,1000000,1000000,1000000,127286,4127286,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,129059170,159928469,123754726,52149748,88518369,553410482,null,0.81]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0,null,0]
[null,"Impact fees received",null,6000000,6000000,6000000,6000000,6000000,30000000,null,0.04]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","Palm Beach County Total",null,155204516,172523434,145778019,84981006,124754342,683241317,0.9999999999999993,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Atlantic High Modernization",null,100000,2960542,45448497,2500000,null,51009039]
[null,"Belvedere Elementary Modernization",null,100000,{"$nulls":4},100000]
[null,"Boca Raton Elem - expand media, dining & kitchen; 16 new classrooms",null,9353700,{"$nulls":4},9353700]
[null,"Boca Raton High School - Modernization",null,112641,43475645,2500000,null,null,46088286]
[null,"Career Academies Modifications",null,1000000,1000000,null,null,null,2000000]
[null,"Central Bus Compound",null,275000,2750000,null,null,null,3025000]
[null,"Conniston Mid Modernization",null,null,19117126,null,null,null,19117126]
[null,"Dreyfoos SOA Addition",null,195000,{"$nulls":4},195000]
[null,"Feasibilty Studies",null,null,525000,null,null,null,525000]
[null,"Forest Hill Elem  - expand media, dining & kitchen; 12 new classrooms",null,11651453,{"$nulls":4},11651453]
[null,"Forest Hill High Modernization",null,2095240,null,37596205,null,null,39691445]
[null,"Future School Modernizations",null,1678505,33791911,28587035,54994771,21146782,140199004]
[null,"Greenacres Elem Modernization",null,100000,{"$nulls":4},100000]
[null,"H.L. Watkins Middle School Modernization",null,100000,{"$nulls":4},100000]
[null,"Indian Pines Addition",null,null,100000,null,null,null,100000]
[null,"John I Leonard High Modernization",null,null,null,100000,3062843,48851208,52014051]
[null,"Jupiter Elem - expand dining & kitchen;  12 new classrooms",null,104561,11116463,null,null,null,11221024]
[null,"Jupiter High Modernization",null,null,null,2750000,null,null,2750000]
[null,"Lake Worth High School Addition",null,4524000,{"$nulls":4},4524000]
[null,"New Elem School \"A\"","Jupiter Area Elem School",849040,{"$nulls":4},849040]
[null,"New Elem School \"B\"","Acreage Area Elem",1000000,{"$nulls":4},1000000]
[null,"New Elem School \"D\"","Elementary Holding School",12010540,{"$nulls":4},12010540]
[null,"New Elem School \"H\"","West Boca Raton Elem",1000000,{"$nulls":4},1000000]
[null,"New Elem School \"I\"","Boynton/Delray Area Elem",12093960,{"$nulls":4},12093960]
[null,"New Elem School \"J\"","Western Communities Elem",12142460,null," ",null,null,12142460]
[null,"New Elem School \"K\"","WPB Area Elem",1304838,{"$nulls":4},1304838]
[null,"New Elem School \"L\"","Wellington Area Elem",1000000,null," ",null,null,1000000]
[null,"New Elem School \"M\"","Boynton/Delray Area Elem",1000000," "," ",null,null,1000000]
[null,"New Elem School \"N\"","Pleasant City Area Elem",1320911,{"$nulls":4},1320911]
[null,"New Elem School \"Q\"","Acreage Area Elem",null,null,100000,12932920,null,13032920]
[null,"New High School \"EEE\"","West Boynton High",null,null,null,3295472,48629066,51924538]
[null,"New High School \"III\"","Boynton Beach High",1073074,{"$nulls":4},1073074]
[null,"New High School \"JJJ\"","Central WPB Area High",48760169," "," ",null,null,48760169]
[null,"Village Academy Secondary Level",null,100000,{"$nulls":4},100000]
[null,"New Mid School \"BB\"","Boynton/Delray Area Middle",1010690," "," ",null,null,1010690]
[null,"New Mid School \"DD\"","Lantana Middle Replacement",18531752,{"$nulls":4},18531752]
[null,"New Mid School \"EE\"","WPB Area Middle",1258533,18367011,1350000,null,null,20975544]
[null,"New Mid School \"FF\"","Jupiter Area Middle",1500000," "," ",null,null,1500000]
[null,"New Mid School \"GG\"","Boca Raton Area Middle",1201256,17719673,1100000,null,null,20020929]
[null,"New Mid School \"HH\"","Acreage Area Middle",null,100000,19246282,1195000,null,20541282]
[null,"New Mid School \"II\"","Mid/High Holding School",6905628,{"$nulls":4},6905628]
[null,"Palm Beach Public Modernization",null,201710,6792816,null,null,null,6994526]
[null,"Palm Springs Elementary Modernization",null,100000,{"$nulls":4},100000]
[null,"Roosevelt Elementary Modernization",null,100000,{"$nulls":4},100000]
[null,"South Olive Modernization",null,null,8007207,null,null,null,8007207]
[null,"U.B. Kinsey/Palmview Elem. Modernization",null,100000,{"$nulls":4},100000]
[null,"West Gate Elem - expand media;  12 new classrooms",null,2332228,{"$nulls":4},2332228]
["5.","Palm Beach County Total",0,158286889,165823394,138778019,77981006,118627056,659496364]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,null,null,0,0]
["6.","Palm Beach County Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["7.","Palm Beach County Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2000-01 ","2001-02 ","2002-03 ","2003-04 ","2004-05","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2000."]
[]
[null,"SCHOOL BOARD OF ","Palm Beach County  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}