{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","01_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"01_5YrWkPlan","index":1,"n_rows":1246,"n_cols":25,"rows_kept":1246,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Palm Beach County  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Palm Beach County   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2001, and all data accurate as of July 15, 2001.",{"$nulls":8},"2000-03-17",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Palm Beach County","Date: ==>","2001-10-01",null,"For fiscal years","  2001-2002 through 2005-2006"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"ADA Compliance","Various Schools",897000,933000,969000,1015000,900000,4714000]
[null,"Facilities Management Projects","Various Schools",null,50000,50000,50000,50000,200000]
[null,"Fire & Life Safety","Various Schools",1178000,1161000,1138000,1000000,1000000,5477000]
[null,"Health Clinic Compliance","Various Schools",500000,200000,100000,100000,100000,1000000]
[null,"Kitchen HVAC","Various Schools",1500000,{"$nulls":4},1500000]
[null,"Major Renov.&Systems Replmnt","Various Schools",10110000,10900000,10400000,10300000,9800000,51510000]
[null,"Minor Bldg Add./Space Renov.","Various Schools",6979000,6113000,6329000,6614000,6329000,32364000]
[null,"PECO Maintenance Projects","Various Schools",7412011,6341479,5855527,5674801,5690865,30974683]
[null,"Playground Replace/Resurfacing","Various Schools",1170000,350000,100000,100000,100000,1820000]
[null,"Portable Leasing","Various Schools",1300000,1000000,700000,500000,175000,3675000]
[null,"Portable Relocation","Various Schools",8000000,6400000,6100000,6100000,5800000,32400000]
[null,"Portable Replacement","Various Schools",7000000,7000000,7000000,7000000,null,28000000]
[null,"Roof Replacement","Various Schools",4560000,6726000,7291200,7291200,7297000,33165400]
[null,"Title 9 Gender Equity","Various Schools",250000,250000,100000,100000,100000,800000]
[null,"Traffic Improvements","Various Schools",650000,500000,500000,500000,500000,2650000]
[{"$nulls":8},0]
[null,"Maintenance, Repair, and Renovation Totals",null,51506011,47924479,46632727,46345001,37841865,230250083]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,7412011,6341479,5855527,5674801,5690865,30974683]
["1.","Palm Beach County Total",null,44094000,41583000,40777200,40670200,32151000,199275400]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Addison Mizner Elementary Remodeling",null,105965,0,0,null,null,105965]
[null,"Atlantic High School Modernization",null,2329480,45347887,1108680,null,null,48786047]
[null,"Auditoriums - High Schools",null,204750,3717500,3743250,3743250,3648750,15057500]
[null,"Belvedere Elementary Modernization",null,8656666,{"$nulls":4},8656666]
[null,"Boca Raton Elementary Modernization",null,362778,{"$nulls":4},362778]
[null,"Boca Raton High School Modernization",null,45589532,1000966,null,null,null,46590498]
[null,"Career Academies Modifications",null,2000000,{"$nulls":4},2000000]
[null,"Central Bus Compound",null,7778888,{"$nulls":4},7778888]
[null,"Conniston Middle School Modernization",null,1685617,385617,null,null,null,2071234]
[null,"Coral Sunset Elementary Addition",null,105000,2374113,null,null,null,2479113]
[null,"Dreyfoos SOA Addition",null,5637222,{"$nulls":4},5637222]
[null,"Forest Hill Elementary Modernization",null,454224,{"$nulls":4},454224]
[null,"Forest Hill High Modernization",null,119988,34648265,845080,null,null,35613333]
[null,"Future School Modernizations",null,null,31665608,109024423,78679735,49854973,269224739]
[null,"Greenacres Elementary Modernization",null,8442977,{"$nulls":4},8442977]
[null,"H. L. Watkins Middle School Modernization",null,2479050,18886895,462055,null,null,21828000]
[null,"Hammock Point Elementary Addition",null,105000,1217912,null,null,null,1322912]
[null,"John I Leonard High School Modernization",null,null,105000,3215985,51293768,null,54614753]
[null,"Jupiter Elementary Modernization",null,10166153,{"$nulls":4},10166153]
[null,"Jupiter High Modernization",null,3765574,1005575,null,null,null,4771149]
[null,"K-3 Class Size Reduction",null,356860,{"$nulls":4},356860]
[null,"Lake Park Elementary Modernization",null,481586,{"$nulls":4},481586]
[null,"Lake Worth High Addition - Phase 3",null,226200,{"$nulls":4},226200]
[null,"Lantana Middle Replacement",null,16308540,251057,null,null,null,16559597]
[null,"Needs Assessment",null,225000,{"$nulls":4},225000]
[null,"New Elementary School \"A\"","Jupiter Area Elementary",86358,{"$nulls":4},86358]
[null,"New Elementary School \"B\"","Frontier Elementary",59418,{"$nulls":4},59418]
[null,"New Elementary School \"D\"","Okeechobee Elementary",513838,{"$nulls":4},513838]
[null,"New  Elementary School \"H\"","Sunrise Park Elementary",52987,{"$nulls":4},52987]
[null,"New Elementary School \"I\"","Boynton/Delray Area Elementary",501923,{"$nulls":4},501923]
[null,"New Elementary School \"J\"","Western Communities Elementary",501448,{"$nulls":4},501448]
[null,"New Elementary School \"K\"","W Palm Beach Area Elementary",508886,{"$nulls":4},508886]
[null,"New Elementary School \"L\"","Discovery Key Elementary",48123,{"$nulls":4},48123]
[null,"New Elementary School \"M\"","Boynton/Delray Area Elementary",485904,{"$nulls":4},485904]
[null,"New Elementary School \"N\"","Pleasant City Elementary",441100,{"$nulls":4},441100]
[null,"New Elementary School \"Q\"","Acreage Area Elementary",null,11968344,null,null,null,11968344]
[null,"New Elementary School \"R\"","West Lake Worth/Lantana Elementary",null,11968344,null,null,null,11968344]
[null,"New High School \"EEE\"","West Boynton High",1575000,48596714,1039432,null,null,51211146]
[null,"New High School \"III\"","Boynton Beach High ",208445,{"$nulls":4},208445]
[null,"New High School \"JJJ\"","Central WPB Area High",4065814,1045814,null,null,null,5111628]
[null,"New High School \"LLL\"","West Boca/Delray Area High",1575000,48596714,1039432,null,null,51211146]
[null,"New Middle School \"BB\"","Odyssey Community Middle",155833,{"$nulls":4},155833]
[null,"New Middle School \"EE\"","West Palm Beach Area Middle",21694192,431566,null,null,null,22125758]
[null,"New Middle School \"FF\"","Jupiter Area Middle",598930,132977,null,null,null,731907]
[null,"New Middle School \"GG\"","Boca Raton Area Middle",60063,19149236,369615,null,null,19578914]
[null,"New Middle School \"HH\"","Acreage Area Middle",105000,20321569,398209,null,null,20824778]
[null,"New Middle School \"II\"","Western Lake Worth Area Middle",1355120,20524715,505481,null,null,22385316]
[null,"Palm Beach Public Modernization",null,6748260,{"$nulls":4},6748260]
[null,"Palm Springs Elementary Modernization",null,556250,10959950,null,null,null,11516200]
[null,"Palmetto Elementary Modernization",null,692957,{"$nulls":4},692957]
[null,"Roosevelt Elementary Modernization",null,556250,10946598,null,null,null,11502848]
[null,"S.D. Spady Elementary Addition",null,105000,{"$nulls":4},105000]
[null,"South Olive Elementary Modernization",null,10233451,{"$nulls":4},10233451]
[null,"Stadiums - High Schools",null,735000,2205000,2940000,null,735000,6615000]
[null,"U.B.Kinsey/Palmview Elem Modernization",null,7351678,{"$nulls":4},7351678]
[null,"Village Academy Secondary Level",null,5000,{"$nulls":4},5000]
[null,"West Gate Elementary Modernization",null,343707,{"$nulls":4},343707]
[null,"Wm. T. Dwyer High School Classroom Addition",null,4946553,{"$nulls":4},4946553]
["2 .","Palm Beach County Total",null,184454538,347453936,124691642,133716753,54238723,844555592]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2000-01 FISH Satisfactory","Actual 2000-01","Actual 2000-01","Actual 2000-01","New Stu Capacity to","Projected 2005-06","Projected 2005-06"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Acreage Pines Elementary",1573,1573,1511,0.96,-811,759,1]
[null,"Addison Mizner Elementary",909,909,884,0.97,-177,715,0.98]
[null,"Allamanda Elementary",851,851,851,1,0,552,0.65]
[null,"Banyan Creek Elementary",1317,1317,998,0.76,-540,736,0.95]
[null,"Barton Elementary",1116,1116,698,0.63,-327,761,0.96]
[null,"Belle Glade Elementary",1045,1045,734,0.7,-25,737,0.72]
[null,"Belvedere Elementary",758,758,568,0.75,-173,521,0.89]
[null,"Berkshire Elementary",1063,1063,910,0.86,-391,681,1.01]
[null,"Binks Forest Elementary",1000,1000,1041,1.04,25,1026,1]
[null,"Boca Raton Elementary",475,475,345,0.73,15,404,0.82]
[null,"Calusa Elementary",839,839,490,0.58,-60,685,0.88]
[null,"Citrus Cove Elementary",1593,1593,1473,0.92,-769,814,0.99]
[null,"Coral Reef Elementary",1000,1000,1043,1.04,0,850,0.85]
[null,"Coral Sunset Elementary",1132,1132,945,0.83,-260,1022,1.17]
[null,"Crystal Lakes Elementary",1003,1003,967,0.96,-138,845,0.98]
[null,"Cypress Trails Elementary",943,943,896,0.95,-153,784,0.99]
[null,"C.O.Taylor/Kirklane Elementary",1230,1230,1147,0.93,-357,808,0.93]
[null,"Del Prado Elementary",1293,1293,1285,0.99,-526,769,1]
[null,"Dr. Mary McLeod Bethune Elem.",970,970,723,0.75,0,897,0.92]
[null,"D.D. Eisenhower Elementary",950,950,442,0.47,-19,657,0.71]
[null,"Egret Lake Elementary",934,934,877,0.94,-149,753,0.96]
[null,"Forest Hill Elementary",1207,1207,1118,0.93,-499,1006,1.42]
[null,"Forest Park Elementary",986,986,604,0.61,-327,658,1]
[null,"Galaxy Elementary",765,765,701,0.92,-132,614,0.97]
[null,"Glade View Elementary",968,968,497,0.51,0,513,0.53]
[null,"Golden Grove Elementary",1172,1172,1059,0.9,-112,1070,1.01]
[null,"Gove Elementary",1293,1293,745,0.58,0,794,0.61]
[null,"Greenacres Elementary",753,753,575,0.76,-54,589,0.84]
[null,"Grove Park Elementary",823,823,830,1.01,-41,769,0.98]
[null,"Hagen Road Elementary",736,736,513,0.7,-23,656,0.92]
[null,"Hammock Pointe Elementary",919,919,915,1,-144,902,1.16]
[null,"Heritage Elementary",992,992,"-",0,0,962,0.97]
[null,"Highland Elementary",848,848,782,0.92,0,784,0.92]
[null,"H.L. Johnson Elementary",1460,1460,1156,0.79,-659,805,1]
[null,"Indian Pines Elementary",1026,1026,951,0.93,-257,740,0.96]
[null,"Jerry Thomas Elementary",853,853,849,1,-38,813,1]
[null,"Jupiter Elementary",723,723,496,0.69,0,678,0.94]
[null,"Jupiter Farms Elementary",783,783,803,1.03,75,854,1]
[null,"J.C. Mitchell Elementary",883,883,670,0.76,-104,747,0.96]
[null,"K.E.C./Canal Point Elementary",904,904,630,0.7,0,578,0.64]
[null,"Lake Park Elementary",599,599,606,1.01,-205,460,1.17]
[null,"Lantana Elementary",680,680,695,1.02,-25,603,0.92]
[null,"Liberty Park Elementary",1439,1439,1274,0.89,-637,759,0.95]
[null,"Lighthouse Elementary",1349,1349,1237,0.92,-546,778,0.97]
[null,"Limestone Creek Elementary",1026,1026,1018,0.99,-134,844,0.95]
[null,"Lincoln Elementary",1200,1200,803,0.67,0,1007,0.84]
[null,"Loxahatchee Groves Elementary",908,908,776,0.85,-135,724,0.94]
[null,"Manatee Elementary",1165,1165,1223,1.05,-187,974,1]
[null,"Meadow Park Elementary",797,797,611,0.77,-129,654,0.98]
[null,"Melaleuca Elementary",1101,1101,1012,0.92,-267,823,0.99]
[null,"Morikami Park Elementary",1025,1025,1002,0.98,0,1000,0.98]
[null,"New Horizons Elementary",750,750,700,0.93,0,736,0.98]
[null,"North Grade Elementary",829,829,572,0.69,0,717,0.86]
[null,"North Palm Beach Elementary",834,834,523,0.63,0,440,0.53]
[null,"Northboro Elementary",1084,1084,692,0.64,-196,807,0.91]
[null,"Northmore Elementary",880,880,564,0.64,0,578,0.66]
[null,"Orchard View Elementary",1034,1034,921,0.89,0,894,0.86]
[null,"Pahokee Elementary",869,869,679,0.78,-173,649,0.93]
[null,"Palm Beach Gardens Elementary",757,757,676,0.89,-99,626,0.95]
[null,"Palm Beach Public Elementary",435,435,385,0.89,0,370,0.85]
[null,"Palm Springs Elementary",828,828,671,0.81,142,934,0.96]
[null,"Palmetto Elementary",861,861,588,0.68,109,714,0.74]
[null,"Panther Run Elementary",1435,1435,1483,1.03,-595,829,0.99]
[null,"Pine Grove Elementary",1108,1108,678,0.61,-376,659,0.9]
[null,"Pioneer Park Elementary",1045,1045,657,0.63,0,675,0.65]
[null,"Plumosa Elementary",708,708,598,0.84,-37,621,0.93]
[null,"Poinciana Elementary",922,922,701,0.76,0,744,0.81]
[null,"Rolling Green Elementary",1173,1173,850,0.72,-546,617,0.98]
[null,"Roosevelt Elementary",1185,1185,963,0.81,-389,832,1.05]
[null,"Rosenwald Elementary",797,797,419,0.53,0,427,0.54]
[null,"Sandpiper Shores Elementary",1311,1311,1235,0.94,-471,839,1]
[null,"Seminole Trails Elementary",943,943,813,0.86,-117,748,0.91]
[null,"South Grade Elementary",793,793,789,0.99,75,868,1]
[null,"South Olive Elementary",1021,1021,916,0.9,-339,629,0.92]
[null,"Starlight Cove Elementary",1153,1153,883,0.77,-188,890,0.92]
[null,"S.D. Spady Elementary",709,709,502,0.71,-243,620,1.33]
[null,"Timber Trace Elementary",999,999,723,0.72,-174,763,0.92]
[null,"U.B. Kinsey/Palmview Elementary",876,876,618,0.71,-159,590,0.82]
[null,"Verde Elementary",856,856,727,0.85,-97,700,0.92]
[null,"Village Academy",487,487,223,0.46,0,450,0.92]
[null,"Washington Elementary",712,712,557,0.78,-65,629,0.97]
[null,"Waters Edge Elementary",1050,1050,784,0.75,100,1142,0.99]
[null,"Wellington Elementary",1041,1041,977,0.94,-107,948,1.01]
[null,"West Gate Elementary",866,866,684,0.79,104,752,0.78]
[null,"West Riviera Elementary",1086,1086,658,0.61,-221,857,0.99]
[null,"Westward Elementary",873,873,686,0.79,-82,787,0.99]
[null,"Whispering Pines Elementary",1202,1202,904,0.75,-377,807,0.98]
[null,"Wynnebrook Elementary",1132,1132,1026,0.91,-427,631,0.9]
[null,"Bear Lakes Middle",2145,1930,1477,0.77,-746,1136,0.96]
[null,"Boca Raton Middle",1623,1460,1196,0.82,-244,1070,0.88]
[null,"Carver Middle",2116,1904,1702,0.89,-527,1350,0.98]
[null,"Christa McAuliffe Middle",1759,1583,1477,0.93,-315,1260,0.99]
[null,"Congress Middle",1891,1701,1415,0.83,-357,1334,0.99]
[null,"Conniston Middle",1349,1214,934,0.77,-44,889,0.76]
[null,"Crestwood Middle",1935,1741,1439,0.83,-417,1292,0.98]
[null,"Eagles Landing Middle",1830,1647,1396,0.85,-317,1245,0.94]
[null,"H.L. Watkins Middle",1483,1334,1429,1.07,-269,883,0.83]
[null,"Jefferson Davis Middle",1988,1789,1622,0.91,-391,1274,0.91]
[null,"Jupiter Middle",2008,1807,1621,0.9,-486,1326,1]
[null,"J.F. Kennedy Middle",1964,1767,1441,0.82,-540,1011,0.82]
[null,"Lake Shore Middle",1662,1496,1227,0.82,0,1220,0.82]
[null,"Lake Worth Middle",2179,1961,1505,0.77,-733,1014,0.83]
[null,"Lantana Middle",1024,921,845,0.92,-420,749,1.5]
[null,"Loggers Run Middle",1747,1572,1371,0.87,-356,1129,0.93]
[null,"Middle School of the Arts",1863,1676,1232,0.74,-711,1200,1.24]
[null,"Okeeheelee Middle",1929,1736,1599,0.92,-458,1273,1]
[null,"Omni Middle",1696,1526,1263,0.83,-275,1236,0.99]
[null,"Polo Park Middle",1459,1313,956,0.73,50,1380,1.01]
[null,"Roosevelt Middle",1726,1553,1519,0.98,-202,1269,0.94]
[null,"Watson B. Duncan Middle",1717,1545,1494,0.97,-356,1006,0.85]
[null,"Wellington Landings Middle",1695,1525,1503,0.99,-394,1100,0.97]
[null,"Western Pines Middle",1733,1559,1503,0.96,-218,1244,0.93]
[null,"Woodlands Middle",1901,1710,1717,1,-267,1350,0.94]
[null,"Atlantic High",2522,2395,2911,1.22,-667,1884,1.09]
[null,"Boca Raton High",2408,2287,1867,0.82,-271,1796,0.89]
[null,"Dreyfoos School of the Arts",1474,1326,1270,0.96,0,1220,0.92]
[null,"Forest Hill High",1820,1729,1591,0.92,-60,1860,1.11]
[null,"Glades Central High",1710,1624,1398,0.86,-28,1268,0.79]
[null,"Inlet Grove High",812,974,261,0.27,226,1200,1]
[null,"Jupiter High",2706,2570,1709,0.66,0,2349,0.91]
[null,"J.I. Leonard High",2972,2823.4,3049,1.08,-207,2626,1]
[null,"Lake Worth High",3536,3359,3031,0.9,-575,2742,0.98]
[null,"Olympic Heights High",2931,2784,2608,0.94,-256,2536,1]
[null,"Pahokee Mid./Sr. High",1480,1332,1089,0.82,-24,941,0.72]
[null,"Palm Beach Gardens High",2496,2371,2475,1.04,-142,2193,0.98]
[null,"Palm Beach Lakes High",3210,3049,2842,0.93,-281,2768,1]
[null,"Royal Palm Beach High",2625,2493,2448,0.98,100,2671,1.03]
[null,"Santaluces High",4069,3865,3612,0.93,-1377,2299,0.92]
[null,"South Tech",1048,1257,403,0.32,343,1600,1]
[null,"Spanish River High",3301,3135,3270,1.04,-682,2454,1]
[null,"Suncoast High",1164,989,1287,1.3,0,1225,1.24]
[null,"Wellington High",3062,2908,3094,1.06,-319,2587,1]
[null,"West Tech",769,922,214,0.23,118,1040,1]
[null,"Wm. T. Dwyer High",2148,2040,2132,1.05,-98,2234,1.15]
[null,"Adult Education Center",688,1032,55,0.05,0,66.91590963200001,0.06]
[null,"Cypress Hammock School",0,0,0,0,0,66,0]
[null,"Delray Full Service Center",1243,1118,105,0.09,0,126,0.11]
[null,"Gold Coast Community School",367,367,296,0.81,0,350,0.95]
[null,"Indian Ridge School",151,151,120,0.79,0,120,0.79]
[null,"So. Area Middle School of Choice",392,392,68,0.17,0,100,0.26]
[null,"Roosevelt Service Center",615,615,110,0.18,0,150,0.24]
[null,"Royal Palm School",330,330,200,0.61,0,250,0.76]
[null,"Sabal Palm School(High Ridge)",78,78,42,0.54,0,50,0.64]
[null,"School of Choice",636,636,74,0.12,0,100,0.16]
["2a.","Palm Beach County Total",183206,176942.4,148518,0.84,-27556,137564.915909632,0.92]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School \"D\" (970 Stu Sta) Benoist Farms Rd. and Okeechobee Blvd., West Palm Beach to accommodate growth."]
[null,"New Elementary School \"I\" (970 Stu Sta) Congress Avenue, Boynton Beach to accommodate growth."]
[null,"New Elementary School \"J\" (970) Folsom Rd. and Okeechobee Blvd., Royal Palm Beach to accommodate growth."]
[null,"New Elementary School \"K\" (970) Dillman Rd. Ext., Greenacres to accommodate growth."]
[null,"New Elementary School \"M\" (970) Hypoluxo Rd., Boynton Beach to accommodate growth."]
[null,"New Elementary School \"N\" (490) Pleasant City area, West Palm Beach to accommodate growth."]
[null,"New Elementary School \"Q\" (970 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New Elementary School \"R\" (770 Stu Sta) in the western Lake Worth/Lantana area to accommodate growth."]
[null,"New Middle School \"EE\" (1444 Stu Sta) in the West Palm Beach area to accommodate growth."]
[null,"New Middle School \"FF\" (1444 Stu Sta) in the Abacoa community of Jupiter to accommodate growth."]
[null,"New Middle School \"GG\" (1111 Stu Sta) in the Boca Raton area to accommodate growth."]
[null,"New Middle School \"HH\" (1111 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New Middle School \"II\" (1449 Stu Sta) in the western Lake Worth area to accommodate growth."]
[null,"New High School \"EEE\" (1894 Stu Sta) Jog Road in the western Boynton Beach area to accommodate growth."]
[null,"New High School \"LLL\" (1894 Stu Sta) in the west Boca Raton/Delray Beach area to accommodate growth."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2000-01","Owner","Student Stations","as classroom space","in 2005-06","units by 2005-06","Column \"C\""]
[null,"Acreage Pines Elementary",32,"PBCSD/Leased",811,0,0,32,0]
[null,"Addison Mizner Elementary",10,"PBCSD/Leased",252,0,3,7,0]
[null,"Allamanda Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Banyan Creek Elementary",24,"PBCSD/Leased",540,0,0,24,0]
[null,"Barton Elementary",19,"PBCSD/Leased",377,0,11,8,0]
[null,"Belle Glade Elementary",1,"PBCSD/Leased",25,0,1,0,0]
[null,"Belvedere Elementary",8,"PBCSD/Leased",173,0,0,8,0]
[null,"Berkshire Elementary",19,"PBCSD/Leased",391,4,0,19,0]
[null,"Binks Forest Elementary",0,"PBCSD/Leased",0,0,1,-1,0]
[null,"Boca Raton Elementary",13,"PBCSD/Leased",250,0,0,13,0]
[null,"Calusa Elementary",2,"PBCSD/Leased",60,0,2,0,0]
[null,"Citrus Cove Elementary",34,"PBCSD/Leased",819,0,2,32,0]
[null,"Coral Reef Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Coral Sunset Elementary",15,"PBCSD/Leased",335,1,3,12,0]
[null,"Crystal Lakes Elementary",9,"PBCSD/Leased",213,0,3,6,0]
[null,"Cypress Trails Elementary",6,"PBCSD/Leased",153,0,0,6,0]
[null,"C.O.Taylor/Kirklane Elementary",20,"PBCSD/Leased",357,5,0,20,0]
[null,"Del Prado Elementary",22,"PBCSD/Leased",526,0,0,22,0]
[null,"Dr. Mary McLeod Bethune Elem.",0,"PBCSD/Leased",0,0,0,0,0]
[null,"D.D. Eisenhower Elementary",5,"PBCSD/Leased",49,0,3,2,0]
[null,"Egret Lake Elementary",6,"PBCSD/Leased",149,0,0,6,0]
[null,"Forest Hill Elementary",25,"PBCSD/Leased",524,1,1,24,0]
[null,"Forest Park Elementary",16,"PBCSD/Leased",377,1,2,14,0]
[null,"Galaxy Elementary",5,"PBCSD/Leased",132,0,0,5,0]
[null,"Glade View Elementary",19,"PBCSD/Leased",305,1,11,8,0]
[null,"Golden Grove Elementary",6,"PBCSD/Leased",162,0,2,4,0]
[null,"Gove Elementary",21,"PBCSD/Leased",486,1,13,8,0]
[null,"Greenacres Elementary",4,"PBCSD/Leased",54,0,0,4,0]
[null,"Grove Park Elementary",5,"PBCSD/Leased",116,0,3,2,0]
[null,"Hagen Road Elementary",2,"PBCSD/Leased",23,0,2,0,0]
[null,"Hammock Pointe Elementary",6,"PBCSD/Leased",144,0,0,6,0]
[null,"Heritage Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Highland Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"H.L. Johnson Elementary",30,"PBCSD/Leased",659,0,0,30,0]
[null,"Indian Pines Elementary",12,"PBCSD/Leased",257,1,0,12,0]
[null,"Jerry Thomas Elementary",3,"PBCSD/Leased",63,0,1,2,0]
[null,"Jupiter Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Jupiter Farms Elementary",0,"PBCSD/Leased",0,0,3,-3,0]
[null,"J.C. Mitchell Elementary",7,"PBCSD/Leased",104,2,0,7,0]
[null,"K.E.C./Canal Point Elementary",6,"PBCSD/Leased",107,0,0,6,0]
[null,"Lake Park Elementary",9,"PBCSD/Leased",205,0,0,9,0]
[null,"Lantana Elementary",2,"PBCSD/Leased",25,0,0,2,0]
[null,"Liberty Park Elementary",30,"PBCSD/Leased",637,0,0,30,0]
[null,"Lighthouse Elementary",22,"PBCSD/Leased",571,0,1,21,0]
[null,"Limestone Creek Elementary",8,"PBCSD/Leased",209,0,3,5,0]
[null,"Lincoln Elementary",2,"PBCSD/Leased",47,0,2,0,0]
[null,"Loxahatchee Groves Elementary",7,"PBCSD/Leased",135,0,7,0,0]
[null,"Manatee Elementary",9,"PBCSD/Leased",187,1,0,9,0]
[null,"Meadow Park Elementary",8,"PBCSD/Leased",154,0,1,7,0]
[null,"Melaleuca Elementary",14,"PBCSD/Leased",292,1,1,13,0]
[null,"Morikami Park Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"New Horizons Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"North Grade Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"North Palm Beach Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Northboro Elementary",12,"PBCSD/Leased",196,3,12,0,0]
[null,"Northmore Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Orchard View Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Pahokee Elementary",11,"PBCSD/Leased",173,3,0,11,0]
[null,"Palm Beach Gardens Elementary",5,"PBCSD/Leased",99,0,0,5,0]
[null,"Palm Beach Public Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Palm Springs Elementary",14,"PBCSD/Leased",234,0,0,14,0]
[null,"Palmetto Elementary",33,"PBCSD/Leased",620,3,0,33,0]
[null,"Panther Run Elementary",30,"PBCSD/Leased",645,2,2,28,0]
[null,"Pine Grove Elementary",15,"PBCSD/Leased",376,0,9,6,0]
[null,"Pioneer Park Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Plumosa Elementary",3,"PBCSD/Leased",37,0,0,3,0]
[null,"Poinciana Elementary",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Rolling Green Elementary",22,"PBCSD/Leased",571,0,1,21,0]
[null,"Roosevelt Elementary",20,"PBCSD/Leased",389,0,0,20,0]
[null,"Rosenwald Elementary",5,"PBCSD/Leased",119,0,5,0,0]
[null,"Sandpiper Shores Elementary",22,"PBCSD/Leased",521,2,2,20,0]
[null,"Seminole Trails Elementary",9,"PBCSD/Leased",117,0,0,9,0]
[null,"South Grade Elementary",0,"PBCSD/Leased",0,0,3,-3,0]
[null,"South Olive Elementary",17,"PBCSD/Leased",339,1,0,17,0]
[null,"Starlight Cove Elementary",7,"PBCSD/Leased",188,0,7,0,0]
[null,"S.D. Spady Elementary",12,"PBCSD/Leased",268,0,1,11,0]
[null,"Timber Trace Elementary",7,"PBCSD/Leased",174,0,0,7,0]
[null,"U.B. Kinsey/Palmview Elementary",7,"PBCSD/Leased",159,0,0,7,0]
[null,"Verde Elementary",5,"PBCSD/Leased",97,0,0,5,0]
[null,"Village Academy",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Washington Elementary",6,"PBCSD/Leased",140,0,6,0,0]
[null,"Waters Edge Elementary",0,"PBCSD/Leased",0,0,4,-4,0]
[null,"Wellington Elementary",12,"PBCSD/Leased",107,5,0,12,0]
[null,"West Gate Elementary",26,"PBCSD/Leased",496,0,0,26,0]
[null,"West Riviera Elementary",12,"PBCSD/Leased",246,0,4,8,0]
[null,"Westward Elementary",7,"PBCSD/Leased",132,0,7,0,0]
[null,"Whispering Pines Elementary",17,"PBCSD/Leased",377,0,6,11,0]
[null,"Wynnebrook Elementary",22,"PBCSD/Leased",427,3,0,22,0]
[null,"Bear Lakes Middle",33,"PBCSD/Leased",829,0,0,33,0]
[null,"Boca Raton Middle",17,"PBCSD/Leased",271,4,13,4,0]
[null,"Carver Middle",25,"PBCSD/Leased",586,0,0,25,0]
[null,"Christa McAuliffe Middle",15,"PBCSD/Leased",377,0,1,14,0]
[null,"Congress Middle",17,"PBCSD/Leased",397,0,0,17,0]
[null,"Conniston Middle",4,"PBCSD/Leased",49,1,0,4,0]
[null,"Crestwood Middle",26,"PBCSD/Leased",602,0,5,21,0]
[null,"Eagles Landing Middle",13,"PBCSD/Leased",352,0,0,13,0]
[null,"H.L. Watkins Middle",16,"PBCSD/Leased",300,3,0,16,0]
[null,"Jefferson Davis Middle",26,"PBCSD/Leased",435,8,0,26,0]
[null,"Jupiter Middle",27,"PBCSD/Leased",568,3,1,26,0]
[null,"J.F. Kennedy Middle",24,"PBCSD/Leased",600,0,0,24,0]
[null,"Lake Shore Middle",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Lake Worth Middle",36,"PBCSD/Leased",814,0,0,36,0]
[null,"Lantana Middle",17,"PBCSD/Leased",467,0,0,17,0]
[null,"Loggers Run Middle",16,"PBCSD/Leased",395,0,0,16,0]
[null,"Middle School of the Arts",29,"PBCSD/Leased",791,0,0,29,0]
[null,"Okeeheelee Middle",19,"PBCSD/Leased",509,0,0,19,0]
[null,"Omni Middle",16,"PBCSD/Leased",305,1,0,16,0]
[null,"Polo Park Middle",0,"PBCSD/Leased",0,0,2,-2,0]
[null,"Roosevelt Middle",8,"PBCSD/Leased",224,0,0,8,0]
[null,"Watson B. Duncan Middle",17,"PBCSD/Leased",395,0,0,17,0]
[null,"Wellington Landings Middle",16,"PBCSD/Leased",438,0,0,16,0]
[null,"Western Pines Middle",9,"PBCSD/Leased",243,0,0,9,0]
[null,"Woodlands Middle",11,"PBCSD/Leased",297,0,0,11,0]
[null,"Atlantic High",31,"PBCSD/Leased",703,6,0,31,0]
[null,"Boca Raton High",12,"PBCSD/Leased",285,0,0,12,0]
[null,"Dreyfoos School of the Arts",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Forest Hill High",13,"PBCSD/Leased",142,4,3,10,0]
[null,"Glades Central High",2,"PBCSD/Leased",30,0,2,0,0]
[null,"Inlet Grove High",10,"PBCSD/Leased",237,1,10,0,0]
[null,"Jupiter High",0,"PBCSD/Leased",0,0,0,0,0]
[null,"J.I. Leonard High",9,"PBCSD/Leased",218,0,0,9,0]
[null,"Lake Worth High",41,"PBCSD/Leased",1085,3,0,41,0]
[null,"Olympic Heights High",9,"PBCSD/Leased",270,0,0,9,0]
[null,"Pahokee Mid./Sr. High",1,"PBCSD/Leased",26,0,1,0,0]
[null,"Palm Beach Gardens High",5,"PBCSD/Leased",149,0,0,5,0]
[null,"Palm Beach Lakes High",16,"PBCSD/Leased",480,0,7,9,0]
[null,"Royal Palm Beach High",0,"PBCSD/Leased",0,0,4,-4,0]
[null,"Santaluces High",52,"PBCSD/Leased",1450,1,0,52,0]
[null,"South Tech",20,"PBCSD/Leased",464,1,20,0,0]
[null,"Spanish River High",27,"PBCSD/Leased",797,0,3,24,0]
[null,"Suncoast High",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Wellington High",15,"PBCSD/Leased",389,2,2,13,0]
[null,"West Tech",12,"PBCSD/Leased",353,0,12,0,0]
[null,"Wm. T. Dwyer High",5,"PBCSD/Leased",103,0,0,5,0]
[null,"Adult Education Center",8,"PBCSD/Leased",209,0,8,0,0]
[null,"Cypress Hammock School",0,"PBCSD/Leased",0,0,0,0,0]
[null,"Delray Full Service Center",5,"PBCSD/Leased",112,0,5,0,0]
[null,"Gold Coast Community School",5,"PBCSD/Leased",88,1,5,0,0]
[null,"Indian Ridge School",9,"PBCSD/Leased",70,0,9,0,0]
[null,"So. Area Middle School of Choice",15,"PBCSD/Leased",293,0,15,0,0]
[null,"Roosevelt Service Center",1,"PBCSD/Leased",15,0,1,0,0]
[null,"Royal Palm School",5,"PBCSD/Leased",50,0,5,0,0]
[null,"Sabal Palm School(High Ridge)",6,"PBCSD/Leased",0,6,6,0,0]
[null,"School of Choice",4,"PBCSD/Leased",90,0,4,0,0]
["2c1.","Palm Beach County Total",1656,null,37054,86,295,1361,"Avg Age 0"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"Acreage Pines Elementary",32,26,0,0,6,0,32]
[null,"Addison Mizner Elementary",7,1,5,1,0,0,7]
[null,"Allamanda Elementary",0,0,0,0,0,0,0]
[null,"Banyan Creek Elementary",24,13,8,3,0,0,24]
[null,"Barton Elementary",8,8,0,0,0,0,8]
[null,"Belle Glade Elementary",0,0,0,0,0,0,0]
[null,"Belvedere Elementary",8,0,2,6,0,0,8]
[null,"Berkshire Elementary",19,0,5,2,0,12,19]
[null,"Binks Forest Elementary",0,0,0,0,0,0,0]
[null,"Boca Raton Elementary",13,13,0,0,0,0,13]
[null,"Calusa Elementary",0,0,0,0,0,0,0]
[null,"Citrus Cove Elementary",32,0,24,2,6,0,32]
[null,"Coral Reef Elementary",0,0,0,0,0,0,0]
[null,"Coral Sunset Elementary",12,0,0,0,12,0,12]
[null,"Crystal Lakes Elementary",6,0,3,3,0,0,6]
[null,"Cypress Trails Elementary",6,0,3,3,0,0,6]
[null,"C.O.Taylor/Kirklane Elementary",20,0,0,0,20,0,20]
[null,"Del Prado Elementary",22,20,2,0,0,0,22]
[null,"Dr. Mary McLeod Bethune Elem.",0,0,0,0,0,0,0]
[null,"D.D. Eisenhower Elementary",2,0,2,0,0,0,2]
[null,"Egret Lake Elementary",6,0,0,0,2,4,6]
[null,"Forest Hill Elementary",24,0,4,20,0,0,24]
[null,"Forest Park Elementary",14,6,5,3,0,0,14]
[null,"Galaxy Elementary",5,0,3,2,0,0,5]
[null,"Glade View Elementary",8,8,0,0,0,0,8]
[null,"Golden Grove Elementary",4,0,0,0,4,0,4]
[null,"Gove Elementary",8,0,8,0,0,0,8]
[null,"Greenacres Elementary",4,0,0,4,0,0,4]
[null,"Grove Park Elementary",2,0,2,0,0,0,2]
[null,"Hagen Road Elementary",0,0,0,0,0,0,0]
[null,"Hammock Pointe Elementary",6,0,0,0,6,0,6]
[null,"Heritage Elementary",0,0,0,0,0,0,0]
[null,"Highland Elementary",0,0,0,0,0,0,0]
[null,"H.L. Johnson Elementary",30,0,25,5,0,0,30]
[null,"Indian Pines Elementary",12,0,0,0,10,2,12]
[null,"Jerry Thomas Elementary",2,0,0,0,2,0,2]
[null,"Jupiter Elementary",0,0,0,0,0,0,0]
[null,"Jupiter Farms Elementary",0,0,0,0,0,0,0]
[null,"J.C. Mitchell Elementary",7,0,4,3,0,0,7]
[null,"K.E.C./Canal Point Elementary",6,6,0,0,0,0,6]
[null,"Lake Park Elementary",9,9,0,0,0,0,9]
[null,"Lantana Elementary",2,0,0,2,0,0,2]
[null,"Liberty Park Elementary",30,0,14,8,8,0,30]
[null,"Lighthouse Elementary",21,21,0,0,0,0,21]
[null,"Limestone Creek Elementary",5,0,0,5,0,0,5]
[null,"Lincoln Elementary",0,0,0,0,0,0,0]
[null,"Loxahatchee Groves Elementary",0,0,0,0,0,0,0]
[null,"Manatee Elementary",9,0,6,0,3,0,9]
[null,"Meadow Park Elementary",7,0,0,0,7,0,7]
[null,"Melaleuca Elementary",13,0,0,0,9,4,13]
[null,"Morikami Park Elementary",0,0,0,0,0,0,0]
[null,"New Horizons Elementary",0,0,0,0,0,0,0]
[null,"North Grade Elementary",0,0,0,0,0,0,0]
[null,"North Palm Beach Elementary",0,0,0,0,0,0,0]
[null,"Northboro Elementary",3,0,0,3,0,0,3]
[null,"Northmore Elementary",0,0,0,0,0,0,0]
[null,"Orchard View Elementary",0,0,0,0,0,0,0]
[null,"Pahokee Elementary",11,11,0,0,0,0,11]
[null,"Palm Beach Gardens Elementary",5,0,5,0,0,0,5]
[null,"Palm Beach Public Elementary",0,0,0,0,0,0,0]
[null,"Palm Springs Elementary",14,0,0,0,14,0,14]
[null,"Palmetto Elementary",33,0,0,33,0,0,33]
[null,"Panther Run Elementary",28,6,2,0,20,0,28]
[null,"Pine Grove Elementary",6,6,0,0,0,0,6]
[null,"Pioneer Park Elementary",0,0,0,0,0,0,0]
[null,"Plumosa Elementary",3,0,3,0,0,0,3]
[null,"Poinciana Elementary",0,0,0,0,0,0,0]
[null,"Rolling Green Elementary",21,8,10,3,0,0,21]
[null,"Roosevelt Elementary",20,0,0,0,20,0,20]
[null,"Rosenwald Elementary",0,0,0,0,0,0,0]
[null,"Sandpiper Shores Elementary",20,18,2,0,0,0,20]
[null,"Seminole Trails Elementary",9,0,2,1,6,0,9]
[null,"South Grade Elementary",0,0,0,0,0,0,0]
[null,"South Olive Elementary",17,0,0,17,0,0,17]
[null,"Starlight Cove Elementary",0,0,0,0,0,0,0]
[null,"S.D. Spady Elementary",11,0,0,0,11,0,11]
[null,"Timber Trace Elementary",7,2,3,2,0,0,7]
[null,"U.B. Kinsey/Palmview Elementary",7,0,0,7,0,0,7]
[null,"Verde Elementary",5,0,4,1,0,0,5]
[null,"Village Academy",0,0,0,0,0,0,0]
[null,"Washington Elementary",0,0,0,0,0,0,0]
[null,"Waters Edge Elementary",0,0,0,0,0,0,0]
[null,"Wellington Elementary",12,0,2,8,2,0,12]
[null,"West Gate Elementary",26,0,26,0,0,0,26]
[null,"West Riviera Elementary",8,8,0,0,0,0,8]
[null,"Westward Elementary",0,0,0,0,0,0,0]
[null,"Whispering Pines Elementary",11,7,4,0,0,0,11]
[null,"Wynnebrook Elementary",22,0,0,0,16,6,22]
[null,"Bear Lakes Middle",33,0,0,0,20,13,33]
[null,"Boca Raton Middle",4,0,0,4,0,0,4]
[null,"Carver Middle",25,18,7,0,0,0,25]
[null,"Christa McAuliffe Middle",14,0,0,0,11,3,14]
[null,"Congress Middle",17,4,0,0,9,4,17]
[null,"Conniston Middle",4,0,0,4,0,0,4]
[null,"Crestwood Middle",21,0,0,12,9,0,21]
[null,"Eagles Landing Middle",13,0,0,0,9,4,13]
[null,"H.L. Watkins Middle",16,0,6,10,0,0,16]
[null,"Jefferson Davis Middle",26,0,0,6,20,0,26]
[null,"Jupiter Middle",26,0,20,6,0,0,26]
[null,"J.F. Kennedy Middle",24,11,8,5,0,0,24]
[null,"Lake Shore Middle",0,0,0,0,0,0,0]
[null,"Lake Worth Middle",36,0,0,0,28,8,36]
[null,"Lantana Middle",17,0,0,17,0,0,17]
[null,"Loggers Run Middle",16,0,0,0,11,5,16]
[null,"Middle School of the Arts",29,0,0,0,0,29,29]
[null,"Okeeheelee Middle",19,0,0,9,10,0,19]
[null,"Omni Middle",16,0,0,0,16,0,16]
[null,"Polo Park Middle",0,0,0,0,0,0,0]
[null,"Roosevelt Middle",8,0,0,0,6,2,8]
[null,"Watson B. Duncan Middle",17,0,17,0,0,0,17]
[null,"Wellington Landings Middle",16,0,0,0,11,5,16]
[null,"Western Pines Middle",9,0,0,0,5,4,9]
[null,"Woodlands Middle",11,0,0,0,7,4,11]
[null,"Atlantic High",31,18,0,0,13,0,31]
[null,"Boca Raton High",12,0,0,12,0,0,12]
[null,"Dreyfoos School of the Arts",0,0,0,0,0,0,0]
[null,"Forest Hill High",10,0,0,0,0,10,10]
[null,"Glades Central High",0,0,0,0,0,0,0]
[null,"Inlet Grove High",1,0,0,1,0,0,1]
[null,"Jupiter High",0,0,0,0,0,0,0]
[null,"J.I. Leonard High",9,0,0,5,4,0,9]
[null,"Lake Worth High",41,0,41,0,0,0,41]
[null,"Olympic Heights High",9,0,0,0,6,3,9]
[null,"Pahokee Mid./Sr. High",0,0,0,0,0,0,0]
[null,"Palm Beach Gardens High",5,0,0,1,2,2,5]
[null,"Palm Beach Lakes High",9,0,0,4,5,0,9]
[null,"Royal Palm Beach High",0,0,0,0,0,0,0]
[null,"Santaluces High",52,27,0,0,19,6,52]
[null,"South Tech",1,0,0,1,0,0,1]
[null,"Spanish River High",24,0,0,0,20,4,24]
[null,"Suncoast High",0,0,0,0,0,0,0]
[null,"Wellington High",13,0,0,8,5,0,13]
[null,"West Tech",0,0,0,0,0,0,0]
[null,"Wm. T. Dwyer High",5,0,0,5,0,0,5]
[null,"Adult Education Center",0,0,0,0,0,0,0]
[null,"Cypress Hammock School",0,0,0,0,0,0,0]
[null,"Delray Full Service Center",0,0,0,0,0,0,0]
[null,"Gold Coast Community School",1,0,0,0,1,0,1]
[null,"Indian Ridge School",0,0,0,0,0,0,0]
[null,"So. Area Middle School of Choice",0,0,0,0,0,0,0]
[null,"Roosevelt Service Center",0,0,0,0,0,0,0]
[null,"Royal Palm School",0,0,0,0,0,0,0]
[null,"Sabal Palm School(High Ridge)",6,0,0,6,0,0,6]
[null,"School of Choice",0,0,0,0,0,0,0]
["2c2.","Palm Beach County Total",1390,275,287,263,431,134,1390]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2000-01","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2005-06","FISH Stu. Sta.","# Years Leased "]
[null,"Acreage Pines Elementary",1,"Leased",25,13,0,0,0]
[null,"Addison Mizner Elementary",4,"Leased",100,13,0,0,0]
[null,"Allamanda Elementary",0,"Leased",0,13,0,0,0]
[null,"Banyan Creek Elementary",9,"Leased",90,13,0,0,0]
[null,"Barton Elementary",10,"Leased",200,13,0,0,0]
[null,"Belle Glade Elementary",0,"Leased",0,13,0,0,0]
[null,"Belvedere Elementary",0,"Leased",0,13,0,0,0]
[null,"Berkshire Elementary",1,"Leased",15,13,0,0,0]
[null,"Binks Forest Elementary",0,"Leased",0,13,0,0,0]
[null,"Boca Raton Elementary",4,"Leased",65,13,0,0,0]
[null,"Calusa Elementary",0,"Leased",0,13,0,0,0]
[null,"Citrus Cove Elementary",10,"Leased",215,13,0,0,0]
[null,"Coral Reef Elementary",0,"Leased",0,13,0,0,0]
[null,"Coral Sunset Elementary",2,"Leased",44,13,0,0,0]
[null,"Crystal Lakes Elementary",1,"Leased",25,13,0,0,0]
[null,"Cypress Trails Elementary",0,"Leased",0,13,0,0,0]
[null,"C.O.Taylor/Kirklane Elementary",0,"Leased",0,13,0,0,0]
[null,"Del Prado Elementary",6,"Leased",144,13,0,0,0]
[null,"Dr. Mary McLeod Bethune Elem.",0,"Leased",0,13,0,0,0]
[null,"D.D. Eisenhower Elementary",0,"Leased",0,13,0,0,0]
[null,"Egret Lake Elementary",1,"Leased",25,13,0,0,0]
[null,"Forest Hill Elementary",5,"Leased",84,13,0,0,0]
[null,"Forest Park Elementary",4,"Leased",94,13,0,0,0]
[null,"Galaxy Elementary",2,"Leased",52,13,0,0,0]
[null,"Glade View Elementary",6,"Leased",96,13,0,0,0]
[null,"Golden Grove Elementary",0,"Leased",0,13,0,0,0]
[null,"Gove Elementary",11,"Leased",255,13,0,0,0]
[null,"Greenacres Elementary",1,"Leased",15,13,0,0,0]
[null,"Grove Park Elementary",0,"Leased",0,13,0,0,0]
[null,"Hagen Road Elementary",0,"Leased",0,13,0,0,0]
[null,"Hammock Pointe Elementary",0,"Leased",0,13,0,0,0]
[null,"Heritage Elementary",0,"Leased",0,13,0,0,0]
[null,"Highland Elementary",0,"Leased",0,13,0,0,0]
[null,"H.L. Johnson Elementary",4,"Leased",0,13,0,0,0]
[null,"Indian Pines Elementary",5,"Leased",105,13,0,0,0]
[null,"Jerry Thomas Elementary",0,"Leased",0,13,0,0,0]
[null,"Jupiter Elementary",0,"Leased",0,13,0,0,0]
[null,"Jupiter Farms Elementary",0,"Leased",0,13,0,0,0]
[null,"J.C. Mitchell Elementary",0,"Leased",0,13,0,0,0]
[null,"K.E.C./Canal Point Elementary",0,"Leased",0,13,0,0,0]
[null,"Lake Park Elementary",5,"Leased",114,13,0,0,0]
[null,"Lantana Elementary",0,"Leased",0,13,0,0,0]
[null,"Liberty Park Elementary",4,"Leased",84,13,0,0,0]
[null,"Lighthouse Elementary",5,"Leased",125,13,0,0,0]
[null,"Limestone Creek Elementary",4,"Leased",100,13,0,0,0]
[null,"Lincoln Elementary",0,"Leased",0,13,0,0,0]
[null,"Loxahatchee Groves Elementary",3,"Leased",57,13,0,0,0]
[null,"Manatee Elementary",4,"Leased",84,13,0,0,0]
[null,"Meadow Park Elementary",3,"Leased",38,13,0,0,0]
[null,"Melaleuca Elementary",3,"Leased",63,13,0,0,0]
[null,"Morikami Park Elementary",0,"Leased",0,13,0,0,0]
[null,"New Horizons Elementary",0,"Leased",0,13,0,0,0]
[null,"North Grade Elementary",0,"Leased",0,13,0,0,0]
[null,"North Palm Beach Elementary",0,"Leased",0,13,0,0,0]
[null,"Northboro Elementary",1,"Leased",16,13,0,0,0]
[null,"Northmore Elementary",0,"Leased",0,13,0,0,0]
[null,"Orchard View Elementary",0,"Leased",0,13,0,0,0]
[null,"Pahokee Elementary",4,"Leased",64,13,0,0,0]
[null,"Palm Beach Gardens Elementary",0,"Leased",0,13,0,0,0]
[null,"Palm Beach Public Elementary",0,"Leased",0,13,0,0,0]
[null,"Palm Springs Elementary",4,"Leased",68,13,0,0,0]
[null,"Palmetto Elementary",7,"Leased",132,13,0,0,0]
[null,"Panther Run Elementary",12,"Leased",258,13,0,0,0]
[null,"Pine Grove Elementary",4,"Leased",100,13,0,0,0]
[null,"Pioneer Park Elementary",0,"Leased",0,13,0,0,0]
[null,"Plumosa Elementary",0,"Leased",0,13,0,0,0]
[null,"Poinciana Elementary",0,"Leased",0,13,0,0,0]
[null,"Rolling Green Elementary",2,"Leased",52,13,0,0,0]
[null,"Roosevelt Elementary",5,"Leased",95,13,0,0,0]
[null,"Rosenwald Elementary",3,"Leased",69,13,0,0,0]
[null,"Sandpiper Shores Elementary",8,"Leased",189,13,0,0,0]
[null,"Seminole Trails Elementary",1,"Leased",13,13,0,0,0]
[null,"South Grade Elementary",0,"Leased",0,13,0,0,0]
[null,"South Olive Elementary",3,"Leased",40,13,0,0,0]
[null,"Starlight Cove Elementary",0,"Leased",0,13,0,0,0]
[null,"S.D. Spady Elementary",1,"Leased",22,13,0,0,0]
[null,"Timber Trace Elementary",1,"Leased",25,13,0,0,0]
[null,"U.B. Kinsey/Palmview Elementary",0,"Leased",0,13,0,0,0]
[null,"Verde Elementary",0,"Leased",0,13,0,0,0]
[null,"Village Academy",0,"Leased",0,13,0,0,0]
[null,"Washington Elementary",1,"Leased",23,13,0,0,0]
[null,"Waters Edge Elementary",0,"Leased",0,13,0,0,0]
[null,"Wellington Elementary",1,"Leased",0,13,0,0,0]
[null,"West Gate Elementary",12,"Leased",209,13,0,0,0]
[null,"West Riviera Elementary",0,"Leased",0,13,0,0,0]
[null,"Westward Elementary",2,"Leased",30,13,0,0,0]
[null,"Whispering Pines Elementary",2,"Leased",30,13,0,0,0]
[null,"Wynnebrook Elementary",8,"Leased",152,13,0,0,0]
[null,"Bear Lakes Middle",3,"Leased",50,13,0,0,0]
[null,"Boca Raton Middle",5,"Leased",80,13,0,0,0]
[null,"Carver Middle",21,"Leased",480,13,0,0,0]
[null,"Christa McAuliffe Middle",9,"Leased",225,13,0,0,0]
[null,"Congress Middle",3,"Leased",69,13,0,0,0]
[null,"Conniston Middle",0,"Leased",0,13,0,0,0]
[null,"Crestwood Middle",6,"Leased",115,13,0,0,0]
[null,"Eagles Landing Middle",7,"Leased",189,13,0,0,0]
[null,"H.L. Watkins Middle",1,"Leased",15,13,0,0,0]
[null,"Jefferson Davis Middle",0,"Leased",0,13,0,0,0]
[null,"Jupiter Middle",10,"Leased",210,13,0,0,0]
[null,"J.F. Kennedy Middle",15,"Leased",375,13,0,0,0]
[null,"Lake Shore Middle",0,"Leased",0,13,0,0,0]
[null,"Lake Worth Middle",8,"Leased",181,13,0,0,0]
[null,"Lantana Middle",4,"Leased",108,13,0,0,0]
[null,"Loggers Run Middle",2,"Leased",50,13,0,0,0]
[null,"Middle School of the Arts",20,"Leased",540,13,0,0,0]
[null,"Okeeheelee Middle",1,"Leased",27,13,0,0,0]
[null,"Omni Middle",2,"Leased",38,13,0,0,0]
[null,"Polo Park Middle",0,"Leased",0,13,0,0,0]
[null,"Roosevelt Middle",8,"Leased",224,13,0,0,0]
[null,"Watson B. Duncan Middle",2,"Leased",46,13,0,0,0]
[null,"Wellington Landings Middle",11,"Leased",189,13,0,0,0]
[null,"Western Pines Middle",2,"Leased",54,13,0,0,0]
[null,"Woodlands Middle",4,"Leased",108,13,0,0,0]
[null,"Atlantic High",2,"Leased",46,13,0,0,0]
[null,"Boca Raton High",2,"Leased",48,13,0,0,0]
[null,"Dreyfoos School of the Arts",4,"Leased",0,13,0,0,0]
[null,"Forest Hill High",0,"Leased",0,13,0,0,0]
[null,"Glades Central High",0,"Leased",0,13,0,0,0]
[null,"Inlet Grove High",0,"Leased",0,13,0,0,0]
[null,"Jupiter High",0,"Leased",0,13,0,0,0]
[null,"J.I. Leonard High",1,"Leased",24,13,0,0,0]
[null,"Lake Worth High",8,"Leased",208,13,0,0,0]
[null,"Olympic Heights High",9,"Leased",270,13,0,0,0]
[null,"Pahokee Mid./Sr. High",0,"Leased",0,13,0,0,0]
[null,"Palm Beach Gardens High",2,"Leased",60,13,0,0,0]
[null,"Palm Beach Lakes High",4,"Leased",120,13,0,0,0]
[null,"Royal Palm Beach High",0,"Leased",0,13,0,0,0]
[null,"Santaluces High",23,"Leased",644,13,0,0,0]
[null,"South Tech",1,"Leased",23,13,0,0,0]
[null,"Spanish River High",2,"Leased",60,13,0,0,0]
[null,"Suncoast High",0,"Leased",0,13,0,0,0]
[null,"Wellington High",5,"Leased",130,13,0,0,0]
[null,"West Tech",8,"Leased",235,13,0,0,0]
[null,"Wm. T. Dwyer High",1,"Leased",21,13,0,0,0]
[null,"Adult Education Center",2,"Leased",50,13,0,0,0]
[null,"Cypress Hammock School",0,"Leased",0,13,0,0,0]
[null,"Delray Full Service Center",0,"Leased",0,13,0,0,0]
[null,"Gold Coast Community School",2,"Leased",35,13,0,0,0]
[null,"Indian Ridge School",1,"Leased",15,13,0,0,0]
[null,"So. Area Middle School of Choice",1,"Leased",20,13,0,0,0]
[null,"Roosevelt Service Center",1,"Leased",15,13,0,0,0]
[null,"Royal Palm School",0,"Leased",0,13,0,0,0]
[null,"Sabal Palm School(High Ridge)",0,"Leased",26,13,0,0,0]
[null,"School of Choice",0,"Leased",52,13,0,0,0]
["2c3.","Palm Beach County Total",423,null,9376,1872,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"Academy School of Boca Raton - Middle, Basic",11,"Academy School of Boca Raton, Inc.","2000-01",275,141,5,303]
[null,"Chancellor Charter School of Lantana - Elem, Basic",20,"Chancellor Charter School of Lantana","2001-02",500,383,10,550]
[null,"Cultural Arts Institute - Grades 4-6, Art Curriculum",4,"Cultural Arts Institute","2001-02",100,40,10,110]
[null,"Delray Beach Academy -  Middle, At Risk",3,"Delray Beach Academy","1998-99",75,54,3,83]
[null,"Ed Venture - High ESE",8,"Edventure Charter School, Inc.","1998-99",120,29,3,132]
[null,"Glades Academy - Grades K-2, Core Curriculum",4,"Glades Academy of Agricultural & Ecological Studies, Inc.","2001-02",100,64,5,110]
[null,"Hope Learning Community of the Gardens (dba Bright Futures International) - Grades K - 2, Core Curriculum",4,"Hope Learning Community of the Gardens (dba Bright Futures International)","2001-02",100,64,5,110]
[null,"Hope Learning Community of Riviera Beach (dba Noah's Ark International) - Grades K-1, Core Curriculum",5,"Hope Learning Community of Riviera Beach (dba Noah's Ark International)","2001-02",125,35,5,138]
[null,"Joseph Littles - Nguzo Saba - Grades K - 4, At Risk",6,"Joseph Littles - Nguzo Saba Charter School, Inc.","1998-99",150,75,5,165]
[null,"Lakeside Academy - Elem, Basic",6,"Lakeside Academy","1998-99",150,102,3,165]
[null,"Palm Beach Maritime Academy - Grades K-8, Sea Theme",9,"Palm Beach Maritime Museum, Inc.","1999-2000",225,146,5,248]
[null,"Potentials - Elem, ESE",4,"The Arc","1998-1999",60,26,3,66]
[null,"Renaissance Learning Center - Elem, ESE",1,"Renaissance Learning Center","1999-2000",15,6,3,17]
[null,"St. Mary's Preschool Autism Center - Pre-school, ESE",4,"St. Mary's Inc.","1999-2000",60,13,5,66]
[null,"Survivors - High, At risk",8,"Survivors","2001-2002",200,51,10,220]
[null,"Toussaint L'Ouverture High School for Arts & Social Justice - High, Arts/Social Justice",8,"Toussaint L'Overture","2001-2002",200,125,5,220]
["2c4.","Palm Beach County Total",105,null,null,2455,1354,85,2703]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
["2e.","Average Class Size (5 years out -- 2005-06) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2000-01 CO-FTE","2000-01 Class size","2005-06 CO-FTE","be added (removed)","2005-06 Class size"]
[null,"Acreage Pines Elementary",59,1573,1511,25.61,759,-32,28.11]
[null,"Addison Mizner Elementary",36,909,884,24.56,715,-7,24.66]
[null,"Allamanda Elementary",32,851,851,26.59,552,0,17.25]
[null,"Banyan Creek Elementary",49,1317,998,20.37,736,-21,26.29]
[null,"Barton Elementary",45,1116,698,15.51,761,-8,20.57]
[null,"Belle Glade Elementary",40,1045,734,18.35,737,0,18.43]
[null,"Belvedere Elementary",34,758,568,16.71,521,-8,20.04]
[null,"Berkshire Elementary",41,1063,910,22.2,681,-13,24.32]
[null,"Binks Forest Elementary",35,1000,1041,29.74,1026,1,28.5]
[null,"Boca Raton Elementary",20,475,345,17.25,404,-3,23.76]
[null,"Calusa Elementary",29,839,490,16.9,685,0,23.62]
[null,"Citrus Cove Elementary",63,1593,1473,23.38,814,-32,26.26]
[null,"Coral Reef Elementary",37,1000,1043,28.19,850,0,22.97]
[null,"Coral Sunset Elementary",41,1132,945,23.05,1022,-6,29.2]
[null,"Crystal Lakes Elementary",38,1003,967,25.45,845,-6,26.41]
[null,"Cypress Trails Elementary",35,943,896,25.6,784,-6,27.03]
[null,"C.O.Taylor/Kirklane Elementary",34,1230,1147,33.74,808,-4,26.93]
[null,"Del Prado Elementary",47,1293,1285,27.34,769,-20,28.48]
[null,"Dr. Mary McLeod Bethune Elem.",36,970,723,20.08,897,0,24.92]
[null,"D.D. Eisenhower Elementary",17,950,442,26,657,6,28.57]
[null,"Egret Lake Elementary",34,934,877,25.79,753,-6,26.89]
[null,"Forest Hill Elementary",50,1207,1118,22.36,1006,-8,23.95]
[null,"Forest Park Elementary",41,986,604,14.73,658,-14,24.37]
[null,"Galaxy Elementary",31,765,701,22.61,614,-2,21.17]
[null,"Glade View Elementary",38,968,497,13.08,513,-8,17.1]
[null,"Golden Grove Elementary",43,1172,1059,24.63,1070,-4,27.44]
[null,"Gove Elementary",49,1293,745,15.2,794,-8,19.37]
[null,"Greenacres Elementary",39,753,575,14.74,589,-2,15.92]
[null,"Grove Park Elementary",34,823,830,24.41,769,-2,24.03]
[null,"Hagen Road Elementary",13,736,513,39.46,656,8,31.24]
[null,"Hammock Pointe Elementary",34,919,915,26.91,902,6,22.55]
[null,"Heritage Elementary",37,992,1017,27.49,962,0,26]
[null,"Highland Elementary",31,848,782,25.23,784,0,25.29]
[null,"H.L. Johnson Elementary",55,1460,1156,21.02,805,-26,27.76]
[null,"Indian Pines Elementary",39,1026,951,24.38,740,-12,27.41]
[null,"Jerry Thomas Elementary",34,853,849,24.97,813,-2,25.41]
[null,"Jupiter Elementary",39,723,496,12.72,678,0,17.38]
[null,"Jupiter Farms Elementary",29,783,803,27.69,854,3,26.69]
[null,"J.C. Mitchell Elementary",44,883,670,15.23,747,-5,19.15]
[null,"K.E.C./Canal Point Elementary",34,904,630,18.53,578,-5,19.93]
[null,"Lake Park Elementary",26,599,606,23.31,460,-9,27.06]
[null,"Lantana Elementary",28,680,695,24.82,603,-1,22.33]
[null,"Liberty Park Elementary",52,1439,1274,24.5,759,-24,27.11]
[null,"Lighthouse Elementary",50,1349,1237,24.74,778,-21,26.83]
[null,"Limestone Creek Elementary",38,1026,1018,26.79,844,-5,25.58]
[null,"Lincoln Elementary",61,1200,803,13.16,1007,0,16.51]
[null,"Loxahatchee Groves Elementary",32,908,776,24.25,724,0,22.63]
[null,"Manatee Elementary",43,1165,1223,28.44,974,-9,28.65]
[null,"Meadow Park Elementary",32,797,611,19.09,654,-5,24.22]
[null,"Melaleuca Elementary",43,1101,1012,23.53,823,-11,25.72]
[null,"Morikami Park Elementary",40,1025,1002,25.05,1000,0,25]
[null,"New Horizons Elementary",26,750,700,26.92,736,0,28.31]
[null,"North Grade Elementary",37,829,572,15.46,717,0,19.38]
[null,"North Palm Beach Elementary",35,834,523,14.94,440,0,12.57]
[null,"Northboro Elementary",44,1084,692,15.73,807,0,18.34]
[null,"Northmore Elementary",32,880,564,17.63,578,0,18.06]
[null,"Orchard View Elementary",40,1034,921,23.03,894,0,22.35]
[null,"Pahokee Elementary",37,869,679,18.35,649,-10,24.04]
[null,"Palm Beach Gardens Elementary",31,757,676,21.81,626,-3,22.36]
[null,"Palm Beach Public Elementary",24,435,385,16.04,370,0,15.42]
[null,"Palm Springs Elementary",32,828,671,20.97,934,0,29.19]
[null,"Palmetto Elementary",40,861,588,14.7,714,0,17.85]
[null,"Panther Run Elementary",54,1435,1483,27.46,829,-27,30.7]
[null,"Pine Grove Elementary",43,1108,678,15.77,659,-6,17.81]
[null,"Pioneer Park Elementary",38,1045,657,17.29,675,0,17.76]
[null,"Plumosa Elementary",28,708,598,21.36,621,-1,23]
[null,"Poinciana Elementary",32,922,701,21.91,744,0,23.25]
[null,"Rolling Green Elementary",46,1173,850,18.48,617,-21,24.68]
[null,"Roosevelt Elementary",45,1185,963,21.4,832,-12,25.21]
[null,"Rosenwald Elementary",31,797,419,13.52,427,0,13.77]
[null,"Sandpiper Shores Elementary",52,1311,1235,23.75,839,-20,26.22]
[null,"Seminole Trails Elementary",39,943,813,20.85,748,-1,19.68]
[null,"South Grade Elementary",28,793,789,28.18,868,3,28]
[null,"South Olive Elementary",44,1021,916,20.82,629,-14,20.97]
[null,"Starlight Cove Elementary",41,1153,883,21.54,890,0,21.71]
[null,"S.D. Spady Elementary",28,709,502,17.93,620,-10,34.44]
[null,"Timber Trace Elementary",36,999,723,20.08,763,-7,26.31]
[null,"U.B. Kinsey/Palmview Elementary",48,876,618,12.88,590,-7,14.39]
[null,"Verde Elementary",34,856,727,21.38,700,-3,22.58]
[null,"Village Academy",17,487,223,13.12,450,0,26.47]
[null,"Washington Elementary",29,712,557,19.21,629,0,21.69]
[null,"Waters Edge Elementary",40,1050,784,19.6,1142,4,25.95]
[null,"Wellington Elementary",41,1041,977,23.83,948,-3,24.95]
[null,"West Gate Elementary",38,866,684,18,752,-8,25.07]
[null,"West Riviera Elementary",32,1086,658,20.56,857,-4,30.61]
[null,"Westward Elementary",47,873,686,14.6,787,0,16.74]
[null,"Whispering Pines Elementary",45,1202,904,20.09,807,-11,23.74]
[null,"Wynnebrook Elementary",44,1132,1026,23.32,631,-15,21.76]
[null,"Bear Lakes Middle",71,1930,1477,20.8,1136,-30,27.71]
[null,"Boca Raton Middle",55,1460,1196,21.75,1070,-4,20.98]
[null,"Carver Middle",68,1904,1702,25.03,1350,-19,27.55]
[null,"Christa McAuliffe Middle",55,1583,1477,26.85,1260,-13,30]
[null,"Congress Middle",63,1701,1415,22.46,1334,-13,26.68]
[null,"Conniston Middle",49,1214,934,19.06,889,-1,18.52]
[null,"Crestwood Middle",62,1741,1439,23.21,1292,-21,31.51]
[null,"Eagles Landing Middle",57,1647,1396,24.49,1245,-13,28.3]
[null,"H.L. Watkins Middle",59,1334,1429,24.22,883,-12,18.79]
[null,"Jefferson Davis Middle",87,1789,1622,18.64,1274,-23,19.91]
[null,"Jupiter Middle",68,1807,1621,23.84,1326,-22,28.83]
[null,"J.F. Kennedy Middle",65,1807,1621,24.94,1326,-20,29.47]
[null,"Lake Shore Middle",48,1496,1227,25.56,1220,0,25.42]
[null,"Lake Worth Middle",72,1961,1505,20.9,1014,-27,22.53]
[null,"Lantana Middle",37,921,845,22.84,749,-12,29.96]
[null,"Loggers Run Middle",53,1572,1371,25.87,1129,-13,28.23]
[null,"Middle School of the Arts",71,1676,1232,17.35,1200,-29,28.57]
[null,"Okeeheelee Middle",60,1736,1599,26.65,1273,-19,31.05]
[null,"Omni Middle",54,1526,1263,23.39,1236,-9,27.47]
[null,"Polo Park Middle",45,1313,956,21.24,1380,2,29.36]
[null,"Roosevelt Middle",54,1553,1519,28.13,1269,-8,27.59]
[null,"Watson B. Duncan Middle",55,1545,1494,27.16,1006,-13,23.95]
[null,"Wellington Landings Middle",55,1525,1503,27.33,1100,-16,28.21]
[null,"Western Pines Middle",54,1559,1503,27.83,1244,-9,27.64]
[null,"Woodlands Middle",59,1710,1717,29.1,1350,-11,28.13]
[null,"Atlantic High",101,2395,2911,28.82,1884,-23,24.15]
[null,"Boca Raton High",87,2287,1867,21.46,1796,-9,23.03]
[null,"Dreyfoos School of the Arts",57,1326,1270,22.28,1220,0,21.4]
[null,"Forest Hill High",66,1729,1591,24.11,1860,-6,31]
[null,"Glades Central High",63,1624,1398,22.19,1268,0,20.13]
[null,"Inlet Grove High",55,974,261,4.75,1200,0,21.82]
[null,"Jupiter High",92,2570,1709,18.58,2349,0,25.53]
[null,"J.I. Leonard High",116,2823.4,3049,26.28,2626,-6,23.87]
[null,"Lake Worth High",123,3359,3031,24.64,2742,-40,33.04]
[null,"Olympic Heights High",110,2784,2608,23.71,2536,-9,25.11]
[null,"Pahokee Mid./Sr. High",57,1332,1089,19.11,941,0,16.51]
[null,"Palm Beach Gardens High",92,2371,2475,26.9,2193,-5,25.21]
[null,"Palm Beach Lakes High",113,3049,2842,25.15,2768,-9,26.62]
[null,"Royal Palm Beach High",83,2493,2448,29.49,2671,4,30.7]
[null,"Santaluces High",140,3865,3612,25.8,2299,-49,25.26]
[null,"South Tech",62,1257,403,6.5,1600,0,25.81]
[null,"Spanish River High",120,3135,3270,27.25,2454,-24,25.56]
[null,"Suncoast High",47,989,1287,27.38,1225,0,26.06]
[null,"Wellington High",109,2908,3094,28.39,2587,-13,26.95]
[null,"West Tech",41,922,214,5.22,1040,0,25.37]
[null,"Wm. T. Dwyer High",84,2040,2132,25.38,2234,-5,28.28]
[null,"Adult Education Center",27,1032,55,2.04,66.91590963200001,0,2.48]
[null,"Cypress Hammock School",1,4,0,0,0,0,0]
[null,"Delray Full Service Center",47,1118,105,2.23,126,0,2.68]
[null,"Gold Coast Community School",2,367,296,148,350,12,25]
[null,"Indian Ridge School",0,151,120,0,120,0,0]
[null,"So. Area Middle School of Choice",12,392,68,5.67,100,0,8.33]
[null,"Roosevelt Service Center",27,615,110,4.07,150,0,5.56]
[null,"Royal Palm School",0,330,200,0,250,0,0]
[null,"Sabal Palm School(High Ridge)",0,78,42,0,50,0,0]
[null,"School of Choice",20,636,74,3.7,100,0,5]
["2e.","Palm Beach County Total",6769,176986.4,149715,"District Avg 22",137813.915909632,-1044,"District Avg 24"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR AVERAGE"]
[null,"Acreage Pines Elementary",null,150,150,150,0,0,90]
[null,"Addison Mizner Elementary",null,225,100,75,0,0,80]
[null,"Allamanda Elementary",null,0,0,0,0,0,0]
[null,"Banyan Creek Elementary",null,248,75,0,0,0,64.6]
[null,"Barton Elementary",null,160,160,160,160,160,160]
[null,"Belle Glade Elementary",null,25,25,25,25,25,25]
[null,"Belvedere Elementary",null,377,332,200,200,200,261.8]
[null,"Berkshire Elementary",null,391,286,244,244,0,233]
[null,"Binks Forest Elementary",null,0,0,25,25,25,15]
[null,"Boca Raton Elementary",null,0,0,0,0,0,0]
[null,"Calusa Elementary",null,60,60,60,60,60,60]
[null,"Citrus Cove Elementary",null,819,243,195,51,51,271.8]
[null,"Coral Reef Elementary",null,0,0,0,0,0,0]
[null,"Coral Sunset Elementary",null,335,335,335,44,44,218.6]
[null,"Crystal Lakes Elementary",null,213,142,71,71,71,113.6]
[null,"Cypress Trails Elementary",null,153,77,0,0,0,46]
[null,"C.O.Taylor/Kirklane Elementary",null,357,357,357,0,0,214.2]
[null,"Del Prado Elementary",null,46,0,0,0,0,9.2]
[null,"Dr. Mary McLeod Bethune Elem.",null,0,0,0,0,0,0]
[null,"D.D. Eisenhower Elementary",null,49,29,29,29,29,33]
[null,"Egret Lake Elementary",null,149,149,149,100,0,109.4]
[null,"Forest Hill Elementary",null,524,436,16,16,16,201.6]
[null,"Forest Park Elementary",null,233,113,48,48,48,98]
[null,"Galaxy Elementary",null,132,53,0,0,0,37]
[null,"Glade View Elementary",null,177,177,177,177,177,177]
[null,"Golden Grove Elementary",null,162,162,162,54,54,118.8]
[null,"Gove Elementary",null,486,300,300,300,300,337.2]
[null,"Greenacres Elementary",null,54,54,0,0,0,21.6]
[null,"Grove Park Elementary",null,116,70,70,70,70,79.2]
[null,"Hagen Road Elementary",null,23,23,23,23,23,23]
[null,"Hammock Pointe Elementary",null,144,144,144,0,0,86.4]
[null,"Heritage Elementary",null,0,0,0,0,0,0]
[null,"Highland Elementary",null,0,0,0,0,0,0]
[null,"H.L. Johnson Elementary",null,659,110,0,0,0,153.8]
[null,"Indian Pines Elementary",null,257,257,257,44,0,163]
[null,"Jerry Thomas Elementary",null,63,63,63,21,21,46.2]
[null,"Jupiter Elementary",null,0,0,0,0,0,0]
[null,"Jupiter Farms Elementary",null,0,0,0,0,0,0]
[null,"J.C. Mitchell Elementary",null,104,45,0,0,0,29.8]
[null,"K.E.C./Canal Point Elementary",null,0,0,0,0,0,0]
[null,"Lake Park Elementary",null,0,0,0,0,0,0]
[null,"Lantana Elementary",null,25,25,0,0,0,10]
[null,"Liberty Park Elementary",null,637,340,148,0,0,225]
[null,"Lighthouse Elementary",null,0,0,0,0,0,0]
[null,"Limestone Creek Elementary",null,209,209,78,78,78,130.4]
[null,"Lincoln Elementary",null,47,47,47,47,47,47]
[null,"Loxahatchee Groves Elementary",null,135,135,135,135,135,135]
[null,"Manatee Elementary",null,187,63,63,0,0,62.6]
[null,"Meadow Park Elementary",null,154,154,154,19,19,100]
[null,"Melaleuca Elementary",null,292,292,292,105,21,200.4]
[null,"Morikami Park Elementary",null,0,0,0,0,0,0]
[null,"New Horizons Elementary",null,0,0,0,0,0,0]
[null,"North Grade Elementary",null,0,0,0,0,0,0]
[null,"North Palm Beach Elementary",null,0,0,0,0,0,0]
[null,"Northboro Elementary",null,196,196,48,48,48,107.2]
[null,"Northmore Elementary",null,0,0,0,0,0,0]
[null,"Orchard View Elementary",null,0,0,0,0,0,0]
[null,"Pahokee Elementary",null,0,0,0,0,0,0]
[null,"Palm Beach Gardens Elementary",null,99,0,0,0,0,19.8]
[null,"Palm Beach Public Elementary",null,0,0,0,0,0,0]
[null,"Palm Springs Elementary",null,234,234,234,0,0,140.4]
[null,"Palmetto Elementary",null,620,620,0,0,0,248]
[null,"Panther Run Elementary",null,516,473,473,43,43,309.6]
[null,"Pine Grove Elementary",null,225,225,225,225,225,225]
[null,"Pioneer Park Elementary",null,0,0,0,0,0,0]
[null,"Plumosa Elementary",null,37,0,0,0,0,7.4]
[null,"Poinciana Elementary",null,0,0,0,0,0,0]
[null,"Rolling Green Elementary",null,363,103,26,26,26,108.8]
[null,"Roosevelt Elementary",null,389,389,389,0,0,233.4]
[null,"Rosenwald Elementary",null,119,119,119,119,119,119]
[null,"Sandpiper Shores Elementary",null,95,47,47,47,47,56.6]
[null,"Seminole Trails Elementary",null,117,91,78,0,0,57.2]
[null,"South Grade Elementary",null,0,0,0,0,0,0]
[null,"South Olive Elementary",null,339,339,0,0,0,135.6]
[null,"Starlight Cove Elementary",null,188,188,188,188,188,188]
[null,"S.D. Spady Elementary",null,268,268,268,22,22,169.6]
[null,"Timber Trace Elementary",null,124,50,0,0,0,34.8]
[null,"U.B. Kinsey/Palmview Elementary",null,159,159,0,0,0,63.6]
[null,"Verde Elementary",null,97,25,0,0,0,24.4]
[null,"Village Academy",null,0,0,0,0,0,0]
[null,"Washington Elementary",null,140,140,140,140,140,140]
[null,"Waters Edge Elementary",null,0,0,0,0,0,0]
[null,"Wellington Elementary",null,107,89,18,0,0,42.8]
[null,"West Gate Elementary",null,496,0,0,0,0,99.2]
[null,"West Riviera Elementary",null,82,82,82,82,82,82]
[null,"Westward Elementary",null,132,132,132,132,132,132]
[null,"Whispering Pines Elementary",null,220,133,133,133,133,150.4]
[null,"Wynnebrook Elementary",null,427,427,427,116,0,279.4]
[null,"Bear Lakes Middle",null,746,746,746,294,0,506.4]
[null,"Boca Raton Middle",null,244,244,186,186,186,209.2]
[null,"Carver Middle",null,148,0,0,0,0,29.6]
[null,"Christa McAuliffe Middle",null,339,339,339,90,23,226]
[null,"Congress Middle",null,273,273,273,83,0,180.4]
[null,"Conniston Middle",null,44,44,0,0,0,17.6]
[null,"Crestwood Middle",null,542,542,292,103,103,316.4]
[null,"Eagles Landing Middle",null,317,317,317,97,0,209.6]
[null,"H.L. Watkins Middle",null,270,162,0,0,0,86.4]
[null,"Jefferson Davis Middle",null,392,392,306,0,0,218]
[null,"Jupiter Middle",null,511,132,19,19,19,140]
[null,"J.F. Kennedy Middle",null,293,113,0,0,0,81.2]
[null,"Lake Shore Middle",null,0,0,0,0,0,0]
[null,"Lake Worth Middle",null,733,733,733,163,0,472.4]
[null,"Lantana Middle",null,420,420,0,0,0,168]
[null,"Loggers Run Middle",null,356,356,356,113,0,236.2]
[null,"Middle School of the Arts",null,712,712,712,712,0,569.6]
[null,"Okeeheelee Middle",null,458,458,243,0,0,231.8]
[null,"Omni Middle",null,275,275,275,0,0,165]
[null,"Polo Park Middle",null,0,0,0,0,0,0]
[null,"Roosevelt Middle",null,202,202,202,50,0,131.2]
[null,"Watson B. Duncan Middle",null,355,0,0,0,0,71]
[null,"Wellington Landings Middle",null,394,394,394,123,0,261]
[null,"Western Pines Middle",null,219,219,219,97,0,150.8]
[null,"Woodlands Middle",null,267,267,267,97,0,179.6]
[null,"Atlantic High",null,280,280,280,0,0,168]
[null,"Boca Raton High",null,271,271,0,0,0,108.4]
[null,"Dreyfoos School of the Arts",null,0,0,0,0,0,0]
[null,"Forest Hill High",null,135,135,135,135,27,113.4]
[null,"Glades Central High",null,0,0,0,0,0,0]
[null,"Inlet Grove High",null,225,225,225,225,225,225]
[null,"Jupiter High",null,0,0,0,0,0,0]
[null,"J.I. Leonard High",null,207,207,91,0,0,101]
[null,"Lake Worth High",null,1031,0,0,0,0,206.2]
[null,"Olympic Heights High",null,257,257,257,86,0,171.4]
[null,"Pahokee Mid./Sr. High",null,25,25,25,25,25,25]
[null,"Palm Beach Gardens High",null,142,142,113,57,0,90.8]
[null,"Palm Beach Lakes High",null,456,456,342,199,199,330.4]
[null,"Royal Palm Beach High",null,0,0,0,0,0,0]
[null,"Santaluces High",null,662,662,662,159,0,429]
[null,"South Tech",null,441,441,441,441,441,441]
[null,"Spanish River High",null,757,757,757,197,86,510.8]
[null,"Suncoast High",null,0,0,0,0,0,0]
[null,"Wellington High",null,370,370,172,49,49,202]
[null,"West Tech",null,335,335,335,335,335,335]
[null,"Wm. T. Dwyer High",null,98,98,0,0,0,39.2]
[null,"Adult Education Center",null,178,178,178,178,178,178]
[null,"Cypress Hammock School",null,0,0,0,0,0,0]
[null,"Delray Full Service Center",null,95,95,95,95,95,95]
[null,"Gold Coast Community School",null,75,75,75,75,75,75]
[null,"Indian Ridge School",null,60,60,60,60,60,60]
[null,"So. Area Middle School of Choice",null,249,249,249,249,249,249]
[null,"Roosevelt Service Center",null,15,15,15,15,15,15]
[null,"Royal Palm School",null,42,42,42,42,42,42]
[null,"Sabal Palm School(High Ridge)",null,0,0,0,0,0,0]
[null,"School of Choice",null,76,76,76,76,76,76]
["2f.","Palm Beach County Total students in relocatables by year",null,29358,23112,17783,8392,5387,16806.4]
[null,"Total number of CO-FTE students projected by year",null,151989,154629,157761,160502,163136,157603.4]
[null,"Percent in relocatables by year",null,0.19,0.15,0.11,0.05,0.03,0.11]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,79,110,156,9213,12712,22844]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,86,113,165,9863,13571,18853]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,68,128,222,14900,18106,26448]
[]
["3a.","2001-02 Year","Type of School (new schools only)  Others=0","2001-02","2001-02 ","2001-02","2001-02","2000 State Avg","2000 State Avg","2000 State Avg","2000 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"96-DD Lantana Middle Replacement",2,16559597,1131,152194,134.57,86,86,165,14641.55]
[null,"98-EE WPB Area Middle",2,22125758,1444,189872,131.49,86,86,165,15322.55]
[null,"99-HH Acreage Area Middle",2,20824778,1449,189295,130.64,86,86,165,14371.83]
[null,"98-II Western Lake Worth Area Middle",2,22385316,1449,189872,131.04,86,86,165,15448.8]
[null,"91-EEE West Boynton High",3,51211146,1895,303903,160.37,68,68,222,27024.35]
[null,"01-LLL West Boca/Delray Area High",3,51211146,1895,303903,160.37,68,68,222,27024.35]
[null,"Belvedere Elementary Modernization",0,8656666,753,344838,457.95,0,0,0,11496.24]
[null,"Coral Sunset Elementary Addition",0,2479113,173,174945,1011.24,0,0,0,14330.13]
[null,"Greenacres Elementary Modernization",0,8442977,650,81427,125.27,0,0,0,12989.2]
[null,"Hammock Point Elementary Addition",0,1322912,195,9006,46.18,0,0,0,6784.16]
[null,"South Olive Elementary Modernization",0,10233451,656,81288,123.91,0,0,0,15599.77]
[null,"Wm T. Dwyer High Addition",0,4946553,199,30681,154.18,0,0,0,24857.05,0,0,0]
["3a.","Palm Beach County Total 2001-02",null,220399413,11889,2051224,172.53,null,null,null,18538.1]
[]
["3b.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03 ","2002-03 ","2002-03 ","2002-03 ","2000 State Avg","2000 State Avg","2000 State Avg","2001 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Elem School \"Q\"",1,11968344,770,105831,137.44,79,110,156,15543.3,9213,12712,22844]
[null,"New Elem School \"R\"",2,11968344,770,105831,137.44,86,113,165,15543.3,9863,13571,18853]
[null,"John I Leonard High Modernization",3,54614753,2753,244663,88.87,68,128,222,19838.27,14900,18106,26448]
["3b","Palm Beach County Total 2002-03",null,78551441,4293,456325,106.3,null,null,null,18297.56]
[]
["3c.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[{"$nulls":6},0,0,0,0,0,0,0,0]
["3c","Palm Beach County Total 2003-04",null,0,0,0,0,null,null,null,0]
[]
["3d.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
["3d.","Palm Beach County Total 2004-05",null,0,0,0,0,null,null,null,0]
[]
["3e.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,null,null,0,0,0,null,0,0,0,0,0,0,0]
["3e","Palm Beach County Total 2005-06",null,0,0,0,{"$nulls":4},0]
[]
["3f.","Palm Beach County 5-Year Total",null,298950854,16182,2507549]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,155304942,162800000,170800000,179100000,187900000,855904942]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,155304942,162800000,170800000,179100000,187900000,855904942,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,5000000,5000000,4990164,4422340,5000000,24412504,0.03]
[null,"  less amount used to purchase other vehicles",null,1600000,1600000,0,0,1600000,4800000,0.01]
[null,"  less amount transferred to operating budget for maintenance/repair",null,34700000,34900000,35100000,35300000,35500000,175500000,0.21]
[null,"  less amount used for maintenance/repair",null,35052211,22273171,25199836,26379000,24854000,133758218,0.16]
[null,"  less amount used to purchase capital outlay equipment",null,23323288,26971090,21510000,19998660,19275030,111078068,0.13]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,48000000,61800000,74600000,83400000,90000000,357800000,0.42]
[null,"  less amount used to purchase land",null,0,0,0,0,0,0]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,7629443,10255739,9400000,9600000,11670970,48556152,0.0567307765352288,0.05]
[null,"P E C O New Construction",null,17572818,11609829,6877364,5868140,6106331,48034482,null,0.05]
[null,"C O & D S   Bond Proceeds  ",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,700000,700000,700000,700000,700000,3500000,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,125182753,345617708,117925333,129611545,38803668,757141007,null,0.84]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,9000000,9000000,9000000,9000000,9000000,45000000,null,0.05]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","Palm Beach County Total",null,160085014,377183276,143902697,154779685,66280969,902231641,1.0167307765352287,0.99]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Addison Mizner Elementary Remodeling",null,105965,0,0,null,null,105965]
[null,"Atlantic High School Modernization",null,2329480,45347887,1108680,null,null,48786047]
[null,"Auditoriums - High Schools",null,204750,3717500,3743250,3743250,3648750,15057500]
[null,"Belvedere Elementary Modernization",null,8656666,{"$nulls":4},8656666]
[null,"Boca Raton Elementary Modernization",null,362778,{"$nulls":4},362778]
[null,"Boca Raton High School Modernization",null,45589532,1000966,null,null,null,46590498]
[null,"Career Academies Modifications",null,2000000,{"$nulls":4},2000000]
[null,"Central Bus Compound",null,7778888,{"$nulls":4},7778888]
[null,"Conniston Middle School Modernization",null,1685617,385617,null,null,null,2071234]
[null,"Coral Sunset Elementary Addition",null,105000,2374113,null,null,null,2479113]
[null,"Dreyfoos SOA Addition",null,5637222,{"$nulls":4},5637222]
[null,"Forest Hill Elementary Modernization",null,454224,{"$nulls":4},454224]
[null,"Forest Hill High Modernization",null,119988,34648265,845080,null,null,35613333]
[null,"Future School Modernizations",null,null,31665608,109024423,78679735,49854973,269224739]
[null,"Greenacres Elementary Modernization",null,8442977,{"$nulls":4},8442977]
[null,"H. L. Watkins Middle School Modernization",null,2479050,18886895,462055,null,null,21828000]
[null,"Hammock Point Elementary Addition",null,105000,1217912,null,null,null,1322912]
[null,"John I Leonard High School Modernization",null,null,105000,3215985,51293768,null,54614753]
[null,"Jupiter Elementary Modernization",null,10166153,{"$nulls":4},10166153]
[null,"Jupiter High Modernization",null,3765574,1005575,null,null,null,4771149]
[null,"K-3 Class Size Reduction",null,356860,{"$nulls":4},356860]
[null,"Lake Park Elementary Modernization",null,481586,{"$nulls":4},481586]
[null,"Lake Worth High Addition - Phase 3",null,226200,{"$nulls":4},226200]
[null,"Lantana Middle Replacement",null,16308540,251057,null,null,null,16559597]
[null,"Needs Assessment",null,225000,{"$nulls":4},225000]
[null,"New Elementary School \"A\"","Jupiter Area Elementary",86358,{"$nulls":4},86358]
[null,"New Elementary School \"B\"","Frontier Elementary",59418,{"$nulls":4},59418]
[null,"New Elementary School \"D\"","Okeechobee Elementary",513838,{"$nulls":4},513838]
[null,"New  Elementary School \"H\"","Sunrise Park Elementary",52987,{"$nulls":4},52987]
[null,"New Elementary School \"I\"","Boynton/Delray Area Elementary",501923,{"$nulls":4},501923]
[null,"New Elementary School \"J\"","Western Communities Elementary",501448,{"$nulls":4},501448]
[null,"New Elementary School \"K\"","W Palm Beach Area Elementary",508886,{"$nulls":4},508886]
[null,"New Elementary School \"L\"","Discovery Key Elementary",48123,{"$nulls":4},48123]
[null,"New Elementary School \"M\"","Boynton/Delray Area Elementary",485904,{"$nulls":4},485904]
[null,"New Elementary School \"N\"","Pleasant City Elementary",441100,{"$nulls":4},441100]
[null,"New Elementary School \"Q\"","Acreage Area Elementary",null,11968344,null,null,null,11968344]
[null,"New Elementary School \"R\"","West Lake Worth/Lantana Elementary",null,11968344,null,null,null,11968344]
[null,"New High School \"EEE\"","West Boynton High",1575000,48596714,1039432,null,null,51211146]
[null,"New High School \"III\"","Boynton Beach High ",208445,{"$nulls":4},208445]
[null,"New High School \"JJJ\"","Central WPB Area High",4065814,1045814,null,null,null,5111628]
[null,"New High School \"LLL\"","West Boca/Delray Area High",1575000,48596714,1039432,null,null,51211146]
[null,"New Middle School \"BB\"","Odyssey Community Middle",155833,{"$nulls":4},155833]
[null,"New Middle School \"EE\"","West Palm Beach Area Middle",21694192,431566,null,null,null,22125758]
[null,"New Middle School \"FF\"","Jupiter Area Middle",598930,132977,null,null,null,731907]
[null,"New Middle School \"GG\"","Boca Raton Area Middle",60063,19149236,369615,null,null,19578914]
[null,"New Middle School \"HH\"","Acreage Area Middle",105000,20321569,398209,null,null,20824778]
[null,"New Middle School \"II\"","Western Lake Worth Area Middle",1355120,20524715,505481,null,null,22385316]
[null,"Palm Beach Public Modernization",null,6748260,{"$nulls":4},6748260]
[null,"Palm Springs Elementary Modernization",null,556250,10959950,null,null,null,11516200]
[null,"Palmetto Elementary Modernization",null,692957,{"$nulls":4},692957]
[null,"Roosevelt Elementary Modernization",null,556250,10946598,null,null,null,11502848]
[null,"S.D. Spady Elementary Addition",null,105000,{"$nulls":4},105000]
[null,"South Olive Elementary Modernization",null,10233451,{"$nulls":4},10233451]
[null,"Stadiums - High Schools",null,735000,2205000,2940000,null,735000,6615000]
[null,"U.B.Kinsey/Palmview Elem Modernization",null,7351678,{"$nulls":4},7351678]
[null,"Village Academy Secondary Level",null,5000,{"$nulls":4},5000]
[null,"West Gate Elementary Modernization",null,343707,{"$nulls":4},343707]
[null,"Wm. T. Dwyer High School Classroom Addition",null,4946553,{"$nulls":4},4946553]
["5.","Palm Beach County Total",0,184454538,347453936,124691642,133716753,54238723,844555592]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,1000000,1000000,1000000,0,0,3000000]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","Palm Beach County Total",null,1000000,1000000,1000000,0,0,3000000]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["7.","Palm Beach County Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2001-02 ","2002-03 ","2003-04 ","2004-05","2005-06","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2001."]
[]
[null,"SCHOOL BOARD OF ","Palm Beach County  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}