{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","02_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"02_5YrWkPlan","index":1,"n_rows":1212,"n_cols":25,"rows_kept":1212,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Palm Beach County  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Palm Beach County   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to DOE, Office of Educational Facilities , and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format (email: janet.burns@fldoe.org), as you received it (not a fax), prior to October 1, 2002, and all data accurate as of July 15, 2002.",{"$nulls":8},"2003-01-09T19:26:04.700",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Palm Beach County","Date: ==>","2002-10-01",null,"For fiscal years","  2002-2003 through 2006-2007"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"ADA Compliance",null,896086,956651,1021456,1090797,1164991,5129981]
[null,"Facilities Management Misc. Projects",null,50000,50000,50000,50000,50000,250000]
[null,"Fire & life Safety Systems",null,896086,956651,1021456,1090797,1164991,5129981]
[null,"Health Clinic Compliance",null,358434,382660,408582,436319,465997,2051992]
[null,"Heating, Ventilation & Air Conditioning",null,1254520,1339311,1430038,1527115,1630988,7181972]
[null,"Kitchen HVAC",null,1075303,1147981,1225747,1308956,1397990,6155977]
[null,"Major Renovations & Systems Replacement",null,9273897,9900706,10571391,11289025,12056892,53091911]
[null,"Minor Building Additions/Space Renovations",null,2301212,2456748,2623170,2801243,2991781,13174154]
[null,"PECO Maintenance Projects",null,3523588,4550434,3445421,5184629,5499935,22204007]
[null,"Playground Replacement & Resurfacing",null,716869,765321,817164,872637,931993,4103984]
[null,"Roof Replacement",null,1225909,1308766,1397424,1492287,1593791,7018177]
[null,"Traffic Improvements",null,716869,765321,817164,872637,931993,4103984]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Maintenance, Repair, and Renovation Totals",null,22288773,24580550,24829013,28016442,29881342,129596120]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,3523588,4550434,3445421,5184629,5499935,22204007]
["1.","Palm Beach County Total",null,18765185,20030116,21383592,22831813,24381407,107392113]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New Schools"]
[null,"Acreage Area Elem (00-Q)",null,14362240,0,0,0,0,14362240]
[null,"Acreage Area High (02-NNN)",null,3888881,54125213,0,0,0,58014094]
[null,"Acreage Area Middle (99-HH)",null,23866094,0,0,0,0,23866094]
[null,"Boca Raton Area Middle (98-GG)",null,24415226,0,0,0,0,24415226]
[null,"Okeechobee/Jog Rd Area Elem (02-T)",null,14761717,0,0,0,0,14761717]
[null,"Riviera Beach Area High ((02-MMM)",null,5398188,57123402,0,0,0,62521590]
[null,"Wellington Area Elem (02-U)",null,0,0,0,1692437,16387894,18080331]
[null,"Wellington Area Middle (02-JJ)",null,2946242,25734718,0,0,0,28680960]
[null,"Western Lake Worth Area Middle (98-II)",null,28022738,{"$nulls":4},28022738]
[{"$nulls":8},0]
[null,"Modernizations, Additions, Replacements",{"$nulls":6},0]
[null,"Atlantic High Career Academy & Add'l Capacity",null,926104,10876473,0,0,0,11802577]
[null,"Atlantic High Modernization",null,4027238,49443909,0,0,0,53471147]
[null,"Auditoriums-High Schools",null,4331250,4263000,4263000,4121250,0,16978500]
[null,"Berkshire Elem Modernization",null,0,1721692,15130227,0,0,16851919]
[null,"Boca Raton High Career Academy",null,0,152744,2624278,0,0,2777022]
[null,"Boca Raton High Modernization",null,1000966,0,0,0,0,1000966]
[null,"Conniston Middle Modernization",null,385617,0,0,0,0,385617]
[null,"Coral Sunset Elem Add",null,109941,2322308,0,0,0,2432249]
[null,"Delray Full Service Center",null,100000,6916581,0,0,0,7016581]
[null,"Future Classroom Additions",null,0,1768080,18501783,0,0,20269863]
[null,"Future School Modernizations",null,0,4326188,47446363,59369449,114678097,225820097]
[null,"H.L. Watkins Middle School Modernization",null,21837328,0,0,0,0,21837328]
[null,"Hammock Point Elem Add",null,152227,2594599,0,0,0,2746826]
[null,"J.F. Kennedy Middle Mod/Add",null,0,3025276,26192449,0,0,29217725]
[null,"Jefferson Davis Middle Modernization",null,2880317,24099716,0,0,0,26980033]
[null,"John I. Leonard High Modernization",null,0,5764987,55731141,0,0,61496128]
[null,"Jupiter High School Career Academy",null,251857,4259608,0,0,0,4511465]
[null,"Lantana Elem Modernization",null,12662187,0,0,0,0,12662187]
[null,"Meadow Park Elem Modernization",null,1530644,13467221,0,0,0,14997865]
[null,"Middle School of the Arts Modernization",null,3029660,26224019,0,0,0,29253679]
[null,"Palm Beach Public Modernization",null,11430825,0,0,0,0,11430825]
[null,"Palm Springs Elementary Modernization",null,17073526,0,0,0,0,17073526]
[null,"Roosevelt Elementary Modernization",null,16964687,0,0,0,0,16964687]
[null,"S.D. Spady Elementary School Mod/Addition",null,0,1058443,9634741,0,0,10693184]
[null,"Stadiums-High Schools",null,2100000,0,0,0,0,2100000]
[null,"Village Academy Secondary Level",null,1779723,16483259,0,0,0,18262982]
[null,"West Tech at Glades Central",null,0,0,554100,8300990,0,8855090]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2 .","Palm Beach County Total",null,220235423,315751436,180078082,73484126,131065991,920615058]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2001-02 FISH Satisfactory","Actual 2001-02","Actual 2001-02","Actual 2001-02","New Stu Capacity to","Projected 2006-07","Projected 2006-07"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"AW Dreyfoos School of Arts",1457,1311,1319,1.01,0,1320,1.01]
[null,"Acreage Pines Elementary",917,917,891,0.97,-155,753,0.99]
[null,"Addison Mizner Elementary",657,657,870,1.32,0,703,1.07]
[null,"Adult Education Center",688,1032,51,0.05,0,51,0.05]
[null,"Allamanda Elementary",851,851,604,0.71,0,593,0.7]
[null,"Atlantic High",2169,2060,2199,1.07,440,2496,1]
[null,"Banyan Creek Elementary",957,957,961,1,-158,770,0.96]
[null,"Barton Elementary",880,880,715,0.81,-8,773,0.89]
[null,"Beacon Cove Intermediate",969,969,1014,1.05,0,972,1]
[null,"Bear Lakes Middle",2059,1853,1444,0.78,-669,1144,0.97]
[null,"Belle Glade Elementary",990,990,799,0.81,0,624,0.63]
[null,"Belvedere Elementary",632,632,557,0.88,121,592,0.79]
[null,"Berkshire Elementary",783,783,888,1.13,187,963,0.99]
[null,"Binks Forest Elementary",1000,1000,1137,1.14,0,1038,1.04]
[null,"Boca Raton Elementary",540,540,313,0.58,-50,461,0.94]
[null,"Boca Raton High",2263,2149,1816,0.85,-149,1805,0.9]
[null,"Boca Raton Middle",1315,1183,1118,0.95,33,1123,0.92]
[null,"Boynton Beach High",2600,2470,1867,0.76,0,2494,1.01]
[null,"CoTaylor/Kirklane Elementary",1020,1020,1118,1.1,-147,820,0.94]
[null,"Calusa Elementary",1339,1339,460,0.34,-578,515,0.68]
[null,"Carver Middle",1485,1337,1435,1.07,0,1510,1.13]
[null,"Christa McAuliffe Middle",1393,1253,1400,1.12,-50,1243,1.03]
[null,"Citrus Cove Elementary",959,959,1478,1.54,11,1060,1.09]
[null,"Congress Middle",1685,1516,1296,0.85,-172,1475,1.1]
[null,"Conniston Middle",1776,1598,990,0.62,-298,1226,0.94]
[null,"Coral Reef Elementary",1000,1000,1300,1.3,0,1075,1.08]
[null,"Coral Sunset Elementary",934,934,1015,1.09,36,1068,1.1]
[null,"Crestwood Middle",1746,1571,1510,0.96,-372,1259,1.05]
[null,"Crystal Lakes Elementary",871,871,1033,1.19,99,980,1.01]
[null,"Cypress Trails Elementary",834,834,1012,1.21,136,941,0.97]
[null,"DD Eisenhower Elementary",1169,1169,521,0.45,-268,554,0.61]
[null,"Del Prado Elementary",975,975,821,0.84,-208,752,0.98]
[null,"Delray Full Service Center",1265,1265,221,0.17,-248,300,0.29]
[null,"Discovery Key Elementary",961,961,781,0.81,0,1039,1.08]
[null,"Dr. Mary McLeod Bethune Elem.",1015,1015,643,0.63,0,666,0.66]
[null,"Eagles Landing Middle",1556,1400,1488,1.06,-70,1295,0.97]
[null,"Egret Lake Elementary",1023,1023,837,0.82,-238,682,0.87]
[null,"Forest Hill Elementary",1182,1182,1111,0.94,-212,1058,1.09]
[null,"Forest Hill High",1738,1651,1486,0.9,149,1848,1.03]
[null,"Forest Park Elementary",903,903,676,0.75,-154,732,0.98]
[null,"Frontier Elementary",960,960,754,0.79,0,895,0.93]
[null,"Galaxy Elementary",657,657,685,1.04,-24,630,1]
[null,"Glade View Elementary",779,779,494,0.63,-36,460,0.62]
[null,"Glades Central High",1674,1590,1361,0.86,288,1900,1.01]
[null,"Gold Coast Community School",367,367,450,1.23,0,550,1.5]
[null,"Golden Grove Elementary",1262,1262,1084,0.86,-262,948,0.95]
[null,"Gove Elementary",1030,1030,807,0.78,-94,855,0.91]
[null,"Greenacres Elementary",669,669,577,0.86,0,615,0.92]
[null,"Grove Park Elementary",734,734,768,1.05,-27,613,0.87]
[null,"HL Johnson Elementary",849,849,1249,1.47,-48,801,1]
[null,"Hagen Road Elementary",713,713,532,0.75,0,638,0.89]
[null,"Hammock Pointe Elementary",957,957,998,1.04,13,1000,1.03]
[null,"Heritage Elementary",1104,1104,1277,1.16,-66,1038,1]
[null,"Highland Elementary",848,848,803,0.95,0,827,0.98]
[null,"Howell L. Watkins Middle",1286,1157,1205,1.04,-22,1123,0.99]
[null,"Indian Pines Elementary",1025,1025,943,0.92,-55,965,0.99]
[null,"Indian Ridge School",151,151,110,0.73,-29,56,0.46]
[null,"Inlet Grove High",610,732,394,0.54,-732,0,0]
[null,"JC Mitchell Elementary",825,825,706,0.86,145,704,0.73]
[null,"Jefferson Davis Middle",1900,1710,1730,1.01,-355,1449,1.07]
[null,"Jerry Thomas Elementary",957,957,870,0.91,13,991,1.02]
[null,"John F. Kennedy Middle",1462,1315,1134,0.86,185,1481,0.99]
[null,"John I. Leonard High",2904,2758,2969,1.08,-142,2804,1.07]
[null,"Jupiter Elementary",720,720,483,0.67,30,682,0.91]
[null,"Jupiter Farms Elementary",783,783,783,1,0,831,1.06]
[null,"Jupiter High",2866,2722,1723,0.63,-222,2508,1]
[null,"Jupiter Middle",1447,1302,1543,1.19,-46,1373,1.09]
[null,"KE Cunningham/Canal Pt. Elem.",935,935,575,0.61,-38,531,0.59]
[null,"Lake Park Elementary",394,394,501,1.27,96,426,0.87]
[null,"Lake Shore Middle",1702,1531,1208,0.79,11,1215,0.79]
[null,"Lake Worth Middle",1649,1484,1586,1.07,-256,1348,1.1]
[null,"Lake Worth High",3208,3047,2941,0.97,-255,3022,1.08]
[null,"Lantana Elementary",752,752,641,0.85,-101,513,0.79]
[null,"Lantana Middle",731,657,868,1.32,343,1003,1]
[null,"Liberty Park Elementary",1131,1131,1184,1.05,-161,1032,1.06]
[null,"Lighthouse Elementary",187,1187,635,0.53,-409,828,1.06]
[null,"Limestone Creek Elementary",890,890,1010,1.13,80,996,1.03]
[null,"Lincoln Elementary",1501,1501,1050,0.7,-301,1083,0.9]
[null,"Loggers Run Middle",1631,1467,1383,0.94,-251,1165,0.96]
[null,"Loxahatchee Groves Elementary",916,916,755,0.82,-143,834,1.08]
[null,"Manatee Elementary",1044,1044,1277,1.22,-44,902,0.9]
[null,"Meadow Park Elementary",785,785,545,0.69,-142,550,0.86]
[null,"Melaleuca Elementary",984,984,1130,1.15,-175,874,1.08]
[null,"Middle School of the Arts",1091,981,1242,1.27,319,1250,0.96]
[null,"Morikami Park Elementary",996,996,1001,1.01,0,1000,1]
[null,"New Horizons Elementary",762,762,772,1.01,0,783,1.03]
[null,"North Grade Elementary",825,825,716,0.87,1,831,1.01]
[null,"North Palm Beach Elementary",834,834,570,0.68,0,795,0.95]
[null,"Northboro Elementary",932,932,693,0.74,-44,545,0.61]
[null,"Northmore Elementary",880,880,693,0.79,0,630,0.72]
[null,"Odyssey Middle",1416,1274,952,0.75,0,1381,1.08]
[null,"Okeeheelee Middle",1819,1637,1636,1,-327,1318,1.01]
[null,"Olympic Heights High",2661,2527,2548,1.01,-28,2408,0.96]
[null,"Omni Middle",1458,1312,1251,0.95,-61,1106,0.88]
[null,"Orchard View Elementary",1071,1071,904,0.84,-66,725,0.72]
[null,"Pahokee Elementary",816,816,582,0.71,0,494,0.61]
[null,"Pahokee Middle/Sr. High",1465,1318,1037,0.79,-23,1050,0.81]
[null,"Palm Beach Gardens Elementary",717,717,683,0.95,-59,644,0.98]
[null,"Palm Beach Gardens High",2377,2258,2506,1.11,-29,2172,0.97]
[null,"Palm Beach Lakes High",3223,3061,2780,0.91,-484,2446,0.95]
[null,"Palm Beach Public",417,417,398,0.95,73,400,0.82]
[null,"Palm Springs Elementary",616,616,619,1,354,946,0.98]
[null,"Palmetto  Elementary",469,469,608,1.3,501,662,0.68]
[null,"Panther Run Elementary",1037,1037,1129,1.09,-67,1062,1.09]
[null,"Pine Grove Elementary",892,892,736,0.83,-30,846,0.98]
[null,"Pioneer Park Elementary",1015,1015,604,0.6,0,563,0.55]
[null,"Plumosa Elementary",698,698,567,0.81,-46,561,0.86]
[null,"Poinciana Elementary",922,922,678,0.74,0,685,0.74]
[null,"Polo Park Middle",1493,1343,1230,0.92,1,1202,0.89]
[null,"Rolling Green Elementary",964,964,849,0.88,-147,889,1.09]
[null,"Roosevelt Elementary",951,951,900,0.95,19,718,0.74]
[null,"Roosevelt Full Service Center",615,615,205,0.33,-615,0,0]
[null,"Roosevelt Middle",1457,1311,1411,1.08,0,1418,1.08]
[null,"Rosenwald Elementary",722,722,397,0.55,-44,411,0.61]
[null,"Royal Palm School",402,402,221,0.55,0,122,0.3]
[null,"Royal Palm Beach High",2642,2509,2631,1.05,1,2420,0.96]
[null,"SD Spady Elementary",547,547,480,0.88,53,523,0.87]
[null,"Sabal Palm School (High Ridge)",78,78,52,0.67,0,0,0]
[null,"Sandpiper Shores Elementary",1021,1021,765,0.75,-231,782,0.99]
[null,"Santaluces High",2857,2714,2880,1.06,-226,2541,1.02]
[null,"School of Choice",636,636,148,0.23,0,0,0]
[null,"Seminole Trails Elementary",848,848,885,1.04,-22,764,0.92]
[null,"So. Area Middle School of Choice",392,392,127,0.32,0,0,0]
[null,"South Grade Elementary",808,808,872,1.08,0,783,0.97]
[null,"South Olive Elementary",761,761,788,1.04,39,651,0.81]
[null,"South Technical Education Ctr.",809,970,704,0.73,-970,0,0]
[null,"Spanish River High",2892,2747,3076,1.12,-369,2253,0.95]
[null,"Starlight Cove Elementary",1073,1073,940,0.88,-98,957,0.98]
[null,"Suncoast High",1269,1142,1298,1.14,-54,1250,1.15]
[null,"Sunrise Park Elementary",962,962,728,0.76,0,918,0.95]
[null,"Timber Trace Elementary",894,894,834,0.93,-69,887,1.08]
[null,"UB Kinsey/Palmview Elementary",645,645,641,0.99,105,662,0.88]
[null,"Verde Elementary",766,766,771,1.01,-7,760,1]
[null,"Village Academy Center",487,487,280,0.57,170,448,0.68]
[null,"Washington Elementary",689,689,563,0.82,-99,585,0.99]
[null,"Waters' Edge Elementary",1114,1114,1098,0.99,-94,1100,1.08]
[null,"Watson B. Duncan Middle",1352,1216,1347,1.11,-50,1235,1.06]
[null,"Wellington Elementary",934,934,1002,1.07,0,985,1.05]
[null,"Wellington High",2955,2807,3320,1.18,-285,2400,0.95]
[null,"Wellington Landings Middle",1185,1066,1488,1.4,1,1065,1]
[null,"West Gate Elementary",1233,1233,745,0.6,-219,778,0.77]
[null,"West Riviera Elementary",1129,1129,814,0.72,-208,788,0.86]
[null,"West Technical Education Ctr.",759,910,207,0.23,-910,0,0]
[null,"Western Pines Middle",1657,1491,1553,1.04,-150,1364,1.02]
[null,"Westward Elementary",949,949,709,0.75,-208,705,0.95]
[null,"Whispering Pines Elementary",1027,1027,782,0.76,-202,842,1.02]
[null,"William T. Dwyer High",2026,1924,2208,1.15,1,1936,1.01]
[null,"Woodlands Middle",1982,1783,1870,1.05,-271,1371,0.91]
[null,"Wynnebrook Elementary",1022,1022,1095,1.07,-317,655,0.93]
["2a.","Palm Beach County Total",172948,168260,153735,0.91,-11715,146303,0.93]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School (00-Q) (770 Stu Sta) in the Acreage area of West Palm Beach, FL to accommodate growth."]
[null,"New Crosspointe Elementary School (98-I) (970 Stu Sta) on Congress Ave. south of Golf Road in Delray Beach, FL to accommodate growth."]
[null,"New Freedom Shores Elementary School (97-M) (970 Stu Sta) on Hypoluxo Road west of Congress Ave. in Boynton Beach, FL to accommodate growth."]
[null,"New Elementary School (96-D) (970 Stu Sta) on Benoist Farms Rd. south of Okeechobee Blvd. in West Palm Beach, FL to accommodate growth."]
[null,"New Elementary School (02-T) (770 Stu Sta) on Jog Rd. north of Okeechobee Blvd. in West Palm Beach, FL to accommodate growth."]
[null,"New Pleasant City Elementary School (98-N) (490 Stu Sta) in the Pleasant City neighborhood of West Palm Beach, FL to accommodate growth."]
[null,"New Royal Palm Beach Elementary School (96-J) (970 Stu Sta) in the Madison Green neighborhood of Royal Palm Beach, FL to accommodate growth."]
[null,"New Cholee Lake Elementary School (97-K) (970 Stu Sta) on Dillman Rd. west of Jog Rd. in Greenacres, FL to accommodate growth."]
[null,"New Elementary School (02-S) (970 Stu Sta) in the Olympia neighborhood of Wellington, FL to accommodate growth."]
[null,"New Elementary School (02-U) (970 Stu Sta) in the Birkdale neighborhood of Wellington, FL to accommodate growth."]
[null,"New Elementary School (01-R) (970 Stu Sta) on Haverhill Rd. south of Melaleuca Lane in Lantana, FL to accommodate growth."]
[null,"New Middle School (99-HH) (1000 Stu Sta) in the Acreage area of West Palm Beach, FL to accommodate growth."]
[null,"New Middle School (98-GG) (1000 Stu Sta) on Spanish River Blvd. east of Military Trail in Boca Raton, FL to accommodate growth."]
[null,"New Independence Middle School (98-FF) (1300 Stu Sta) in the Abacoa community of Jupiter, FL to accommodate growth."]
[null,"New Middle School (98-EE) (1300 Stu Sta) on Jog Rd. north of Okeechobee Blvd. in West Palm Beach, FL to accommodate growth."]
[null,"New Middle School (02-JJ) (1000 Stu Sta) in the Olympia neighborhood of Wellington, FL to accommodate growth."]
[null,"New Middle School (98-II) (1300 Stu Sta) on Haverhill Rd. south of Melaleuca Lane in Lantana, FL to accommodate growth."]
[null,"New High School (02-NNN) (1800 Stu Sta) in the Acreage area of West Palm Beach, FL to accommodate growth."]
[null,"New High School (98-JJJ) (2500 Stu Sta) in the Olympia neighborhood of Wellington, FL to accommodate growth."]
[null,"New High School (02-MMM) (1800 Stu Sta) south of Broadway, west of US-1 in Riviera Beach, FL to accommodate growth."]
[null,"New High School (01-LLL) (1800 Stu Sta) on Glades Road in the vicinity of the Boca Falls neighborhood in Boca Raton, FL to accommodate growth."]
[null,"New High School (91-EEE) (2500 Stu Sta) on Jog Rd. south of Hypoluxo Rd. in Boynton Beach, FL to accommodate growth."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2001-02","Owner","Student Stations","as classroom space","in 2006-07","units by 2006-07","Column \"C\""]
[null,"AW Dreyfoos School of Arts",0,"-",0,0,0,0,0]
[null,"Acreage Pines Elementary",15,"PBCSB",370,8,0,15,176]
[null,"Addison Mizner Elementary",10,"PBCSB/Leased",252,10,4,6,200]
[null,"Adult Education Center",7,"PBCSB/Leased",209,0,7,0,124]
[null,"Allamanda Elementary",0,"-",0,0,0,0,0]
[null,"Atlantic High",20,"PBCSB/Leased",597,9,0,20,199]
[null,"Banyan Creek Elementary",17,"PBCSB/Leased",393,10,0,17,282]
[null,"Barton Elementary",17,"PBCSB/Leased",336,16,19,-2,271]
[null,"Beacon Cove Intermediate",0,"-",0,0,0,0,0]
[null,"Bear Lakes Middle",31,"PBCSB",829,3,0,31,558]
[null,"Belle Glade Elementary",1,"PBCSB",25,1,0,1,18]
[null,"Belvedere Elementary",6,"PBCSB",144,4,0,6,95]
[null,"Berkshire Elementary",18,"PBCSB/Leased",455,14,0,18,358]
[null,"Binks Forest Elementary",0,"-",0,0,1,-1,0]
[null,"Boca Raton Elementary",0,"-",0,0,0,0,0]
[null,"Boca Raton High",12,"PBCSB/Leased",285,6,0,12,247]
[null,"Boca Raton Middle",16,"PBCSB/Leased",333,15,1,15,512]
[null,"Boynton Beach High",0,"-",0,0,1,-1,0]
[null,"CoTaylor/Kirklane Elementary",18,"PBCSB",443,12,4,14,452]
[null,"Calusa Elementary",24,"PBCSB",578,0,0,24,38]
[null,"Carver Middle",14,"PBCSB/Leased",366,14,16,-2,253]
[null,"Christa McAuliffe Middle",15,"PBCSB/Leased",377,13,3,12,170]
[null,"Citrus Cove Elementary",34,"PBCSB/Leased",819,26,4,30,129]
[null,"Congress Middle",17,"PBCSB/Leased",397,9,6,11,350]
[null,"Conniston Middle",19,"PBCSB",471,2,0,19,83]
[null,"Coral Reef Elementary",0,"PBCSB",0,0,3,-3,0]
[null,"Coral Sunset Elementary",13,"PBCSB/Leased",335,9,4,9,203]
[null,"Crestwood Middle",26,"PBCSB/Leased",675,10,4,22,448]
[null,"Crystal Lakes Elementary",10,"PBCSB/Leased",238,6,0,10,129]
[null,"Cypress Trails Elementary",6,"PBCSB",153,4,0,6,82]
[null,"DD Eisenhower Elementary",4,"PBCSB",293,1,4,0,139]
[null,"Del Prado Elementary",11,"PBCSB/Leased",285,3,0,11,119]
[null,"Delray Full Service Center",6,"PBCSB",134,0,0,6,87]
[null,"Discovery Key Elementary",0,"-",0,0,3,-3,0]
[null,"Dr. Mary McLeod Bethune Elem.",0,"-",0,0,0,0,0]
[null,"Eagles Landing Middle",13,"PBCSB/Leased",352,10,0,13,241]
[null,"Egret Lake Elementary",14,"PBCSB/Leased",339,4,0,14,506]
[null,"Forest Hill Elementary",35,"PBCSB/Leased",832,14,5,30,630]
[null,"Forest Hill High",15,"PBCSB/Leased",323,13,0,15,258]
[null,"Forest Park Elementary",11,"PBCSB/Leased",277,5,6,5,72]
[null,"Frontier Elementary",0,"-",0,0,0,0,0]
[null,"Galaxy Elementary",2,"PBCSB",60,2,0,2,62]
[null,"Glade View Elementary",16,"PBCSB/Leased",345,14,3,13,297]
[null,"Glades Central High",1,"Leased",30,0,0,1,15]
[null,"Gold Coast Community School",5,"PBCSB/Leased",96,1,5,0,71]
[null,"Golden Grove Elementary",10,"PBCSB",262,0,0,10,180]
[null,"Gove Elementary",21,"PBCSB/Leased",494,17,6,15,337]
[null,"Greenacres Elementary",1,"PBCSB",22,1,0,1,37]
[null,"Grove Park Elementary",2,"PBCSB",53,1,0,2,24]
[null,"HL Johnson Elementary",29,"PBCSB/Leased",669,27,0,29,554]
[null,"Hagen Road Elementary",2,"PBCSB",25,2,2,0,40]
[null,"Hammock Pointe Elementary",11,"PBCSB",262,3,2,9,127]
[null,"Heritage Elementary",5,"PBCSB/Leased",115,0,2,3,12]
[null,"Highland Elementary",0,null,0,0,0,0,0]
[null,"Howell L. Watkins Middle",7,"PBCSB/Leased",142,2,0,7,104]
[null,"Indian Pines Elementary",19,"PBCSB/Leased",435,8,0,19,202]
[null,"Indian Ridge School",9,"PBCSB/Leased",70,0,9,0,90]
[null,"Inlet Grove High",10,"PBCSB",261,9,0,10,317]
[null,"JC Mitchell Elementary",6,"PBCSB",133,4,0,6,141]
[null,"Jefferson Davis Middle",27,"PBCSB",405,11,6,21,422]
[null,"Jerry Thomas Elementary",7,"PBCSB/Leased",167,0,0,7,70]
[null,"John F. Kennedy Middle",23,"PBCSB/Leased",600,19,7,16,417]
[null,"John I. Leonard High",13,"PBCSB/Leased",338,8,8,5,180]
[null,"Jupiter Elementary",0,"-",0,0,0,0,0]
[null,"Jupiter Farms Elementary",0,"-",0,0,3,-3,0]
[null,"Jupiter High",0,"-",0,0,0,0,0]
[null,"Jupiter Middle",25,"PBCSB/Leased",632,23,6,19,473]
[null,"KE Cunningham/Canal Pt. Elem.",5,"PBCSB",107,3,5,0,91]
[null,"Lake Park Elementary",9,"PBCSB/Leased",205,9,0,9,253]
[null,"Lake Shore Middle",0,"-",0,0,0,0,0]
[null,"Lake Worth Middle",30,"PBCSB/Leased",722,19,6,24,667]
[null,"Lake Worth High",30,"PBCSB/Leased",842,20,8,22,624]
[null,"Lantana Elementary",5,"PBCSB/Leased",126,1,3,2,70]
[null,"Lantana Middle",17,"PBCSB/Leased",467,11,0,17,344]
[null,"Liberty Park Elementary",23,"PBCSB/Leased",531,9,3,20,331]
[null,"Lighthouse Elementary",27,"PBCSB/Leased",689,10,3,24,336]
[null,"Limestone Creek Elementary",10,"PBCSB/Leased",261,7,0,10,206]
[null,"Lincoln Elementary",2,"Federal",47,0,0,2,6]
[null,"Loggers Run Middle",16,"PBCSB",395,4,0,16,143]
[null,"Loxahatchee Groves Elementary",12,"PBCSB/Leased",260,6,16,-4,184]
[null,"Manatee Elementary",9,"PBCSB/Leased",211,7,0,9,159]
[null,"Meadow Park Elementary",12,"PBCSB/Leased",242,5,0,12,164]
[null,"Melaleuca Elementary",16,"PBCSB/Leased",365,8,3,13,257]
[null,"Middle School of the Arts",29,"PBCSB/Leased",791,25,0,29,324]
[null,"Morikami Park Elementary",0,"-",0,0,0,0,0]
[null,"New Horizons Elementary",0,"-",0,0,0,0,0]
[null,"North Grade Elementary",0,"-",0,0,0,0,0]
[null,"North Palm Beach Elementary",0,"-",0,0,0,0,0]
[null,"Northboro Elementary",11,"PBCSB/Leased",260,9,0,11,249]
[null,"Northmore Elementary",0,"-",0,0,0,0,0]
[null,"Odyssey Middle",0,"-",0,0,5,-5,0]
[null,"Okeeheelee Middle",22,"PBCSB/Leased",595,9,0,22,400]
[null,"Olympic Heights High",10,"PBCSB/Leased",300,9,0,10,153]
[null,"Omni Middle",10,"PBCSB/Leased",237,6,0,10,126]
[null,"Orchard View Elementary",3,"PBCSB",66,0,0,3,24]
[null,"Pahokee Elementary",11,"PBCSB/Leased",133,11,0,11,483]
[null,"Pahokee Middle/Sr. High",1,"PBCSB",26,0,0,1,18]
[null,"Palm Beach Gardens Elementary",4,"PBCSB",84,1,4,0,42]
[null,"Palm Beach Gardens High",5,"PBCSB",149,4,0,5,110]
[null,"Palm Beach Lakes High",21,"PBCSB/Leased",630,4,0,21,186]
[null,"Palm Beach Public",0,"-",0,0,0,0,0]
[null,"Palm Springs Elementary",13,"PBCSB/Leased",282,12,0,13,259]
[null,"Palmetto  Elementary",24,"PBCSB/Leased",519,15,0,24,569]
[null,"Panther Run Elementary",14,"PBCSB/Leased",329,4,5,9,305]
[null,"Pine Grove Elementary",10,"PBCSB/Leased",266,9,10,0,254]
[null,"Pioneer Park Elementary",0,"-",0,0,0,0,0]
[null,"Plumosa Elementary",2,"PBCSB",46,0,0,2,60]
[null,"Poinciana Elementary",0,"-",0,0,0,0,0]
[null,"Polo Park Middle",0,"-",0,0,0,0,0]
[null,"Rolling Green Elementary",17,"PBCSB/Leased",433,12,7,10,208]
[null,"Roosevelt Elementary",19,"PBCSB/Leased",428,12,0,19,120]
[null,"Roosevelt Full Service Center",1,"PBCSB",15,0,1,0,18]
[null,"Roosevelt Middle",8,"Leased",224,8,9,-1,120]
[null,"Rosenwald Elementary",5,"PBCSB/Leased",119,3,0,5,76]
[null,"Royal Palm School",13,"PBCSB",122,0,13,0,126]
[null,"Royal Palm Beach High",0,"-",0,0,0,0,0]
[null,"SD Spady Elementary",12,"PBCSB/Leased",268,7,0,12,188]
[null,"Sabal Palm School (High Ridge)",6,"PBCSB",72,6,6,0,240]
[null,"Sandpiper Shores Elementary",11,"PBCSB/Leased",279,2,2,9,173]
[null,"Santaluces High",35,"PBCSB/Leased",1012,27,3,32,824]
[null,"School of Choice",3,"State",90,0,0,3,63]
[null,"Seminole Trails Elementary",9,"PBCSB/Leased",164,8,4,5,278]
[null,"So. Area Middle School of Choice",12,"PBCSB/Leased",293,0,12,0,294]
[null,"South Grade Elementary",0,"-",0,0,0,0,0]
[null,"South Olive Elementary",15,"PBCSB/Leased",318,11,0,15,291]
[null,"South Technical Education Ctr.",19,"PBCSB/Leased",497,11,0,19,534]
[null,"Spanish River High",28,"PBCSB/Leased",828,15,0,28,632]
[null,"Starlight Cove Elementary",9,"PBCSB",238,5,9,0,142]
[null,"Suncoast High",2,"PBCSB",60,0,2,0,10]
[null,"Sunrise Park Elementary",0,"-",0,0,0,0,0]
[null,"Timber Trace Elementary",7,"PBCSB",174,4,4,3,96]
[null,"UB Kinsey/Palmview Elementary",6,"PBCSB",143,5,0,6,166]
[null,"Verde Elementary",5,"PBCSB",97,4,1,4,80]
[null,"Village Academy Center",0,"-",0,0,0,0,0]
[null,"Washington Elementary",9,"PBCSB",239,5,9,0,214]
[null,"Waters' Edge Elementary",4,"PBCSB/Leased",94,0,4,0,61]
[null,"Watson B. Duncan Middle",12,"PBCSB/Leased",257,10,4,8,368]
[null,"Wellington Elementary",12,"PBCSB/Leased",216,12,3,9,333]
[null,"Wellington High",19,"PBCSB/Leased",567,9,0,19,287]
[null,"Wellington Landings Middle",16,"PBCSB/Leased",438,16,0,16,385]
[null,"West Gate Elementary",25,"PBCSB/Leased",582,15,0,25,433]
[null,"West Riviera Elementary",11,"PBCSB",254,3,12,-1,186]
[null,"West Technical Education Ctr.",13,"PBCSB/Leased",343,0,0,13,146]
[null,"Western Pines Middle",14,"PBCSB/Leased",383,8,1,13,319]
[null,"Westward Elementary",11,"PBCSB/Leased",252,2,12,-1,123]
[null,"Whispering Pines Elementary",12,"PBCSB/Leased",250,3,8,4,126]
[null,"William T. Dwyer High",5,"PBCSB/Leased",103,5,1,4,135]
[null,"Woodlands Middle",19,"PBCSB/Leased",518,8,0,19,341]
[null,"Wynnebrook Elementary",24,"PBCSB/Leased",600,11,5,19,554]
["2c1.","Palm Beach County Total",1587,null,38684,887,357,1230,"Avg Age 17.45"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"Acreage Pines Elementary",15,7,null,8,null,null,15]
[null,"Addison Mizner Elementary",6,6,{"$nulls":4},6]
[null,"Atlantic High",20,null,null,null,20,null,20]
[null,"Banyan Creek Elementary",17,10,7,null,null,null,17]
[null,"Bear Lakes Middle",31,null,null,21,10,null,31]
[null,"Belle Glade Elementary",1,null,1,null,null,null,1]
[null,"Belvedere Elementary",6,null,6,null,null,null,6]
[null,"Berkshire Elementary",18,null,null,18,null,null,18]
[null,"Boca Raton High",12,null,null,12,null,null,12]
[null,"Boca Raton Middle",15,8,null,7,null,null,15]
[null,"CoTaylor/Kirklane Elementary",14,null,null,14,null,null,14]
[null,"Calusa Elementary",24,null,24,null,null,null,24]
[null,"Christa McAuliffe Middle",12,null,null,9,3,null,12]
[null,"Citrus Cove Elementary",30,17,null,13,null,null,30]
[null,"Congress Middle",11,4,null,7,null,null,11]
[null,"Conniston Middle",19,null,19,null,null,null,19]
[null,"Coral Sunset Elementary",9,null,null,9,null,null,9]
[null,"Crestwood Middle",22,null,null,22,null,null,22]
[null,"Crystal Lakes Elementary",10,null,10,null,null,null,10]
[null,"Cypress Trails Elementary",6,null,null,6,null,null,6]
[null,"Del Prado Elementary",11,null,null,null,11,null,11]
[null,"Delray Full Service Center",6,null,null,null," ",6,6]
[null,"Eagles Landing Middle",13,null,null,13,null,null,13]
[null,"Egret Lake Elementary",14,null,null,14,null,null,14]
[null,"Forest Hill Elementary",30,30,{"$nulls":4},30]
[null,"Forest Hill High",15,null,null,15,null,null,15]
[null,"Forest Park Elementary",5,5,{"$nulls":4},5]
[null,"Galaxy Elementary",2,null,null,2,null,null,2]
[null,"Glade View Elementary",13,{"$nulls":4},13,13]
[null,"Glades Central High",1,null,null,null,1,null,1]
[null,"Golden Grove Elementary",10,null,null,10,null,null,10]
[null,"Gove Elementary",15,15,{"$nulls":4},15]
[null,"Greenacres Elementary",1,null,1,null,null,null,1]
[null,"Grove Park Elementary",2,null,null,2,null,null,2]
[null,"HL Johnson Elementary",29,22,null,7,null,null,29]
[null,"Hammock Pointe Elementary",9,null,null,9,null,null,9]
[null,"Heritage Elementary",3,null,3,null,null,null,3]
[null,"Howell L. Watkins Middle",7,null,null,7,null,null,7]
[null,"Indian Pines Elementary",19,null,null,19,null,null,19]
[null,"Inlet Grove High",10,null,null,null,10,null,10]
[null,"JC Mitchell Elementary",6,null,null,null,6,null,6]
[null,"Jefferson Davis Middle",21,null,null,21,null,null,21]
[null,"Jerry Thomas Elementary",7,null,null,7,null,null,7]
[null,"John F. Kennedy Middle",16,null,null,16,null,null,16]
[null,"John I. Leonard High",5,null,5,null,null,null,5]
[null,"Jupiter Middle",19,11,8,null,null,null,19]
[null,"Lake Park Elementary",9,9,{"$nulls":4},9]
[null,"Lake Worth Middle",24,null,null,24,null,null,24]
[null,"Lake Worth High",22,22,{"$nulls":4},22]
[null,"Lantana Elementary",2,null,2,null,null,null,2]
[null,"Lantana Middle",17,null,17,null,null,null,17]
[null,"Liberty Park Elementary",20,null,null,20,null,null,20]
[null,"Lighthouse Elementary",24,null,24,null,null,null,24]
[null,"Limestone Creek Elementary",10,null,null,10,null,null,10]
[null,"Lincoln Elementary",2,null,2,null,null,null,2]
[null,"Loggers Run Middle",16,{"$nulls":4},16,16]
[null,"Manatee Elementary",9,null,9,null,null,null,9]
[null,"Meadow Park Elementary",12,12,{"$nulls":4},12]
[null,"Melaleuca Elementary",13,13,{"$nulls":4},13]
[null,"Middle School of the Arts",29,null,null,29,null,null,29]
[null,"Northboro Elementary",11,null,null,7,4,null,11]
[null,"Okeeheelee Middle",22,null,22,null,null,null,22]
[null,"Olympic Heights High",10,null,null,5,5,null,10]
[null,"Omni Middle",10,null,null,10,null,null,10]
[null,"Orchard View Elementary",3,3,{"$nulls":4},3]
[null,"Pahokee Elementary",11,11,{"$nulls":4},11]
[null,"Pahokee Middle/Sr. High",1,null,1,null,null,null,1]
[null,"Palm Beach Gardens High",5,null,null,null,5,null,5]
[null,"Palm Beach Lakes High",21,null,15,6,null,null,21]
[null,"Palm Springs Elementary",13,null,null,13,null,null,13]
[null,"Palmetto Elementary",24,24,{"$nulls":4},24]
[null,"Panther Run Elementary",9,null,6,3,null,null,9]
[null,"Plumosa Elementary",2,2,{"$nulls":4},2]
[null,"Rolling Green Elementary",10,10,{"$nulls":4},10]
[null,"Roosevelt Elementary",19,null,null,19,null,null,19]
[null,"Rosenwald Elementary",5,5,{"$nulls":4},5]
[null,"SD Spady Elementary",12,null,null,12,null,null,12]
[null,"Sandpiper Shores Elementary",9,7,2,null,null,null,9]
[null,"Santaluces High",32,9,null,23,null,null,32]
[null,"School of Choice",3,{"$nulls":4},3,3]
[null,"Seminole Trails Elementary",5,null,null,5,null,null,5]
[null,"South Olive Elementary",15,null,15,null,null,null,15]
[null,"South Technical Education Ctr.",19,null,null,19,null,null,19]
[null,"Spanish River High",28,null,null,26,2,null,28]
[null,"Timber Trace Elementary",3,3,{"$nulls":4},3]
[null,"UB Kinsey/Palmview Elementary",6,null,6,null,null,null,6]
[null,"Verde Elementary",4,4,{"$nulls":4},4]
[null,"Watson B. Duncan Middle",8,5,3,null,null,null,8]
[null,"Wellington Elementary",9,2,7,null,null,null,9]
[null,"Wellington High",19,null,11,8,null,null,19]
[null,"Wellington Landings Middle",16,null,null,12,4,null,16]
[null,"West Gate Elementary",25,25,{"$nulls":4},25]
[null,"West Technical Education Ctr.",13,{"$nulls":4},13,13]
[null,"Western Pines Middle",13,null,null,13,null,null,13]
[null,"Whispering Pines Elementary",4,4,{"$nulls":4},4]
[null,"William T. Dwyer High",4,null,4,null,null,null,4]
[null,"Woodlands Middle",19,null,null,19,null,null,19]
[null,"Wynnebrook Elementary",19,19,{"$nulls":4},19]
["2c2.","Palm Beach County Total",1257,324,230,571,81,51,1257]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2006-07","FISH Stu. Sta.","# Years Leased "]
[null,"Addison Mizner Elementary",4,"Wm. Scotsman",100,15,0,0,0]
[null,"Adult Education Center",2,"Wm. Scotsman",60,15,0,0,0]
[null,"Atlantic High",2,"Wm. Scotsman",60,15,0,0,0]
[null,"Banyan Creek Elementary",4,"Wm. Scotsman",92,15,0,0,0]
[null,"Barton Elementary",11,"Wm. Scotsman",220,6,0,0,0]
[null,"Berkshire Elementary",2,"Wm. Scotsman",50,15,0,0,0]
[null,"Boca Raton High",2,"Wm. Scotsman",48,15,0,0,0]
[null,"Boca Raton Middle",3,"Wm. Scotsman",63,15,0,0,0]
[null,"Carver Middle",13,"Wm. Scotsman",338,15,0,0,0]
[null,"Christa McAuliffe Middle",19,"Wm. Scotsman",475,15,0,0,0]
[null,"Citrus Cove Elementary",11,"Wm. Scotsman",264,9,0,0,0]
[null,"Congress Middle",3,"Wm. Scotsman",69,15,0,0,0]
[null,"Coral Sunset Elementary",2,"Wm. Scotsman",52,15,0,0,0]
[null,"Crestwood Middle",5,"Wm. Scotsman",130,13,0,0,0]
[null,"Crystal Lakes Elementary",1,"Wm. Scotsman",24,15,0,0,0]
[null,"Del Prado Elementary",1,"Wm. Scotsman",26,15,0,0,0]
[null,"Eagles Landing Middle",7,"Wm. Scotsman",189,19,0,0,0]
[null,"Egret Lake Elementary",1,"Wm. Scotsman",24,15,0,0,0]
[null,"Forest Hill Elementary",5,"Wm. Scotsman",110,8,0,0,0]
[null,"Forest Hill High",1,"Wm. Scotsman",21,15,0,0,0]
[null,"Forest Park Elementary",4,"Wm. Scotsman",100,15,0,0,0]
[null,"Glade View Elementary",6,"Wm. Scotsman",126,15,0,0,0]
[null,"Glades Central High",1,"Wm. Scotsman",30,15,0,0,0]
[null,"Gold Coast Community School",3,"Wm. Scotsman",57,15,0,0,0]
[null,"Gove Elementary",10,"Wm. Scotsman",230,15,0,0,0]
[null,"HL Johnson Elementary",4,"Wm. Scotsman",92,15,0,0,0]
[null,"Heritage Elementary",2,"Wm. Scotsman",46,6,0,0,0]
[null,"Howell L. Watkins Middle",1,"Wm. Scotsman",20,15,0,0,0]
[null,"Indian Pines Elementary",12,"Wm. Scotsman",276,6,0,0,0]
[null,"Indian Ridge School",1,"Wm. Scotsman",8,15,0,0,0]
[null,"Jerry Thomas Elementary",2,"Wm. Scotsman",48,15,0,0,0]
[null,"John F. Kennedy Middle",15,"Wm. Scotsman",390,15,0,0,0]
[null,"John I. Leonard High",1,"Wm. Scotsman",26,15,0,0,0]
[null,"Jupiter Middle",11,"Wm. Scotsman",275,15,0,0,0]
[null,"Lake Park Elementary",4,"Wm. Scotsman",92,8,0,0,0]
[null,"Lake Worth Middle",8,"Wm. Scotsman",192,15,0,0,0]
[null,"Lake Worth High",6,"Wm. Scotsman",168,15,0,0,0]
[null,"Lantana Elementary",1,"Wm. Scotsman",25,15,0,0,0]
[null,"Lantana Middle",1,"Wm. Scotsman",27,15,0,0,0]
[null,"Liberty Park Elementary",3,"Wm. Scotsman",69,15,0,0,0]
[null,"Lighthouse Elementary",6,"Wm. Scotsman",156,8,0,0,0]
[null,"Limestone Creek Elementary",3,"Wm. Scotsman",78,9,0,0,0]
[null,"Loxahatchee Groves Elementary",3,"Wm. Scotsman",66,15,0,0,0]
[null,"Manatee Elementary",4,"Wm. Scotsman",92,15,0,0,0]
[null,"Meadow Park Elementary",4,"Wm. Scotsman",80,15,0,0,0]
[null,"Melaleuca Elementary",4,"Wm. Scotsman",92,15,0,0,0]
[null,"Middle School of the Arts",21,"Wm. Scotsman",567,6,0,0,0]
[null,"Northboro Elementary",1,"Wm. Scotsman",24,15,0,0,0]
[null,"Okeeheelee Middle",1,"Wm. Scotsman",27,15,0,0,0]
[null,"Olympic Heights High",9,"Wm. Scotsman",270,15,0,0,0]
[null,"Omni Middle",2,"Wm. Scotsman",48,15,0,0,0]
[null,"Pahokee Elementary",3,"Wm. Scotsman",36,15,0,0,0]
[null,"Palm Beach Lakes High",4,"Wm. Scotsman",120,15,0,0,0]
[null,"Palm Springs Elementary",4,"Wm. Scotsman",88,15,0,0,0]
[null,"Palmetto Elementary",2,"Wm. Scotsman",44,15,0,0,0]
[null,"Panther Run Elementary",6,"Wm. Scotsman",144,15,0,0,0]
[null,"Pine Grove Elementary",4,"Wm. Scotsman",108,7,0,0,0]
[null,"Rolling Green Elementary",2,"Wm. Scotsman",50,15,0,0,0]
[null,"Roosevelt Elementary",6,"Wm. Scotsman",132,15,0,0,0]
[null,"Roosevelt Middle",8,"Wm. Scotsman",224,15,0,0,0]
[null,"Rosenwald Elementary",2,"Wm. Scotsman",48,15,0,0,0]
[null,"SD Spady Elementary",2,"Wm. Scotsman",44,15,0,0,0]
[null,"Sandpiper Shores Elementary",3,"Wm. Scotsman",75,15,0,0,0]
[null,"Santaluces High",15,"Wm. Scotsman",435,11,0,0,0]
[null,"Seminole Trails Elementary",1,"Wm. Scotsman",18,15,0,0,0]
[null,"So. Area Middle School of Choice",1,"Wm. Scotsman",24,4,0,0,0]
[null,"South Olive Elementary",2,"Wm. Scotsman",42,15,0,0,0]
[null,"South Technical Education Ctr.",1,"Wm. Scotsman",26,15,0,0,0]
[null,"Spanish River High",2,"Wm. Scotsman",60,15,0,0,0]
[null,"Waters' Edge Elementary",1,"Wm. Scotsman",23,4,0,0,0]
[null,"Watson B. Duncan Middle",2,"Wm. Scotsman",42,15,0,0,0]
[null,"Wellington Elementary",1,"Wm. Scotsman",18,15,0,0,0]
[null,"Wellington High",5,"Wm. Scotsman",150,15,0,0,0]
[null,"Wellington Landings Middle",11,"Wm. Scotsman",297,15,0,0,0]
[null,"West Gate Elementary",11,"Wm. Scotsman",253,15,0,0,0]
[null,"West Technical Education Ctr.",8,"Wm. Scotsman",208,15,0,0,0]
[null,"Western Pines Middle",6,"Wm. Scotsman",162,16,0,0,0]
[null,"Westward Elementary",2,"Wm. Scotsman",46,15,0,0,0]
[null,"Whispering Pines Elementary",2,"Wm. Scotsman",42,15,0,0,0]
[null,"William T. Dwyer High",1,"Wm. Scotsman",21,15,0,0,0]
[null,"Woodlands Middle",9,"Wm. Scotsman",243,15,0,0,0]
[null,"Wynnebrook Elementary",8,"Wm. Scotsman",200,21,0,0,0]
["2c3.","Palm Beach County Total",388,null,9635,1136,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[]
[1,"Academy Charter of Boca Raton",8,"Third Party","2000-01",330,200,10,300]
[2,"Chancellor Charter School at Lantana",21,"Third Party","2001-02",550,525,10,700]
[3,"Delray Beach Academy",3,"Third Party","2002-03",65,65,3,80]
[4,"Ed Venture",4,"Third Party","2001-02",55,50,5,55]
[5,"Glades Academy of Agricultural and Ecological Studies",5,"Third Party","2001-02",140,120,5,200]
[6,"Hope Learning Community of the Gardens (Bright Futures)",6,"Third Party","2001-02",150,140,5,200]
[7,"Hope Learning Community of the Gardens (Noah's Ark)",3,"Third Party","2001-02",100,60,5,100]
[8,"Joseph Littles-Nguzo Saba",6,"Third Party","1998-99",160,140,5,190]
[9,"Lakeside Academy",6,"Third Party","1999-2000",160,140,5,190]
[10,"Palm Beach Maritime Academy",10,"Third Party","1999-2000",300,250,10,350]
[11,"Potentials",3,"Third Party","2001-02",50,30,15,50]
[12,"Renaissance Learning Center",2,"Third Party","2002-03",30,11,10,15]
[13,"St Mary's Pre-School for Autism",2,"Third Party","2000-01",30,28,3,30]
[14,"Survivors",16,"Third Party","2001-02",400,500,10,800]
[15,"Toussaint L'Ouverture High School for Arts & Social Justice",6,"Third Party","2001-02",160,150,5,250]
[16,"Cambridge Educational Academy ",6,"Third Party","2001-02",280,150,10,280]
[17,"Seagull Academy for Independent Living",2,"Third Party","2001-02",45,25,3,45]
[18,"Charter School of Boynton Beach",5,"Third Party","2001-02",180,110,10,180]
[19,"JFK Charter School",7,"Third Party","2002-03",550,170,5,400]
[20,"Delray Youth Vocational ",2,"Third Party","2002-03",30,25,5,40]
[21,"Riviera Beach Academy",5,"Third Party","2002-03",180,120,5,180]
[22,"Everglades Prepartatory Academy",5,"Third Party","2002-03",150,120,5,150]
[23,"The IMAGINE School",4,"Third Party","2002-03",200,100,5,200]
[24,"Palm Beach Shores",null,null,"2001-02",null,100,5,100]
[25,"Studio in the Arts G-Star",null,null,"2002-03",null,175,5,250]
[]
["2c4.","Palm Beach County Total",137,null,null,4295,3504,164,3504]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
["2e.","Average Class Size (5 years out -- 2006-07) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: You are no longer required to exclude exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2001-02 CO-FTE","2001-02 Class size","2006-07 CO-FTE","be added (removed)","2006-07 Class size"]
[null,"AW Dreyfoos School of Arts",57,1311,1319,23.14,1320,0,23.16]
[null,"Acreage Area Elementary (00-Q)",0,0,0,0,550,31,17.74]
[null,"Acreage Area High (02-NNN)",0,0,0,0,1895,74,25.61]
[null,"Acreage Area Middle (99-HH)",0,0,0,0,1000,39,25.64]
[null,"Acreage Pines Elementary",34,917,891,26.21,753,-8,28.96]
[null,"Addison Mizner Elementary",36,657,870,24.17,703,-10,27.04]
[null,"Adult Education Center",28,1032,51,1.82,51,0,1.82]
[null,"Allamanda Elementary",32,851,604,18.88,593,0,18.53]
[null,"Atlantic High",88,2060,2199,24.99,2496,0,28.36]
[null,"Banyan Creek Elementary",45,957,961,21.36,770,-15,25.67]
[null,"Barton Elementary",53,880,715,13.49,773,-13,19.33]
[null,"Beacon Cove Intermediate",34,969,1014,29.82,972,0,28.59]
[null,"Bear Lakes Middle",71,1853,1444,20.34,1144,-20,22.43]
[null,"Belle Glade Elementary",37,990,799,21.59,624,-1,17.33]
[null,"Belvedere Elementary",32,632,557,17.41,592,0,18.5]
[null,"Berkshire Elementary",44,783,888,20.18,963,-1,22.4]
[null,"Binks Forest Elementary",36,1000,1137,31.58,1038,0,28.83]
[null,"Boca Raton Area Middle (98-GG)",0,0,0,0,964,40,24.1]
[null,"Boca Raton Elementary",21,540,313,14.9,461,0,21.95]
[null,"Boca Raton High",87,2149,1816,20.87,1805,1,20.51]
[null,"Boca Raton Middle",58,1183,1118,19.28,1123,5,17.83]
[null,"Boynton Beach High",85,2470,1867,21.96,2494,0,29.34]
[null,"CoTaylor/Kirklane Elementary",32,1020,1118,34.94,820,0,25.63]
[null,"Calusa Elementary",27,1339,460,17.04,515,0,19.07]
[null,"Carver Middle",63,1337,1435,22.78,1510,-7,26.96]
[null,"Central WPB Area High (98-JJJ)",0,0,0,0,2285,85,26.88]
[null,"Cholee Lake Elementary (97-K)",0,0,0,0,1061,36,29.47]
[null,"Christa McAuliffe Middle",59,1253,1400,23.73,1243,-13,27.02]
[null,"Citrus Cove Elementary",61,959,1478,24.23,1060,-18,24.65]
[null,"Congress Middle",67,1516,1296,19.34,1475,-13,27.31]
[null,"Conniston Middle",65,1598,990,15.23,1226,-16,25.02]
[null,"Coral Reef Elementary",36,1000,1300,36.11,1075,0,29.86]
[null,"Coral Sunset Elementary",41,934,1015,24.76,1068,-5,29.67]
[null,"Crestwood Middle",68,1571,1510,22.21,1259,-24,28.61]
[null,"Crosspointe Elementary",0,0,0,0,807,36,22.42]
[null,"Crystal Lakes Elementary",49,871,1033,21.08,980,-13,27.22]
[null,"Cypress Trails Elementary",35,834,1012,28.91,941,1,26.14]
[null,"DD Eisenhower Elementary",19,1169,521,27.42,554,0,29.16]
[null,"Del Prado Elementary",38,975,821,21.61,752,-11,27.85]
[null,"Delray Full Service Center",44,1265,221,5.02,300,-22,13.64]
[null,"Discovery Key Elementary",34,961,781,22.97,1039,0,30.56]
[null,"Dr. Mary McLeod Bethune Elem.",38,1015,643,16.92,666,0,17.53]
[null,"Eagles Landing Middle",58,1400,1488,25.66,1295,-13,28.78]
[null,"Egret Lake Elementary",42,1023,837,19.93,682,-14,24.36]
[null,"Forest Hill Elementary",61,1182,1111,18.21,1058,-23,27.84]
[null,"Forest Hill High",70,1651,1486,21.23,1848,10,23.1]
[null,"Forest Park Elementary",41,903,676,16.49,732,-5,20.33]
[null,"Freedom Shores Elementary",0,0,0,0,960,36,26.67]
[null,"Frontier Elementary",34,960,754,22.18,895,0,26.32]
[null,"Galaxy Elementary",31,657,685,22.1,630,-2,21.72]
[null,"Glade View Elementary",40,779,494,12.35,460,-10,15.33]
[null,"Glades Central High",63,1590,1361,21.6,1900,16,24.05]
[null,"Gold Coast Community School",31,367,450,14.52,550,-1,18.33]
[null,"Golden Grove Elementary",46,1262,1084,23.57,948,-10,26.33]
[null,"Gove Elementary",50,1030,807,16.14,855,-5,19]
[null,"Greenacres Elementary",36,669,577,16.03,615,-10,23.65]
[null,"Grove Park Elementary",31,734,768,24.77,613,-2,21.14]
[null,"HL Johnson Elementary",56,849,1249,22.3,801,-25,25.84]
[null,"Hagen Road Elementary",16,713,532,33.25,638,10,24.54]
[null,"Hammock Pointe Elementary",39,957,998,25.59,1000,-1,26.32]
[null,"Heritage Elementary",41,1104,1277,31.15,1038,-5,28.83]
[null,"Highland Elementary",31,848,803,25.9,827,0,26.68]
[null,"Howell L. Watkins Middle",55,1157,1205,21.91,1123,-4,22.02]
[null,"Independence Middle",0,0,0,0,1426,46,31]
[null,"Indian Pines Elementary",46,1025,943,20.5,965,-8,25.39]
[null,"Indian Ridge School",27,151,110,4.07,56,-9,3.11]
[null,"Inlet Grove High",55,732,394,7.16,0,-55,0]
[null,"JC Mitchell Elementary",38,825,706,18.58,704,-2,19.56]
[null,"Jefferson Davis Middle",85,1710,1730,20.35,1449,-23,23.37]
[null,"Jerry Thomas Elementary",38,957,870,22.89,991,-2,27.53]
[null,"John F. Kennedy Middle",72,1315,1134,15.75,1481,6,18.99]
[null,"John I. Leonard High",113,2758,2969,26.27,2804,-10,27.22]
[null,"Jupiter Elementary",38,720,483,12.71,682,0,17.95]
[null,"Jupiter Farms Elementary",29,783,783,27,831,0,28.66]
[null,"Jupiter High",89,2722,1723,19.36,2508,0,28.18]
[null,"Jupiter Middle",68,1302,1543,22.69,1373,-19,28.02]
[null,"KE Cunningham/Canal Pt. Elem.",34,935,575,16.91,531,-3,17.13]
[null,"Lake Park Elementary",26,394,501,19.27,426,-9,25.06]
[null,"Lake Shore Middle",52,1531,1208,23.23,1215,0,23.37]
[null,"Lake Worth Middle",73,1484,1586,21.73,1348,-14,22.85]
[null,"Lake Worth High",125,3047,2941,23.53,3022,-19,28.51]
[null,"Lantana Elementary",32,752,641,20.03,513,-5,19]
[null,"Lantana Middle",41,657,868,21.17,1003,9,20.06]
[null,"Liberty Park Elementary",52,1131,1184,22.77,1032,-14,27.16]
[null,"Lighthouse Elementary",28,1187,635,22.68,828,0,29.57]
[null,"Limestone Creek Elementary",40,890,1010,25.25,996,-2,26.21]
[null,"Lincoln Elementary",56,1501,1050,18.75,1083,0,19.34]
[null,"Loggers Run Middle",58,1467,1383,23.84,1165,-13,25.89]
[null,"Loxahatchee Groves Elementary",38,916,755,19.87,834,-3,23.83]
[null,"Manatee Elementary",45,1044,1277,28.38,902,-9,25.06]
[null,"Meadow Park Elementary",36,785,545,15.14,550,-9,20.37]
[null,"Melaleuca Elementary",46,984,1130,24.57,874,-14,27.31]
[null,"Middle School of the Arts",74,981,1242,16.78,1250,-13,20.49]
[null,"Morikami Park Elementary",37,996,1001,27.05,1000,0,27.03]
[null,"New Horizons Elementary",27,762,772,28.59,783,0,29]
[null,"North Grade Elementary",32,825,716,22.38,831,0,25.97]
[null,"North Palm Beach Elementary",35,834,570,16.29,795,0,22.71]
[null,"Northboro Elementary",44,932,693,15.75,545,-9,15.57]
[null,"Northmore Elementary",32,880,693,21.66,630,0,19.69]
[null,"Odyssey Middle",46,1274,952,20.7,1381,0,30.02]
[null,"Okeechobee Corr.Area Elem.(96-D)",0,0,0,0,812,36,22.56]
[null,"Okeechobee/Jog Rd. Elem. (02-T)",0,0,0,0,635,31,20.48]
[null,"Okeeheelee Middle",67,1637,1636,24.42,1318,-13,24.41]
[null,"Olympic Heights High",110,2527,2548,23.16,2408,-10,24.08]
[null,"Omni Middle",56,1312,1251,22.34,1106,-7,22.57]
[null,"Orchard View Elementary",40,1071,904,22.6,725,0,18.13]
[null,"Pahokee Elementary",37,816,582,15.73,494,-10,18.3]
[null,"Pahokee Middle/Sr. High",57,1318,1037,18.19,1050,-1,18.75]
[null,"Palm Beach Gardens Elementary",31,717,683,22.03,644,-3,23]
[null,"Palm Beach Gardens High",92,2258,2506,27.24,2172,-5,24.97]
[null,"Palm Beach Lakes High",118,3061,2780,23.56,2446,-21,25.22]
[null,"Palm Beach Public",21,417,398,18.95,400,0,19.05]
[null,"Palm Springs Elementary",36,616,619,17.19,946,2,24.89]
[null,"Palmetto Elementary",37,469,608,16.43,662,0,17.89]
[null,"Panther Run Elementary",42,1037,1129,26.88,1062,-4,27.95]
[null,"Pine Grove Elementary",46,892,736,16,846,0,18.39]
[null,"Pioneer Park Elementary",37,1015,604,16.32,563,0,15.22]
[null,"Pleasant City Elementary",0,0,0,0,466,21,22.19]
[null,"Plumosa Elementary",28,698,567,20.25,561,0,20.04]
[null,"Poinciana Elementary",32,922,678,21.19,685,0,21.41]
[null,"Polo Park Middle",50,1343,1230,24.6,1202,0,24.04]
[null,"Riviera Beach Area HS (02-MMM)",0,0,0,0,1827,74,24.69]
[null,"Rolling Green Elementary",41,964,849,20.71,889,-3,23.39]
[null,"Roosevelt Elementary",50,951,900,18,718,-12,18.89]
[null,"Roosevelt Full Service Center",26,615,205,7.88,205,0,7.88]
[null,"Roosevelt Middle",59,1311,1411,23.92,1418,-8,27.8]
[null,"Rosenwald Elementary",31,722,397,12.81,411,-5,15.81]
[null,"Royal Palm School",41,402,221,5.39,122,-13,4.36]
[null,"Royal Palm Beach Elementary",0,0,0,0,1064,38,28]
[null,"Royal Palm Beach High",84,2509,2631,31.32,2420,0,28.81]
[null,"SD Spady Elementary",26,547,480,18.46,523,2,18.68]
[null,"Sabal Palm School (High Ridge)",12,78,52,4.33,52,0,4.33]
[null,"Sandpiper Shores Elementary",41,1021,765,18.66,782,-11,26.07]
[null,"Santaluces High",125,2714,2880,23.04,2541,-34,27.92]
[null,"School of Choice",30,636,148,4.93,148,0,4.93]
[null,"Seminole Trails Elementary",43,848,885,20.58,764,-5,20.11]
[null,"So. Area Middle School of Choice",12,392,127,10.58,127,0,10.58]
[null,"South Grade Elementary",29,808,872,30.07,783,0,27]
[null,"South Olive Elementary",42,761,788,18.76,651,-10,20.34]
[null,"South Technical Education Ctr.",62,970,704,11.35,0,-62,0]
[null,"Spanish River High",118,2747,3076,26.07,2253,-28,25.03]
[null,"Starlight Cove Elementary",44,1073,940,21.36,957,-5,24.54]
[null,"Suncoast High",47,1142,1298,27.62,1250,0,26.6]
[null,"Sunrise Park Elementary",34,962,728,21.41,918,0,27]
[null,"Timber Trace Elementary",36,894,834,23.17,887,-4,27.72]
[null,"UB Kinsey/Palmview Elementary",38,645,641,16.87,662,-9,22.83]
[null,"Verde Elementary",34,766,771,22.68,760,-3,24.52]
[null,"Village Academy Center",17,487,280,16.47,448,8,17.92]
[null,"Village Academy Middle/High",0,0,0,0,150,26,5.77]
[null,"W.Boca/Delray Area High (01-LLL)",0,0,0,0,1928,74,26.05]
[null,"W.Lake Worth/Lantana Elem.(01-R)",0,0,0,0,961,36,26.69]
[null,"Washington Elementary",39,689,563,14.44,585,-9,19.5]
[null,"Waters' Edge Elementary",44,1114,1098,24.95,1100,-4,27.5]
[null,"Watson B. Duncan Middle",56,1216,1347,24.05,1235,-8,25.73]
[null,"Wellington Area Elementary (02-S)",0,0,0,0,1047,36,29.08]
[null,"Wellington Area Middle (02-JJ)",0,0,0,0,801,40,20.03]
[null,"Wellington Elementary",46,934,1002,21.78,985,-8,25.92]
[null,"Wellington High",113,2807,3320,29.38,2400,-19,25.53]
[null,"Wellington Landings Middle",61,1066,1488,24.39,1065,-16,23.67]
[null,"West Boynton Area High (98-EEE)",0,0,0,0,2684,85,31.58]
[null,"West Gate Elementary",62,1233,745,12.02,778,-24,20.47]
[null,"West Palm Bch Area Midd (98-EE)",0,0,0,0,1417,46,30.8]
[null,"West Riviera Elementary",40,1129,814,20.35,788,-1,20.21]
[null,"West Technical Education Ctr.",42,910,207,4.93,0,-42,0]
[null,"Western Lake Worth Middle(98-II)",0,0,0,0,1269,46,27.59]
[null,"Western Pines Middle",63,1491,1553,24.65,1364,-14,27.84]
[null,"Westward Elementary",43,949,709,16.49,705,-10,21.36]
[null,"Whispering Pines Elementary",40,1027,782,19.55,842,-10,28.07]
[null,"William T. Dwyer High",73,1924,2208,30.25,1936,18,21.27]
[null,"Woodlands Middle",72,1783,1870,25.97,1371,-19,25.87]
[null,"Wynnebrook Elementary",52,1022,1095,21.06,655,-23,22.59]
["2e.","Palm Beach County Total",7238,168260,153735,"District Avg 21",172844,3,"District Avg 24"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR AVERAGE"]
[null,"AW Dreyfoos School of Arts",null,0,0,0,0,0,0]
[null,"Acreage Pines Elementary",null,208,208,0,0,0,83.2]
[null,"Addison Mizner Elementary",null,96,96,96,96,108,98.4]
[null,"Adult Education Center",null,14,14,14,14,14,14]
[null,"Allamanda Elementary",null,0,0,0,0,0,0]
[null,"Atlantic High",null,500,500,500,0,0,300]
[null,"Banyan Creek Elementary",null,147,0,0,0,0,29.4]
[null,"Barton Elementary",null,221,221,221,221,361,249]
[null,"Beacon Cove Intermediate",null,0,0,0,0,0,0]
[null,"Bear Lakes Middle",null,620,620,200,0,0,288]
[null,"Belle Glade Elementary",null,22,0,0,0,0,4.4]
[null,"Belvedere Elementary",null,102,0,0,0,0,20.4]
[null,"Berkshire Elementary",null,360,360,0,0,0,144]
[null,"Binks Forest Elementary",null,0,0,0,29,29,11.6]
[null,"Boca Raton Elementary",null,0,0,0,0,0,0]
[null,"Boca Raton High",null,252,252,0,0,0,100.8]
[null,"Boca Raton Middle",null,133,133,19,19,16,64]
[null,"Boynton Beach High",null,0,0,0,0,29,5.8]
[null,"CoTaylor/Kirklane Elementary",null,443,443,100,100,100,237.2]
[null,"Calusa Elementary",null,408,0,0,0,0,81.6]
[null,"Carver Middle",null,368,368,368,368,432,380.8]
[null,"Christa McAuliffe Middle",null,360,360,144,144,81,217.8]
[null,"Citrus Cove Elementary",null,408,403,96,96,100,220.6]
[null,"Congress Middle",null,247,247,114,114,162,176.8]
[null,"Conniston Middle",null,285,0,0,0,0,57]
[null,"Coral Reef Elementary",null,0,0,90,90,90,54]
[null,"Coral Sunset Elementary",null,325,325,325,100,120,239]
[null,"Crestwood Middle",null,572,572,88,88,116,287.2]
[null,"Crystal Lakes Elementary",null,210,0,0,0,0,42]
[null,"Cypress Trails Elementary",null,174,174,0,0,0,69.6]
[null,"DD Eisenhower Elementary",null,108,108,108,108,116,109.6]
[null,"Del Prado Elementary",null,242,242,242,0,0,145.2]
[null,"Delray Full Service Center",null,30,30,30,30,0,24]
[null,"Discovery Key Elementary",null,0,0,0,0,93,18.6]
[null,"Dr. Mary McLeod Bethune Elem.",null,0,0,0,0,0,0]
[null,"Eagles Landing Middle",null,338,338,0,0,0,135.2]
[null,"Egret Lake Elementary",null,280,280,0,0,0,112]
[null,"Forest Hill Elementary",null,90,90,90,90,140,100]
[null,"Forest Hill High",null,315,315,0,0,0,126]
[null,"Forest Park Elementary",null,96,96,96,96,120,100.8]
[null,"Frontier Elementary",null,0,0,0,0,0,0]
[null,"Galaxy Elementary",null,44,44,0,0,0,17.6]
[null,"Glade View Elementary",null,192,192,192,192,45,162.6]
[null,"Glades Central High",null,12,12,12,0,0,7.2]
[null,"Gold Coast Community School",null,75,75,75,75,90,78]
[null,"Golden Grove Elementary",null,240,240,0,0,0,96]
[null,"Gove Elementary",null,96,96,96,96,114,99.6]
[null,"Greenacres Elementary",null,16,0,0,0,0,3.2]
[null,"Grove Park Elementary",null,50,50,0,0,0,20]
[null,"HL Johnson Elementary",null,154,154,0,0,0,61.6]
[null,"Hagen Road Elementary",null,66,66,66,66,66,66]
[null,"Hammock Pointe Elementary",null,286,286,52,52,52,145.6]
[null,"Heritage Elementary",null,155,62,62,62,58,79.8]
[null,"Highland Elementary",null,0,0,0,0,0,0]
[null,"Howell L. Watkins Middle",null,154,154,0,0,0,61.6]
[null,"Indian Pines Elementary",null,399,399,0,0,0,159.6]
[null,"Indian Ridge School",null,36,36,36,36,36,36]
[null,"Inlet Grove High",null,261,261,261,0,0,156.6]
[null,"JC Mitchell Elementary",null,114,114,114,0,0,68.4]
[null,"Jefferson Davis Middle",null,540,540,120,120,138,291.6]
[null,"Jerry Thomas Elementary",null,161,161,0,0,0,64.4]
[null,"John F. Kennedy Middle",null,368,368,112,112,133,218.6]
[null,"John I. Leonard High",null,338,338,208,208,216,261.6]
[null,"Jupiter Elementary",null,0,0,0,0,0,0]
[null,"Jupiter Farms Elementary",null,0,0,0,0,87,17.4]
[null,"Jupiter High",null,0,0,0,0,0,0]
[null,"Jupiter Middle",null,322,138,138,138,168,180.8]
[null,"KE Cunningham/Canal Pt. Elem.",null,85,85,85,85,85,85]
[null,"Lake Park Elementary",null,0,0,0,0,0,0]
[null,"Lake Shore Middle",null,0,0,0,0,0,0]
[null,"Lake Worth Middle",null,660,660,132,132,138,344.4]
[null,"Lake Worth High",null,192,192,192,192,232,200]
[null,"Lantana Elementary",null,100,60,60,60,57,67.4]
[null,"Lantana Middle",null,357,0,0,0,0,71.4]
[null,"Liberty Park Elementary",null,529,529,69,69,81,255.4]
[null,"Lighthouse Elementary",null,621,69,69,69,90,183.6]
[null,"Limestone Creek Elementary",null,250,250,0,0,0,100]
[null,"Lincoln Elementary",null,38,0,0,0,0,7.6]
[null,"Loggers Run Middle",null,384,384,384,384,0,307.2]
[null,"Loxahatchee Groves Elementary",null,240,240,240,320,320,272]
[null,"Manatee Elementary",null,252,252,0,0,0,100.8]
[null,"Meadow Park Elementary",null,0,0,0,0,0,0]
[null,"Melaleuca Elementary",null,75,75,75,75,81,76.2]
[null,"Middle School of the Arts",null,493,493,0,0,0,197.2]
[null,"Morikami Park Elementary",null,0,0,0,0,0,0]
[null,"New Horizons Elementary",null,0,0,0,0,0,0]
[null,"North Grade Elementary",null,0,0,0,0,0,0]
[null,"North Palm Beach Elementary",null,0,0,0,0,0,0]
[null,"Northboro Elementary",null,176,176,64,0,0,83.2]
[null,"Northmore Elementary",null,0,0,0,0,0,0]
[null,"Odyssey Middle",null,0,0,0,0,150,30]
[null,"Okeeheelee Middle",null,528,0,0,0,0,105.6]
[null,"Olympic Heights High",null,230,230,115,0,0,115]
[null,"Omni Middle",null,220,220,0,0,0,88]
[null,"Orchard View Elementary",null,0,0,0,0,0,0]
[null,"Pahokee Elementary",null,0,0,0,0,0,0]
[null,"Pahokee Middle/Sr. High",null,18,0,0,0,0,3.6]
[null,"Palm Beach Gardens Elementary",null,88,88,88,88,92,88.8]
[null,"Palm Beach Gardens High",null,135,135,135,0,0,81]
[null,"Palm Beach Lakes High",null,504,144,0,0,0,129.6]
[null,"Palm Beach Public",null,0,0,0,0,0,0]
[null,"Palm Springs Elementary",null,221,221,0,0,0,88.4]
[null,"Palmetto  Elementary",null,0,0,0,0,0,0]
[null,"Panther Run Elementary",null,378,216,135,135,140,200.8]
[null,"Pine Grove Elementary",null,160,160,160,160,230,174]
[null,"Pioneer Park Elementary",null,0,0,0,0,0,0]
[null,"Plumosa Elementary",null,0,0,0,0,0,0]
[null,"Poinciana Elementary",null,0,0,0,0,0,0]
[null,"Polo Park Middle",null,0,0,0,0,0,0]
[null,"Rolling Green Elementary",null,147,147,147,147,161,149.8]
[null,"Roosevelt Elementary",null,342,342,0,0,0,136.8]
[null,"Roosevelt Full Service Center",null,8,8,8,8,8,8]
[null,"Roosevelt Middle",null,192,192,192,216,216,201.6]
[null,"Rosenwald Elementary",null,0,0,0,0,0,0]
[null,"Royal Palm School",null,65,65,65,65,65,65]
[null,"Royal Palm Beach High",null,0,0,0,0,0,0]
[null,"SD Spady Elementary",null,216,216,0,0,0,86.4]
[null,"Sabal Palm School (High Ridge)",null,24,24,24,24,24,24]
[null,"Sandpiper Shores Elementary",null,44,38,38,38,52,42]
[null,"Santaluces High",null,598,598,69,69,84,283.6]
[null,"School of Choice",null,15,15,15,15,0,12]
[null,"Seminole Trails Elementary",null,189,189,84,84,80,125.2]
[null,"So. Area Middle School of Choice",null,132,132,132,132,132,132]
[null,"South Grade Elementary",null,0,0,0,0,0,0]
[null,"South Olive Elementary",null,285,0,0,0,0,57]
[null,"South Technical Education Ctr.",null,209,209,0,0,0,83.6]
[null,"Spanish River High",null,728,728,52,0,0,301.6]
[null,"Starlight Cove Elementary",null,189,189,189,189,225,196.2]
[null,"Suncoast High",null,56,56,56,56,54,55.6]
[null,"Sunrise Park Elementary",null,0,0,0,0,0,0]
[null,"Timber Trace Elementary",null,92,92,92,92,112,96]
[null,"UB Kinsey/Palmview Elementary",null,102,0,0,0,0,20.4]
[null,"Verde Elementary",null,23,23,23,23,25,23.4]
[null,"Village Academy Center",null,0,0,0,0,0,0]
[null,"Washington Elementary",null,126,126,126,126,126,126]
[null,"Waters' Edge Elementary",null,100,100,100,100,112,102.4]
[null,"Watson B. Duncan Middle",null,168,96,96,96,104,112]
[null,"Wellington Elementary",null,220,66,66,66,66,96.8]
[null,"Wellington High",null,551,232,0,0,0,156.6]
[null,"Wellington Landings Middle",null,384,384,96,0,0,172.8]
[null,"West Gate Elementary",null,0,0,0,0,0,0]
[null,"West Riviera Elementary",null,220,220,220,220,240,224]
[null,"West Technical Education Ctr.",null,65,65,65,65,0,52]
[null,"Western Pines Middle",null,350,350,25,25,28,155.6]
[null,"Westward Elementary",null,176,176,176,176,192,179.2]
[null,"Whispering Pines Elementary",null,160,160,160,160,224,172.8]
[null,"William T. Dwyer High",null,150,30,30,30,30,54]
[null,"Woodlands Middle",null,494,494,0,0,0,197.6]
[null,"Wynnebrook Elementary",null,105,105,105,105,115,107]
["2f.","Palm Beach County Total students in relocatables by year",null,25912,21327,8939,7056,7601,14167]
[null,"Total number of CO-FTE students projected by year",null,159075,162824,166508,169903,172606,166183.2]
[null,"Percent in relocatables by year",null,0.16,0.13,0.05,0.04,0.04,0.09]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"During the next 5 years the School District of Palm Beach County plans to close its 3 technical education centers as the district moves towards comprehensive"]
[null,"vocational high schools.  The schools to close are:  Inlet Grove High School, South Technical Education Center, and West Technical Center.  The District"]
[null,"plans to reuse these facilities for alternative program and ancillary space needs."]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,82,107,146,8756,12965,23176]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,84,119,161,9899,13498,17138]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,93,112,185,12826,15024,22033]
[]
["3a.","2002-03 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"New Schools"]
[null,"Acreage Area Elem (00-Q)",1,14362240,770,107000,138.96,82,82,146,18652.26,8756,12965,23176]
[null,"Acreage Area Middle (99-HH)",2,23866094,1111.111111111111,172000,154.8,84,84,161,21479.48,9899,13498,17138]
[null,"Boca Raton Area Middle (98-GG)",2,24415226,1111,172000,154.82,84,84,161,21975.9,9899,13498,17138]
[null,"Okeechobee/Jog Rd Area Elem (02-T)",1,14761717,770,107000,138.96,82,82,146,19171.06,8756,12965,23176]
[null,"Western Lake Worth Area Middle (98-II)",2,28022738,1444,190000,131.58,84,84,161,19406.33,9899,13498,17138]
[]
[null,"Modernizations, Additions, Replacements"]
[null,"Auditoriums-High Schools",0,4331250,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Boca Raton High Modernization",0,1000966,2105.263157894737,368375,174.98,0,0,0,475.46,0,0,0]
[null,"Conniston Middle Modernization",0,385617,1444,190000,131.58,0,0,0,267.05,0,0,0]
[null,"H.L. Watkins Middle School Modernization",0,21837328,1261.111111111111,172000,136.39,0,0,0,17315.94,0,0,0]
[null,"Lantana Elem Modernization",0,12662187,651,95000,145.93,0,0,0,19450.36,0,0,0]
[null,"Palm Beach Public Modernization",0,11430825,490,73000,148.98,0,0,0,23328.21,0,0,0]
[null,"Palm Springs Elementary Modernization",0,17073526,970,122000,125.77,0,0,0,17601.57,0,0,0]
[null,"Roosevelt Elementary Modernization",0,16964687,970,122000,125.77,0,0,0,17489.37,0,0,0]
[null,"Stadiums-High Schools",0,2100000,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[]
["3a.","Palm Beach County Total 2002-03",null,193214401,13097.48538011696,1890375,144.33,null,null,null,14752.02]
[]
["3b.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"New Schools"]
[null,"Acreage Area High (02-NNN)",3,58014094,1894.7368421052633,332000,175.22,93,112,185,30618.55,12826,15024,22033]
[null,"Riviera Beach Area High ((02-MMM)",3,62521590,1894.7368421052633,332000,175.22,93,112,185,32997.51,12826,15024,22033]
[null,"Wellington Area Middle (02-JJ)",2,28680960,1111,172000,154.82,84,119,161,25815.45,9899,13498,17138]
[]
[null,"Modernizations, Additions, Replacements"]
[null,"Atlantic High Career Academy & Add'l Capacity",0,11802577,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Atlantic High Modernization",0,53471147,2631.5789473684213,400000,152,0,0,0,20319.04,0,0,0]
[null,"Auditoriums-High Schools",0,4263000,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Coral Sunset Elem Add",0,2432249,170,12410,73,0,0,0,14307.35,0,0,0]
[null,"Delray Full Service Center",0,7016581,300,44700,149,0,0,0,23388.6,0,0,0]
[null,"Hammock Point Elem Add",0,2746826,200,14600,73,0,0,0,13734.13,0,0,0]
[null,"Jefferson Davis Middle Modernization",0,26980033,1506,225000,149.4,0,0,0,17915.03,0,0,0]
[null,"Jupiter High School Career Academy",0,4511465,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Meadow Park Elem Modernization",0,14997865,643,95000,147.74,0,0,0,23324.83,0,0,0]
[null,"Middle School of the Arts Modernization",0,29253679,1444.4444444444443,190000,131.54,0,0,0,20252.55,0,0,0]
[null,"Village Academy Secondary Level",0,18262982,552.6315789473684,80000,144.76,0,0,0,33047.3,0,0,0]
[]
["3b","Palm Beach County Total 2003-04",null,324955048,12348.12865497076,1897710,153.68,null,null,null,26316.14]
[]
["3c.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2004 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"Modernizations, Additions, Replacements"]
[null,"Auditoriums-High Schools",0,4263000,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Berkshire Elem Modernization",0,16851919,970,122000,125.77,0,0,0,17373.11,0,0,0]
[null,"Boca Raton High Career Academy",0,2777022,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Future Classroom Additions",0,20269863,null,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Future School Modernizations",0,51772551,null,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"J.F. Kennedy Middle Mod/Add",0,29217725,1666.6666666666665,200000,120,0,0,0,17530.64,0,0,0]
[null,"John I. Leonard High Modernization",0,61496128,2632,400000,151.98,0,0,0,23364.79,0,0,0]
[null,"S.D. Spady Elementary School Mod/Addition",0,10693184,600,93000,155,0,0,0,17821.97,0,0,0]
[]
["3c","Palm Beach County Total 2004-05",null,197341392,5868.666666666666,815000,138.87,null,null,null,33626.27]
[]
["3d.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2005 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"Modernizations, Additions, Replacements"]
[null,"Auditoriums-High Schools",0,4121250,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"Future School Modernizations",0,59369449,null,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,"West Tech at Glades Central",0,8855090,0,null,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[]
["3d.","Palm Beach County Total 2005-06",null,72345789,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2000 State Avg","2000 State Avg","2000 State Avg","2006 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[null,"New Schools"]
[null,"Wellington Area Elem (02-U)",1,18080331,970,122000,125.77,82,107,146,18639.52,8756,12965,23176]
[]
[null,"Modernizations, Additions, Replacements"]
[null,"Future School Modernizations",0,114678097,0,0,{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[null,null,null,0]
["3e","Palm Beach County Total 2006-07",null,132758428,970,122000,125.77,null,null,null,136864.36]
[]
["3f.","Palm Beach County 5-Year Total",null,920615058,32284.280701754386,4725085]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,168164774,179936308,192531850,206009080,220429715,967071727]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,168164774,179936308,192531850,206009080,220429715,967071727,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,5150000,5498081,5870527,6269045,6695459,29483112,0.0304869961315703]
[null,"  less amount used to purchase other vehicles",null,1170000,1249079,1333693,1424230,1521104,6698106,0.00692617291250828]
[null,"  less amount transferred to operating budget for maintenance/repair",null,32850000,35070282,37445983,39987983,42707925,188062173,0.194465589003824]
[null,"  less amount used for maintenance/repair",null,18765185,20030116,21383592,22831813,24381407,107392113,0.111048756779548]
[null,"  less amount used to purchase capital outlay equipment",null,2720000,2903650,3100155,3310416,3535395,15569616,0.0160997530641282]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,67176718,81500000,93000000,99500000,106500000,447676718,0.462919869851598]
[null,"  less other (Ed Plant Survey)",null,250000,0,0,0,0,250000,0.0013293476088889]
[null,"  less other (Facilities Audit)",null,150000,0,0,0,0,150000,0.000155107419452042,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,39932871,33685100,30397900,32685593,35088425,171789889,0.177639242471619,0.15]
[null,"P E C O New Construction",null,18976879,7907842,8758148,9728885,9823095,55194849,null,0.05]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,null,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,700000,700000,700000,700000,700000,3500000,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,104000000,96300000,0,null,200300000,null,0.18]
[null,"Proceeds from Certificates of Participation (COP's)",null,177772611,203608512,82472318,61600088,118877191,644330720,null,0.58]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"Impact fees received",null,8000000,8000000,8000000,8000000,8000000,40000000,null,0.04]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","Palm Beach County Total",null,245382361,357901454,226628366,112714566,172488711,1115115458,1.0010708352431368,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New Schools"]
[null,"Acreage Area Elem (00-Q)",null,14362240,0,0,0,0,14362240]
[null,"Acreage Area High (02-NNN)",null,3888881,54125213,0,0,0,58014094]
[null,"Acreage Area Middle (99-HH)",null,23866094,0,0,0,0,23866094]
[null,"Boca Raton Area Middle (98-GG)",null,24415226,0,0,0,0,24415226]
[null,"Okeechobee/Jog Rd Area Elem (02-T)",null,14761717,0,0,0,0,14761717]
[null,"Riviera Beach Area High ((02-MMM)",null,5398188,57123402,0,0,0,62521590]
[null,"Wellington Area Elem (02-U)",null,0,0,0,1692437,16387894,18080331]
[null,"Wellington Area Middle (02-JJ)",null,2946242,25734718,0,0,0,28680960]
[null,"Western Lake Worth Area Middle (98-II)",null,28022738,{"$nulls":4},28022738]
[{"$nulls":8},0]
[null,"Modernizations, Additions, Replacements",{"$nulls":6},0]
[null,"Atlantic High Career Academy & Add'l Capacity",null,926104,10876473,0,0,0,11802577]
[null,"Atlantic High Modernization",null,4027238,49443909,0,0,0,53471147]
[null,"Auditoriums-High Schools",null,4331250,4263000,4263000,4121250,0,16978500]
[null,"Berkshire Elem Modernization",null,0,1721692,15130227,0,0,16851919]
[null,"Boca Raton High Career Academy",null,0,152744,2624278,0,0,2777022]
[null,"Boca Raton High Modernization",null,1000966,0,0,0,0,1000966]
[null,"Conniston Middle Modernization",null,385617,0,0,0,0,385617]
[null,"Coral Sunset Elem Add",null,109941,2322308,0,0,0,2432249]
[null,"Delray Full Service Center",null,100000,6916581,0,0,0,7016581]
[null,"Future Classroom Additions",null,0,1768080,18501783,0,0,20269863]
[null,"Future School Modernizations",null,0,4326188,47446363,59369449,114678097,225820097]
[null,"H.L. Watkins Middle School Modernization",null,21837328,0,0,0,0,21837328]
[null,"Hammock Point Elem Add",null,152227,2594599,0,0,0,2746826]
[null,"J.F. Kennedy Middle Mod/Add",null,0,3025276,26192449,0,0,29217725]
[null,"Jefferson Davis Middle Modernization",null,2880317,24099716,0,0,0,26980033]
[null,"John I. Leonard High Modernization",null,0,5764987,55731141,0,0,61496128]
[null,"Jupiter High School Career Academy",null,251857,4259608,0,0,0,4511465]
[null,"Lantana Elem Modernization",null,12662187,0,0,0,0,12662187]
[null,"Meadow Park Elem Modernization",null,1530644,13467221,0,0,0,14997865]
[null,"Middle School of the Arts Modernization",null,3029660,26224019,0,0,0,29253679]
[null,"Palm Beach Public Modernization",null,11430825,0,0,0,0,11430825]
[null,"Palm Springs Elementary Modernization",null,17073526,0,0,0,0,17073526]
[null,"Roosevelt Elementary Modernization",null,16964687,0,0,0,0,16964687]
[null,"S.D. Spady Elementary School Mod/Addition",null,0,1058443,9634741,0,0,10693184]
[null,"Stadiums-High Schools",null,2100000,0,0,0,0,2100000]
[null,"Village Academy Secondary Level",null,1779723,16483259,0,0,0,18262982]
[null,"West Tech at Glades Central",null,0,0,554100,8300990,0,8855090]
[{"$nulls":8},0]
["5.","Palm Beach County Total",0,220235423,315751436,180078082,73484126,131065991,920615058]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,2000000,1000000,0,0,0,3000000]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","Palm Beach County Total",null,2000000,1000000,0,0,0,3000000]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["7.","Palm Beach County Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2003."]
[]
[null,"SCHOOL BOARD OF ","Palm Beach County  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:",{"$nulls":4},"Arthur C. Johnson, Ph.D"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF OF FACILITIES MANAGEMENT: ",{"$nulls":4},"Joseph Sanches",null,null,null," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  ",null,null,"Susan Olson","         Special Projects Coordinator    561-434-8012",null,null,"olsons@mail.palmbeack.k12.fl.us",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}