{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","99_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"99_5YrWkPlan","index":1,"n_rows":1088,"n_cols":25,"rows_kept":1088,"cut":false,"hidden":false,"merged":[[60,1,60,2]],"flags":["formulas_cached_only"]}
[]
["PALM BEACH  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["PALM BEACH   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to September 15, 1999, and all data accurate as of July 15, 1999.",{"$nulls":8},"1999-08-05",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"PALM BEACH","Date: ==>","1999-09-15",null,"For fiscal years","  1999-2000 through 2003-2004"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-04 "]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"ADA Compliance","Various Schools",832000,865000,897000,933000,969000,4496000]
[null,"Facility Support","Various Schools",8000000,8000000,8000000,8000000,8000000,40000000]
[null,"Fire & Life Safety","Various Schools",1096000,1000000,1000000,1000000,1000000,5096000]
[null,"Health Clinic Compliance","Various Schools",100000,{"$nulls":4},100000]
[null,"HVAC","Various Schools",2080000,2163000,2250000,2340000,3430000,12263000]
[null,"Major Renov.& Systems Replmnt.","Various Schools",3300000,3000000,3000000,3000000,3000000,15300000]
[null,"Minor Bldg. Add./Space Renov.","Various Schools",5642000,5842000,5979000,5113000,5329000,27905000]
[null,"Planned Asset Replacement","Various Schools",936000,947000,1013000,1054000,1095000,5045000]
[null,"Portable Leasing","Various Schools",1925000,1925000,1500000,1100000,990000,7440000]
[null,"Portable Relocation","Various Schools",4000000,4000000,3500000,3000000,2500000,17000000]
[null,"Roof Replacement","Various Schools",null,5408000,5624000,5849000,6074000,22955000]
[null,"Title 9 Gender Equity","Various Schools",500000,500000,250000,100000,50000,1400000]
[null,"Traffic Improvements","Various Schools",500000,500000,500000,500000,500000,2500000]
["1.","PALM BEACH Total",null,28911000,34150000,33513000,31989000,32937000,161500000]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Addison Mizner Elem Remodeling",null,2290000,{"$nulls":4},2290000]
[null,"Atlantic High Athletic Facility Phase 2",null,300000,null," ",null,null,300000]
[null,"Atlantic High Modernization",null,null,375519,1000000,30433368,2579099,34387986]
[null,"Boca Raton Elem - expand media, dining & kitchen; 16 new classrooms",null,224195,5372280,null,null,null,5596475]
[null,"Boca Raton High School - Modernization",null,2000000,36854817,3208035,null,null,42062852]
[null,"Career Academies Modifications",null,1500000,5000000,3000000,null,null,9500000]
[null,"Conniston Mid Modernization",null,850553,14799614,1360884,null,null,17011051]
[null,"Forest Hill Elem  - expand media, dining & kitchen; 12 new classrooms",null,10910,8398551,null,null,null,8409461]
[null,"Forest Hill High Modernization",null,304518,1000000,28862470,2445972,null,32612960]
[null,"Future School Modernizations",null,null,1678505,32062365,28444843,42797776,104983489]
[null,"John I Leonard High Modernization",null,null,null,208109,1000000,26729406,27937515]
[null,"Jupiter Elem - expand dining & kitchen;  12 new classrooms",null,605000,11454723,null,null,null,12059723]
[null,"Jupiter High Modernization",null,38782755,3144549,null," ",null,41927304]
[null,"Lake Park Elem -  expand dining & kitchen; 12 new classrooms",null,8133562,{"$nulls":4},8133562]
[null,"Lake Shore Mid School Replacement Facility",null,1500000," "," "," ",null,1500000]
[null,"Lake Worth High School, Phase II - \nRemodel Bldgs 3,4,9,12,20;  21 new classrooms; expand media center",null,11112402," "," "," ",null,11112402]
[null,"New Elem School \"A\"",null,11197440,{"$nulls":4},11197440]
[null,"New Elem School \"B\"",null,11197440,{"$nulls":4},11197440]
[null,"New Elem School \"C\"",null,462367,{"$nulls":4},462367]
[null,"New Elem School \"D\"",null," "," ",638000,12123320,null,12761320]
[null,"New Elem School \"F\"",null,476310,{"$nulls":4},476310]
[null,"New Elem School \"H\"",null,605000,11477990,null,null,null,12082990]
[null,"New Elem School \"I\"",null,null,620000,11799880,null,null,12419880]
[null,"New Elem School \"J\"",null," ",620000,11799880," ",null,12419880]
[null,"New Elem School \"K\"",null,11787440," ",null,null,null,11787440]
[null,"New Elem School \"L\"",null," ",620000,11799880," ",null,12419880]
[null,"New Elem School \"M\"",null,605000,11487990," "," ",null,12092990]
[null,"New Elem School \"N\"",null,474204,{"$nulls":4},474204]
[null,"New High School \"EEE\"",{"$nulls":4},426433,3000000,3426433]
[null,"New High School \"JJJ\"",null,38928152,2489130," "," ",null,41417282]
[null,"New Mid School \"BB\"",null," ",1010690," "," ",null,1010690]
[null,"New Mid School \"CC\"",null,581786,{"$nulls":4},581786]
[null,"New Mid School \"DD\"",null,1035675,18177780,1500000,null,null,20713455]
[null,"New Mid School \"EE\"",null," ",1035675,18177780,1500000,null,20713455]
[null,"New Mid School \"FF\"",null,17678917,1500000," "," ",null,19178917]
[null,"New Mid School \"GG\"",null," ",null,763650,13031119,1300000,15094769]
[null,"New Mid School \"HH\"",{"$nulls":5},1120000,1120000]
[null,"New Mid/High Holding School",null,11290572,{"$nulls":4},11290572]
[null,"North Grade Elem Replacement Facility",null,480268," "," "," ",null,480268]
[null,"Pahokee Elem Remodeling Phase 2",null,6721500," "," "," ",null,6721500]
[null,"Palm Beach Public Modernization",null,231883,5101428,null,null,null,5333311]
[null,"Palmetto Elem - expand media, dining & kitchen; 25 new classrooms",null,11617497,{"$nulls":4},11617497]
[null,"South Olive Modernization",null,357758,4925519,549592,null,null,5832869]
[null,"Village Academy (PK-5)",null,6076000,{"$nulls":4},6076000]
[null,"West Gate Elem - expand media;  12 new classrooms",null,7473503,{"$nulls":4},7473503]
["2 .","PALM BEACH Total",null,206892607,147144760,126730525,89405055,77526281,647699228]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1998-99 FISH Satisfactory","Actual 1998-99","Actual 1998-99","Actual 1998-99","New Stu Capacity to","Projected 2003-04","Projected 2003-04"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Acreage Pines Elem",1063,1063,1298,1.22,601,1700,1.02]
[null,"Addison Mizner Elem",878,878,864,0.98,-121,768,1.01]
[null,"Allamanda Elem",948,948,702,0.74,-75,681,0.78]
[null,"Banyan Creek Elem",1105,1105,1032,0.93,-217,895,1.01]
[null,"Barton Elem",1388,1388,979,0.71,-501,906,1.02]
[null,"Belle Glade Elem",994,994,897,0.9,0,948,0.95]
[null,"Belvedere Elem",866,866,854,0.99,104,1007,1.04]
[null,"Berkshire Elem",977,977,890,0.91,-98,878,1]
[null,"Boca Raton Elem",444,444,321,0.72,-49,331,0.84]
[null,"C.O.Taylor/Kirklane Elem",1288,1288,1116,0.87,-250,999,0.96]
[null,"Calusa Elem",824,824,607,0.74,-104,613,0.85]
[null,"Citrus Cove Elem",1255,1255,1272,1.01,102,1415,1.04]
[null,"Coral Sunset Elem",1097,1097,1012,0.92,-131,1020,1.06]
[null,"Crystal Lakes Elem",980,980,914,0.93,-72,999,1.1]
[null,"Cypress Trails Elem",912,912,867,0.95,-12,954,1.06]
[null,"D.D. Eisenhower Elem",892,892,621,0.7,-95,730,0.92]
[null,"Del Prado Elem",1149,1149,1144,1,-79,1094,1.02]
[null,"Egret Lake Elem",760,760,792,1.04,250,1005,1]
[null,"Forest Hill Elem",1165,1165,1135,0.97,-130,1092,1.06]
[null,"Forest Park Elem",758,758,691,0.91,-100,695,1.06]
[null,"Galaxy Elem",757,757,877,1.16,92,774,0.91]
[null,"Glade View Elem",930,930,629,0.68,-296,581,0.92]
[null,"Golden Grove Elem",995,995,1022,1.03,100,1137,1.04]
[null,"Gove Elem",1091,1091,808,0.74,-300,790,1]
[null,"Greenacres Elem",987,987,787,0.8,-205,765,0.98]
[null,"Grove Park Elem",790,790,736,0.93,-52,765,1.04]
[null,"H.L. Johnson Elem",1206,1206,1194,0.99,10,1275,1.05]
[null,"Hagen Road Elem",844,844,534,0.63,-3,846,1.01]
[null,"Hammock Pointe Elem",842,842,948,1.13,-4,866,1.03]
[null,"Highland Elem",1393,1393,941,0.68,-450,999,1.06]
[null,"Indian Pines Elem",893,893,982,1.1,87,981,1]
[null,"J.C. Mitchell Elem",830,830,770,0.93,-86,676,0.91]
[null,"Jerry Thomas Elem",865,865,764,0.88,-44,794,0.97]
[null,"Jupiter Elem",667,667,606,0.91,50,643,0.9]
[null,"Jupiter Farms Elem",729,729,809,1.11,67,816,1.03]
[null,"K.E. Cunningham/Canal Point Elem",1042,1042,656,0.63,-267,614,0.79]
[null,"Lake Park Elem",596,596,655,1.1,39,663,1.04]
[null,"Lantana Elem",898,898,904,1.01,-2,901,1.01]
[null,"Liberty Park Elem",1322,1322,1404,1.06,130,1523,1.05]
[null,"Lighthouse Elem",1228,1228,1206,0.98,107,1395,1.04]
[null,"Limestone Creek Elem",892,892,988,1.11,42,983,1.05]
[null,"Lincoln Elem",1635,1635,1030,0.63,-496,997,0.88]
[null,"Loxahatchee Groves Elem",854,854,845,0.99,11,898,1.04]
[null,"Manatee Elem",1577,1577,1751,1.11,-491,1155,1.06]
[null,"Meadow Park Elem",800,800,664,0.83,-136,656,0.99]
[null,"Melaleuca Elem",1163,1163,993,0.85,-189,980,1.01]
[null,"Morikami Park Elem",968,968,806,0,0,968,1]
[null,"New Horizons Elem",1262,1262,1466,1.16,-136,1143,1.02]
[null,"North Grade Elem",82,82,512,6.24,708,607,0.77]
[null,"North Palm Beach Elem",808,808,686,0.85,0,657,0.81]
[null,"Northboro Elem",1035,1035,743,0.72,-147,820,0.92]
[null,"Northmore Elem",1465,1465,625,0.43,-699,674,0.88]
[null,"Orchard View Elem",1021,1021,908,0.89,0,973,0.95]
[null,"Pahokee (K-6) Elem",1114,1114,753,0.68,-278,772,0.92]
[null,"Palm Beach Gardens Elem",823,823,686,0.83,-123,609,0.87]
[null,"Palm Beach Public Elem",434,434,365,0.84,0,366,0.84]
[null,"Palm Springs Elem",984,984,928,0.94,-118,945,1.09]
[null,"Palmetto Elem",648,648,582,0.9,322,584,0.6]
[null,"Panther Run Elem",905,905,1199,1.32,680,1685,1.06]
[null,"Pine Grove Elem",967,967,708,0.73,-235,757,1.03]
[null,"Pioneer Park Elem",1019,1019,673,0.66,0,650,0.64]
[null,"Plumosa Elem",778,778,611,0.79,-78,642,0.92]
[null,"Poinciana Elem",917,917,756,0.82,0,917,1]
[null,"Rolling Green Elem",1194,1194,865,0.72,-367,857,1.04]
[null,"Roosevelt Elem",1060,1060,913,0.86,0,1063,1]
[null,"Rosenwald Elem",849,849,444,0.52,-159,472,0.68]
[null,"S.D. Spady Elem",791,791,532,0.67,-135,700,1.07]
[null,"Sandpiper Shores Elem",1223,1223,1139,0.93,-47,1195,1.02]
[null,"Seminole Trails Elem",946,946,885,0.94,0,958,1.01]
[null,"South Grade Elem",818,818,0,0,0,818,1]
[null,"South Olive Elem",947,947,996,1.05,9,956,1]
[null,"Starlight Cove Elem",1339,1339,1276,0.95,26,1425,1.04]
[null,"Timber Trace Elem",891,891,888,1,134,1075,1.05]
[null,"U.B.Kinsey/Palmview Elem",708,708,631,0.89,138,670,0.79]
[null,"Verde Elem",1020,1020,787,0.77,-261,782,1.03]
[null,"Washington Elem",723,723,576,0.8,-103,620,1]
[null,"Waters Edge Elem",995,995,695,0.7,0,894,0.9]
[null,"Wellington Elem",1103,1103,1184,1.07,-141,968,1.01]
[null,"West Gate Elem",943,943,711,0.75,27,743,0.77]
[null,"West Riviera Elem",1313,1313,845,0.64,-419,867,0.97]
[null,"Westward Elem",815,815,672,0.82,-75,692,0.94]
[null,"Whispering Pines Elem",1137,1137,893,0.79,-311,879,1.06]
[null,"Wynnebrook Elem",1149,1149,1052,0.92,-177,1011,1.04]
[null,"Bear Lakes Middle",2195,1975,1465,0.74,-503,1602,1.09]
[null,"Boca Raton Middle",1639,1475,1216,0.82,-364,1202,1.08]
[null,"Carver Middle",1855,1669,1606,0.96,34,1765,1.04]
[null,"Christa McAuliffe Middle",1652,1486,1150,0.77,-161,1394,1.05]
[null,"Congress Middle",1874,1686,1445,0.86,-159,1589,1.04]
[null,"Conniston Middle",1621,1458,1075,0.74,-220,1221,0.99]
[null,"Crestwood Middle",1920,1728,1537,0.89,-237,1650,1.11]
[null,"Eagles Landing Middle",1402,1261.8,1252,0,150,1460,1.03]
[null,"H.L. Watkins Middle",1325,1192,1374,1.15,186,1425,1.03]
[null,"J.F. Kennedy Middle",2024,1821,1423,0.78,-321,1548,1.03]
[null,"Jefferson Davis Middle",1919,1727,1623,0.94,-148,1652,1.05]
[null,"Jupiter Middle",1928,1735,1427,0.82,-338,1454,1.04]
[null,"Lake Shore Middle",1313,1181,1281,1.08,325,1400,0.93]
[null,"Lake Worth Middle",1958,1762,1543,0.88,-83,1798,1.07]
[null,"Lantana Middle",872,784,760,0.97,20,820,1.02]
[null,"Loggers Run Middle",1580,1422,1475,1.04,22,1485,1.03]
[null,"Middle School of the Arts",1932,1738,1198,0.69,-600,1200,1.05]
[null,"Okeeheelee Middle",1695,1525,1397,0.92,-30,1596,1.07]
[null,"Omni Middle",1801,1620,1254,0.77,-272,1440,1.07]
[null,"Roosevelt Middle",1473,1325.7,1441,1.09,200,1597,1.05]
[null,"Watson B. Duncan Middle",1661,1494,1529,1.02,309,1778,0.99]
[null,"Wellington Landings Middle",2151,1935,1846,0.95,122,2029,0.99]
[null,"Western Pines Middle",1389,1250,1238,0.99,400,1682,1.02]
[null,"Woodlands Middle",1633,1469,1472,1,400,1864,1]
[null,"Atlantic High",2466,2342,2619,1.12,773,2992,0.96]
[null,"Boca Raton High",2299,2184,1916,0.88,433,1890,0.72]
[null,"Dreyfoos School of the Arts",1474,1326,1147,0.87,0,1326,1]
[null,"Forest Hill High",1812,1721,1571,0.91,-75,1733,1.05]
[null,"Glades Central High",1671,1587,1444,0.91,0,1400,0.88]
[null,"J.I. Leonard High",2768,2629,2792,1.06,208,2940,1.04]
[null,"Jupiter High",2662,2528,1692,0.67,0,1907,0.75]
[null,"Lake Worth High",2926,2779,2724,0.98,-124,2879,1.08]
[null,"Olympic Heights High",2093,1988,2537,1.28,720,2781,1.03]
[null,"Palm Beach Gardens High",2436,2314,2324,1,-89,1367,0.61]
[null,"Palm Beach Lakes High",3105,2949,2936,1,40,2954,0.99]
[null,"Pahokee Mid/Sr.  (7-12)",1421,1278,975,0.76,-26,1081,0.86]
[null,"Royal Palm Beach High",2641,2508,1804,0.72,0,2503,1]
[null,"Santaluces High",3472,3298,3476,1.05,475,4330,1.15]
[null,"Spanish River High",2799,2659,2837,1.07,294,3071,1.04]
[null,"Suncoast High",1164,989,1268,1.28,0,989,1]
[null,"W.T. Dwyer High",2124,2017,2048,1.02,0,2194,1.09]
[null,"Wellington High",2970,2821,2742,0.97,132,3207,1.09]
["2a.","PALM BEACH Total",163878,157399.5,142381,0.9,-3735,151812,0.99]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New Elementary School \"A\" (970 Stu Sta) in the Jupiter area to accommodate growth."]
[null,"New Elementary School \"B\" (970 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New Elementary School \"C\" (970 Stu Sta) 13th Street and Avenue \"U\" in Riviera Beach to accommodate growth."]
[null,"New Elementary School \"D\" (970 Stu Sta) in the Okeechobee corridor area, West Palm Beach to accommodate growth."]
[null,"New Elementary School \"E\" (970 Stu Sta) Bent Creek Road, Wellington to accommodate growth."]
[null,"New Elementary School \"F\" (970 Stu Sta) Melaleuca Lane and Haverhill Road, extended, Greenacres to accommodate growth."]
[null,"New Elementary School \"G\" (970 Stu Sta) Smith Dairy, West PUD, Lake Worth to accommodate growth."]
[null,"New Elementary School \"H\" (970 Stu Sta) Kimberly Blvd.  and Coral Ridge Drive, western Boca Raton to accommodate growth."]
[null,"New Elementary School \"I\" (970 Stu Sta) in the west Boca Raton/Delray Beach area to accommodate growth."]
[null,"New Elementary School \"J\" (970 Stu Sta) in the Royal Palm Beach area to accommodate growth."]
[null,"New Elementary School \"K\" (970 Stu Sta) in the West Palm Beach area to accommodate growth."]
[null,"New Elementary School \"L\" (970 Stu Sta) in the Wellington area to accommodate growth."]
[null,"New Elementary School \"M\" (970 Stu Sta) in the Boynton Beach/Delray Beach area to accommodate growth."]
[null,"New Elementary School \"N\" (500 Stu Sta) in the eastern West Palm Beach area to accommodate growth."]
[null,"New Elementary School \"P\" (500 Stu Sta) in the Delray Beach area to accommodate growth."]
[null,"New Middle School \"BB\" (1300 Stu Sta) in the Boynton Beach/Delray Beach area to accommodate growth."]
[null,"New Middle School \"CC\" (1300 Stu Sta) Orange Pointe PUD, Wellington to accommodate growth."]
[null,"New Middle School \"DD\" (1300 Stu Sta) in the Lake Worth area to accommodate growth."]
[null,"New Middle School \"EE\" (1300 Stu Sta) in the West Palm Beach area to accommodate growth."]
[null,"New Middle School \"FF\" (1300 Stu Sta) in the Jupiter area to accommodate growth."]
[null,"New Middle School \"GG\" (1300 Stu Sta) in the Boca Raton area to accommodate growth."]
[null,"New Middle School \"HH\" (1300 Stu Sta) in the Acreage area to accommodate growth."]
[null,"New High School \"EEE\" (2500 Stu Sta) Jog Road in the western Boynton Beach area to accommodate growth."]
[null,"New High School \"III\" (2500 Stu Sta) N.W. 22nd Ave., Quantum Park, Boynton Beach area to accommodate growth.",{"$nulls":4}," "]
[null,"New High School \"JJJ\" (2500 Stu Sta) in the west central West Palm Beach area to accommodate growth."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1998-99","Owner","Student Stations","as classroom space","in 2003-04","units by 2003-04","Column \"C\""]
[null,"Acreage Pines Elem",16,"PBCSD/Leased",369,0,3,13]
[null,"Addison Mizner Elem",10,"PBCSD/Leased",221,0,1,9]
[null,"Allamanda Elem",6,"PBCSD/Leased",75,0,4,2]
[null,"Banyan Creek Elem",15,"PBCSD/Leased",317,0,2,13]
[null,"Barton Elem",29,"PBCSD/Leased",651,0,5,24]
[null,"Belle Glade Elem",0," ",0,0,0,0]
[null,"Belvedere Elem",11,"PBCSD/Leased",264,1,2,9]
[null,"Berkshire Elem",16,"PBCSD/Leased",353,3,4,12]
[null,"Boca Raton Elem",12,"PBCSD/Leased",212,0,0,12]
[null,"C.O.Taylor/Kirklane Elem",16,"PBCSD/Leased",250,5,0,16]
[null,"Calusa Elem",5,"PBCSD/Leased",104,0,0,5]
[null,"Citrus Cove Elem",22,"PBCSD/Leased",498,0,6,16]
[null,"Coral Sunset Elem",15,"PBCSD/Leased",331,1,1,14]
[null,"Crystal Lakes Elem",6,"PBCSD/Leased",172,0,3,3]
[null,"Cypress Trails Elem",8,"PBCSD/Leased",212,0,2,6]
[null,"D.D. Eisenhower Elem",6,"PBCSD/Leased",95,0,0,6]
[null,"Del Prado Elem",19,"PBCSD/Leased",429,0,6,13]
[null,"Egret Lake Elem",0," ",0,0,2,-2]
[null,"Forest Hill Elem",21,"PBCSD/Leased",487,1,3,18]
[null,"Forest Park Elem",5,"PBCSD/Leased",130,0,2,3]
[null,"Galaxy Elem",6,"PBCSD/Leased",158,0,0,6]
[null,"Glade View Elem",17,"PBCSD/Leased",296,1,0,17]
[null,"Golden Grove Elem",0," ",0,0,2,-2]
[null,"Gove Elem",21,"PBCSD/Leased",400,1,0,21]
[null,"Greenacres Elem",19,"PBCSD/Leased",355,1,0,19]
[null,"Grove Park Elem",2,"PBCSD/Leased",52,0,1,1]
[null,"H.L. Johnson Elem",21,"PBCSD/Leased",440,0,3,18]
[null,"Hagen Road Elem",6,"PBCSD/Leased",153,0,2,4]
[null,"Hammock Pointe Elem",4,"PBCSD/Leased",104,0,0,4]
[null,"Highland Elem",30,"PBCSD/Leased",626,1,0,30]
[null,"Indian Pines Elem",9,"PBCSD/Leased",193,1,2,7]
[null,"J.C. Mitchell Elem",8,"PBCSD/Leased",86,3,0,8]
[null,"Jerry Thomas Elem",2,"PBCSD/Leased",44,0,0,2]
[null,"Jupiter Elem",0," ",0,0,0,0]
[null,"Jupiter Farms Elem",0," ",0,0,1,-1]
[null,"K.E. Cunningham/Canal Point Elem",10,"PBCSD/Leased",267,0,0,10]
[null,"Lake Park Elem",9,"PBCSD/Leased",186,0,0,9]
[null,"Lantana Elem",11,"PBCSD/Leased",277,0,1,10]
[null,"Liberty Park Elem",27,"PBCSD/Leased",524,0,3,24]
[null,"Lighthouse Elem",21,"PBCSD/Leased",493,0,4,17]
[null,"Limestone Creek Elem",7,"PBCSD/Leased",158,0,0,7]
[null,"Lincoln Elem",28,"PBCSD/Leased",600,6,0,28]
[null,"Loxahatchee Groves Elem",7,"PBCSD/Leased",132,0,2,5]
[null,"Manatee Elem",29,"PBCSD/Leased",611,2,8,21]
[null,"Meadow Park Elem",7,"PBCSD/Leased",136,0,2,5]
[null,"Melaleuca Elem",14,"PBCSD/Leased",363,1,1,13]
[null,"Morikami Park Elem",0,null,0,0,0,0]
[null,"New Horizons Elem",22,"PBCSD/Leased",568,0,4,18]
[null,"North Grade Elem",4,"PBCSD/Leased",82,0,0,4]
[null,"North Palm Beach Elem",0," ",0,0,0,0]
[null,"Northboro Elem",10,"PBCSD/Leased",207,3,1,9]
[null,"Northmore Elem",46,"PBCSD/Leased",1083,1,0,46]
[null,"Orchard View Elem",0," ",0,0,0,0]
[null,"Pahokee (K-6) Elem",22,"PBCSD/Leased",423,5,0,22]
[null,"Palm Beach Gardens Elem",8,"PBCSD/Leased",123,0,0,8]
[null,"Palm Beach Public Elem",0," ",0,0,0,0]
[null,"Palm Springs Elem",16,"PBCSD/Leased",368,0,1,15]
[null,"Palmetto Elem",21,"PBCSD/Leased",446,3,0,21]
[null,"Panther Run Elem",9,"PBCSD/Leased",218,2,8,1]
[null,"Pine Grove Elem",12,"PBCSD/Leased",235,0,1,11]
[null,"Pioneer Park Elem",0," ",0,0,0,0]
[null,"Plumosa Elem",3,"PBCSD/Leased",78,0,0,3]
[null,"Poinciana Elem",0," ",0,0,0,0]
[null,"Rolling Green Elem",23,"PBCSD/Leased",592,0,2,21]
[null,"Roosevelt Elem",11,"PBCSD/Leased",277,0,2,9]
[null,"Rosenwald Elem",7,"PBCSD/Leased",159,0,0,7]
[null,"S.D. Spady Elem",8,"PBCSD/Leased",204,0,2,6]
[null,"Sandpiper Shores Elem",19,"PBCSD/Leased",421,2,2,17]
[null,"Seminole Trails Elem",9,"PBCSD/Leased",172,0,1,8]
[null,"South Olive Elem",15,"PBCSD/Leased",315,1,0,15]
[null,"Starlight Cove Elem",14,"PBCSD/Leased",374,0,4,10]
[null,"Timber Trace Elem",3,"PBCSD/Leased",66,0,0,3]
[null,"U.B.Kinsey/Palmview Elem",20,"PBCSD/Leased",316,0,0,20]
[null,"Verde Elem",11,"PBCSD/Leased",261,0,1,10]
[null,"Washington Elem",6,"PBCSD/Leased",103,0,1,5]
[null,"Waters Edge Elem",0," ",0,0,0,0]
[null,"Wellington Elem",18,"PBCSD/Leased",261,8,1,17]
[null,"West Gate Elem",25,"PBCSD/Leased",562,0,0,25]
[null,"West Riviera Elem",24,"PBCSD/Leased",443,3,5,19]
[null,"Westward Elem",5,"PBCSD/Leased",75,0,2,3]
[null,"Whispering Pines Elem",23,"PBCSD/Leased",311,0,0,23]
[null,"Wynnebrook Elem",23,"PBCSD/Leased",488,3,0,23]
[null,"Bear Lakes Middle",34,"PBCSD/Leased",850,0,1,33]
[null,"Boca Raton Middle",19,"PBCSD/Leased",355,4,1,18]
[null,"Carver Middle",13,"PBCSD/Leased",366,0,2,11]
[null,"Christa McAuliffe Middle",12,"PBCSD/Leased",287,1,0,12]
[null,"Congress Middle",15,"PBCSD/Leased",409,0,2,13]
[null,"Conniston Middle",14,"PBCSD/Leased",307,1,1,13]
[null,"Crestwood Middle",28,"PBCSD/Leased",587,0,9,19]
[null,"Eagles Landing Middle",0,null,0,0,9,-9]
[null,"H.L. Watkins Middle",17,"PBCSD/Leased",296,3,4,13]
[null,"J.F. Kennedy Middle",27,"PBCSD/Leased",655,0,3,24]
[null,"Jefferson Davis Middle",28,"PBCSD/Leased",606,8,3,25]
[null,"Jupiter Middle",22,"PBCSD/Leased",530,3,1,21]
[null,"Lake Shore Middle",18,"PBCSD/Leased",496,0,0,18]
[null,"Lake Worth Middle",36,"PBCSD/Leased",683,0,6,30]
[null,"Lantana Middle",12,"PBCSD/Leased",330,0,0,12]
[null,"Loggers Run Middle",8,"PBCSD/Leased",228,0,9,-1]
[null,"Middle School of the Arts",30,"PBCSD/Leased",802,0,3,27]
[null,"Okeeheelee Middle",10,"PBCSD/Leased",280,0,1,9]
[null,"Omni Middle",21,"PBCSD/Leased",472,0,9,12]
[null,"Roosevelt Middle",0," ",0,0,0,0]
[null,"Watson B. Duncan Middle",17,"PBCSD/Leased",341,0,0,17]
[null,"Wellington Landings Middle",31,"PBCSD/Leased",878,0,0,31]
[null,"Western Pines Middle",0," ",0,0,18,-18]
[null,"Woodlands Middle",0," ",0,0,15,-15]
[null,"Atlantic High",28,"PBCSD/Leased",780,6,3,25]
[null,"Boca Raton High",6,"PBCSD/Leased",177,0,0,6]
[null,"Dreyfoos School of the Arts",0," ",0,0,0,0]
[null,"Forest Hill High",13,"PBCSD/Leased",221,4,2,11]
[null,"Glades Central High",0," ",0,0,0,0]
[null,"J.I. Leonard High",32,"PBCSD/Leased",732,2,0,32]
[null,"Jupiter High",0," ",0,0,0,0]
[null,"Lake Worth High",40,"PBCSD/Leased",1137,4,6,34]
[null,"Olympic Heights High",4,"PBCSD/Leased",120,0,2,2]
[null,"Palm Beach Gardens High",3,"PBCSD/Leased",89,0,4,-1]
[null,"Palm Beach Lakes High",12,"PBCSD/Leased",360,0,0,12]
[null,"Pahokee Mid/Sr.  (7-12)",1,"PBCSD/Leased",26,0,1,0]
[null,"Royal Palm Beach High",0," ",0,0,0,0]
[null,"Santaluces High",31,"PBCSD/Leased",854,1,18,13]
[null,"Spanish River High",10,"PBCSD/Leased",295,0,3,7]
[null,"Suncoast High",2,"PBCSD/Leased",59,2,2,0]
[null,"W.T. Dwyer High",5,"PBCSD/Leased",103,0,0,5]
[null,"Wellington High",12,"PBCSD/Leased",321,3,9,3]
["2c1.","PALM BEACH Total",1601,null,36087,101,263,1338,"Avg Age 0"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"Acreage Pines Elem",13,null,null,null,13,null,13]
[null,"Addison Mizner Elem",9,{"$nulls":4},9,9]
[null,"Allamanda Elem",2,null,null,null,2,null,2]
[null,"Banyan Creek Elem",13,null,null,13,null," ",13]
[null,"Barton Elem",24,null,null,8,8,8]
[null,"Belvedere Elem",9,null,null,null,9,null,9]
[null,"Berkshire Elem",12,null,null,3,null,9,12]
[null,"Boca Raton Elem",12,{"$nulls":4},12,12]
[null,"C.O.Taylor/Kirklane Elem",16,null,null,13,3,null,16]
[null,"Calusa Elem",5,null,null,null,5,null,5]
[null,"Citrus Cove Elem",16,{"$nulls":4},16,16]
[null,"Coral Sunset Elem",14,null,null,null,14,null,14]
[null,"Crystal Lakes Elem",3,{"$nulls":4},3,3]
[null,"Cypress Trails Elem",6,{"$nulls":4},6,6]
[null,"D.D. Eisenhower Elem",6,null,null,null,2,4,6]
[null,"Del Prado Elem",13,null,null,null,13,null,13]
[null,"Forest Hill Elem",18,null,null,null,18,null,18]
[null,"Forest Park Elem",3,{"$nulls":4},3,3]
[null,"Galaxy Elem",6,{"$nulls":4},6,6]
[null,"Greenacres Elem",19,null,11,null,null,8,19]
[null,"Grove Park Elem",1,{"$nulls":4},1]
[null,"H.L. Johnson Elem",18,{"$nulls":4},18,18]
[null,"Hagen Road Elem",4,null,null,null,4]
[null,"Hammock Pointe Elem",4,null,null,null,4,null,4]
[null,"Highland Elem",30,30,{"$nulls":4},30]
[null,"Indian Pines Elem",7,null,5,null,2,null,7]
[null,"J.C. Mitchell Elem",8,{"$nulls":4},8,8]
[null,"Jerry Thomas Elem",2,null,null,null,2]
[null,"Lake Park Elem",9,null,null,9," ",null,9]
[null,"Lantana Elem",10,null,null,null,8,2]
[null,"Liberty Park Elem",24,null,8,null,14,2,24]
[null,"Lighthouse Elem",17,null,null,14,3,null,17]
[null,"Limestone Creek Elem",7,null,null,null,5,2]
[null,"Lincoln Elem",28,28,{"$nulls":4},28]
[null,"Loxahatchee Groves Elem",5,null,null,null,2,3,5]
[null,"Manatee Elem",21,8,10,null,3,null,21]
[null,"Meadow Park Elem",5,null,null,null,5,null,5]
[null,"Melaleuca Elem",13,null," ",null,4,9,13]
[null,"New Horizons Elem",18,null,10,null,null,8,18]
[null,"North Grade Elem",4,4,null," ",null,null,4]
[null,"Northboro Elem",9,null,null,8,1,null,9]
[null,"Northmore Elem",46,null,null,46,null,null,46]
[null,"Pahokee (K-6) Elem",22,null,null,22,null,null,22]
[null,"Palm Beach Gardens Elem",8,null,5," ",3,null,8]
[null,"Palm Springs Elem",15,null,4,3,null,8,15]
[null,"Palmetto Elem",21,null,null,14,null,7,21]
[null,"Panther Run Elem",1,null,1,null,null,2,3]
[null,"Pine Grove Elem",11,null,null,null,5,6,11]
[null,"Plumosa Elem",3,null,null,null,3,null,3]
[null,"Rolling Green Elem",21,null,null,7,null,14,21]
[null,"Roosevelt Elem",9,null,null,null,9,null,9]
[null,"Rosenwald Elem",7,3,2,2,null,null,7]
[null,"S.D. Spady Elem",6,{"$nulls":4},6,6]
[null,"Sandpiper Shores Elem",17,4,null,null,9,4,17]
[null,"Seminole Trails Elem",8,null,null,3,2,3,8]
[null,"South Olive Elem",15,null,null,null,15,null,15]
[null,"Starlight Cove Elem",10,null,null,3,2,5,10]
[null,"Timber Trace Elem",3,null,null," ",3,null,3]
[null,"U.B.Kinsey/Palmview Elem",20,6," ",6,null,8,20]
[null,"Verde Elem",10,null,null,null,10,null,10]
[null,"Washington Elem",5,null,null,5,null,null,5]
[null,"Wellington Elem",17,null,6,null,null,11,17]
[null,"West Gate Elem",25,null,null,null,25,null,25]
[null,"West Riviera Elem",19,null,null,15,4,null,19]
[null,"Westward Elem",3,null,null,null,3,null,3]
[null,"Whispering Pines Elem",23,null,3,6,9,5,23]
[null,"Wynnebrook Elem",23,null,null,null,20,3,23]
[null,"Bear Lakes Middle",33,15,null,5," ",13,33]
[null,"Boca Raton Middle",18,null,null,18,null,null,18]
[null,"Carver Middle",11,null,null,11,null,null,11]
[null,"Christa McAuliffe Middle",12,null,null,12,null,null,12]
[null,"Congress Middle",13,null,null,10,3,null,13]
[null,"Conniston Middle",13,null,null,null,9,4,13]
[null,"Crestwood Middle",19,null,null,9,null,10,19]
[null,"H.L. Watkins Middle",13,null,null," ",13,null,13]
[null,"J.F. Kennedy Middle",24,null,null," ",24,null,24]
[null,"Jefferson Davis Middle",25,14,null,2,null,9,25]
[null,"Jupiter Middle",21,null,null,15,6]
[null,"Lake Shore Middle",18,null,18," ",null,null,18]
[null,"Lake Worth Middle",30,null,null,null,24,6,30]
[null,"Lantana Middle",12,null,null,8,4]
[null,"Loggers Run Middle",8," "," ",null,null,8,8]
[null,"Middle School of the Arts",27,null,8,19,null,null,27]
[null,"Okeeheelee Middle",9,null,null,5,null,4,9]
[null,"Omni Middle",12,null," ",8,null,4,12]
[null,"Watson B. Duncan Middle",17,null,null,9,8]
[null,"Wellington Landings Middle",31,null,null,26,5,null,31]
[null,"Atlantic High",25,null,null,null,21,4,25]
[null,"Boca Raton High",6,null,null,null,6," ",6]
[null,"Forest Hill High",11,{"$nulls":4},11,11]
[null,"J.I. Leonard High",32,null,25,null,null,7,32]
[null,"Lake Worth High",34,null,null,34,null,null,34]
[null,"Olympic Heights High",2,null,2]
[null,"Palm Beach Lakes High",12,null,3,2,7]
[null,"Santaluces High",18,null,null,14,4,null,18]
[null,"Spanish River High",7,null,null,null,5,2,7]
[null,"W.T. Dwyer High",5,null,null,null,5]
[null,"Wellington High",3,null,null,null,3," ",3]
["2c2.","PALM BEACH Total",1352,112,121,407,413,301,1237]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1998-99","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2003-04","FISH Stu. Sta.","# Years Leased "]
[null,"Acreage Pines Elem",1,"Leased",25,11,0,0,16]
[null,"Addison Mizner Elem",4,"Leased",100,11,1,25,16]
[null,"Allamanda Elem",2,"Leased",50,11,2,50,16]
[null,"Banyan Creek Elem",3,"Leased",75,11,0,0,16]
[null,"Barton Elem",6,"Leased",150,11,6,150,16]
[null,"Belle Glade Elem",0,"Leased",0,11,0,0,16]
[null,"Belvedere Elem",1,"Leased",25,11,1,25,16]
[null,"Berkshire Elem",0,"Leased",0,11,0,0,16]
[null,"Boca Raton Elem",3,"Leased",75,11,0,0,16]
[null,"C.O.Taylor/Kirklane Elem",0,"Leased",0,11,0,0,16]
[null,"Calusa Elem",0,"Leased",0,11,0,0,16]
[null,"Citrus Cove Elem",5,"Leased",125,11,5,125,16]
[null,"Coral Sunset Elem",1,"Leased",25,11,1,25,16]
[null,"Crystal Lakes Elem",1,"Leased",25,11,0,0,16]
[null,"Cypress Trails Elem",0,"Leased",0,11,0,0,16]
[null,"D.D. Eisenhower Elem",0,"Leased",0,11,0,0,16]
[null,"Del Prado Elem",5,"Leased",125,11,5,125,16]
[null,"Egret Lake Elem",0,"Leased",0,11,0,0,16]
[null,"Forest Hill Elem",2,"Leased",50,11,1,25,16]
[null,"Forest Park Elem",0,"Leased",0,11,0,0,16]
[null,"Galaxy Elem",0,"Leased",0,11,0,0,16]
[null,"Glade View Elem",7,"Leased",175,11,2,50,16]
[null,"Golden Grove Elem",0,"Leased",0,11,0,0,16]
[null,"Gove Elem",11,"Leased",275,11,7,175,16]
[null,"Greenacres Elem",2,"Leased",50,11,0,0,16]
[null,"Grove Park Elem",0,"Leased",0,11,0,0,16]
[null,"H.L. Johnson Elem",0,"Leased",0,11,0,0,16]
[null,"Hagen Road Elem",0,"Leased",0,11,2,50,16]
[null,"Hammock Pointe Elem",0,"Leased",0,11,0,0,16]
[null,"Highland Elem",0,"Leased",0,11,0,0,16]
[null,"Indian Pines Elem",3,"Leased",75,11,2,50,16]
[null,"J.C. Mitchell Elem",0,"Leased",0,11,0,0,16]
[null,"Jerry Thomas Elem",0,"Leased",0,11,0,0,16]
[null,"Jupiter Elem",0,"Leased",0,11,0,0,16]
[null,"Jupiter Farms Elem",0,"Leased",0,11,0,0,16]
[null,"K.E. Cunningham/Canal Point Elem",0,"Leased",0,11,0,0,16]
[null,"Lake Park Elem",4,"Leased",100,11,0,0,16]
[null,"Lantana Elem",0,"Leased",0,11,1,25,16]
[null,"Liberty Park Elem",3,"Leased",75,11,3,75,16]
[null,"Lighthouse Elem",1,"Leased",25,11,0,0,16]
[null,"Limestone Creek Elem",1,"Leased",25,11,1,25,16]
[null,"Lincoln Elem",0,"Leased",0,11,0,0,16]
[null,"Loxahatchee Groves Elem",3,"Leased",75,11,1,25,16]
[null,"Manatee Elem",4,"Leased",100,11,0,0,16]
[null,"Meadow Park Elem",2,"Leased",50,11,0,0,16]
[null,"Melaleuca Elem",3,"Leased",75,11,1,25,16]
[null,"Morikami Park Elem",0,"Leased",0,11,0,0,16]
[null,"New Horizons Elem",5,"Leased",125,11,0,0,16]
[null,"North Grade Elem",0,"Leased",0,11,0,0,16]
[null,"North Palm Beach Elem",0,"Leased",0,11,0,0,16]
[null,"Northboro Elem",1,"Leased",25,11,1,25,16]
[null,"Northmore Elem",31,"Leased",775,11,0,0,16]
[null,"Orchard View Elem",0,"Leased",0,11,2,50,16]
[null,"Pahokee (K-6) Elem",3,"Leased",75,11,1,25,16]
[null,"Palm Beach Gardens Elem",2,"Leased",50,11,0,0,16]
[null,"Palm Beach Public Elem",0,"Leased",0,11,0,0,16]
[null,"Palm Springs Elem",6,"Leased",150,11,4,100,16]
[null,"Palmetto Elem",5,"Leased",125,11,0,0,16]
[null,"Panther Run Elem",6,"Leased",150,11,4,100,16]
[null,"Pine Grove Elem",1,"Leased",25,11,1,25,16]
[null,"Pioneer Park Elem",0,"Leased",0,11,0,0,16]
[null,"Plumosa Elem",0,"Leased",0,11,0,0,16]
[null,"Poinciana Elem",0,"Leased",0,11,0,0,16]
[null,"Rolling Green Elem",2,"Leased",50,11,2,50,16]
[null,"Roosevelt Elem",2,"Leased",50,11,2,50,16]
[null,"Rosenwald Elem",0,"Leased",0,11,0,0,16]
[null,"S.D. Spady Elem",1,"Leased",25,11,0,0,16]
[null,"Sandpiper Shores Elem",7,"Leased",175,11,2,50,16]
[null,"Seminole Trails Elem",0,"Leased",0,11,0,0,16]
[null,"South Olive Elem",0,"Leased",0,11,0,0,16]
[null,"Starlight Cove Elem",3,"Leased",75,11,0,0,16]
[null,"Timber Trace Elem",2,"Leased",50,11,0,0,16]
[null,"U.B.Kinsey/Palmview Elem",2,"Leased",50,11,0,0,16]
[null,"Verde Elem",2,"Leased",50,11,1,25,16]
[null,"Washington Elem",1,"Leased",25,11,1,25,16]
[null,"Waters Edge Elem",0,"Leased",0,11,0,0,16]
[null,"Wellington Elem",6,"Leased",150,11,5,125,16]
[null,"West Gate Elem",10,"Leased",250,11,0,0,16]
[null,"West Riviera Elem",0,"Leased",0,11,0,0,16]
[null,"Westward Elem",2,"Leased",50,11,0,0,16]
[null,"Whispering Pines Elem",2,"Leased",50,11,0,0,16]
[null,"Wynnebrook Elem",9,"Leased",225,11,0,0,16]
[null,"Bear Lakes Middle",3,"Leased",75,11,2,50,16]
[null,"Boca Raton Middle",5,"Leased",125,11,3,75,16]
[null,"Carver Middle",8,"Leased",200,11,5,125,16]
[null,"Christa McAuliffe Middle",8,"Leased",200,11,0,0,16]
[null,"Congress Middle",3,"Leased",75,11,3,75,16]
[null,"Conniston Middle",0,"Leased",0,11,0,0,16]
[null,"Crestwood Middle",10,"Leased",250,11,0,0,16]
[null,"Eagles Landing Middle",3,"Leased",75,11,3,75,16]
[null,"H.L. Watkins Middle",1,"Leased",25,11,0,0,16]
[null,"J.F. Kennedy Middle",15,"Leased",375,11,3,75,16]
[null,"Jefferson Davis Middle",0,"Leased",0,11,0,0,16]
[null,"Jupiter Middle",9,"Leased",225,11,0,0,16]
[null,"Lake Shore Middle",0,"Leased",0,11,0,0,16]
[null,"Lake Worth Middle",8,"Leased",200,11,6,150,16]
[null,"Lantana Middle",4,"Leased",100,11,0,0,16]
[null,"Loggers Run Middle",2,"Leased",50,11,2,50,16]
[null,"Middle School of the Arts",14,"Leased",350,11,3,75,16]
[null,"Okeeheelee Middle",0,"Leased",0,11,0,0,16]
[null,"Omni Middle",2,"Leased",50,11,1,25,16]
[null,"Roosevelt Middle",0,"Leased",0,11,0,0,16]
[null,"Watson B. Duncan Middle",2,"Leased",50,11,0,0,16]
[null,"Wellington Landings Middle",11,"Leased",275,11,0,0,16]
[null,"Western Pines Middle",2,"Leased",50,11,2,50,16]
[null,"Woodlands Middle",2,"Leased",50,11,2,50,16]
[null,"Atlantic High",2,"Leased",50,11,0,0,16]
[null,"Boca Raton High",2,"Leased",50,11,0,0,16]
[null,"Dreyfoos School of the Arts",0,"Leased",0,11,0,0,16]
[null,"Forest Hill High",0,"Leased",0,11,0,0,16]
[null,"Glades Central High",0,"Leased",0,11,0,0,16]
[null,"J.I. Leonard High",5,"Leased",125,11,0,0,16]
[null,"Jupiter High",0,"Leased",0,11,0,0,16]
[null,"Lake Worth High",8,"Leased",200,11,6,150,16]
[null,"Olympic Heights High",8,"Leased",200,11,0,0,16]
[null,"Palm Beach Gardens High",2,"Leased",50,11,0,0,16]
[null,"Palm Beach Lakes High",2,"Leased",50,11,0,0,16]
[null,"Pahokee Mid/Sr.  (7-12)",0,"Leased",0,11,0,0,16]
[null,"Royal Palm Beach High",0,"Leased",0,11,0,0,16]
[null,"Santaluces High",11,"Leased",275,11,7,175,16]
[null,"Spanish River High",0,"Leased",0,11,0,0,16]
[null,"Suncoast High",0,"Leased",0,11,0,0,16]
[null,"W.T. Dwyer High",1,"Leased",25,11,0,0,16]
[null,"Wellington High",0,"Leased",0,11,0,0,16]
["2c3.","PALM BEACH Total",342,null,8550,1364,116,2900,1984]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2003-04"]
[null,"Edventure - High, ESE",8,"Edventure Charter School, Inc","1998-99",40,35,3,35]
[null,"Potentials - Elem, ESE",2,"The Arc","1998-99",30,21,3,21]
[null,"Partnership Academy - Elem",5,"The Partnership Academy of the Glades, Inc","1998-99",100,97,3,97]
[null,"Delray Beach Academy - Midd",3,"Delray Beach Academy","1998-99",66,66,3,66]
[null,"Nguzo Saba - Elem",5,"Joseph Littels - Nguzo Saba Charter School, Inc","1998-99",125,108,5,108]
[null,"Renaissance Learning Center - Elem, ESE",1,"Renaissance Learning Center","1999-00",10,6,3,6]
[null,"St. Mary's Preschool Autism Center - Elem, ESE",4,"St. Mary's Inc.","1999-00",40,22,5,22]
["2c4.","PALM BEACH Total",28,null,null,411,355,25,355]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2003-04) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1998-99 CO-FTE","1998-99 Class size","2003-04 CO-FTE","be added (removed)","2003-04 Class size"]
[null,"Acreage Pines Elem",47,1063,1298,27.62,1700,28,22.67]
[null,"Addison Mizner Elem",38,878,864,22.74,768,2,19.2]
[null,"Allamanda Elem",39,948,702,18,681,-1,17.92]
[null,"Banyan Creek Elem",51,1105,1032,20.24,895,0,17.55]
[null,"Barton Elem",35,1388,979,27.97,906,7,21.57]
[null,"Belle Glade Elem",41,994,897,21.88,948,0,23.12]
[null,"Belvedere Elem",43,866,854,19.86,1007,2,22.38]
[null,"Berkshire Elem",45,977,890,19.78,878,-4,21.41]
[null,"Boca Raton Elem",21,444,321,15.29,331,0,15.76]
[null,"C.O.Taylor/Kirklane Elem",53,1288,1116,21.06,999,-4,20.39]
[null,"Calusa Elem",37,824,607,16.41,613,-2,17.51]
[null,"Citrus Cove Elem",50,1255,1272,25.44,1415,5,25.73]
[null,"Coral Reef Elem",42,970,0,0,1145,0,27.26]
[null,"Coral Sunset Elem",49,1097,1012,20.65,1020,2,20]
[null,"Crystal Lakes Elem",43,980,914,21.26,999,-3,24.98]
[null,"Cypress Trails Elem",44,912,867,19.7,954,4,19.88]
[null,"D.D. Eisenhower Elem",34,892,621,18.26,730,0,21.47]
[null,"Del Prado Elem",48,1149,1144,23.83,1094,-2,23.78]
[null,"Egret Lake Elem",32,760,792,24.75,1005,3,28.71]
[null,"Forest Hill Elem",51,1165,1135,22.25,1092,2,20.6]
[null,"Forest Park Elem",38,758,691,18.18,695,0,18.29]
[null,"Galaxy Elem",40,757,877,21.93,774,3,18]
[null,"Glade View Elem",46,930,629,13.67,581,-8,15.29]
[null,"Golden Grove Elem",42,995,1022,24.33,1137,5,24.19]
[null,"Gove Elem",51,1091,808,15.84,790,-8,18.37]
[null,"Greenacres Elem",42,987,787,18.74,765,-5,20.68]
[null,"Grove Park Elem",37,790,736,19.89,765,0,20.68]
[null,"H.L. Johnson Elem",54,1206,1194,22.11,1275,0,23.61]
[null,"Hagen Road Elem",32,844,534,16.69,846,2,24.88]
[null,"Hammock Pointe Elem",37,842,948,25.62,866,3,21.65]
[null,"Highland Elem",49,1393,941,19.2,999,0,20.39]
[null,"Indian Pines Elem",42,893,982,23.38,981,1,22.81]
[null,"J.C. Mitchell Elem",47,830,770,16.38,676,-3,15.36]
[null,"Jerry Thomas Elem",37,865,764,20.65,794,0,21.46]
[null,"Jupiter Elem",40,667,606,15.15,643,0,16.08]
[null,"Jupiter Farms Elem",35,729,809,23.11,816,0,23.31]
[null,"K.E. Cunningham/Canal Point Elem",46,1042,656,14.26,614,-7,15.74]
[null,"Lake Park Elem",28,596,655,23.39,663,2,22.1]
[null,"Lantana Elem",34,898,904,26.59,901,0,26.5]
[null,"Liberty Park Elem",57,1322,1404,24.63,1523,4,24.97]
[null,"Lighthouse Elem",53,1228,1206,22.75,1395,16,20.22]
[null,"Limestone Creek Elem",38,892,988,26,983,5,22.86]
[null,"Lincoln Elem",55,1635,1030,18.73,997,-3,19.17]
[null,"Loxahatchee Groves Elem",42,854,845,20.12,898,3,19.96]
[null,"Manatee Elem",61,1751,1751,28.7,1155,29,12.83]
[null,"Meadow Park Elem",40,800,664,16.6,656,0,16.4]
[null,"Melaleuca Elem",43,1163,993,23.09,980,-3,24.5]
[null,"Morikami Park Elem",44,968,806,18.32,968,0,22]
[null,"New Horizons Elem",53,1262,1466,27.66,1143,13,17.32]
[null,"North Grade Elem",24,82,512,21.33,607,2,23.35]
[null,"North Palm Beach Elem",37,808,686,18.54,657,0,17.76]
[null,"Northboro Elem",46,1035,743,16.15,820,-5,20]
[null,"Northmore Elem",39,1465,625,16.03,674,2,16.44]
[null,"Orchard View Elem",42,1021,908,21.62,973,5,20.7]
[null,"Pahokee (K-6) Elem",45,1114,753,16.73,772,-2,17.95]
[null,"Palm Beach Gardens Elem",39,823,686,17.59,609,-2,16.46]
[null,"Palm Beach Public Elem",23,434,365,15.87,366,0,15.91]
[null,"Palm Springs Elem",38,984,928,24.42,945,0,24.87]
[null,"Palmetto Elem",38,648,582,15.32,584,-2,16.22]
[null,"Panther Run Elem",37,905,1199,32.41,1685,19,30.09]
[null,"Pine Grove Elem",41,967,708,17.27,757,0,18.46]
[null,"Pioneer Park Elem",43,1019,673,15.65,650,0,15.12]
[null,"Plumosa Elem",31,778,611,19.71,642,-2,22.14]
[null,"Poinciana Elem",37,917,756,20.43,917,0,24.78]
[null,"Rolling Green Elem",44,1194,865,19.66,857,-9,24.49]
[null,"Roosevelt Elem",50,1060,913,18.26,1063,-2,22.15]
[null,"Rosenwald Elem",37,849,444,12,472,-3,13.88]
[null,"S.D. Spady Elem",27,791,532,19.7,700,-4,30.43]
[null,"Sandpiper Shores Elem",57,1223,1139,19.98,1195,0,20.96]
[null,"Seminole Trails Elem",39,946,885,22.69,958,-2,25.89]
[null,"South Grade Elem",37,818,0,0,818,0,22.11]
[null,"South Olive Elem",48,947,996,20.75,956,0,19.92]
[null,"Starlight Cove Elem",51,1339,1276,25.02,1425,2,26.89]
[null,"Timber Trace Elem",37,891,888,24,1075,3,26.88]
[null,"U.B.Kinsey/Palmview Elem",35,708,631,18.03,670,4,17.18]
[null,"Verde Elem",45,1020,787,17.49,782,-4,19.07]
[null,"Washington Elem",37,723,576,15.57,620,0,16.76]
[null,"Waters Edge Elem",43,995,695,16.16,894,2,19.87]
[null,"Wellington Elem",57,1103,1184,20.77,968,0,16.98]
[null,"West Gate Elem",45,943,711,15.8,743,-4,18.12]
[null,"West Riviera Elem",54,1313,845,15.65,867,-11,20.16]
[null,"Westward Elem",45,815,672,14.93,692,0,15.38]
[null,"Whispering Pines Elem",54,1137,893,16.54,879,-3,17.24]
[null,"Wynnebrook Elem",54,1149,1052,19.48,1011,-4,20.22]
[null,"Bear Lakes Middle",87,1975,1465,16.84,1602,-17,22.89]
[null,"Boca Raton Middle",78,1475,1216,15.59,1202,-12,18.21]
[null,"Carver Middle",69,1669,1060,15.36,1765,11,22.06]
[null,"Christa McAuliffe Middle",62,1486,1150,18.55,1394,-8,25.81]
[null,"Congress Middle",68,1686,1445,21.25,1589,2,22.7]
[null,"Conniston Middle",66,1458,1075,16.29,1221,-7,20.69]
[null,"Crestwood Middle",73,1728,1537,21.05,1650,-5,24.26]
[null,"Eagles Landing Middle",54,1262,1252,23.19,1460]
[null,"H.L. Watkins Middle",69,1192,1374,19.91,1425,9,18.27]
[null,"J.F. Kennedy Middle",84,1821,1423,16.94,1548,-9,20.64]
[null,"Jefferson Davis Middle",70,1727,1623,23.19,1652,-8,26.65]
[null,"Jupiter Middle",53,1735,1427,26.92,1454,9,23.45]
[null,"Lake Shore Middle",73,1181,1281,17.55,1400,13,16.28]
[null,"Lake Worth Middle",54,1762,1543,28.57,1798,6,29.97]
[null,"Lantana Middle",28,784,760,27.14,820,5,24.85]
[null,"Loggers Run Middle",100,1422,1475,14.75,1485,-27,20.34]
[null,"Middle School of the Arts",49,1738,1198,24.45,1200,-3,26.09]
[null,"Okeeheelee Middle",58,1525,1397,24.09,1596,0,27.52]
[null,"Omni Middle",74,1620,1254,16.95,1440,0,19.46]
[null,"Roosevelt Middle",53,1325.7,1441,27.19,1597,10,25.35]
[null,"Watson B. Duncan Middle",63,1494,1529,24.27,1778,13,23.39]
[null,"Wellington Landings Middle",83,1935,1846,22.24,2029,8,22.3]
[null,"Western Pines Middle",54,1250,1238,22.93,1682,12,25.48]
[null,"Woodlands Middle",55,1469,1472,26.76,1864,0,33.89]
[null,"Atlantic High",112,2342,2619,23.38,2992,21,22.5]
[null,"Boca Raton High",94,2184,1916,20.38,1890,-4,21]
[null,"Dreyfoos School of the Arts",71,1326,1147,16.15,1326,0,18.68]
[null,"Forest Hill High",78,1721,1571,20.14,1733,0,22.22]
[null,"Glades Central High",79,1587,1444,18.28,1400,0,17.72]
[null,"J.I. Leonard High",129,2629,2792,21.64,2940,20,19.73]
[null,"Jupiter High",108,2528,1692,15.67,1907,0,17.66]
[null,"Lake Worth High",120,2779,2724,22.7,2879,2,23.6]
[null,"Olympic Heights High",92,1988,2537,27.58,2781,24,23.97]
[null,"Palm Beach Gardens High",110,2314,2324,21.13,1367,5,11.89]
[null,"Palm Beach Lakes High",113,2949,2936,25.98,2954,24,21.56]
[null,"Pahokee Mid/Sr.  (7-12)",72,1278,975,13.54,1081,0,15.01]
[null,"Royal Palm Beach High",108,2508,1804,16.7,2503,0,23.18]
[null,"Santaluces High",125,3298,3476,27.81,4330,35,27.06]
[null,"Spanish River High",110,2659,2837,25.79,3071,10,25.59]
[null,"Suncoast High",50,989,1268,25.36,989,0,19.78]
[null,"W.T. Dwyer High",94,2017,2048,21.79,2194,9,21.3]
[null,"Wellington High",116,2821,2742,23.64,3207,33,21.52]
["2e.","PALM BEACH Total",6920,158543.7,141835,"District Avg 20",152957,249,"District Avg 21"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR AVERAGE"]
[null,"Acreage Pines Elem",null,336,336,336,63,63,226.8]
[null,"Addison Mizner Elem",null,210,210,210,210,21,172.2]
[null,"Allamanda Elem",null,126,126,126,42,42,92.4]
[null,"Banyan Creek Elem",null,315,315,42,42,42,151.2]
[null,"Barton Elem",null,609,609,441,273,105,407.4]
[null,"Belle Glade Elem",null,0,0,0,0,0,0]
[null,"Belvedere Elem",null,231,231,231,42,42,155.4]
[null,"Berkshire Elem",null,336,336,273,273,84,260.4]
[null,"Boca Raton Elem",null,252,252,252,252,0,201.6]
[null,"C.O.Taylor/Kirklane Elem",null,336,336,63,0,0,147]
[null,"Calusa Elem",null,105,105,105,0,0,63]
[null,"Citrus Cove Elem",null,462,462,462,462,126,394.8]
[null,"Coral Sunset Elem",null,315,315,315,21,21,197.4]
[null,"Crystal Lakes Elem",null,126,126,126,126,63,113.4]
[null,"Cypress Trails Elem",null,168,168,168,168,42,142.8]
[null,"D.D. Eisenhower Elem",null,126,126,126,84,0,92.4]
[null,"Del Prado Elem",null,399,399,399,63,63,264.6]
[null,"Egret Lake Elem",null,0,0,25,25,25,15]
[null,"Forest Hill Elem",null,441,441,441,63,63,289.8]
[null,"Forest Park Elem",null,105,105,105,105,42,92.4]
[null,"Galaxy Elem",null,126,126,126,126,0,100.8]
[null,"Glade View Elem",null,357,357,357,357,357,357]
[null,"Golden Grove Elem",null,0,0,42,42,42,25.2]
[null,"Gove Elem",null,441,441,441,441,441,441]
[null,"Greenacres Elem",null,399,168,168,168,0,180.6]
[null,"Grove Park Elem",null,42,42,42,42,21,37.8]
[null,"H.L. Johnson Elem",null,441,441,441,441,63,365.4]
[null,"Hagen Road Elem",null,126,126,126,42,42,92.4]
[null,"Hammock Pointe Elem",null,84,84,84,0,0,50.4]
[null,"Highland Elem",null,0,0,0,0,0,0]
[null,"Indian Pines Elem",null,189,84,84,42,42,88.2]
[null,"J.C. Mitchell Elem",null,168,168,168,168,0,134.4]
[null,"Jerry Thomas Elem",null,42,42,42,0,0,25.2]
[null,"Jupiter Elem",null,0,0,0,0,0,0]
[null,"Jupiter Farms Elem",null,0,0,0,21,21,8.4]
[null,"K.E. Cunningham/Canal Point Elem",null,210,210,210,210,210,210]
[null,"Lake Park Elem",null,189,189,0,0,0,75.6]
[null,"Lantana Elem",null,231,231,231,63,21,155.4]
[null,"Liberty Park Elem",null,567,399,399,105,63,306.6]
[null,"Lighthouse Elem",null,441,441,147,84,84,239.4]
[null,"Limestone Creek Elem",null,147,147,147,105,42,117.6]
[null,"Lincoln Elem",null,0,0,0,0,0,0]
[null,"Loxahatchee Groves Elem",null,147,147,147,105,42,117.6]
[null,"Manatee Elem",null,441,231,231,168,168,247.8]
[null,"Meadow Park Elem",null,147,147,147,42,42,105]
[null,"Melaleuca Elem",null,294,294,294,210,21,222.6]
[null,"Morikami Park Elem",null,0,0,0,0,0,0]
[null,"New Horizons Elem",null,462,462,252,252,84,302.4]
[null,"North Grade Elem",null,0,0,0,0,0,0]
[null,"North Palm Beach Elem",null,0,0,0,0,0,0]
[null,"Northboro Elem",null,210,210,42,21,21,100.8]
[null,"Northmore Elem",null,840,840,0,0,0,336]
[null,"Orchard View Elem",null,0,0,50,50,50,30]
[null,"Pahokee (K-6) Elem",null,462,462,0,0,0,184.8]
[null,"Palm Beach Gardens Elem",null,168,63,63,0,0,58.8]
[null,"Palm Beach Public Elem",null,0,0,0,0,0,0]
[null,"Palm Springs Elem",null,336,252,189,189,21,197.4]
[null,"Palmetto Elem",null,441,441,147,147,0,235.2]
[null,"Panther Run Elem",null,189,168,168,168,126,163.8]
[null,"Pine Grove Elem",null,252,252,252,147,21,184.8]
[null,"Pioneer Park Elem",null,0,0,0,0,0,0]
[null,"Plumosa Elem",null,63,63,63,0,0,37.8]
[null,"Poinciana Elem",null,0,0,0,0,0,0]
[null,"Rolling Green Elem",null,483,483,336,336,42,336]
[null,"Roosevelt Elem",null,231,231,231,42,42,155.4]
[null,"Rosenwald Elem",null,84,42,0,0,0,25.2]
[null,"S.D. Spady Elem",null,168,168,168,168,42,142.8]
[null,"Sandpiper Shores Elem",null,315,315,315,126,42,222.6]
[null,"Seminole Trails Elem",null,189,189,126,84,21,121.8]
[null,"South Olive Elem",null,315,315,315,0,0,189]
[null,"Starlight Cove Elem",null,294,294,231,189,84,218.4]
[null,"Timber Trace Elem",null,63,63,63,0,0,37.8]
[null,"U.B.Kinsey/Palmview Elem",null,294,294,168,168,0,184.8]
[null,"Verde Elem",null,231,231,231,21,21,147]
[null,"Washington Elem",null,126,126,21,21,21,63]
[null,"Waters Edge Elem",null,0,0,0,0,25,5]
[null,"Wellington Elem",null,378,252,252,252,21,231]
[null,"West Gate Elem",null,525,525,525,0,0,315]
[null,"West Riviera Elem",null,504,504,189,105,105,281.4]
[null,"Westward Elem",null,105,105,105,42,42,79.8]
[null,"Whispering Pines Elem",null,483,420,294,105,0,260.4]
[null,"Wynnebrook Elem",null,483,483,483,63,0,302.4]
[null,"Bear Lakes Middle",null,399,399,294,294,21,281.4]
[null,"Boca Raton Middle",null,399,399,21,21,21,172.2]
[null,"Carver Middle",null,273,273,42,42,42,134.4]
[null,"Christa McAuliffe Middle",null,252,252,0,0,0,100.8]
[null,"Congress Middle",null,315,315,105,42,42,163.8]
[null,"Conniston Middle",null,294,294,294,105,21,201.6]
[null,"Crestwood Middle",null,588,588,399,399,189,432.6]
[null,"Eagles Landing Middle",null,0,42,105,189,189,105]
[null,"H.L. Watkins Middle",null,357,357,357,84,84,247.8]
[null,"J.F. Kennedy Middle",null,567,567,567,63,63,365.4]
[null,"Jefferson Davis Middle",null,294,294,252,252,63,231]
[null,"Jupiter Middle",null,462,462,147,21,21,222.6]
[null,"Lake Shore Middle",null,378,378,0,0,0,151.2]
[null,"Lake Worth Middle",null,756,756,756,126,0,478.8]
[null,"Lantana Middle",null,252,252,84,0,0,117.6]
[null,"Loggers Run Middle",null,168,168,168,168,0,134.4]
[null,"Middle School of the Arts",null,630,462,63,63,63,256.2]
[null,"Okeeheelee Middle",null,210,210,105,105,21,130.2]
[null,"Omni Middle",null,441,441,273,273,189,323.4]
[null,"Roosevelt Middle",null,0,0,0,0,0,0]
[null,"Watson B. Duncan Middle",null,357,357,168,0,0,176.4]
[null,"Wellington Landings Middle",null,651,651,105,0,0,281.4]
[null,"Western Pines Middle",null,0,0,0,0,100,20]
[null,"Woodlands Middle",null,0,0,0,0,0,0]
[null,"Atlantic High",null,588,588,588,147,63,394.8]
[null,"Boca Raton High",null,126,126,126,0,0,75.6]
[null,"Dreyfoos School of the Arts",null,0,0,0,0,0,0]
[null,"Forest Hill High",null,273,273,273,273,42,226.8]
[null,"Glades Central High",null,0,0,0,0,0,0]
[null,"J.I. Leonard High",null,672,672,147,147,0,327.6]
[null,"Jupiter High",null,0,0,0,0,0,0]
[null,"Lake Worth High",null,840,840,126,126,126,411.6]
[null,"Olympic Heights High",null,84,42,42,42,42,50.4]
[null,"Palm Beach Gardens High",null,63,63,84,84,84,75.6]
[null,"Palm Beach Lakes High",null,252,189,147,0,0,117.6]
[null,"Pahokee Mid/Sr.  (7-12)",null,21,21,21,21,21,21]
[null,"Royal Palm Beach High",null,0,0,0,0,0,0]
[null,"Santaluces High",null,651,651,357,273,273,441]
[null,"Spanish River High",null,210,210,210,105,63,159.6]
[null,"Suncoast High",null,42,42,42,42,42,42]
[null,"W.T. Dwyer High",null,105,105,105,0,0,63]
[null,"Wellington High",null,252,252,252,189,189,226.8]
["2f.","PALM BEACH Total students in relocatables by year",null,31143,29757,20424,11688,5471,19696.599999999988]
[null,"Total number of CO-FTE students projected by year",null,145351,148245,150446,152744,154591,150275.4]
[null,"Percent in relocatables by year",null,0.21,0.2,0.14,0.08,0.04,0.13]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1998,1998,1998,1998,1998,1998]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Mid low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Mid low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","1999-00 Year","Type of School (new schools only)  Others=0","1999-00","1999-00","1999-00","1999-00","1998 State Avg","1998 State Avg","1998 State Avg","1999 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"96-H, West Boca Raton Elem",1,12082990,970,125393,129.27,70,70,174,12456.69,7485,11173,16419]
[null,"97-K, E Palm Beach Area Elem",1,11787440,970,125393,129.27,70,70,174,12152,7485,11173,16419]
[null,"97-DD, Lantana Mid Replacement",1,20713455,1449,202761,139.93,70,70,174,14295,7485,11173,16419]
[null,"97-M, Boynton/Delray Area Elem",1,12092990,970,125393,129.27,70,70,174,12467,7485,11173,16419]
[null,"Boca Raton Elem Modernization",0,5596475,490,63342.3,129.27,0,0,0,11421.38,0,0,0]
[null,"Conniston Mid Modernization",0,17011051,1449,202758.57,139.93,0,0,0,11739.86,0,0,0]
[null,"Forest Hill High Modernization",0,32612960,1815,262721.25,144.75,0,0,0,17968.57,0,0,0]
[null,"Jupiter Elem Modernization",0,12059723,970,125391.9,129.27,0,0,0,12432.7,0,0,0]
[null,"Jupiter High Modernization",0,41927304,2633,381126.75,144.75,0,0,0,15923.78,0,0,0]
[null,"Middle/High Holding School",3,11290572,1666,233123.38,139.93,117,117,144,6777.05,16957,19232,21507]
[null,"Palm Beach Public Modernization",0,5333311,490,63342.3,129.27,0,0,0,10884.31,0,0,0]
[null,"South Olive Modernization",0,5832869,656,84801.12,129.27,0,0,0,8891.57,0,0,0]
[null,"Village Academy",1,6076000,490,63342.3,129.27,70,70,174,12400,7485,11173,16419]
["3a.","PALM BEACH Total 1999-00",null,194417140,15018,2058889.8699999999,137.09,null,null,null,12945.61]
[]
["3b.","2000-2001 Year","Type of School (new schools only)  Others=0","2000-01","2000-01","2000-01","2000-01","1998 State Avg","1998 State Avg","1998 State Avg","2000 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"New Elem School \"C\"",1,8000000,970,125393,129.27,70,107,174,8247.42,7485,11173,16419]
[null,"96-J, Western Communities Elem",1,12419880,970,125393,129.27,70,107,174,12804,7485,11173,16419]
[null,"96-L, Wellington Area Elem",1,12419880,970,125393,129.27,70,107,174,12804,7485,11173,16419]
[null,"98-EE, W Palm Beach Area Mid",2,20713455,1449,202761,139.93,88,90,180,14295,7226,13517,18473]
[null,"98-I, Boynton/Delray Area Elem",1,12419880,970,125393,129.27,70,107,174,12804,7485,11173,16419]
[null,"Atlantic High Modernization",0,34387986,1898,274735.5,144.75,0,0,0,18118.01,0,0,0]
[null,"Belvedere Elem Modernization",0,6850690,753,97340.31,129.27,0,0,0,9097.86,0,0,0]
[null,"U.B. Kinsey/Palmview Elem Modernization",0,4107376,796,102898.92,129.27,0,0,0,5160.02,0,0,0]
[null,"Greenacres Elem Modernization",0,5760546,647,83637.69,129.27,0,0,0,8903.47,0,0,0]
["3b","PALM BEACH Total 2000-01",null,117079693,9423,1262945.42,134.03,null,null,null,12424.89]
[]
["3c.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02","1998 State Avg","1998 State Avg","1998 State Avg","2001 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"96-D, Okeechobee Corridor Elem",1,12761320,970,125393,129.27,70,107,174,13156,7485,11173,16419]
[null,"98-GG, Boca Raton Area Mid",2,15094769,1111,155462.23,139.93,88,90,180,13586.65,7226,13517,18473]
[null,"John I Leonard High Modernization",0,27937515,2638,381850.5,144.75,0,0,0,10590.42,0,0,0]
[null,"Palm Springs Elem Modernization",0,5614224,716,92557.32,129.27,0,0,0,7841.09,0,0,0]
[null,"Future School Modernizations",0,54713138,null,null,null,0,0,0,null,0,0,0]
["3c","PALM BEACH Total 2001-02",null,116120966,5435,755263.05,543.22,158,197,354,45174.16,14711,24690,34892]
[]
["3d.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","1998 State Avg","1998 State Avg","1998 State Avg","2002 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"91-EEE, West Boynton High",3,3426433,1895,274301.25,144.75,117,130,144,1808.14,16957,19232,21507]
["3d.","PALM BEACH Total 2002-03",null,3426433,1895,274301.25,144.75,117,130,144,1808.14,16957,19232,21507]
[]
["3e.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1998 State Avg","1998 State Avg","1998 State Avg","2003 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"99-HH, Acreage Area Mid",2,1120000,1449,202761,139.93,88,90,180,772.95,7226,13517,18473]
["3e","PALM BEACH Total 2003-04",null,1120000,1449,202761,139.93,88,90,180,772.95,7226,13517,18473]
[]
["3f.","PALM BEACH 5-Year Total",null,432164232,33220,4554160.59]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millage projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,133310729,138566200,144710800,151974500,159323225,727885454]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,133310729,138566200,144710800,151974500,159323225,727885454,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,5057170,5636700,5940000,5940000,5940000,28513870,0.0391735675487204]
[null,"  less amount used to purchase other vehicles",null,515000,626300,660000,660000,660000,3121300,0.00428817471601789]
[null,"  less amount transferred to operating budget for maintenance/repair",null,33595885,28436608,27346516,26134994,24837296,140351299,0.192820584926815]
[null,"  less amount used for maintenance/repair",null,28911000,34150000,33513000,31989000,32937000,161500000,0.221875569998683]
[null,"  less amount used to purchase capital outlay equipment",null,17567351,20706000,19069000,14945000,11590000,83877351,0.115234272836561]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,18954592,18948062,18946017,18949362,18957330,94755363,0.130178948458558]
[null,"less amount used to purchase land",null,9000000,11000000,8000000,8000000,8000000,44000000]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,0,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,19709731,19062530,31236267,45356144,56401599,171766271,0.235979809812218,0.29]
[null,"P E C O New Construction",null,13503012,13117093,13213165,13519361,14124682,67477313,null,0.11]
[null,"C O & D S   Bond Proceeds",null,1400000,560000,300000,0,0,2260000,null,0]
[null,"C O & D S maximum potential bond proceeds",null,1000000,1000000,1000000,1000000,1000000,5000000,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,141000000,107405137,74981093,0,null,323386230,null,0.54]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Impact fees received",null,6000000,6000000,6000000,6000000,6000000,30000000,null,0.05]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,490805,0,0,0,0,490805,null,0]
["4.","PALM BEACH Total",null,183103548,147144760,126730525,65875505,77526281,600380619,0.9395509282975733,1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"91-EEE, West Boynton High",{"$nulls":4},426433,3000000,3426433]
[null,"96-A, Jupiter Area Elem",null,11197440,{"$nulls":4},11197440]
[null,"96-AA Lake Shore, New Midd",null,1500000,{"$nulls":4},1500000]
[null,"96-B, Acreage Area Elem",null,918832,{"$nulls":4},918832]
[null,"96-BB, Boynton/Delray Area Mid",null,null,1010690,null,null,null,1010690]
[null,"96-C, West Riviera Beach Elem",null,462367,{"$nulls":4},462367]
[null,"96-CC, Western Communities Mid",null,581786,{"$nulls":4},581786]
[null,"96-F, Greenacres/Liberty Park Elem",null,476310,{"$nulls":4},476310]
[null,"96-FF, Jupiter Area Mid",null,17678917,1500000,null,null,null,19178917]
[null,"96-H, West Boca Raton Elem",null,null,11477990,null,null,null,11477990]
[null,"96-J, Western Communities Elem",null,null,620000,11799880,null,null,12419880]
[null,"96-JJJ, Central WPB Area High",null,38928152,2489130,null,null,null,41417282]
[null,"97-K, E Palm Beach Area Elem",null,11787440,{"$nulls":4},11787440]
[null,"96-L, Wellington Area Elem",null,null,620000,11799880,null,null,12419880]
[null,"96-D, Okeechobee Corridor Elem",null,null,null,638000,12123320,null,12761320]
[null,"97-DD, Lantana Mid Replacement",null,null,18177780,1500000,null,null,19677780]
[null,"97-M, Boynton/Delray Area Elem",null,null,11487990,null,null,null,11487990]
[null,"98-EE, W Palm Beach Area Mid",null,null,1035675,18177780,1500000,null,20713455]
[null,"98-GG, Boca Raton Area Mid",null,null,null,763650,13031119,1300000,15094769]
[null,"98-I, Boynton/Delray Area Elem",null,null,620000,11799880,null,null,12419880]
[null,"99-HH, Acreage Area Mid",{"$nulls":5},1120000,1120000]
[null,"Addison Mizner Elem Remodeling",null,2290000,{"$nulls":4},2290000]
[null,"Atlantic High Athletic Facility Ph 2",null,300000,{"$nulls":4},300000]
[null,"Atlantic High Modernization",null,null,375519,1000000,30433368,2579099,34387986]
[null,"Boca Raton Elem Modernization",null,224195,5372280,null,null,null,5596475]
[null,"Boca Raton High Modernization",null,2000000,36854817,3208035,null,null,42062852]
[null,"Career Academies",null,1500000,5000000,3000000,null,null,9500000]
[null,"Conniston Mid Modernization",null,850553,14799614,1360884,null,null,17011051]
[null,"Future School Modernizations",null,null,1678505,32062365,4915293,42797776,81453939]
[null,"Forest Hill El, Addition",null,10910,8398551,null,null,null,8409461]
[null,"Forest Hill High Modernization",null,304518,1000000,28862470,2445972,null,32612960]
[null,"John I Leonard High Modernization",null,null,null,208109,1000000,26729406,27937515]
[null,"Jupiter Elem Modernization",null,605000,11454723,null,null,null,12059723]
[null,"Jupiter High Modernization",null,38782755,3144549,null,null,null,41927304]
[null,"Lake Park, Addition",null,8133562,{"$nulls":4},8133562]
[null,"Lake Worth High Additions Ph 2",null,11112402,{"$nulls":4},11112402]
[null,"Middle/High Holding School",null,500000,{"$nulls":4},500000]
[null,"North Grade Elem Replacement",null,480268,{"$nulls":4},480268]
[null,"Pahokee Elem Phase 2 OCR",null,6721500,{"$nulls":4},6721500]
[null,"Palm Beach Public Modernization",null,231883,5101428,null,null,null,5333311]
[null,"Palmetto, Remodeling",null,11617497,{"$nulls":4},11617497]
[null,"South Olive Modernization",null,357758,4925519,549592,null,null,5832869]
[null,"Village Academy",null,6076000,{"$nulls":4},6076000]
[null,"West Gate Elem Modernization",null,7473503,{"$nulls":4},7473503]
["5.","PALM BEACH Total",null,183103548,147144760,126730525,65875505,77526281,600380619]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Effort Index Grants",null,23700071,0,0,0,0,23700071]
[null,"SIT Program awards",null,88988,0,0,0,0,88988]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,23529550,null,23529550,null,0.04]
["6.","PALM BEACH Total",null,23789059,0,0,23529550,0,47318609]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"96-B, Acreage Area Elem",null,10278608,{"$nulls":4},10278608]
[null,"97-M, Boynton/Delray Area Elem",null,605000,{"$nulls":4},605000]
[null,"97-DD, Lantana Mid Replacement",null,1035675,{"$nulls":4},1035675]
[null,"Middle/High Holding School",null,10790572,{"$nulls":4},10790572]
[null,"Future School Modernizations",{"$nulls":4},23529550,null,23529550]
[null,"96-N, Pleasant City Area Elem",null,474204,{"$nulls":4},474204]
[null,"96-H, West Boca Raton Elem",null,605000,{"$nulls":4},605000]
["7.","PALM BEACH Total",null,23789059,0,0,23529550,0,47318609]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 1999."]
[]
[null,"SCHOOL BOARD OF ","PALM BEACH  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Linda Hines, Director, Planning & Real Estate",null,"561-434-8935",null,"evans_b1@popmail.firn.edu",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}