{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","99_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"99_5YrWkPlan","index":1,"n_rows":1188,"n_cols":25,"rows_kept":1188,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["SCHOOL DISTRICT FACILITIES WORK PROGRAM -- WORKSHEET"]
["PINELLAS  SCHOOL  DISTRICT"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":23},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to September 15, 1999, and all data accurate as of July 15, 1999.",{"$nulls":23},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"PINELLAS","Date: ==>","1999-08-31",null,"For fiscal years","  1999-2000 through 2003-2004"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-04 "]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"INFRASTRUCTURE(1999/00 subtotal = 6,000,000)"]
[null,"Various/TBD",null,null,6000000,6000000,6000000,6000000,24000000]
[null,null,"Dunedin Middle",490000,{"$nulls":4},490000]
[null,null,"Seminole Middle ",280000,{"$nulls":4},280000]
[null,null,"Lealman Elementary",450000,{"$nulls":4},450000]
[null,null,"Northeast High ",350000,{"$nulls":4},350000]
[null,null,"Osceola Middle",2100000,{"$nulls":4},2100000]
[null,null,"Tarpon Springs Elementary",200000,{"$nulls":4},200000]
[null,null,"Orange Grove Elementary",780000,{"$nulls":4},780000]
[null,"Overhead","Various",1350000,{"$nulls":4},1350000]
[null,"FIRE/HEALTH/SAFETY(1999/00 subtotal = 510,500)"]
[null,"Various/TBD",null,426100,510500,510500,510500,510500,2468100]
[null,"Fume Capture System","49TH St. Bus Compound",28000,{"$nulls":4},28000]
[null,"Replace Walkway Roof","South Ward Elementary",56400,{"$nulls":4},56400]
[null,"HVAC(1999/00 subtotal = 3,200,000)"]
[null,"Various/TBD",null,null,3200000,3200000,3200000,3200000,12800000]
[null,"Building 9,10, & 13","Tyrone Elementary",150000,{"$nulls":4},150000]
[null,"Bldg 3 - Renovation HVAC","Seminole Middle",300000,{"$nulls":4},300000]
[null,"Renovate HVAC - Facility","Starkey Elementary",2000000,{"$nulls":4},2000000]
[null,"Replace ductboard/ducting - Auditorium","Seminole High",450000,{"$nulls":4},450000]
[null,"Building 10 & 11","Southern Oak Elementary",150000,{"$nulls":4},150000]
[null,"HVAC Controls","Tyrone Middle",150000,{"$nulls":4},150000]
[null,"ROOFS/COVERED WALKWAYS (1999/00 subtotal = 763,764)"]
[null,"Various/TBD",null,null,763764,763764,763764,763764,3055056]
[null,"Re-roof Building 2","Coachman Fundamental",135000,{"$nulls":4},135000]
[null,"Gutter Building 2 & 3","Coachman Fundamental",23000,{"$nulls":4},23000]
[null,"Roof Access Ladder","Coachman Fundamental",1950,{"$nulls":4},1950]
[null,"Bus Loop Building 4 & 5","Pinellas Park Middle",100000,{"$nulls":4},100000]
[null,"Replace Bldg. 7 Wings 2 & 3","Pinellas Park Elementary",90000,{"$nulls":4},90000]
[null,"Replace Gutters Building 5","Largo Middle",14375,{"$nulls":4},14375]
[null,"Replace Gutters","Tarpon Springs Middle",95200,{"$nulls":4},95200]
[null,"Covered Walk","Mt. Vernon Elementary",14000,{"$nulls":4},14000]
[null,"Replace Covered Walk","North Shore Elementary",27000,{"$nulls":4},27000]
[null,"Replace Covered Walk","Tyrone Middle",188000,{"$nulls":4},188000]
[null,"Covered Walk Bldg. 6 & 1","High Point Elementary",25000,{"$nulls":4},25000]
[null,"Covered Walk","Lakeview Fundamental",39239,{"$nulls":4},39239]
[null,"Covered Walk","Largo Central Elementary",11000,{"$nulls":4},11000]
[null,"DRAINAGE (1999/00 subtotal = 201,000)"]
[null,"Various/TBD",null,null,201000,201000,201000,201000,804000]
[null,"Correct Flooding Bldg. 2,3,4,5,&6","Pinellas Park Elementary",38000,{"$nulls":4},38000]
[null,"Sea Wall","Boca Ciega High",40000,{"$nulls":4},40000]
[null,"Repair Drainage Bldg. 2 & 7","Westgate Elementary",30000,{"$nulls":4},30000]
[null,"Correct Flooding","Kings Highway Elem.",82000,{"$nulls":4},82000]
[null,"Provide Drainage","San Jose Elementary",11000,{"$nulls":4},11000]
[null,"PAVING (1999/00 subtotal = 713,660)"]
[null,"Various/TBD",null,null,713660,713660,713660,713660,2854640]
[null,"Overlay Parking Lots","Largo High",105000,{"$nulls":4},105000]
[null,"Overlay Parking Lots","Pinellas Central Elem.",29000,{"$nulls":4},29000]
[null,"Overlay","Curlew Creek Elem.",79660,{"$nulls":4},79660]
[null,"Overlay Parking & Bus Drive","Fitzgerald Middle",55000,{"$nulls":4},55000]
[null,"Grade & Pave Area","Tarpon Bus Compound",52000,{"$nulls":4},52000]
[null,"Overlay Parking","Cypress Woods Elem.",60000,{"$nulls":4},60000]
[null,"New Exit & Entrance","Riviera Middle",65000,{"$nulls":4},65000]
[null,"Resurface & Correct Drainage Track","Seminole High",55000,{"$nulls":4},55000]
[null,"Overlay Parking","Druid Complex",30000,{"$nulls":4},30000]
[null,"Overlay Parking","Highland Lakes Elem.",40000,{"$nulls":4},40000]
[null,"Overlay Track","Osceola Middle",45000,{"$nulls":4},45000]
[null,"Add Parking","Fairmount Park Elem.",58000,{"$nulls":4},58000]
[null,"Tennis Court ","East Lake High",16000,{"$nulls":4},16000]
[null,"Seal/Restrip Track","Pinellas Park High",12000,{"$nulls":4},12000]
[null,"Seal/Restrip Track","Largo High",12000,{"$nulls":4},12000]
[null,"PAINTING (1999/00 SUBTOTAL = 1,500,000)"]
[null,"Various/TBD",null,1500000,1500000,1500000,1500000,1500000,7500000]
[null,"SITES/GROUNDS (1999/00 subtotal = 269,500)",{"$nulls":6},0]
[null,"Various/TBD",null,null,269500,269500,269500,269500,1078000]
[null,"Payback 98/99","Lakewood High",48500,{"$nulls":4},48500]
[null,"Grade & Re-sod PE Field","Westgate Elementary",18000,{"$nulls":4},18000]
[null,"Replace Pool Deck","Northeast High",60000,{"$nulls":4},60000]
[null,"Loading Dock","Tarpon Elementary",18000,{"$nulls":4},18000]
[null,"Retaining Wall/Kindergarten","Rio Vista Elementary",25000,{"$nulls":4},25000]
[null,"Replace Play Courts","Belcher Elementary",30000,{"$nulls":4},30000]
[null,"Elevate K Pod Area ","Tarpon Elementary",12000,{"$nulls":4},12000]
[null,"Grade & Sod PE","Mt. Vernon Elementary",18000,{"$nulls":4},18000]
[null,"Replace Fence w/10 ft","Lealman Bus Compound",24000,{"$nulls":4},24000]
[null,"Replace Temporary Fence","Kings Highway Elementary",4000,{"$nulls":4},4000]
[null,"Sidewalk","Woodlawn Elementary",5500,{"$nulls":4},5500]
[null,"Play Ground Equipment","Leila Davis Elementary",6500,{"$nulls":4},6500]
[null,"FIRE ALARM /INTERCOM (1999/00 subtotal = 643,000)",{"$nulls":6},0]
[null,"Various/TBD",null,null,643000,643000,643000,643000,2572000]
[null,"Replace Fire Alarm","Azalea Elementary",85000,{"$nulls":4},85000]
[null,"Replace Fire Alarm","Rio Vista Elementary",110000,{"$nulls":4},110000]
[null,"Replace Fire Alarm","Largo High",110000,{"$nulls":4},110000]
[null,"Replace Fire Alarm","Osceola High",22882,{"$nulls":4},22882]
[null,"Replace Fire Alarm","Osceola High",92118,{"$nulls":4},92118]
[null,"Replace Fire Alarm","Skyview Elementary",78000,{"$nulls":4},78000]
[null,"Replace Intercom Console","Walsingham Elementary",65000,{"$nulls":4},65000]
[null,"Replace Intercom","Maximo Elementary",55000,{"$nulls":4},55000]
[null,"Replace Intercom Console","Sandy Lane Elementary",25000,{"$nulls":4},25000]
[null,"Various/TBD",null,null,380261,380261,380261,380261,1521044]
[null,"Ceiling & Lights/Payback","Largo Middle",100000,{"$nulls":4},100000]
[null,"Ceiling & Lights Bldg. 1","Kings Highway Elem.",100000,{"$nulls":4},100000]
[null,"New 2 X 2 Ceiling/Lights","Mildred Helms Elem.",42000,{"$nulls":4},42000]
[null,"Relight Gym","Osceola High",28500,{"$nulls":4},28500]
[null,"Replace Ceiling/Lights Bldg. 2","Mt. Vernon Elementary",15000,{"$nulls":4},15000]
[null,"Replace Ceilings/Lights","Lealman Elementary",30000,{"$nulls":4},30000]
[null,"Relight Classrooms","Safety Harbor Middle",24000,{"$nulls":4},24000]
[null,"Ceiling/Relight","PTEC South",40761,{"$nulls":4},40761]
[null,"FLOOR COVERING (1999/00subtotal = 1,287,200)",{"$nulls":6},0]
[null,"Various/TBD",null,null,1287200,1287200,1287200,1287200,5148800]
[null,"Replace Carpet","Sawgrass Elementary",90000,{"$nulls":4},90000]
[null,"Replace Carpet Bldg.4,5,7,8 & 9","Cypress Woods Elem.",140000,{"$nulls":4},140000]
[null,"Replace Carpet Bldg.1,2 & 4","Bay Vista Elementary",100000,{"$nulls":4},100000]
[null,"Replace Carpet ","Bay Vista Elementary",7000,{"$nulls":4},7000]
[null,"Replace Carpet","Rawlings Elementary",185000,{"$nulls":4},185000]
[null,"Quarry Tile","Ponce de Leon Elem.",53000,{"$nulls":4},53000]
[null,"Administration Building","Clearwater High",75000,{"$nulls":4},75000]
[null,"Replace Carpet, 705-713, Cafeteria Building","Lakewood High",89200,{"$nulls":4},89200]
[null,"Replace Carpet","Southern Oak Elem.",160000,{"$nulls":4},160000]
[null,"Replace Carpet Bldg. 2,3,4 & 5","Safety Harbor Elem.",50000,{"$nulls":4},50000]
[null,"Replace Carpet","Hamilton Disston",160000,{"$nulls":4},160000]
[null,"Replace Carpet Bldg. 1, 2 & 4","Tyrone Elementary",64200,{"$nulls":4},64200]
[null,"Floor Tile Cafeteria","Boca Ciega High",17800,{"$nulls":4},17800]
[null,"Replace Carpet Media","Azalea Elementary",32000,{"$nulls":4},32000]
[null,"Replace Carpet Administration","Dixie Hollins High",30000,{"$nulls":4},30000]
[null,"Floor Tile Cafeteria","Starkey Elementary",8000,{"$nulls":4},8000]
[null,"Replace Tile Restrooms","Lakeview Elementary",6000,{"$nulls":4},6000]
[null,"Replace Tile Cafeteria","Lealman Elementary",6000,{"$nulls":4},6000]
[null,"Replace Tile Cafeteria","High Point Elementary",6000,{"$nulls":4},6000]
[null,"Replace Tile Cafeteria","Belleair Elementary",8000,{"$nulls":4},8000]
[null,"PLUMBING (1999/00 subtotal = 579,000)",{"$nulls":6},0]
[null,"Various/TBD",null,null,579000,579000,579000,579000,2316000]
[null,"Repipe Domestic Water","Northwest Elementary",350000,{"$nulls":4},350000]
[null,"Lift Station","Cross Bayou Elementary",80000,{"$nulls":4},80000]
[null,"Standardize Plumbing","Largo Central Elem.",10000,{"$nulls":4},10000]
[null,"Sprinkler System","High Point Elementary",90000,{"$nulls":4},90000]
[null,"Repipe Water Main","PTEC, St. Petersburg",42000,{"$nulls":4},42000]
[null,"Sink & Drain","Countryside High",7000,{"$nulls":4},7000]
[null,"RESTROOM RENOVATION (1999/00 subtotal = 210,000)",{"$nulls":6},0]
[null,"Various/TBD",null,null,210000,210000,210000,210000,840000]
[null,"Repipe, Remodel Bldg. 1,2,3 & 4","Seventy-Fourth St. Elem.",160000,{"$nulls":4},160000]
[null,"Restroom Renovation","Tyrone Elementary",50000,{"$nulls":4},50000]
[null,"EPA (1999/00 subtotal = 1,300,000)",{"$nulls":6},0]
[null,"Various/TBD (to meet EPA requirements)",null,1300000,1300000,1300000,1300000,1300000,6500000]
[null,"HANDICAP ACCESS (1999/00 subtotal = 6,000)",{"$nulls":6},0]
[null,"Electric Door Opener","Fitzgerald Middle",6000,6000,6000,6000,6000,30000]
[null,"GYM/STAGE FLOOR (1999/00 subtotal 77,200)",{"$nulls":6},0]
[null,"Various/TBD",null,null,77200,77200,77200,77200,308800]
[null,"Stage","Clearview Elementary",2200,{"$nulls":4},2200]
[null,"Gym Floor","Pinellas Park Middle",21000,{"$nulls":4},21000]
[null,"Gym Floor","Dixie Hollins High",15000,{"$nulls":4},15000]
[null,"Stage","Countryside High",24000,{"$nulls":4},24000]
[null,"Gym","Largo High",15000,{"$nulls":4},15000]
[null,"SPECTATOR SEATING (1999/00 subtotal = 98,100)",{"$nulls":6},0]
[null,"Various/TBD",null,null,98100,98100,98100,98100,392400]
[null,"Refurbish Gym Bleachers","St. Petersburg High",51100,{"$nulls":4},51100]
[null,"Replace Softball Bleachers","Seminole High",35000,{"$nulls":4},35000]
[null,"Bleachers Softball","Boca Ciega High",12000,{"$nulls":4},12000]
[null,"WINDOW REPLACEMENT (1999/00 subtotal = 960,000)",{"$nulls":6},0]
[null,"Various/TBD",null,null,960000,960000,960000,960000,3840000]
[null,"Replace Windows","Osceola Middle",425000,{"$nulls":4},425000]
[null,"Replace Windows","Tarpon Springs Middle",355000,{"$nulls":4},355000]
[null,"Replace Windows","Anona Elementary",140000,{"$nulls":4},140000]
[null,"Evaluation Exterior","Palm Harbor Middle",40000,{"$nulls":4},40000]
[null,"ELECTRICAL UPGRADE (1999/00 subtotal = 382,800)",{"$nulls":6},0]
[null,"Various/TBD",null,null,382800,382800,382800,382800,1531200]
[null,"Exit Signs","Countywide",20000,{"$nulls":4},20000]
[null,"Parking Lot Lights","Rio Vista Elementary",46800,{"$nulls":4},46800]
[null,"Panel Board","Fitzgerald Middle",8000,{"$nulls":4},8000]
[null,"Replace Panel Boards","Azalea Elementary",50000,{"$nulls":4},50000]
[null,"Parking Lot Lights","High Point Elementary",42000,{"$nulls":4},42000]
[null,"Replace Pole Lights","Pinellas Park Sr",50000,{"$nulls":4},50000]
[null,"Auditorium Lights/Sound Board","Osceola High",75000,{"$nulls":4},75000]
[null,"Re-light Gym","Coachman Fundamental",26000,{"$nulls":4},26000]
[null,"Replace Pole Lights","Eisenhower Elementary",50000,{"$nulls":4},50000]
[null,"Walkway Lights","Shore Acres Elementary",15000,{"$nulls":4},15000]
[null,"CASEWORK (1999/00 subtotal = 885,015)",{"$nulls":6},0]
[null,"Various/TBD",null,null,885015,885015,885015,885015,3540060]
[null,"New Cabinets Building 1","Paul B. Stephens",15000,{"$nulls":4},15000]
[null,"Cabinet Replacement","Pinellas Park Middle",72600,{"$nulls":4},72600]
[null,"Replace Markerboards, Cabinets","Pinellas Park Elementary",135000,{"$nulls":4},135000]
[null,"Replace Cabinets","North Shore Elementary",92500,{"$nulls":4},92500]
[null,"Cabinets/Replace Logo","Countryside High",39000,{"$nulls":4},39000]
[null,"Replace Markerboards","Maderia Beach Middle",72500,{"$nulls":4},72500]
[null,"Replace Markerboards, Cabinets","Northwest Elementary",176000,{"$nulls":4},176000]
[null,"Replace Markerboards","Ponce de Leon Elem. ",50000,{"$nulls":4},50000]
[null,"Convert Shop to Classroom","Tarpon Springs Middle",64000,{"$nulls":4},64000]
[null,"Replace Markerboards","Seventy-Fourth St. Elem.",36320,{"$nulls":4},36320]
[null,"Replace Cabinets","Curtis Fundamental ",132095,{"$nulls":4},132095]
[null,"Portable repair","County wide",200000,200000,200000,200000,200000,1000000]
[null,"STUDENT LOCKERS (1999/00 subtotal = 154,500)",{"$nulls":6},0]
[null,"Various/TBD",null,null,154500,154500,154500,154500,618000]
[null,"Lockers/Stadium/Visitors","Dunedin High",4500,{"$nulls":4},4500]
[null,"Student Locker","Seminole Middle",150000,{"$nulls":4},150000]
[null,"FLAMMABLE STORAGE BLDGS. (1999/00 subtotal = 38,500)",{"$nulls":6},0]
[null,"Various/TBD",null,null,38500,38500,38500,38500,154000]
[null,"Construct Storage Area ","Northwest Elementary ",38500,{"$nulls":4},38500]
[null,"OVERHEAD COSTS ","Various",640000,640000,640000,640000,640000,3200000]
[null,"INFLATION ADJUSTMENT (3% per year)",null,null,630000,1260000,1890000,2520000,6300000]
["1.","PINELLAS Total",null,21000000,21630000,22260000,22890000,23520000,111300000]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Azalea Md, Construction, Renovate, Remodel",null,5450700,966100,811900,null,null,7228700]
[null,"Bay Point Md, Planning, Construction, Renovate, Remodel, FHS, ADA",null,2583607,338668,null,null,null,2922275]
[null,"Bay Point Elem, Planning, Construction, Renovate, Remodel, FHS, ADA",null,5167213,672282,null,null,null,5839495]
[null,"Dunedin Sr, Construction, Renovate, Remodel, Sitework, Drainage, FHS, ADA",null,700000,791300,600000,null,null,2091300]
[null,"Northeast Sr, Construction, Renovate, Remodel, Sitework, Drainage, FHS, ADA ",null,820000,757000,700000,null,null,2277000]
[null,"Tarpon Springs Sr, Construct, Renovate, Remodel, FHS, ADA, Site, Demolition ",null,675600,700000,null,null,null,1375600]
[null,"New Alternative Sr, Planning",null,800000,1200000,8000000,5000000,null,15000000]
[null,"Academie Da Vinci (Charter School SIT)",null,346000,{"$nulls":4},346000]
[null,"Elementary Stu Stations, Planning, New Construction, Renovation, Remodeling",null,11800000,10500000,10000000,6335000,1055750,39690750]
[null,"Middle School Stu Stations, Planning, New Construction, Renovation, Reml",null,2700000,9750000,6615000,1135000,null,20200000]
[null,"Gibbs Sr, Construct, Renovate, Remodel ",null,1500000,2600000,2600000,11050000,5950600,23700600]
[null,"PTEC St Pete (Gibbs High/PATA), Renovation",null,400000,400000,null,null,null,800000]
[null,"Clearwater Sr, Planning, Additions, Renovate, Remodel",null,694000,{"$nulls":4},694000]
[null,"Lealman Discovery, Scope to be defined",null,4500000,{"$nulls":4},4500000]
[null,"Pasadena Fund, Planning, Construction, Remodel, Renovate, FHS, ADA",null,436090,{"$nulls":4},436090]
[null,"Nina Harris ESE, Planning, New Construction, Remodeling",null,7700000,2328000,750000,null,null,10778000]
[null,"Stephens ESE, Planning, New Construction, Remodeling",null,4490320,5495730,null,null,null,9986050]
[null,"Meadowlawn Md, Planning, New Construction, Remodeling",null,9000000,9089640,1673500,1396700,null,21159840]
[null,"Largo Md, Planning, New Construction, Remodeling",null,600000,6759473,466200,null,null,7825673]
[null,"Sanders ESE, Planning, New Construction, Remodeling",null,600000,7496510,1603490,null,null,9700000]
[null,"Maximo Elem, Planning, New Construction, Remodeling",null,800000,8389163,693200,null,null,9882363]
[null,"Dunedin Highland Middle, Planning, New Construction, Remodeling, Renovation",null,800000,7873085,6693607,887800,478100,16732592]
[null,"Melrose Elem, Planning, New Construction, Remodeling, Renovation",null,350000,4703405,null,null,null,5053405]
[null,"Lake St George Elem, Planning, New Construction, Remodeling",null,null,412000,3800606,null,null,4212606]
[null,"Shore Acres Elem, Planning, New Construction, Remodeling",null,null,618000,6769402,283150,null,7670552]
[null,"Sunset Hills Elem, Planning, New Construction, Remodeling, Renovations",null,null,412000,5502155,246700,null,6160855]
[null,"Eisenhower Elem, Planning, New Construction, Remodeling",null,null,null,3057177,null,null,3057177]
[null,"Cypress Woods, Planning, New Construction, Remodeling, Renovation",null,null,null,2915855,null,null,2915855]
[null,"Dunedin Elem, Planning, New Construction, Remodeling",null,null,463500,5967293,null,null,6430793]
[null,"San Jose Elem, Planning, New Construction, Remodeling, Renovations",null,null,721000,7621579,780200,null,9122779]
[null,"Skyview Elem, , Planning, New Construction, Remodeling, Renovations",null,null,null,636000,8256900,810000,9702900]
[null,"Oak Grove Middle, Planning, New Construction, Remodeling",null,null,null,636000,7506386,615200,8757586]
[null,"Tarpon Springs Fund Elem, Planning, New Construction, Remodeling",null,null,null,2134913,null,null,2134913]
[null,"Druid Complex, Planning, New Construction, Renovations",null,null,null,277223,null,null,277223]
[null,"Safety Harbor Middle, Planning, New Construction, Remodeling, Renovations",null,null,null,848000,11400000,8458260,20706260]
[null,"Starkey Elem, Planning, New Construction, Remodeling",null,null,null,530000,3636982,null,4166982]
[null,"Belleair Elem, Planning, New Construction, Renovation",null,null,null,477000,3437617,null,3914617]
[null,"Lynch Elem, Planning, New Construction, Remodeling",null,null,null,424000,4880827,467600,5772427]
[null,"Palm Harbor Middle, Planning, New Construction, Remodeling",null,null,null,318000,3309147,181200,3808347]
[null,"Rio Vista Elem, Planning, New Construction, Remodeling",null,null,null,371000,3885516,426200,4682716]
[null,"Belcher Elem, Planning, New Construction, Remodeling",null,null,null,477000,5394108,469050,6340158]
[null,"Sutherland Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":4},545000,3005756,3550756]
[null,"Tarpon Springs Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":4},545000,5678390,6223390]
[null,"Curlew Creek Elem, Planning, New Construction, Remodeling",{"$nulls":4},381500,3080690,3462190]
[null,"Davis Elem, Planning, New Construction, Remodeling",{"$nulls":5},7149883,7149883]
[null,"Osceola Middle, Planning, New Construction, Remodeling",{"$nulls":5},3281955,3281955]
[null,"Blanton Elem, Planning, New Construction, Remodeling",{"$nulls":5},3991654,3991654]
[null,"Countryside High, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},11878198,11878198]
[null,"Hunsinger ESE Center, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},2842088,2842088]
[null,"Bauder Elem, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},6821036,6821036]
[null,"Tyrone Elem, Remodel, FHS/ADA, Maintenance, New Construction",{"$nulls":5},3891232,3891232]
[null,"Orange Grove Elem, New Constr, Remodel, Site",{"$nulls":5},3151129,3151129]
[null,"Tyrone Middle, New Constr, Remodeling, FHS/ADA",{"$nulls":5},5008362,5008362]
[null,"Palm Harbor Univ High, Planning, New Constr, Remodeling, FHS/ADA, Site",{"$nulls":5},6075326,6075326]
[null,"Pinellas Central Elem, Planning, New Construction, Remodeling",{"$nulls":5},2782166,2782166]
[null,"Cross Bayou Elem, New Constr, Remodel",{"$nulls":5},2773771,2773771]
[null,"Palm Harbor Elem, Planning, New Construction, Remodeling",{"$nulls":5},3413266,3413266]
[null,"Boca Ciega High, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},15868463,15868463]
[null,"Kennedy Middle, Planning, New Construction, Remodeling, Renovations ",{"$nulls":5},8488447,8488447]
[null,"Mount Vernon Elem, Planning New Construction, Remodeling, Renovations",{"$nulls":5},3128730,3128730]
[null,"Westgate Elem, New Construction, Remodeling, FHS/ADA",{"$nulls":5},2034865,2034865]
[null,"Southern Oak Elem, Remodel, FHS/ADA, Maintenance, New Construction",{"$nulls":5},1569548,1569548]
[null,"Pinellas Park High, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},5861978,5861978]
[null,"Kings Highway Elem, New Constr, Remodel, Maintenance",{"$nulls":5},4547147,4547147]
[null,"Seventy-Forth Street Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},3660667,3660667]
[null,"Campbell Park Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},2511064,2511064]
[null,"Garrison-Jones Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},1462612,1462612]
[null,"Seminole Middle, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},11262747,11262747]
[null,"Clearview Elem, Site, Renovate, Remodel, etc.",{"$nulls":5},1915882,1915882]
[null,"Azalea Elem, New Constr, Remodeling, etc.",{"$nulls":5},1529094,1529094]
[null,"Curtis Fund Elem, New Constr, Maintenance",{"$nulls":5},2556682,2556682]
[null,"Madeira Beach Elem, Plan, New Constr, Remodel, Site",{"$nulls":5},2732094,2732094]
[null,"Madeira Beach Middle, New Constr, Remodel, Site, etc.",{"$nulls":5},2605934,2605934]
[null,"Osceola High, Renovate, Remodel, FHS/ADA, etc.",{"$nulls":5},5570995,5570995]
[null,"Carwise Middle, New Constr, Maintenance",{"$nulls":5},1368944,1368944]
[null,"Oldsmar Elem, New Constr, Maintenance",{"$nulls":5},1464596,1464596]
[null,"Sawgrass Lakes Elem, New Cons, Remdl, FHS/ADA, etc",{"$nulls":5},894951,894951]
[null,"Disston SED Center, New Constr, Site, Maintenance",{"$nulls":5},3398642,3398642]
[null,"Fairmount Park Elem, New Constr, Remodel, etc.",{"$nulls":5},3294911,3294911]
[null,"Tarpon Springs Middle, New Constr, Site, Maintenance",{"$nulls":5},3263030,3263030]
[null,"Bardmoor Elem, New Constr, Remodel, etc.",{"$nulls":5},7733902,7733902]
[null,"Ponce De Leon Elem, New Constr, Remdl, FHS/ADA, etc.",{"$nulls":5},5527492,5527492]
[null,"High Point Elem, Remodel, FHS/ADA, Maintenance",{"$nulls":5},4219323,4219323]
[null,"Coachman Fund Middle, New Constr, Remodel, Site, etc.",{"$nulls":5},2544856,2544856]
[null,"Pinellas Park Elem, Site, Maintenance",{"$nulls":5},948000,948000]
[null,"Mildred Helms Elem, New Constr, Remodel, Site, etc.",{"$nulls":5},3398806,3398806]
[null,"Walter Pownall Service Center, Remodel, Site, FHS/ADA, Maint.",{"$nulls":5},2211100,2211100]
[null,"Woodlawn Elem, Site, Maintenance",{"$nulls":5},1898500,1898500]
[null,"Northwest Elem, Remodel, FHS/ADA, Maintenance",{"$nulls":5},859227,859227]
[null,"Fuguitt Elem, Site, New Constr, Remodel, etc.",{"$nulls":5},1136068,1136068]
[null,"Safety Harbor Elem, New Cons, Renovate, Remdl, etc.",{"$nulls":5},2358532,2358532]
[null,"Gulf Beaches Elem, New Constr, Remodel, Site, etc.",{"$nulls":5},1288107,1288107]
[null,"Clearwater Discovery, New Constr, Maintenance",{"$nulls":5},854600,854600]
[null,"Lealman Elem, Remodel, FHS/ADA, Maintenance",{"$nulls":5},1862005,1862005]
[null,"Seminole Vo Ed, New Const, Renov, Remodel, etc.",{"$nulls":5},7653793,7653793]
[null,"Highland Lakes Elem, New Constr, Maintenance",{"$nulls":5},943855,943855]
[null,"Lakewood High, New Const, Remodel, Maint., etc.",{"$nulls":5},3521506,3521506]
[null,"Lakeview Fund Elem, Renovate, FHS/ADA, Maintenance",{"$nulls":5},2912198,2912198]
[null,"Cleveland Street Bus Compound, Remodel, Maintenance, FHS/ADA",{"$nulls":5},1439444,1439444]
[null,"Lealman Bus Compound, Site, Maintenance",{"$nulls":5},255625,255625]
[null,"Safety Harbor IBIS Center, Renovate, Site, FHS/ADA, Maint.",{"$nulls":5},2060806,2060806]
[null,"Forty-Ninth Street Bus Compound, Remodel, Maintenance, FHS/ADA",{"$nulls":5},1520611,1520611]
[null,"Administration, Remodeling, etc.",{"$nulls":5},13137,13137]
[null,"PTEC St Pete, Site, Maintenance",{"$nulls":5},782800,782800]
[null,"Bay Vista Elem, Remodeling, Maintenance, etc.",{"$nulls":5},2637360,2637360]
["2 .","PINELLAS Total",null,62913530,83436856,83970100,80293533,245310538,555924557]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1998-99 FISH Satisfactory","Actual 1998-99","Actual 1998-99","Actual 1998-99","New Stu Capacity to","Projected 2003-04","Projected 2003-04"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Anona Elem",471,471,443,0.94,-69,401,1]
[null,"Azalea Elem",978,978,751,0.77,-256,692,0.96]
[null,"Bardmoor Elem",752,752,773,1.03,70,761,0.93]
[null,"Bauder Elem",941,941,955,1.01,11,945,0.99]
[null,"Bay Point Elem",825,825,749,0.91,78,632,0.7]
[null,"Bay Vista Fund Elem",669,669,456,0.68,-126,642,1.18]
[null,"Bear Creek Elem",661,661,523,0.79,318,659,0.67]
[null,"Belcher Elem",651,651,586,0.9,-135,482,0.93]
[null,"Belleair Elem",551,551,440,0.8,-167,396,1.03]
[null,"Blanton Elem",1012,1012,811,0.8,-13,799,0.8]
[null,"Brooker Creek Elem",781,781,614,0.79,0,740,0.95]
[null,"Campbell Park Elem",516,516,441,0.85,-105,458,1.11]
[null,"Clearview Ave Elem",646,646,635,0.98,1,630,0.97]
[null,"Cross Bayou Elem",856,856,703,0.82,13,724,0.83]
[null,"Curlew Creek Elem",893,893,815,0.91,0,781,0.87]
[null,"Curtis Fund Elem",384,384,411,1.07,7,413,1.06]
[null,"Cypress Woods Elem",800,800,735,0.92,24,783,0.95]
[null,"Dunedin Elem",769,769,688,0.89,-20,711,0.95]
[null,"Eisenhower Elem",718,718,718,1,25,665,0.9]
[null,"Fairmount Park Elem",466,466,470,1.01,23,427,0.87]
[null,"Forest Lakes Elem",848,848,761,0.9,0,828,0.98]
[null,"Frontier Elem",1037,1037,873,0.84,0,795,0.77]
[null,"Fuguitt Elem",871,871,791,0.91,-126,700,0.94]
[null,"Garrison-Jones Elem",826,826,775,0.94,-20,848,1.05]
[null,"Gulf Beaches Elem",481,481,384,0.8,-116,373,1.02]
[null,"Gulfport Elem",537,537,408,0.76,5,465,0.86]
[null,"High Point Elem",660,660,478,0.72,-99,551,0.98]
[null,"Highland Lakes Elem",727,727,660,0.91,75,743,0.93]
[null,"John M Sexton Elem",868,868,792,0.91,0,783,0.9]
[null,"Kings Highway Elem",685,685,573,0.84,-197,537,1.1]
[null,"Lake Saint George Elem",703,703,734,1.04,95,767,0.96]
[null,"Lakeview Fund Elem",293,293,292,1,0,291,0.99]
[null,"Lakewood Elem",749,749,382,0.51,772,724,0.48]
[null,"Largo Central Elem",521,521,455,0.87,-28,450,0.91]
[null,"Lealman Avenue Elem",776,776,655,0.84,-53,683,0.94]
[null,"Leila Davis Elem",765,765,628,0.82,34,736,0.92]
[null,"Lynch Elem",798,798,754,0.94,-74,693,0.96]
[null,"Madeira Beach Elem",714,714,530,0.74,-100,491,0.8]
[null,"Marjorie Kinnan Rawlings Elem",938,938,824,0.88,0,766,0.82]
[null,"Maximo Elem",861,861,658,0.76,-189,658,0.98]
[null,"McMullen-Booth Elem ",820,820,656,0.8,0,769,0.94]
[null,"Melrose Elem",705,705,630,0.89,-15,626,0.91]
[null,"Mildred Helms Elem",734,734,629,0.86,-148,631,1.08]
[null,"Mount Vernon Elem",513,513,572,1.12,31,550,1.01]
[null,"North Shore Elem",582,582,600,1.03,200,623,0.8]
[null,"North Ward Elem",0,0,267,null,0,248]
[null,"Northwest Elem",794,794,797,1,0,735,0.93]
[null,"Norwood Elem",168,null,null,null,0,0]
[null,"Oakhurst Elem",771,771,694,0.9,-65,718,1.02]
[null,"Oldsmar Elem",774,774,706,0.91,10,697,0.89]
[null,"Orange Grove Elem",403,403,407,1.01,-5,339,0.85]
[null,"Ozona Elem",823,823,782,0.95,0,700,0.85]
[null,"Palm Harbor Elem",475,475,487,1.03,20,541,1.09]
[null,"Pasadena Fund Elem",590,590,485,0.82,48,485,0.76]
[null,"Perkins Elem",824,824,540,0.66,195,561,0.55]
[null,"Pinellas Central Elem",837,837,872,1.04,174,771,0.76]
[null,"Pinellas Park Elem",887,887,640,0.72,-318,613,1.08]
[null,"Plumb Elem",808,808,848,1.05,0,804,1]
[null,"Ponce De Leon Elem",776,776,661,0.85,-218,580,1.04]
[null,"Ridgecrest Elem",809,809,715,0.88,-165,663,1.03]
[null,"Rio Vista Elem",668,668,659,0.99,115,593,0.76]
[null,"Safety Harbor Elem",595,595,562,0.94,-89,563,1.11]
[null,"Samuel L Robinson Challenge",25,25,219,8.76,0,188,7.52]
[null,"San Jose Elem",757,757,715,0.94,-70,682,0.99]
[null,"Sandy Lane Elem",686,686,771,1.12,-4,758,1.11]
[null,"Sawgrass Lake Elem",898,898,762,0.85,2,771,0.86]
[null,"Seminole Elem",960,960,813,0.85,-80,844,0.96]
[null,"Seventy-Fourth Street Elem",849,849,668,0.79,-244,619,1.02]
[null,"Shore Acres Elem",712,712,692,0.97,27,719,0.97]
[null,"Skycrest Elem",882,882,663,0.75,-206,614,0.91]
[null,"Skyview Elem",806,806,804,1,-18,727,0.92]
[null,"South Ward Elem",0,0,350,null,0,294]
[null,"Southern Oak Elem",780,780,672,0.86,-94,634,0.92]
[null,"Starkey Elem",784,784,712,0.91,-196,692,1.18]
[null,"Sunset Hills Elem",600,600,522,0.87,-12,474,0.81]
[null,"Sutherland Elem",741,741,815,1.1,84,774,0.94]
[null,"Tarpon Springs Elem",822,822,637,0.77,-221,596,0.99]
[null,"Tarpon Springs Fund Elem",273,273,291,1.07,36,255,0.83]
[null,"Tyrone Elem",995,995,669,0.67,-402,657,1.11]
[null,"Walsingham Elem",725,725,783,1.08,53,718,0.92]
[null,"Westgate Elem",744,744,876,1.18,66,787,0.97]
[null,"Woodlawn Elem",738,738,771,1.04,22,774,1.02]
[null,"Azalea Middle",1145,1030,930,0.9,635,1072,0.64]
[null,"Bay Point Middle",1474,1326,1378,1.04,-6,1381,1.05]
[null,"Carwise Middle",1626,1463,1382,0.94,0,1475,1.01]
[null,"Clearwater Disc Middle",700,630,391,0.62,-144,429,0.88]
[null,"Coachman Fund Middle",595,535,475,0.89,69,459,0.76]
[null,"Dunedin Highland Middle",1081,972,1134,1.17,355,1286,0.97]
[null,"John Hopkins Middle",1916,1724,1545,0.9,1612,1512,0.45]
[null,"Kennedy Middle",1101,990,1019,1.03,152,1029,0.9]
[null,"Largo Middle",1432,1288,1305,1.01,162,1430,0.99]
[null,"Lealman Disc Middle",163,146,414,2.84,0,459,3.14]
[null,"Madeira Beach Middle",1177,1059,1028,0.97,305,1231,0.9]
[null,"Meadowlawn Middle",1280,1152,1173,1.02,204,1206,0.89]
[null,"Morgan Fitzgerald Middle",1665,1498,1051,0.7,-162,1309,0.98]
[null,"North Ward IBIS",0,0,52,null,0,41]
[null,"Oak Grove Middle",1150,1035,1116,1.08,298,1282,0.96]
[null,"Osceola Middle",1657,1491,1149,0.77,-12,1267,0.86]
[null,"Palm Harbor Middle",1648,1483,1327,0.89,30,1511,1]
[null,"Pinellas Park Middle",1592,1432,1148,0.8,59,1232,0.83]
[null,"Riviera Middle",1479,1331,1141,0.86,-23,1256,0.96]
[null,"Safety Harbor IBIS",213,213,51,0.24,0,41,0.19]
[null,"Safety Harbor Middle",1706,1535,1461,0.95,101,1684,1.03]
[null,"Seminole Middle",1416,1274,1229,0.96,292,1416,0.9]
[null,"Southside Fund Middle",56,50,664,13.28,0,663,13.26]
[null,"Tarpon Springs Middle",1439,1295,1259,0.97,292,1553,0.98]
[null,"Tyrone Middle",1161,1044,1102,1.06,202,1205,0.97]
[null,"Boca Ciega High",2162,2053,1961,0.96,422,2065,0.83]
[null,"Clearwater High",2529,2402,1797,0.75,-89,1912,0.83]
[null,"Countryside High",2440,2318,1737,0.75,-214,1920,0.91]
[null,"Dixie Hollins High",2311,2195,1587,0.72,168,1839,0.78]
[null,"Dunedin High",1623,1541,1640,1.06,479,1848,0.91]
[null,"East Lake High",2396,2276,2021,0.89,0,2117,0.93]
[null,"Gibbs High",1904,1808,1652,0.91,20,1789,0.98]
[null,"Lakewood High",1755,1667,1580,0.95,-20,1630,0.99]
[null,"Largo High",2254,2141,1728,0.81,-197,1900,0.98]
[null,"Northeast High",2703,2567,1862,0.73,-647,1941,1.01]
[null,"Osceola High",1712,1626,1226,0.75,-67,1536,0.99]
[null,"Palm Harbor Univ High",2003,1902,1318,0.69,440,2036,0.87]
[null,"Pinellas Park High",2267,2153,2016,0.94,104,2196,0.97]
[null,"Seminole High",2224,2112,1779,0.84,-107,1987,0.99]
[null,"St Petersburg High",2096,1991,2035,1.02,0,2117,1.06]
[null,"Tarpon Springs High",2006,1905,1497,0.79,87,1851,0.93]
[null,"Calvin Hunsinger Exceptional",233,233,224,0.96,233,273,0.59]
[null,"Disston Gifted Program",27,27,36,1.33,-21,null,0]
[null,"Hamilton Disston SED Center",232,232,202,0.87,194,232,0.54]
[null,"Nina Harris Exceptional",328,328,294,0.9,80,319,0.78]
[null,"Oldsmar Community",158]
[null,"Paul B Stephens Exceptional",278,278,230,0.83,71,238,0.68]
[null,"Pinellas Vo-Tech",967,967,1804,1.87,134,184,0.17]
[null,"Richard Sanders School",252,252,208,0.83,84,198,0.59]
[null,"Seminole Vocational Center",250,250,226,0.9,91,81,0.24]
[null,"St Petersburg Challenge",295,295,180,0.61,0,163,0.55]
[null,"St Petersburg Vo-Tech",1359,1359,1324,0.97,0,193,0.14]
[null,"Tomlinson Adult",406,406,370,0.91,0,0,0]
["2a.","PINELLAS Total",125173,120243,108996,0.91,3837,111004,0.89]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"Two (potential of 3) new Elementary Schools (2587 Stu Sta), in the vicinity of South St Petersburg, to accommodate unitary status.  New Middle School (1000 Stu Sta), in the vicinity of South St Petersburg"]
[null," to accommodate unitary status.  New Alternative High School \"Penny for Pinellas\", in the vicinity of Eastern Largo, to participate in a cooperative venture with Pinellas County and other local agencies."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1998-99","Owner","Student Stations","as classroom space","in 2003-04","units by 2003-04","Column \"C\""]
[null,"Anona Elem",3,"PCSB",81,0,3,0,23]
[null,"Azalea Elem",2,"PCSB",48,0,3,-1,8]
[null,"Azalea Elem",1,"FED",13,0,1,0,8]
[null,"Azalea Middle",1,"PCSB",28,0,0,1,23]
[null,"Bardmoor Elem",1,"FED",13,0,1,0,9]
[null,"Bauder Elem",5,"PCSB",136,0,5,0,66]
[null,"Bauder Elem",2,"FED",26,0,2,0,15]
[null,"Bay Point Elem",13,"PCSB",364,0,5,8,103]
[null,"Bay Point Middle",1,"PCSB",28,0,0,1,28]
[null,"Bay Point Middle",1,"FED",13,0,0,1,9]
[null,"Bear Creek Elem",11,"PCSB",271,0,0,11,85]
[null,"Bear Creek Elem",1,"FED (C)",0,0,0,1,9]
[null,"Belcher Elem",2,"PCSB",54,0,2,0,15]
[null,"Belleair Elem",1,"FED (C)",0,0,1,0,24]
[null,"Blanton Elem",6,"FED (C)",30,0,6,57,51]
[null,"Blanton Elem",1,"FED",12,0,1,0,7]
[null,"Boca Ciega High",17,"PCSB",448,0,17,0,249]
[null,"Campbell Park Elem",2,"FED",26,0,2,0,17]
[null,"Campbell Park Elem",1,"FED (C)",0,0,1,0,12]
[null,"Clearview Elem",7,"PCSB",168,0,7,0,81]
[null,"Clearview Elem",2,"FED (C)",0,0,2,0,28]
[null,"Clearwater High",13,"PCSB",416,0,0,13,101]
[null,"Cross Bayou Elem",3,"PCSB",81,0,1,2,55]
[null,"Cross Bayou Elem",1,"FED (C)",0,0,1,0,4]
[null,"Cross Bayou Elem",2,"FED",26,0,2,0,26]
[null,"Curlew Creek Elem",6,"PCSB",162,0,6,0,58]
[null,"Curtis Fund Elem",1,"PCSB",27,0,1,0,10]
[null,"Dunedin Elem",2,"PCSB",54,0,0,2,15]
[null,"Dunedin High",2,"PCSB",56,0,0,2,1]
[null,"Eisenhower Elem",1,"PCSB",25,0,1,0,11]
[null,"Fairmount Park Elem",5,"PCSB",135,0,5,0,55]
[null,"Fairmount Park Elem",2,"FED (C)",0,0,2,0,27]
[null,"Fairmount Park Elem",2,"FED",26,0,2,0,18]
[null,"Fuguitt Elem",1,"PCSB",24,0,1,0,1]
[null,"Garrison Jones Elem",1,"FED",13,0,1,0,11]
[null,"Gibbs High",2,"PCSB",64,0,2,0,27]
[null,"Gulf Beaches Elem",1,"PCSB",12,0,1,0,9]
[null,"Gulfport Elem",6,"PCSB",129,0,0,6,43]
[null,"Gulfport Elem",1,"FED (C)",0,0,0,1,9]
[null,"Hamilton Disston",1,"PCSB",27,0,1,0,4]
[null,"Hamilton Disston",2,"FED",24,0,2,0,23]
[null,"High Point Elem",2,"FED (C)",0,0,2,0,9]
[null,"Hunsinger Calvin",4,"PCSB",58,0,4,0,44]
[null,"Hunsinger Calvin",1,"FED",13,0,1,0,9]
[null,"John Hopkins Middle",12,"PCSB",336,0,10,2,139]
[null,"Kennedy Middle",4,"PCSB",112,0,4,0,76]
[null,"Kennedy Middle",1,"FED",13,0,1,0,7]
[null,"Kings Highway Elem",1,"FED (C)",0,0,1,0,6]
[null,"Largo Central Elem",1,"PCSB",27,0,1,0,26]
[null,"Lealman Ave Elem",2,"FED (C)",0,0,2,0,27]
[null,"Lealman Discovery",5,"PCSB",140,0,5,0,52]
[null,"Lynch Elem",1,"FED (C)",0,0,1,0,5]
[null,"Madeira Beach Elem",7,"PCSB",189,0,7,0,79]
[null,"Maximo Elem",1,"FED",13,0,1,0,9]
[null,"Meadowlawn Middle",8,"PCSB",153,0,0,8,108]
[null,"Meadowlawn Middle",2,"FED",26,0,0,2,19]
[null,"Melrose Elem",1,"PCSB",27,0,1,0,6]
[null,"Melrose Elem",8,"FED(C)",204,0,8,0,89]
[null,"Melrose Elem",1,"FED",13,0,1,0,10]
[null,"Mildred Helms Elem",2,"PCSB",52,0,2,0,18]
[null,"Mount Vernon Elem",2,"PCSB",52,0,2,0,33]
[null,"Mount Vernon Elem",3,"FED(C)",0,0,3,0,28]
[null,"Mount Vernon Elem",1,"FED",13,0,1,0,8]
[null,"Nina Harris Excep",7,"FED",86,0,0,7,59]
[null,"Oak Grove Middle",1,"FED",13,0,1,0,8]
[null,"Oakhurst Elem",2,"PCSB",46,0,2,0,33]
[null,"Orange Grove Elem",5,"PCSB",101,0,5,0,72]
[null,"Orange Grove Elem",1,"FED(C)",0,0,1,0,18]
[null,"Palm Harbor Elem",4,"PCSB",97,0,4,0,57]
[null,"Palm Harbor Univ High",14,"PCSB",448,0,14,0,221]
[null,"Pasadena Fund Elem",6,"PCSB",162,0,0,6,38]
[null,"Paul B Stephens Excep",3,"PCSB",81,0,3,0,46]
[null,"Paul B Stephens Excep",1,"FED",13,0,1,0,8]
[null,"Perkins Elem",7,"PCSB",189,0,0,7,145]
[null,"Pinellas Central Elem",1,"PCSB",23,0,1,0,1]
[null,"Pinellas Central Elem",2,"FED",26,0,2,0,20]
[null,"Pinellas Park Elem",1,"FED(C)",0,0,1,0,20]
[null,"Plumb Elem",1,"PCSB",27,0,1,0,22]
[null,"Ponce De Leon Elem",2,"PCSB",54,0,2,0,28]
[null,"Ponce De Leon Elem",1,"FED (C)",0,0,1,0,8]
[null,"PTEC North",2,"PCSB",54,0,2,0,35]
[null,"PTEC South",1,"PCSB",32,0,1,0,17]
[null,"Rawlings Elem",2,"PCSB",48,0,2,0,30]
[null,"Rawlings Elem",3,"FED(C)",0,0,3,0,21]
[null,"Rio Vista Elem",6,"PCSB",162,0,6,0,34]
[null,"Rio Vista Elem",3,"FED(C)",0,0,3,0,51]
[null,"Rio Vista Elem",1,"FED",13,0,1,0,26]
[null,"Riviera Middle",1,"PCSB",0,0,1,0,4]
[null,"Robinson Challenge",1,"PCSB",25,0,1,0,11]
[null,"Safety Harbor Elem",2,"FED",26,0,2,0,8]
[null,"Safety Harbor Middle IBIS",1,"PCSB",11,0,1,0,19]
[null,"Safety Harbor Middle",4,"PCSB",106,0,0,4,31]
[null,"San Jose Elem",3,"FED",39,0,0,3,11]
[null,"Sanders, Richard L ",11,"PCSB",73,0,0,11,158]
[null,"Sanders, Richard L ",3,"FED",36,0,0,3,44]
[null,"Sandy Lane Elem",1,"PCSB",27,0,1,0,23]
[null,"Sawgrass Elem",1,"PCSB",27,0,1,0,5]
[null,"Sawgrass Elem",1,"FED(C)",0,0,1,0,18]
[null,"Sawgrass Elem",2,"FED",26,0,2,0,12]
[null,"Seminole Elem",5,"PCSB",135,0,5,0,68]
[null,"Seminole Middle",2,"PCSB",54,0,2,0,13]
[null,"Seminole Vo-Ed",7,"PCSB",189,0,7,0,128]
[null,"Seventy Fourth Elem",1,"FED",13,0,1,0,7]
[null,"Seventy Fourth Elem",2,"FED(C)",0,0,2,0,26]
[null,"Sexton Elem",1,"PCSB",27,0,1,0,1]
[null,"Sexton Elem",1,"FED",13,0,1,0,9]
[null,"Shore Acres Elem",1,"PCSB",0,0,1,0,5]
[null,"Shore Acres Elem ",1,"FED(C)",0,0,1,0,24]
[null,"Skycrest Elem",6,"PCSB",162,0,6,0,83]
[null,"Skycrest Elem",1,"FED(C)",0,0,1,0,9]
[null,"Skycrest Elem",2,"FED",26,0,2,0,15]
[null,"Skyview Elem",5,"PCSB",135,0,0,5,73]
[null,"Skyview Elem",1,"FED(C)",0,0,0,1,14]
[null,"Skyview Elem",1,"FED",13,0,0,1,11]
[null,"Southern Oak Elem",3,"PCSB",81,0,3,0,21]
[null,"Starkey Elem",2,"PCSB",54,0,2,0,28]
[null,"Starkey Elem",1,"FED (c)",0,0,1,0,4]
[null,"Sunset Hills Elem",5,"PCSB",105,0,0,5,42]
[null,"Sutherland Elem",1,"PCSB",27,0,1,0,14]
[null,"Sutherland Elem",2,"FED",26,0,2,0,10]
[null,"Tarpon Springs Elem",1,"PCSB",0,0,1,0,5]
[null,"Tarpon Springs Elem",3,"FED",39,0,3,0,26]
[null,"Tarpon Springs Fund.",4,"PCSB",96,0,4,0,49]
[null,"Tarpon Springs High",2,"PCSB",40,0,0,2,33]
[null,"Tarpon Springs Middle",1,"PCSB",0,0,1,0,5]
[null,"Tyrone Elem",1,"FED",13,0,1,0,7]
[null,"Tyrone Middle",11,"PCSB",277,0,11,0,158]
[null,"Tyrone Middle",1,"FED",13,0,1,0,8]
[null,"Walsingham Elem",1,"PCSB",27,0,1,0,1]
[null,"Westgate Elem",3,"FED(C)",0,0,3,0,42]
[null,"Woodlawn Elem",2,"PCSB",54,0,2,0,35]
[null,"Woodlawn Elem",1,"FED(C)",0,0,1,0,7]
["2c1.","PINELLAS Total",396,null,8191,0,281,172,"Avg Age 11.43"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"Azalea Middle",3,0,0,0,3,0,3]
[null,"Bay Point Elem",12,0,0,12,0,0,12]
[null,"Bay Point Middle",2,0,0,0,2,0,2]
[null,"Dunedin High",3,0,3,0,0,0,3]
[null,"Tarpon Springs High",2,0,0,2,0,0,2]
[null,"Clearwater High",24,24,0,0,0,0,24]
[null,"Lakewood Elem",11,11,0,0,0,0,11]
[null,"Pasadena Elem",8,0,8,0,0,0,8]
[null,"Nina Harris ESE",7,0,0,0,7,0,7]
[null,"Gulfport Elem",7,0,0,0,7,0,7]
[null,"Meadowlawn Middle",9,0,0,0,9,0,9]
[null,"Sanders ESE",14,0,0,0,0,14,14]
[null,"Sunset Hills Elem",5,0,0,0,0,5,5]
[null,"Dunedin Elem",2,0,0,0,0,2,2]
[null,"San Jose Elem",5,0,0,0,0,5,5]
[null,"Skyview Elem",9,0,0,0,0,9,9]
[null,"Safety Harbor Elem",7,0,0,0,0,7,7]
["2c2.","PINELLAS Total",130,35,11,14,28,42,130]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1998-99","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2003-04","FISH Stu. Sta.","# Years Leased "]
[null,"Azalea Elem",4,"Leased",108,1,3,108,1]
[null,"Azeala Middle",2,"Leased",56,1,0,0,0]
[null,"Bauder Elem",3,"Leased",69,1,3,69,1]
[null,"Bear Creek Elem",4,"Leased",108,1,0,0,0]
[null,"Belcher Elem",1,"Leased",27,1,1,27,1]
[null,"Blanton",3,"Leased",81,1,1,81,1]
[null,"Clearwater High",20,"Leased",640,1,0,0,0]
[null,"Curlew Creek Elem",1,"Leased",27,1,1,27,1]
[null,"Cypress Woods Elem",1,"Leased",27,1,1,27,1]
[null,"Dunedin Elem",2,"Leased",54,1,2,54,1]
[null,"Dunedin High",21,"Leased",567,1,0,0,0]
[null,"Frontier Elem",9,"Leased",243,1,4,162,1]
[null,"Fuguitt Elem",2,"Leased",54,1,0,0,0]
[null,"Gulf Beaches Elem",1,"Leased",27,1,1,27,1]
[null,"Lake St George Elem",1,"Leased",27,1,1,27,1]
[null,"Largo Central Elem",2,"Leased",54,1,2,54,1]
[null,"Lealman Discovery",1,"Leased",28,1,1,28,1]
[null,"Lealman Elem",1,"Leased",27,1,1,27,1]
[null,"Lynch Elem",1,"Leased",21,1,1,21,1]
[null,"Madeira Beach Elem",1,"Leased",27,1,1,27,1]
[null,"Northeast High",9,"Leased",288,1,0,0,0]
[null,"Northwest Elem",1,"Leased",27,1,1,27,1]
[null,"Orange Grove Elem",1,"Leased",27,1,1,27,1]
[null,"Palm Harbor Elem",1,"Leased",27,1,1,27,1]
[null,"Paul B Stephens",2,"Leased",26,1,2,26,1]
[null,"Pinellas Central Elem",9,"Leased",243,1,1,27,1]
[null,"Pinellas Park Elem",1,"Leased",27,1,1,27,1]
[null,"Pasadena Fund Elem",2,"Leased",54,1,0,0,0]
[null,"Ponce De Leon Elem",2,"Leased",54,1,2,54,1]
[null,"Rawlings Elem",2,"Leased",54,1,2,54,1]
[null,"Rio Vista Elem",2,"Leased",54,1,2,54,1]
[null,"Safety Harbor Middle",2,"Leased",55,1,0,0,0]
[null,"San Jose Elem",2,"Leased",54,1,0,0,0]
[null,"Seminole Elem",3,"Leased",81,1,3,81,1]
[null,"Seminole Mid",1,"Leased",28,1,1,28,1]
[null,"Sexton Elem",1,"Leased",27,1,1,27,1]
[null,"Skyview Elem",1,"Leased",20,1,0,0,0]
[null,"Southside Fund. Middle",2,"Leased",56,1,1,56,1]
[null,"Sunset Hills Elem",1,"Leased",27,1,0,0,0]
[null,"Tarpon Springs Elem",3,"Leased",81,1,1,81,1]
[null,"Tyrone Middle",1,"Leased",28,1,1,28,1]
[null,"Walsingham Elem",1,"Leased",27,1,1,27,1]
["2c3.","PINELLAS Total",131,null,3637,42,46,1417,31]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2003-04"]
[null,"Charter # 1 - Elem",3,"Academie DaVinci","1997-98",60,60,3,60]
[null,"Charter #2 - Pre-K",1,"UPARC","1999-00",20,20,3,20]
["2c4.","PINELLAS Total",4,null,null,80,80,6,80]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2003-04) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1998-99 CO-FTE","1998-99 Class size","2003-04 CO-FTE","be added (removed)","2003-04 Class size"]
[null,"Anona Elem",20,471,443,22.15,385,0,19.25]
[null,"Azalea Elem",39,934,707,18.13,664,null,17.03]
[null,"Bardmoor Elem",24,711,732,30.5,731,null,30.46]
[null,"Bauder Elem",34,903,917,26.97,907,null,26.68]
[null,"Bay Point Elem",36,825,749,20.81,607,2,15.97]
[null,"Bay Vista Fund Elem",27,632,419,15.52,616,null,22.81]
[null,"Bear Creek Elem",28,623,485,17.32,633,null,22.61]
[null,"Belcher Elem",28,646,581,20.75,463,3,14.94]
[null,"Belleair Elem",21,523,412,19.62,380,null,18.1]
[null,"Blanton Elem",40,967,766,19.15,767,8,15.98]
[null,"Brooker Creek Elem",30,751,584,19.47,710,null,23.67]
[null,"Campbell Park Elem",25,511,436,17.44,440,null,17.6]
[null,"Clearview Ave Elem",30,646,635,21.17,605,null,20.17]
[null,"Cross Bayou Elem",33,775,622,18.85,695,null,21.06]
[null,"Curlew Creek Elem",18,823,745,41.39,750,2,37.5]
[null,"Curtis Fund Elem",17,384,411,24.18,396,null,23.29]
[null,"Cypress Woods Elem",33,756,691,20.94,752,null,22.79]
[null,"Dunedin Elem",30,762,681,22.7,683,1,22.03]
[null,"Eisenhower Elem",23,615,615,26.74,638,1,26.58]
[null,"Fairmount Park Elem",20,415,419,20.95,410,null,20.5]
[null,"Forest Lakes Elem",31,779,692,22.32,795,null,25.65]
[null,"Frontier Elem",37,938,774,20.92,763,null,20.62]
[null,"Fuguitt Elem",36,848,768,21.33,672,null,18.67]
[null,"Garrison-Jones Elem",28,736,685,24.46,814,null,29.07]
[null,"Gulf Beaches Elem",18,469,372,20.67,358,null,19.89]
[null,"Gulfport Elem",25,537,408,16.32,446,5,14.87]
[null,"High Point Elem",27,660,478,17.7,529,null,19.59]
[null,"Highland Lakes Elem",29,670,603,20.79,713,null,24.59]
[null,"John M Sexton Elem",30,767,691,23.03,752,null,25.07]
[null,"Kings Highway Elem",28,672,560,20,516,null,18.43]
[null,"Lake Saint George Elem",29,675,706,24.34,736,7,20.44]
[null,"Lakeview Fund Elem",12,287,286,23.83,279,null,23.25]
[null,"Lakewood Elem",28,716,349,12.46,695,null,24.82]
[null,"Largo Central Elem",23,485,419,18.22,432,null,18.78]
[null,"Lealman Avenue Elem",31,746,625,20.16,656,null,21.16]
[null,"Leila Davis Elem",14,729,592,42.29,707,6,35.35]
[null,"Lynch Elem",29,722,678,23.38,665,null,22.93]
[null,"Madeira Beach Elem",29,694,510,17.59,471,null,16.24]
[null,"Marjorie Kinnan Rawlings Elem",32,818,704,22,735,null,22.97]
[null,"Maximo Elem",29,805,602,20.76,632,-9,31.6]
[null,"McMullen-Booth Elem ",28,716,552,19.71,738,null,26.36]
[null,"Melrose Elem",31,692,617,19.9,601,null,19.39]
[null,"Mildred Helms Elem",29,734,629,21.69,606,null,20.9]
[null,"Mount Vernon Elem",24,490,549,22.88,528,null,22]
[null,"North Shore Elem",27,556,574,21.26,598,null,22.15]
[null,"North Ward Elem",16,0,267,16.69,238,null,14.88]
[null,"Northwest Elem",33,770,773,23.42,706,null,21.39]
[null,"Norwood Elem",19,0,0,0,0,null,0]
[null,"Oakhurst Elem",30,727,650,21.67,689,null,22.97]
[null,"Oldsmar Elem",18,740,672,37.33,669,null,37.17]
[null,"Orange Grove Elem",18,403,407,22.61,325,5,14.13]
[null,"Ozona Elem",28,716,675,24.11,672,null,24]
[null,"Palm Harbor Elem",21,456,468,22.29,519,null,24.71]
[null,"Pasadena Fund Elem",25,590,485,19.4,466,null,18.64]
[null,"Perkins Elem",30,736,452,15.07,539,null,17.97]
[null,"Pinellas Central Elem",29,795,830,28.62,740,null,25.52]
[null,"Pinellas Park Elem",34,858,611,17.97,588,null,17.29]
[null,"Plumb Elem",34,743,783,23.03,772,null,22.71]
[null,"Ponce De Leon Elem",32,734,619,19.34,557,null,17.41]
[null,"Ridgecrest Elem",30,744,744,650,636,null,21.2]
[null,"Rio Vista Elem",26,629,620,23.85,569,10,15.81]
[null,"Safety Harbor Elem",25,562,529,21.16,540,null,21.6]
[null,"Samuel L Robinson Challenge",14,25,219,15.64,180,null,12.86]
[null,"San Jose Elem",29,681,639,22.03,655,-6,28.48]
[null,"Sandy Lane Elem",34,660,745,21.91,728,null,21.41]
[null,"Sawgrass Lake Elem",32,841,705,22.03,740,null,23.13]
[null,"Seminole Elem",39,927,780,20,810,null,20.77]
[null,"Seventy-Fourth Street Elem",33,799,618,18.73,594,null,18]
[null,"Shore Acres Elem",30,675,655,21.83,690,3,20.91]
[null,"Skycrest Elem",35,869,650,18.57,589,null,16.83]
[null,"Skyview Elem",36,773,771,21.42,698,-8,24.93]
[null,"South Ward Elem",17,0,350,20.59,282,null,16.59]
[null,"Southern Oak Elem",31,780,672,21.68,609,null,19.65]
[null,"Starkey Elem",33,746,674,20.42,664,null,20.12]
[null,"Sunset Hills Elem",24,588,510,21.25,455,3,16.85]
[null,"Sutherland Elem",30,699,773,25.77,743,2,23.22]
[null,"Tarpon Springs Elem",30,772,587,19.57,572,-8,26]
[null,"Tarpon Springs Fund Elem",12,273,291,24.25,245,3,16.33]
[null,"Tyrone Elem",40,938,612,15.3,631,3,14.67]
[null,"Walsingham Elem",22,618,676,30.73,689,null,31.32]
[null,"Westgate Elem",29,644,776,26.76,756,null,26.07]
[null,"Woodlawn Elem",33,711,744,22.55,743,null,22.52]
[null,"Azalea Middle",43,1020,910,21.16,1029,9,19.79]
[null,"Bay Point Middle",53,1292,1344,25.36,1326,5,22.86]
[null,"Carwise Middle",50,1427,1346,26.92,1416,null,28.32]
[null,"Clearwater Disc Middle",27,588,349,12.93,412,null,15.26]
[null,"Coachman Fund Middle",21,521,461,21.95,441,null,21]
[null,"Dunedin Highland Middle",46,960,1122,24.39,1235,19,19]
[null,"John Hopkins Middle",62,1700,1521,24.53,1452,null,23.42]
[null,"Kennedy Middle",38,934,963,25.34,988,null,26]
[null,"Largo Middle",51,1237,1230,24.12,1373,10,22.51]
[null,"Lealman Disc Middle",36,146,414,11.5,441,null,12.25]
[null,"Madeira Beach Middle",46,988,957,20.8,1182,null,25.7]
[null,"Meadowlawn Middle",40,1004,1025,25.63,1158,10,23.16]
[null,"Morgan Fitzgerald Middle",59,1360,1659,28.12,1257,null,21.31]
[null,"North Ward IBIS",11,0,52,4.73,39,null,3.55]
[null,"Oak Grove Middle",49,1005,1086,22.16,1231,16,18.94]
[null,"Osceola Middle",52,1474,1132,21.77,1216,4,21.71]
[null,"Palm Harbor Middle",58,1460,1304,22.48,1451,-1,25.46]
[null,"Pinellas Park Middle",52,1345,1061,20.4,1183,null,22.75]
[null,"Riviera Middle",49,1278,1088,22.2,1206,null,24.61]
[null,"Safety Harbor IBIS",9,192,30,3.33,39,null,4.33]
[null,"Safety Harbor Middle",59,1484,1410,23.9,1617,2,26.51]
[null,"Seminole Middle",46,1199,1154,25.09,1359,null,29.54]
[null,"Southside Fund Middle",29,19,633,21.83,636,null,21.93]
[null,"Tarpon Springs Middle",50,1250,1214,24.28,1491,null,29.82]
[null,"Tyrone Middle",44,935,993,22.57,1157,16,19.28]
[null,"Boca Ciega High",87,2053,1961,22.54,1982,null,22.78]
[null,"Clearwater High",94,2402,1797,19.12,1836,null,19.53]
[null,"Countryside High",103,2279,1698,16.49,1843,-8,19.4]
[null,"Dixie Hollins High",93,2098,1490,16.02,1765,null,18.98]
[null,"Dunedin High",88,1507,1606,18.25,1774,25,15.7]
[null,"East Lake High",82,2231,1976,24.1,2032,null,24.78]
[null,"Gibbs High",77,1798,1642,21.32,1717,6,20.69]
[null,"Lakewood High",65,1667,1580,24.31,1565,null,24.08]
[null,"Largo High",90,2101,1688,18.76,1824,null,20.27]
[null,"Northeast High",98,2513,1808,18.45,1863,-32,28.23]
[null,"Osceola High",60,1619,1219,20.32,1475,null,24.58]
[null,"Palm Harbor Univ High",73,1862,2242,30.71,1955,18,21.48]
[null,"Pinellas Park High",79,2057,1920,24.3,2108,null,26.68]
[null,"Seminole High",80,2112,1779,22.24,1908,null,23.85]
[null,"St Petersburg High",84,1948,1992,23.71,2032,null,24.19]
[null,"Tarpon Springs High",78,1873,1465,18.78,1777,3,21.94]
[null,"Oldsmar Community",9,0,0,0,0,null,0]
[null,"Pinellas Vo-Tech",88,967,1804,20.5,177,null,2.01]
[null,"Seminole Vocational Center",21,250,226,10.76,78,null,3.71]
[null,"St Petersburg Challenge",13,26,151,11.62,156,null,12]
[null,"St Petersburg Vo-Tech",91,1359,1324,14.55,185,null,2.03]
[null,"Tomlinson Adult",22,406,370,16.82,0,null,0]
["2e.","PINELLAS Total",4926,113782,104701,"District Avg 21",105354,135,"District Avg 21"]
["2f."]
[null,"The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[null,"Site                              ",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR AVERAGE"]
[null,"Anona Elem",null,75,75,75,75,75,75]
[null,"Azalea Elem",null,47,47,47,47,47,47]
[null,"Azalea Mid",null,54,54,54,0,0,32.4]
[null,"Bauder Elem",null,172,172,172,172,172,172]
[null,"Bay Point Elem",null,288,288,288,0,0,172.8]
[null,"Bay Point Mid",null,30,30,30,30,0,24]
[null,"Bear Creek Elem",null,361,361,361,361,361,361]
[null,"Belcher Elem",null,81,81,81,81,81,81]
[null,"Belleair Elem",null,0,0,0,0,0,0]
[null,"Blanton Elem",null,79,79,79,79,79,79]
[null,"Boca Ciega High",null,425,425,425,425,425,425]
[null,"Campbell Park Elem",null,18,18,18,18,18,18]
[null,"Clearview Elem",null,129,129,129,129,129,129]
[null,"Clearwater High",null,684,0,0,0,0,136.8]
[null,"Cross Bayou Elem",null,135,135,135,135,135,135]
[null,"Curlew Creek Elem",null,179,179,179,179,179,179]
[null,"Curtis Fund Elem",null,29,29,29,29,29,29]
[null,"Dunedin Elem",null,54,54,54,54,54,54]
[null,"Dunedin High",null,736,736,736,0,0,441.6]
[null,"Eisenhower Elem",null,27,27,27,27,27,27]
[null,"Fairmount Park Elem",null,148,148,148,148,148,148]
[null,"Frontier",null,235,235,235,235,235,235]
[null,"Fuguitt Elem",null,81,81,81,81,81,81]
[null,"Garrison Jones Elem",null,13,13,13,13,13,13]
[null,"Gibbs High",null,46,46,46,46,46,46]
[null,"Gulf Beaches Elem",null,54,54,54,54,54,54]
[null,"Gulfport Elem",null,49,49,0,0,0,19.6]
[null,"Hamilton Disston",null,24,24,24,24,24,24]
[null,"High Point Elem",null,0,0,0,0,0,0]
[null,"Hunsinger Calvin",null,48,48,48,48,48,48]
[null,"John Hopkins Middle",null,336,336,336,336,336,336]
[null,"Kennedy Middle",null,134,134,134,134,134,134]
[null,"Lake St George Elem",null,27,27,27,27,27,27]
[null,"Lakewood Elem",null,262,0,0,0,0,52.4]
[null,"Largo Central Elem",null,42,42,42,42,42,42]
[null,"Lealman Ave Elem",null,43,43,43,43,43,43]
[null,"Lealman Discovery",null,104,104,0,0,0,41.6]
[null,"Lynch Elem",null,25,25,25,25,25,25]
[null,"Madeira Beach Elem",null,94,94,94,94,94,94]
[null,"Maximo Elem",null,18,18,18,18,0,14.4]
[null,"Meadowlawn Mid",null,188,188,188,0,0,112.8]
[null,"Melrose Elem",null,173,173,173,0,0,103.8]
[null,"Mildred Helms Elem",null,23,23,23,23,23,23]
[null,"Mount Vernon Elem",null,117,117,117,117,117,117]
[null,"Nina Harris Ex",null,91,91,91,0,0,54.6]
[null,"North East High",null,288,288,288,0,0,172.8]
[null,"North Shore Elem",null,105,105,105,105,105,105]
[null,"Northwest Elem",null,27,27,27,27,27,27]
[null,"Oak Grove Middle",null,13,13,13,13,13,13]
[null,"Oakhurst Elem",null,54,54,54,54,54,54]
[null,"Oldsmar Elem",null,27,27,27,27,27,27]
[null,"Orange Grove Elem",null,118,118,118,118,118,118]
[null,"Palm Harbor Elem",null,116,116,116,116,116,116]
[null,"Palm Harbor U High",null,372,372,372,372,372,372]
[null,"Pasadena Fund Elem",null,182,0,0,0,0,36.4]
[null,"Paul B Stephens Ex",null,57,57,57,57,0,45.6]
[null,"Perkins Elem",null,76,76,76,76,76,76]
[null,"Pinellas Central Elem",null,312,312,312,312,312,312]
[null,"Pinellas Park Elem",null,27,27,27,27,27,27]
[null,"Plumb Elem",null,25,25,25,25,25,25]
[null,"Ponce De Leon Elem",null,79,79,79,79,79,79]
[null,"PTEC North",null,64,64,64,64,64,64]
[null,"PTEC South",null,0,0,0,0,0,0]
[null,"Rawlings Elem",null,194,194,194,194,194,194]
[null,"Rio Vista Elem",null,208,208,208,208,208,208]
[null,"Robinson Challenge",null,0,0,0,0,0,0]
[null,"Safety Harbor Elem",null,26,26,26,26,26,26]
[null,"Safety Harbor Middle IBIS",null,0,0,0,0,0,0]
[null,"Safety Harbor Middle",null,107,107,107,107,107,107]
[null,"Sandy Lane Elem",null,27,27,27,27,27,27]
[null,"San Jose Elem",null,90,90,90,90,90,90]
[null,"Sanders, Richard L ",null,156,156,156,156,156,156]
[null,"Sawgrass Elem",null,53,53,53,53,53,53]
[null,"Seminole Elem",null,170,170,170,170,170,170]
[null,"Seminole Middle",null,63,63,63,63,63,63]
[null,"Seminole Vo-Ed",null,66,66,66,66,66,66]
[null,"Seventy Fourth Elem",null,40,40,40,40,40,40]
[null,"Sexton Elem",null,67,67,67,67,67,67]
[null,"Shore Acres Elem",null,0,0,0,0,0,0]
[null,"Skycrest Elem",null,108,108,108,108,108,108]
[null,"Skyview Elem",null,167,167,167,167,167,167]
[null,"Southern Oak Elem",null,81,81,81,81,81,81]
[null,"Southside Fundamental",null,42,42,42,42,42,42]
[null,"Starkey Elem",null,42,42,42,42,42,42]
[null,"Sunset Hills Elem",null,110,110,110,110,110,110]
[null,"Sutherland Elem",null,42,42,42,42,42,42]
[null,"Tarpon Springs Elem",null,84,84,84,84,84,84]
[null,"Tarpon Springs Fund.",null,108,108,108,108,108,108]
[null,"Tarpon Springs High",null,50,50,0,0,0,20]
[null,"Tarpon Springs Middle",null,0,0,0,0,0,0]
[null,"Tyrone Elem",null,15,15,15,15,15,15]
[null,"Tyrone Middle",null,207,207,207,207,207,207]
[null,"Walsingham Elem",null,52,52,52,52,52,52]
[null,"Westgate Elem",null,0,0,0,0,0,0]
[null,"Woodlawn Elem",null,54,54,54,54,54,54]
["2f.","PINELLAS Total students in relocatables by year",null,10349,9221,9018,7200,7095,8576.6]
[null,"Total number of CO-FTE students projected by year",null,108546,109243,109966,110601,111004,109872]
[null,"Percent in relocatables by year",null,0.1,0.08,0.08,0.07,0.06,0.08]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1998,1998,1998,1998,1998,1998]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,96,112,147,8492,13172,19094]
[null,"1997 State-wide totals - Gross Sq Ft per student station: Elem low 96, avg 112, high 147; Middle low 68, avg 108, high 131; High School low 127, avg 150, high 178 ",{"$nulls":7},2,68,108,131,11596,14169,17037]
[null,"1997 State-wide totals - Cost per student station: Elem low 8,341, avg 11,305, high 16,402; Middle low 7,478,avg 12,759, high 15,800; High School low 13,985, avg 20,182, high  28,785 ",{"$nulls":7},3,127,150,178,11385,25596,64760]
["3a.","1999-00 Year","Type of School (new schools only)  Others=0","1999-00","1999-00","1999-00","1999-00","1998 State Avg","1998 State Avg","1998 State Avg","1999 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Azalea Md, Construction, Renovate, Remodel",null,21003000,645,208642,323.48,0,0,0,32562.79,0,0,0]
[null,"Bay Point Elem, Master Planning, Construction, Renovate, Remodel",null,10368551,78,86661,1111.04,0,0,0,132930.14,0,0,0]
[null,"Dunedin Sr, Construction, Renovate, Remodel, Replace State Relocatables ",null,20167200,479,246787,515.21,0,0,0,42102.71,0,0,0]
[null,"Tarpon Springs Sr, Construction, Renovate, Remodel ",null,15613300,83,312462,3764.6,0,0,0,188112.05,0,0,0]
[null,"Alt Sr, Planning, New Construction, Site",3,15000000,"N/A","N/A",null,127,150,178,null,13985,20182,28785]
[null,"Elem Stu Sta, Plan, New Construct, Site",1,38114750,2587,"N/A",null,96,112,147,14733.19,8341,13305,16402]
[null,"Midd Stu Stat, Plan, New Construct, Site",2,23300000,1000,"N/A",null,68,108,131,23300,7478,12759,15800]
[null,"Pasadena Elem, Planning, Construction, Renovate, Remodel ",null,6492915,48,50464,1051.33,0,0,0,135269.06,0,0,0]
[null,"Nina Harris ESE, Planning, New Construction, Remodeling",null,12030300,80,119176,1489.7,0,0,0,150378.75,0,0,0]
[null,"Gulfport Elem, Planning, New Construction",null,6900000,319,98196,307.82,0,0,0,21630.09,0,0,0]
[null,"Largo Middle, Planning, New Construction, Remodeling",null,7825673,162,40836,252.07,0,0,0,48306.62,0,0,0]
[null,"Sanders ESE, Planning, New Construction, Remodeling",null,9800000,84,78367,932.94,0,0,0,116666.67,0,0,0]
[null,"Dunedin Highland Middle, Planning, New Construction, Remodeling, Renovation",null,16732592,355,181920,512.45,0,0,0,47134.06,0,0,0]
[null,"Stephens ESE, Planning, New Construction, Remodeling",null,10536050,71,38027,535.59,0,0,0,148395.07,0,0,0]
[null,"Meadowlawn Md, Planning, New Construction, Remodeling",null,21959840,204,199136,976.16,0,0,0,107646.27,0,0,0]
["3a.","PINELLAS Total 1999-00",null,235844171,6195,1660674,11772.390000000001,null,null,null,1209167.47]
["3b.","2000-2001 Year","Type of School (new schools only)  Others=0","2000-01","2000-01","2000-01","2000-01","1998 State Avg","1998 State Avg","1998 State Avg","2000 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Lake St. George, Planning, New Construction, Remodeling",null,4212606,95,21407,225.34,0,0,0,44343.22,0,0,0]
[null,"Shore Acres Elem, Planning, New Construction, Remodeling",null,7670552,67,56147,838.01,0,0,0,114485.85,0,0,0]
["3b","PINELLAS Total 2000-01",null,11883158,162,77554,478.73,null,null,null,73352.83]
[]
["3c.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02","1998 State Avg","1998 State Avg","1998 State Avg","2001 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Eisenhower Elem, Planning, New Construction, Remodeling",null,3057177,25,32274,1290.96,0,0,0,122287.08,0,0,0]
[null,"Cypress Woods Elem, Planning, New Construction",null,2915855,24,7875,328.13,0,0,0,121493.96,0,0,0]
[null,"Skyview Elem, Planning, New Construction",null,9702900,5,98196,19639.2,0,0,0,1940580,0,0,0]
[null,"Oak Grove Elem, Planning, New Construction, Remodeling",null,8757586,298,75372,252.93,0,0,0,29387.87,0,0,0]
[null,"Tarpon Springs Fund Elem, Planning, New Construction",null,2134913,36,17843,495.64,0,0,0,59303.14,0,0,0]
[null,"Safety Harbor Middle, Planning, New Construction, Remodeling, Renovation",null,20706260,101,262711,2601.1,0,0,0,205012.48,0,0,0]
[null,"Palm Harbor Middle, Planning, New Construction",null,3808347,30,21135,704.5,0,0,0,126944.9,0,0,0]
[null,"Rio Vista Elem, Planning, New Construction, Remodeling",null,4682716,154,37103,240.93,0,0,0,30407.25,0,0,0]
["3c","PINELLAS Total 2001-02",null,55765754,673,552509,820.96,null,null,null,82861.45]
[]
["3d.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","1998 State Avg","1998 State Avg","1998 State Avg","2002 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Sutherland Elem, Planning, New Construction",null,3550756,84,13069,155.58,0,0,0,42270.9,0,0,0]
["3d.","PINELLAS Total 2002-03",null,3550756,84,13069,155.58,null,null,null,42270.9]
[]
["3e.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1998 State Avg","1998 State Avg","1998 State Avg","2003 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Davis Elem, Planning, New Construction, Remodeling",null,7149883,34,52029,1530.26,0,0,0,210290.68,0,0,0]
[null,"Hunsinger ESE Center, Planning, New Construction, Remodeling, Renovation",null,2842088,233,22429,96.26,0,0,0,12197.8,0,0,0]
[null,"Bauder Elem, Planning, New Construction, Remodeling, Renovation",null,6821036,11,65271,5933.73,0,0,0,620094.18,0,0,0]
[null,"Tyrone Middle, New Constr, Remodeling, FHS/ADA",null,5008362,69,153752,2228.29,0,0,0,72584.96,0,0,0]
[null,"Palm Harbor Univ High, Planning, New Constr, Remodeling, FHS/ADA, Site",null,6075326,335,41826,124.85,0,0,0,18135.3,0,0,0]
[null,"Pinellas Central Elem, Planning, New Construction, Remodeling",null,2782166,174,115339,662.87,0,0,0,15989.46,0,0,0]
["3e","PINELLAS Total 2003-04",null,30678861,856,450646,526.46,null,null,null,35839.79]
[]
["3f.","PINELLAS 5-Year Total",null,337722700,7970,2754452]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,69485090,71917068,74434166,77039361,79350542,372226227]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,69485090,71917068,74434166,77039361,79350542,372226227,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,3300000,2884000,2968000,3052000,3136000,15340000,0.0412114968997066]
[null,"  less amount used to purchase other vehicles",null,350000,515000,530000,545000,560000,2500000,0.00671634564858322]
[null,"  less amount transferred to operating budget for maintenance/repair",null,3600000,3708000,3816000,3924000,4032000,19080000,0.0512591499899871]
[null,"  less amount used for maintenance/repair",null,11468579,15450000,15900000,16350000,16800000,75968579,0.20409249399828]
[null,"  less amount used to purchase capital outlay equipment",null,6432969,7210000,7423180,7630000,7840000,36536149,0.0981557621408553]
[null,"  less amount used to correct environmental problems",null,3550000,6180000,6360000,6540000,6720000,29350000,0.078849897914367]
[null,"  less amount transferred to operating budget for salaries",null,1600000,1648000,1696000,1744000,1792000,8480000,0.0227818444399943]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount used for site acquisition",null,4300000,3920000,2964000,4360000,4480000,20024000,0.0537952421068922]
[null,"  less amount to pay relocatables ",null,800000,824000,848000,872000,896000,4240000,0.0113909222199971,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,34083542,29578068,31928986,32022361,33094542,160707499,0.431746844641337,0.51]
[null,"P E C O New Construction",null,1074531,1200000,1200000,1300000,1300000,6074531,0.395992894393742,0.02]
[null,"General Revenue/Capital Outlay",null,2012126,2100000,2100000,2200000,2200000,10612126]
[null,"Trust Fund/Capital Outlay",null,3572440,3600000,3600000,3700000,3700000]
[null,"CO & DS Flow Thru",{"$nulls":7},0]
[null,"C O & D S   Bond Proceeds  ",null,14000000,30500000,2725000,0,null,47225000,2.47510482180294,0.15]
[null,"C O & D S maximum potential bond proceeds",{"$nulls":6},0,0,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,0,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,0,0]
[null,"Proceeds from local governmental infra sales surtax (Penny for Pinellas)",null,800000,9200000,5000000,0,0,15000000,1.7688679245283,0.05]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,0,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,6064000,null,30000000,33500000,8000000,77564000,18.2933962264151,0.24]
[null,"Impact fees received",null,0,0,0,0,0,0,0,0]
[null,"Private donations",null,0,0,0,0,0,0,0,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","PINELLAS Total",null,61606639,76178068,76553986,72722361,48294542,317183156,23.933361867140082,0.9700000000000001]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Azalea Md, Construction, Renovate, Remodel",null,5450700,966100,811900,null,null,7228700]
[null,"Bay Point Md, Planning, Construction, Renovate, Remodel, FHS, ADA",null,2583607,338668,null,null,null,2922275]
[null,"Bay Point Elem, Planning, Construction, Renovate, Remodel, FHS, ADA",null,5167213,672282,null,null,null,5839495]
[null,"Dunedin Sr, Construction, Renovate, Remodel, Sitework, Drainage, FHS, ADA",null,700000,791300,600000,null,null,2091300]
[null,"Northeast Sr, Construction, Renovate, Remodel, Sitework, Drainage, FHS, ADA ",null,820000,757000,700000,null,null,2277000]
[null,"Tarpon Springs Sr, Construct, Renovate, Remodel, FHS, ADA, Site, Demolition ",null,675600,700000,null,null,null,1375600]
[null,"New Alternative Sr, Planning",null,800000,1200000,8000000,5000000,null,15000000]
[null,"Academie Da Vinci (Charter School SIT)",null,346000,{"$nulls":4},346000]
[null,"Elementary Stu Stations, Planning, New Construction, Renovation, Remodeling",null,11800000,10500000,10000000,6335000,1055750,39690750]
[null,"Middle School Stu Stations, Planning, New Construction, Renovation, Reml",null,2700000,9750000,6615000,1135000,null,20200000]
[null,"Gibbs Sr, Construct, Renovate, Remodel ",null,1500000,2600000,2600000,11050000,5950600,23700600]
[null,"PTEC St Pete (Gibbs High/PATA), Renovation",null,400000,400000,null,null,null,800000]
[null,"Clearwater Sr, Planning, Additions, Renovate, Remodel",null,694000,{"$nulls":4},694000]
[null,"Lealman Discovery, Scope to be defined",null,4500000,{"$nulls":4},4500000]
[null,"Pasadena Fund, Planning, Construction, Remodel, Renovate, FHS, ADA",null,436090,{"$nulls":4},436090]
[null,"Nina Harris ESE, Planning, New Construction, Remodeling",null,7700000,2328000,750000,null,null,10778000]
[null,"Stephens ESE, Planning, New Construction, Remodeling",null,4490320,5495730,null,null,null,9986050]
[null,"Meadowlawn Md, Planning, New Construction, Remodeling",null,9000000,9089640,1673500,1396700,null,21159840]
[null,"Largo Md, Planning, New Construction, Remodeling",null,600000,6759473,466200,null,null,7825673]
[null,"Sanders ESE, Planning, New Construction, Remodeling",null,600000,7496510,1603490,null,null,9700000]
[null,"Maximo Elem, Planning, New Construction, Remodeling",null,800000,8389163,693200,null,null,9882363]
[null,"Dunedin Highland Middle, Planning, New Construction, Remodeling, Renovation",null,800000,7873085,6693607,887800,478100,16732592]
[null,"Melrose Elem, Planning, New Construction, Remodeling, Renovation",null,350000,4703405,null,null,null,5053405]
[null,"Lake St George Elem, Planning, New Construction, Remodeling",null,null,412000,3800606,null,null,4212606]
[null,"Shore Acres Elem, Planning, New Construction, Remodeling",null,null,618000,6769402,283150,null,7670552]
[null,"Sunset Hills Elem, Planning, New Construction, Remodeling, Renovations",null,null,412000,5502155,246700,null,6160855]
[null,"Eisenhower Elem, Planning, New Construction, Remodeling",null,null,null,3057177,null,null,3057177]
[null,"Cypress Woods, Planning, New Construction, Remodeling, Renovation",null,null,null,2915855,null,null,2915855]
[null,"Dunedin Elem, Planning, New Construction, Remodeling",null,null,463500,5967293,null,null,6430793]
[null,"San Jose Elem, Planning, New Construction, Remodeling, Renovations",null,null,721000,7621579,780200,null,9122779]
[null,"Skyview Elem, , Planning, New Construction, Remodeling, Renovations",null,null,null,636000,8256900,810000,9702900]
[null,"Oak Grove Middle, Planning, New Construction, Remodeling",null,null,null,636000,7506386,615200,8757586]
[null,"Tarpon Springs Fund Elem, Planning, New Construction, Remodeling",null,null,null,2134913,null,null,2134913]
[null,"Druid Complex, Planning, New Construction, Renovations",null,null,null,277223,null,null,277223]
[null,"Safety Harbor Middle, Planning, New Construction, Remodeling, Renovations",null,null,null,848000,11400000,7577360,19825360]
[null,"Starkey Elem, Planning, New Construction, Remodeling",null,null,null,530000,3636982,null,4166982]
[null,"Belleair Elem, Planning, New Construction, Renovation",null,null,null,477000,3437617,null,3914617]
[null,"Lynch Elem, Planning, New Construction, Remodeling",null,null,null,424000,4880827,467600,5772427]
[null,"Palm Harbor Middle, Planning, New Construction, Remodeling",null,null,null,318000,3309147,181200,3808347]
[null,"Rio Vista Elem, Planning, New Construction, Remodeling",null,null,null,371000,3885516,426200,4682716]
[null,"Belcher Elem, Planning, New Construction, Remodeling",null,null,null,477000,5394108,469050,6340158]
[null,"Sutherland Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":4},545000,3005756,3550756]
[null,"Tarpon Springs Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":4},545000,5678390,6223390]
[null,"Curlew Creek Elem, Planning, New Construction, Remodeling",{"$nulls":4},381500,3080690,3462190]
[null,"Davis Elem, Planning, New Construction, Remodeling",{"$nulls":5},1120000,1120000]
[null,"Osceola Middle, Planning, New Construction, Remodeling",{"$nulls":5},3281955,3281955]
[null,"Blanton Elem, Planning, New Construction, Remodeling",{"$nulls":5},3991654,3991654]
[null,"Countryside High, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},3000000,3000000]
[null,"Hunsinger ESE Center, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},2842088,2842088]
[null,"Bauder Elem, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},3560000,3560000]
[null,"Tyrone Elem, Remodel, FHS/ADA, Maintenance, New Construction",{"$nulls":5},3891232,3891232]
[null,"Orange Grove Elem, New Constr, Remodel, Site",{"$nulls":5},1768000,1768000]
[null,"Tyrone Middle, New Constr, Remodeling, FHS/ADA",{"$nulls":5},1992000,1992000]
[null,"Palm Harbor Univ High, Planning, New Constr, Remodeling, FHS/ADA, Site",{"$nulls":5},560000,560000]
[null,"Pinellas Central Elem, Planning, New Construction, Remodeling",{"$nulls":5},336000,336000]
["5.","PINELLAS Total",null,62913530,83436856,83970100,80293533,56138825,366752844]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Effort Index Grants",null,0,0,0,0,0,0]
[null,"SIT Program awards (Charter School)",null,364210,0,0,0,0,364210]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","PINELLAS Total",null,364210,0,0,0,0,364210]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Safety Harbor Middle, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},880900,880900]
[null,"Davis Elem, Planning, New Construction, Remodeling",{"$nulls":5},6029883,6029883]
[null,"Countryside High, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},8878198,8878198]
[null,"Bauder Elem, Planning, New Construction, Remodeling, Renovation",{"$nulls":5},3261036,3261036]
[null,"Orange Grove Elem, New Constr, Remodel, Site",{"$nulls":5},1383129,1383129]
[null,"Tyrone Middle, New Constr, Remodeling, FHS/ADA",{"$nulls":5},3016362,3016362]
[null,"Cross Bayou Elem, New Constr, Remodel",{"$nulls":5},2773771,2773771]
[null,"Palm Harbor Elem, Planning, New Construction, Remodeling",{"$nulls":5},3413266,3413266]
[null,"Palm Harbor Univ High, Planning, New Constr, Remodeling, FHS/ADA, Site",{"$nulls":5},5515326,5515326]
[null,"Pinellas Central Elem, Planning, New Construction, Remodeling",{"$nulls":5},2446166,2446166]
[null,"Boca Ciega High, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},15868463,15868463]
[null,"Kennedy Middle, Planning, New Construction, Remodeling, Renovations ",{"$nulls":5},8488447,8488447]
[null,"Mount Vernon Elem, Planning New Construction, Remodeling, Renovations",{"$nulls":5},3128730,3128730]
[null,"Westgate Elem, New Construction, Remodeling, FHS/ADA",{"$nulls":5},2034865,2034865]
[null,"Southern Oak Elem, Remodel, FHS/ADA, Maintenance, New Construction",{"$nulls":5},1569548,1569548]
[null,"Pinellas Park High, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},5861978,5861978]
[null,"Kings Highway Elem, New Constr, Remodel, Maintenance",{"$nulls":5},4547147,4547147]
[null,"Seventy-Forth Street Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},3660667,3660667]
[null,"Campbell Park Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},2511064,2511064]
[null,"Garrison-Jones Elem, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},1462612,1462612]
[null,"Seminole Middle, Planning, New Construction, Remodeling, Renovations",{"$nulls":5},11262747,11262747]
[null,"Clearview Elem, Site, Renovate, Remodel, etc.",{"$nulls":5},1915882,1915882]
[null,"Azalea Elem, New Constr, Remodeling, etc.",{"$nulls":5},1529094,1529094]
[null,"Curtis Fund Elem, New Constr, Maintenance",{"$nulls":5},2556682,2556682]
[null,"Madeira Beach Elem, Plan, New Constr, Remodel, Site",{"$nulls":5},2732094,2732094]
[null,"Madeira Beach Middle, New Constr, Remodel, Site, etc.",{"$nulls":5},2605934,2605934]
[null,"Osceola High, Renovate, Remodel, FHS/ADA, etc.",{"$nulls":5},5570995,5570995]
[null,"Carwise Middle, New Constr, Maintenance",{"$nulls":5},1368944,1368944]
[null,"Oldsmar Elem, New Constr, Maintenance",{"$nulls":5},1464596,1464596]
[null,"Sawgrass Lakes Elem, New Cons, Remdl, FHS/ADA, etc",{"$nulls":5},894951,894951]
[null,"Disston SED Center, New Constr, Site, Maintenance",{"$nulls":5},3398642,3398642]
[null,"Fairmount Park Elem, New Constr, Remodel, etc.",{"$nulls":5},3294911,3294911]
[null,"Tarpon Springs Middle, New Constr, Site, Maintenance",{"$nulls":5},3263030,3263030]
[null,"Bardmoor Elem, New Constr, Remodel, etc.",{"$nulls":5},7733902,7733902]
[null,"Ponce De Leon Elem, New Constr, Remdl, FHS/ADA, etc.",{"$nulls":5},5527492,5527492]
[null,"High Point Elem, Remodel, FHS/ADA, Maintenance",{"$nulls":5},4219323,4219323]
[null,"Coachman Fund Middle, New Constr, Remodel, Site, etc.",{"$nulls":5},2544856,2544856]
[null,"Pinellas Park Elem, Site, Maintenance",{"$nulls":5},948000,948000]
[null,"Mildred Helms Elem, New Constr, Remodel, Site, etc.",{"$nulls":5},3398806,3398806]
[null,"Walter Pownall Service Center, Remodel, Site, FHS/ADA, Maint.",{"$nulls":5},2211100,2211100]
[null,"Woodlawn Elem, Site, Maintenance",{"$nulls":5},1898500,1898500]
[null,"Northwest Elem, Remodel, FHS/ADA, Maintenance",{"$nulls":5},859227,859227]
[null,"Fuguitt Elem, Site, New Constr, Remodel, etc.",{"$nulls":5},1136068,1136068]
[null,"Safety Harbor Elem, New Cons, Renovate, Remdl, etc.",{"$nulls":5},2358532,2358532]
[null,"Gulf Beaches Elem, New Constr, Remodel, Site, etc.",{"$nulls":5},1288107,1288107]
[null,"Clearwater Discovery, New Constr, Maintenance",{"$nulls":5},854600,854600]
[null,"Lealman Elem, Remodel, FHS/ADA, Maintenance",{"$nulls":5},1862005,1862005]
[null,"Seminole Vo Ed, New Const, Renov, Remodel, etc.",{"$nulls":5},7653793,7653793]
[null,"Highland Lakes Elem, New Constr, Maintenance",{"$nulls":5},943855,943855]
[null,"Lakewood High, New Const, Remodel, Maint., etc.",{"$nulls":5},3521506,3521506]
[null,"Lakeview Fund Elem, Renovate, FHS/ADA, Maintenance",{"$nulls":5},2912198,2912198]
[null,"Cleveland Street Bus Compound, Remodel, Maintenance, FHS/ADA",{"$nulls":5},1439444,1439444]
[null,"Lealman Bus Compound, Site, Maintenance",{"$nulls":5},255625,255625]
[null,"Safety Harbor IBIS Center, Renovate, Site, FHS/ADA, Maint.",{"$nulls":5},2060806,2060806]
[null,"Forty-Ninth Street Bus Compound, Remodel, Maintenance, FHS/ADA",{"$nulls":5},1520611,1520611]
[null,"Administration, Remodeling, etc.",{"$nulls":5},13137,13137]
[null,"PTEC St Pete, Site, Maintenance",{"$nulls":5},782800,782800]
[null,"Bay Vista Elem, Remodeling, Maintenance, etc.",{"$nulls":5},2637360,2637360]
["7.","PINELLAS Total",null,0,0,0,0,189171713,189171713]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 1999."]
[]
[null,"SCHOOL BOARD OF ","PINELLAS  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}