{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","2003-04_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"2003-04_5YrWkPlan","index":1,"n_rows":1131,"n_cols":16,"rows_kept":1131,"cut":false,"hidden":false,"merged":[[1,0,1,8]],"flags":["formulas_cached_only"]}
[]
["POLK  SCHOOL DISTRICT - - TENTATIVE FACILITIES WORK PROGRAM"]
["POLK   SCHOOL  DISTRICT - -  WORKSHEET ",{"$nulls":7},"Last Revised"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the Office of Educational Facilities, and a copy submitted ",{"$nulls":7},"2004-06-16"]
["electronically in digital format, as you received it (not a fax), prior to November 1, 2004, and all data accurate as of July 15, 2004."]
["District: ====>",null,"POLK","Date: ==>","2004-10-15",null,"For fiscal years","  2004-2005 through 2008-2009"]
[]
["Section 1013.35 School district facilities 5 - Year work program; definitions; preparation, adoption, and amendment."]
[]
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["2b1","A schedule of major repair and renovation projects necessary to maintain the educational facilities and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Add a canopy for car riders as well as a roof over the concreted area in the back of the lunchroom to cover Friendship Square.","Alta Vista El",40000,{"$nulls":4},40000]
[null,"Covered Pavilion","Alturas El",65000,{"$nulls":4},65000]
[null,"Canopy from wings 1-4","Auburndale Central ",30000,{"$nulls":4},30000]
[null,"Install fence (227' of 8' fence w/ 2 double drive gates)","Auburndale HS",3200,{"$nulls":4},3200]
[null,"Remove carpet and install new carpet in media center.","Auburndale HS",12000,{"$nulls":4},12000]
[null,"Install 2 small metal storage shed buildings (1) beside the covered area behind the safety building and (2) behind the lunchroom near the double doors into the lunchroom. ($12,600 each)","Babson Park El",25200,{"$nulls":4},25200]
[null,"Concrete area under trees by covered area and replace old wooden benches with new aluminum benches.","Babson Park El",5000,{"$nulls":4},5000]
[null,"Replace carpet in Administration.  Replace carpet to tile in classrooms (Rms. 025, 024, 222A, 222B).","Bartow Acad",12000,{"$nulls":4},12000]
[null,"Build Large Storage Shed","Bartow HS",50000,{"$nulls":4},50000]
[null,"Replace 10 toilet stall partitions in mens and womens restroom of gym lobby","Bartow HS",6000,{"$nulls":4},6000]
[null,"Replace 8 shower stalls that are beyond repair in the girls locker room","Bartow MS",4000,{"$nulls":4},4000]
[null,"Rekey entire school to Primus system","Bethune Acad",15000,{"$nulls":4},15000]
[null,"Finish Clinic","Boone MS",50000,{"$nulls":4},50000]
[null,"Remodel gang restrooms by Room 1, Room 15, Room 16 (old building).","Boone MS",45000,{"$nulls":4},45000]
[null,"New  Kindergarten play area and equipment","Boswell El",60000,{"$nulls":4},60000]
[null,"Install 2 course retaining with concrete slab","Brigham Acad",8000,{"$nulls":4},8000]
[null,"Install blinds throughout school","Caldwell El",14000,{"$nulls":4},14000]
[null,"Add stage lights","Cleveland Court El",6000,{"$nulls":4},6000]
[null,"Install subfeed panel with tvss protection off of main services.  Install branch circuits to handle load of 24 combuter stations.","Combee El",4400,{"$nulls":4},4400]
[null,"Fabricate and install FISH numbers on all rooms in all schools","Countywide",50000,{"$nulls":4},50000]
[null,"Removal paint from all windows or replace all windows","Crystal Lake El",10000,{"$nulls":4},10000]
[null,"Locate and provide area  for kiln","Crystal Lake El",6000,{"$nulls":4},6000]
[null,"Men's/Women's restroom facilities in the cafetorium","Davenport School of the Arts",40000,{"$nulls":4},40000]
[null,"Replace carpet in Media Center","Denison MS",5500,{"$nulls":4},5500]
[null,"Parking Lot Landscaping","Dixieland El",10000,{"$nulls":4},10000]
[null,"Build a new shade house on the west side of the campus.","Doris Sanders LC",20000,{"$nulls":4},20000]
[null,"Redo Bus Area to provide additional covered concrete area with benches for students waiting for the bus","Eagle Lake El",5000,{"$nulls":4},5000]
[null,"Covered Pavilion","Eagle Lake El",65000,{"$nulls":4},65000]
[null,"Re-Key School","East Area Adult",10000,{"$nulls":4},10000]
[null,"Install new 16 heat pump units in classrooms and remove old units","Elbert El",40000,{"$nulls":4},40000]
[null,"Resurface PE court and repair running track area","Floral Avenue El",25000,{"$nulls":4},25000]
[null,"Replace wooden storage racks in storeroom of cafeteria with metal racks.","Fort Meade MSHS",20000,{"$nulls":4},20000]
[null,"Upgrade and replace sound board and light board in Fine Arts Auditorium.","Fort Meade MSHS",60000,{"$nulls":4},60000]
[null,"Install new fresh air makeup for kitchen to stop all the cold air from being sucked out of the cafeteria","Frostproof El",16000,{"$nulls":4},16000]
[null,"Resurface blacktop in PE area and repaint lines for courts.","Gause Riverside Acad",20000,{"$nulls":4},20000]
[null,"Fix drainage problem in hallway by teacher's lounge area.","Gause Riverside Academy",5000,{"$nulls":4},5000]
[null,"Install blinds","George Jenkins HS",2710,{"$nulls":4},2710]
[null,"Install blinds","George Jenkins HS",4870,{"$nulls":4},4870]
[null,"Install a light post in area between buildings 4 and the Band room (rose garden area)","George Jenkins HS",3000,{"$nulls":4},3000]
[null,"Replace cracked panels and repaint school's marquee","George Jenkins HS",3000,{"$nulls":4},3000]
[null,"Replace classroom doors and locks in building #1 and #3.","Gibbons Street El",30000,{"$nulls":4},30000]
[null,"Remodel Gang Restrooms","Griffin El",60000,{"$nulls":4},60000]
[null,"Add canopy over sidewalk from media center to Donovan Jones bldg.","Highland City El",50000,{"$nulls":4},50000]
[null,"Replace two AC units in Bldg. 12","Highland City El",6000,{"$nulls":4},6000]
[null,"Add PE storage area by playground","Hillcrest El",8000,{"$nulls":4},8000]
[null,"Covered Pavilion","Inwood El",65000,{"$nulls":4},65000]
[null,"Remove Comp Lab from media center A/C, Install 5 ton unit for lab only, replace media A/C with 10 ton heat pump","Janie Howard Wilson El",20000,{"$nulls":4},20000]
[null,"Portico at Bus Loading Area","Karen M. Siegel Acad",30000,{"$nulls":4},30000]
[null,"Expand PE building to house equipment and ultimately a bathroom facility for the students.","Kathleen El",6000,{"$nulls":4},6000]
[null,"Install retractable goals","Kathleen HS",15000,{"$nulls":4},15000]
[null,"Build or provide a storage area for custodial supplies and /or furniture and equipment.","Kingsford El",6000,{"$nulls":4},6000]
[null,"Replace green wallboard installed in 1978 with dry wall inside rooms 1-4, 9-12, & 17-20 and the green wallboard outside the interior doors of these same rooms.","Lake Alfred El",80000,{"$nulls":4},80000]
[null,"Repair Gymnasium bleachers ","Lake Gibson HS",6000,{"$nulls":4},6000]
[null,"Recarpet band room","Lake Gibson MS",6300,{"$nulls":4},6300]
[null,"Replace folding wall with permanent wall between CR 132/133","Lake Gibson MS",10000,{"$nulls":4},10000]
[null,"Install sink and toilet in the softball locker room ","Lake Region HS",5000,{"$nulls":4},5000]
[null,"Storage","Lake Shipp El",6000,{"$nulls":4},6000]
[null,"Resurface auditorium stage floor, replace curtains and PA system","Lake Wales HS",40000,{"$nulls":4},40000]
[null,"Install sound-proofing material within boys' & girls' locker rooms","Lakeland Highlands MS",20000,{"$nulls":4},20000]
[null,"Parking Lot Landscaping","Lawton Chiles MA",15000,{"$nulls":4},15000]
[null,"Install 3 ton Marvair Scholar heat pump A/C unit ","Lawton Chiles MA",7500,{"$nulls":4},7500]
[null,"Create opening/install door from art room to supply room","Lena Vista El",3000,{"$nulls":4},3000]
[null,"Install tile on stage floor","Lena Vista El",2500,{"$nulls":4},2500]
[null,"Covered Pavilion","Lewis El",65000,{"$nulls":4},65000]
[null,"Rekey school to Primus system","Loughman Oaks El",10000,{"$nulls":4},10000]
[null,"Install benches at the bus loading area and around campus.","Loughman Oaks El",10000,{"$nulls":4},10000]
[null,"Install lift or elevator to provide wheelchair access to second floor auditorium. ","Medulla El",80000,{"$nulls":4},80000]
[null,"Replace carpet in band room","Mulberry HS",10000,{"$nulls":4},10000]
[null,"Covered Pavilion","North Lakeland El",65000,{"$nulls":4},65000]
[null,"Covered Pavilion","Oscar J. Pope El",65000,{"$nulls":4},65000]
[null,"Replace toilets in the current Kindergarten wing with toilets of the appropriate size for an early childhood wing.","Polk Avenue El",8000,{"$nulls":4},8000]
[null,"Window replacement","Polk City El",60000,{"$nulls":4},60000]
[null,"Replace floor, quarry tile, in cafeteria with vinyl tile.","Ridge Tech",16000,{"$nulls":4},16000]
[null,"Repair/replace stage floor","RochelleSchool of the Arts",6000,{"$nulls":4},6000]
[null,"Rekey the school","Roosevelt Acad",20000,{"$nulls":4},20000]
[null,"Install Smithbuilt shed for PE Storage","Sandhill El",6000,{"$nulls":4},6000]
[null,"Resurface the PE Play area with a smooth surface. (Like Sikes Elem.)","Scott Lake El",20000,{"$nulls":4},20000]
[null,"Install handicap lift for access to stage in auditorium","Snively El",20000,{"$nulls":4},20000]
[null,"Covered Pavilion","Snively El",65000,{"$nulls":4},65000]
[null,"Install blinds","Southwest MS",7000,{"$nulls":4},7000]
[null,"Install blinds","Southwest MS",4122,{"$nulls":4},4122]
[null,"Surface bike rack area","Stephens El",10000,{"$nulls":4},10000]
[null,"Covered Pavilion","Stephens El",65000,{"$nulls":4},65000]
[null,"Add addition to metal tire storage area.","Support Services / Transportation / Bartow Bus Garage",10000,{"$nulls":4},10000]
[null,"Install blinds","Traviss Tech ",1992,{"$nulls":4},1992]
[null,"Install blinds","Traviss Tech ",2232,{"$nulls":4},2232]
[null,"Re-carpet Bandroom","Union Acad",10000,{"$nulls":4},10000]
[null,"Replace hallway entrance doors and frame, including side lights and top light.  Replace wood frame with metal.","Union Acad",7000,{"$nulls":4},7000]
[null,"Replace carpet in Main Office and Media Center. Building 1.","Valleyview El",9000,{"$nulls":4},9000]
[null,"Install cubbies for backpack storage at east entrance of cafeteria","Wahneta El",10000,{"$nulls":4},10000]
[null,"Covered Pavilion","Wahneta El",65000,{"$nulls":4},65000]
[null,"Repair the overhang on the walkway to the shop, self-contained ESE classroom, and ag area.","Westwood MS",30000,{"$nulls":4},30000]
[null,"Covered Pavilion","Winston El",65000,{"$nulls":4},65000]
["2b1","POLK Total",null,2195526,0,0,0,0,2195526]
[]
["2b2","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Alta Vista Ele - 8 Classrooms (CR) & PE Storage",null,1420000,{"$nulls":4},1420000]
[null,"Bethune Acad - 6 classroom and playfield",null,1150000,{"$nulls":4},1150000]
[null,"Lake Alfred Ele - 12 classrooms including art/music.",null,2200000,{"$nulls":4},2200000]
[null,"Lime St. Ele -  12 classrooms, 4 for ESE units and 8 for regular students ",null,2100000,{"$nulls":4},2100000]
[null,"Lincoln Acad. - 10 classrooms including art/music",null,1750000,{"$nulls":4},1750000]
[null,"Loughman Oaks Ele - 8 Classrooms/New Playcourt",null,1500000,{"$nulls":4},1500000]
[null,"Pinewood Ele - 10 classrooms (Bldg. 6)",null,1750000,{"$nulls":4},1750000]
[null,"Rochelle School of Arts - 20 classrooms (two story) ",null,3500000,{"$nulls":4},3500000]
[null,"Spook Hill Ele - 8 classrooms",null,1400000,{"$nulls":4},1400000]
[null,"New Elementary \"H\" (Poinciana)",null,13000000,{"$nulls":4},13000000]
[null,"Bartow Acad - 6 classrooms including art/music",null,1150000,{"$nulls":4},1150000]
[null,"Brigham Ele - 6 classrooms ",null,1050000,{"$nulls":4},1050000]
[null,"Churchwell Ele - 12 classrooms including art/music",null,2100000,{"$nulls":4},2100000]
[null,"Jewett Ele - 8 classrooms",null,1400000,{"$nulls":4},1400000]
[null,"Kathleen Ele - 10 classrooms including art/music",null,1850000,{"$nulls":4},1850000]
[null,"Kingsford Ele - 8 classrooms/land",null,1500000,{"$nulls":4},1500000]
[null,"Southwest Ele - 10 classrooms including art/music",null,1850000,{"$nulls":4},1850000]
[null,"Stephens Ele - 8 classrooms",null,1400000,{"$nulls":4},1400000]
[null,"New Elementary \"I\" (North Lakeland)",null,14000000,{"$nulls":4},14000000]
[null,"New Elementary \"J\" (South Lakeland)",null,14000000,{"$nulls":4},14000000]
[null,"New High School \"BBB\" (NE Lakeland)",null,42000000,{"$nulls":4},42000000]
[null,"New Middle School \"CC\" (Lakeland)",null,24000000,{"$nulls":4},24000000]
[null,"Bartow Middle - Remodel Bldg. 1 (4 classrooms, resources, chorus, home ec.)",null,53000,{"$nulls":4},53000]
[null,"Auburndale Central - Two Story Classroom addition and Demo Bldgs. 1-5, 7 & 10 ",null,null,5650000,null,null,null,5650000]
[null,"Carton Palmore Ele - 8 classrooms including art/music ",null,null,1500000,null,null,null,1500000]
[null,"Crystal Lake Ele - 6 classrooms including art/music plus media",null,null,1050000,null,null,null,1050000]
[null,"Davenport Ele - 16 clasrooms",null,null,2800000,null,null,null,2800000]
[null,"Dr. N. E. Roberts Ele - 8 classrooms",null,null,1400000,null,null,null,1400000]
[null,"Elbert Ele - 6 classrooms plus media",null,null,1800000,null,null,null,1800000]
[null,"Hillcrest Ele - 4 classrooms",null,null,700000,null,null,null,700000]
[null,"Janie Howard Wilson Ele - 6 classroom addition including art/music",null,null,1150000,null,null,null,1150000]
[null,"Medulla Ele - 6 classrooms",null,null,1050000,null,null,null,1050000]
[null,"Snively Ele - 6 classrooms",null,null,1050000,null,null,null,1050000]
[null,"Ben Hill Briffin Ele - 8 classrooms",null,null,1400000,null,null,null,1400000]
[null,"Combee Ele - 8 classrooms including art, music & computer lab",null,null,1050000,null,null,null,1050000]
[null,"Gause Acad - 12 classrooms",null,null,2100000,null,null,null,2100000]
[null,"Highland City Ele - 10 classrooms/playcourt",null,null,1850000,null,null,null,1850000]
[null,"Jesse Keen Ele - 8 classrooms",null,null,1400000,null,null,null,1400000]
[null,"Lawton Chiles Acad - 8 classrooms",null,null,1400000,null,null,null,1400000]
[null,"R. Bruce Wagner Ele - 8 classrooms",null,null,1400000,null,null,null,1400000]
[null,"Ridgeview Global Acad - 6 classrooms",null,null,1050000,null,null,null,1050000]
[null,"Sandhill Ele - 6 classrooms",null,null,1050000,null,null,null,1050000]
[null,"Socrum Ele - 10 classrooms/land",null,null,2300000,null,null,null,2300000]
[null,"Boone Middle - 10 classrooms plus Agri/Science",null,null,2500000,null,null,null,2500000]
[null,"Berkley Ele - Construct remaining classroom wing",null,null,null,1750000,null,null,1750000]
[null,"Crystal Lake Middle - 8 classrooms",null,null,null,1400000,null,null,1400000]
[null,"Kathleen High - Classroom addition",null,null,null,4550000,null,null,4550000]
[null,"Mulberry Middle - 12 classroom addition (Art, Chorus, Comp. Lab & Resource)",null,null,null,2200000,null,null,2200000]
[null,"Polk Ave. Ele - 4 classrooms including art/music",null,null,null,850000,null,null,850000]
[null,"Sleepy Hill Middle - 10 classrooms for ESE",null,null,null,1800000,null,null,1800000]
[null,"Southwest Middle - 6 classroom addition",null,null,null,1050000,null,null,1050000]
[null,"Lake Wales High - New Home Ec. Suite",null,null,null,1300000,null,null,1300000]
[null,"New Elementary School \"K\" - South Lakeland/Mulberry",null,null,null,14000000,null,null,14000000]
[null,"New Elementary School \"L\" - Northeast Polk County",null,null,null,14000000,null,null,14000000]
[null,"Westwood Middle - 6 classroom addition including art",{"$nulls":5},1050000,1050000]
["2b2","POLK Total",null,136123000,35650000,42900000,0,1050000,215723000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2b2a","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2004-05 FISH Satisfactory","Actual 2004-05","Actual 2003-04","Actual 2004-05","New Stu Capacity to","Projected 2008-09","Projected 2008-09"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Alta Vista Elementary",978,978,746,0.76,-198,820.6,1.05]
[null,"Alturas Elementary",331,331,257,0.78,-36,282.70000000000005,0.96]
[null,"Anna Woodbury Elementary","(See Lewis Anna Woodbury)",{"$nulls":4},0]
[null,"Auburndale Central Elementary",520,520,359,0.69,33,394.90000000000003,0.71]
[null,"Auburndale High",2282,2167,1767,0.82,-150,1943.7,0.96]
[null,"Babson Park Elementary",562,562,486,0.86,null,534.6,0.95]
[null,"Bartow Academy",395,395,383,0.97,108,421.3,0.84]
[null,"Bartow Middle",1501,1350,842,0.62,17,926.2,0.68]
[null,"Bartow High",2226,2114,1186,0.56,null,1304.6000000000001,0.62]
[null,"Ben Hill Griffin Elementary",724,724,390,0.54,144,429.00000000000006,0.49]
[null,"Berkley Elementary",634,634,567,0.89,144,623.7,0.8]
[null,"Bethune Academy",480,480,427,0.89,108,469.70000000000005,0.8]
[null,"Bill Duncan Opportunity Center",315,315,241,0.77,null,265.1,0.84]
[null,"Brigham Academy",728,728,572,0.79,108,629.2,0.75]
[null,"Carlton Palmore Elementary",784,784,634,0.81,41,697.4000000000001,0.85]
[null,"Clarence Boswell Elementary",779,779,503,0.65,null,553.3000000000001,0.71]
[null,"Cleveland Court Elementary",232,232,505,2.18,-18,555.5,2.6]
[null,"Combee Elementary",862,862,624,0.72,15,686.4000000000001,0.78]
[null,"Crystal Lake Elementary",817,817,640,0.78,-108,704,0.99]
[null,"Crystal Lake Middle",1406,1265,944,0.75,120,1038.4,0.75]
[null,"Davenport Elementary",693,693,523,0.75,230,575.3000000000001,0.62]
[null,"Denison Middle",1376,1238,992,0.8,null,1091.2,0.88]
[null,"Discovery Academy at LK Alfred",1409,1268,879,0.69,null,966.9000000000001,0.76]
[null,"Dixieland Elementary",502,502,463,0.92,-18,509.30000000000007,1.05]
[null,"Donald E Woods Center",174,174,218,1.25,null,239.8,1.38]
[null,"Doris A Sanders Learning Center",106,106,110,1.04,null,121.00000000000001,1.14]
[null,"Dr. N. E. Roberts Elementary ",918,918,753,0.82,144,828.3000000000001,0.78]
[null,"Dundee Elementary",1356,1356,495,0.37,-638,544.5,0.76]
[null,"Dundee Ridge Middle",1562,1405,1014,0.72,null,1115.4,0.79]
[null,"Dwight C Smith Center",237,237,121,0.51,null,133.10000000000002,0.56]
[null,"Eagle Lake Elementary",960,960,641,0.67,-54,705.1,0.78]
[null,"Eastside Elementary",1124,1124,823,0.73,null,905.3000000000001,0.81]
[null,"Edgar L Padgett Elementary",948,948,600,0.63,23,660,0.68]
[null,"Elbert Elementary",750,750,497,0.66,38,546.7,0.69]
[null,"Floral Avenue Elementary",828,828,567,0.68,-36,623.7,0.79]
[null,"Fort Meade Middle Senior High",1354,1254,775,0.62,null,852.5000000000001,0.68]
[null,"Fred G Garner Elementary",974,974,537,0.55,-18,590.7,0.62]
[null,"Frostproof Elementary",706,706,392,0.56,null,431.20000000000005,0.61]
[null,"Frostproof Middle Senior High",1962,1765,1168,0.66,null,1284.8000000000002,0.73]
[null,"Fruitland Park Learning Center",242,242,101,0.42,-68,111.10000000000001,0.64]
[null,"Garden Grove Elementary",848,848,754,0.89,null,829.4000000000001,0.98]
[null,"Gause Academy of Applied Tech",809,728,300,0.41,128,330,0.39]
[null,"George Jenkins High",2261,2147,2013,0.94,-442,2214.3,1.3]
[null,"Gibbons Street Elementary",526,526,346,0.66,-31,380.6,0.77]
[null,"Griffin Elementary",738,738,539,0.73,-156,592.9000000000001,1.02]
[null,"Haines City High",3119,2963,2010,0.68,-1315,2211,1.34]
[null,"Harrison Arts Center",201,140,150,1.07,null,165,1.18]
[null,"Highland City Elementary",571,571,464,0.81,134,510.40000000000003,0.72]
[null,"Hillcrest Elementary",791,791,577,0.73,-98,634.7,0.92]
[null,"Homer K Addair Career Academy",936,936,368,0.39,null,404.8,0.43]
[null,"Inwood Elementary",506,506,513,1.01,-54,564.3000000000001,1.25]
[null,"J Daniel Jenkins Academy",646,581,338,0.58,null,371.8,0.64]
[null,"James E Stephens Elementary",631,631,543,0.86,69,597.3000000000001,0.85]
[null,"James W Sikes Elementary",1130,1130,675,0.6,-222,742.5000000000001,0.82]
[null,"Janie Howard Wilson Elementary",880,880,585,0.66,27,643.5,0.71]
[null,"Jere L Stambaugh Middle",1354,1218,955,0.78,null,1050.5,0.86]
[null,"Jesse Keen Elementary",868,868,552,0.64,-151,607.2,0.85]
[null,"Jewett School of the Arts",996,896,739,0.82,35,812.9000000000001,0.87]
[null,"Jewett Middle Academy",890,801,578,0.72,null,635.8000000000001,0.79]
[null,"John Snively Elementary",707,707,465,0.66,-108,511.50000000000006,0.85]
[null,"Kathleen Elementary",670,670,544,0.81,114,598.4000000000001,0.76]
[null,"Kathleen Middle",1256,1130,790,0.7,16,869.0000000000001,0.76]
[null,"Kathleen High",1929,1832,1493,0.81,509,1642.3000000000002,0.7]
[null,"Kingsford Elementary",690,690,483,0.7,15,531.3000000000001,0.75]
[null,"Lake Alfred Elementary",681,681,464,0.68,107,510.40000000000003,0.65]
[null,"Lake Gibson Middle",1460,1314,1088,0.83,null,1196.8000000000002,0.91]
[null,"Lake Gibson High",2223,2111,1676,0.79,1,1843.6000000000001,0.87]
[null,"Lake Region High",2289,2174,1938,0.89,-235,2131.8,1.1]
[null,"Lake Shipp Elementary",833,833,601,0.72,null,661.1,0.79]
[null,"Lake Wales High",1987,1887,1349,0.71,null,1483.9,0.79]
[null,"Lakeland Highlands Middle",1362,1225,1081,0.88,-270,1189.1000000000001,1.25]
[null,"Lawton Chiles Middle Academy",756,680,565,0.83,176,621.5,0.73]
[null,"Lakeland High ",2536,2409,2123,0.88,null,2335.3,0.97]
[null,"Lena Vista Elementary",1011,1011,688,0.68,-18,756.8000000000001,0.76]
[null,"Lewis/Anna Woodbury ",1199,1199,1184,0.99,-90,1302.4,1.17]
[null,"Lime Street Elementary",617,617,546,0.88,112,600.6,0.82]
[null,"Lincoln Academy",527,527,492,0.93,159,541.2,0.79]
[null,"Loughman Oaks Elementary",920,920,815,0.89,78,896.5000000000001,0.9]
[null,"Traviss Vocational Technical Center",1097,1316,930,0.71,null,1023.0000000000001,0.78]
[null,"Mckeel Academy",1315,1183,944,0.8,null,1038.4,0.88]
[null,"McLaughlin Middle",1569,1412,888,0.63,null,976.8000000000001,0.69]
[null,"Medulla Elementary",987,987,693,0.7,31,762.3000000000001,0.75]
[null,"Mulberry Middle",1127,1014,820,0.81,176,902.0000000000001,0.76]
[null,"Mulberry High ",1402,1261,887,0.7,null,975.7,0.77]
[null,"North Lakeland Elementary",972,972,693,0.71,-243,762.3000000000001,1.05]
[null,"Oscar J Pope Elementary",975,975,382,0.39,-18,420.20000000000005,0.44]
[null,"Pinewood Elementary",634,634,580,0.91,180,638,0.78]
[null,"Polk Avenue Elementary",752,752,452,0.6,5,497.20000000000005,0.66]
[null,"Polk City Elementary",790,790,534,0.68,-36,587.4000000000001,0.78]
[null,"Polk Life and Learning Center",148,148,52,0.35,null,57.2,0.39]
[null,"Purcell Elementary",604,604,452,0.75,-213,497.20000000000005,1.27]
[null,"R. Bruce Wagner Elementary",956,956,672,0.7,144,739.2,0.67]
[null,"R Clem Churchwell Elementary",778,778,586,0.75,148,644.6,0.7]
[null,"Ridge Vocational Technical Center",848,1017,706,0.69,null,776.6,0.76]
[null,"Ridgeview Elementary",862,862,715,0.83,108,786.5000000000001,0.81]
[null,"Rochelle School of the Arts",1029,926,791,0.85,306,870.1,0.71]
[null,"Roosevelt Academy",281,281,343,1.22,null,377.3,1.34]
[null,"Rosabelle W Blake Elementary",861,861,583,0.68,null,641.3000000000001,0.74]
[null,"Sandhill Elementary",958,958,944,0.99,12,1038.4,1.07]
[null,"Scott Lake Elementary",1008,1008,865,0.86,-100,951.5000000000001,1.05]
[null,"Shelley S Boone Middle",1373,1235,1043,0.84,16,1147.3000000000002,0.92]
[null,"Sleepy Hill Middle",1532,1378,1058,0.77,147,1163.8000000000002,0.76]
[null,"Socrum Loop Elementary",803,803,602,0.75,180,662.2,0.67]
[null,"Southwest Elementary",628,628,499,0.79,173,548.9000000000001,0.69]
[null,"Southwest Middle",1399,1259,953,0.76,-132,1048.3000000000002,0.93]
[null,"Spook Hill Elementary",763,763,522,0.68,20,574.2,0.73]
[null,"Union Academy",586,527,404,0.77,null,444.40000000000003,0.84]
[null,"Valleyview Elementary",1163,1163,1125,0.97,-107,1237.5,1.17]
[null,"Wahneta Elementary",708,708,565,0.8,-144,621.5,1.1]
[null,"Walter Caldwell Elementary",797,797,688,0.86,null,756.8000000000001,0.95]
[null,"Wendell Watson Elementary",875,875,761,0.87,null,837.1,0.96]
[null,"Westwood Middle",1526,1373,1005,0.73,-132,1105.5,0.89]
[null,"Winston Elementary",869,869,597,0.69,-129,656.7,0.89]
[null,"Winter Haven High",2066,1962,1753,0.89,107,1928.3000000000002,0.93]
["2b2a","POLK Total",112132,108036,81213,0.75,-1080,89334.30000000003,0.84]
[]
["2b2a1","Necessary offsite infrastructure requirements resulting from expansions or new schools.  "]
[null,"This section should include the same project information from 2b2."]
[null,"NA"]
[]
[]
[]
["2b2b","Proposed location of planned facilities, whether those locations are consistent with the comprehensive plans of all affected local governments, and "]
[null,"recommendations for infrastructure and other improvements to land adjacent to existing facilities. Provisions of 1013.33(12), (13), and (14) and 1013.36"]
[null," must be addressed for new facilities planned within the 1st 3 years  of the plan"]
[null,"Consistent with Comp Plan?","Description"]
[null,"Yes","Elementary H - Poinciana or East Polk"]
[null,"Yes","Elementary I - Northwest Lakeland"]
[null,"Yes","Elementary J - Southeast Lakeland"]
[null,"Yes","BBB High - Northeast Lakeland"]
[null,"Yes","CCC High - Northeast Lakeland"]
[]
[{"$nulls":6},"# of Units","Projected "]
["2b2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2004-05","Owner","Student Stations","as classroom space","in 2008-09","units by 2008-09","Column \"C\""]
[null,"AAA High School",3,"PCSB",0,0,0,3,104]
[null,"Alta Vista Elementary",11,"PCSB",272,0,3,8,117]
[null,"Alta Vista Elementary",3,"Fed",0,0,0,3,54]
[null,"Alturas Elementary",2,"PCSB",62,0,2,0,29]
[null,"Alturas Elementary",2,"Fed",0,0,0,2,13]
[null,"Anna Woodbury Elementary",1,"PCSB",21,0,0,1,12]
[null,"Anna Woodbury Elementary",1,"Fed",0,0,0,0,6]
[null,"Auburndale Central Elementary",4,"PCSB",111,0,0,4,64]
[null,"Auburndale Central Elementary",2,"Fed",0,0,0,2,12]
[null,"Auburndale High",6,"PCSB",150,0,0,6,159]
[null,"Babson Park Elementary",7,"PCSB",97,0,7,0,163]
[null,"Bartow Middle",6,"PCSB",159,0,0,6,53]
[null,"Bartow High",2,"PCSB",41,0,2,0,16]
[null,"Bill Duncan Opportunity Center",3,"PCSB",48,0,3,0,80]
[null,"Blake Elementary",1,"PCSB",18,0,1,0,16]
[null,"Boone Middle",6,"PCSB",204,0,0,6,90]
[null,"Boone Middle",2,"Fed",0,0,0,2,6]
[null,"Caldwell Elementary",5,"PCSB",68,0,5,0,106]
[null,"Carlton Palmore Elementary",5,"PCSB",103,0,0,5,63]
[null,"Churchwell Elementary",2,"PCSB",68,0,0,2,32]
[null,"Churchwell Elementary",1,"Fed",0,0,0,1,7]
[null,"Cleveland Court Elementary",1,"PCSB",0,0,0,1,8]
[null,"Combee Elementary",5,"PCSB",129,0,0,5,101]
[null,"Combee Elementary",2,"Fed",0,0,0,2,53]
[null,"Crystal Lake Elementary",4,"PCSB",129,0,0,4,51]
[null,"Crystal Lake Elementary",2,"Fed",0,0,0,2,13]
[null,"Crystal Lake Middle",2,"PCSB",56,0,0,2,12]
[null,"Davenport Elementary",1,"PCSB",58,0,0,1,15]
[null,"Davenport Elementary",2,"Fed",0,0,0,2,14]
[null,"Dixieland Elementary",4,"PCSB",78,0,4,0,95]
[null,"Dixieland Elementary",1,"Fed",0,0,0,1,6]
[null,"Don E Woods Opportunity Center",5,"PCSB",32,0,5,0,62]
[null,"Dundee Elementary",25,"PCSB",638,0,0,25,393]
[null,"Dundee Elementary",6,"Fed",0,0,0,6,96]
[null,"Eagle Lake Elementary",14,"PCSB",303,0,14,0,307]
[null,"Eagle Lake Elementary",3,"Fed",0,0,0,3,117]
[null,"East Area Adult Center",7,"PCSB",147,0,7,0,97]
[null,"Eastside Elementary",10,"PCSB",198,0,6,4,170]
[null,"Elbert Elementary",5,"PCSB",70,0,0,5,78]
[null,"Floral Avenue Elementary",6,"PCSB",225,0,6,0,187]
[null,"Floral Avenue Elementary",2,"Fed",0,0,0,2,13]
[null,"Fort Meade Middle/Senior High",4,"PCSB",38,0,4,0,107]
[null,"Frostproof Elementary",2,"PCSB",44,0,2,0,134]
[null,"Frostproof Middle/Senior High",7,"PCSB",184,0,7,0,107]
[null,"Fruitland Park Learning Center",8,"PCSB",68,0,0,8,295]
[null,"Garner Elementary",1,"PCSB",48,0,1,0,8]
[null,"Garner Elementary",1,"Fed",0,0,0,1,11]
[null,"Gause Academy",7,"PCSB",172,0,0,7,147]
[null,"George Jenkins High",15,"PCSB",442,0,0,15,172]
[null,"Gibbons Street Elementary",1,"PCSB",31,0,1,0,30]
[null,"Gibbons Street Elementary",3,"Fed",0,0,0,3,75]
[null,"Griffin Elementary",7,"PCSB",156,0,0,7,99]
[null,"Haines City High",16,"PCSB",1315,0,0,16,337]
[null,"Haines City High",30,"Williams Scottsman",0,0,0,30,275]
[null,"Highland City Elementary",2,"PCSB",46,0,0,2,21]
[null,"Hillcrest Elementary",2,"PCSB",98,0,0,2,27]
[null,"Hillcrest Elementary",2,"Fed",0,0,0,2,14]
[null,"Inwood Elementary",3,"PCSB",84,0,3,0,118]
[null,"Inwood Elementary",3,"Fed",0,0,0,3,57]
[null,"Janie Howard Wilson",2,"PCSB",81,0,0,2,29]
[null,"Janie Howard Wilson",2,"Fed",0,0,0,2,35]
[null,"Jesse Keen Elementary",5,"PCSB",151,0,0,5,82]
[null,"Jesse Keen Elementary",1,"Fed",0,0,0,1,24]
[null,"Jewett Elementary Arts",7,"PCSB",109,0,0,7,125]
[null,"Kathleen Elementary",2,"PCSB",66,0,0,2,46]
[null,"Kathleen Elementary",1,"Fed",0,0,0,1,16]
[null,"Kathleen Middle",10,"PCSB",204,0,2,8,281]
[null,"Kathleen High",5,"PCSB",141,0,0,5,75]
[null,"Kingsford Elementary",3,"PCSB",129,0,0,3,27]
[null,"Kingsford Elementary",4,"Fed",0,0,0,4,58]
[null,"Lake Alfred Elementary",7,"PCSB",109,0,0,7,150]
[null,"Lake Alfred Elementary",3,"Fed",0,0,0,3,51]
[null,"Lake Gibson Middle",5,"PCSB",95,0,5,0,67]
[null,"Lake Gibson High",16,"PCSB",399,0,0,16,333]
[null,"Lake Region High",8,"PCSB",235,0,0,8,168]
[null,"Lake Wales High",8,"PCSB",169,0,8,0,104]
[null,"Lakeland Highlands Middle",11,"PCSB",270,0,0,11,200]
[null,"Lena Vista Elementary",4,"PCSB",98,0,4,0,47]
[null,"Lena Vista Elementary",1,"Fed",0,0,0,1,6]
[null,"Lewis Elementary",3,"PCSB",138,0,3,0,60]
[null,"Lewis Elementary",4,"Fed",0,0,0,4,96]
[null,"Lime Street Elementary",5,"PCSB",104,0,0,5,78]
[null,"Lincoln Elementary Academy",2,"PCSB",21,0,0,2,44]
[null,"Loughman Oaks Elementary",3,"PCSB",66,0,0,3,31]
[null,"Mark Wilcox Center",3,"PCSB",82,0,3,0,66]
[null,"McKeel Academy",2,"PCSB",41,0,2,0,14]
[null,"McLaughlin Middle",1,"PCSB",25,0,1,0,14]
[null,"Medulla Elementary",5,"PCSB",77,0,0,5,71]
[null,"Mulberry Middle",4,"PCSB",88,0,0,4,62]
[null,"North Lakeland Elementary",11,"PCSB",243,0,0,11,231]
[null,"North Lakeland Elementary",2,"Fed",0,0,0,2,35]
[null,"Oscar J Pope Elementary",1,"Fed",18,0,0,1,29]
[null,"Padgett Elementary",9,"PCSB",193,0,0,9,111]
[null,"PEER Center",2,"PCSB",53,0,2,0,59]
[null,"Polk Avenue Elementary ",3,"PCSB",67,0,0,3,53]
[null,"Polk Avenue Elementary ",1,"Fed",0,0,0,1,29]
[null,"Polk City Elementary",1,"PCSB",68,0,1,0,7]
[null,"Polk City Elementary",2,"Fed",0,0,0,2,36]
[null,"Polk Life and Learning Center",3,"PCSB",28,0,3,0,76]
[null,"Purcell Elementary",8,"PCSB",213,0,0,8,105]
[null,"Purcell Elementary",3,"Fed",0,0,0,3,67]
[null,"Ridge Technical Center",20,"PCSB",350,0,20,0,288]
[null,"Riverside Gause Elementary",1,"PCSB",24,0,1,0,44]
[null,"Rochelle School of the Arts",3,"PCSB",54,0,0,3,14]
[null,"Roosevelt Academy",3,"PCSB",29,0,3,0,48]
[null,"Sandhill Elementary",4,"PCSB",96,0,0,4,63]
[null,"Scott Lake Elementary",4,"PCSB",100,0,0,4,58]
[null,"Sikes Elementary",10,"PCSB",222,0,0,10,137]
[null,"Sleepy Hill Middle",4,"PCSB",73,0,0,4,56]
[null,"Snively Elementary",13,"PCSB",270,0,7,6,292]
[null,"Snively Elementary",4,"Fed",0,0,0,4,52]
[null,"Southwest Elementary",2,"PCSB",7,0,0,2,31]
[null,"Southwest Middle",8,"PCSB",185,0,2,6,109]
[null,"Spook Hill Elementary",5,"PCSB",124,0,0,5,74]
[null,"Spook Hill Elementary",1,"Fed",0,0,0,1,7]
[null,"Stambaugh Middle",1,"PCSB",23,0,1,0,15]
[null,"Stephens Elementary",4,"PCSB",75,0,0,4,54]
[null,"Traviss Technical Center",7,"PCSB",197,0,8,0,161]
[null,"Traviss Technical Center",1,"Non-PCSB Owned",0,0,1,0,44]
[null,"Union Academy",2,"PCSB",20,0,2,0,47]
[null,"Valleyview Elementary",6,"PCSB",107,0,0,6,106]
[null,"Wahneta Elementary",4,"PCSB",181,0,4,0,66]
[null,"Wahneta Elementary",8,"Fed",0,0,0,8,153]
[null,"West Area Adult",6,"PCSB",158,0,6,0,95]
[null,"West Area Adult at BHS",1,"PCSB",25,0,1,0,10]
[null,"Westwood Middle",11,"PCSB",278,0,5,6,179]
[null,"Winston Elementary",2,"PCSB",129,0,0,2,74]
[null,"Winston Elementary",4,"Fed",0,0,0,4,82]
[null,"Winter Haven High",4,"PCSB",93,0,0,3,119]
["2b2c1.","POLK Total",622,null,12812,0,178,443,"Avg Age 17.52"]
[]
["2b2c1a.","Continuation of 2b2c1 - The year in which all long term (4 years or more) relocatables,listed in 2b2c1, which will be used as classrooms will meet standards"]
[null,"Location","Year"]
[null,"All portables that are listed meet the standards to be used as clasrooms.  "]
["2b2c1a.","POLK Maximum Year",0]
[]
[]
[]
["2b2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09","5 YEAR TOTAL"]
[null,"AAA High School",3,3,{"$nulls":4},3]
[null,"Alta Vista Elementary",11,null,8,1,1,1,11]
[null,"Alturas Elementary",2,null,null,1,1,null,2]
[null,"Anna Woodbury Elementary",1,null,null,1,null,null,1]
[null,"Auburndale Central",6,null,null,6,null,null,6]
[null,"Auburndale High",6,null,6,null,null,null,6]
[null,"Bartow Middle",6,{"$nulls":4},6,6]
[null,"Boone Middle",8,null,null,8,null,null,8]
[null,"Carlton Palmore Elementary",5,null,null,5,null,null,5]
[null,"Churchwell Elementary",3,null,3,null,null,null,3]
[null,"Cleveland Court Elementary",1,null,null,1,null,null,1]
[null,"Combee Elementary",7,null,7,null,null,null,7]
[null,"Crystal Lake Elementary",6,null,null,6,null,null,6]
[null,"Crystal Lake Middle",2,null,null,null,2,null,2]
[null,"Davenport Elementary",3,null,null,3,null,null,3]
[null,"Dixieland Elementary",1,null,null,1,null,null,1]
[null,"Dundee Elementary ",31,31,{"$nulls":4},31]
[null,"Eagle Lake Elementary",3,null,null,1,1,1,3]
[null,"Eastside Elementary",4,null,4,null,null,null,4]
[null,"Elbert Elementary",5,null,null,5,null,null,5]
[null,"Floral Avenue Elementary",2,null,null,null,1,1,2]
[null,"Fruitland Park Learning Ctr",8,8,{"$nulls":4},8]
[null,"Garner Elementary",1,null,null,null,1,null,1]
[null,"Gause Academy",7,null,null,7,null,null,7]
[null,"George Jenkins High",15,null,15,null,null,null,15]
[null,"Gibbons Street Elementary",3,null,null,1,1,1,3]
[null,"Griffin Elementary",7,null,null,7,null,null,7]
[null,"Haines City High",46,46,{"$nulls":4},46]
[null,"Highland City Elementary",2,null,null,2,null,null,2]
[null,"Hillcrest Elementary",4,null,null,4,null,null,4]
[null,"Inwood Elementary",3,null,null,1,1,1,3]
[null,"J. H. Wilson Elementary ",4,null,null,4,null,null,4]
[null,"Jesse Keen Elementary",6,null,null,6,null,null,6]
[null,"Jewett School of the Arts",7,null,7,null,null,null,7]
[null,"Kathleen Elementary",3,null,3,null,null,null,3]
[null,"Kathleen Middle",8,null,8,null,null,null,8]
[null,"Kathleen High",5,null,null,5,null,null,5]
[null,"Kingsford Elementary",7,null,7,null,null,null,7]
[null,"Lake Alfred Elementary",10,null,10,null,null,null,10]
[null,"Lake Gibson High",16,null,16,null,null,null,16]
[null,"Lake Region High",8,null,8,null,null,null,8]
[null,"Lakeland Highlands Middle",11,null,11,null,null,null,11]
[null,"Lena Vista Elementary",1,null,null,null,1,null,1]
[null,"Lewis Elementary",4,null,null,1,1,2,4]
[null,"Lime Street Elementary",5,null,5,null,null,null,5]
[null,"Lincoln Academy",2,null,2,null,null,null,2]
[null,"Loughman Oaks Elementary",3,null,3,null,null,null,3]
[null,"Medulla Elementary",5,null,null,5,null,null,5]
[null,"Mulberry Middle",4,null,null,null,4,null,4]
[null,"North Lakeland Elementary",13,null,null,11,1,1,13]
[null,"Oscar Pope Elementary",1,null,null,1,null,null,1]
[null,"Padgett Elementary",9,null,9,null,null,null,9]
[null,"Polk Avenue Elementary",4,null,null,null,4,null,4]
[null,"Polk City Elementary",2,null,null,1,1,null,2]
[null,"Purcell Elementary",11,null,10,1,null,null,11]
[null,"Rochelle School of the Arts",3,null,3,null,null,null,3]
[null,"Sandhill Elementary",4,null,null,4,null,null,4]
[null,"Scott Lake Elementary",4,null,null,4,null,null,4]
[null,"Sikes Elementary",10,null,8,2,null,null,10]
[null,"Sleepy Hill Middle",4,null,null,null,4,null,4]
[null,"Snively Elementary",10,null,null,6,2,2,10]
[null,"Southwest Elementary",2,null,2,null,null,null,2]
[null,"Southwest Middle",6,null,null,null,6,null,6]
[null,"Spook Hill Elementary",6,null,6,null,null,null,6]
[null,"Stephens Elementary",4,null,4,null,null,null,4]
[null,"Valleyview Elementary",6,null,null,6,null,null,6]
[null,"Wahneta Elementary",8,null,4,2,1,1,8]
[null,"Westwood Middle",6,{"$nulls":4},6,6]
[null,"Winston Elementary",6,null,null,6,null,null,6]
[null,"Winter Haven High",3,null,3,null,null,null,3]
["2b2c2.","POLK Total",443,88,172,126,34,23,443]
[]
["2b2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2004-05","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2008-09","FISH Stu. Sta.","# Years Leased "]
[null,"Haines City High",30,"Williams Scottsman",750,1,0,0,0]
[null,"Superintendent's Office",0,"Williams Scottsman",0,2,0,0,0]
["2b2c3.","POLK Total",30,null,750,3,0,0,0]
[]
["2b2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2008-09"]
[null,"Achievement Academy/CDC",20,"Achievement Acad/CDC","1997-98",89,79,10,150]
[null,"STAR Charter",6,"Early Childhood/STAR","1999-00",108,94,3,145]
[null,"ACE",1,"Cen. Fl. Speech & Hear","2000-01",15,12,5,15]
[null,"McKeel Academy",56,"PCSB","1998-99",1344,967,7,1000]
[null,"Foundation Charter",9,"Cen. Fl. Human Svcs.","1997-98",150,150,5,150]
[null,"Apple School",13,"6/Apple&4/Presbeterian","1996-97",170,154,10,254]
[null,"Hartridge Academy",10,"Annan, Inc.","2001-02",256,115,5,136]
[null,"ARC @ Lake Gibson High",12,"PCSB","2001-02",260,217,5,350]
[null,"Discovery Academy @ Lake Alfred",58,"PCSB","2001-02",1014,993,1,1014]
[null,"Ridgeview Global Studies",35,"PCSB","2001-02",850,750,5,682]
[null,"Compass Middle Charter",11,"PCSB","2002-03",275,168,3,200]
[null,"Bartow High Charter",6,"PCSB","2003-04",144,120,3,225]
[null,"McKeel Elementary Academy",21,"McKeel El. Academy","2003-04",396,396,3,396]
[null,"Berkley Charter School",40,"PCSB","2003-04",556,556,3,780]
[null,"PCC Collegiate High School",6,"Polk Community College","2004-05",210,166,3,250]
[null,"Lakeland Montessori Schoolhouse",3,"Charles Bunch","2004-05",99,66,3,130]
[null,"Oaks Middle School",4,"City of Bartow","2004-05",50,41,3,140]
[null,"Polk Avenue Elementary",34,"PCSB","2004-05",659,444,3,500]
[null,"Janie Howard Wilson",37,"PCSB","2004-05",880,600,3,669]
[null,"Hillcrest Elementary",37,"PCSB","2004-05",718,614,3,600]
[null,"Babson Park Elementary",33,"PCSB","2004-05",484,452,3,484]
[null,"Lake Wales High School",59,"PCSB","2004-05",1987,1417,3,1560]
[null,"Berkley Accelerated Middle",5,"First Bapt. Church/Aub.","2004-05",110,104,3,500]
[null,"Haines City Literacy Learning Aca",11,"PCSB","2004-05",197,162,3,500]
["2b2c4.","POLK Total",527,null,null,11021,8837,98,8837]
[]
["2b2d.","Plans approved by the school board that reduce the need for permanent student stations such as acceptable school capacity levels, redistricting, "]
[null,"busing, year-round schools, charter schools, magnet schools, public-private partnerships, multitrack scheduling, grade level organization,"]
[null," block scheduling, or other alternatives."]
[null,"NA"]
[]
[]
[]
["2b2e.","Average Class Size (5 years out -- 2008-09) that will result if the district facilities work plan is fully implemented."]
[{"$nulls":5},"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","# CLASSROOMS","Capacity (NOT Stu Sta)","2003-04 CO-FTE","2003-04 Class size","2008-09 CO-FTE","be added (removed)","2008-09 Class size"]
[null,"Alta Vista Elementary",49,978,746,15.22,820.6,-3,17.84]
[null,"Alturas Elementary",20,331,257,12.85,282.70000000000005,-2,15.71]
[null,"Anna Woodbury Elementary","See Lewis/Anna Woodbury",null,null,null,0]
[null,"Auburndale Central Elementary",36,520,359,9.97,394.90000000000003,2,10.39]
[null,"Auburndale High",103,2167,1767,17.16,1943.7,-6,20.04]
[null,"Babson Park Elementary",32,562,486,15.19,534.6,null,16.71]
[null,"Bartow Academy",20,395,383,19.15,421.3,6,16.2]
[null,"Bartow Middle",64,1350,842,13.16,926.2,2,14.03]
[null,"Bartow High",95,2114,1186,12.48,1304.6000000000001,null,13.73]
[null,"Ben Hill Griffin Elementary",39,724,390,10,429.00000000000006,8,9.13]
[null,"Berkley Elementary",34,634,567,16.68,623.7,8,14.85]
[null,"Bethune Academy",25,480,427,17.08,469.70000000000005,6,15.15]
[null,"Bill Duncan Opportunity Center",26,315,241,9.27,265.1,null,10.2]
[null,"Brigham Academy",35,728,572,16.34,629.2,6,15.35]
[null,"Carlton Palmore Elementary",39,784,634,16.26,697.4000000000001,3,16.6]
[null,"Clarence Boswell Elementary",40,779,503,12.58,553.3000000000001,null,13.83]
[null,"Cleveland Court Elementary",25,232,505,20.2,555.5,-1,23.15]
[null,"Combee Elementary",43,862,624,14.51,686.4000000000001,1,15.6]
[null,"Crystal Lake Elementary",42,817,640,15.24,704,null,16.76]
[null,"Crystal Lake Middle",58,1265,944,16.28,1038.4,6,16.23]
[null,"Davenport Elementary",43,693,523,12.16,575.3000000000001,13,10.27]
[null,"Denison Middle",65,1238,992,15.26,1091.2,null,16.79]
[null,"Discovery Academy at LK Alfred",64,1268,879,13.73,966.9000000000001,null,15.11]
[null,"Dixieland Elementary",27,502,463,17.15,509.30000000000007,-1,19.59]
[null,"Donald E Woods Center",18,174,218,12.11,239.8,null,13.32]
[null,"Doris A Sanders Learning Center",19,106,110,5.79,121.00000000000001,null,6.37]
[null,"Dr. N. E. Roberts Elementary ",44,918,753,17.11,828.3000000000001,8,15.93]
[null,"Dundee Elementary",64,1356,495,7.73,544.5,-31,16.5]
[null,"Dundee Ridge Middle",66,1405,1014,15.36,1115.4,null,16.9]
[null,"Dwight C Smith Center",30,237,121,4.03,133.10000000000002,null,4.44]
[null,"Eagle Lake Elementary",45,960,641,14.24,705.1,-3,16.79]
[null,"Eastside Elementary",55,1124,823,14.96,905.3000000000001,null,16.46]
[null,"Edgar L Padgett Elementary",43,948,600,13.95,660,3,14.35]
[null,"Elbert Elementary",36,750,497,13.81,546.7,2,14.39]
[null,"Floral Avenue Elementary",46,828,567,12.33,623.7,-2,14.18]
[null,"Fort Meade Middle Senior High",60,1254,775,12.92,852.5000000000001,null,14.21]
[null,"Fred G Garner Elementary",54,974,537,9.94,590.7,-1,11.15]
[null,"Frostproof Elementary",37,706,392,10.59,431.20000000000005,null,11.65]
[null,"Frostproof Middle Senior High",82,1765,1168,14.24,1284.8000000000002,null,15.67]
[null,"Fruitland Park Learning Center",18,242,101,5.61,111.10000000000001,-8,11.11]
[null,"Garden Grove Elementary",40,848,754,18.85,829.4000000000001,null,20.74]
[null,"Gause Academy of Applied Tech",36,728,300,8.33,330,5,8.05]
[null,"George Jenkins High",113,2147,2013,17.81,2214.3,-15,22.59]
[null,"Gibbons Street Elementary",26,526,346,13.31,380.6,-3,16.55]
[null,"Griffin Elementary",36,738,539,14.97,592.9000000000001,-7,20.44]
[null,"Haines City High",119,2963,2010,16.89,2211,-46,30.29]
[null,"Harrison Arts Center",9,140,150,16.67,165,null,18.33]
[null,"Highland City Elementary",30,571,464,15.47,510.40000000000003,8,13.43]
[null,"Hillcrest Elementary",38,791,577,15.18,634.7,null,16.7]
[null,"Homer K Addair Career Academy",44,936,368,8.36,404.8,null,9.2]
[null,"Inwood Elementary",29,506,513,17.69,564.3000000000001,-3,21.7]
[null,"J Daniel Jenkins Academy",26,581,338,13,371.8,null,14.3]
[null,"James E Stephens Elementary",36,631,543,15.08,597.3000000000001,4,14.93]
[null,"James W Sikes Elementary",54,1130,675,12.5,742.5000000000001,-2,14.28]
[null,"Janie Howard Wilson Elementary",44,880,585,13.3,643.5,2,13.99]
[null,"Jere L Stambaugh Middle",64,1218,955,14.92,1050.5,null,16.41]
[null,"Jesse Keen Elementary",45,868,552,12.27,607.2,2,12.92]
[null,"Jewett School of the Arts",48,896,739,15.4,812.9000000000001,1,16.59]
[null,"Jewett Middle Academy",34,801,578,17,635.8000000000001,null,18.7]
[null,"John Snively Elementary",37,707,465,12.57,511.50000000000006,-4,15.5]
[null,"Kathleen Elementary",34,670,544,16,598.4000000000001,7,14.6]
[null,"Kathleen Middle",54,1130,790,14.63,869.0000000000001,2,15.52]
[null,"Kathleen High",95,1832,1493,15.72,1642.3000000000002,21,14.16]
[null,"Kingsford Elementary",33,690,483,14.64,531.3000000000001,1,15.63]
[null,"Lake Alfred Elementary",32,681,464,14.5,510.40000000000003,2,15.01]
[null,"Lake Gibson Middle",72,1314,1088,15.11,1196.8000000000002,null,16.62]
[null,"Lake Gibson High",97,2111,1676,17.28,1843.6000000000001,null,19.01]
[null,"Lake Region High",106,2174,1938,18.28,2131.8,-8,21.75]
[null,"Lake Shipp Elementary",39,833,601,15.41,661.1,null,16.95]
[null,"Lake Wales High",93,1887,1349,14.51,1483.9,null,15.96]
[null,"Lakeland Highlands Middle",63,1225,1081,17.16,1189.1000000000001,1,18.58]
[null,"Lawton Chiles Middle Academy",28,680,565,20.18,621.5,8,17.26]
[null,"Lakeland High ",109,2409,2123,19.48,2335.3,null,21.42]
[null,"Lena Vista Elementary",48,1011,688,14.33,756.8000000000001,-1,16.1]
[null,"Lewis/Anna Woodbury ",56,1199,1184,21.14,1302.4,-5,25.54]
[null,"Lime Street Elementary",31,617,546,17.61,600.6,7,15.81]
[null,"Lincoln Academy",29,527,492,16.97,541.2,8,14.63]
[null,"Loughman Oaks Elementary",51,920,815,15.98,896.5000000000001,5,16.01]
[null,"Traviss Vocational Technical Center",95,1316,930,9.79,1023.0000000000001,null,10.77]
[null,"Mckeel Academy",70,1183,944,13.49,1038.4,null,14.83]
[null,"McLaughlin Middle",62,1412,888,14.32,976.8000000000001,null,15.75]
[null,"Medulla Elementary",48,987,693,14.44,762.3000000000001,1,15.56]
[null,"Mulberry Middle",49,1014,820,16.73,902.0000000000001,8,15.82]
[null,"Mulberry High ",65,1261,887,13.65,975.7,null,15.01]
[null,"North Lakeland Elementary",49,972,693,14.14,762.3000000000001,-13,21.18]
[null,"Oscar J Pope Elementary",52,975,382,7.35,420.20000000000005,-1,8.24]
[null,"Pinewood Elementary",34,634,580,17.06,638,10,14.5]
[null,"Polk Avenue Elementary",35,752,452,12.91,497.20000000000005,null,14.21]
[null,"Polk City Elementary",40,790,534,13.35,587.4000000000001,-2,15.46]
[null,"Polk Life and Learning Center",21,148,52,2.48,57.2,null,2.72]
[null,"Purcell Elementary",34,604,452,13.29,497.20000000000005,-1,15.07]
[null,"R. Bruce Wagner Elementary",44,956,672,15.27,739.2,8,14.22]
[null,"R Clem Churchwell Elementary",38,778,586,15.42,644.6,9,13.71]
[null,"Ridge Vocational Technical Center",71,1017,706,9.94,776.6,null,10.94]
[null,"Ridgeview Elementary",44,862,715,16.25,786.5000000000001,6,15.73]
[null,"Rochelle School of the Arts",49,926,791,16.14,870.1,17,13.18]
[null,"Roosevelt Academy",43,281,343,7.98,377.3,null,8.77]
[null,"Rosabelle W Blake Elementary",49,861,583,11.9,641.3000000000001,null,13.09]
[null,"Sandhill Elementary",48,958,944,19.67,1038.4,2,20.77]
[null,"Scott Lake Elementary",49,1008,865,17.65,951.5000000000001,-4,21.14]
[null,"Shelley S Boone Middle",65,1235,1043,16.05,1147.3000000000002,2,17.12]
[null,"Sleepy Hill Middle",63,1378,1058,16.79,1163.8000000000002,6,16.87]
[null,"Socrum Loop Elementary",45,803,602,13.38,662.2,10,12.04]
[null,"Southwest Elementary",31,628,499,16.1,548.9000000000001,8,14.07]
[null,"Southwest Middle",58,1259,953,16.43,1048.3000000000002,null,18.07]
[null,"Spook Hill Elementary",40,763,522,13.05,574.2,2,13.67]
[null,"Union Academy",26,527,404,15.54,444.40000000000003,null,17.09]
[null,"Valleyview Elementary",64,1163,1125,17.58,1237.5,-6,21.34]
[null,"Wahneta Elementary",37,708,565,15.27,621.5,-8,21.43]
[null,"Walter Caldwell Elementary",42,797,688,16.38,756.8000000000001,null,18.02]
[null,"Wendell Watson Elementary",49,875,761,15.53,837.1,null,17.08]
[null,"Westwood Middle",65,1373,1005,15.46,1105.5,null,17.01]
[null,"Winston Elementary",45,869,597,13.27,656.7,-6,16.84]
[null,"Winter Haven High",103,1962,1753,17.02,1928.3000000000002,5,17.85]
["2b2e.","POLK Total",5541,108036,81213,"District Avg 15",89334.30000000003,59,"District Avg 16"]
[]
["2b2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[null,"Please see attached explanation of work plan for additional details"]
[null,"Site                              ",null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09","5 YEAR AVERAGE"]
[null,"Alta Vista Elementary",null,272,128,110,92,74,135.2]
[null,"Alturas Elementary",null,62,62,44,26,26,44]
[null,"Anna Woodbury Elementary",null,21,21,0,0,0,8.4]
[null,"Auburndale Central Elementary",null,111,111,0,0,0,44.4]
[null,"Auburndale High",null,150,0,0,0,0,30]
[null,"Babson Park Elementary",null,97,97,97,97,97,97]
[null,"Bartow Middle",null,159,159,159,159,0,127.2]
[null,"Bartow High",null,41,41,41,41,41,41]
[null,"Bill Duncan Opportunity Center",null,48,48,48,48,48,48]
[null,"Blake Elementary",null,18,18,18,18,18,18]
[null,"Boone Middle",null,204,204,0,0,0,81.6]
[null,"Caldwell Elementary",null,68,68,68,68,68,68]
[null,"Carlton Palmore Elementary",null,103,103,0,0,0,41.2]
[null,"Churchwell Elementary",null,68,0,0,0,0,13.6]
[null,"Combee Elementary",null,129,0,0,0,0,25.8]
[null,"Crystal Lake Elementary",null,129,129,21,0,0,55.8]
[null,"Crystal Lake Middle",null,56,56,56,0,0,33.6]
[null,"Davenport Elementary",null,58,58,0,0,0,23.2]
[null,"Dixieland Elementary",null,78,78,60,60,60,67.2]
[null,"Don E Woods Opportunity Center",null,32,32,32,32,32,32]
[null,"Dundee Elementary",null,638,0,0,0,0,127.6]
[null,"Eagle Lake Elementary",null,303,303,285,267,249,281.4]
[null,"East Area Adult Center",null,147,147,147,147,147,147]
[null,"Eastside Elementary",null,198,126,126,126,126,140.4]
[null,"Elbert Elementary",null,70,70,0,0,0,28]
[null,"Floral Avenue Elementary",null,225,225,207,189,189,207]
[null,"Fort Meade Middle/Senior High",null,38,38,38,38,38,38]
[null,"Frostproof Elementary",null,44,44,44,44,44,44]
[null,"Frostproof Middle/Senior High",null,184,184,184,184,184,184]
[null,"Fruitland Park Learning Center",null,68,0,0,0,0,13.6]
[null,"Garner Elementary",null,48,48,30,30,30,37.2]
[null,"Gause Academy",null,172,172,0,0,0,68.8]
[null,"George Jenkins High",null,442,0,0,0,0,88.4]
[null,"Gibbons Street Elementary",null,31,31,13,0,0,15]
[null,"Griffin Elementary",null,156,156,0,0,0,62.4]
[null,"Haines City High",null,1315,0,0,0,0,263]
[null,"Highland City Elementary",null,46,46,0,0,0,18.4]
[null,"Hillcrest Elementary",null,98,98,26,8,0,46]
[null,"Inwood Elementary",null,84,84,66,48,30,62.4]
[null,"Janie Howard Wilson",null,81,81,0,0,0,32.4]
[null,"Jesse Keen Elementary",null,151,151,7,0,0,61.8]
[null,"Jewett Elementary Arts",null,109,0,0,0,0,21.8]
[null,"Kathleen Elementary",null,66,0,0,0,0,13.2]
[null,"Kathleen Middle",null,204,0,0,0,0,40.8]
[null,"Kathleen High",null,141,141,0,0,0,56.4]
[null,"Kingsford Elementary",null,129,0,0,0,0,25.8]
[null,"Lake Alfred Elementary",null,109,0,0,0,0,21.8]
[null,"Lake Gibson Middle",null,95,95,95,95,95,95]
[null,"Lake Gibson High",null,399,0,0,0,0,79.8]
[null,"Lake Region High",null,235,0,0,0,0,47]
[null,"Lake Wales High",null,169,169,169,169,169,169]
[null,"Lakeland Highlands Middle",null,270,0,0,0,0,54]
[null,"Lena Vista Elementary",null,98,98,80,80,80,87.2]
[null,"Lewis Elementary",null,138,138,120,102,66,112.8]
[null,"Lime Street Elementary",null,104,0,0,0,0,20.8]
[null,"Lincoln Elementary Academy",null,21,0,0,0,0,4.2]
[null,"Loughman Oaks Elementary",null,66,0,0,0,0,13.2]
[null,"Mark Wilcox Center",null,82,82,82,82,82,82]
[null,"McKeel Academy",null,41,41,41,41,41,41]
[null,"McLaughlin Middle",null,25,25,25,25,25,25]
[null,"Medulla Elementary",null,77,77,0,0,0,30.8]
[null,"Mulberry Middle",null,88,88,88,0,0,52.8]
[null,"North Lakeland Elementary",null,243,243,23,5,0,102.8]
[null,"Oscar J Pope Elementary",null,18,18,0,0,0,7.2]
[null,"Padgett Elementary",null,193,0,0,0,0,38.6]
[null,"PEER Center",null,53,53,53,53,53,53]
[null,"Polk Avenue Elementary ",null,67,67,67,0,0,40.2]
[null,"Polk City Elementary",null,68,68,50,32,32,50]
[null,"Polk Life and Learning Center",null,28,28,28,28,28,28]
[null,"Purcell Elementary",null,213,33,15,15,15,58.2]
[null,"Ridge Technical Center",null,350,350,350,350,350,350]
[null,"Riverside Gause Elementary",null,24,24,24,24,24,24]
[null,"Rochelle School of the Arts",null,54,54,0,0,0,21.6]
[null,"Roosevelt Academy",null,29,29,29,29,29,29]
[null,"Sandhill Elementary",null,96,96,0,0,0,38.4]
[null,"Scott Lake Elementary",null,100,100,0,0,0,40]
[null,"Sikes Elementary",null,222,78,0,0,0,60]
[null,"Sleepy Hill Middle",null,73,73,73,0,0,43.8]
[null,"Snively Elementary",null,270,270,162,126,90,183.6]
[null,"Southwest Elementary",null,7,7,7,0,0,4.2]
[null,"Southwest Middle",null,185,185,185,53,53,132.2]
[null,"Spook Hill Elementary",null,124,0,0,0,0,24.8]
[null,"Stambaugh Middle",null,23,23,23,23,23,23]
[null,"Stephens Elementary",null,75,0,0,0,0,15]
[null,"Traviss Technical Center",null,197,197,197,197,197,197]
[null,"Union Academy",null,20,20,20,20,20,20]
[null,"Valleyview Elementary",null,107,107,0,0,0,42.8]
[null,"Wahneta Elementary",null,181,109,73,55,37,91]
[null,"West Area Adult",null,158,158,158,158,158,158]
[null,"West Area Adult at BHS",null,25,25,25,25,25,25]
[null,"Westwood Middle",null,278,278,278,278,146,251.6]
[null,"Winston Elementary",null,129,129,0,0,0,51.6]
[null,"Winter Haven High",null,93,0,0,0,0,18.6]
["2b2f1","POLK Total students in relocatables by year",null,12812,7193,4467,3787,3339,6319.6]
["2b2f2","POLK Total number of CO-FTE students projected by year",null,82837,84494,86184,87908,89334,86151.4]
["2b2f3","POLK Percent in relocatables by year",null,0.15,0.09,0.05,0.04,0.04,0.07]
[]
["2b2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"NA"]
[]
[]
["2b2h.","Projects for which capital outlay and debt service funds accruing under s. 9(d), Art. XII of the State Constitution are to be used shall be identified "]
[null,"separately in priority order on a project priority list within the district faciliteis work program."]
[null,"Projects to be implementd with CO & DS funds in ranked order:"]
[null,"Project Description:"]
[null,"NA"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["2b3","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2004,2004,2004,2004,2004,2004]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,96,127,247,11269,15778,23876]
[null,"2004 State-wide totals - Gross Sq Ft per student station: Elem low 81, avg 84, high 133; Middle low 91, avg 109, high 122; High School low 76, avg 136, high 145 ",{"$nulls":7},2,107,178,329,15083,25712,50508]
[null,"2004 State-wide totals - Cost per student station: Elem low 9,561, avg 12,823, high 16,656; Middle low 13,844 avg 15,379, high 17,552; High School low 20,309, avg 23,771, high  30,365 ",{"$nulls":7},3,120,143,182,14229,21749,31693]
[]
["2b3a.","2004-05 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2004-05 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2005 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Alta Vista Ele - 8 Classrooms (CR) & PE Storage",null,1420000,144,null,0,9861.11,null,0,0,0,9861.11,0,0,0]
[null,"Bethune Acad - 6 classroom and playfield",null,1150000,108,null,0,10648.15,null,0,0,0,10648.15,0,0,0]
[null,"Lake Alfred Ele - 12 classrooms including art/music.",null,2200000,216,null,0,10185.19,null,0,0,0,10185.19,0,0,0]
[null,"Lime St. Ele -  12 classrooms, 4 for ESE units and 8 for regular students ",null,2100000,216,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Lincoln Acad. - 10 classrooms including art/music",null,1750000,180,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Loughman Oaks Ele - 8 Classrooms/New Playcourt",null,1500000,144,null,0,10416.67,null,0,0,0,10416.67,0,0,0]
[null,"Pinewood Ele - 10 classrooms (Bldg. 6)",null,1750000,180,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Rochelle School of Arts - 20 classrooms (two story) ",null,3500000,360,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Spook Hill Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"New Elementary \"H\" (Poinciana)",1,13000000,825,null,0,15757.58,null,96,96,247,15757.58,11269,15778,23876]
[null,"Bartow Acad - 6 classrooms including art/music",null,1150000,108,null,0,10648.15,null,0,0,0,10648.15,0,0,0]
[null,"Brigham Ele - 6 classrooms ",null,1050000,108,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Churchwell Ele - 12 classrooms including art/music",null,2100000,216,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Jewett Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Kathleen Ele - 10 classrooms including art/music",null,1850000,180,null,0,10277.78,null,0,0,0,10277.78,0,0,0]
[null,"Kingsford Ele - 8 classrooms/land",null,1500000,144,null,0,10416.67,null,0,0,0,10416.67,0,0,0]
[null,"Southwest Ele - 10 classrooms including art/music",null,1850000,180,null,0,10277.78,null,0,0,0,10277.78,0,0,0]
[null,"Stephens Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"New Elementary \"I\" (North Lakeland)",1,14000000,825,null,0,16969.7,null,96,96,247,16969.7,11269,15778,23876]
[null,"New Elementary \"J\" (South Lakeland)",1,14000000,825,null,0,16969.7,null,96,127,247,16969.7,11269,15778,23876]
[null,"New High School \"BBB\" (NE Lakeland)",3,42000000,1800,null,0,23333.33,null,120,120,182,23333.33,14229,21749,31693]
[null,"New Middle School \"CC\" (Lakeland)",2,24000000,1100,null,0,21818.18,null,107,107,329,21818.18,15083,25712,50508]
[null,"Bartow Middle - Remodel Bldg. 1 (4 classrooms, resources, chorus, home ec.)",null,53000,88,null,0,602.27,null,0,0,0,602.27,0,0,0]
["2b3a.","POLK Total 2004-05",null,136123000,8379,null,null,16245.73,{"$nulls":4},16245.73]
[]
["2b3b.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06 ","2005-06 ","2005-06 ","2005-06 ","2005-06 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2004 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Auburndale Central - Two Story Classroom addition and Demo Bldgs. 1-5, 7 & 10 ",null,5650000,144,null,0,39236.11,null,0,0,0,39236.11,0,0,0]
[null,"Carton Palmore Ele - 8 classrooms including art/music ",null,1500000,144,null,0,10416.67,null,0,0,0,10416.67,0,0,0]
[null,"Crystal Lake Ele - 6 classrooms including art/music plus media",null,1050000,108,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Davenport Ele - 16 clasrooms",null,2800000,288,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Dr. N. E. Roberts Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Elbert Ele - 6 classrooms plus media",null,1800000,108,null,0,16666.67,null,0,0,0,16666.67,0,0,0]
[null,"Hillcrest Ele - 4 classrooms",null,700000,72,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Janie Howard Wilson Ele - 6 classroom addition including art/music",null,1150000,108,null,0,10648.15,null,0,0,0,10648.15,0,0,0]
[null,"Medulla Ele - 6 classrooms",null,1050000,108,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Snively Ele - 6 classrooms",null,1050000,108,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Ben Hill Briffin Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Combee Ele - 8 classrooms including art, music & computer lab",null,1050000,144,null,0,7291.67,null,0,0,0,7291.67,0,0,0]
[null,"Gause Acad - 12 classrooms",null,2100000,300,null,0,7000,null,0,0,0,7000,0,0,0]
[null,"Highland City Ele - 10 classrooms/playcourt",null,1850000,180,null,0,10277.78,null,0,0,0,10277.78,0,0,0]
[null,"Jesse Keen Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Lawton Chiles Acad - 8 classrooms",null,1400000,176,null,0,7954.55,null,0,0,0,7954.55,0,0,0]
[null,"R. Bruce Wagner Ele - 8 classrooms",null,1400000,144,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Ridgeview Global Acad - 6 classrooms",null,1050000,108,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Sandhill Ele - 6 classrooms",null,1050000,108,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Socrum Ele - 10 classrooms/land",null,2300000,180,null,0,12777.78,null,0,0,0,12777.78,0,0,0]
[null,"Boone Middle - 10 classrooms plus Agri/Science",null,2500000,220,null,0,11363.64,null,0,0,0,11363.64,0,0,0]
["2b3b","POLK Total 2005-06",null,35650000,3180,null,0,11210.69,{"$nulls":4},11210.69]
[]
["2b3c.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2006-07 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2005 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Berkley Ele - Construct remaining classroom wing",null,1750000,180,null,0,9722.22,null,0,0,0,9722.22,0,0,0]
[null,"Crystal Lake Middle - 8 classrooms",null,1400000,176,null,0,7954.55,null,0,0,0,7954.55,0,0,0]
[null,"Kathleen High - Classroom addition",null,4550000,650,null,null,7000,null,0,0,0,7000,0,0,0]
[null,"Mulberry Middle - 12 classroom addition (Art, Chorus, Comp. Lab & Resource)",null,2200000,264,null,null,8333.33,null,0,0,0,8333.33,0,0,0]
[null,"Polk Ave. Ele - 4 classrooms including art/music",null,850000,72,null,null,11805.56,null,0,0,0,11805.56,0,0,0]
[null,"Sleepy Hill Middle - 10 classrooms for ESE",null,1800000,220,null,null,8181.82,null,0,0,0,8181.82,0,0,0]
[null,"Southwest Middle - 6 classroom addition",null,1050000,132,null,null,7954.55,null,0,0,0,7954.55,0,0,0]
[null,"Lake Wales High - New Home Ec. Suite",null,1300000,65,null,null,20000,null,0,0,0,20000,0,0,0]
[null,"New Elementary School \"K\" - South Lakeland/Mulberry",1,14000000,825,null,null,16969.7,null,96,127,247,16969.7,11269,15778,23876]
[null,"New Elementary School \"L\" - Northeast Polk County",1,14000000,825,null,null,16969.7,null,96,127,247,16969.7,11269,15778,23876]
["2b3c","POLK Total 2006-07",null,42900000,3409,null,0,12584.34,{"$nulls":4},12584.34]
[]
["2b3d.","2007-2008 Year","Type of School (new schools only)  Others=0","2007-08","2007-08","2007-08","2007-08","2007-08 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2006 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
["2b3d.","POLK Total 2007-08",{"$nulls":10},{"$error":"#DIV/0!"}]
[]
["2b3e","2008-2009 Year","Type of School (new schools only)  Others=0","2008-09","2008-09","2008-09","2008-09","2008-09 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2007 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Westwood Middle - 6 classroom addition including art",null,1050000,132,null,null,7954.55,null,0,0,0,7954.55,0,0,0]
["2b3e","POLK Total 2008-09",null,1050000,132,null,0,7954.55,{"$nulls":4},7954.55]
[]
["2b3f","POLK 5-Year Total",null,215723000,15100]
[]
["2b4","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.1011.71",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.1011.71",null,37994811,39894552,41889280,43983744,46182931,209945318]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,37994811,39894552,41889280,43983744,46182931,209945318,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,3468316,3727861,3914254,4109966,4315465,19535862,0.0930521441778473]
[null,"  less amount used to purchase other vehicles",null,1000000,1000000,1000000,1000000,1000000,5000000,0.0238157251975488]
[null,"  less amount transferred to op. bud for minor maint/repair projects",null,4000000,4400000,4840000,5324000,5856400,24420400,0.116317907122844]
[null,"  less amount trnsfrd to op bud for salaries assoc w/maintenance/repair projects",null,8400000,8904000,9438240,10004534,10604806,47351580,0.22554244338995]
[null,"  less amount used for minor maint/repair projects",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase capital outlay equipment",null,3385300,4500000,4500000,4500000,4500000,21385300,0.101861285613428]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,1217900,153655,12805,0,0,1384360,0.00659390746689574]
[null,"  less amount to pay debt service for COP's ",null,17523295,17419445,17426752,17443031,17446095,87258618,0.415625453481177]
[null,"  less other (please be specific) SAP Software Upgrade",null,0,0,0,1500000,0,1500000,0.00714471755926465,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,-1000000,-210409,757229,102213,2460165,2109198,0.0100464159910439,0.01]
[null,"P E C O New Construction",null,0,2632745,2658239,2718291,2718291,10727566,null,0.04]
[null,"P E C O Maintenance Dollars",null,8724048,5018971,5324202,5587811,5587811,30242843,null,0.11]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,0,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,350000,350000,350000,350000,350000,1750000,null,0.01]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,26000000,26520000,27050400,27591408,28143236,135305044,null,0.47]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,50000000,null,50000000,null,0.17]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0,null,0]
[null,"Classrooms for Kids",null,26785055,0,0,0,0,26785055,null,0.09]
[null,"District Equity Recognition",null,0,0,0,0,0,0,null,0]
[null,"Federal Grants",null,0,0,0,0,0,0,null,0]
[null,"Impact fees received",null,5821000,5937420,6056168,6177291,6300837,30292716,null,0.11]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["2b4","POLK Total",null,66680103,40248727,42196238,92527014,45560340,287212422,0.9999999999999993,1.01]
[]
["2b5","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Alta Vista Ele - 8 Classrooms (CR) & PE Storage",144,1420000,{"$nulls":4},1420000]
[null,"Bethune Acad - 6 classroom and playfield",108,1150000,{"$nulls":4},1150000]
[null,"Lake Alfred Ele - 12 classrooms including art/music.",216,2200000,{"$nulls":4},2200000]
[null,"Lime St. Ele -  12 classrooms, 4 for ESE units and 8 for regular students ",216,2100000,{"$nulls":4},2100000]
[null,"Lincoln Acad. - 10 classrooms including art/music",180,1750000,{"$nulls":4},1750000]
[null,"Loughman Oaks Ele - 8 Classrooms/New Playcourt",144,1500000,{"$nulls":4},1500000]
[null,"Pinewood Ele - 10 classrooms (Bldg. 6)",180,1750000,{"$nulls":4},1750000]
[null,"Rochelle School of Arts - 20 classrooms (two story) ",360,3500000,{"$nulls":4},3500000]
[null,"Spook Hill Ele - 8 classrooms",144,1400000,{"$nulls":4},1400000]
[null,"New Elementary \"H\" (Poinciana)",825,13000000,{"$nulls":4},13000000]
[null,"Bartow Acad - 6 classrooms including art/music",108,1150000,{"$nulls":4},1150000]
[null,"Brigham Ele - 6 classrooms ",108,1050000,{"$nulls":4},1050000]
[null,"Churchwell Ele - 12 classrooms including art/music",216,2100000,{"$nulls":4},2100000]
[null,"Jewett Ele - 8 classrooms",144,1400000,{"$nulls":4},1400000]
[null,"Kathleen Ele - 10 classrooms including art/music",180,1850000,{"$nulls":4},1850000]
[null,"Kingsford Ele - 8 classrooms/land",144,1500000,{"$nulls":4},1500000]
[null,"Southwest Ele - 10 classrooms including art/music",180,1850000,{"$nulls":4},1850000]
[null,"Stephens Ele - 8 classrooms",144,1400000,{"$nulls":4},1400000]
[null,"New Elementary \"I\" (North Lakeland)",825,14000000,{"$nulls":4},14000000]
[null,"New Elementary \"J\" (South Lakeland)",825,14000000,{"$nulls":4},14000000]
[null,"New High School \"BBB\" (NE Lakeland)",1800,42000000,{"$nulls":4},42000000]
[null,"New Middle School \"CC\" (Lakeland)",1100,24000000,{"$nulls":4},24000000]
[null,"Bartow Middle - Remodel Bldg. 1 (4 classrooms, resources, chorus, home ec.)",88,53000,{"$nulls":4},53000]
[null,"Auburndale Central - Two Story Classroom addition and Demo Bldgs. 1-5, 7 & 10 ",144,null,5650000,null,null,null,5650000]
[null,"Carton Palmore Ele - 8 classrooms including art/music ",144,null,1500000,null,null,null,1500000]
[null,"Crystal Lake Ele - 6 classrooms including art/music plus media",108,null,1050000,null,null,null,1050000]
[null,"Davenport Ele - 16 clasrooms",288,null,2800000,null,null,null,2800000]
[null,"Dr. N. E. Roberts Ele - 8 classrooms",144,null,1400000,null,null,null,1400000]
[null,"Elbert Ele - 6 classrooms plus media",108,null,1800000,null,null,null,1800000]
[null,"Hillcrest Ele - 4 classrooms",72,null,700000,null,null,null,700000]
[null,"Janie Howard Wilson Ele - 6 classroom addition including art/music",108,null,1150000,null,null,null,1150000]
[null,"Medulla Ele - 6 classrooms",108,null,1050000,null,null,null,1050000]
[null,"Snively Ele - 6 classrooms",108,null,1050000,null,null,null,1050000]
[null,"Ben Hill Briffin Ele - 8 classrooms",144,null,1400000,null,null,null,1400000]
[null,"Combee Ele - 8 classrooms including art, music & computer lab",144,null,1050000,null,null,null,1050000]
[null,"Gause Acad - 12 classrooms",300,null,2100000,null,null,null,2100000]
[null,"Highland City Ele - 10 classrooms/playcourt",180,null,1850000,null,null,null,1850000]
[null,"Jesse Keen Ele - 8 classrooms",144,null,1400000,null,null,null,1400000]
[null,"Lawton Chiles Acad - 8 classrooms",176,null,1400000,null,null,null,1400000]
[null,"R. Bruce Wagner Ele - 8 classrooms",144,null,1400000,null,null,null,1400000]
[null,"Ridgeview Global Acad - 6 classrooms",108,null,1050000,null,null,null,1050000]
[null,"Sandhill Ele - 6 classrooms",108,null,1050000,null,null,null,1050000]
[null,"Socrum Ele - 10 classrooms/land",180,null,2300000,null,null,null,2300000]
[null,"Boone Middle - 10 classrooms plus Agri/Science",220,null,2500000,null,null,null,2500000]
[null,"Berkley Ele - Construct remaining classroom wing",180,null,null,1750000,null,null,1750000]
[null,"Crystal Lake Middle - 8 classrooms",176,null,null,1400000,null,null,1400000]
[null,"Kathleen High - Classroom addition",650,null,null,4550000,null,null,4550000]
[null,"Mulberry Middle - 12 classroom addition (Art, Chorus, Comp. Lab & Resource)",264,null,null,2200000,null,null,2200000]
[null,"Polk Ave. Ele - 4 classrooms including art/music",72,null,null,850000,null,null,850000]
[null,"Sleepy Hill Middle - 10 classrooms for ESE",220,null,null,1800000,null,null,1800000]
[null,"Southwest Middle - 6 classroom addition",132,null,null,1050000,null,null,1050000]
[null,"Lake Wales High - New Home Ec. Suite",65,null,null,1300000,null,null,1300000]
[null,"New Elementary School \"K\" - South Lakeland/Mulberry",825,null,null,14000000,null,null,14000000]
[null,"New Elementary School \"L\" - Northeast Polk County",825,null,null,14000000,null,null,14000000]
[null,"Westwood Middle - 6 classroom addition including art",132,{"$nulls":4},1050000,1050000]
["2b5.","POLK Total",15100,136123000,35650000,42900000,null,1050000,215723000]
[]
["2b6","Schedule of options for generation of additional revenues by the district for expenditure on projects identified in the district facilities work "]
[null,"program which are not funded under paragraph 5 above.  Additional anticipated revenues may include SIT Program awards and Classrooms First funds."]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,null,null,0,0,0,0,0,0]
[null,"Other (carry-over for CO Projects)  ","2003/04 COPS & Sales Tax Rev Bonds",95536081.03999999,0,0,0,0,95536081.03999999]
["2b6.","POLK Total",null,95536081.03999999,0,0,0,0,95536081.03999999]
[]
["2b7","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"NA",0,0,0,0,0,0,0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2b7","POLK Total",0,0,0,0,0,0,0]
[]
["NOTE: If the sum of the totals in paragraphs 2b5. and 2b7. above DO NOT equal the total in paragraph 2b2. above, the message \"Check Totals\" appears.   "]
[null,"-- They should balance ! !"]
[null,null,null,"2004-05 ","2005-06 ","2006-07 ","2007-08","2008-09","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
[]
["POLK  SCHOOL DISTRICT - - FACILITIES TEN (10) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the next 5 years beyond the above 5-year work plan. (years 6-10)"]
[]
[null,null,null,"2009/10 - 2013/14"]
[null,"Project","Location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"NA - we schedule and fund these projects on an annual basis."]
{"$rows_empty":7}
["2b1","POLK Total",null,0,{"$nulls":4},0]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the future 5 years beyond the above 5-year work plan."]
[]
[null,null,"Location - Community, quadrant,","2009/10 - 2013/14"]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[null,"Construct additional 10 classrooms.","Eagle Lake Ele",1800000,{"$nulls":4},1800000]
[null,"Construct an eight classroom addition for ESE and home ec.","McLaughlin Mid",1150000,{"$nulls":4},1150000]
[null,"Remodel old administration suite into ESE classrooms.","Westwood Mid",240000,{"$nulls":4},240000]
[null,"Expand existing kindergarten building, add two classrooms.","Bartow Acad",400000]
[null,"Construct additional classroom wing to replace six portables.","Traviss Tech Adult",900000]
[null,"Construct a eight classroom pod to replace existing portable classrooms, includes demolition of house.","West Area Adult",1200000]
[null,"Construct mini pod (2 classrooms) for the adjudicated youth program.","West Area Adult",400000]
[null,"Construct four classrooms for ESE and resource","Lewis Ele",800000]
["2b2","POLK Total",null,3190000,{"$nulls":4},3190000]
[]
["2b2a.","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2003-04","Actual 2003-04","Actual 2004-05","04/05 - 13/14         New Stu Capacity to","Projected 2013- 14","Projected 2013-14"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[]
[]
[]
[]
["2b2a.","POLK Total",0,0,0,null,0,0,{"$error":"#DIV/0!"}]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the next 5 year period beyond the 5-year work plan above."]
[]
[]
["2b2g.","Plans for closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the next 5 year period beyond the 5-year plan above."]
[]
[]
["POLK  SCHOOL DISTRICT - - FACILITIES TWENTY (20) - YEAR LONG RANGE PLAN"]
[]
["2b1","A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the 11 thru 20 out years."]
[]
[null,null,null,"2013/14-2023/24 ","Annual"]
[null,"Project","Location","Projected Cost","Average Cost",null,null,null,"10 YEAR TOTAL"]
[null,"NA - we schedule and fund these projects on an annual basis."]
[]
[]
[]
[]
[]
[]
["2b1","POLK Total",null,0,{"$nulls":4},0]
[]
["2b2","A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the 11 thru 20 out years."]
[]
[null,null,"Location - Community, quadrant,","2013/14-2023/24 "]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"10 YEAR TOTAL"]
[null,"Remodel current PE building into wrestling and weight room with aerobic room and 2 academic classrooms.","Haines City High",550000]
[null,"Construct 8 classroom addition.","Bill Duncan Opp. Ctr",1600000]
[null,"One new elementary located near Area 4 and 5 boundary, west of Winter Haven area.","New School(s) ~ To be funded by revenue source other than sales tax.",13000000]
[null,"One new elementary school to be constructed in Planning Area 2, southeast Lakeland near Planning Area 3 to serve student growth from both areas.","New School(s) ~ To be funded by revenue source other than sales tax.",13000000]
[null,"One new elementary school to be constructed in Planning Area 8, south of Dundee.","New School(s) ~ To be funded by revenue source other than sales tax.",13000000]
[null,"One new elementary to be located in Area 6, north of Bartow.","New School(s) ~ To be funded by revenue source other than sales tax.",13000000]
[null,"One new middle school to be constructed between South Lakeland and Bartow, Planning Area 3.","New School(s) ~ To be funded by revenue source other than sales tax.",24000000]
[null,"One new middle school to be located between Areas 4 and 5.","New School(s) ~ To be funded by revenue source other than sales tax.",24000000]
[null,"Two new elementaries:  one to be constructed in the northeast portion of Area 5; one to be constructed in the southeast portion of area 5.","New School(s) ~ To be funded by revenue source other than sales tax.",26000000]
[null,"Two new elementary schools to be constructed: one northwest of Lakeland, Planning Area 1; second northeast Lakeland, Planning Area 2.   Area 3 school project has been moved up to accommodate for CSR.","New School(s) ~ To be funded by revenue source other than sales tax.",24000000]
["2b2","POLK Total",null,74000000,{"$nulls":4},0]
[]
["2b2a","Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2003-04","Actual 2003-04","Actual 2001-02","13/14 - 23/24         New Stu Capacity to","District Projected 2023-24","Projected 2023-24"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[]
[]
[]
[]
["2b2a","POLK Total",0,0,0,null,0,0,{"$error":"#DIV/0!"}]
[]
["2b2b","Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the 11 thru 20 out years. "]
[]
[]
["2b2g","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the 11 thru 20 out years."]
[]
[]
[]
[]
[]
[null,"To the extent available, the tentative district facilities work program shall be based on information produced by the demographic, revenue, and"]
[null,"education estimating conferences pursuant to 216.136."]
[null,"Provision shall be made for public comment concerning the tentative district educational facilities plan."]
[null,"The district school board shall coordinate with each affected local government to ensure consistency between the tentative district educational facilities plan and"]
[null,"the local government comprehensive plans of the affected local governments during the deveolpment of the tentative district educational facilities plan."]
[null,"The adopted district facilities work program shall:"]
[null,"Be a complete, balanced capital outlay financial plan for the district."]
[null,"Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities, including safe access ways from neighborhoods to schools."]
[null,"The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 1013.61."]
[null,"The adopted district educational facilities plan shall include the information required in subparagraphs (2) (b) 1., 2., and 3., based upon projects actually"]
[null,"funded in the plan with the exception of the 10 and 20 year portions."]
{"$rows_empty":9}
["Respectfully submitted this ___________ day of ____________________, 2004."]
[]
[null,"SCHOOL BOARD OF ","POLK  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}