{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","0506WkPl","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":6,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"0506WkPl","index":1,"n_rows":1309,"n_cols":16,"rows_kept":1309,"cut":false,"hidden":false,"merged":[[1,0,1,8]],"flags":["formulas_cached_only"]}
[]
["Polk  SCHOOL DISTRICT - - TENTATIVE FACILITIES WORK PROGRAM"]
["Polk   SCHOOL  DISTRICT - -  WORKSHEET ",{"$nulls":7},"Last Revised"]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the Office of Educational Facilities, and a copy submitted ",{"$nulls":7},"2005-04-22"]
["electronically in digital format, as you received it (not a fax), prior to October 1, 2005, and all data accurate as of July 15, 2005."]
["District: ====>",null,"Polk","Date: ","2005-10-01",null,"For fiscal years","  2005-2006 through 2009-2010"]
[]
["Section 1013.35 (2) - (5) School district facilities 5 - Year work program; definitions; preparation, adoption, and amendment."]
[]
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
[1,"A schedule of major repair and renovation projects necessary to maintain the educational facilities and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[]
[null,"Restroom Upgrades/Additions",{"$nulls":6},0]
[null,"Replace toilets and tile wing 1","Auburndale Central",8600,{"$nulls":4},8600]
[null,"Restrooms in cafeteria","Janie Howard Wilson",16800,null,null,40000,null,56800]
[null,"Bathroom added on to cafeteria","Lawton Chiles MIddle",18000,null,null,50000,null,68000]
[null,"Renovate kindergarten bathrooms","Lena Vista Elem.",8850,{"$nulls":4},8850]
[null,"Redo plumbing in 3rd wing gang baths-2 Toilets","North Lakeand Elementary",12500,{"$nulls":4},12500]
[null,"Add an adult toilet area for 1/2 grade building","Rochelle School of the Arts",6000,null,null,10000,20000,36000]
[]
[null,"Cafeteria Expansions/Remodel",{"$nulls":6},0]
[null,"Replace replace dividers in cafeteria","Blake Academy",34000]
[null,"Expand cafeteria","Lake Gibson Middle",42000,null,null,10000,null,52000]
[null,"Expand Teachers Lounge in the Cafeteria area.","Lake Gibson Senior High",22000,{"$nulls":4},22000]
[null,"Expand cafeteria","Sikes Elementary",8500,{"$nulls":4},8500]
[null,"replace floor in cafeteria ","Wendell Watson Elementary",12000,null,null,null,40000,52000]
[]
[null,"Carpet/Tile",{"$nulls":6},0]
[null,"New carpet in Fine Arts Building","Auburndale High School",4365,{"$nulls":4},4365]
[null,"New Carpet - Media Center-Bldg. 13","Frostproof Elementary",9191,{"$nulls":4},9191]
[null,"New Carpet-Bldg 16- hallway","Frostproof Elementary",1483,{"$nulls":4},1483]
[null,"New carpet - Office Bldg. 1","Frostproof Elementary",2925,{"$nulls":4},2925]
[null,"Re-carpet Office office wing/Media Center","Griffin Elementary",13500,{"$nulls":4},13500]
[null,"Carpeting for the media center","Lawton Chiles Middle",5366,{"$nulls":4},5366]
[null,"Replace carpet and tile in the main office building.","Purcell Elementary",4556,{"$nulls":4},4556]
[null,"Remove carpet and replace with vinyl tile. All rooms except admin office.Bldg-1 Aprox. 16,000  SQ FT","Ridge Technical Center  1691",28000,{"$nulls":4},28000]
[null,"Replacement of carpet in admin area. Aprox 4000 sq. ft.","Ridge Technical Center  1691",7000,{"$nulls":4},7000]
[null,"Abate asbestos flooring in the main office and replace carpet","Rochelle School of the Arts",3700,{"$nulls":4},3700]
[null,"Replace carpet in media center","Wahneta Elementary",5046,{"$nulls":4},5046]
[null,"Replace carpet in the media center.  ","Westwood Middle",5860,{"$nulls":4},5860]
[]
[null,"Blinds"]
[null,"Replace blinds throughout the school","Auburndale Central",6000]
[null,"Replace worn out blinds Main Office","Bartow High / IB",3515]
[null,"Replace blinds/window covering throughout the campus/buildings","Boone Middle",15900]
[null,"Blinds- 7 Classrooms ","Sleepy Hill Middle",3676]
[]
[null,"Benches"]
[null,"Replace all wooden benches","Boone Middle",5000]
[null,"Seating for car riders on east side of main building.","Dixieland Elementary",2900]
[null,"Benches at bus loop area ","Sleepy Hill Middle",5000]
[null,"Benches- Parent pick-up area for Pre-K students","Snively Elementary",6000]
[]
[null,"Paving/Resurface"]
[null,"Pave parent pick-up and drop off area west side of campus","Bartow Middle",62000]
[null,"Resurface old blacktop area. Located directly behind Bldg. 7. ","Garden Grove Elementary",12500]
[null,"Pave all Parking Areas","Griffin Elementary",19000]
[null,"Resurface student parking- pothole forming","Haines City High",92000]
[null,"Resurface PE blacktop","Jesse Keen Elementary",22000]
[null,"Resurface track","Kathleen High Schoo",30000]
[null,"Resurface/repave driveway","Kathleen Middle",64000]
[null,"Install sidewalk ","Lake Region High",2500]
[null,"Resurface Tennis and Outdoor Basketball Courts","Lake Wales High School",65000]
[null,"Resurface Track at Practice Field","Lake Wales High School",30000]
[null,"Paved parking area in front of administration building.","Medulla Elementary",18000]
[null,"Re-asphalt bus loop","Snively Elementary",12000]
[null,"Re-asphalt teacher parking lot","Snively Elementary",28000]
[]
[null,"Fencing"]
[null,"Fencing-- the north and west side of school","East Area Adult School",6000]
[null,"Build wall around dumpster areas.","Kathleen High School",44700]
[null,"Block walls around garbage dumpsters","Scott Lake Elementary",23700]
[]
[null,"Walkways"]
[null,"Widen sidewalk on east end of main building","Dixieland Elementary",1440]
[null,"Walkway to be covered on east side of main building.","Dixieland Elementary",14040]
[null,"Replace walkways on the east side of campus","Garner",42000]
[null,"Constuct sidewalk and correct drainage wash out problem.","Gause Riverside Academy",6800]
[null,"Extend the covered Walkway to bus loading area.  Add cover over existing concrete open area.","Lakeland Highlands Middle School",35600]
[null,"Covered walkway for bus loading area","Lake Gibson Middle",37000]
[null,"Install 2 concrete evacuation routes stairways ","Mulberry High School",12000]
[null,"Disabled Ramps At Bldg 100","Traviss Technical Center",2400]
[]
[null,"Other"]
[null,"Balcony repairs in the auditorium","Bartow Elementary Academy",16000]
[null,"Finish leveling surfacing for play activity area","Boone Middle",9200]
[null,"Add tracking system in the ceiling for lifting students and moving to equipment, etc.","Doris Sanders Learning Center",15000]
[null,"Rekey the school","Eagle Lake Elementary",17000]
[null,"Construct room for Cumulative folders, safe and keys","Eagle Lake Elementary",8500]
[null,"Additional Parking","Floral Avenue",28000]
[null,"Provide irrigation to  front entrance of school","Frostproof Middle/Sr",45000]
[null,"Replace lockers in boys' and girls' locker rooms","Frostproof Mid/Sr",52900]
[null,"Redesign drainage and repair drainage to bus landing","Frostproof Mid/Sr",30000]
[null,"Patio area extention to include a sidewalk leading to playground area","Garden Grove Elementary",1800]
[null,"Create PE play area","Garner",7000]
[null,"Relighting of baseball complex ","Haines City High",82000]
[null,"Redsign work space for computer opertors, Techical testing lab, and operation manager's office ","Information Systems & Technology",26300]
[null,"Provide a one way exit in child pick up area.","Janie Howard Wilson",8200]
[null,"Create an outside entrance to clinic","Kingsford Elementary",6600]
[null,"Add lockers to the existing band stroage area.","Lakeland Highlands Middle School",8000]
[null,"Install handicapped sidewalk to softball/baseball fields.","Lake Gibson Senior High",13500]
[null,"Replace current stadium lights with new ones.","Lake Gibson Senior High",80000]
[null,"Install security lights on student parking lot, music building, auditorium, and picnic table area between auditorium and gymnasium","Lake Region High",9000]
[null,"Build wall to divide tutoring room into two areas for tutoring","Lena Vista Elem.",5100]
[null,"Fix drainage problem east of building 1","Lewis Anna Woodbury PK-# (Lewis Campus)",32000]
[null,"Expand Compass Lab to the current Reading Resource Room. Provide additional computer drops/hubs to accommodate 20 computers.","Lincoln Avenue Academy #2",15000]
[null,"Additional parents and staff parking","Loughman Oaks Elementary School",57000]
[null,"Install secondary means of egress - building 5 rooms 101/103","McKeel Academy",4000]
[null,"Install secondary means of egress - building 5 - room 106","McKeel Academy",4000]
[null,"Install lighting on Baseball field","Mulberry High School",74000]
[null,"Remove asbestos tile in main building","Padgett Elementary",5800]
[null,"Remodel and convert a classroom to serve as an Art Classroom including a Kiln.","Padgett Elementary",16000]
[null,"Installation of a doorway from ESE to Admin","Polk City Elementary",4900]
[null,"Install a softball backstop and creat a Softball Field on PE Field","Roosevelt Academy",4000]
[null,"Remodel journalism/tv production classroom to include a TV studio.","Southwest Middle ",5300]
[]
["1","Polk Total",null,1702013,0,0,0,0,0]
[]
[2,"A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"New Elementary A",null,1700000]
[null,"New Elementary B",null,1700000]
[null,"New High School BBB",null,35000000,3000000]
[null,"Boone Kitchen Addition",null,640000]
[null,"Carlton Palmore 8 Cr add",null,1600000]
[" ","Crystal Lake Ele 8 Cr add/art",null,1700000]
[null,"Davenport 16 cr",null,3175000]
[null,"Dr. NE Roberts 8 cr",null,1586000]
[null,"Hillcrest 4 cr",null,790000]
[null,"JH Wilson 6 cr",null,1187000]
[null,"Medulla 6 cr",null,1200000]
[null,"Snively 6 cr  ",null,1200000]
[null,"Transportation 800 mhz Radio System",null,4000000,4000000]
[null,"Blake Kit Remodel",null,200000]
[null,"Eagle Lake 10 cr",null,2200000]
[null,"Frostproof El Kit Remodel",null,700000]
[null,"Jewett Arts Kit/Din Remodel",null,1000000]
[null,"Scott Lake 8 cr",null,2200000]
[null,"Adale Cent Rebuild",null,3650000,2000000]
[null,"Adale Sr. Fire Sprinkler",null,420000]
[null,"Adale Sr. Remodel Audit.",null,500000]
[null,"Alturus Café",null,1260000]
[null,"Ben Hill Griffin 8 cr",null,1636000]
[null,"Boone 10 cr",null,2200000]
[null,"Harrison Arts Expansion",null,8156537,843527]
[null,"Lake Wales Sr- New Cafeteria",null,null,3500000]
[null,"Kathleen Sr-MP, ",null,null,6000000]
[null,"Bartow Sr-MP Phase IV",null,null,1920000]
[null,"Portable Classrooms ",null,null,4000000,4000000,4000000]
[null,"Stambaugh Middle-Gym remodel and renovation",null,null,2000000]
[null,"Transportation Garage - North Central",null,null,null,10000000]
[null,"Maintenance Shop - UA - 1 Replacement",null,null,1500000]
[null,"Dundee Ridge - Brick Facade",null,null,1000000]
[null,"Middle BBB",null,null,24000000]
[null,"Boone Ag/Sci",null,null,1030000]
[null,"Crystal Lake El Media",null,null,650000]
[null,"Crystal Lake Mid Media",null,null,542000]
[null,"Eastside 4 cr/media",null,null,2620000]
[null,"Fruitland Park remodel Ph 2",null,null,400000]
[null,"Gibbons St 4 cr",null,null,747000]
[null,"Highland City 10 cr",null,null,2020000]
[null,"Jesse Keen 8 cr",null,null,1636000]
[null,"Lime St Café remodel",null,null,1300000]
[null,"R. B. Wagner 8 cr",null,null,1536000]
[null,"Ridgeview 6 cr",null,null,1150000]
[null,"Sandhill 6 cr",null,null,1150000]
[null,"Socrum 10 cr",null,null,2300000]
[null,"Warehouse Dist expand",null,null,450000]
[null,"Bartow Ac Kit/Din Remodel",null,null,700000]
[null,"Caldwell Kit/Din Remodel",null,null,450000]
[null,"Berkely 10 cr",null,null,2800000]
[null,"Crystal Lake Mid 8 cr",null,null,1850000]
[null,"District Office media ser blg",null,null,1500000]
[null,"Hillcrest renov bldg 4-office",null,null,800000]
[null,"Jewett El café expand",null,null,1200000]
[null,"Kathleen Mid chorus/band",null,null,2000000]
[null,"Kathleen Sr. demo 1,5,13,16",null,null,740000]
[null,"Land Purchases for BBB, A-D, BB, CC",null,null,8800000]
[null,"Portables",null,null,4000000,3000000,5000000,3000000]
[null,"Small Projects  (Pushed back from original year)",null,null,1500000,1500000,1500000,1500000]
[null,"Satellite Offices (four) - Itenerants",null,null,null,4000000]
[null,"Traviss Update",null,null,null,6000000]
[null,"Dwight Smith/Karen Siegel Center - Ridge Area",null,null,null,10000000,10900000]
[null,"Boone Middle-Revised Master Plan",null,null,null,6000000,2000000]
[null,"Auburndale Sr-MP Phase III,",null,null,null,9741319]
[null,"Auburndale Sr-MP Phase IV",null,null,null,2600000,null,5000000]
[null,"Additional Elementary Schools (3) - TBA",null,null,null,18000000,36000000]
[null,"Union Academy - Fine arts, music suite",null,null,null,2712000]
[null,"High School CCC",{"$nulls":4},30000000,28000000]
[null,"Kathleen Sr. 30 cr addition",null,null,null,3450000,3498258]
[null,"Elementary C",null,null,null,17000000]
[null,"Inwood Kit Remodel",null,null,null,800000]
[null,"Snively Kit/Din Remodel",null,null,null,800000]
[null,"Southwest El Kit Remodel",null,null,null,1200000]
[null,"Mulberry Mid 12 cr",{"$nulls":4},2880000]
[null,"Lake Wales Sr Home Ec ste",{"$nulls":4},1300000]
[null,"Elementary D",{"$nulls":4},21000000]
[null,"Alta Vista relocate/remodel media",{"$nulls":4},300000]
[null,"Dundee Ele Expand parking ",{"$nulls":4},150000]
[null,"Dundee Ele New PE area",{"$nulls":4},170000]
[null,"Eastside Din Remodel",{"$nulls":4},1200000]
[null,"Ft Meade Sr Rem Boys/Girls locker rms",{"$nulls":4},250000]
[null,"Ft. Meade Sr Press Box",{"$nulls":4},200000]
[null,"Garden Grove HVAC",{"$nulls":4},750000]
[null,"Gibbons St Kit Remodel",{"$nulls":4},700000]
[null,"Lake Gibson Mid Fire Sprinkler",{"$nulls":4},400000]
[null,"McKeel Aca Fire Sprinkler",{"$nulls":4},550000]
[null,"N. Lakeland Din Remodel",{"$nulls":4},750000]
[null,"Elementary School - Southwest Lakeland",{"$nulls":4},21000000]
[null,"Combee El - Expand and remodel media",{"$nulls":5},250000]
[null,"Denison Middle-Expand kitchen and dining",{"$nulls":5},650000]
[null,"District Office- expand the auditorium",{"$nulls":5},320000]
[null,"Hillcrest El-Renovate admin",{"$nulls":5},450000]
[null,"Hillcrest El-Expand and renovate cafeteria",{"$nulls":5},750000]
[null,"Lime Street El-convert media into music & multipurpose",{"$nulls":5},225000]
[null,"Lime Street-Expand admin & guidance",{"$nulls":5},250000]
[null,"Mulberry Sr-Demolish bldgs 1 &25, replace&varsity lockers",{"$nulls":5},1250000]
[null,"Mulberry Sr-Remodel Ag facility",{"$nulls":5},200000]
[null,"Mulberry Sr-Remodel Industrial Arts Bldg",{"$nulls":5},200000]
[null,"Altruas El-Demolish Bldg 1, Construct new admin/classrooms",{"$nulls":5},2000000]
[null,"Bartow Sr- MP Phase I",{"$nulls":5},1080000]
[null,"Cleveland Court El-Remodel classrooms",{"$nulls":5},501120]
[null,"Crystal Lake El-Remodel media center for ESE and resource",{"$nulls":5},226120]
[null,"Griffin El- Renovate bldgs 2 and 3 for art, music, labs",{"$nulls":5},1200000]
[null,"Winter Haven Sr-Phase I Master Plan",{"$nulls":5},3176119]
[null,"Babson Park El-Demolish bldg 3 and construct new art suite",{"$nulls":5},600000]
[null,"Kathleen El-Remodel media center",{"$nulls":5},500000]
[null,"Kingsford El-New media center",{"$nulls":5},1300000]
[null,"Lakeland Sr-MP - Phase 2a, renovate remaining classrooms",{"$nulls":5},5000000]
[null,"Polk City El-Construct media center and remodel existing",{"$nulls":5},1200000]
[null,"Ridge Tech-Replace roofs",{"$nulls":5},1000000]
[null,"Southwest Middle-New admin",{"$nulls":5},3000000]
[null,"Stambaugh Middle-Replace HVAC system",{"$nulls":5},1000000]
[null,"Kingford El-remodel old media center into art/music",{"$nulls":5},500000]
[null,"Auburndale Sr-MP Phase 2, Media center and classrooms",{"$nulls":5},3356000]
[null,"Bartow Middle-Expand Admin ",{"$nulls":5},750000]
[null,"District Office-Data/Technology Center",{"$nulls":5},23000000]
[null,"Eastside El-Remodel bldg 4 for admin",{"$nulls":5},1300000]
[null,"Floral Ave-Expand admin",{"$nulls":5},500000]
[null,"Hillcrest El-Expand media center",{"$nulls":5},800000]
[null,"Jewett SOA-Expand admin suite",{"$nulls":5},475000]
[null,"Lake Alfred El-Expand cafeteria",{"$nulls":5},750000]
[null,"Lake Gibson Middle-construct mini-gym",{"$nulls":5},1550000]
[null,"Lakeland Highlands Middle-Construct mini-gym",{"$nulls":5},1750000]
[null,"West Area Adult-Remodel and fire sprinkle bldg 1",{"$nulls":5},2750000]
[null,"Bartow Sr-MP Phase III - Music Suite",{"$nulls":5},1380000]
[null,"Winter Haven Sr-Phase II Master Plan",{"$nulls":5},3452000]
[2,"Polk Total",null,79600537,97634527,100803319,144498258,106141359,528678000]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
[3,"Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2005-06 FISH Satisfactory","Actual 2005-06","Actual 2004-05","Actual 2005-06","New Stu Capacity to","Projected 2009-10","Projected 2009-10"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Alta Vista Elementary",867,700,773,1.1,-311,850.3000000000001,2.19]
[null,"Alturas Elementary",347,200,263,1.32,-36,289.3,1.76]
[null,"Anna Woodbury Elementary","(See Lewis Anna Woodbury)",{"$nulls":4},0]
[null,"Auburndale Central Elementary",520,400,373,0.93,33,410.3,0.95]
[null,"Auburndale High",2282,1500,1754,1.17,-150,1929.4,1.43]
[null,"Babson Park Elementary",544,400,445,1.11,null,489.50000000000006,1.22]
[null,"Bartow Academy",380,500,386,0.77,108,424.6,0.7]
[null,"Bartow Middle",1445,1000,846,0.85,17,930.6,0.92]
[null,"Bartow High",1500,2390,1223,0.51,null,1345.3000000000002,0.56]
[null,"Ben Hill Griffin Elementary",700,724,381,0.53,144,419.1,0.48]
[null,"Berkley Elementary",700,634,564,0.89,144,620.4000000000001,0.8]
[null,"Bethune Academy",450,445,442,0.99,108,486.20000000000005,0.88]
[null,"Bill Duncan Opportunity Center",200,234,210,0.9,null,231.00000000000003,0.99]
[null,"Brigham Academy",600,579,591,1.02,108,650.1,0.95]
[null,"Carlton Palmore Elementary",755,826,690,0.84,41,759.0000000000001,0.88]
[null,"Clarence Boswell Elementary",700,779,534,0.69,null,587.4000000000001,0.75]
[null,"Cleveland Court Elementary",250,274,458,1.67,-18,503.80000000000007,1.97]
[null,"Combee Elementary",750,903,669,0.74,15,735.9000000000001,0.8]
[null,"Crystal Lake Elementary",750,817,643,0.79,-108,707.3000000000001,1]
[null,"Crystal Lake Middle",950,1458,906,0.62,120,996.6000000000001,0.63]
[null,"Davenport Elementary",648,693,566,0.82,230,622.6,0.67]
[null,"Denison Middle",1376,1000,971,0.97,null,1068.1000000000001,1.07]
[null,"Discovery Academy at LK Alfred",900,1409,983,0.7,null,1081.3000000000002,0.77]
[null,"Dixieland Elementary",300,467,516,1.1,-18,567.6,1.26]
[null,"Donald E Woods Center",174,210,218,1.04,null,239.8,1.14]
[null,"Doris A Sanders Learning Center",100,106,107,1.01,null,117.7,1.11]
[null,"Dr. N. E. Roberts Elementary ",800,796,836,1.05,144,919.6,0.98]
[null,"Dundee Elementary",700,1232,488,0.4,-638,536.8000000000001,0.9]
[null,"Dundee Ridge Middle",1100,1562,1029,0.66,null,1131.9,0.72]
[null,"Dwight C Smith Center",77,242,108,0.45,null,118.80000000000001,0.49]
[null,"Eagle Lake Elementary",502,795,651,0.82,-54,716.1,0.97]
[null,"Eastside Elementary",850,1271,996,0.78,null,1095.6000000000001,0.86]
[null,"Edgar L Padgett Elementary",800,948,630,0.66,23,693,0.71]
[null,"Elbert Elementary",600,780,494,0.63,38,543.4000000000001,0.66]
[null,"Floral Avenue Elementary",550,768,589,0.77,-36,647.9000000000001,0.89]
[null,"Fort Meade Middle Senior High",771,1199,765,0.64,null,841.5000000000001,0.7]
[null,"Fred G Garner Elementary",750,878,627,0.71,-18,689.7,0.8]
[null,"Frostproof Elementary",575,706,423,0.6,null,465.3,0.66]
[null,"Frostproof Middle Senior High",1230,2078,1201,0.58,null,1321.1000000000001,0.64]
[null,"Fruitland Park Learning Center",83,142,109,0.77,-68,119.9,1.62]
[null,"Garden Grove Elementary",700,848,749,0.88,null,823.9000000000001,0.97]
[null,"Gause Academy of Applied Tech",328,809,263,0.33,128,289.3,0.31]
[null,"Gause Riverside Academy",170,170,69,0.41,0,75.9]
[null,"George Jenkins High",1500,2261,2094,0.93,-442,2303.4,1.27]
[null,"Gibbons Street Elementary",375,513,334,0.65,-31,367.40000000000003,0.76]
[null,"Griffin Elementary",400,624,561,0.9,-156,617.1,1.32]
[null,"Haines City High",1500,3092,2051,0.66,-1315,2256.1000000000004,1.27]
[null,"Harrison Arts Center",140,201,145,0.72,null,159.5,0.79]
[null,"Highland City Elementary",675,634,463,0.73,134,509.30000000000007,0.66]
[null,"Hillcrest Elementary",600,791,593,0.75,-98,652.3000000000001,0.94]
[null,"Homer K Addair Career Academy",327,936,441,0.47,null,485.1,0.52]
[null,"Inwood Elementary",350,481,562,1.17,-54,618.2,1.45]
[null,"J Daniel Jenkins Academy",408,646,315,0.49,null,346.5,0.54]
[null,"James E Stephens Elementary",650,694,506,0.73,69,556.6,0.73]
[null,"James W Sikes Elementary",600,861,687,0.8,-222,755.7,1.18]
[null,"Janie Howard Wilson Elementary",700,880,594,0.68,27,653.4000000000001,0.72]
[null,"Jere L Stambaugh Middle",900,1354,977,0.72,null,1074.7,0.79]
[null,"Jesse Keen Elementary",750,868,537,0.62,-151,590.7,0.82]
[null,"Jewett School of the Arts",762,1059,727,0.69,35,799.7,0.73]
[null,"Jewett Middle Academy",580,890,573,0.64,null,630.3000000000001,0.71]
[null,"John Snively Elementary",450,749,520,0.69,-108,572,0.89]
[null,"Kathleen Elementary",700,670,563,0.84,114,619.3000000000001,0.79]
[null,"Kathleen Middle",900,1495,822,0.55,16,904.2,0.6]
[null,"Kathleen High",1400,1929,1574,0.82,509,1731.4,0.71]
[null,"Kingsford Elementary",400,539,466,0.86,15,512.6,0.93]
[null,"Lake Alfred Elementary",700,681,453,0.67,107,498.30000000000007,0.63]
[null,"Lake Gibson Middle",1100,1266,1102,0.87,null,1212.2,0.96]
[null,"Lake Gibson High",1500,2223,1808,0.81,1,1988.8000000000002,0.89]
[null,"Lake Region High",1500,2289,1999,0.87,-235,2198.9,1.07]
[null,"Lake Shipp Elementary",700,811,679,0.84,null,746.9000000000001,0.92]
[null,"Lake Wales High",1300,1894,1345,0.71,null,1479.5000000000002,0.78]
[null,"Lakeland Highlands Middle",1000,1394,1155,0.83,-270,1270.5,1.13]
[null,"Lawton Chiles Middle Academy",580,756,566,0.75,176,622.6,0.67]
[null,"Lakeland High ",1500,2536,2168,0.85,null,2384.8,0.94]
[null,"Lena Vista Elementary",700,818,694,0.85,-18,763.4000000000001,0.95]
[null,"Lewis/Anna Woodbury ",450,620,659,1.06,-90,724.9000000000001,1.37]
[null,"Lime Street Elementary",800,617,588,0.95,112,646.8000000000001,0.89]
[null,"Lincoln Academy",650,590,504,0.85,159,554.4000000000001,0.74]
[null,"Loughman Oaks Elementary",750,1080,886,0.82,78,974.6,0.84]
[null,"Traviss Vocational Technical Center",133,1097,211,0.19,null,232.10000000000002,0.21]
[null,"Mckeel Academy",1054,1108,958,0.86,null,1053.8000000000002,0.95]
[null,"McLaughlin Middle",1569,1412,899,0.64,null,988.9000000000001,0.7]
[null,"Medulla Elementary",850,987,719,0.73,31,790.9000000000001,0.78]
[null,"Mulberry Middle",900,1153,852,0.74,176,937.2,0.71]
[null,"Mulberry High ",900,1402,921,0.66,null,1013.1000000000001,0.72]
[null,"North Lakeland Elementary",500,829,694,0.84,-243,763.4000000000001,1.3]
[null,"Oscar J Pope Elementary",650,786,380,0.48,-18,418.00000000000006,0.54]
[null,"Pinewood Elementary",750,634,597,0.94,180,656.7,0.81]
[null,"Polk Avenue Elementary",600,752,449,0.6,5,493.90000000000003,0.65]
[null,"Polk City Elementary",500,645,583,0.9,-36,641.3000000000001,1.05]
[null,"Polk Life and Learning Center",42,162,51,0.31,null,56.1,0.35]
[null,"Purcell Elementary",500,625,480,0.77,-213,528,1.28]
[null,"R. Bruce Wagner Elementary",800,956,722,0.76,144,794.2,0.72]
[null,"R Clem Churchwell Elementary",725,820,597,0.73,148,656.7,0.68]
[null,"Ridge Vocational Technical Center",105,848,229,0.27,null,251.90000000000003,0.3]
[null,"Ridgeview Elementary",800,862,739,0.86,108,812.9000000000001,0.84]
[null,"Rochelle School of the Arts",876,1091,815,0.75,306,896.5000000000001,0.64]
[null,"Roosevelt Academy",245,247,306,1.24,null,336.6,1.36]
[null,"Rosabelle W Blake Elementary",726,759,635,0.84,null,698.5,0.92]
[null,"Sandhill Elementary",800,890,1061,1.19,12,1167.1000000000001,1.29]
[null,"Scott Lake Elementary",800,1113,953,0.86,-100,1048.3000000000002,1.03]
[null,"Shelley S Boone Middle",950,1451,1052,0.73,16,1157.2,0.79]
[null,"Sleepy Hill Middle",1000,1592,1143,0.72,147,1257.3000000000002,0.72]
[null,"Socrum Loop Elementary",800,803,623,0.78,180,685.3000000000001,0.7]
[null,"Southwest Elementary",725,628,492,0.78,173,541.2,0.68]
[null,"Southwest Middle",1000,1399,938,0.67,-132,1031.8000000000002,0.81]
[null,"Spook Hill Elementary",650,763,424,0.56,20,466.40000000000003,0.6]
[null,"Union Academy",420,583,388,0.67,null,426.8,0.73]
[null,"Valleyview Elementary",838,1226,1173,0.96,-107,1290.3000000000002,1.15]
[null,"Wahneta Elementary",400,771,563,0.73,-144,619.3000000000001,0.99]
[null,"Walter Caldwell Elementary",500,643,717,1.12,null,788.7,1.23]
[null,"Wendell Watson Elementary",800,875,790,0.9,null,869.0000000000001,0.99]
[null,"Westwood Middle",978,1577,1045,0.66,-132,1149.5,0.8]
[null,"Winston Elementary",550,891,582,0.65,-129,640.2,0.84]
[null,"Winter Haven High",1500,2213,1751,0.79,107,1926.1000000000001,0.83]
[3,"Polk Total",83007,108207,81782,88.94000000000001,-1193,89960.20000000001,0.84]
[]
[4,"Necessary offsite infrastructure requirements resulting from expansions or new schools.  "]
[null,"This section should include the same project information from 2."]
[null,"NA"]
[]
[]
[]
[5,"Proposed location of planned facilities, whether those locations are consistent with the comprehensive plans of all affected local governments, and "]
[null,"recommendations for infrastructure and other improvements to land adjacent to existing facilities. Provisions of 1013.33(12), (13), and (14) and 1013.36"]
[null," must be addressed for new facilities planned within the 1st 3 years  of the plan"]
[null,"Consistent with Comp Plan?","Description"]
[null,"Yes","Elementary C-- SW Lakeland"]
[null,"Yes","Elementary D-- NE Lakeland",{"$nulls":5},"Year in which all"]
[null,"Yes","Elementary E-- Poinciana"]
[null,"Yes","Middle School CC-- SW Lakeland",{"$nulls":5},"long term ( 4 yrs or"]
[null,"Yes","High School CCC-- SW Lakeland"]
[{"$nulls":6},"# of Units","Projected "," more) relocatables"]
[6,"Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","which will be used"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","as Classrooms will"]
[null,"Location","Actual # of Units in 2005-06","Owner","Student Stations","as classroom space","in 2009-10","units by 2009-10","will meet standards"]
[null,"AAA High School",3,"PCSB",0,0,0,3,2005]
[null,"Alta Vista Elementary",15,"PCSB",201,0,3,8,2008]
[null,"Alta Vista Elementary",3,"Fed",69,0,0,3,2008]
[null,"Alturas Elementary",8,"PCSB",111,0,2,0,2005]
[null,"Alturas Elementary",2,"Fed",33,0,0,2,2005]
[null,"Anna Woodbury Elementary",1,"PCSB",0,0,0,1,2005]
[null,"Anna Woodbury Elementary",1,"Fed",18,0,0,0,2005]
[null,"Auburndale Central Elementary",7,"PCSB",90,0,0,4,2005]
[null,"Auburndale Central Elementary",2,"Fed",36,0,0,2,2005]
[null,"Auburndale High",5,"PCSB",125,0,0,5,2010]
[null,"Auburndale High",1,"Fed",15,0,0,1,2010]
[null,"Babson Park Elementary",7,"PCSB",98,0,7,0,2010]
[null,"Bartow El",4,"PCSB",72,0,0,4,2006]
[null,"Bartow Middle",13,"PCSB",264,0,0,6,2005]
[null,"Bartow Middle",1,"Fed",22,0,0,0,2005]
[null,"Bartow High",4,"PCSB",100,0,2,0,2005]
[null,"Berkley El",2,"PCSB",36,0,2,0,2005]
[null,"Bethune El",2,"PCSB",36,0,0,2,2005]
[null,"Bill Duncan Opportunity Center",2,"PCSB",25,0,3,0,2010]
[null,"Bill Duncan Opportunity Center",1,"Fed",25,0,0,0,2010]
[null,"Blake Elementary",3,"PCSB",54,0,0,3,2005]
[null,"Blake Elementary",1,"Fed",0,0,1,0,2005]
[null,"Boone Middle",13,"PCSB",286,0,0,6,2005]
[null,"Boone Middle",3,"Fed",66,0,0,2,2005]
[null,"Boswell El",2,"PCSB",33,0,0,0,2005]
[null,"Boswell El",1,"Fed",22,0,0,0,2005]
[null,"Brigham Acad",3,"PCSB",54,0,0,3,2005]
[null,"Caldwell Elementary",12,"PCSB",210,0,5,0,2005]
[null,"Caldwell Elementary",1,"Fed",22,0,0,0,2005]
[null,"Carlton Palmore Elementary",8,"PCSB",140,0,0,8,2005]
[null,"Carlton Palmore Elementary",1,"Fed",22,0,0,0,2005]
[null,"Chain of Lakes El",6,"PCSB",108,0,0,0,2005]
[null,"Churchwell Elementary",7,"PCSB",126,0,1,6,2005]
[null,"Churchwell Elementary",1,"Fed",22,0,0,1,2005]
[null,"Cleveland Court Elementary",4,"PCSB",54,0,0,4,2005]
[null,"Combee Elementary",7,"PCSB",127,0,0,6,2010]
[null,"Combee Elementary",3,"Fed",72,0,0,2,2010]
[null,"Crystal Lake Elementary",6,"PCSB",94,0,0,4,2005]
[null,"Crystal Lake Elementary",2,"Fed",36,0,0,2,2005]
[null,"Crystal Lake Middle",6,"PCSB",132,0,0,0,2005]
[null,"Davenport Elementary",7,"PCSB",148,0,0,7,2005]
[null,"Davenport Elementary",3,"Fed",58,0,0,3,2005]
[null,"Dixieland Elementary",5,"PCSB",96,0,1,0,2005]
[null,"Dixieland Elementary",1,"Fed",18,0,1,0,2005]
[null,"Don E Woods Opportunity Center",4,"PCSB",30,0,4,0,2005]
[null,"Don E Woods Opportunity Center",1,"Fed",10,0,1,0,2005]
[null,"Doris Sanders Lrn Ctr",2,"PCSB",30,0,0,0,2005]
[null,"Dr. NE Roberts El",14,"PCSB",249,0,6,0,2005]
[null,"Dundee Elementary",3,"PCSB",28,0,0,3,2005]
[null,"Dundee Elementary",1,"Fed",14,0,0,1,2005]
[null,"Dundee Ridge Middle",3,"PCSB",66,0,0,3,2005]
[null,"Dundee Ridge Middle",4,"Fed",88,0,0,4,2005]
[null,"Eagle Lake Elementary",12,"PCSB",193,0,6,0,2010]
[null,"Eagle Lake Elementary",5,"Fed",82,0,0,3,2010]
[null,"East Area Adult Center",5,"PCSB",125,0,5,0,2005]
[null,"East Area Adult Center",2,"Fed",25,0,2,0,2005]
[null,"Eastside Elementary",29,"PCSB",521,0,0,29,2010]
[null,"Elbert Elementary",4,"PCSB",80,0,0,4,2005]
[null,"Elbert Elementary",1,"Fed",10,0,0,1,2005]
[null,"Floral Avenue Elementary",7,"PCSB",138,0,6,0,2010]
[null,"Floral Avenue Elementary",6,"Fed",124,0,0,2,2005]
[null,"Fort Meade Middle/Senior High",6,"PCSB",119,0,4,0,2010]
[null,"Fort Meade Middle/Senior High",1,"Fed",0,0,0,0,2005]
[null,"Frostproof Elementary",2,"PCSB",40,0,0,0,2010]
[null,"Frostproof Middle/Senior High",11,"PCSB",269,0,6,0,2005]
[null,"Fruitland Park Learning Center",7,"PCSB",40,0,0,7,2010]
[null,"Fruitland Park Learning Center",1,"Fed",10,0,0,1,2010]
[null,"Garner Elementary",1,"PCSB",18,0,1,0,2005]
[null,"Garner Elementary",1,"Fed",40,0,1,0,2005]
[null,"Gause Academy",6,"PCSB",138,0,0,7,2010]
[null,"Gause Academy",1,"Fed",0,0,0,1,2010]
[null,"George Jenkins High",19,"PCSB",475,0,0,19,2005]
[null,"Gibbons Street Elementary",7,"PCSB",105,0,1,4,2010]
[null,"Gibbons Street Elementary",3,"Fed",50,0,0,3,2010]
[null,"Griffin Elementary",11,"PCSB",207,0,0,7,2005]
[null,"Griffin Elementary",1," Fed",22,0,0,1,2005]
[null,"Haines City High",18,"Williams Scottsman",400,0,0,18,2006]
[null,"Highland City Elementary",7,"PCSB",126,0,0,7,2005]
[null,"Hillcrest Elementary",2,"PCSB",44,0,0,2,2005]
[null,"Hillcrest Elementary",2,"Fed",40,0,0,2,2005]
[null,"Inwood Elementary",4,"PCSB",50,0,3,0,2010]
[null,"Inwood Elementary",3,"Fed",51,0,0,3,2010]
[null,"Janie Howard Wilson",6,"PCSB",116,0,2,4,2005]
[null,"Janie Howard Wilson",1,"Fed",18,0,0,1,2005]
[null,"Jesse Keen Elementary",6,"PCSB",128,0,0,4,2005]
[null,"Jesse Keen Elementary",3,"Fed",46,0,0,3,2010]
[null,"Jewett Mid Academy",3,"PCSB",66,0,0,3,2005]
[null,"Jewett Elementary Arts",10,"PCSB",169,0,0,10,2010]
[null,"Karen M Siegel Acad",1,"PCSB",15,0,1,0,2005]
[null,"Kathleen Elementary",2,"PCSB",33,0,0,2,2006]
[null,"Kathleen Elementary",2,"Fed",44,0,0,2,2006]
[null,"Kathleen Middle",10,"PCSB",196,0,0,10,2010]
[null,"Kathleen High",14,"PCSB",350,0,0,14,2010]
[null,"Kingsford Elementary",3,"PCSB",54,0,0,3,2010]
[null,"Kingsford Elementary",4,"Fed",58,0,0,4,2010]
[null,"Lake Alfred Elementary",5,"PCSB",55,0,0,5,2006]
[null,"Lake Alfred Elementary",3,"Fed",44,0,1,2,2006]
[null,"Lake Gibson Middle",4,"PCSB",80,0,4,0,2010]
[null,"Lake Gibson Middle",1,"Fed",10,0,1,null,2010]
[null,"Lake Gibson High",23,"PCSB",490,0,0,23,2010]
[null,"Lake Region High",12,"PCSB",300,0,0,12,2010]
[null,"Lake Shipp El",4,"Fed",50,0,0,4,2005]
[null,"Lake Wales High",7,"PCSB",165,0,0,7,2005]
[null,"Lake Wales High",1,"Fed",15,0,0,1,2005]
[null,"Lakeland Highlands Middle",16,"PCSB",338,0,0,16,2010]
[null,"Lakeland Highlands Middle",1,"Fed",0,0,0,1,2010]
[null,"Lakeland Sr",5,"PCSB",125,0,0,5,2005]
[null,"Lawton Chiles Mid Acad",4,"PCSB",88,0,0,4,2005]
[null,"Lena Vista Elementary",7,"PCSB",127,0,4,3,2005]
[null,"Lena Vista Elementary",4,"Fed",72,0,2,2,2005]
[null,"Lewis Elementary",2,"PCSB",36,0,0,0,2006]
[null,"Lewis Elementary",5,"Fed",98,0,5,0,2006]
[null,"Lime Street Elementary",8,"PCSB",145,0,0,8,2005]
[null,"Lime Street Elementary",1,"Fed",22,0,0,1,2005]
[null,"Lincoln Elementary Academy",5,"PCSB",72,0,1,4,2005]
[null,"Loughman Oaks Elementary",18,"PCSB",328,0,1,17,2005]
[null,"Loughman Oaks Elementary",1,"Fed",22,0,1,0,2005]
[null,"Mark Wilcox Center",3,"PCSB",69,0,3,0,2010]
[null,"McKeel Academy",2,"Fed",37,0,2,0,2005]
[null,"McLaughlin Middle",1,"PCSB",22,0,1,0,2005]
[null,"Medulla Elementary",5,"PCSB",98,0,0,5,2005]
[null,"Medulla Elementary",2,"Fed",46,0,0,2,2005]
[null,"Mulberry Middle",5,"PCSB",109,0,0,5,2005]
[null,"Mulberry Sr",3,"PCSB",75,0,0,3,2005]
[null,"North Lakeland Elementary",6,"PCSB",108,0,0,6,2010]
[null,"North Lakeland Elementary",9,"Fed",171,0,0,9,2010]
[null,"Oscar J Pope Elementary",1,"Fed",22,0,0,0,2010]
[null,"Padgett Elementary",7,"PCSB",135,0,0,7,2006]
[null,"Padgett Elementary",2,"Fed",28,0,0,2,2006]
[null,"PEER Center",2,"PCSB",50,0,2,0,2010]
[null,"Pinewood El",2,"Fed",25,0,0,2,2005]
[null,"Polk Avenue Elementary ",4,"PCSB",76,0,4,0,2010]
[null,"Polk Avenue Elementary ",3,"Williams Scottsman",54,0,3,0,2005]
[null,"Polk City Elementary",4,"PCSB",76,0,1,3,2005]
[null,"Polk City Elementary",2,"Fed",40,0,0,2,2010]
[null,"Polk Life and Learning Center",2,"PCSB",10,0,0,2,2010]
[null,"Polk Life and Learning Center",2,"Fed",20,0,0,2,2010]
[null,"Purcell Elementary",10,"PCSB",184,0,2,8,2006]
[null,"Purcell Elementary",4,"Fed",72,0,0,4,2006]
[null,"R Bruce Wagner",5,"PCSB",98,0,0,5,2005]
[null,"Ridge Technical Center",21,"PCSB",375,0,20,0,2005]
[null,"Riverside Gause Elementary",1,"PCSB",0,0,0,1,2010]
[null,"Rochelle School of the Arts",16,"PCSB",312,0,0,15,2005]
[null,"Roosevelt Academy",3,"Fed",35,0,3,0,2005]
[null,"Sandhill Elementary",31,"PCSB",494,0,0,31,2005]
[null,"Sandhill Elementary",1,"Fed",22,0,0,1,2005]
[null,"Scott Lake Elementary",20,"PCSB",333,0,0,20,2005]
[null,"Sikes Elementary",5,"PCSB",98,0,0,5,2005]
[null,"Sikes Elementary",1,"Fed",18,0,0,1,2005]
[null,"Sleepy Hill Middle",6,"PCSB",125,0,0,6,2005]
[null,"Sleepy Hill Middle",5,"Fed",132,0,0,3,2005]
[null,"Snively Elementary",15,"PCSB",227,0,7,8,2010]
[null,"Snively Elementary",5,"Fed",98,0,5,0,2010]
[null,"Socrum El",2,"PCSB",33,0,0,2,2005]
[null,"Southwest Elementary",4,"PCSB",61,0,0,4,2005]
[null,"Southwest Elementary",1,"Fed",22,0,1,0,2005]
[null,"Southwest Middle",11,"PCSB",228,0,2,9,2005]
[null,"Spook Hill Elementary",5,"PCSB",90,0,0,5,2005]
[null,"Spook Hill Elementary",1,"Fed",18,0,0,1,2005]
[null,"Stambaugh Middle",1,"PCSB",20,0,0,1,2005]
[null,"Stephens Elementary",5,"PCSB",33,0,0,5,2005]
[null,"Stephens Elementary",2,"Fed",94,0,0,2,2005]
[null,"Traviss Technical Center",7,"PCSB",174,0,7,0,2010]
[null,"Traviss Technical Center",1,"Non-PCSB Owned",0,0,1,0,2010]
[null,"Union Academy",3,"PCSB",54,0,0,3,2005]
[null,"Union Academy",1,"Williams Scottsman",10,0,0,1,2005]
[null,"Valleyview Elementary",10,"PCSB",193,0,0,10,2005]
[null,"Wahneta Elementary",7,"PCSB",116,0,0,7,2010]
[null,"Wahneta Elementary",8,"Fed",104,0,7,1,2010]
[null,"Wendell watson El",5,"PCSB",87,0,0,5,2005]
[null,"West Area Adult",4,"PCSB",100,0,6,0,2005]
[null,"West Area Adult",2,"Fed",50,0,2,0,2005]
[null,"West Area Adult at BHS",1,"PCSB",25,0,1,0,2005]
[null,"Westwood Middle",14,"PCSB",293,0,5,9,2010]
[null,"Westwood Middle",2,"Fed",44,0,2,0,2005]
[null,"Winston Elementary",2,"PCSB",36,0,0,2,2010]
[null,"Winston Elementary",4,"Fed",84,0,0,4,2010]
[null,"Winter Haven High",1,"PCSB",25,0,0,1,2010]
[null,"Winter Haven High",2,"Fed",40,0,0,2,2010]
[6,"Polk Total",931,null,17336,0,184,637,359183]
[]
[7,"Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10","5 YEAR TOTAL"]
[null,"Alta Vista Elementary",20,20,0,0,0,0,20]
[null,"Alturas Elementary",8,8,null,0,0,null,8]
[null,"Anna Woodbury Elementary",2,null,1,1,null,null,2]
[null,"Auburndale Central",7,7,{"$nulls":4},7]
[null,"Auburndale High",6,null,6,null,null,null,6]
[null,"Bartow Middle",14,7,7,null,null,null,14]
[null,"Boone Middle",15,15,{"$nulls":4},15]
[null,"Carlton Palmore Elementary",5,null,null,5,null,null,5]
[null,"Churchwell Elementary",8,null,3,5,null,null,8]
[null,"Cleveland Court Elementary",1,null,null,1,null,null,1]
[null,"Combee Elementary",7,null,7,null,null,null,7]
[null,"Crystal Lake Elementary",8,8,{"$nulls":4},8]
[null,"Crystal Lake Middle",6,null,null,3,3,null,6]
[null,"Davenport Elementary",10,10,{"$nulls":4},3]
[null,"Dixieland Elementary",6,null,null,3,3,null,6]
[null,"Dundee Elementary ",4,null,null,2,2,null,4]
[null,"Eagle Lake Elementary",19,10,null,5,4,null,19]
[null,"Eastside Elementary",31,4,6,11,5,5,31]
[null,"Elbert Elementary",5,5,{"$nulls":4},5]
[null,"Floral Avenue Elementary",2,null,null,null,1,1,2]
[null,"Fruitland Park Learning Ctr",8,null,8,null,null,null,8]
[null,"Garner Elementary",2,null,null,null,2,null,2]
[null,"Gause Academy",7,{"$nulls":4},7,7]
[null,"George Jenkins High",15,{"$nulls":4},15,15]
[null,"Gibbons Street Elementary",4,4,{"$nulls":4},4]
[null,"Griffin Elementary",12,{"$nulls":4},12,12]
[null,"Haines City High",23,23,{"$nulls":4},23]
[null,"Highland City Elementary",7,null,7,2,null,null,2]
[null,"Hillcrest Elementary",4,null,4,null,null,null,4]
[null,"Inwood Elementary",7,null,null,null,3,4,7]
[null,"J. H. Wilson Elementary ",4,4,{"$nulls":4},4]
[null,"Jesse Keen Elementary",6,6,{"$nulls":4},6]
[null,"Jewett School of the Arts",7,7,{"$nulls":4},7]
[null,"Kathleen Elementary",3,null,3,null,null,null,3]
[null,"Kathleen Middle",8,null,8,null,null,null,8]
[null,"Kathleen High",14,14,{"$nulls":4},14]
[null,"Kingsford Elementary",7,null,7,null,null,null,7]
[null,"Lake Alfred Elementary",10,null,10,null,null,null,10]
[null,"Lake Gibson High",16,null,16,null,null,null,16]
[null,"Lake Region High",8,null,8,null,null,null,8]
[null,"Lakeland Highlands Middle",11,null,11,null,null,null,11]
[null,"Lena Vista Elementary",1,null,null,null,1,null,1]
[null,"Lewis Elementary",4,null,null,1,1,2,4]
[null,"Lime Street Elementary",9,9,{"$nulls":4},5]
[null,"Lincoln Academy",2,null,2,null,null,null,2]
[null,"Loughman Oaks Elementary",3,3,{"$nulls":4},3]
[null,"Medulla Elementary",5,null,null,5,null,null,5]
[null,"Mulberry Middle",4,null,null,null,4,null,4]
[null,"North Lakeland Elementary",13,null,null,11,1,1,13]
[null,"Oscar Pope Elementary",1,null,null,1,null,null,1]
[null,"Padgett Elementary",9,null,9,null,null,null,9]
[null,"Polk Avenue Elementary",4,null,null,null,4,null,4]
[null,"Polk City Elementary",2,null,null,1,1,null,2]
[null,"Purcell Elementary",11,null,10,1,null,null,11]
[null,"Rochelle School of the Arts",3,null,3,null,null,null,3]
[null,"Sandhill Elementary",4,null,null,4,null,null,4]
[null,"Scott Lake Elementary",4,4,{"$nulls":4},4]
[null,"Sikes Elementary",10,null,8,2,null,null,10]
[null,"Sleepy Hill Middle",4,null,null,null,4,null,4]
[null,"Snively Elementary",10,null,null,6,2,2,10]
[null,"Southwest Elementary",2,null,2,null,null,null,2]
[null,"Southwest Middle",6,null,null,null,6,null,6]
[null,"Spook Hill Elementary",6,null,6,null,null,null,6]
[null,"Stephens Elementary",4,null,4,null,null,null,4]
[null,"Valleyview Elementary",6,null,null,6,null,null,6]
[null,"Wahneta Elementary",8,null,4,2,1,1,8]
[null,"Westwood Middle",6,{"$nulls":4},6,6]
[null,"Winston Elementary",6,null,null,6,null,null,6]
[null,"Winter Haven High",3,null,3,null,null,null,3]
[]
[7,"Polk Total",517,168,163,84,48,56,501]
[]
[8,"Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2005-06","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2009-10","FISH Stu. Sta.","# Years Leased "]
[null,"Polk Ave El",3,"Williams Scottsman",54,1,0]
[null,"Union Middle Academy",1,"Williams Scottsman",22,1]
[null,"Haines City High",18,"Williams Scottsman",750,1,0,0,0]
[null,"Superintendent's Office",1,"Williams Scottsman",0,2,0,0,0]
[8,"Polk Total",23,null,826,5,0,0,854]
[]
[9,"Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2009-10"]
[null,"Achievement Academy/CDC",20,"Achievement Acad/CDC","1997-98",89,79,10,150]
[null,"STAR Charter",6,"Early Childhood/STAR","1999-00",108,94,3,145]
[null,"ACE",1,"Cen. Fl. Speech & Hear","2000-01",15,12,5,15]
[null,"McKeel Academy",56,"PCSB","1998-99",1344,967,7,1000]
[null,"Foundation Charter",9,"Cen. Fl. Human Svcs.","1997-98",150,150,5,150]
[null,"Apple School",13,"6/Apple&4/Presbeterian","1996-97",170,154,10,254]
[null,"Hartridge Academy",10,"Annan, Inc.","2001-02",256,115,5,136]
[null,"Discovery Academy @ Lake Alfred",58,"PCSB","2001-02",1014,993,1,1014]
[null,"Ridgeview Global Studies",35,"PCSB","2001-02",850,750,5,682]
[null,"Compass Middle Charter",11,"PCSB","2002-03",275,168,3,200]
[null,"McKeel Elementary Academy",21,"McKeel El. Academy","2003-04",396,396,3,396]
[null,"Berkley Charter School",40,"PCSB","2003-04",556,556,3,780]
[null,"PCC Collegiate High School",6,"Polk Community College","2004-05",210,166,3,250]
[null,"Lakeland Montessori Schoolhouse",3,"Charles Bunch","2004-05",99,66,3,130]
[null,"Polk Avenue Elementary",34,"PCSB","2004-05",659,444,3,500]
[null,"Janie Howard Wilson",37,"PCSB","2004-05",880,600,3,669]
[null,"Hillcrest Elementary",37,"PCSB","2004-05",718,614,3,600]
[null,"Babson Park Elementary",33,"PCSB","2004-05",484,452,3,484]
[null,"Lake Wales High School",59,"PCSB","2004-05",1987,1417,3,1560]
[null,"Berkley Accelerated Middle",5,"First Bapt. Church/Aub.","2004-05",110,104,3,500]
[null,"Life Skills",0,"Management Co.","2005-2006",150,150,1,600]
[null,"Haines City Literacy Learning Aca",11,"PCSB","2004-05",197,162,3,500]
[]
[9,"Polk Total",1163,null,null,10839,8671,153,8671]
[]
[10,"Plans approved by the school board that reduce the need for permanent student stations such as acceptable school capacity levels, redistricting, "]
[null,"busing, year-round schools, charter schools, magnet schools, public-private partnerships, multitrack scheduling, grade level organization,"]
[null," block scheduling, or other alternatives."]
[]
[]
[]
[]
[11,"Average Class Size (5 years out -- 2009-10) that will result if the district facilities work plan is fully implemented."]
[{"$nulls":5},"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","# CLASSROOMS","Capacity (NOT Stu Sta)","2004-05 CO-FTE","2004-05 Class size","2009-10 CO-FTE","be added (removed)","2009-10 Class size"]
[null,"Alta Vista Elementary",49,978,773,15.78,850.3000000000001,-3,18.48]
[null,"Alturas Elementary",20,331,283,14.15,311.3,-2,17.29]
[null,"Anna Woodbury Elementary","See Lewis/Anna Woodbury",null,null,null,0]
[null,"Auburndale Central Elementary",36,520,373,10.36,410.3,2,10.8]
[null,"Auburndale High",103,2167,1754,17.03,1929.4,-6,19.89]
[null,"Babson Park Elementary",32,562,445,13.91,489.50000000000006,null,15.3]
[null,"Bartow Academy",20,395,386,19.3,424.6,6,16.33]
[null,"Bartow Middle",64,1350,846,13.22,930.6,2,14.1]
[null,"Bartow High",95,2114,1223,12.87,1345.3000000000002,null,14.16]
[null,"Ben Hill Griffin Elementary",39,724,381,9.77,419.1,8,8.92]
[null,"Berkley Elementary",34,634,564,16.59,620.4000000000001,8,14.77]
[null,"Bethune Academy",25,480,442,17.68,486.20000000000005,6,15.68]
[null,"Bill Duncan Opportunity Center",26,315,210,8.08,231.00000000000003,null,8.88]
[null,"Brigham Academy",35,728,591,16.89,650.1,6,15.86]
[null,"Carlton Palmore Elementary",39,784,690,17.69,759.0000000000001,3,18.07]
[null,"Clarence Boswell Elementary",40,779,534,13.35,587.4000000000001,null,14.69]
[null,"Cleveland Court Elementary",25,232,458,18.32,503.80000000000007,-1,20.99]
[null,"Combee Elementary",43,862,669,15.56,735.9000000000001,1,16.73]
[null,"Crystal Lake Elementary",42,817,643,15.31,707.3000000000001,null,16.84]
[null,"Crystal Lake Middle",58,1265,906,15.62,996.6000000000001,6,15.57]
[null,"Davenport Elementary",43,693,566,13.16,622.6,13,11.12]
[null,"Denison Middle",65,1238,971,14.94,1068.1000000000001,null,16.43]
[null,"Discovery Academy at LK Alfred",64,1268,983,15.36,1081.3000000000002,null,16.9]
[null,"Dixieland Elementary",27,502,516,19.11,567.6,-1,21.83]
[null,"Donald E Woods Center",18,174,218,12.11,239.8,null,13.32]
[null,"Doris A Sanders Learning Center",19,106,107,5.63,117.7,null,6.19]
[null,"Dr. N. E. Roberts Elementary ",44,918,836,19,919.6,8,17.68]
[null,"Dundee Elementary",64,1356,488,7.63,536.8000000000001,-31,16.27]
[null,"Dundee Ridge Middle",66,1405,1029,15.59,1131.9,null,17.15]
[null,"Dwight C Smith Center",30,237,108,3.6,118.80000000000001,null,3.96]
[null,"Eagle Lake Elementary",45,960,651,14.47,716.1,-3,17.05]
[null,"Eastside Elementary",55,1124,996,18.11,1095.6000000000001,null,19.92]
[null,"Edgar L Padgett Elementary",43,948,630,14.65,693,3,15.07]
[null,"Elbert Elementary",36,750,494,13.72,543.4000000000001,2,14.3]
[null,"Floral Avenue Elementary",46,828,589,12.8,647.9000000000001,-2,14.73]
[null,"Fort Meade Middle Senior High",60,1254,765,12.75,841.5000000000001,null,14.03]
[null,"Fred G Garner Elementary",54,974,627,11.61,689.7,-1,13.01]
[null,"Frostproof Elementary",37,706,423,11.43,465.3,null,12.58]
[null,"Frostproof Middle Senior High",82,1765,1201,14.65,1321.1000000000001,null,16.11]
[null,"Fruitland Park Learning Center",18,242,109,6.06,119.9,-8,11.99]
[null,"Garden Grove Elementary",40,848,749,18.73,823.9000000000001,null,20.6]
[null,"Gause Academy of Applied Tech",36,728,263,7.31,289.3,5,7.06]
[null,"Gause Riverside Academy",170,170,69,0.41,75.9,75.9,0.31]
[null,"George Jenkins High",113,2147,2094,18.53,2303.4,-15,23.5]
[null,"Gibbons Street Elementary",26,526,334,12.85,367.40000000000003,-3,15.97]
[null,"Griffin Elementary",36,738,561,15.58,617.1,-7,21.28]
[null,"Haines City High",119,2963,2051,17.24,2256.1000000000004,-46,30.91]
[null,"Harrison Arts Center",9,140,145,16.11,159.5,null,17.72]
[null,"Highland City Elementary",30,571,463,15.43,509.30000000000007,8,13.4]
[null,"Hillcrest Elementary",38,791,593,15.61,652.3000000000001,null,17.17]
[null,"Homer K Addair Career Academy",44,936,441,10.02,485.1,null,11.03]
[null,"Inwood Elementary",29,506,562,19.38,618.2,-3,23.78]
[null,"J Daniel Jenkins Academy",26,581,315,12.12,346.5,null,13.33]
[null,"James E Stephens Elementary",36,631,506,14.06,556.6,4,13.92]
[null,"James W Sikes Elementary",54,1130,687,12.72,755.7,-2,14.53]
[null,"Janie Howard Wilson Elementary",44,880,594,13.5,653.4000000000001,2,14.2]
[null,"Jere L Stambaugh Middle",64,1218,977,15.27,1074.7,null,16.79]
[null,"Jesse Keen Elementary",45,868,537,11.93,590.7,2,12.57]
[null,"Jewett School of the Arts",48,896,727,15.15,799.7,1,16.32]
[null,"Jewett Middle Academy",34,801,573,16.85,630.3000000000001,null,18.54]
[null,"John Snively Elementary",37,707,520,14.05,572,-4,17.33]
[null,"Kathleen Elementary",34,670,563,16.56,619.3000000000001,7,15.1]
[null,"Kathleen Middle",54,1130,822,15.22,904.2,2,16.15]
[null,"Kathleen High",95,1832,1493,15.72,1642.3000000000002,21,14.16]
[null,"Kingsford Elementary",33,690,483,14.64,531.3000000000001,1,15.63]
[null,"Lake Alfred Elementary",32,681,464,14.5,510.40000000000003,2,15.01]
[null,"Lake Gibson Middle",72,1314,1088,15.11,1196.8000000000002,null,16.62]
[null,"Lake Gibson High",97,2111,1676,17.28,1843.6000000000001,null,19.01]
[null,"Lake Region High",106,2174,1938,18.28,2131.8,-8,21.75]
[null,"Lake Shipp Elementary",39,833,601,15.41,661.1,null,16.95]
[null,"Lake Wales High",93,1887,1349,14.51,1483.9,null,15.96]
[null,"Lakeland Highlands Middle",63,1225,1081,17.16,1189.1000000000001,1,18.58]
[null,"Lawton Chiles Middle Academy",28,680,565,20.18,621.5,8,17.26]
[null,"Lakeland High ",109,2409,2123,19.48,2335.3,null,21.42]
[null,"Lena Vista Elementary",48,1011,688,14.33,756.8000000000001,-1,16.1]
[null,"Lewis/Anna Woodbury ",56,1199,1184,21.14,1302.4,-5,25.54]
[null,"Lime Street Elementary",31,617,546,17.61,600.6,7,15.81]
[null,"Lincoln Academy",29,527,492,16.97,541.2,8,14.63]
[null,"Loughman Oaks Elementary",51,920,815,15.98,896.5000000000001,5,16.01]
[null,"Traviss Vocational Technical Center",95,1316,930,9.79,1023.0000000000001,null,10.77]
[null,"Mckeel Academy",70,1183,944,13.49,1038.4,null,14.83]
[null,"McLaughlin Middle",62,1412,888,14.32,976.8000000000001,null,15.75]
[null,"Medulla Elementary",48,987,693,14.44,762.3000000000001,1,15.56]
[null,"Mulberry Middle",49,1014,820,16.73,902.0000000000001,8,15.82]
[null,"Mulberry High ",65,1261,887,13.65,975.7,null,15.01]
[null,"North Lakeland Elementary",49,972,693,14.14,762.3000000000001,-13,21.18]
[null,"Oscar J Pope Elementary",52,975,382,7.35,420.20000000000005,-1,8.24]
[null,"Pinewood Elementary",34,634,580,17.06,638,10,14.5]
[null,"Polk Avenue Elementary",35,752,452,12.91,497.20000000000005,null,14.21]
[null,"Polk City Elementary",40,790,534,13.35,587.4000000000001,-2,15.46]
[null,"Polk Life and Learning Center",21,148,52,2.48,57.2,null,2.72]
[null,"Purcell Elementary",34,604,452,13.29,497.20000000000005,-1,15.07]
[null,"R. Bruce Wagner Elementary",44,956,672,15.27,739.2,8,14.22]
[null,"R Clem Churchwell Elementary",38,778,586,15.42,644.6,9,13.71]
[null,"Ridge Vocational Technical Center",71,1017,706,9.94,776.6,null,10.94]
[null,"Ridgeview Elementary",44,862,715,16.25,786.5000000000001,6,15.73]
[null,"Rochelle School of the Arts",49,926,791,16.14,870.1,17,13.18]
[null,"Roosevelt Academy",43,281,343,7.98,377.3,null,8.77]
[null,"Rosabelle W Blake Elementary",49,861,583,11.9,641.3000000000001,null,13.09]
[null,"Sandhill Elementary",48,958,944,19.67,1038.4,2,20.77]
[null,"Scott Lake Elementary",49,1008,865,17.65,951.5000000000001,-4,21.14]
[null,"Shelley S Boone Middle",65,1235,1043,16.05,1147.3000000000002,2,17.12]
[null,"Sleepy Hill Middle",63,1378,1058,16.79,1163.8000000000002,6,16.87]
[null,"Socrum Loop Elementary",45,803,602,13.38,662.2,10,12.04]
[null,"Southwest Elementary",31,628,499,16.1,548.9000000000001,8,14.07]
[null,"Southwest Middle",58,1259,953,16.43,1048.3000000000002,null,18.07]
[null,"Spook Hill Elementary",40,763,522,13.05,574.2,2,13.67]
[null,"Union Academy",26,527,404,15.54,444.40000000000003,null,17.09]
[null,"Valleyview Elementary",64,1163,1125,17.58,1237.5,-6,21.34]
[null,"Wahneta Elementary",37,708,565,15.27,621.5,-8,21.43]
[null,"Walter Caldwell Elementary",42,797,688,16.38,756.8000000000001,null,18.02]
[null,"Wendell Watson Elementary",49,875,761,15.53,837.1,null,17.08]
[null,"Westwood Middle",65,1373,1005,15.46,1105.5,null,17.01]
[null,"Winston Elementary",45,869,597,13.27,656.7,-6,16.84]
[null,"Winter Haven High",103,1962,1753,17.02,1928.3000000000002,5,17.85]
[11,"Polk Total",5711,108206,82297,"District Avg 14",90526.70000000001,134.9,"District Avg 15"]
[]
[12,"The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[null,"Please see attached explanation of work plan for additional details"]
[null,"Site                              ",null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10","5 YEAR AVERAGE"]
[null,"Alta Vista Elementary",null,270,128,110,92,74,{"$error":"#DIV/0!"}]
[null,"Alturas Elementary",null,144,62,44,26,26,{"$error":"#DIV/0!"}]
[null,"Anna Woodbury Elementary",null,36,21,0,0,0,{"$error":"#DIV/0!"}]
[null,"Auburndale Central Elementary",null,126,111,0,0,0,134.8]
[null,"Auburndale High",null,150,0,0,0,0,60.4]
[null,"Babson Park Elementary",null,97,97,97,97,97,11.4]
[null,"Bartow Elementary",null,72]
[null,"Bartow Middle",null,308,159,159,159,0,47.4]
[null,"Bartow High",null,125,41,41,41,41,30]
[null,"Berkley Elementary",null,36]
[null,"Bill Duncan Opportunity Center",null,32,48,48,48,48,97]
[null,"Blake Elementary",null,72,18,18,18,18,157]
[null,"Boone Middle",null,330,204,0,0,0,57.8]
[null,"Boswell Elementary",null,54]
[null,"Brigham Academy",null,54]
[null,"Caldwell Elementary",null,234,68,68,68,68,44.8]
[null,"Carlton Palmore Elementary",null,162,103,0,0,0,28.8]
[null,"Chain of Lakes Elementary",null,108]
[null,"Churchwell Elementary",null,144,0,0,0,0,106.8]
[null,"Cleveland Court Elementary",null,72]
[null,"Combee Elementary",null,180,0,0,0,0,101.2]
[null,"Crystal Lake Elementary",null,144,129,21,0,0,53]
[null,"Crystal Lake Middle",null,132,56,56,0,0,28.8]
[null,"Davenport Elementary",null,180,58,0,0,0,36]
[null,"Dixieland Elementary",null,108,78,60,60,60,58.8]
[null,"Don E Woods Opportunity Center",null,32,32,32,32,32,48.8]
[null,"Dr. N.E. Roberts Elementary",null,252]
[null,"Dundee Elementary",null,72,0,0,0,0,47.6]
[null,"Eagle Lake Elementary",null,342,303,285,267,249,73.2]
[null,"East Area Adult Center",null,147,147,147,147,147,32]
[null,"Eastside Elementary",null,558,126,126,126,126,14.4]
[null,"Elbert Elementary",null,70,70,0,0,0,289.2]
[null,"Floral Avenue Elementary",null,198,225,207,189,189,147]
[null,"Fort Meade Middle/Senior High",null,175,38,38,38,38,212.4]
[null,"Frostproof Elementary",null,18,44,44,44,44,28]
[null,"Frostproof Middle/Senior High",null,275,184,184,184,184,201.6]
[null,"Fruitland Park Learning Center",null,68,0,0,0,0,65.4]
[null,"Garner Elementary",null,36,48,30,30,30,38.8]
[null,"Gause Academy",null,172,172,0,0,0,202.2]
[null,"George Jenkins High",null,475,0,0,0,0,13.6]
[null,"Gibbons Street Elementary",null,180,31,13,0,0,34.8]
[null,"Griffin Elementary",null,216,156,0,0,0,68.8]
[null,"Haines City High",null,275,0,0,0,0,95]
[null,"Highland City Elementary",null,126,46,0,0,0,44.8]
[null,"Hillcrest Elementary",null,72,98,26,8,0,74.4]
[null,"Inwood Elementary",null,126,84,66,48,30,55]
[null,"Janie Howard Wilson",null,126,81,0,0,0,34.4]
[null,"Jesse Keen Elementary",null,144,151,7,0,0,40.8]
[null,"Jewett Elementary Arts",null,180,0,0,0,0,70.8]
[null,"Jewett Mid Academy",null,66]
[null,"Kathleen Elementary",null,72,0,0,0,0,41.4]
[null,"Kathleen Middle",null,220,0,0,0,0,60.4]
[null,"Kathleen High",null,325,141,0,0,0,36]
[null,"Kingsford Elementary",null,126,0,0,0,0,14.4]
[null,"Lake Alfred Elementary",null,164,0,0,0,0,44]
[null,"Lake Gibson Middle",null,95,95,95,95,95,93.2]
[null,"Lake Gibson High",null,575,0,0,0,0,25.2]
[null,"Lake Region High",null,350,0,0,0,0,32.8]
[null,"Lake Ship Elementary",null,25]
[null,"Lake Wales High",null,200,169,169,169,169,95]
[null,"Lakeland Highlands Middle",null,374,0,0,0,0,115]
[null,"Lakeland Sr High",null,125]
[null,"Lawton Chiles Mid Academy",null,88]
[null,"Lena Vista Elementary",null,141,98,80,80,80,70]
[null,"Lewis Elementary",null,126,138,120,102,66,175.2]
[null,"Lime Street Elementary",null,162,0,0,0,0,74.8]
[null,"Lincoln Elementary Academy",null,90,0,0,0,0,95.8]
[null,"Loughman Oaks Elementary",null,342,0,0,0,0,110.4]
[null,"Mark Wilcox Center",null,82,82,82,82,82,32.4]
[null,"McKeel Academy",null,41,41,41,41,41,18]
[null,"McLaughlin Middle",null,25,25,25,25,25,68.4]
[null,"Medulla Elementary",null,126,77,0,0,0,82]
[null,"Mulberry Middle",null,88,88,88,0,0,41]
[null,"Mulberry Sr High",null,75]
[null,"North Lakeland Elementary",null,200,243,23,5,0,25]
[null,"Oscar J Pope Elementary",null,18,18,0,0,0,40.6]
[null,"Padgett Elementary",null,193,0,0,0,0,52.8]
[null,"PEER Center",null,53,53,53,53,53,94.2]
[null,"Pinewood Elementary",null,36]
[null,"Polk Avenue Elementary ",null,126,67,67,0,0,7.2]
[null,"Polk City Elementary",null,108,68,50,32,32,38.6]
[null,"Polk Life and Learning Center",null,28,28,28,28,28,53]
[null,"Purcell Elementary",null,252,33,15,15,15,52]
[null,"R Bruce Wagner Elementary",null,90]
[null,"Ridge Technical Center",null,385,350,350,350,350,58]
[null,"Riverside Gause Elementary",null,24,24,24,24,24,28]
[null,"Rochelle School of the Arts",null,324,54,0,0,0,66]
[null,"Roosevelt Academy",null,29,29,29,29,29,357]
[null,"Sandhill Elementary",null,576,96,0,0,0,24]
[null,"Scott Lake Elementary",null,360,100,0,0,0,75.6]
[null,"Sikes Elementary",null,144,78,0,0,0,29]
[null,"Sleepy Hill Middle",null,242,73,73,0,0,134.4]
[null,"Snively Elementary",null,360,270,162,126,90,92]
[null,"Socrum Elementary",null,36]
[null,"Southwest Elementary",null,90,7,7,0,0,44.4]
[null,"Southwest Middle",null,242,185,185,53,53,77.6]
[null,"Spook Hill Elementary",null,108,0,0,0,0,201.6]
[null,"Stambaugh Middle",null,23,23,23,23,23,20.8]
[null,"Stephens Elementary",null,126,0,0,0,0,143.6]
[null,"Traviss Technical Center",null,197,197,197,197,197,21.6]
[null,"Union Academy",null,88,20,20,20,20,23]
[null,"Valleyview Elementary",null,180,107,0,0,0,25.2]
[null,"Wahneta Elementary",null,270,109,73,55,37,197]
[null,"Wendell Watson Elementary",null,90]
[null,"West Area Adult",null,200,158,158,158,158,33.6]
[null,"West Area Adult at BHS",null,25,25,25,25,25,57.4]
[null,"Westwood Middle",null,352,278,278,278,146,108.8]
[null,"Winston Elementary",null,90,129,0,0,0,90]
[null,"Winter Haven High",null,100,0,0,0,0,25,null,"State Average","State Average","State Average","State Average","State Average","State Average"]
[12.1,"Polk Total students in relocatables by year",null,17573,7193,4467,3787,3339,266.4,"Year",2004,2004,2004,2004,2004,2004]
[12.2,"Polk Total number of CO-FTE students projected by year",null,83351,84621,85783,87049,88517,{"$error":"#REF!"},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[12.3,"Polk Percent in relocatables by year",null,0.21,0.09,0.05,0.04,0.04,{"$error":"#REF!"},1,96,127,247,11269,15778,23876]
[]
[13,"Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"NA"]
[]
[]
[14,"Projects for which capital outlay and debt service funds accruing under s. 9(d), Art. XII of the State Constitution are to be used shall be identified "]
[null,"separately in priority order on a project priority list within the district faciliteis work program."]
[null,"Projects to be implementd with CO & DS funds in ranked order:"]
[null,"Project Description:"]
[null,"NA"]
[]
[]
[]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
[15,"The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2004,2004,2004,2004,2004,2004]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,93,144,9309,13008,24934]
[null,"2004 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 93, high 144; Middle low 56, avg 69, high 114; High School low 89, avg 104, high 116 ",{"$nulls":7},2,56,69,114,9761,11179,14377]
[null,"2004 State-wide totals - Cost per student station: Elem low 9,309, avg 13,008, high 24,934; Middle low 9,761 avg 11,179, high 14,377; High School low 16,455, avg 19,304, high  21,827 ",{"$nulls":7},3,89,104,116,16455,19304,21827]
[]
["15A","2005-06 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2005-06 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2005 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Elementary A","Elementary",17000000,800]
[null,"Elementary B","Elementary",17000000,800]
[null,"New High School BBB","High School",38000000,1200]
[null,"Carlton Palmore 8 Cr add","Elementary",16000000,144]
[null,"Crystal Lake Ele 8 Cr Add","Elementary",17000000,144]
[null,"Davenport El 16 Cr Add","Elementary",3175000,288]
[null,"Roberts Elementary 8 Cr Add","Elementary",1586000,144]
[null,"Hillcrest El 4 Cr Add","Elementary",790000,72]
[null,"J H Wilson Ele 6 Cr Add","Elemenatry",1187000,108]
[null,"Medulla Ele 6 Cr Add","Elementary",1200000,108]
[null,"Snively El 6 Cr Add","Elementary",1200000,108]
[null,"Eagle Lake Ele 10 Cr Add","Elementary",2200000,180]
[null,"Scott lake El 8 Cr Add","Elementary",2200000,144]
[null,"Ben Hill griffin El 8 Cr Add","Elementary",1636000,144]
[null,"Boone Middle","Middle School",2200000,220]
["15A","Polk Total 2005-06",null,122374000,4604,0,0,26579.93,{"$nulls":4},26579.93]
[]
["15B","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07 ","2006-07 ","2006-07 ","2006-07 ","2006-07 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2004 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Middle School BBB ",2,24000000,850]
[null,"Gibbons Street Ele 4Cr Add",1,747000,72]
[null,"Highland City El 10 Cr Add",1,2020000,180]
[null,"Jesse Keen 8 Cr Add",1,1636000,144]
[null,"Wagner Elementray 8 Cr Add",1,1536000,144]
[null,"Ridgeview Acad 6 Cr Add",1,1150000,108]
[null,"Sandhill El 6 Cr Add",1,1150000,108]
[null,"Socrum El 10 Cr Add",1,2300000,180]
[null,"Berkley Ele 10 Cr Add",1,2800000,180]
[null,"Crystal Lake Middle",2,1850000,176]
["15B","Polk Total 2006-07",12,39189000,97634527,0,0,0.4,{"$nulls":4},0.4]
[]
["15C","2007-2008 Year","Type of School (new schools only)  Others=0","2007-08","2007-08","2007-08","2007-08","2007-08 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2005 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"High School CCC",3,60000000,1200]
[null,"Kathleen Sr 30 Cr Add",3,6900000,750]
[null,"Elementary C",1,18000000,650]
["15C","Polk Total 2007-08",null,84900000,2600,{"$error":"#REF!"},{"$error":"#REF!"},32653.85,{"$nulls":4},32653.85]
[]
["15D","2008-2009 Year","Type of School (new schools only)  Others=0","2008-09","2008-09","2008-09","2008-09","2008-09 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2006 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Mulberry Middle School 12 Cr Add",2,2880000,264]
[null,"Elementary D",1,18000000,650]
["15D","Polk Total 2008-09",null,20880000,914,{"$error":"#REF!"},{"$error":"#REF!"},22844.64,{"$nulls":4},22844.64]
[]
["15E","2009-2010 Year","Type of School (new schools only)  Others=0","2009-10","2009-10","2009-10","2009-10","2009-10 Projected",null,"2004 State Avg","2004 State Avg","2004 State Avg","2007 Projected","2004 State Avg","2004 State Avg","2004 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","COST/per StuSta",null,"GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[]
[]
[]
[]
[]
["15E","Polk Total 2009-10",null,0,0,0,{"$error":"#DIV/0!"},{"$error":"#DIV/0!"},{"$nulls":4},{"$error":"#DIV/0!"}]
[]
[15,"Polk 5-Year Total",null,267343000,97642645,{"$error":"#REF!"}]
[]
[16,"Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.1011.71",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.1011.71",null,44889174,47133633,49490315,51964831,54563073,248041026]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,44889174,47133633,49490315,51964831,54563073,248041026,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,3557450,3824259,4111078,4419409,4750865,20663061,0.0833050134214491]
[null,"  less amount used to purchase other vehicles",null,".",".",".",".",".",0,0]
[null,"  less amount transferred to op. bud for minor maint/repair projects",null,5000000,5500000,6050000,6655000,7320500,30525500,0.123066335002178]
[null,"  less amount trnsfrd to op bud for salaries assoc w/maintenance/repair projects",null,8400000,8820000,9261000,9724050,10210253,46415303,0.187127523815355]
[null,"  less amount used for minor maint/repair projects",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase capital outlay equipment",null,5361338,5629405,5910875,6206419,6516740,29624777,0.119434988145872]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,17507614,17507250,17507513,17508411,17106139,87136927,0.351300461884076]
[null,"  less other (please be specific)",null,2262772,2852719,2649849,2451542,3658576,13875458,0.0559401733808342,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,2800000,3000000,4000000,5000000,5000000,19800000,0.079825504350236,0.04]
[null,"P E C O New Construction",null,6043261,2658239,2718291,2718291,2718291,16856373,null,0.03]
[null,"P E C O Maintenance Dollars (NOT added in totals - can't be used for New Const.)",null,6739434,6739434,6739434,6739434,6739434,33697170,null,0.06,null,null,4608674]
[null,"C O & D S   Bond Proceeds ",null,375000,375000,375000,375000,375000,1875000,null,0]
[null,"C O & D S maximum potential bond proceeds",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,34500000,35190000,35893800,36611676,37343910,179539386,null,0.34]
[null,"Less: Debt Service on Sales Tax Revenue Bonds",null,-13657313,-13661712,-13658232,-13657130,-13657870,-68292257,null,-0.13]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,40546472,0,40546472,null,0.08]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Grants",null,0,0,0,0,0,0,null,0]
[null,"Classrooms for Kids",null,3539589,0,0,0,0,3539589,null,0.01]
[null,"District Equity Recognition",null,0,0,0,0,0,0,null,0]
[null,"Federal Grants",null,0,0,0,0,0,0,null,0]
[null,"Impact fees received",null,46000000,70073000,71474460,72903949,74362028,334813437,null,0.63]
[null,"Private donations",null,0,0,0,0,0,0,null,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
[16,"Polk Total",null,79600537,97634527,100803319,144498258,106141359,528678000,1.0000000000000004,1.06]
[]
[17,"Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 16 above."]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"New Elementary A",650,1700000]
[null,"New Elementary B",650,1700000]
[null,"New High School BBB",1800,35000000,3000000]
[null,"Boone Kitchen Addition",null,640000]
[null,"Carlton Palmore 8 Cr add",null,1600000]
[" ","Crystal Lake Ele 8 Cr add/art",null,1700000]
[null,"Davenport 16 cr",288,3175000]
[null,"Dr. NE Roberts 8 cr",144,1586000]
[null,"Hillcrest 4 cr",72,790000]
[null,"JH Wilson 6 cr",108,1187000]
[null,"Medulla 6 cr",108,1200000]
[null,"Snively 6 cr  ",108,1200000]
[null,"Transportation 800 mhz Radio System",null,4000000,4000000]
[null,"Blake Kit Remodel",null,200000]
[null,"Eagle Lake 10 cr",180,2200000]
[null,"Frostproof El Kit Remodel",null,700000]
[null,"Jewett Arts Kit/Din Remodel",null,1000000]
[null,"Scott Lake 8 cr",144,2200000]
[null,"Adale Cent Rebuild",null,3650000,2000000]
[null,"Adale Sr. Fire Sprinkler",null,420000]
[null,"Adale Sr. Remodel Audit.",null,500000]
[null,"Alturus Café",null,1260000]
[null,"Ben Hill Griffin 8 cr",144,1636000]
[null,"Boone 10 cr",220,2200000]
[null,"Harrison Arts Expansion",null,8156537,843527]
[null,"Lake Wales Sr- New Cafeteria",null,null,3500000]
[null,"Kathleen Sr-MP, ",null,null,6000000]
[null,"Bartow Sr-MP Phase IV",null,null,1920000]
[null,"Portable Classrooms ",null,null,4000000,4000000,4000000]
[null,"Stambaugh Middle-Gym remodel and renovation",null,null,2000000]
[null,"Transportation Garage - North Central",null,null,null,10000000]
[null,"Maintenance Shop - UA - 1 Replacement",null,null,1500000]
[null,"Dundee Ridge - Brick Facade",null,null,1000000]
[null,"Middle BB",850,null,24000000]
[null,"Boone Ag/Sci",null,null,1030000]
[null,"Crystal Lake El Media",null,null,650000]
[null,"Crystal Lake Mid Media",null,null,542000]
[null,"Eastside 4 cr/media",72,null,2620000]
[null,"Fruitland Park remodel Ph 2",null,null,400000]
[null,"Gibbons St 4 cr",72,null,747000]
[null,"Highland City 10 cr",180,null,2020000]
[null,"Jesse Keen 8 cr",144,null,1636000]
[null,"Lime St Café remodel",null,null,1300000]
[null,"R. B. Wagner 8 cr",144,null,1536000]
[null,"Ridgeview 6 cr",108,null,1150000]
[null,"Sandhill 6 cr",108,null,1150000]
[null,"Socrum 10 cr",108,null,2300000]
[null,"Warehouse Dist expand",null,null,450000]
[null,"Bartow Ac Kit/Din Remodel",null,null,700000]
[null,"Caldwell Kit/Din Remodel",null,null,450000]
[null,"Berkely 10 cr",180,null,2800000]
[null,"Crystal Lake Mid 8 cr",176,null,1850000]
[null,"District Office media ser blg",null,null,1500000]
[null,"Hillcrest renov bldg 4-office",null,null,800000]
[null,"Jewett El café expand",null,null,1200000]
[null,"Kathleen Mid chorus/band",null,null,2000000]
[null,"Kathleen Sr. demo 1,5,13,16",null,null,740000]
[null,"Land Purchases for BBB, A-D, BB, CC",null,null,8800000]
[null,"Portables",null,null,4000000,3000000,5000000,3000000]
[null,"Small Projects  (Pushed back from original year)",null,null,1500000,1500000,1500000,1500000]
[null,"Satellite Offices (four) - Itenerants",null,null,null,4000000]
[null,"Traviss Update",null,null,null,6000000]
[null,"Dwight Smith/Karen Siegel Center - Ridge Area",null,null,null,10000000,10900000]
[null,"Boone Middle-Revised Master Plan",null,null,null,6000000,2000000]
[null,"Auburndale Sr-MP Phase III,",null,null,null,9741319]
[null,"Auburndale Sr-MP Phase IV",null,null,null,2600000,null,5000000]
[null,"Additional Elementary Schools (3) - TBA",null,null,null,18000000,36000000]
[null,"Union Academy - Fine arts, music suite",null,null,null,2712000]
[null,"High School CCC",1600,null,null,null,30000000,28000000]
[null,"Kathleen Sr. 30 cr addition",750,null,null,3450000,3498258]
[null,"Elementary C",650,null,null,17000000]
[null,"Inwood Kit Remodel",null,null,null,800000]
[null,"Snively Kit/Din Remodel",null,null,null,800000]
[null,"Southwest El Kit Remodel",null,null,null,1200000]
[null,"Mulberry Mid 12 cr",264,null,null,null,2880000]
[null,"Lake Wales Sr Home Ec ste",{"$nulls":4},1300000]
[null,"Elementary D",650,null,null,null,21000000]
[null,"Alta Vista relocate/remodel media",{"$nulls":4},300000]
[null,"Dundee Ele Expand parking ",{"$nulls":4},150000]
[null,"Dundee Ele New PE area",{"$nulls":4},170000]
[null,"Eastside Din Remodel",{"$nulls":4},1200000]
[null,"Ft Meade Sr Rem Boys/Girls locker rms",{"$nulls":4},250000]
[null,"Ft. Meade Sr Press Box",{"$nulls":4},200000]
[null,"Garden Grove HVAC",{"$nulls":4},750000]
[null,"Gibbons St Kit Remodel",{"$nulls":4},700000]
[null,"Lake Gibson Mid Fire Sprinkler",{"$nulls":4},400000]
[null,"McKeel Aca Fire Sprinkler",{"$nulls":4},550000]
[null,"N. Lakeland Din Remodel",{"$nulls":4},750000]
[null,"Elementary School - Southwest Lakeland",650,null,null,null,21000000]
[null,"Combee El - Expand and remodel media",{"$nulls":5},250000]
[null,"Denison Middle-Expand kitchen and dining",{"$nulls":5},650000]
[null,"District Office- expand the auditorium",{"$nulls":5},320000]
[null,"Hillcrest El-Renovate admin",{"$nulls":5},450000]
[null,"Hillcrest El-Expand and renovate cafeteria",{"$nulls":5},750000]
[null,"Lime Street El-convert media into music & multipurpose",{"$nulls":5},225000]
[null,"Lime Street-Expand admin & guidance",{"$nulls":5},250000]
[null,"Mulberry Sr-Demolish bldgs 1 &25, replace&varsity lockers",{"$nulls":5},1250000]
[null,"Mulberry Sr-Remodel Ag facility",{"$nulls":5},200000]
[null,"Mulberry Sr-Remodel Industrial Arts Bldg",{"$nulls":5},200000]
[null,"Altruas El-Demolish Bldg 1, Construct new admin/classrooms",{"$nulls":5},2000000]
[null,"Bartow Sr- MP Phase I",{"$nulls":5},1080000]
[null,"Cleveland Court El-Remodel classrooms",{"$nulls":5},501120]
[null,"Crystal Lake El-Remodel media center for ESE and resource",{"$nulls":5},226120]
[null,"Griffin El- Renovate bldgs 2 and 3 for art, music, labs",{"$nulls":5},1200000]
[null,"Winter Haven Sr-Phase I Master Plan",{"$nulls":5},3176119]
[null,"Babson Park El-Demolish bldg 3 and construct new art suite",{"$nulls":5},600000]
[null,"Kathleen El-Remodel media center",{"$nulls":5},500000]
[null,"Kingsford El-New media center",{"$nulls":5},1300000]
[null,"Lakeland Sr-MP - Phase 2a, renovate remaining classrooms",{"$nulls":5},5000000]
[null,"Polk City El-Construct media center and remodel existing",{"$nulls":5},1200000]
[null,"Ridge Tech-Replace roofs",{"$nulls":5},1000000]
[null,"Southwest Middle-New admin",{"$nulls":5},3000000]
[null,"Stambaugh Middle-Replace HVAC system",{"$nulls":5},1000000]
[null,"Kingford El-remodel old media center into art/music",{"$nulls":5},500000]
[null,"Auburndale Sr-MP Phase 2, Media center and classrooms",{"$nulls":5},3356000]
[null,"Bartow Middle-Expand Admin ",{"$nulls":5},750000]
[null,"District Office-Data/Technology Center",{"$nulls":5},23000000]
[null,"Eastside El-Remodel bldg 4 for admin",{"$nulls":5},1300000]
[null,"Floral Ave-Expand admin",{"$nulls":5},500000]
[null,"Hillcrest El-Expand media center",{"$nulls":5},800000]
[null,"Jewett SOA-Expand admin suite",{"$nulls":5},475000]
[null,"Lake Alfred El-Expand cafeteria",{"$nulls":5},750000]
[null,"Lake Gibson Middle-construct mini-gym",{"$nulls":5},1550000]
[null,"Lakeland Highlands Middle-Construct mini-gym",{"$nulls":5},1750000]
[null,"West Area Adult-Remodel and fire sprinkle bldg 1",{"$nulls":5},2750000]
[null,"Bartow Sr-MP Phase III - Music Suite",{"$nulls":5},1380000]
[null,"Winter Haven Sr-Phase II Master Plan",{"$nulls":5},3452000]
[null,"Polk Total",null,79600537,97634527,100803319,144498258,106141359,528678000]
[]
[18,"Schedule indicating which projects included in the tentative district facilities work program in Section 2 above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[]
[18,"Polk Total",0,0,0,0,0,0,0]
[]
[19,"Schedule of options for generation of additional revenues by the district for expenditure on projects identified in the district facilities work "]
[null,"program which are not funded under paragraph 17 above.  Additional anticipated revenues may include SIT Program awards and Classrooms First funds."]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
[19,"Polk Total",null,0,0,0,0,0,0]
[]
[]
["NOTE: If the sum of the totals in paragraphs 17 and 18 above DO NOT equal the total in paragraph 2 above, the message \"Check Totals\" appears.   "]
[null,"-- They should balance ! !"]
[null,null,null,"2005-06 ","2006-07 ","2007-08 ","2008-09","2009-10","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"Check Totals","Check Totals","Check Totals","Check Totals","Check Totals","Check Totals"]
[]
[]
["Polk  SCHOOL DISTRICT - - FACILITIES TEN (10) - YEAR LONG RANGE PLAN"]
[]
[20,"A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the next 5 years beyond the above 5-year work plan. (years 6-10)"]
[]
[null,null,null,"2010/11 - 2014/15"]
[null,"Project","Location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[]
[]
[]
[20,"Polk Total",null,0,{"$nulls":4},0]
[]
[21,"A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the future 5 years beyond the above 5-year work plan."]
[]
[null,null,"Location - Community, quadrant,","2010/11 - 2014/15"]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"5 YEAR TOTAL"]
[]
[]
[]
[21,"Polk Total",null,0,{"$nulls":4},0]
[]
[22,"Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2004-05","Actual 2004-05","Actual 2005-06","05/06 - 14/15         New Stu Capacity to","Projected 2014- 15","Projected 2014-15"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[null,"Elementary - District Totals",850,850,622,0.73,null,1175,1.38]
[null,"Middle - District Totals",771,771,868,1.13,104,875,1]
[null,"High - District Totals",1244,1131,1090,0.96,-17,1125,1.01]
[null,"Other - ESE, etc",924,840,1237,1.47,300,1185,1.04]
[22,"Polk Total",3789,3592,3817,1.06,387,4360,1.1]
[]
[23,"Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the next 5 year period beyond the 5-year work plan above."]
[null,"(Brief one line narritive i.e.) New Elementary School (600 Stu Sta) in the vicinity of the SouthernAir subdivision in the Southeastern part of Sometown, FL, to accommodate growth."]
[]
[24,"Plans for closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the next 5 year period beyond the 5-year plan above."]
[null,"(Brief one line narritive)"]
[]
["Polk  SCHOOL DISTRICT - - FACILITIES TWENTY (20) - YEAR LONG RANGE PLAN"]
[]
[25,"A schedule of major repair and renovation projects projected to maintain the educational plant and ancillary facilities"]
[null,"of the district for the 11 thru 20 out years."]
[]
[null,null,null,"2014/15-2024/25 ","Annual"]
[null,"Project","Location","Projected Cost","Average Cost",null,null,null,"10 YEAR TOTAL"]
[]
[]
[]
[25,"Polk Total",null,0,{"$nulls":4},0]
[]
[26,"A schedule of capital outlay projects projected to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs for the 11 thru 20 out years."]
[]
[null,null,"Location - Community, quadrant,","2014/15-2024/25 "]
[null,"Project Description"," or other general location","Projected Cost",{"$nulls":4},"10 YEAR TOTAL"]
[]
[]
[]
[26,"Polk Total",null,0,{"$nulls":4},0]
[]
[27,"Locations, capacities, and planned utilization rates of future educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"FISH Satisfactory","Actual 2004-05","Actual 2004-05","Actual 2002-03","14/15 - 24/25         New Stu Capacity to","District Projected 2024-25","Projected 2024-25"]
[null,"Grade Level Projections","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added or removed","CO-FTE ","Utilization"]
[]
[]
[]
[]
[27,"Polk Total",0,0,0,{"$error":"#DIV/0!"},0,0,{"$error":"#DIV/0!"}]
[]
[28,"Proposed Location of Planned New, Remodeled, or New Additions to Facilities in the 11 thru 20 out years. "]
[null,"(Brief one line narritive i.e.) New Elementary School (600 Stu Sta) in the vicinity of the SouthernAir subdivision in the Southeastern part of Sometown, FL, to accommodate growth."]
[]
[29,"Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues in the 11 thru 20 out years."]
[null,"(Brief one line narritive)"]
[]
[]
[]
[]
[null,"To the extent available, the tentative district facilities work program shall be based on information produced by the demographic, revenue, and"]
[null,"education estimating conferences pursuant to 216.136."]
[null,"Provision shall be made for public comment concerning the tentative district educational facilities plan."]
[null,"The district school board shall coordinate with each affected local government to ensure consistency between the tentative district educational facilities plan and"]
[null,"the local government comprehensive plans of the affected local governments during the deveolpment of the tentative district educational facilities plan."]
[null,"The adopted district facilities work program shall:"]
[null,"Be a complete, balanced capital outlay financial plan for the district."]
[null,"Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities, including safe access ways from neighborhoods to schools."]
[null,"The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 1013.61."]
[null,"The adopted district educational facilities plan shall include the information required in subparagraphs (2) (b) 1., 2., and 3., based upon projects actually"]
[null,"funded in the plan with the exception of the 10 and 20 year portions."]
{"$rows_empty":9}
["Respectfully submitted this ___________ day of ____________________, 2004."]
[]
[null,"SCHOOL BOARD OF ","Polk  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"Jesse W. Pearson","Facilities Planner","863-534-0811",null,"Jesse.pearson@polk-fl.net",null," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}