{"text_format":"2","workbook":"xls","n_sheets":4,"sheets":["*****","SGV","99_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[{"sheet":"SGV","index":1,"reason":"not_a_worksheet"}],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"99_5YrWkPlan","index":2,"n_rows":499,"n_cols":25,"rows_kept":499,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["ST. LUCIE  COUNTY - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["ST. LUCIE   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format, as you received it (not a fax), prior to September 15, 1999, and all data accurate as of July 15, 1999.",{"$nulls":8},"1999-08-05",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"ST. LUCIE","Date: ==>","1999-10-27",null,"For fiscal years","  1999-2000 through 2003-2004"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"1999-00 ","2000-01 ","2001-02 ","2002-03 ","2003-04 "]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[1,"Replace facility with the exception of the cafeteria/kitchen","Fairlawn Elem. ",7742500,{"$nulls":4},7742500]
[2,"Replace facility with the exception of the media, art, cafeteria, k-pod and covered PE","F. K. Sweet Elem.",7742500,{"$nulls":4},7742500]
[3,"Renovate bldg 3, Cafeteria.","Garden City Elem. ",1000000,{"$nulls":4},1000000]
[4,"Expand Media, Admin & Food Svc. Cover walk, play area, skills lab, & art classroom","Lawnwood Elem.",150000,{"$nulls":4},150000]
[5,"Replace entire facility with the exception of the Vocational and Gymnasium Buidlings","Dan McCarty Middle",11063000,{"$nulls":4},11063000]
[6,"Master Plan Development, New Auditorium, Band, & Chorus classrooms. ","Lincoln Park Academy",3360000,{"$nulls":4},3360000]
[7,"Renovate and remodel the Gymnasium","Lincoln Park Academy",1384000,{"$nulls":4},1384000]
[8,"Renovate buildings 1-7, HVAC","Ft. Pierce Westwood High",2200000,{"$nulls":4},2200000]
[9,"Renovate bldgs 1 thru 20, HVAC","Ft. Pierce Central High",2285000,{"$nulls":4},2285000]
[10,"Add ESE to Bldg 1","Port St. Lucie Elem.",45565,{"$nulls":4},45565]
[11,null,"Dale Cassens",155000,{"$nulls":4},155000]
[12,"Bathrooms","ESE",50000,{"$nulls":4},50000]
[13,"Bathrooms and Front","District Office",150000,{"$nulls":4},150000]
[14,"Retention System","Savanah Ridge",50000,{"$nulls":4},50000]
[15,"Cafeteria","FPMSA",56289,{"$nulls":4},56289]
[17,"Test and Balance",null,70000,{"$nulls":4},70000]
[18,"Stormwater Maintenance","Districtwide",145000,{"$nulls":4},145000]
[19,"Wetlands Monitoring","Districtwide",20000,{"$nulls":4},20000]
[20,"Roofing Repairs","Northport Middle Bldg & Ft Pierce Westwood HS",1302000,{"$nulls":4},1302000]
[21,"Roofing Repairs","Pt St Lucie Elem, Village Green Elem & Windmill Point Elem",null,298399,1101601,null,null,1400000]
[22,"Roofing Repairs","Ft Pierce Central, Floresta Elem, Anglewood, Dale Cassens & ESE",null,null,58076,178822,881102,1118000]
[23,"Roofing Repairs","White City Elem, Forest Grove MS & Mariposa Elem",{"$nulls":4},1125000,1125000]
[24,"Roofing Repairs","Southport MS, District Office, Preston Court and Pt St Lucie HS",{"$nulls":4},1071664,1071664]
[25,"Flooring / Carpet"," Dale Cassens Center, Bayshore & Parkway Elem.",280000,{"$nulls":4},280000]
[26,"Flooring / Carpet","PSL High, Manatee, Parkway, Bayshore",null,300000,null,null,null,300000]
[27,"Flooring / Carpet","Pt St lucie High, Manatee, Mariposa",null,null,300000,null,null,300000]
[28,"Flooring / Carpet","Anglewood, Garden City, Floresta",null,null,null,300000,null,300000]
[29,"Flooring / Carpet","Floresta, Southport, Forest Grove",{"$nulls":4},300000,300000]
[30,"HVAC Repairs","Lincoln Park Academy, Manatee, Southport, Pt St Lucie Elem",1698000,{"$nulls":4},1698000]
[31,"HVAC Repairs","Northport Middle, Village Green",null,1420000,null,null,null,1420000]
[32,"HVAC Repairs","Dale Cassens Center & Port St. Lucie Elem.",null,null,1140000,null,null,1140000]
[33,"HVAC Repairs","Garden City Elem. & Means Court Annex",null,null,null,1149000,null,1149000]
[34,"HVAC Repairs","Pt. St. Lucie High School, Windmill Point Elementary, Bayshore, Mariposa",{"$nulls":4},1550000,1550000]
[35,"Painting","White City Elem, Northport Middle, Lwnwood Elem, Agriscience, County Office, & SLW Svc Ctr",111000,{"$nulls":4},111000]
[36,"Painting","Bayshore, Manatee, Mariposa, Lakewood Park, & Ft. Pierce Westwood",null,117700,null,null,null,117700]
[37,"Painting","Dale Cassens, Ft. Pierce Central, Garden City Elem & PSL High",null,null,233900,null,null,233900]
[38,"Painting","Dan McCarty, Rivers Edge, St Lucie, Weatherbee & Ft.Pierce Magnet (West)",null,null,null,123000,null,123000]
[39,"Painting","St Lucie West Centennial HS, St Lucie West Middle, Savanna Ridge Elem, Lincoln Park Academy",{"$nulls":4},231000,231000]
[40,"Pave parking & Repaving","North Bus Compound, County Office / St Lucie Superintendentrs Office",330000,{"$nulls":4},330000]
[41,"Fire Alarms / Security Systems","District wide",275000,275000,275000,275000,275000,1375000]
[42,"Life Safety","District wide",300000,300000,300000,300000,300000,1500000]
[43,"Relocate Portables","Various Locations Districtwide",75000,185000,185000,75000,75000,595000]
[44,"Re-Varnishing - Gym floors","Gym Floors at Middle & High Schools",82000,70000,70000,70000,80000,372000]
[45,"Replace Transformers","Football Stadium - Lawnwood",110000,{"$nulls":4},110000]
[46,"Basketball Court resurfacing","Various Locations Districtwide",80000,80000,80000,80000,100000,420000]
[47,"Replace Doors & hardware","Various Locations Districtwide",25000,25000,25000,25000,35000,135000]
[48,"ADA upgrades","Various Locations Districtwide",null,750000,750000,750000,800000,3050000]
[49,"Renovate buildings 1,3,5,6,7,11,12,13,18,19,20,24 & 25","Lincoln Park Academy",{"$nulls":4},19000000,19000000]
[50,"Renovate bldgs 1 thru 20, HVAC","Ft. Pierce Central High",{"$nulls":4},19000000,19000000]
[51,"Renovate buildings 1-7, HVAC","Ft. Pierce Westwood High",{"$nulls":4},19000000,19000000]
[52,"Correct Drainage Problems","Parkway",null,200000,null,null,null,200000]
[null,null,"Morningside Elem.",null,200000,null,null,null,200000]
[null,null,"Anglewood Center",null,200000,null,null,null,200000]
[null,null,"Woodlands",null,200000,null,null,null,200000]
[null,null,"Lakewood Park Elem.",null,200000,null,null,null,200000]
[null,null,"Floresta Elem. ",null,200000,null,null,null,200000]
[59,"Covered bus drop off & pick up","Port St. Lucie High",null,null,200000,null,null,200000]
[null,null,"Manatee Elem.",null,null,200000,null,null,200000]
[null,null,"Forrest Grove Middle ",null,null,200000,null,null,200000]
[60,"Cafeteria-Food Service","Lawnwood Elem.",null,null,null,400000,null,400000]
[61,"Expand ESE suite. Remodel 8 - intermediate classrooms.","Garden City Elem. ",null,null,null,460000,null,460000]
[62,"Expand Media, Admin., Skills lab, & art classroom","Lawnwood Elem.",null,null,null,617750,null,617750]
[63,"Add ESE to Bldg 1, 1-Music, 1-Art, 2-skill Dev Labs","Port St. Lucie Elem.",{"$nulls":4},778189,778189]
[64,"Add 1-Art, 2-Skill Development Labs,  5-Resource Rooms","Lakewood Park Elem.",{"$nulls":4},729073,729073]
[65,"District Offices","New Admin Building",null,5000000,null,null,null,5000000]
[66,"Districtwide","Purchase capital outlay equipment throughout district.",null,707000,677000,null,null,1384000]
[{"$nulls":8},0]
["1.","ST. LUCIE Total",null,42336854,10728099,5795577,4803572,65331028,128995130]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"No new school construction is planned during the next 5 years.",{"$nulls":6},0]
["2 .","ST. LUCIE Total","NONE",0,0,0,0,0,0]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"1998-99 FISH Satisfactory","Actual 1998-99","Actual 1998-99","Actual 1998-99","New Stu Capacity to","Projected 2003-04","Projected 2003-04"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[1,"White City Elem.",604,604,639,1.0579470198675496,0,600,0.9933774834437086]
[2,"Fairlawn Elem.",883,883,612,0.6930917327293318,0,650,0.7361268403171007]
[3,"Ft. Pierce Magnet School",502,451,292,0.647450110864745,0,350,0.7760532150776053]
[4,"Lawnwood Elem.",959,959,678,0.7069864442127216,0,650,0.6777893639207507]
[5,"St. Lucie Elem.",986,986,606,0.6146044624746451,0,650,0.6592292089249493]
[6,"Dan McCarty Middle",1002,902,990,1.0975609756097562,0,997.85151856018,1.1062655416409979]
[7,"F. K. Sweet Elem.",1211,1211,643,0.5309661436829067,0,650,0.5367464905037159]
[8,"Garden City Elem.",1448,1448,556,0.3839779005524862,0,650,0.4488950276243094]
[9,"C.A. Moore Elem.",1079,1079,575,0.5329008341056534,0,700,0.6487488415199258]
[10,"Lincoln Park Academy",2570,2313,1683,0.7276264591439688,0,1846.8922008392417,0.7984834417809087]
[11,"Ft. Pierce Central",2499,2374,1515,0.6381634372367313,0,1765.618479880775,0.7437314574055498]
[12,"Ft. Pierce Westwood",2415,2294,1341,0.5845684394071491,0,1400,0.6102877070619006]
[13,"Anglewood Center",191,191,48,0.2513089005235602,0,52.67428736796411,0.2757816092563566]
[14,"Woodlands Academy",259,259,113,0.4362934362934363,0,115.35829604438877,0.4453988264262114]
[15,"Port St. Lucie Elem.",938,938,866,0.9232409381663113,0,767.043024585477,0.8177430965730033]
[16,"Morningside Elem.",848,848,729,0.8596698113207547,0,700,0.8254716981132075]
[17,"Lakewood Park Elem.",856,856,690,0.8060747663551402,0,700,0.8177570093457944]
[18,"Floresta Elem.",779,779,709,0.9101412066752247,0,700,0.8985879332477535]
[19,"Bayshore Elem.",816,816,812,0.9950980392156863,0,750,0.9191176470588235]
[20,"Northport Middle",1612,1451,1162,0.8008270158511371,0,1175.55905511811,0.8101716437754033]
[21,"Windmill Point Elem.",842,842,764,0.9073634204275535,0,750,0.8907363420427553]
[22,"Village Green Elem.",790,790,835,1.0569620253164558,0,750,0.9493670886075949]
[23,"Port St. Lucie High",2623,2491,1762,0.7073464472099559,0,2053.478390461997,0.824359048760336]
[24,"Parkway Elem.",884,884,648,0.7330316742081447,0,650,0.7352941176470589]
[25,"Dale Cassens ESE Center",240,240,97,0.4041666666666667,0,98.93553606097647,0.4122314002540686]
[26,"Southport Middle",1423,1280,1027,0.80234375,0,1036.07930258718,0.8094369551462345]
[27,"Mariposa Elem.",838,838,711,0.8484486873508353,0,700,0.8353221957040573]
[28,"Manatee Elem.",885,885,861,0.9728813559322034,0,762.325686106346,0.8613849560523683]
[29,"Forrest Grove Middle",1708,1537,1203,0.7826935588809368,0,1217.91957255343,0.7924005026372349]
[30,"Agritech Alternative School",104,104,0,0,0,0,0]
[31,"Rivers Edge Elem.",952,952,850,0.8928571428571429,0,751.947541452258,0.7898608628700189]
[32,"Southern Oaks Middle",1648,1483,1054,0.7107215104517869,0,1063.97525309336,0.7174479117284962]
[33,"Weatherbee Elem.",1003,1003,747,0.744765702891326,0,750,0.7477567298105683]
[34,"St. Lucie West Cent. High",2123,2016,1148,0.5694444444444444,0,1800,0.8928571428571429]
[35,"St. Lucie West Middle",1458,1312,582,0.44359756097560976,0,772,0.5884146341463414]
[36,"Savanna Ridge Elem.",1003,1003,387,0.38584247258225324,0,517,0.5154536390827518]
["2a.","ST. LUCIE Total",40981,39302,27935,0.71,0,29544.658144711684,0.75]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"No new school construction is planned for the next 5 years."]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 1998-99","Owner","Student Stations","as classroom space","in 2003-04","units by 2003-04","Column \"C\""]
[1,"White City Elem.",0,"-",0,0,0,0,0]
[2,"Fairlawn Elem.",13,"SLCSB",318,0,0,13,24]
[3,"Ft. Pierce Magnet School",0,"-",0,0,0,0,0]
[4,"Lawnwood Elem.",6,"4SLCSB/2FED",109,0,2,4,92]
[5,"St. Lucie Elem.",0,"-",0,0,0,0,0]
[6,"Dan McCarty Middle",6,"5SLCSB/1FED",140,0,2,4,50]
[7,"F. K. Sweet Elem.",30,"12LEASE/15SLCSB/3FED",679,0,2,28,176]
[8,"Garden City Elem.",2,"SLCSB",52,0,1,1,18]
[9,"C.A. Moore Elem.",0,"-",0,0,0,0,"-"]
[10,"Lincoln Park Academy",3,"SLCSB",88,0,0,3,21]
[11,"Ft. Pierce Central",26,"24SLCSB/2FED",750,0,13,13,309]
[12,"Ft. Pierce Westwood",17,"15SLCSB/FED2",493,0,8,9,220]
[13,"Anglewood Center",2,"1SLCSB/1FED",44,0,2,0,27]
[14,"Woodlands Academy",13,"11SLCSB/2FED",259,0,13,0,152]
[15,"Port St. Lucie Elem.",8,"4SLCSB/4FED",196,0,4,4,115]
[16,"Morningside Elem.",5,"SLCSB",96,0,2,3,44]
[17,"Lakewood Park Elem.",4,"FED",104,0,2,2,95]
[18,"Floresta Elem.",1,"SLCSB",26,0,1,0,4]
[19,"Bayshore Elem.",3,"SLCSB",78,0,1,2,31]
[20,"Northport Middle",13,"SLCSB",336,0,6,7,108]
[21,"Windmill Point Elem.",4,"SLCSB",104,0,2,2,16]
[22,"Village Green Elem.",1,"FED",26,0,0,1,20]
[23,"Port St. Lucie High",26,"25SLCSB/1FED",780,0,20,6,252]
[24,"Parkway Elem.",6,"SLCSB",146,0,3,3,82]
[25,"Dale Cassens ESE Center",3,"SLCSB",24,0,1,2,57]
[26,"Southport Middle",4,"SLCSB",112,0,2,2,16]
[27,"Mariposa Elem.",0,"-",0,0,0,0,"-"]
[28,"Manatee Elem.",2,"SLCSB",52,0,1,1,14]
[29,"Forrest Grove Middle",9,"SLCSB",252,0,4,5,58]
[30,"Agritech Alternative School",4,"SLCSB",104,0,3,1,16]
[31,"St. Lucie Superintendent Ofc.",8,"SLCSB","-",0,2,6,36]
[32,"Preston Court Annex",3,"FED","-",0,2,1,42]
[33,"Alternate Ed",3,"SLCSB","-",0,3,0,88]
[34,"Rivers Edge Elem.",1,"SLCSB",26,0,1,0,4]
[35,"Southern Oaks Middle",7,"SLCSB",168,0,3,4,56]
[36,"Weatherbee Elem.",0,"-",0,0,0,0,"-"]
[37,"St. Lucie West Cent. High",0,"-",0,0,0,0,"-"]
[38,"St. Lucie West Middle",0,"-",0,0,0,0,"-"]
[39,"Savanna Ridge Elem.",0,"-",0,0,0,0,"-"]
["2c1.","ST. LUCIE Total",233,null,5562,0,106,127,"Avg Age 9.63"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"No relocatable classrooms are identified for replacement.",0,0,0,0,0,0,0]
["2c2.","ST. LUCIE Total",0,0,0,0,0,0,0]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 1998-99","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2003-04","FISH Stu. Sta.","# Years Leased "]
[null,"Fairlawn Elementary",2,"Williams Scotsman",52,1,0,0,0]
[null,"FK Sweet Elementary",12,"Williams Scotsman",312,1,0,0,0]
["2c3.","ST. LUCIE Total",14,null,364,2,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2003-04"]
[null,"No Charter Schools are projected"]
["2c4.","ST. LUCIE Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
["2e.","Average Class Size (5 years out -- 2003-04) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","1998-99 CO-FTE","1998-99 Class size","2003-04 CO-FTE","be added (removed)","2003-04 Class size"]
[1,"White City Elem.",29,604,639,22.03,600,0,20.69]
[2,"Fairlawn Elem.",40,883,612,15.3,650,0,16.25]
[3,"Ft. Pierce Magnet School",20,451,292,14.6,350,0,17.5]
[4,"Lawnwood Elem.",39,959,678,17.38,650,0,16.67]
[5,"St. Lucie Elem.",39,986,606,15.54,650,0,16.67]
[6,"Dan McCarty Middle",47,902,990,21.06,997.85151856018,0,21.23]
[7,"F. K. Sweet Elem.",55,1211,643,11.69,650,0,11.82]
[8,"Garden City Elem.",58,1448,556,9.59,650,0,11.21]
[9,"C.A. Moore Elem.",41,1079,575,14.02,700,0,17.07]
[10,"Lincoln Park Academy",93,2313,1683,18.1,1846.8922008392417,0,19.86]
[11,"Ft. Pierce Central",90,2374,1515,16.83,1765.618479880775,0,19.62]
[12,"Ft. Pierce Westwood",86,2294,1341,15.59,1400,0,16.28]
[13,"Anglewood Center",9,139,48,5.33,52.67428736796411,0,5.85]
[14,"Woodlands Academy",11,259,113,10.27,115.35829604438877,0,10.49]
[15,"Port St. Lucie Elem.",37,938,866,23.41,767.043024585477,0,20.73]
[16,"Morningside Elem.",32,848,729,22.78,700,0,21.88]
[17,"Lakewood Park Elem.",32,856,690,21.56,700,0,21.88]
[18,"Floresta Elem.",29,779,709,24.45,700,0,24.14]
[19,"Bayshore Elem.",31,816,812,26.19,750,0,24.19]
[20,"Northport Middle",50,1451,1162,23.24,1175.55905511811,0,23.51]
[21,"Windmill Point Elem.",32,842,764,23.88,750,0,23.44]
[22,"Village Green Elem.",30,790,835,27.83,750,0,25]
[23,"Port St. Lucie High",99,2491,1762,17.8,2053.478390461997,0,20.74]
[24,"Parkway Elem.",34,884,648,19.06,650,0,19.12]
[25,"Dale Cassens Center",0,240,97,"-",98.93553606097647,null,"-"]
[26,"Southport Middle",39,1280,1027,26.33,1036.07930258718,0,26.57]
[27,"Mariposa Elem.",31,838,711,22.94,700,0,22.58]
[28,"Manatee Elem.",29,885,861,29.69,762.325686106346,0,26.29]
[29,"Forrest Grove Middle",52,1537,1203,23.13,1217.91957255343,0,23.42]
[30,"Agritech Alternative School",4,104,0,0,0,0,0]
[31,"Rivers Edge Elem.",36,952,850,23.61,751.947541452258,0,20.89]
[32,"Southern Oaks Middle",52,1483,1054,20.27,1063.97525309336,0,20.46]
[33,"Weatherbee Elem.",37,1003,747,20.19,750,0,20.27]
[34,"St. Lucie West Cent. High",83,2016,1148,13.83,1800,0,21.69]
[35,"St. Lucie West Middle",48,1312,582,12.13,772,0,16.08]
[36,"Savanna Ridge Elem.",37,1003,387,10.46,517,0,13.97]
["2e.","ST. LUCIE Total",1511,39250,27935,"District Avg 18",29544.658144711684,0,"District Avg 20"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR AVERAGE"]
[1,"White City Elem.",null,0,0,0,0,0,0,null,0]
[2,"Fairlawn Elem.",null,199,0,0,0,0,39.8]
[3,"Ft. Pierce Magnet School",null,0,0,0,0,0,0]
[4,"Lawnwood Elem.",null,104,104,35,35,35,62.6]
[5,"St. Lucie Elem.",null,0,0,0,0,0,0]
[6,"Dan McCarty Middle",null,126,126,63,63,42,84]
[7,"F. K. Sweet Elem.",null,642,0,0,0,0,128.4]
[8,"Garden City Elem.",null,19,0,0,0,0,3.8]
[9,"C.A. Moore Elem.",null,0,0,0,0,0,0]
[10,"Lincoln Park Academy",null,54,54,54,18,18,39.6]
[11,"Ft. Pierce Central",null,438,438,438,218,218,350]
[12,"Ft. Pierce Westwood",null,265,265,265,125,125,209]
[13,"Anglewood Center",null,10,10,10,10,10,10]
[14,"Woodlands Academy",null,134,134,134,134,134,134]
[15,"Port St. Lucie Elem.",null,187,187,187,94,94,149.8]
[16,"Morningside Elem.",null,114,114,45,45,45,72.6]
[17,"Lakewood Park Elem.",null,86,86,86,43,43,68.8]
[18,"Floresta Elem.",null,24,24,24,0,0,14.4]
[19,"Bayshore Elem.",null,78,78,78,26,26,57.2]
[20,"Northport Middle",null,302,302,302,138,138,236.4]
[21,"Windmill Point Elem.",null,95,95,95,48,48,76.2]
[22,"Village Green Elem.",null,27,27,27,0,0,16.2]
[23,"Port St. Lucie High",null,460,460,354,354,354,396.4]
[24,"Parkway Elem.",null,114,114,114,57,57,91.2]
[25,"Dale Cassens ESE Center",null,12,12,12,4,4,8.8]
[26,"Southport Middle",null,105,105,105,53,53,84.2]
[27,"Mariposa Elem.",null,0,0,0,0,0,0]
[28,"Manatee Elem.",null,59,59,59,30,30,47.4]
[29,"Forrest Grove Middle",null,208,208,208,92,92,161.6]
[30,"Agritech Alternative School",null,"-",0,0,0,0,0]
[31,"Rivers Edge Elem.",null,24,0,0,0,0,4.8]
[32,"Southern Oaks Middle",null,142,142,142,60,60,109.2]
[33,"Weatherbee Elem.",null,0,0,0,0,0,0]
[34,"St. Lucie West Cent. High",null,0,0,0,0,0,0]
[35,"St. Lucie West Middle",null,0,0,0,0,0,0]
[36,"Savanna Ridge Elem.",null,0,0,0,0,0,0]
["2f.","ST. LUCIE Total students in relocatables by year",null,4028,3144,2837,1647,1626,2656.4]
[null,"Total number of CO-FTE students projected by year",null,28437,28829,29139,29456,29545,29081.2]
[null,"Percent in relocatables by year",null,0.14,0.11,0.1,0.06,0.06,0.09]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",1998,1998,1998,1998,1998,1998]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,70,107,174,7485,11173,16419]
[null,"1998 State-wide totals - Gross Sq Ft per student station: Elem low 70, avg 107, high 174; Middle low 88, avg 90, high 180; High School low 117, avg 130, high 143 ",{"$nulls":7},2,88,90,180,7226,13517,18473]
[null,"1998 State-wide totals - Cost per student station: Elem low 7,485, avg 11,173, high 16,419; Middle low 7,226,avg 13,517, high 18,473; High School low 16,957, avg 19,323, high  21,507 ",{"$nulls":7},3,117,130,144,16957,19232,21507]
[]
["3a.","1999-00 Year","Type of School (new schools only)  Others=0","1999-00","1999-00","1999-00","1999-00","1998 State Avg","1998 State Avg","1998 State Avg","1999 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","ST. LUCIE Total 1999-00",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3b.","2000-2001 Year","Type of School (new schools only)  Others=0","2000-01","2000-01","2000-01","2000-01","1998 State Avg","1998 State Avg","1998 State Avg","2000 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","ST. LUCIE Total 2000-01",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2001-2002 Year","Type of School (new schools only)  Others=0","2001-02","2001-02","2001-02","2001-02","1998 State Avg","1998 State Avg","1998 State Avg","2001 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","ST. LUCIE Total 2001-02",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2002-2003 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","1998 State Avg","1998 State Avg","1998 State Avg","2002 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","ST. LUCIE Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","1998 State Avg","1998 State Avg","1998 State Avg","2003 Projected","1998 State Avg","1998 State Avg","1998 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"No school construction planned",{"$nulls":4},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","ST. LUCIE Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","ST. LUCIE 5-Year Total",null,0,0,0]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,0,0,0,0,0,0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,15315512,15682000,16027000,16348000,16675000,80047512,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,1000000,1100000,1200000,1300000,1400000,6000000,0.0749554839380892]
[null,"  less amount used to purchase other vehicles",null,291000,0,0,0,0,291000,0.00363534097099732]
[null,"  less amount transferred to operating budget for maintenance/repair",null,3800000,3500000,3200000,2800000,2500000,15800000,0.197382774370301]
[null,"  less amount used for maintenance/repair",null,0,0,0,0,0,0,0]
[null,"  less amount used to purchase capital outlay equipment",null,2778512,1114000,1723000,2400000,2686000,10701512]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,null,1792000,1728000,1664000,0,5184000]
[null,"  less amount to pay debt service for COP's ",null,6316000,8000000,8000000,8000000,8000000,38316000]
[null,"  less other (land aquisition)",null,0,0,0,null,null,0,0]
[null,"  less other (capital lease)",null,176000,176000,176000,176000,176000,880000,0.0109934709775864]
[null,"  less other (FL. P. & Light Contingent)","FPL Contingent",954000,0,0,0,0,954000,0.0119179219461562]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,0,0,8000,1913000,1921000,0.0239982474408449,0.03]
[null,"P E C O New Construction",null,2904059,1914099,2318577,2117822,3710766,12965323]
[null,"C O & D S   Bond Proceeds",null,0,0,0,0,0,0]
[null,"C O & D S maximum potential bond proceeds",null,210000,200000,200000,200000,200000,1010000]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,18250000,0,0,0,null,18250000]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,16827000,0,0,0,0,16827000]
[null,"Impact fees received",null,1070000,1100000,1100000,1100000,1100000,5470000]
[null,"  less amount used to pay for technology throughout district",null,-1070000,-1100000,-1100000,-1100000,-1100000,-5470000]
[null,"Interest",null,0,0,0,0,0,0,null,0]
[null,"Effort Index Distribution",null,4074680,0,0,0,0,4074680,null,0.07]
[null,"  less amount used to pay debt service for s.237 loan",null,-1835000,0,0,0,0,-1835000,null,-0.03]
[null,"SIT Awards Estimated",null,3922719,1000000,1000000,0,0,5922719,null,0.1]
[null,"  less amount used to purchase cabling throughout district",null,-300000,0,0,null,null,-300000,null,-0.01]
[null,"  less amount used to purchase capital outlay equipment throughout district",null,-1716604,-293000,0,null,null,-2009604,null,-0.04]
["4.","ST. LUCIE Total",null,42336854,2821099,3518577,2325822,5823766,56826118,0.32288323964397503,0.12]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[1,"Replace facility with the exception of the cafeteria/kitchen","Fairlawn Elem. ",7742500,{"$nulls":4},7742500]
[2,"Replace facility with the exception of the media, art, cafeteria, k-pod and covered PE","F. K. Sweet Elem.",7742500,{"$nulls":4},7742500]
[3,"Renovate bldg 3, Cafeteria.","Garden City Elem. ",1000000,{"$nulls":4},1000000]
[4,"Expand Media, Admin & Food Svc. Cover walk, play area, skills lab, & art classroom","Lawnwood Elem.",150000,{"$nulls":4},150000]
[5,"Replace entire facility with the exception of the Vocational and Gymnasium Buidlings","Dan McCarty Middle",11063000,{"$nulls":4},11063000]
[6,"Master Plan Development, New Auditorium, Band, & Chorus classrooms. ","Lincoln Park Academy",3360000,{"$nulls":4},3360000]
[7,"Renovate and remodel the Gymnasium","Lincoln Park Academy",1384000,{"$nulls":4},1384000]
[8,"Renovate buildings 1-7, HVAC","Ft. Pierce Westwood High",2200000,{"$nulls":4},2200000]
[9,"Renovate bldgs 1 thru 20, HVAC","Ft. Pierce Central High",2285000,{"$nulls":4},2285000]
[10,"Add ESE to Bldg 1","Port St. Lucie Elem.",45565,{"$nulls":4},45565]
[11,null,"Dale Cassens",155000,{"$nulls":4},155000]
[12,"Bathrooms","ESE",50000,{"$nulls":4},50000]
[13,"Bathrooms and Front","District Office",150000,{"$nulls":4},150000]
[14,"Retention System","Savanah Ridge",50000,{"$nulls":4},50000]
[15,"Cafeteria","FPMSA",56289,{"$nulls":4},56289]
[17,"Test and Balance",null,70000,{"$nulls":4},70000]
[18,"Stormwater Maintenance","Districtwide",145000,{"$nulls":4},145000]
[19,"Wetlands Monitoring","Districtwide",20000,{"$nulls":4},20000]
[20,"Roofing Repairs","Northport Middle Bldg & Ft Pierce Westwood HS",1302000,{"$nulls":4},1302000]
[21,"Roofing Repairs","Pt St Lucie Elem, Village Green Elem & Windmill Point Elem",null,298399,1101601,null,null,1400000]
[22,"Roofing Repairs","Ft Pierce Central, Floresta Elem, Anglewood, Dale Cassens & ESE",null,null,58076,178822,881102,1118000]
[23,"Roofing Repairs","White City Elem, Forest Grove MS & Mariposa Elem",{"$nulls":4},1125000,1125000]
[24,"Roofing Repairs","Southport MS, District Office, Preston Court and Pt St Lucie HS",{"$nulls":4},1071664,1071664]
[25,"Flooring / Carpet"," Dale Cassens Center, Bayshore & Parkway Elem.",280000,{"$nulls":4},280000]
[26,"Flooring / Carpet","PSL High, Manatee, Parkway, Bayshore",null,300000,null,null,null,300000]
[27,"Flooring / Carpet","Pt St lucie High, Manatee, Mariposa",null,null,300000,null,null,300000]
[28,"Flooring / Carpet","Anglewood, Garden City, Floresta",null,null,null,300000,null,300000]
[29,"Flooring / Carpet","Floresta, Southport, Forest Grove",{"$nulls":4},300000,300000]
[30,"HVAC Repairs","Lincoln Park Academy, Manatee, Southport, Pt St Lucie Elem",1698000,{"$nulls":4},1698000]
[31,"HVAC Repairs","Northport Middle, Village Green",null,420000,null,null,null,420000]
[32,"HVAC Repairs","Dale Cassens Center & Port St. Lucie Elem.",null,null,140000,null,null,140000]
[33,"HVAC Repairs","Garden City Elem. & Means Court Annex",null,null,null,149000,null,149000]
[34,"HVAC Repairs","Pt. St. Lucie High School, Windmill Point Elementary, Bayshore, Mariposa",{"$nulls":4},550000,550000]
[35,"Painting","White City Elem, Northport Middle, Lwnwood Elem, Agriscience, County Office, & SLW Svc Ctr",111000,{"$nulls":4},111000]
[36,"Painting","Bayshore, Manatee, Mariposa, Lakewood Park, & Ft. Pierce Westwood",null,117700,null,null,null,117700]
[37,"Painting","Dale Cassens, Ft. Pierce Central, Garden City Elem & PSL High",null,null,233900,null,null,233900]
[38,"Painting","Dan McCarty, Rivers Edge, St Lucie, Weatherbee & Ft.Pierce Magnet (West)",null,null,null,123000,null,123000]
[39,"Painting","St Lucie West Centennial HS, St Lucie West Middle, Savanna Ridge Elem, Lincoln Park Academy",{"$nulls":4},231000,231000]
[40,"Pave parking & Repaving","North Bus Compound, County Office / St Lucie Superintendentrs Office",330000,{"$nulls":4},330000]
[41,"Fire Alarms / Security Systems","District wide",275000,275000,275000,275000,275000,1375000]
[42,"Life Safety","District wide",300000,300000,300000,300000,300000,1500000]
[43,"Relocate Portables","Various Locations Districtwide",75000,185000,185000,75000,75000,595000]
[44,"Re-Varnishing - Gym floors","Gym Floors at Middle & High Schools",82000,70000,70000,70000,80000,372000]
[45,"Replace Transformers","Football Stadium - Lawnwood",110000,{"$nulls":4},110000]
[46,"Basketball Court resurfacing","Various Locations Districtwide",80000,80000,80000,80000,100000,420000]
[47,"Replace Doors & hardware","Various Locations Districtwide",25000,25000,25000,25000,35000,135000]
[48,"ADA upgrades","Various Locations Districtwide",null,750000,750000,750000,800000,3050000]
[{"$nulls":8},0]
[null,null,null,0,0,0,null,null,0]
["5.","ST. LUCIE Total",null,42336854,2821099,3518577,2325822,5823766,56826118]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
[null,null,null,0,0,0,0,0,0]
["6.","ST. LUCIE Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"1999-00","2000-01","2001-02","2002-03","2003-04"]
[null,"Project Description",null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[1,"HVAC Repairs","Northport Middle, Village Green",null,1000000,null,null,null,1000000]
[2,"HVAC Repairs","Dale Cassens Center & Port St. Lucie Elem. And Districtwide",null,null,1000000,null,null,1000000]
[3,"HVAC Repairs","Garden City Elem. & Means Court Annex and Districtwide",null,null,null,1000000,null,1000000]
[4,"HVAC Repairs","Pt. St. Lucie High School, Windmill Point Elementary, Bayshore, Mariposa and Districtwide",{"$nulls":4},1000000,1000000]
[5,"Renovate buildings 1,3,5,6,7,11,12,13,18,19,20,24 & 25","Lincoln Park Academy",{"$nulls":4},19000000,19000000]
[6,"Renovate bldgs 1 thru 20, HVAC","Ft. Pierce Central High",{"$nulls":4},19000000,19000000]
[7,"Renovate buildings 1-7, HVAC","Ft. Pierce Westwood High",{"$nulls":4},19000000,19000000]
[8,"Correct Drainage Problems","Parkway",null,200000,null,null,null,200000]
[null,null,"Morningside Elem.",null,200000,null,null,null,200000]
[null,null,"Anglewood Center",null,200000,null,null,null,200000]
[null,null,"Woodlands",null,200000,null,null,null,200000]
[null,null,"Lakewood Park Elem.",null,200000,null,null,null,200000]
[null,null,"Floresta Elem. ",null,200000,null,null,null,200000]
[9,"Covered bus drop off & pick up","Port St. Lucie High",null,null,200000,null,null,200000]
[null,null,"Manatee Elem.",null,null,200000,null,null,200000]
[null,null,"Forrest Grove Middle ",null,null,200000,null,null,200000]
[10,"Cafeteria-Food Service","Lawnwood Elem.",null,null,null,400000,null,400000]
[11,"Expand ESE suite. Remodel 8 - intermediate classrooms.","Garden City Elem. ",null,null,null,460000,null,460000]
[12,"Expand Media, Admin., Skills lab, & art classroom","Lawnwood Elem.",null,null,null,617750,null,617750]
[13,"Add ESE to Bldg 1, 1-Music, 1-Art, 2-skill Dev Labs","Port St. Lucie Elem.",{"$nulls":4},778189,778189]
[14,"Add 1-Art, 2-Skill Development Labs,  5-Resource Rooms","Lakewood Park Elem.",{"$nulls":4},729073,729073]
[15,"District Offices","New Admin Building",null,5000000,null,null,null,5000000]
[16,"Districtwide","Purchase capital outlay equipment throughout district.",null,707000,677000,null,null,1384000]
[null,null,null,0,0,0,null,0,0]
["7.","ST. LUCIE Total",null,0,7907000,2277000,2477750,59507262,72169012]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"1999-00","2000-01","2001-02","2002-03","2003-04","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 1999."]
[]
[null,"SCHOOL BOARD OF ","ST. LUCIE  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":3,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}