{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["Recovered_Sheet1","02_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"Recovered_Sheet1","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"02_5YrWkPlan","index":1,"n_rows":283,"n_cols":25,"rows_kept":283,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Wakulla  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Wakulla   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to DOE, Office of Educational Facilities , and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format (email: janet.burns@fldoe.org), as you received it (not a fax), prior to October 1, 2002, and all data accurate as of July 15, 2002.",{"$nulls":8},"2002-09-05T08:52:25.290",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Wakulla","Date: ==>","2002-10-01",null,"For fiscal years","  2002-2003 through 2006-2007"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"HVAC Upgrades",{"$nulls":6},0]
[null,"Hot Water Coils (Food Labs)","Wakulla High School ",null,null,null,15000,null,15000]
[null,"Hvac Controls","Wakulla High & Middle School",null,null,null,250000,null,250000]
[]
[null,"P.E.Fields","Riversprings",116560,{"$nulls":4},116560]
[null,null,"Wakulla High School",150000]
[]
[null,"Furniture & Equipment","Crawfordville ",118983.12]
[null,null,"Wakulla High School",25000]
[]
[null,"Remodeling & Renovations","Crawfordville School",759756]
[null,null,"Sopchoppy School",44767,{"$nulls":4},44767]
[null,null,"Wakulla High School",3089]
[null,null,"District  Wide",556962]
[]
[null,"Waste Water Demolition","Shadeville",null,50000,null,null,null,50000]
[{"$nulls":8},0]
[null,"Roofing",{"$nulls":6},0]
[null,"Re-Roofing","Shadeville",192619,{"$nulls":4},192619]
[null,null,"Crawfordville (Kindergarden)",95699,{"$nulls":4},95699]
[]
[null,"EPA Fuel Tank Replacement","Wakulla High School",{"$nulls":4},130000,130000]
[]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[null,"Maintenance, Repair, and Renovation Totals",null,2063435.12,50000,0,265000,130000,894645]
[null," Less projected PECO Maintenance Funds (235.435(1))",{"$nulls":6},0]
["1.","Wakulla Total",null,2063435.12,50000,0,265000,130000,894645]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[{"$nulls":8},0]
[{"$nulls":6},0,null,0]
[{"$nulls":6},0,null,0]
["2 .","Wakulla Total",null,0,0,0,0,0,0]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2001-02 FISH Satisfactory","Actual 2001-02","Actual 2001-02","Actual 2001-02","New Stu Capacity to","Projected 2006-07","Projected 2006-07"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Medart",803,803,588,0.73,null,747,0.93]
[null,"Crawfordville",859,859,649,0.76,null,747,0.87]
[null,"Shadeville",866,866,708,0.82,null,747,0.86]
[null,"Wakulla Middle School ",1041,936,665,0.71,null,537,0.57]
[null,"Riversprings",760,689,504,0.73,null,538,0.78]
[null,"Wakulla High School",1659,1576,1183,0.75,null,1218,0.77]
["2a.","Wakulla Total",5988,5729,4297,0.75,0,4534,0.79]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"Renovate and Remodel Existing Crawfordville School for District use ( County Office)"]
[{"$nulls":6},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2001-02","Owner","Student Stations","as classroom space","in 2006-07","units by 2006-07","Column \"C\""]
[null,"Existing Crawfordville",15,"WCSB",300,15,0,15]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
[{"$nulls":7},0]
["2c1.","Wakulla Total",15,null,300,15,0,15,"Avg Age 0"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"Existing Crawfordville",15,15,0,0,0,0,15]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","Wakulla Total",15,15,0,0,0,0,15]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2006-07","FISH Stu. Sta.","# Years Leased "]
[null,"Existing Crawfordville",2,"Williams/Scottsman",52,1,0]
[]
["2c3.","Wakulla Total",2,null,52,1,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"St. Marks Elementery / Middle",3,"Coast Charter School",1999,null,110,4,120]
[{"$nulls":8},0]
["2c4.","Wakulla Total",3,null,null,0,110,4,110]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2006-07) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: The average shall not include exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2001-02 CO-FTE","2001-02 Class size","2006-07 CO-FTE","be added (removed)","2006-07 Class size"]
[null,"Medart",31,803,588,18.97,747,null,24.1]
[null,"Shadeville",33,866,708,21.45,747,null,22.64]
[null,"New Crawfordville",30,859,649,21.63,747,null,24.9]
[null,"Riversprings ",17,684,504,29.65,538,null,31.65]
[null,"Wakulla Middle School",24,936,665,27.71,537,null,22.38]
[null,"Wakulla High School ",40,1576,1183,29.58,1218,null,30.45]
["2e.","Wakulla Total",175,5724,4297,"District Avg 25",4534,0,"District Avg 26"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR AVERAGE"]
[{"$nulls":8},{"$error":"#DIV/0!"},null,0]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
[{"$nulls":8},{"$error":"#DIV/0!"}]
["2f.","Wakulla Total students in relocatables by year",null,0,0,0,0,0,0]
[null,"Total number of CO-FTE students projected by year",null,4318,4324,4397,4465,4534,4407.6]
[null,"Percent in relocatables by year",null,0,0,0,0,0,0]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"This work plan take into consideration  closing  Existing Crawfordville School  and  converting it to a county office."]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,82,107,146,8756,12965,23176]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,84,119,161,9899,13498,17138]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,93,112,185,12826,15024,22033]
[]
["3a.","2002-03 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","Wakulla Total 2002-03",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3b.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","Wakulla Total 2003-04",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3c.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2004 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","Wakulla Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2005 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3d.","Wakulla Total 2005-06",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3e.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2000 State Avg","2000 State Avg","2000 State Avg","2006 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e",null,null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","Wakulla 5-Year Total",null,0,0,0]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,2,10]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",{"$nulls":6},0]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",null,1135430,1248973,1373870,1511257,1662383,6931913,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,0,null,500000,500000,500000,1500000,0.216390482684938]
[null,"  less amount used to purchase other vehicles",null,0,{"$nulls":4},0,0]
[null,"  less amount transferred to operating budget for maintenance/repair",null,0,{"$nulls":4},0,0]
[null,"  less amount used for maintenance/repair",null,91528,119913,451138,468927,912383,2043889,0.294852084842957]
[null,"  less amount used to purchase capital outlay equipment",null,0,0,230402,350000,250000,830402,0.119794059735026]
[null,"  less amount used to correct environmental problems",null,0,0,0,0,0,0,0]
[null,"  less amount transferred to operating budget for salaries",null,0,0,0,0,0,0,0]
[null,"  less amount used to pay debt service for s.237 loans",null,0,0,0,0,0,0,0]
[null,"  less amount to pay debt service for COP's ",null,192330,192330,192330,192330,null,769320,0.110982350759451]
[null,"  less other (please be specific)","payback Special Facilities Account",851572,936730,0,0,0,1788302,0.257981021977627,"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,0,0,0,0,0,0,null,0]
[null,"P E C O New Construction",null,0,{"$nulls":4},0,null,0]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",null,0,null,0,0,0,0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,0,{"$nulls":4},0,null,0]
[null,"Proceeds from 1/2 cent sales surtax authorized",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from a s.237 loan",null,0,0,0,0,0,0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",null,0,0,0,0,0,0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",null,0,0,0,0,null,0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",null,0,0,0,0,null,0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",null,100000,389756,0,0,0,489756,null,0.4]
[null,"Effort Index Grants",null,null,728322,0,0,0,728322]
[null,"Impact fees received",null,0,0,0,0,0,0,null,0]
[null,"Private donations",null,0,0,0,0,0,0,0.9999999999999989,0]
[null,"Grants from local governments or not-for-profit organizations",null,0,0,0,0,0,0,null,0]
["4.","Wakulla Total",null,100000,1118078,0,0,0,1218078,null,0.4]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[{"$nulls":6},0,0,0]
[null,null,null,0,null,null,null,0,0]
[null,null,null,0,0,null,null,0,0]
[{"$nulls":6},0,0,0]
[null,null,null,0,0,null,null,null,0]
[null,null,null,0,0,0,null,null,0]
["5.","Wakulla Total",0,0,0,0,0,0,0]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"SIT Program awards",null,0,0,0,0,0,0]
[null,"Other (specify)",null,0,0,0,0,0,0]
["6.","Wakulla Total",null,0,0,0,0,0,0]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,null,null,0,0,0,0,null,0]
[null,null,null,0,0,null,0,0,0]
[null,null,null,0,0,0,null,0,0]
["7.","Wakulla Total",0,0,0,0,0,0,0]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2002."]
[]
[null,"SCHOOL BOARD OF ","Wakulla  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"," "]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"," "," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",null,null,"William R. Bristol","Coordinator of Facilities","850-926-8111",null,"BristolR@wakulla.k12.fl.us"]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}