{"text_format":"2","workbook":"xls","n_sheets":3,"sheets":["*****","02_5YrWkPlan","EXPLANATIONS OF WORK PLAN"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":3,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"*****","index":0,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":true,"merged":[],"flags":["formulas_cached_only"]}

{"sheet":"02_5YrWkPlan","index":1,"n_rows":291,"n_cols":25,"rows_kept":291,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[]
["Washington  SCHOOL DISTRICT - - FACILITIES FIVE-YEAR WORK PROGRAM"]
["Washington   SCHOOL  DISTRICT - -  WORKSHEET "]
["This work program worksheet must be filled out completely and a paper copy signed and submitted to DOE, Office of Educational Facilities , and a copy submitted ",{"$nulls":8},"Last Revised",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["electronically in digital format (email: janet.burns@fldoe.org), as you received it (not a fax), prior to October 1, 2002, and all data accurate as of July 15, 2002.",{"$nulls":8},"2002-09-26T13:45:13.190",{"$nulls":14},"The application must be filled out completely and a paper copy signed and submitted to the SMART Schools Clearinghouse, and a copy submitted electronically by September 1, 1998, and all data accurate as of July 15, 1998."]
["District: ====>",null,"Washington","Date: ==>","2002-10-01",null,"For fiscal years","  2002-2003 through 2006-2007"]
[]
["Section 235.185 School district facilities work program; definitions; preparation, adoption, and amendment."]
[]
["(1)    DEFINITIONS"]
["(a)"]
["(b)"]
{"$rows_empty":7}
["(2)     PREPARATION OF TENTATIVE DISTRICT FACILITIES WORK PROGRAM"]
["(a)"]
[]
["1 .","A schedule of major repair and renovation projects necessary to maintain the educational plant and ancillary facilities"]
[null,"of the district."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project","Location","Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Life Safety","Vernon Elementary",2000,1000,1000,1000,null,5000]
[null,"Fire Alarm / Intercom Upgrades","Kate M. Smith Elementary",3000,1000,1000,1000,null,6000]
[null,null,"Vernon High School",1000,1000,1000,1000,null,4000]
[null,null,"Washington-Holmes Tech Center",5000,5000,5000,1000,null,16000]
[null,null,"Chipley High School (Historic)",1000,1000,1000,1000,null,4000]
[null,null,"Vernon Middle School",1000,1000,1000,1000,null,4000]
[null,null,"Chipley High School",1000,1000,1000,1000,null,4000]
[null,null,"Roulhac Middle School",1000,1000,1000,1000,null,4000]
[null,"HVAC Upgrades",{"$nulls":6},0]
[null,"AC Units","Washington Co School Board office",5000,15000,null,null,null,20000]
[null,null,"Washington-Holmes Tech Center",15000,15000,15000,15000,null,60000]
[null,null,"kate M. Smith Elementary ",10000,20000,20000,10000,5000,65000]
[null,null,"Vernon Elementary",15000,10000,10000,10000,null,45000]
[null,null,"Vernon High School",10000,10000,10000,null,null,30000]
[null,null,"Vernon Middle School",2500,3000,4000,5000,5000,19500]
[null,null,"Chipley High School",2500,3000,4000,5000,5000,19500]
[null,null,"Roulhac Middle School",2500,3000,4000,5000,5000,19500]
[null,"Flooring",{"$nulls":6},0]
[null,"Carpeting or Tile","All Facilities",20000,20000,20000,20000,20000,100000]
[{"$nulls":8},0]
[null,"Paint","All Facilities",10000,10000,10000,10000,10000,50000]
[null,"Reroofing","Kate M. Smith Elem Kindergarten",48000,{"$nulls":4},48000]
[null,null,"kate M. Smith Elem Cafeteria",126000,{"$nulls":4},126000]
[null,null,"Vernon Elementary Kindergarten",75000,{"$nulls":4},75000]
[null,null,"WHTC Nursing",35000,{"$nulls":4},35000]
[null,null,"Vernon Elementary Ray Horne Bldg",36000,{"$nulls":4},36000]
[null,null,"Vernon High School Bandroom",null,80000,null,null,null,80000]
[null,null,"Vernon Elem. School Kindergarten",75000,{"$nulls":4},75000]
[null,null,"Kate M. Smith Elem. ESE",108000,{"$nulls":4},108000]
[null,null,"Chipley High School (Historic)",null,null,null,150000,null,150000]
[null,null,"Vernon Bus Barn",15000,{"$nulls":4},15000]
[null,"Maintenance, Repair, and Renovation Totals",null,625500,201000,109000,238000,50000,1223500]
[null," Less projected PECO Maintenance Funds (235.435(1))",null,7000,6000,5000,4000,3000,25000]
["1.","Washington Total",null,618500,195000,104000,234000,47000,1198500]
[]
["2 .","A schedule of capital outlay projects necessary to ensure the availability of satisfactory student stations for the"]
[null,"  projected student enrollment in K-12 programs."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description",null,"Actual Budget","Projected Cost","Projected Cost","Projected Cost","Projected Cost","5 YEAR TOTAL"]
[null,"Vernon HighSchool",null,null,13854900,null,null,null,13854900]
[null,"Intermediate Center KMS",{"$nulls":4},4148429,null,4148429]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2 .","Washington Total",null,0,13854900,0,4148429,0,18003329]
[]
[null,"THIS SCHEDULE SHALL CONSIDER:"]
[]
["2a.","Locations, capacities, and planned utilization rates of current educational facilities of the district. (Include both permanent and relocatable facilities)"]
[null,null,"2001-02 FISH Satisfactory","Actual 2001-02","Actual 2001-02","Actual 2001-02","New Stu Capacity to","Projected 2006-07","Projected 2006-07"]
[null,"Location","Student Stations","FISH Capacity ","CO-FTE ","Utilization","be added (removed)","CO-FTE ","Utilization"]
[null,"Chpley High School / Roulhac"]
[null,"     Middle School",1321,1188,983,0.83,null,970,0.82]
[null,"Kate M. Smith Elementary",892,892,957,1.07,null,420,0.47]
[null,"Vernon HighSchool",867,780,350,0.45,null,435,0.56]
[null,"Vernon Elementary",820,820,528,0.64,null,580,0.71]
[null,"Vernon Middle School",398,358,432,1.21,null,435,1.22]
[null,"Intermediate Center",null,null,null,{"$error":"#DIV/0!"},450,445,0.99]
["2a.","Washington Total",4298,4038,3250,0.8,450,3285,0.73]
[]
["2b.","Proposed Location of Planned Facilities"]
[null,"New High School in Vernon"]
[null,"New Intermediate Center in Chipley",{"$nulls":4},"# of Units","Projected "]
["2c1.","Plans for the use and location of relocatable classroom facilities assigned student capacity.",null,null,null,"Number NOT meeting","projected","( increase ) /","Total age of all"]
[{"$nulls":5},"standards to be used","to be in use","decrease in # of","relocatables in"]
[null,"Location","Actual # of Units in 2001-02","Owner","Student Stations","as classroom space","in 2006-07","units by 2006-07","Column \"C\""]
[null,"Kate M. Smith Elementary",16,"Wash  Co Sch Bd",null,null,4,12,207]
[null,"Vernon High School",2,"Wash  Co Sch Bd",null,null,0,2,37]
[null,"Vernon Elementary School",10,"Wash  Co Sch Bd",null,null,1,9,114]
[null,"Vernon Middle",1,"Wash  Co Sch Bd",null,null,1,0,6]
[{"$nulls":7},0]
[{"$nulls":7},0]
["2c1.","Washington Total",29,null,0,0,6,23,"Avg Age 12.55"]
[]
["2c2.","Number of relocatable classrooms clearly identified and scheduled for replacement in the school board adopted financially feasible 5-year district work program."]
[null,"Location","Total # Units to be replaced","2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"Kate M. Smith elementary",16,null,null,null,12,4,16]
[null,"Vernon Elementary School",9,null,null,null,9,null,9]
[{"$nulls":8},0]
[{"$nulls":8},0]
["2c2.","Washington Total",25,0,0,0,21,4,25]
[]
["2c3.","Plans for the use and location of leased facilities, relocatable units or permanent classrooms. (place each location on a separate line)"]
[null,"Location","# of leased classrooms 2001-02","Owner","FISH Stu. Sta.","# Years Leased ","# leased 2006-07","FISH Stu. Sta.","# Years Leased "]
[null,"KMS Elem School",1,"Affordable structures",0,2,0,0]
[]
["2c3.","Washington Total",1,null,0,2,0,0,0]
[]
["2c4.","Plans for the use and location of Charter Schools, list current and PROJECTED.  (place each Charter School/location on a separate line)",{"$nulls":6},"Total charter students "]
[null,"Location-Type","# relocatable units or permanent classrooms ","Owner","Year Started","Student Stations","Students Enrolled","Years in Contract","projected for 2005-06"]
[null,"N/A",{"$nulls":6},0]
[{"$nulls":8},0]
["2c4.","Washington Total",0,null,null,0,0,0,0]
[]
["2d.","Plans for multitrack scheduling, grade level organization, block scheduling, or other alternatives that reduce the need for permanent student stations."]
[]
[]
[]
[]
["2e.","Average Class Size (5 years out -- 2006-07) that will result if the district facilities work plan is fully implemented."]
[null,"NOTE: You are no longer required to exclude exceptional student education classes or prekindergarten classes.",null,null,null,"Actual Average","Projected","New Rooms to","Projected Average"]
[null,"Location","(ESE & PreK excluded) # CLASSROOMS","Capacity (NOT Stu Sta)","2001-02 CO-FTE","2001-02 Class size","2006-07 CO-FTE","be added (removed)","2006-07 Class size"]
[null,"Vernon Middle School",17,358,432,25.41,435,null,25.59]
[null,"Chipley High School / Roulhac"]
[null,"     Middle School",42,1188,983,23.4,970,null,23.1]
[null,"Vernon Elementry School",26,500,528,20.31,580,null,22.31]
[null,"kate M. Smith Elementary",21,500,519,24.71,420,null,20]
[null,"Vernon High School",20,409,350,17.5,435,null,21.75]
[null,"Intermediate Center (Gr 3-5)",18,450,438,24.33,445,null,24.72]
["2e.","Washington Total",144,3405,3250,"District Avg 23",3285,0,"District Avg 23"]
[]
["2f.","The number and percentage of district students (CO-FTE) planned to be educated in relocatable facilities during each year."]
[]
[null,"Site                              ",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR AVERAGE"]
[null,"Kate Smith elementary",null,100,100,100,50,null,87.5]
[null,"Vernon High Schnool",null,30,30,0,0,null,15]
[null,"Vernon Elementary",null,100,75,50,19,null,61]
[]
[]
[]
["2f.","Washington Total students in relocatables by year",null,230,205,150,69,0,130.8]
[null,"Total number of CO-FTE students projected by year",null,3294,3316,3333,3310,null,3313.25]
[null,"Percent in relocatables by year",null,0.07,0.06,0.05,0.02,null,0.04]
[]
["2g.","Plans for the closure of any school, including plans for disposition of the facility or usage of facility space, and anticipated revenues."]
[null,"None"]
[{"$nulls":10},"State Average","State Average","State Average","State Average","State Average","State Average"]
["3 .","The projected cost for each project identified in the tentative district facilities work program.",{"$nulls":7},"Year",2000,2000,2000,2000,2000,2000]
[{"$nulls":9},"Type of School","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/Hi/StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/Hi/StuSta"]
[{"$nulls":9},1,82,107,146,8756,12965,23176]
[null,"1999 State-wide totals - Gross Sq Ft per student station: Elem low 79, avg 110, high 156; Middle low 86, avg 113, high 165; High School low 68, avg 128, high 222 ",{"$nulls":7},2,84,119,161,9899,13498,17138]
[null,"1999 State-wide totals - Cost per student station: Elem low 9,213, avg 12,712, high 22,844; Middle low 9,863,avg 13,571, high 18,853; High School low 14,900, avg 18,106, high  26,448 ",{"$nulls":7},3,93,112,185,12826,15024,22033]
[]
["3a.","2002-03 Year","Type of School (new schools only)  Others=0","2002-03","2002-03","2002-03","2002-03","2000 State Avg","2000 State Avg","2000 State Avg","2002 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3a.","Washington Total 2002-03",null,0,0,0,{"$nulls":4},{"$error":"#DIV/0!"}]
[]
["3b.","2003-2004 Year","Type of School (new schools only)  Others=0","2003-04","2003-04","2003-04","2003-04","2000 State Avg","2000 State Avg","2000 State Avg","2003 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Vernon High School",3,13854900,545,104652,192.02,93,112,185,25421.83,12826,15024,22033]
[{"$nulls":6},{"$error":"#DIV/0!"},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3b","Washington Total 2003-04",null,13854900,545,104652,192.02,null,null,null,25421.83]
[]
["3c.","2004-2005 Year","Type of School (new schools only)  Others=0","2004-05","2004-05","2004-05","2004-05","2000 State Avg","2000 State Avg","2000 State Avg","2004 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3c","Washington Total 2004-05",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3d.","2005-2006 Year","Type of School (new schools only)  Others=0","2005-06","2005-06","2005-06","2005-06","2000 State Avg","2000 State Avg","2000 State Avg","2005 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"Intermediate Center",null,4148429,450,50000,111,0,0,0,9218.73,0,0,0]
["3d.","Washington Total 2005-06",null,4148429,450,50000,111.11,null,null,null,9218.73]
[]
["3e.","2006-2007 Year","Type of School (new schools only)  Others=0","2006-07","2006-07","2006-07","2006-07","2000 State Avg","2000 State Avg","2000 State Avg","2006 Projected","2000 State Avg","2000 State Avg","2000 State Avg"]
[null,"Project Description","Elem=1, Middle=2, High=3, K-8=2, K-12=3, VoTech=3, ESE=3","PLANNED COST","Student Stations","Gross Sq. Ft","GSF/per StuSta","GSF/Low/StuSta","GSF/Avg/StuSta","GSF/High/StuSta","COST/per StuSta","COST/Low/StuSta","COST/Avg/StuSta","COST/High/StuSta"]
[null,"N/A",{"$nulls":5},0,0,0,{"$error":"#DIV/0!"},0,0,0]
[{"$nulls":7},0,0,0,{"$error":"#DIV/0!"},0,0,0]
["3e","Washington Total 2006-07",null,0,0,0,{"$error":"#DIV/0!"},null,null,null,{"$error":"#DIV/0!"}]
[]
["3f.","Washington 5-Year Total",null,18003329,995,154652,282]
[]
["4 .","Schedule of Estimated Capital Outlay Revenue from each currently approved source which is estimated to be available for expenditures on the"]
[null,"projects included in the tentative district facilities work program.   All amounts below are NET after considering carryover balances, interest earned, new COP's, 237 loans etc."]
[]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"The Millege projected for discretionary capital outlay per s.236.25",null,2,2,2,2,0,8]
[null,"Full value of the 2-Mill discretionary capital outlay per s.236.25",null,1000471,1000471,1000471,1000471,0,4001884]
[null,"Value of the portion of the 2-Mills ACTUALLY levied.",{"$nulls":6},0,"2 mill Expenditures"]
[null,"  less amount used to purchase school busses",null,390000,{"$nulls":4},390000,{"$error":"#DIV/0!"}]
[null,"  less amount used to purchase other vehicles",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less amount transferred to operating budget for maintenance/repair",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less amount used for maintenance/repair",null,610471,250118,250118,250118,null,1360825,{"$error":"#DIV/0!"}]
[null,"  less amount used to purchase capital outlay equipment",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less amount used to correct environmental problems",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less amount transferred to operating budget for salaries",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less amount used to pay debt service for s.237 loans",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less amount to pay debt service for COP's ",{"$nulls":6},0,{"$error":"#DIV/0!"}]
[null,"  less other (please be specific)",null,0,0,0,0,0,0,{"$error":"#DIV/0!"},"ALL Capital Outlay Expenditures"]
[null,"Net available 2-mills to construct new stu stations & core facilities",null,null,750353,750353,750353,0,2251059,{"$error":"#DIV/0!"},0.74]
[null,"P E C O New Construction",null,175398,112462,124554,138360,139699,690473,null,0.23]
[null,"C O & D S   Bond Proceeds  received on 20 March 1998",{"$nulls":6},0,null,0]
[null,"C O & D S maximum potential bond proceeds",null,20217,20217,20217,20217,20217,101085,null,0.03]
[null,"Proceeds from 1/2 cent sales surtax authorized",{"$nulls":6},0,null,0]
[null,"Proceeds from a s.237 loan",{"$nulls":6},0,null,0]
[null,"Proceeds from local governmental infrastructure sales surtax",{"$nulls":6},0,null,0]
[null,"Voted local bond referendum proceeds per s.9, Art VII State Const.",{"$nulls":6},0,null,0]
[null,"Proceeds from Certificates of Participation (COP's)",{"$nulls":6},0,null,0]
[null,"Classrooms First Bond proceeds amount authorized in FY 1997-98",{"$nulls":6},0,null,0]
[null,"Effort Index Grants",{"$nulls":6},0]
[null,"Impact fees received",{"$nulls":6},0,null,0]
[null,"Private donations",{"$nulls":6},0,null,0]
[null,"Grants from local governments or not-for-profit organizations",{"$nulls":6},0,null,0]
["4.","Washington Total",null,195615,883032,895124,908930,159916,3042617,{"$error":"#DIV/0!"},1]
[]
["5 .","Schedule indicating which projects included in the tentative district facilities work program will be funded from current revenues projected"]
[null,"in paragraph 4 above."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Vernon High School",null,null,2687086,null,null,null,2687086]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
[{"$nulls":8},0]
["5.","Washington Total",0,0,2687086,0,0,0,2687086]
[]
["6 .","Schedule of options for generation of additional revenues by the district facilities work program which are not funded under paragraph 5 above."]
[null,"Additional anticipated revenues may include effort index grants and SIT Program awards."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,null,null,"Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Special Appropiations",null,0,0,0,4148429,0,4148429]
[null,"Other (specify) Special Facilities",null,0,11167814,0,0,0,11167814]
["6.","Washington Total",null,0,11167814,0,4148429,0,15316243]
[]
["7 .","Schedule indicating which projects included in the tentative district facilities work program in paragraph (2) 2. above which CANNOT be funded"]
[null,"from current revenues projected over the next 5-years."]
[null,null,null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07"]
[null,"Project Description","Student Stations","Actual Budget","Projected","Projected","Projected","Projected","5 YEAR TOTAL"]
[null,"Vernon HighSchool",545,null,11167814,null,null,null,11167814]
[null,"Intermediate Center",450,null,null,null,4148429,null,4148429]
[{"$nulls":8},0]
["7.","Washington Total",995,0,11167814,0,4148429,0,15316243]
[]
[null,"NOTE: If the sum of the totals in paragraphs 5. and 7. above DO NOT equal the total in paragraph 2. above, the message \"Check Totals\" appears.   -- They should balance ! !"]
[null,"Project Description",null,"2002-03 ","2003-04 ","2004-05","2005-06","2006-07","5 YEAR TOTAL"]
[null,"This row is for \"Checking and Balancing\" only",null,"","","","","",""]
[]
["2.(b)","To the extent available, the tentative district facilities work program shall be based on information produced by the demographic and revenue"]
[null,"education estimating conferences."]
[]
["(3)","The adopted district facilities work program shall:"]
["(a)","Be a complete, balanced capital outlay financial plan for the district."]
["(b)","Set forth the proposed commitments and planned expenditures of the district to address the educational facilities needs of its students"]
[null,"and to adequately provide for the maintenance of the educational plant and ancillary facilities."]
[]
["(4)","The first year of the adopted district facilities work program shall constitute the capital outlay budget required in s. 235.18."]
[null,"The adopted district facilities work program shall include the information required in paragraphs (2) (a) 1., 2., and 3., based upon projects actually"]
[null,"funded in the program."]
{"$rows_empty":7}
["Respectfully submitted this ___________ day of ____________________, 2002."]
[]
[null,"SCHOOL BOARD OF ","Washington  COUNTY"]
[]
["DISTRICT SUPERINTENDENT:"]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date"]
[]
["CHIEF FINANCIAL OFFICER:  ____________________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,"Signature",null,null,"Name Printed",null,null,"Date",null," "]
[]
["DISTRICT POINT-OF-CONTACT PERSON:  _________________________________________________________________________________________________________________________________________________",{"$nulls":8}," "]
[null,null,null,"Name Printed","Job Title","Phone number(s)",null,"E-Mail Address",null,null," "]

{"sheet":"EXPLANATIONS OF WORK PLAN","index":2,"n_rows":0,"n_cols":0,"rows_kept":0,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}