{"text_format":"2","workbook":"xls","n_sheets":6,"sheets":["2005 All New Schools","2005 New Elementary Schools","2005 New Middle Schools","2005 New High Schools","2005 Additions","Source of Funds"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":1,"defined_names":0,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900","formulas":"cached_only"}

{"sheet":"2005 All New Schools","index":0,"n_rows":110,"n_cols":28,"rows_kept":110,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
[null,"FLORIDA DEPARTMENT OF EDUCATION"]
[null,"PUBLIC SCHOOL DISTRICTS"]
[null,"REPORT OF COST OF CONSTRUCTION"]
[]
[null,"NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
[null,"ALL SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05",{"$nulls":10},"January 2005"]
[null,null,null,"Designed/Build Constracts are not included",{"$nulls":10},"Elem",null,13739]
[{"$nulls":14},"Mid",null,15752]
[null,"Revised 6/30/08",{"$nulls":12},"High",null,20845,{"$nulls":9},"TOTAL"]
[{"$nulls":20},"CORRECT",{"$nulls":4},"TOTAL","PLANT"]
[{"$nulls":16},"TOTAL",null,null,null,"SITE",null,null,null,"CONST.","PLANT","COST"]
["Type",{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",null,null,null,"DRAINAGE","PUBLIC",null,null,"CONTRACT","COST","PER"]
["1-Ele",{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL","COST PER","PER","GROSS"]
["2=Mid","DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","HURRICANE","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","STUDENT","STUDENT","SQUARE","REVENUE"]
["3=Hi","NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","SHELTER","COST","COST","AREA COST","COST","COST","COST","STATION","STATION","FOOT","CODES"]
[1,"Broward","Coral Cove ES",1115,54,54,0,0,122000,82000,1284952,509296,597891,9437893,3397136,15227168,13656.652914798206,500000,0,0,89000,33558,0,15849726,8464.47802690583,14215.000896860987,193.28934146341464,"17,18,19"]
[2,"Clay","Argyle Elementary",562,24,18,4,0,62605,95955,200,496459.26,0,10467421.86,930444,11894525.12,21164.635444839856,77137,0,3983,0,0,0,11975645.12,18625.305800711743,21308.97708185053,124.80480558595174,"3,17"]
[2,"Clay","Lake Asbury Jr High",1106,41,0,40,0,118597,156918,0,889974.8,0,15526433.96,1845618,18262026.76,16511.77826401447,304000,1676126,4088,1000,150000,0,20397240.76,14038.36705244123,18442.351500904162,129.9866220573803,"11,17,19"]
[3,"Collier","Golden Gate High",2412,115,0,0,90,251202,340887,0,1750250,4493422,34892388,3283452,44419512,18416.04975124378,120000,2300170,562213,452095,637787,1652787,50144564,14466.164179104477,20789.62023217247,147.10025316307164,"18,19"]
[1,"Collier","Golden Gate Interm.",633,28,20,0,0,71994,109924,0,391450,475937,7531546,800743,9199676,14533.453396524486,620000,1648069,241000,181000,0,0,11889745,11898.176935229068,18783.167456556082,108.16332193151632,"3,17"]
[1,"Collier","Estates Elementary",969,48,48,0,0,85856,109574,41352,344600,2333423,8722740,1539939,12982054,13397.372549019608,1242841,2000000,1755233,710465,634689,0,19325282,9001.795665634674,19943.531475748194,176.3674046762918,"3,17,19"]
[3,"Collier","Palmetto Ridge High",2419,94,0,0,94,297796,323926,0,1599500,6366889,35106204,1800000,44872593,18550.059115336917,543870,2880000,24270,658443,203182,0,49182358,14512.692848284414,20331.689954526664,151.83207893160784,"14,17,18"]
[2,"Dade","S/S \"SS1\"",1506,66,0,66,0,133415,141286,2325701,884565,487595,17891055,2346804,23935720,15893.572377158034,2793925,1500000,2219320,736760,196000,2339100,33720825,11879.850597609562,22390.98605577689,238.6706750845802,"6,7,17,19"]
[3,"Dade","S/S \"WWW\" Miami Sprg Sr Relief",1613,68,3,4,68,154202,163300,659940,876316,0,23166505,3376701,28079462,17408.2219466832,3977081,6000001,836617,481000,65580,1096864,40536605,14362.371357718537,25131.187228766274,248.23395590936926,"17,18"]
[1,"Flagler","Belle Terre Elem.",988,54,54,0,0,21000,161514,454,752496,205000,14497050,1071023,16526023,16726.743927125506,140000,0,45000,55000,453339,0,17219362,14673.127530364372,17428.504048582996,106.61219460851692,"6,16"]
[2,"Hernando","Challenger K-8 Sch",1557,67,24,42,0,167859,246947,0,1324875,0,29628134,3749636,34702645,22288.14707771355,146672,1050000,750,0,0,650,35900717,19028.9877970456,23057.621708413615,145.37822690698815,"5,17,18,19"]
[3,"Hillsborough","Aparicio-Levy Adult Ct",156,12,0,0,12,25943,27500,9026,316794,463608,2994268,300000,4083696,26177.53846153846,0,63754,188751,34323,55000,14925,4440449,19194.02564102564,28464.416666666668,161.47087272727273,"17,19"]
[1,"Hillsborough","Frost Elementary",706,41,41,0,0,79727,85242,210,370633,762837,7182621,797937,9114238,12909.685552407933,139001,1298880,31747,98111,0,0,10681977,10173.684135977337,15130.279036827196,125.31354261983529,"17,18"]
[2,"Hillsborough","Giunta Middle Sch.",1291,52,0,56,0,127985,135664,55,780185,1724047,13048350,1545370,17098007,13244.002323780016,105225,2637120,378403,317518,0,54252,20590525,10107.1649883811,15949.28350116189,151.7758948578842,"13,17"]
[2,"Hillsborough","Rampello Dwntn Partn",965,52,14,32,0,96113,101880,21070,791179,382800,11237145,1127751,13559945,14051.756476683939,0,4120143,256289,84000,172000,257988,18450365,11644.709844559586,19119.549222797927,181.09898900667451,"17,18,19"]
[1,"Hillsborough","Turner Elementary",860,50,47,0,0,84203,89255,112,442255,1114379,8595573,1025904,11178223,12997.933720930232,140000,506220,22582,0,0,0,11847025,9994.852325581396,13775.610465116279,132.73233992493417,"18,19"]
[1,"Lee","Staging School East",809,44,25,11,0,99628,100691,275000,485520,353529,9039480,824000,10977529,13569.257107540174,0,4000000,0,0,0,0,14977529,11173.646477132263,18513.63288009889,148.74744515398595,"16,17"]
[1,"Lee","Rayma Page Elem.",856,45,44,0,0,112365,116194,275000,485520,125000,10323607,950000,12159127,14204.58761682243,0,5700000,0,0,0,0,17859127,12060.288551401869,20863.466121495327,153.7009398075632,"16,17,18"]
[1,"Manatee","Bayshore Elementary",709,50,41,0,0,101230,113698,41040,480172,1416342,9004585,570955,11513094,16238.496473906911,1480250,0,78000,226057,0,0,13297401,12700.40197461213,18755.149506346967,116.95369311685342,"16,19"]
[1,"Manatee","Robert H. Prine Elem.",706,50,41,0,0,101230,113698,46000,485175,1407957,9336976,570955,11847063,16780.542492917848,1336988,0,95000,237073,0,0,13516124,13225.178470254958,19144.651558073656,118.87741209168148,"3,17"]
[1,"Manatee","Robert E. Willis Elem.",751,44,30,0,0,88659,112554,353413,578533,946800,11551847,680717,14111310,18790.026631158456,2030160,638000,125000,420000,76000,0,17400470,15381.953395472703,23169.733688415447,154.59663805817652,"6,7,11,13,16,19"]
[2,"Orange","Freedom Middle",1602,55,0,55,0,131727,168844,157723,880131,2501330,18336596,1899380,23775160,14840.923845193509,200000,7446880,46854,254076,0,250,31723220,11446.064918851436,19802.25967540574,187.8847930634195,19]
[2,"Orange","Legacy Middle",1318,55,0,55,0,131522,168844,258947,802700,3163704,16888233,2063162,23176746,17584.784522003036,200000,4160877,26204,644375,0,2260,28210462,12813.530349013658,21403.992412746586,167.08003837862168,19]
[1,"Orange","McCoy Elementary",860,46,44,0,0,74682,98382,143581,592311,1888191,10216433,900000,13740516,15977.344186046512,0,0,4094,340619,0,1860,14087089,11879.573255813953,16380.336046511628,143.18766644304853,19]
[1,"Orange","Bay Meadows Elem.",1001,46,44,0,0,74691,96927,80774,624772,2169475,10482312,900000,14257333,14243.08991008991,0,2276580,92655,222956,0,0,16849524,10471.84015984016,16832.69130869131,173.8372589680894,"6,19"]
[2,"Orange","Meadowbrook Middle",1679,61,0,61,0,132168,168844,267505,887438,2391808,19535040,1786942,24868733,14811.63371054199,200000,0,92216,470948,0,4541,25636438,11634.925550923168,15268.873138773079,151.8350548435242,19]
[1,"Orange","Whispering Oak Elem",940,45,44,0,0,73983,96927,39905,450305,1660649,8531748,1056669,11739276,12488.591489361703,0,357350,49263,269043,0,0,12414932,9076.327659574468,13207.374468085107,128.0853838455745,18]
[1,"Orange","Andover Elementary",940,46,44,0,0,73983,96927,88803,434074,1870179,9481816,1070745,12945617,13771.932978723404,0,499220,74962,230000,0,0,13749799,10087.038297872341,14627.445744680852,141.85726371392903,"18,19"]
[1,"Orange","East Lake Elementary",940,46,44,0,0,73983,96927,42565,479070,1675165,9529369,1000000,12726169,13538.477659574468,0,523000,41661,197048,0,0,13487878,10137.626595744681,14348.806382978724,139.15501356691118,18]
[3,"Orange","Ocoee High School",3128,117,0,0,117,285596,381913,183770,1279750,5594184,34640372,4700000,46398076,14833.144501278772,300000,1740113,406059,540261,1632285,2904,51019698,11074.287723785166,16310.645140664961,133.58984376022812,19]
[1,"Osceola","Chestnut Elem \"G\"",1110,63,59,0,0,118948,124839,0,690932,249884,12559700,1714654,15215170,13707.36036036036,267151,0,347976,605724,569318,32370,17037709,11315.045045045044,15349.287387387387,136.47745496199104,"18,19"]
[1,"Osceola","St. Cloud Elem \"H\"",1110,63,59,0,0,118948,124839,0,475907,380000,12597084,1699009,15152000,13650.450450450451,252000,457612,317000,316000,777397,20000,17292009,11348.724324324325,15578.386486486486,138.51447864849928,"18,19,20"]
[3,"Palm Beach","West Boca High",2420,115,0,0,48,371432,393718,0,2492414,3799451,35966452.44,3905853,46164170.44,19076.103487603305,2000000,1996860.64,1636708,1118000,53350,0,52969089.08,14862.170429752065,21888.053338842976,134.53560436657708]
[2,"Palm Beach","LC Swain Middle",1900,75,0,33,0,192661,204221,0,1057873,3131595,20460178.31,1286196.03,25935842.34,13650.443336842105,0,6760266.42,299300,215500,1085520,413490,34709918.76,10768.5149,18268.37829473684,169.96253450918366]
[3,"Palm Beach","Seminole Ridge High",2649,120,0,0,50,376677,399278,0,2495788.06,0,44170127.94,3716566,50382482,19019.43450358626,2817432,1859597.27,3609930,489870,59945,0,59219256.269999996,16674.264983012457,22355.325130237823,148.31585078566812]
[1,"Palm Beach","Hidden Oaks Elem.",1235,64,46,0,0,129084,136829,0,566609.5,0,15458430.5,877205,16902245,13686.028340080971,0,4720831.51,0,119645,135459,4697,21882877.509999998,12516.947773279353,17718.929157894734,159.92865189396983]
[1,"Pasco","Sevens Oaks Elem",674,36,36,0,0,74499,95912,0,311440,0,10548532,976954,11836926,17562.20474777448,795000,248757,0,0,0,94810,12975493,15650.640949554896,19251.473293768548,135.2853970306114,"6,13,16,19"]
[1,"Pasco","Longleaf Elem.",674,36,36,0,0,74323,94961,0,333848,0,9718363,1006140,11058351,16407.04896142433,795000,0,14000,0,3000,57025,11927376,14418.936201780416,17696.403560830862,125.60288960731248,"6,16"]
[2,"Pinellas","Safety Harbor Middle",1650,63," "," ",null,138217,193393,0,813258,0,21445949,2468100,24727307,14986.246666666666,0,0,0,0,0,0,24727307,12997.54484848485,14986.246666666666,127.86040342721815,"3,17"]
[1,"Polk","Chain of Lakes Elem",736,0,36,0,0,74355,106628,9458,454300,746784,10106322,1019048,12335912,16760.75,823125,629987,13428,10730,69277,0,13882459,13731.415760869566,18862.036684782608,130.19524890272723,18]
[3,"Polk","Ridge Comm Sr Hi",1788,75,0,0,75,238640,329874,24759,1029432.53,2987700,27955403,2934950,34932244.53,19537.04951342282,3030116,2068016,56973,435562,261312,0,40784223.53,15635.012863534675,22809.96841722595,123.63576253357343,"3,18,19"]
[]
[null,"FLORIDA DEPARTMENT OF EDUCATION"]
[null,"PUBLIC SCHOOL DISTRICTS"]
[null,"REPORT OF COST OF CONSTRUCTION"]
[]
[null,"NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
[null,"ALL SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05",{"$nulls":10},"January 2005"]
[null,null,null,"Designed/Build Constracts are not included",{"$nulls":10},"Elem",null,13739]
[{"$nulls":14},"Mid",null,15752]
[{"$nulls":14},"High",null,20845,{"$nulls":9},"TOTAL"]
[{"$nulls":20},"CORRECT",{"$nulls":4},"TOTAL","PLANT"]
[{"$nulls":16},"TOTAL",null,null,null,"SITE",null,null,null,"CONST.","PLANT","COST"]
["Type",{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",null,null,null,"DRAINAGE","PUBLIC",null,null,"CONTRACT","COST","PER"]
["1-Ele",{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL","COST PER","PER","GROSS"]
["2=Mid","DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","HURRICANE","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","STUDENT","STUDENT","SQUARE","REVENUE"]
["3=Hi","NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","SHELTER","COST","COST","AREA COST","COST","COST","COST","STATION","STATION","FOOT","CODES"]
[1,"St. Johns","Timberlin Creek Elm",616,34,32,0,0,87667,95863,9656.85,579809.67,0,11934876.91,819532.67,13343876.1,21662.136525974027,159000,602477,870371.04,173858.62,486797.02,0,15636379.78,19374.80017857143,25383.733409090906,163.1117300731252,"3,11,12,17,18,19"]
[1,"St. Johns","South Woods Elem.",616,34,32,0,0,87667,95863,5922.3,682963.66,0,11682597.45,934781.56,13306264.97,21601.07949675325,159000,411270,2914105.47,206712.45,457472.47,0,17454825.36,18965.25560064935,28335.755454545455,182.08094217789971,"3,11,12,17,18,19"]
[1,"St. Johns","Hickory Creek Elem.",616,34,32,0,0,87667,95863,854,503150.74,0,11178275.66,989003.99,12671284.39,20570.266866883117,135000,0,293248,250101.13,0,0,13349633.520000001,18146.551396103896,21671.48298701299,139.25741443518356,"4,6,12,17,19"]
[2,"St. Lucie","Oak Hammock K-8",1923,90,31,59,0,227980,248000,451088,1551036,2240652,22199868,3759765,30202409,15705.88091523661,1000000,196000,20000,35000,90554,0,31543963,11544.39313572543,16403.516900676026,127.19339919354839,"6,18,19"]
[1,"Sarasota","Venice Elementary",970,60,60,0,0,109000,109000,5000,689612,325000,10437721,1292000,12749333,13143.642268041238,0,0,5000,10000,0,0,12764333,10760.537113402062,13159.10618556701,117.10397247706422,"17,18,19"]
[1,"Sarasota","Tatum Ridge Elem",970,60,60,0,0,110000,110000,10000,485901,300000,10120000,1292000,12207901,12585.464948453608,60000,1200000,5000,5000,0,0,13477901,10432.98969072165,13894.743298969071,122.52637272727273,"17,18,19"]
[1,"Sarasota","Phillippi Shores Elm",970,39,39,0,0,120900,129048,61795,1280115,1741000,11959900,1184056,16226866,16728.727835051548,135964,0,0,289000,235000,0,16886830,12329.79381443299,17409.103092783505,130.8569679499101,"13,17,19"]
[1,"Sarasota","Wilkinson Elem",544,33,28,0,0,79467,83603,2000,386000,897821,8696372,415758,10397951,19113.88051470588,225000,0,119756,57000,0,0,10799707,15985.97794117647,19852.402573529413,129.178462495365,14]
[1,"Seminole","Walker Elementary",827,40,0,0,0,79621,114568,329221,345000,879664,6797291,1049735,9400911,11367.486094316808,64620,300000,1278,436132,129580,4390,10336911,8219.215235792019,12499.287787182588,90.22511521541792,"17,19"]
[]
[]
[null,"FLORIDA DEPARTMENT OF EDUCATION"]
[null,"PUBLIC SCHOOL DISTRICTS"]
[null,"REPORT OF COST OF CONSTRUCTION"]
[null,"REPORT OF COST OF CONSTRUCTION"]
[]
[null,"NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
[null,"ALL SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
[null,"DESIGN BUILD"]
[{"$nulls":26},"TOTAL"]
[{"$nulls":20},"CORRECT",{"$nulls":4},"TOTAL","PLANT"]
[{"$nulls":16},"TOTAL",null,null,null,"SITE",null,null,null,"CONST.","PLANT","COST"]
[{"$nulls":5},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",null,null,null,"DRAINAGE","PUBLIC",null,null,"CONTRACT","COST","PER"]
[{"$nulls":5},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL","COST PER","PER","GROSS"]
[null,"DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","HURRICANE","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","STUDENT","STUDENT","SQUARE","REVENUE"]
[null,"NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","SHELTER","COST","COST","AREA COST","COST","COST","COST","STATION","STATION","FOOT","CODES"]
[1,"Baker","Pre-k Center",684,19,38,0,0,50383,50383,0,437500,223513,6613746,90000,7364759,10767.191520467837,0,0,0,500000,0,0,7864759,9669.219298245614,11498.185672514619,156.09945815056665,"3,17,18"]
[3,"Broward","Dave  Thomas Ed",616,25,0,0,23,57820,82128,1330281,90224,60262,10380119,1217484,13078370,21231.12012987013,0,0,0,800000,400000,0,14278370,16850.842532467534,23179.172077922078,173.8550798753166,"17,18"]
[3,"Monroe","Coral Shores High",1285,52,0,0,0,201421,202686,1298,1561311,2194139,41313535,662264,45732547,35589.53073929961,0,0,195920,740111,134406,19504,46822488,32150.610894941634,36437.733852140074,231.0099760220242,"3,5,8,11,12,17,19"]
[2,"Pinellas","Oak Grove Middle",1376,52,0,0,0,135312,189329,0,941595,0,21560487,2413987,24916069,18107.60828488372,0,0,0,0,0,0,24916069,15668.958575581395,18107.60828488372,131.6019680027888,17]
[2,"Pinellas","Lealman Intermediate",460,20,null,null,null,63144,88351,0,608040,0,13725000,1450000,15783040,34310.95652173913,0,0,0,0,0,0,15783040,29836.956521739132,34310.95652173913,178.6401964890041,"5,6"]
[]
[]
[]
[31,"Elem Average",null,843.0645161290323,43.61290322580645,null,null,null,88443.32258064517,104794.6129032258,101518.32741935484,520299.0506451613,798271.6129032258,10124993.790967742,1048922.5877419354,12594005.36967742,15262.513146376958,370970.96774193546,903814.6293548386,243785.7906451613,201815.32903225807,130996.33838709678,6940.387096774193,14452328.811935483,12363.420638108428,17525.1515521747,139.2877876366851]
[14,"Mid Average",null,1349.642857142857,55.214285714285715,null,null,null,132807.5,164891.14285714287,248734.92857142858,907807.79,1144537.9285714286,17996420.794999998,2048082.5021428573,22345583.944285717,17653.740697664045,359068.5,2110529.458571429,239100.5,197084.07142857142,121005.28571428571,219466.5,25591838.259999998,14431.091062933423,19915.7572118952,158.12668581476913]
[10,"High Average",null,1848.6,79.3,null,null,null,226072.9,264521,220907.4,1349177.959,2595965.5,29058537.438,2589727,35814315.297000006,20983.825214986326,1278849.9,1890851.191,751744.1,574966.5,350284.7,278698.4,40939710.088,16978.244345362662,23769.781203916595,165.3579278074709]
[55,"All New Sch","Average:",1154.8363636363636,54.03703703703704,38.51428571428571,39.84615384615385,64.11111111111111,124759.58181818182,149133.07272727272,232590.2934210526,769642.8949090911,1627551.3658536586,15571092.23690909,1583400.459090909,19298099.902727272,16904.560852669758,792312.3783783783,2124282.717777778,418686.53431818174,328113.71555555554,330635.9817857142,303733.35,22103727.812545456,13728.795602110107,19269.056565874806,148.82316902215842]

{"sheet":"2005 New Elementary Schools","index":1,"n_rows":68,"n_cols":31,"rows_kept":68,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
["ELEMENTARY SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
[null,null,"Designed/Build Constracts are not included"]
[]
[{"$nulls":29},"TOTAL"]
[{"$nulls":22},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":15},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Broward","Coral Cove ES",1115,54,54,0,0,122000,82000,1284952,509296,597891,9437893,3397136,15227168,13656.652914798206,0,0,500000,0,0,0,89000,33558,0,15849726,null,8464.47802690583,14215.000896860987,193.28934146341464,"17,18,19"]
["Clay","Argyle Elementary",562,24,18,4,0,62605,95955,200,496459.26,0,10467421.86,930444,11894525.12,21164.635444839856,0,0,77137,0,0,3983,0,0,0,11975645.12,null,18625.305800711743,21308.97708185053,124.80480558595174,"3,17"]
["Collier","Golden Gate Interm.",633,28,20,0,0,71994,109924,0,391450,475937,7531546,800743,9199676,14533.453396524486,0,0,620000,0,1648069,241000,181000,0,0,11889745,null,11898.176935229068,18783.167456556082,108.16332193151632,"3,17"]
["Collier","Estates Elementary",969,48,48,0,0,85856,109574,41352,344600,2333423,8722740,1539939,12982054,13397.372549019608,0,0,1242841,0,2000000,1755233,710465,634689,0,19325282,null,9001.795665634674,19943.531475748194,176.3674046762918,"3,17,19"]
["Flagler","Belle Terre Elem.",988,54,54,0,0,21000,161514,454,752496,205000,14497050,1071023,16526023,16726.743927125506,0,0,140000,0,0,45000,55000,453339,0,17219362,null,14673.127530364372,17428.504048582996,106.61219460851692,"6,16"]
["Hillsborough","Frost Elementary",706,41,41,0,0,79727,85242,210,370633,762837,7182621,797937,9114238,12909.685552407933,0,0,139001,0,1298880,31747,98111,0,0,10681977,null,10173.684135977337,15130.279036827196,125.31354261983529,"17,18"]
["Hillsborough","Turner Elementary",860,50,47,0,0,84203,89255,112,442255,1114379,8595573,1025904,11178223,12997.933720930232,0,0,140000,0,506220,22582,0,0,0,11847025," ",9994.852325581396,13775.610465116279,132.73233992493417,"18,19"]
["Lee","Rayma Page Elem.",856,45,44,0,0,112365,116194,275000,485520,125000,10323607,950000,12159127,14204.58761682243,0,0,0,0,5700000,0,0,0,0,17859127,null,12060.288551401869,20863.466121495327,153.7009398075632,"16,17,18"]
["Manatee","Bayshore Elementary",709,50,41,0,0,101230,113698,41040,480172,1416342,9004585,570955,11513094,16238.496473906911,0,0,1480250,0,0,78000,226057,0,0,13297401,null,12700.40197461213,18755.149506346967,116.95369311685342,"16,19"]
["Manatee","Robert H. Prine Elem.",706,50,41,0,0,101230,113698,46000,485175,1407957,9336976,570955,11847063,16780.542492917848,0,0,1336988,0,0,95000,237073,0,0,13516124,null,13225.178470254958,19144.651558073656,118.87741209168148,"3,17"]
["Manatee","Robert E. Willis Elem.",751,44,30,0,0,88659,112554,353413,578533,946800,11551847,680717,14111310,18790.026631158456,0,0,2030160,0,638000,125000,420000,76000,0,17400470,null,15381.953395472703,23169.733688415447,154.59663805817652,"6,7,11,13,16,19"]
["Orange","McCoy Elementary",860,46,44,0,0,74682,98382,143581,592311,1888191,10216433,900000,13740516,15977.344186046512,0,0,0,0,0,4094,340619,0,1860,14087089,null,11879.573255813953,16380.336046511628,143.18766644304853,19]
["Orange","Bay Meadows Elem.",1001,46,44,0,0,74691,96927,80774,624772,2169475,10482312,900000,14257333,14243.08991008991,0,0,0,0,2276580,92655,222956,0,0,16849524,null,10471.84015984016,16832.69130869131,173.8372589680894,"6,19"]
["Orange","Whispering Oak Elem",940,45,44,0,0,73983,96927,39905,450305,1660649,8531748,1056669,11739276,12488.591489361703,0,0,0,0,357350,49263,269043,0,0,12414932,null,9076.327659574468,13207.374468085107,128.0853838455745,18]
["Orange","Andover Elementary",940,46,44,0,0,73983,96927,88803,434074,1870179,9481816,1070745,12945617,13771.932978723404,0,0,0,0,499220,74962,230000,0,0,13749799,null,10087.038297872341,14627.445744680852,141.85726371392903,"18,19"]
["Orange","East Lake Elementary",940,46,44,0,0,73983,96927,42565,479070,1675165,9529369,1000000,12726169,13538.477659574468,0,0,0,0,523000,41661,197048,0,0,13487878,null,10137.626595744681,14348.806382978724,139.15501356691118,18]
["Orange","Ocoee High School",3128,117,0,0,117,285596,381913,183770,1279750,5594184,34640372,4700000,46398076,14833.144501278772,0,0,300000,0,1740113,406059,540261,1632285,2904,51019698,null,11074.287723785166,16310.645140664961,133.58984376022812,19]
["Osceola","Chestnut Elem \"G\"",1110,63,59,0,0,118948,124839,0,690932,249884,12559700,1714654,15215170,13707.36036036036,0,0,267151,0,0,347976,605724,569318,32370,17037709,null,11315.045045045044,15349.287387387387,136.47745496199104,"18,19"]
["Osceola","St. Cloud Elem \"H\"",1110,63,59,0,0,118948,124839,0,475907,380000,12597084,1699009,15152000,13650.450450450451,0,0,252000,0,457612,317000,316000,777397,20000,17292009,null,11348.724324324325,15578.386486486486,138.51447864849928,"18,19,20"]
["Palm Beach","Hidden Oaks Elem.",1235,64,46,0,0,129084,136829,0,566609.5,0,15458430.5,877205,16902245,13686.028340080971,0,0,0,0,4720831.51,0,119645,135459,4697,21882877.509999998,null,12516.947773279353,17718.929157894734,159.92865189396983]
["Pasco","Sevens Oaks Elem",674,36,36,0,0,74499,95912,0,311440,0,10548532,976954,11836926,17562.20474777448,0,0,795000,0,248757,0,0,0,94810,12975493,null,15650.640949554896,19251.473293768548,135.2853970306114,"6,13,16,19"]
["Pasco","Longleaf Elem.",674,36,36,0,0,74323,94961,0,333848,0,9718363,1006140,11058351,16407.04896142433,0,0,795000,0,0,14000,0,3000,57025,11927376,null,14418.936201780416,17696.403560830862,125.60288960731248,"6,16"]
["Polk","Chain of Lakes Elem",736,0,36,0,0,74355,106628,9458,454300,746784,10106322,1019048,12335912,16760.75,0,0,823125,0,629987,13428,10730,69277,0,13882459,null,13731.415760869566,18862.036684782608,130.19524890272723,18]
["St. Johns","Timberlin Creek Elm",616,34,32,0,0,87667,95863,9656.85,579809.67,0,11934876.91,819532.67,13343876.1,21662.136525974027,0,0,159000,0,602477,870371.04,173858.62,486797.02,0,15636379.78,null,19374.80017857143,25383.733409090906,163.1117300731252,"3,11,12,17,18,19"]
["St. Johns","South Woods Elem.",616,34,32,0,0,87667,95863,5922.3,682963.66,0,11682597.45,934781.56,13306264.97,21601.07949675325,0,0,159000,0,411270,2914105.47,206712.45,457472.47,0,17454825.36,null,18965.25560064935,28335.755454545455,182.08094217789971,"3,11,12,17,18,19"]
["St. Johns","Hickory Creek Elem.",616,34,32,0,0,87667,95863,854,503150.74,0,11178275.66,989003.99,12671284.39,20570.266866883117,0,0,135000,0,0,293248,250101.13,0,0,13349633.520000001,null,18146.551396103896,21671.48298701299,139.25741443518356,"4,6,12,17,19"]
["Sarasota","Venice Elementary",970,60,60,0,0,109000,109000,5000,689612,325000,10437721,1292000,12749333,13143.642268041238,0,0,0,0,0,5000,10000,0,0,12764333,null,10760.537113402062,13159.10618556701,117.10397247706422,"17,18,19"]
["Sarasota","Tatum Ridge Elem",970,60,60,0,0,110000,110000,10000,485901,300000,10120000,1292000,12207901,12585.464948453608,0,0,60000,0,1200000,5000,5000,0,0,13477901,null,10432.98969072165,13894.743298969071,122.52637272727273,"17,18,19"]
["Sarasota","Phillippi Shores Elm",970,39,39,0,0,120900,129048,61795,1280115,1741000,11959900,1184056,16226866,16728.727835051548,0,0,135964,0,0,0,289000,235000,0,16886830,null,12329.79381443299,17409.103092783505,130.8569679499101,"13,17,19"]
["Sarasota","Wilkinson Elem",544,33,28,0,0,79467,83603,2000,386000,897821,8696372,415758,10397951,19113.88051470588,0,0,225000,0,0,119756,57000,0,0,10799707,null,15985.97794117647,19852.402573529413,129.178462495365,14]
["Seminole","Walker Elementary",827,40,0,0,0,79621,114568,329221,345000,879664,6797291,1049735,9400911,11367.486094316808,0,0,64620,0,300000,1278,436132,129580,4390,10336911,null,8219.215235792019,12499.287787182588,90.22511521541792,"17,19"]
[]
[]
[]
[]
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
["ELEMENTARY SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
["DESIGN BUILD"]
[]
[{"$nulls":29},"TOTAL"]
[{"$nulls":22},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":15},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Baker","Pre-k Center",684,19,38,0,0,50383,50383,0,437500,223513,6613746,90000,7364759,10767.191520467837,0,0,0,0,0,0,500000,0,0,7864759,null,9669.219298245614,11498.185672514619,156.09945815056665,"3,17,18"]
["Pinellas","Lealman Intermediate",460,20,null,null,null,63144,88351,0,608040,0,13725000,1450000,15783040,34310.95652173913,0,0,0,0,0,0,0,0,0,15783040,null,29836.956521739132,34310.95652173913,178.6401964890041,"5,6"]

{"sheet":"2005 New Middle Schools","index":2,"n_rows":49,"n_cols":31,"rows_kept":49,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
["MIDDLE SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
[null,null,"Designed/Build Constracts are not included"]
[]
[{"$nulls":29},"TOTAL"]
[{"$nulls":22},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":15},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Dade","S/S \"SS1\"",1506,66,0,66,0,133415,141286,2325701,884565,487595,17891055,2346804,23935720,15893.572377158034,0,0,2793925,0,1500000,2219320,736760,196000,2339100,33720825,null,11879.850597609562,22390.98605577689,238.6706750845802,"6,7,17,19"]
["Hernando","Challenger K-8 Sch",1557,67,24,42,0,167859,246947,0,1324875,0,29628134,3749636,34702645,22288.14707771355,0,0,146672,0,1050000,750,0,0,650,35900717,null,19028.9877970456,23057.621708413615,145.37822690698815,"5,17,18,19"]
["Hillsborough","Giunta Middle Sch.",1291,52,0,56,0,127985,135664,55,780185,1724047,13048350,1545370,17098007,13244.002323780016,0,0,105225,0,2637120,378403,317518,0,54252,20590525,null,10107.1649883811,15949.28350116189,151.7758948578842,"13,17"]
["Hillsborough","Rampello Dwntn Partn",965,52,14,32,0,96113,101880,21070,791179,382800,11237145,1127751,13559945,14051.756476683939,0,0,0,0,4120143,256289,84000,172000,257988,18450365,null,11644.709844559586,19119.549222797927,181.09898900667451,"17,18,19"]
["Lee","The Sanibez School",439,25,10,11,0,55777,68375,68610,377945,1618830,6031950,671129,8768464,19973.722095671983,0,0,0,0,0,100000,50000,0,0,8918464,null,13740.205011389522,20315.407744874716,130.4345740402194,"11,12,13,17"]
["Lee","Staging School East",809,44,25,11,0,99628,100691,275000,485520,353529,9039480,824000,10977529,13569.257107540174,0,0,0,0,4000000,0,0,0,0,14977529,null,11173.646477132263,18513.63288009889,148.74744515398595,"16,17"]
["Orange","Freemdon Middle",1602,55,0,55,0,131727,168844,157723,880131,2501330,18336596,1899380,23775160,14840.923845193509,0,0,200000,null,7446880,46854,254076,0,250,31723220," ",11446.064918851436,19802.25967540574,187.8847930634195,19]
["Orange","Legacy Middle",1318,55,0,55,0,131522,168844,258947,802700,3163704,16888233,2063162,23176746,17584.784522003036,0,0,200000,0,4160877,26204,644375,0,2260,28210462,null,12813.530349013658,21403.992412746586,167.08003837862168,19]
["Orange","Meadowbrook Middle",1679,61,0,61,0,132168,168844,267505,887438,2391808,19535040,1786942,24868733,14811.63371054199,0,0,200000,0,0,92216,470948,0,4541,25636438,null,11634.925550923168,15268.873138773079,151.8350548435242,19]
["Palm Beach","LC Swain Middle",1900,75,0,33,0,192661,204221,0,1050657,3131595,25721040.97,1286196.03,31189489,16415.520526315788,0,0,0,0,6760266.42,299300,215500,1085520,413490,39963565.42,null,13537.389984210526,21033.455484210528,195.68783533524956]
["Pinellas","Safety Harbor Middle",1650,63," "," ",null,138217,193393,0,813258,0,21445949,2468100,24727307,14986.246666666666,0,0,0,0,0,0,0,0,0,24727307,null,12997.54484848485,14986.246666666666,127.86040342721815,"3,17"]
[]
[]
[]
[]
[]
[]
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
["MIDDLE SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
["DESIGN BUILD"]
[]
[{"$nulls":29},"TOTAL"]
[{"$nulls":22},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":15},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Pinellas","Oak Grove Middle",1376,52,null,null,null,135312,189329,0,941595,0,21560487,2413987,24916069,18107.60828488372,0,0,0,0,0,0,0,0,0,24916069,null,15668.958575581395,18107.60828488372,131.6019680027888,17]

{"sheet":"2005 New High Schools","index":3,"n_rows":47,"n_cols":33,"rows_kept":47,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
["HIGH SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
[null,null,"Designed/Build Constracts are not included"]
[]
[{"$nulls":29},"TOTAL"]
[{"$nulls":22},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":15},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Clay","Lake Asbury Jr High",1106,41,0,40,0,118597,156918,0,889974.8,0,15526433.96,1845618,18262026.76,16511.77826401447,0,0,304000,0,1676126,4088,1000,150000,0,20397240.76,null,14038.36705244123,18442.351500904162,129.9866220573803,"11,17,19"]
["Collier","Golden Gate High",2412,115,0,0,90,251202,340887,0,1750250,4493422,34892388,3283452,44419512,18416.04975124378,0,0,120000,0,2300170,562213,452095,637787,1652787,50144564,null,14466.164179104477,20789.62023217247,147.10025316307164,"18,19"]
["Collier","Palmetto Ridge High",2419,94,0,0,94,297796,323926,0,1599500,6366889,35106204,1800000,44872593,18550.059115336917,0,0,543870,0,2880000,24270,658443,203182,0,49182358,null,14512.692848284414,20331.689954526664,151.83207893160784,"14,17,18"]
["Dade","S/S \"WWW\" Miami Springs Senior Relief",1613,68,3,4,68,154202,163300,659940,876316,0,23166505,3376701,28079462,17408.2219466832,0,0,3977081,0,6000001,836617,481000,65580,1096864,40536605,null,14362.371357718537,25131.187228766274,248.23395590936926,"17,18"]
["Hillsborough","Aparicio-Levy Adult Ct",156,12,0,0,12,25943,27500,9026,316794,463608,2994268,300000,4083696,26177.53846153846,0,0,0,null,63754,188751,34323,55000,14925,4440449,null,19194.02564102564,28464.416666666668,161.47087272727273,"17,19"]
["Orange","Ocoee High School",3128,117,0,0,117,285596,381913,183770,1279750,5594184,34640372,4700000,46398076,14833.144501278772,0,0,300000,0,1740113,406059,540261,1632285,2904,51019698,null,11074.287723785166,16310.645140664961,133.58984376022812,19]
["Palm Beach","West Boca High",2420,115,0,0,48,371432,393718,0,2492414,3799451,35966452.44,3905853,46164170.44,19076.103487603305,0,0,2000000,0,1996860.64,1636708,1118000,53350,0,52969089.08,null,14862.170429752065,21888.053338842976,134.53560436657708]
["Palm Beach","Seminole Ridge High",2649,120,0,0,50,376677,399278,0,2495788.06,0,44170127.94,3716566,50382482,19019.43450358626,0,0,2817432,0,1859597.27,3609930,489870,59945,0,59219256.269999996,null,16674.264983012457,22355.325130237823,148.31585078566812]
["Polk","Haines City High",0,0,0,0,0,24525,32986,0,178096,495637,3198605,276730,4149068,"N/A",0,0,0,0,0,16849,129388,0,0,4295305,null,"N/A","N/A",130.2160007275814,"19,20",null,"No Student Stations"]
["Polk","Ridge Comm Sr Hi",1788,75,0,0,75,238640,329874,24759,1029432.53,2987700,27955403,2934950,34932244.53,19537.04951342282,0,0,3030116,0,2068016,56973,435562,261312,0,40784223.53,null,15635.012863534675,22809.96841722595,123.63576253357343,"3,18,19"]
[]
[]
[]
[]
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["NEW CONSTRUCTION",null,"CALENDAR YEAR 2005"]
["HIGH SCHOOLS",null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
["DESIGN BUILD"]
[]
[{"$nulls":29},"TOTAL"]
[{"$nulls":22},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":15},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":4},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":4},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Broward","Dave  Thomas Ed",616,25,0,0,23,57820,82128,1330281,90224,60262,10380119,1217484,13078370,21231.12012987013,0,0,0,0,0,0,800000,400000,0,14278370,null,16850.842532467534,23179.172077922078,173.8550798753166,"17,18"]
["Monroe","Coral Shores High",1285,52,null,null,null,201421,202686,1298,1561311,2194139,41313535,662264,45732547,35589.53073929961,0,0,0,0,0,195920,740111,134406,19504,46822488,null,32150.610894941634,36437.733852140074,231.0099760220242,"3,5,8,11,12,17,19"]

{"sheet":"2005 Additions","index":4,"n_rows":160,"n_cols":33,"rows_kept":160,"cut":false,"hidden":false,"merged":[],"flags":["formulas_cached_only"]}
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["ADDITION",null,null,"CALENDAR YEAR 2005"]
["ALL SCHOOLS",null,null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
[null,null,null,"Designed/Build Constracts are not included"]
[]
[{"$nulls":30},"TOTAL"]
[{"$nulls":23},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":16},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":5},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":5},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"TYPE OF","STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","ADDITION","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Alachua","Westwood Middle","Food Srv Bd",0,0,0,0,0,9717,13016,77354.69,175322.55,184445,1595811.6,98210.97,2131144.81,"N/A"," "," ",0," ",0,0,0,0,0,2131144.81,null,"N/A","N/A",163.73269898586355,18,"No Student Stations"]
["Alachua","Bishop Middle","Sci Lab Bldg",88,4,0,4,0,8505,9717,59536.24,94274.98,59000,1080264.28,151777.02,1444852.52,16418.778636363637,null,null,300000,null,0,0,0,0,0,1744852.52,null,12275.730454545455,19827.869545454545,179.566998044664,18]
["Broward","Atlantic Tech Center","Classrooms",600,24,0,0,24,20400,21600,606973,256116,33844,4630628,1706265,7233826,12056.376666666667,0,0,0,null,0,0,19375,41304,0,7294505,null,7717.713333333333,12157.508333333333,337.7085648148148,"17,18,19"]
["Broward","Atlantic West ES","Classrooms",162,9,9,0,0,7650,10640,21395,22160,10324,1657606,164228,1875713,11578.475308641975,0,0,0,null,0,0,0,0,0,1875713,null,10232.135802469136,11578.475308641975,176.2888157894737,18]
["Broward","Challenger ES","Classrooms",216,12,12,0,0,10200,15734,213104,20555,9985,2582533,207405,3033582,14044.361111111111,0,0,0,null,0,0,125000,0,0,3158582,null,11956.171296296296,14623.064814814816,200.74882420236432,"17,18"]
["Broward","Coral Glades Hs","Classrooms",625,36,0,0,36,30600,47202,337689,421959,20413,3797635,650576,5228272,8365.2352,0,0,0,null,0,0,0,0,0,5228272,null,6076.216,8365.2352,110.76378119571204,18]
["Broward","Coral Springs HS","Classrooms",325,13,0,0,13,11050,14867,170000,21150,10139,2201337,291566,2694192,8289.821538461538,0,0,0,null,0,0,12108,0,0,2706300,null,6773.344615384615,8327.076923076924,182.03403511132038,18]
["Broward","Country Isles ES","Classrooms",198,11,11,0,0,9350,14867,162088,23205,8205,1961872,141957,2297327,11602.661616161617,0,0,0,null,0,0,2083,0,0,2299410,null,9908.444444444445,11613.181818181818,154.66536624739356,18]
["Broward","Cypress Bay HS","Classrooms",625,36,0,0,36,30600,47202,537703,23055,39649,5126650,656099,6383156,10213.0496,0,0,0,null,0,0,500,0,0,6383656,null,8202.64,10213.8496,135.24121859243252,"17,19"]
["Broward","Forest Glen MS","Classrooms",528,24,0,24,0,21360,31188,404154,23687,19478,4369405,458392,5275116,9990.75,0,0,0,null,0,0,57004,0,0,5332120,null,8275.388257575758,10098.712121212122,170.96703860459152,"17,18"]
["Broward","Fox Trail ES","Classrooms",360,20,20,0,0,19129,26382,205545,399677,27454,3597093,251184,4480953,12447.091666666667,0,0,0,null,0,0,0,0,0,4480953,null,9991.925,12447.091666666667,169.8488742324312,"17,18"]
["Broward","James Hunt ES","Classrooms",180,10,10,0,0,8500,9000,159129,212892,8177,1916026,168747,2464971,13694.283333333333,0,0,0,null,0,120000,0,0,0,2584971,null,10644.58888888889,14360.95,287.219,"6,17,18,19"]
["Broward","Indian Ridge MS","Classrooms",396,18,0,18,0,15300,21280,232741,21292,14688,3475302,285871,4029894,10176.5,0,0,0,null,0,0,0,0,0,4029894,null,8776.015151515152,10176.5,189.3747180451128,"17,18,19"]
["Broward","Libert ES","Classrooms",440,22,22,0,0,21010,26580,210029,593852,23872,3424201,313428,4565382,10375.868181818181,0,0,0,null,0,0,73086,0,0,4638468,null,7782.275,10541.972727272727,174.5097065462754,"6,17,18"]
["Broward","Manatee Bay ES","Classrooms",320,16,16,0,0,15638,19766,178668,433778,15715,2711803,305922,3645886,11393.39375,0,0,0,null,0,0,0,0,0,3645886,null,8474.384375,11393.39375,184.4523929980775,"6,17,18"]
["Broward","Northeast HS","Classrooms",325,13,0,0,13,11050,14867,169093,21174,10193,2192373,219566,2612399,8038.15076923077,0,0,0,null,0,0,13109,0,0,2625508,null,6745.763076923077,8078.486153846154,176.59971749512343,"17,18"]
["Broward","Oakland Park ES","Classrooms",432,24,24,0,0,20400,31468,365964,21348,27875,4488205,324295,5227687,12101.127314814816,0,0,0,null,0,0,0,0,0,5227687,null,10389.363425925925,12101.127314814816,166.12708147959833,"17,18"]
["Broward","Park Lakes ES","Classrooms",180,10,10,0,0,8890,9600,88036,379707,38614,1262094,133914,1902365,10568.694444444445,0,0,0,null,0,0,0,0,0,1902365,null,7011.633333333333,10568.694444444445,198.16302083333332,"6,17,18"]
["Broward","Park Springs ES","Classrooms",468,26,26,0,0,22100,23400,377815,1117909,36397,4123836,374659,6030616,12885.931623931623,0,0,0,null,0,0,0,0,0,6030616,null,8811.615384615385,12885.931623931623,257.71863247863246,"6,17,18,19"]
["Broward","Quiet Waters ES","Classrooms",252,14,14,0,0,11900,12600,47651,610051,19056,2400066,200186,3277010,13004.007936507936,0,0,0,null,0,0,10458,0,0,3287468,null,9524.07142857143,13045.507936507936,260.91015873015874,"17,18"]
["Broward","Ramblewood MS","Classrooms",286,13,0,13,0,11050,14867,177226,26414,7735,2233483,296113,2740971,9583.814685314685,0,0,0,null,0,0,114297,0,0,2855268,null,7809.381118881119,9983.454545454546,192.05407950494384,"17,18"]
["Broward","Rickards MS","Classrooms",286,13,0,13,0,11050,14867,96178,25199,10436,2096877,249770,2478460,8665.944055944055,0,0,0,null,0,0,0,0,0,2478460,null,7331.737762237763,8665.944055944055,166.70881818793302,18]
["Broward","Sawgrass ES","Classrooms",360,20,20,0,0,19129,26382,188309,377466,15300,3381897,90181,4053153,11258.758333333333,0,0,0,null,0,0,0,0,0,4053153,null,9394.158333333333,11258.758333333333,153.6332726859222,"6,17,18,19"]
["Broward","Seagull School","Classrooms",208,13,0,0,0,11050,14867,100662,20431,8089,1809538,233814,2172534,10444.875,0,0,0,null,0,0,0,0,0,2172534,null,8699.701923076924,10444.875,146.13129750454027,18]
["Broward","Silver Ridge ES","Classrooms",288,16,16,0,0,14960,28638,142568,251756,15300,2250506,198718,2858848,9926.555555555555,0,0,0,null,0,0,123571,0,0,2982419,null,7814.256944444444,10355.621527777777,104.1420141071304,"6,17,18"]
["Broward","Stranahan HS","Classrooms",325,13,0,0,13,11050,14867,112551,20431,13562,1848398,237674,2232616,6869.587692307692,0,0,0,null,0,0,0,0,0,2232616,null,5687.378461538461,6869.587692307692,150.17259702697248,"17,18"]
["Broward","Whiddon Rogers Ct","Classrooms",208,13,0,0,null,11050,14867,224487,20000,10665,3957256,178946,4391354,21112.278846153848,0,0,0,null,0,0,325000,0,0,4716354,null,19025.26923076923,22674.778846153848,317.23642967646464,"17,18"]
["Citrus","Crystal River Midd.","Classrooms",527,23,0,23,0,31379,43845,33724.39,328007.15,0,4941611.28,246646,5549988.82,10531.288083491461,0,0,0,null,0,0,0,0,0,5549988.82,null,9376.871499051234,10531.288083491461,126.58202349184629,"1,11,17"]
["Clay","Ridgeview High","Classrooms",432,16,0,0,16,16042,29917,0,131343.11,0,2338415.07,42029.6,2511787.78,5814.323564814815,0,0,0,null,0,0,0,0,0,2511787.78,null,5412.997847222222,5814.323564814815,83.95854464017113,6]
["Dade","Charles David Wyche Elementary","Classroom",286,13,0,8,0,13633,14437,367256,84911,237251,1763777,79468,2532663,8855.465034965035,0,0,0,null,0,0,108074,0,0,2640737,null,6167.052447552447,9233.346153846154,182.91452517836115,"3,17,19"]
["Dade","Southwest Miami Sr","Classroom",874,35,0,0,35,53703,56871,1427418,416800,1346498,7099958,829006,11119680,12722.745995423342,0,0,0,null,0,0,92220,12324,0,11224224,null,8123.521739130435,12842.361556064074,197.36287387244818,18]
["Dade","Miami Killian Senior","Classroom",875,35,0,0,35,57056,60422,1433957,475350,1307857,7677143,764836,11659143,13324.734857142857,0,0,0,null,0,0,145000,39500,0,11843643,null,8773.877714285714,13535.592,196.0154082949919,18]
["Dade","Shenandoah Elem.","Classroom",437,22,0,22,0,41174,43603,266311,117000,138727,4182340,144969,4849347,11096.903890160183,0,0,0,null,0,0,28000,0,0,4877347,null,9570.572082379862,11160.977116704806,111.85806022521386,17]
["Dade","S/S \"NN-1\"","Classroom",1662,77,0,76,0,110095,145235,2687753,790000,2006557,16686064,2749000,24919374,14993.606498194946,0,0,1888696,null,0,44275,758184,109250,156975,27876754,null,10039.74969915764,16773.016847172083,191.94239680517782,"4,5,17,19"]
["Dade","Cutler Ridge Middle","Classroom",572,26,0,26,0,26586,28155,463975,258000,342800,3226040,161156,4451971,7783.166083916084,0,0,0,null,0,20000,0,0,275000,4746971,null,5639.93006993007,8298.90034965035,168.60134967146155,"3,19"]
["Dade","Cambell Drive Midd","Classroom",286,13,0,13,0,13633,14437,347871,84911,362500,1822438,101578,2719298,9508.034965034965,0,0,0,null,0,20000,0,0,0,2739298,null,6372.160839160839,9577.965034965035,189.7414975410404,"3,18,19"]
["Dade","Bel-Aire Elementary","Classroom",242,11,0,11,0,11834,12538,290121,76847,298000,1353114,161156,2179238,9005.11570247934,0,0,0,null,0,20000,0,0,0,2199238,null,5591.380165289256,9087.760330578512,175.40580634869994,3]
["Dade","Bowman Foster Ashe Elementary","Classroom",286,13,0,13,0,13633,14437,277865,114735,206580,1860008,78378,2537566,8872.608391608392,0,0,0,null,0,20000,0,0,0,2557566,null,6503.524475524476,8942.538461538461,177.15356375978388,"3,14,18"]
["Dade","North Miami Bch Sr","Classroom",550,22,3,4,22,28566,30251,689581,117400,881737,3890801,221155,5800674,10546.68,0,0,0,null,0,0,0,0,0,5800674,null,7074.183636363637,10546.68,191.75147928994082,"2,19"]
["Dade","Norland Middle","Classroom",242,11,0,11,0,11839,12538,344868,76847,307089,1719449,84695,2532948,10466.727272727272,0,0,0,null,0,0,0,0,0,2532948,null,7105.161157024793,10466.727272727272,202.02169405008775,"2,19"]
["Dade","Hialeah-Miami Lk Sr","Classroom",275,11,0,0,11,11839,12538,333017,76847,192140,1702078,94927,2399009,8723.66909090909,0,0,0,null,0,0,31523,0,0,2430532,null,6189.374545454545,8838.298181818182,193.85324613175945,"3,18"]
["Dade","Kendale Elementary","Classroom",242,11,0,11,0,11839,12538,364192,81347,492052,1689350,72012,2698953,11152.698347107438,0,0,0,null,0,20000,0,0,0,2718953,null,6980.785123966943,11235.342975206611,216.85699473600255,"17,19"]
["Dade","David Fairchild Elm","Classroom",242,11,0,11,0,11839,12538,359735,149347,296522,1984418,69012,2859034,11814.190082644629,0,0,0,null,0,0,0,0,0,2859034,null,8200.07438016529,11814.190082644629,228.0295102887223,19]
["Dade","Coral Reef Elem.","Classroom",440,20,0,20,0,25745,27264,288345,95147,406538,4822877,69012,5681919,12913.452272727272,0,0,0,null,0,178335,58775,0,0,5919029,null,10961.084090909091,13452.338636363636,217.10053550469485,19]
["Dade","Kenwood k-8 Center","Classroom",286,13,0,13,0,13633,14437,554444,83347,694104,2458564,79595,3870054,13531.657342657343,0,0,0,null,0,40000,0,0,0,3910054,null,8596.377622377622,13671.517482517482,270.83563067119206,19]
["Dade","H. Flagler Elem.","Classroom",524,27,10,17,0,35280,37362,24531,183000,477000,4418410,274050,5376991,10261.43320610687,0,0,0,null,0,0,105000,0,90000,5571991,null,8432.080152671755,10633.570610687022,149.1352443659333,19]
["Dade","Redland Elementary","Classroom",220,10,0,10,0,10566,11189,308387,84911,70500,1690281,90019,2244098,10200.445454545454,0,0,0,null,0,20000,7000,0,0,2271098,null,7683.095454545454,10323.172727272728,202.97595853069978,19]
["Dade","Cutler Ridge Elem.","Classroom",242,11,0,11,0,11839,12538,556459,81347,218203,1834215,81584,2771808,11453.752066115703,0,0,0,null,0,20000,0,0,0,2791808,null,7579.400826446281,11536.396694214876,222.6677301004945,18]
["Dade","Coral Reef Senior","Classroom",600,24,0,0,24,2933,31061,273676,183000,283055,6064600,440000,7244331,12073.885,0,0,0,null,0,0,7000,0,0,7251331,null,10107.666666666666,12085.551666666666,233.45452496700042,18]
["Dade","Pinecrest Elem.","Classroom",480,24,0,24,0,41676,44135,195286,240150,154011,5515000,301655,6406102,13346.045833333334,0,0,0,null,0,0,168728,0,0,6574830,null,11489.583333333334,13697.5625,148.97088478531776,18]
["Dade","John I Smith Elem.","Classroom",440,20,0,20,0,25745,27264,204510,193500,239432,4909507,137025,5683974,12918.122727272726,0,0,0,null,0,0,0,0,200000,5883974,null,11157.970454545455,13372.668181818182,215.81477406103286,19]
["Dade","Rockway Middle","Classroom",676,32,0,32,0,50094,53050,323461,254000,250000,8070000,245000,9142461,13524.350591715976,0,0,0,null,0,50000,0,0,0,9192461,null,11937.869822485207,13598.315088757396,173.27918944392084,19]
["Dade","Ferguson Senior","Classroom",850,34,0,0,34,45478,48161,990243,250000,394459,8734340,950000,11319042,13316.52,0,0,0,null,0,0,103048,0,0,11422090,null,10275.69411764706,13437.75294117647,237.16471834056603,"3,19"]
["Dade","Kensington Pk Elm","Classroom",524,27,0,17,0,39702,44409,222736,183000,653577,4521592,274050,5854955,11173.57824427481,0,0,0,null,0,18000,272000,0,0,6144955,null,8628.992366412214,11727.013358778626,138.3718390416357,"6,17"]
["Dade","Miami Palmetto Sr.","Classroom",600,24,0,0,24,34836,36891,704661,75000,212183,7943705,561317,9496866,15828.11,0,0,0,null,0,20000,250000,0,0,9766866,null,13239.508333333333,16278.11,264.749288444336,18]
["Dade","Ernest Graham Elm","Classroom",488,22,0,22,0,38955,41253,312946,235000,304179,5789139,137025,6778289,13889.936475409837,0,0,0,null,0,46000,172500,0,0,6996789,null,11862.98975409836,14337.682377049181,169.6067922332921,18]
["Dade","Centennial Middle","Classroom",770,35,0,35,0,48159,51000,1147805,197700,731950,8169582,950000,11197037,14541.606493506493,0,0,0,null,0,126165,151986,0,0,11475188,null,10609.846753246753,14902.841558441558,225.00368627450982,19]
["Dade","Kinlock Park Elem.","Classroom",366,17,0,0,17,24451,25895,699616,198977,731950,3512955,257082,5400580,14755.68306010929,0,0,87319," ",870365,370550,25000,20000,0,6773814,null,9598.237704918032,18507.688524590165,261.5877196369956,19]
["Dade","Lawton Chiles Midd","Classroom",286,13,0,13,0,13633,14437,156953,84911,515880,1871434,99568,2728746,9541.06993006993,0,0,0,null,0,10000,96000,0,0,2834746,null,6543.475524475524,9911.699300699302,196.35284338851562,18]
["Dade","Miami Jackson Sr.","Classroom",2563,93,3,4,93,186956,197986,1126985,2555883,0,44613941,5125116,53421925,20843.513460788137,0,0,3638025,null,0,765900,0,829725,2730757,61386332,null,17406.92196644557,23950.968396410455,310.05390280120815,"18,19"]
["Dade","S/S\"CCC-1\" South Dade Sr. Replace","Classroom",3353,124,3,4,124,321565,340537,5369569,2600198,1684000,58782160,7624648,76060575,22684.334923948703,0,0,4235000,null,0,640000,802027,0,3068473,84806075,null,17531.213838353713,25292.596182523113,249.03630148853134,18]
["Duval","Merrill Road Elem.","Classroom",396,24,24,0,0,38797,47532,225956,455689,505862,6208865,769427,8165799,20620.704545454544,0,0,0,null,0,0,18700,24000,6501,8215000,null,15678.95202020202,20744.949494949495,172.83093494908692,19]
["Duval","Greenland Pines El","Classrooms",360,20,20,0," ",24568,30645,247449,281308,241063,3982312,389500,5141632,14282.31111111111,0,0,0,null,0,0,45000,351000,31500,5569132,null,11061.977777777778,15469.81111111111,181.7305270027737,"6,13"]
["Duval","Terry Parker High","SED",110,8,0,0,8,13806,20371,0,282267,151310,3189826.26,175000,3798403.26,34530.938727272725,0,0,0,null,0,45000,0,0,0,3843403.26,null,28998.420545454544,34940.02963636364,188.67032840803103,19]
["Duval","Paxon Sch/Advanc.","Science Wing",150,6,0,0,6,12143,15980,0,290503,42320,2480657.3,67953.42,2881433.7199999997,19209.558133333332,0,0,0,null,0,0,59545.56,0,0,2940979.28,null,16537.715333333334,19606.52853333333,184.0412565707134,"13,18"]
["Escambia","Pine Forest High","Gym/PE Wgt.",0,0,0,0,0,5939,7971,0,52508,20000,552787,121303,746598,"N/A",0,0,0,null,0,0,30000,0,0,776598,null,"N/A","N/A",97.42792623259315,19,"No Student Stations"]
["Gilchrist","Bell High School","Dinning Area",0,0,0,0,0,0,0,0,66659,0,717896,111033,895588,"N/A",0,0,0,null,0,0,0,0,0,895588,null,"N/A","N/A","N/A",15,"No Student Stations"]
["Gulf","Wewahitchka Jr/Sr.","Athletic Field",0,0,0,0,0,5352,5352,0,0,0,135468.16,23483,158951.16,"N/A",0,0,0," ",0,0,0,0,0,158951.16,null,"N/A","N/A",29.69939461883408,17,"No Student Stations"]
["Hillsborough","Adams Middle","Classrooms",264,12,0,12,0,11163,15028,0,118347,79100,1199400,102798,1499645,5680.473484848485,0,0,39500,null,0,0,32400,0,0,1571545,null,4543.181818181818,5952.82196969697,104.57446100612191,6]
["Hillsborough","Carrollwood Elem","Classrooms",180,10,10,0,0,9390,12641,0,75350,15520,1194781,105163,1390814,7726.7444444444445,0,0,64517,null,0,0,15519,0,0,1470850,null,6637.672222222222,8171.388888888889,116.35550984890436,6]
["Hillsborough","Jefferson High","Athletic Field",0,0,0,0,0,2788,3182,94,50000,30150,546630,50000,676874,"N/A",0,0,0,null,0,0,0,0,0,676874,null,"N/A","N/A",212.71967316153362,19,"No Student Stations"]
["Hillsborough","Jefferson High","Classrooms",500,20,0,0,20,18155,24440,94,160890,294988,1849126,176171,2481269,4962.538,0,0,0,null,0,3603,0,0,0,2484872,null,3698.252,4969.744,101.67234042553191,6]
["Hillsborough","Kenly Elementary","Classrooms",180,10,10,0,0,9688,13042,38,91550,63400,1087484,105163,1347635,7486.861111111111,0,0,80000,null,0,217,10820,0,0,1438672,null,6041.577777777778,7992.622222222222,110.31068854470173,6]
["Hillsborough","Potter Elementary","Classrooms",108,6,6,0,0,5680,7646,0,83554,104465,595141,26566,809726,7497.462962962963,0,0,0,null,0,35000,10400,0,0,855126,null,5510.564814814815,7917.833333333333,111.83965472142296,20]
["Hillsborough","Westchase Elem.","Classrooms",252,14,14,0,0,16974,22850,0,172764,87203,1952449,147288,2359704,9363.904761904761,0,0,0,null,0,0,144113,0,0,2503817,null,7747.813492063492,9935.781746031746,109.5762363238512,7]
["Indian River","Liberty Magnet Sch","Classroom",22,1,1,0,0,864,864,0,874,20686,79149,1178,101887,4631.227272727273,0,0,0," ",0,0,0,0,0,101887,null,3597.681818181818,4631.227272727273,117.92476851851852,"6,7,17"]
["Indian River","Higlands Elementary","Classroom",22,1,1,0,0,864,864,0,694,17415,79127,815,98051,4456.863636363636,0,0,0," ",0,0,0,0,0,98051,null,3596.681818181818,4456.863636363636,113.48495370370371,"6,17"]
["Indian River","Citrus Elementary","Classroom",22,1,1,0,0,864,864,0,651,20360,78237,815,100063,4548.318181818182,0,0,0," ",0,0,0,0,0,100063,null,3556.2272727272725,4548.318181818182,115.8136574074074,"6,7,17"]
["Jackson","Colson Elementary","Cafeteria",0,0,0,0,0,7006,9346,0,106158.29,0,1368646.92,24003.56,1498808.77,"N/A",0,0,0,null,0,0,0,0,0,1498808.77,null,"N/A","N/A",160.36901027177402,"16,19","No Student Stations"]
["Lake","Treadway Elem.","Classroom",320,16,0,0,0,35008,41896,650,265000,317218,4393486,443550,5419904,16937.2,0,0,0,null,0,27153,80937,0,0,5527994,null,13729.64375,17274.98125,131.94562726751957,3]
["Lake","Pine Ridge Elem.","Classrooms",240,12,0,0,0,16673,22627,0,146320,44076,2978906,0,3169302,13205.425,0,0,0,null,0,0,12358,0,0,3181660,null,12412.108333333334,13256.916666666666,140.613426437442,"4,6,13,19"]
["Lake","Lost Lake Elem.","Classrooms",240,12,0,0,0,16566,22510,0,146320,39340,3333879,123236,3642775,15178.229166666666,0,0,0,null,0,0,12358,0,33138,3688271,null,13891.1625,15367.795833333334,163.850333185251,"6,12,19"]
["Lee","The Sanibel School","Media/Admn /Dinning/Cape /Music/Art",439,25,10,11,null,35931,68375,68610,377945,1618830,6031950,671129,8768464,19973.722095671983,0,0,0,null,0,100000,50000,0,0,8918464,null,13740.205011389522,20315.407744874716,130.4345740402194,"11,12,13,17"]
["Leon","Amos P. Godby Hi","ROTC/IMTS",97,3,0,0,3,6714,8142,0,103623,0,1029320.95,90000,1222943.95,12607.669587628865,0,0,0,null,0,13854,0,0,0,1236797.95,null,10611.55618556701,12750.494329896906,151.90345738147874,16]
["Leon","Lawton Chiles Hi","Classrooms",332,14,0,0,14,33965,48244,0,284446.71,0,4182251.73,248089.05,4714787.49,14201.167138554218,0,0,0,null,0,0,0,0,0,4714787.49,null,12597.14376506024,14201.167138554218,97.72795560069646,"6,7,17,18"]
["Leon","Ft. Braden Sch k-8","Gym/Clsrm",192,8,2,6,0,26029,36420,13351.5,286527.21,0,3945819.33,23058.91,4268756.95,22233.109114583334,0,0,56358.27,null,0,0,0,0,88414.98,4413530.2,null,20551.14234375,22987.136458333334,121.18424492037343,"1,2,4,5,17,19"]
["Levy","Williston Elementary","Classrooms",158,6,6,0,0,9871,8598,1006.84,51184.79,92338.39,831045.59,0,975575.61,6174.5291772151895,0,0,4409,null,0,0,0,0,0,979984.61,null,5259.782215189874,6202.434240506329,113.97820539660385,"1,6,11"]
["Marion","Forest High","Clsrm add't",424,17,0,0,17,22601,22601,0,174398,134428,2835417,70094,3214337,7580.983490566037,0,0,0,null,0,0,0,0,0,3214337,null,6687.304245283019,7580.983490566037,142.22100792000353,"12,17"]
["Okaloosa","Lewis Middle","ESE Clsrm",109,5,0,5,0,9405,11232,0,72609,90971,1997675,23246,2184501,20041.29357798165,0,0,0,null,0,0,0,0,0,2184501,null,18327.29357798165,20041.29357798165,194.48904914529913,18]
["Okaloosa","Silver Sand Elem.","ESE Clsrm",60,6,6,0,0,6693,7420,0,70678,99552,1492906,33629,1696765,28279.416666666668,0,0,0,null,0,9465,0,0,0,1706230,null,24881.766666666666,28437.166666666668,229.9501347708895,18]
["Okaloosa","Baker School","ESE Clsrm",100,4,0,0,4,3570,4410,0,54155,126734,1497410,22174,1700473,17004.73,0,0,0,null,0,0,0,0,0,1700473,null,14974.1,17004.73,385.59478458049887,18]
["Okaloosa","Destin Elementary","Classrooms",200,10,10,0,0,9491,11592,0,81643,67152,1870604,27360,2046759,10233.795,0,0,12200,null,0,0,0,0,0,2058959,null,9353.02,10294.795,177.618961352657,6]
["Osceola","St. Cloud Middle","Classrooms",572,27,0,26,0,30051,30988,0,271599.5,194434,3755525.27,384813,4606371.77,8053.097499999999,0,0,0,null,0,0,5000,0,1500,4612871.77,null,6565.603618881119,8064.461136363636,148.85993836323738,6]
["Polk","Haines City High","Adm & Media",0,0,0,0,0,24525,32986,0,178096,495637,3198605,276730,4149068,"N/A",0,0,0,null,0,16849,129388,0,0,4295305,null,"N/A","N/A",130.2160007275814,"19,20","No Student Stations"]
["Polk","Dundee Elementary","Classrooms",198,11,11,0,0,11846,16225,0,86200,98400,1485307,42358,1712265,8647.80303030303,0,0,121610,null,0,0,32000,0,0,1865875,null,7501.550505050505,9423.611111111111,115,"3,5"]
["Polk","Kathleen Middle","Classroom",183,10,0,10,0,11396,15096,0,87360,154680,1488094,89250,1819384,9941.989071038251,0,0,0,null,0,0,0,0,0,1819384,null,8131.661202185793,9941.989071038251,120.52093269740328,"12,17"]
["Polk","Sikes Elem.","Classrooms",148,10,10,0,0,12319,16816,0,154752,226019,1386040,55894,1822705,12315.574324324325,0,0,104325,null,0,0,0,0,0,1927030,null,9365.135135135135,13020.472972972973,114.59502854424358,"5,19"]
["St. Johns","Fruit Cove Middle","Classroom",245,14,0,14,0,15724,19812,2091.06,62302.5,0,2543291.53,27433.1,2635118.19,10755.58444897959,0,0,0,null,0,0,0,0,0,2635118.19,null,10380.78175510204,10755.58444897959,133.00616747425804,"3,12,17,19"]
["St. Lucie","Lake Park Elem.","Classrooms",260,12,1,11,null,11232,11232,150,26976,67920,1432788,135142,1662976,6396.0615384615385,0,0,0,null,0,79968,0,0,0,1742944,null,5510.723076923077,6703.630769230769,155.17663817663816,"6,19"]
["St. Lucie","Northport Middle","Classrooms",66,3,0,3,0,2391,2391,2550,5838,30464,545696,57593,642141,9729.40909090909,0,0,0,null,0,8900,0,0,0,651041,null,8268.121212121212,9864.257575757576,272.28816394813884,"6,19"]
["St. Lucie","Windmill Point Elem","Classrooms",370,17,1,16,0,16033,16033,150,22945,96436,2004603,187891,2312025,6248.716216216216,0,0,123271,null,0,0,0,0,0,2435296,null,5417.845945945946,6581.881081081081,151.89272126239632,"6,19"]
["Sarasota","North Port High Sch","Classroom",760,38,0,0,36,22820,22820,8000,425000,12000,6450000,2050000,8945000,11769.736842105263,0,0,10000," ",0,10000,0,0,0,8965000,null,8486.842105263158,11796.052631578947,392.85714285714283,"17,19"]
["Seminole","Wilson Elem.","Classroom",252,14,null,null,null,21197,26561,42951,129550,426683,2897640,215000,3711824,14729.460317460318,0,0,0," ",20000,160693,222446,0,3600,4118563,null,11498.57142857143,16343.503968253968,155.0605398893114,"13,19"]
["Seminole","Bentley Elem.","Classroom",300,14,0,0,0,19262,26577,50240,129550,366100,2841472.65,210000,3597362.65,11991.208833333332,0,0,0,null,1440000,64700,365210,0,350,5467622.65,null,9471.575499999999,18225.408833333335,205.72760845844152,"13,19"]
["Seminole","Red Bug Elem.","Classroom",336,14,0,0,0,21730,31697,48255.56,145000,229963.93,2901003.07,282265.45,3606488.01,10733.595267857143,0,0,0,null,0,47000,38000,null,5243,3696731.01,null,8633.937708333333,11002.175625,116.62715745969649,"12,13,17,19"]
["Sumter","Lake Panasoffkee El","Classrooms",154,8,0,0,0,9094,13107,1953.93,54832,52771,1138491.85,15102.32,1263151.1,8202.27987012987,0,0,0,null,0,0,300,0,0,1263451.1,null,7392.804220779221,8204.227922077922,96.3951400015259,"3,17"]
["Sumter","Bushnell Elem.","Classrooms",848,40,0,0,0,44398,60418,487.64,245706.65,579588.87,5149601.35,1156,5976540.51,7047.807205188679,0,0,0,null,0,3401.61,0,0,0,5979942.12,null,6072.643101415094,7051.8185377358495,98.97616802939521,"3,17,18"]
["Taylor","Steinhatchee Sch","Gym/Clsrrm",114,4,3,1,0,18278,18278,0,231579.35,0,3007920,0,3239499.35,28416.66096491228,0,0,0,null,0,0,0,0,0,3239499.35,null,26385.263157894737,28416.66096491228,177.23489167304956,"5,6,11,18"]
["Volusia","Spirit Elementary","Classrooms",182,9,9,0,0,9167,12024,0,138399,0,1986490,31500,2156389,11848.291208791208,0,0,0,null,0,0,0,0,0,2156389,null,10914.78021978022,11848.291208791208,179.34040252827677,19]
["Wakulla","Medart Elem.","Classrooms",54,3,3,0,0,3765,5687,0,41663,0,796400,13968,852031,15778.351851851852,0,0,0,null,0,0,0,0,0,852031,null,14748.148148148148,15778.351851851852,149.8208194126956,"5,6,7,13"]
[]
[]
["FLORIDA DEPARTMENT OF EDUCATION"]
["PUBLIC SCHOOL DISTRICTS"]
["REPORT OF COST OF CONSTRUCTION"]
["REPORT OF COST OF CONSTRUCTION"]
[]
["ADDITION",null,null,"CALENDAR YEAR 2005"]
["ALL SCHOOLS",null,null,"Construction Contract Awarded Between 1/01/05 and 12/31/05"]
["DESIGN BUILD"]
[{"$nulls":30},"TOTAL"]
[{"$nulls":23},"CORRECT",{"$nulls":5},"TOTAL","PLANT"]
[{"$nulls":16},"TOTAL",{"$nulls":6},"SITE",{"$nulls":4},"CONST.","PLANT","COST"]
[{"$nulls":5},"NO. OF","NO. OF","NO. OF",null,null,"LEGAL","ARCHITECT",{"$nulls":4},"COST",{"$nulls":6},"DRAINAGE","PUBLIC",null,null,null,"CONTRACT","COST","PER"]
[{"$nulls":5},"CLSRMS","CLSRMS","CLSRMS","NET","GROSS","AND","AND",null,null,"FURNITURE","TOTAL","PER",null,"IMPACT/",null,null,null,"PUBLIC","AND/OR","ROAD","ENVIRON.","TOTAL",null,"COST PER","PER","GROSS"]
["DISTRICT",null,"TYPE OF","STUDENT","TEACHER","GRADE","GRADE","GRADE","SQUARE","SQUARE","ADM .","ENGINEER","SITE","CONTRACT","AND","FACILITY","STUDENT","SITE","CONNECT","HURRICANE","OTHER","SITE","UTILITIES","RETENTION","ACCESS","PROBLEM","PLANT","AWARD","STUDENT","STUDENT","SQUARE","REVENUE"]
["NAME","FACILITY NAME","ADDITION","STATIONS","STATIONS","K-5","6-8","9-12","FEET","FEET"," COST","FEES","IMPROV.","COST","EQUIPMENT","COST","STATION","DEVELOP.","FEES","SHELTER","EXPLAIN","COST","COST","AREA COST","COST","COST","COST","DATE","STATION","STATION","FOOT","CODES"]
["Bradford","Bradford Middle","Band/Music",35,1,null,1,null,3939,3939,0,47025.78,0,515421.65,18747,581194.43,16605.555142857145,0,0,0,null,0,0,0,0,0,581194.43,null,14726.332857142857,16605.555142857145,147.54872556486418,"3,18"]
["Broward","Westchester ES","Classrooms",288,16,16,0,0,13600,14400,434837,649650,24448,2533210,255286,3897431,13532.746527777777,0,0,0,null,0,0,0,0,0,3897431,null,8795.868055555555,13532.746527777777,270.65493055555555,"17,18,19"]
["Charlotte","Port Charlotte High","Classrooms",790,31,null,null,"31",46802,52867,0,392557,561254,5065510,259421,6278742,7947.774683544304,0,0,0,null,0,0,0,0,16500,6295242,null,6412.037974683544,7968.660759493671,119.07696672782643,"3,11,17"]
["Columbia","Fort White Elem","Classrooms",120,6,6,0,0,6640,8977,0,72574,6250,1023050,25586,1127460,9395.5,0,0,0,0,12900,5000,0,0,0,1145360,null,8525.416666666666,9544.666666666666,127.58828116297204,17]
["Escambia","Oakcrest Elem.","Media Center",0,0,0,0,0,6679,8482,0,51640,10000,810435,155000,1027075,"N/A",0,0,0,null,0,0,0,0,0,1027075,null,"N/A","N/A",121.08877623202075,19,"No Student Stations"]
["Hernando","Central High","Classroom",168,6,0,0,"6",8078,9285,0,80000,0,888125,34157,1002282,5965.964285714285,0,0,0,null,0,0,0,0,0,1002282,null,5286.458333333333,5965.964285714285,107.94636510500808,"6,19"]
["Hernando","Powell Middle","Clsrm/Cafet.",220,10,0,10,0,17452,22450,0,220000,0,2727000,58000,3005000,13659.09090909091,0,0,0,null,0,0,0,0,0,3005000,null,12395.454545454546,13659.09090909091,133.85300668151447,6]
["Hernando","Chocachatti Elem.","Classroom",128,6,6,0,0,8008,12132,0,105000,0,1229798,37000,1371798,10717.171875,0,0,0,null,0,0,0,0,0,1371798,null,9607.796875,10717.171875,113.0727002967359,"6,19"]
["Indian River","Vero Bch High","Auditorium",55,3,0,0,"3",27540,27540,0,569936,0,7995651,384124,8949711,162722.0181818182,0,0,0,null,0,0,0,0,0,8949711,null,145375.47272727272,162722.0181818182,324.9713507625272,"3,11,17"]
["Lake","Umatilla High","Classroom",860,34,0,0,0,128369,155070,0,907499,78550,16792380,660318,18438747,21440.403488372092,0,0,0,null,0,0,1500,0,25697,18465944,null,19526.023255813954,21472.027906976746,119.08134390920229,19]
["Lake","South Lake High","Food Service",0,0,0,0,0,24679,28380,0,106366,29921,5353440,376116,5865843,"N/A",0,0,0,null,0,0,33116,0,0,5898959,null,"N/A","N/A",207.8562015503876,19,"No Student Stations"]
["Nassau","Byrcoville Elem","Classrooms",116,6,6,null,null,5783,11788,0,82474.49,200000,855782.75,221468.59,1359725.83,11721.774396551726,0,0,0,null,0,0,0,0,0,1359725.83,null,7377.4375,11721.774396551726,115.34830590430947,"3,11,17"]
["Nassau","Hilliard Middle/Sr","Classrooms",225,10,null,null,9,22361,28342,0,126707.7,0,1693774.22,289844.65,2110326.57,9379.2292,0,0,0,null,0,0,0,0,0,2110326.57,null,7527.885422222222,9379.2292,74.45933843765435,"3,17"]
["Nassau","West Nassau Co Hi","Classrooms",163,9,null,null,9,20895,26176,0,152219.27,0,2021461,395504.76,2569185.0300000003,15761.871349693252,0,0,0,null,0,null,0,0,0,2569185.0300000003,null,12401.601226993866,15761.871349693252,98.15040609718828,"3,17"]
["Pinellas","Starkey Elementary","Kindergarten, Food Serv. Muit-purp., Dinning",754,38,null,null,null,72375,97431,0,444969,0,5377000,914756,6736725,8934.648541114058,0,0,0,null,0,0,0,0,0,6736725,null,7131.29973474801,8934.648541114058,69.14354774147859,"1,17"]
["Union","Union Senior High","Equip Storage",0,0,0,0,0,4687,5360,0,7460.16,9800,110416,22282.48,149958.64,"N/A",0,0,0,null,0,0,0,0,0,149958.64,null,"N/A","N/A",27.977358208955227,13,"No Student Stations"]
["Union","Union Senior High","PE Storage",0,0,0,0,0,520,600,0,1588.64,0,17344,0,18932.64,"N/A",0,0,0,null,0,0,0,0,0,18932.64,null,"N/A","N/A",31.554399999999998,13,"No Student Stations"]
["Walton","Emerald Coast Midd","Classrooms",328,16,0,16,0,26747,31249,0,333546.83,0,3868463,124500,4326509.83,13190.57875,0,0,0,null,0,0,15303,0,18820,4360632.83,null,11794.094512195123,13294.612286585367,139.5447159909117,"3,13,17"]

{"sheet":"Source of Funds","index":5,"n_rows":26,"n_cols":3,"rows_kept":26,"cut":false,"hidden":false,"merged":[[0,0,0,2],[2,0,2,2]],"flags":["formulas_cached_only"]}
["FLORIDA DEPARTMENT OF EDUCATION"]
[]
["Source of Funds for Capital Outlay Projects"]
[]
["Fund",null,"Legal"]
["Code","Fund Title","Reference"]
[1,"PECO Sum of the Digits Maintenance","1013.64(1), F.S."]
[2,"PECO Special Facility Construction Account","1013.64(2), F.S."]
[3,"PECO New Construction Unit Allocation","1013.64(3), F.S."]
[4,"Effort Index Grant (Lottery)","1013.73, F.S."]
[5,"Classrooms First (Lottery)","1013.68, F.S."]
[6,"Classrooms For Kids","1013.735, F.S."]
[7,"District Effort Recognition","1013.736, F.S."]
[8,"Cooperative Use Facilities","1013.52, F.S."]
[9,"Cooperative Career and Tech. Ed. Facilities","1013.75, F.S."]
[10,"Specific Line Item Appropriation"," "]
[11,"CO & DS (Motor Vehicle License Revenue) Flow Thru"]
[12,"SBE Bond (COBI)"]
[13,"Other State Funds (Specify)______________________"]
[14,"Loan 1011.14, F.S.","1011.14, F.S."]
[15,"Loan 1011.15, F.S.","1011.15, F.S."]
[16,"Local Bond Proceeds"," "]
[17,"Two-Mill Revenue","1011.71(2), F.S."]
[18,"Lease Purchase (COPS)","1013.15(4)(a), F.S."]
[19,"Other Local Funds (Specify)______________________"]
[20,"Federal Funds (Specifiy)_________________________"]